## Annual Review Template

Title: Ethiopia Investment Advisory Facility Phase II (EIAF II)
Programme Value £ (full life): £66million		Review date: February 2026
Programme Code: 300588	AMP start date: November 2018	AMP end date: December 2028

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024/2025	2026
Overall Output Score	B	B	A	A	A	A	A
Overall programme risk rating	Moderate	Moderate	Moderate	Moderate	Moderate	Major	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/60056334.odt / https://iati.fcdo.gov.uk/iati_documents/D0005279.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/S30058827.xlsx

Abbreviations
AABE	Accounting and Auditing Board of Ethiopia
AfCFTA	African Continental Free Trade Area
AFSIC Africa Financial Services Investment Conference
AMP	Aid Management Platform
AR	Annual Review
Art Article
ARTTREES TREES
BC	Berbera Corridor
BIFA British International Freight Association
BOFED Bureaus of Finance & Economic Development
B2B	Business-to-Business
CAPE Climate Action Platform for Africa
CISI Chartered Institute for Securities and Investment
CEO Chief Executive Officer
CMA Capital Market Authority
CMP Centrally Managed Programme
COSO Committee of Sponsoring Organizations
Covid 19 Coronavirus disease of 2019
CRGE Climate Resilient Green Economy
CSD Central Securities Depository
CSO Civil Society Organizations
DD Development Director
DDA Due Diligence Assessment
DFID Department for International Development
DPM Deputy Programme Manager
DPW DP World
DRM Disaster Risk Management
ECF	Extended Credit Facility
ECMA	Ethiopian Capital Market Authority
ECMAT Ethiopia Capital Market
EDRC	Ethio-Djibouti Railway Corporation
EIAF	Ethiopia Investment Advisory Facility
EFFSAA Ethiopian Freight Forwarders and Shipping Agents Association
EIH	Ethiopian Investment Holding
ELSA Ethio Logistics Sectorial Association
EMA/LTO	Ethiopian Maritime Authority / Logistics Transformation Office
EMA	Ethiopian Maritime Authority
ESLSE	Ethiopian Shipping and Logistics Services Enterprise
ER reform Exchange rate reform
ESX	Ethiopian Securities Exchange
ETB Ethiopian Birr
FDI	Foreign Direct Investment
GDD	Global Development Delivery Framework
GEDSI	Gender Equality, Disability and Social Inclusion
GESI	Gender Equality and Social Inclusion
FCDO	Foreign Commonwealth and Development Office
FIATA International Federation of Freight Forwarders Associations
FSDA	Financial Sector Deepening Africa
FSDE	Financial Sector Deepening Ethiopia
FY Financial Year
FX Foreign Exchange
GCF Green Climate Fund
GCIP Green Cities and Infrastructure Programme
GDDF Global Development Delivery Framework
GGGI Global Green Growth Institute
GoE	Government of Ethiopia
GRNI Good Received Not Issued
G20 Group of Twenty
HGER Homegrown Economic Reform
HOAI Horn of Africa Initiative
HR Human Resource
IBEX Integrated Budget and Expenditure
IFMIS	Integrated Financial Management Information System
IFRS International Financial Reporting Standards
IMF	International Monetary Fund
IPO Initial Public Offering
KPI	Key Performance Indicator
Logframe	Logical Framework (to monitor results)
MDTF	Multi-Donor Trust Fund
M&E Monitoring and Evaluation
MEL	Monitoring, Evaluation, and Learning
MoF	Ministry of Finance
MOTL   Ministry of Transport and Logistics
MOTRI Ministry of Trade and Regional Co-operation
MoU Memorandum of Understanding
MOWE	Ministry of Water and Energy
MTO	Multimodal Transport Operator
NBE	National Bank of Ethiopia
NTB Non-Tariff Barrier(s)
PDEL Programme Delivery Excellence Lead
PEA Political Economy Analysis
PIAM Public Investment and Asset Management
PIM	Public Investment Management
PMO	Prime Minster’s Office
PO	Programme Officer
PPP	Public-Private Partnership
PRO	Programme Responsible Owner
REDD	Reducing emissions from deforestation & forest degradation in developing countries.
SAP	Simplified Approval Process
SL	Somaliland
SME Small and Medium Enterprise
SOE Stated Owned Enterprises
SRO	Senior Responsible Owner
STP Subsidiary Transformation Plan
TA	Technical Assistance
TMA Trademark Africa
ToC Theory of Change
TREES a forest carbon credit standard (a name itself)
TSA Treasury Single Account
UK	United Kingdom
USD United States Dollar
VFM	Value for Money
WB	World Bank
WB DPO World Bank Development Policy Operation
WBMDTF	The World Bank Multi-donor Trust Fund
WTO World Trade Organisation

A. SUMMARY AND OVERVIEW

Description of programme

The Ethiopia Investment Advisory Facility II (EIAF II) is the second phase of the Ethiopia Investment Advisory Facility (EIAF) programme that was designed to help the Government of Ethiopia (GoE) make better decisions about public investment, grow Ethiopian exports and increase labour-intensive light manufacturing, thereby supporting Ethiopia’s structural transformation. These were key elements of Ethiopia’s strategy to address the demands of a rapidly increasing labour force and the need for new sources of sustainable economic growth.

The programme originally consisted of a £60m technical assistance contract and £6m for monitoring and evaluation and associated support through multilaterals. Global reductions in UK ODA then resulted in significant changes to this programme, including the cancellation of the main contract in 2022. For the next two years the programme delivered against a narrower plan, focused on a sub-set of Ethiopia’s priority macro-economic reforms, as well as capital market reforms and trade facilitation.
As detailed in last year’s Annual Review, in June 2024 the EIAF II Business Case was amended to reflect further, significant changes to the programme’s operating context including a prioritisation of EIAF II’s objectives through the British Embassy Addis Ababa’s Country Business Plan. This clarified the focus areas for the remainder of the EIAF II programme to December 2028:
- Public Investment and Asset Management aligned to the main facility originally envisaged in the business case (including State Owned Enterprise reform and enhancement, Ethiopia Investment Holdings, Public Asset Management, and Public Investment management including Public Private Partnerships);
- Financial Sector development (e.g. capital market development, private climate finance, financial sector reform);
- Macroeconomic support (World Bank Multi-Donor Trust Fund and other bespoke advisory support on key economic reform priorities); and
- Trade facilitation (including logistics, trade corridors, and support for WTO accession).
- Climate Finance (improving Ethiopia’s access to public climate finance)
Together, these components seek to improve the investment and export landscape in Ethiopia to one that is more open and private-sector oriented, while transforming the role of the state in the economy. This aligns closely to Ethiopia’s Homegrown Economic Reform 2.0 agenda. And it is the only way Ethiopia will sustainably move beyond its cycle of macroeconomic imbalances and drive lasting, inclusive growth.
Recent Context
Macro reform progress
Last year’s Annual Review highlighted the GoE’s accelerating economic reform programme – including exchange rate liberalisation, monetary policy modernisation and the launch of Ethiopia’s first stock exchange, and the deals this helped secure with the IMF and World Bank. Since then, recent reform progress has been more mixed, although – on balance – still positive.

The IMF recently completed their fourth ECF review of Ethiopia, in which they commended the GoE’s robust progress on key macro reform indicators. Inflation is down to c.13% (from 30% in 2024). The Government now holds several months of dollar reserves ($4.2billion) up from several days’ worth in 2024.  Foreign exchange availability has improved; exports have increased to nearly 6% of GDP (from half of that) – though supported by high gold and coffee prices globally – and tax reforms are making progress, with a doubling in VAT revenues.

Reforms to ease FDI have sparked some appetite to invest in Ethiopia, which is now up to 4th in Africa’s FDI rankings. While the GoE’s timeline to accede to the WTO in March 2026 slipped, 2025 was the first year in the country’s two-decade-long accession process that two Working Party meetings were successfully concluded, underpinned by continued reform progress at home, most recently on customs.

However, Ethiopia remains in ‘debt distress’. A deal with official creditors on the $1bn 2023 Eurobond loan remains elusive. The depreciating currency has made paying foreign debt and import bills ever more expensive. The ratio of debt servicing to exports remains roughly 50%. Ethiopia continues to struggle to diversify its export base and remains vulnerable to changes in global commodity prices. The business environment remains challenging.

Poverty rates are also on the rise. A World Bank report last year documented a rate of 43% up from 33% a decade ago. But if implementation of the IMF/WB package is successful, and commitment to the associated reforms is maintained – and deepened – there is potential for the GoE to set the foundation for broad-based, inclusive and sustainable economic growth.

Structural and sectoral reform
The GoE’s economic reform agenda is now extending beyond the macro sphere. With the removal of trade preferences to Ethiopia under the American Growth and Opportunity Act (AGOA) and deep-seated challenges with trade and logistics, we assess limited opportunities in the textiles and garments sector for driving export-led growth. While there are positive developments in other job- and export-generating sectors e.g. chemicals and green industry, the lack of anyone – or few – sectors identified by GoE as the drivers of growth increases the relative importance of cross-cutting and enabling sector reforms.

Public Investment Management (PIM), Public Private Partnerships (PPPs) as a means of mobilising more private investment in the economy, State Owned Enterprise (SOE) and Public Asset Management (PAM) reforms are therefore at the heart of Ethiopia’s/HGER 2.0’s next phase of reforms, with a deliberate pivot towards efficiency, fiscal sustainability, and greater private-sector participation. It should be noted that these reforms are slower and more complex to implement than, say, floating an exchange rate.

Liberalisation of the telecoms sector in 2022-23 – the GoE’s signature sectoral reform (and something EIAF I provided critical support for) – has seen mixed progress, with the one private license holder, Safaricom, facing a challenging operating environment. Recent policy changes have though addressed some of the key issues.

Other sectors are now following. The vital logistics sector – the most cited binding constraint to growth and perennial pain-point of business – is opening up, albeit very gradually: of the 6 new licenses offered to the ‘private sector’ to compete with the state-owned Ethiopian Shipping Line, 4 were awarded to SOE-led Joint Ventures, and limited to the least profitable trading routes. Banking has partially opened up – regional banks have expressed interest with Standard Bank opening a Repo office – a step towards investment. Following the launch of Ethiopia’s first stock exchange (the ESX) in January last year (reported in last year’s Annual Review), capital market development has progressed steadily and in line with expectations for an early-stage market. Three initial listings and the licensing of 15 capital ‑market service providers show that the core market infrastructure is taking shape. Although the pace of listings has been cautious, this is typical for newly established exchanges, and the growing pipeline — with over 70 prospectuses under review and several additional listings anticipated —signals increasing momentum. Policy reforms enabling participation by both domestic and international institutional investors are further strengthening confidence in the market’s long-term outlook. Most recently, the retail sector, opened to foreign investment last year, announced that international retailer Carrefour will enter the Ethiopian market this year.
These are positive developments. But the real test will be sustaining implementation of these reforms, especially under fiscal and political pressure. The year ahead – a general election year in Ethiopia– will be an important one. We have explicitly shaped EIAF II to align with these developments.

Wider context
Ethiopia is still beset by political instability and conflict; fighting continues between armed groups in Amhara region and the Federal government, as well as continued insecurity in the Oromia region. In addition, the political settlement established between the Federal Government and the Tigray region following the devasting civil war 2020-2022 has begun to fray, with increasing risks to peace and security in the north of the country. And rising tensions between Ethiopia and neighbouring Eritrea could, if they spill over into conflict, eclipse these internal challenges. Conflict and instability remain a dominant issue for both the Government of Ethiopia and international development partners, with the economy continuing to suffer due to associated fiscal pressures and a highly unpredictable business environment.

On the other hand, Ethiopia was successful in its bid to host the UN climate conference, COP32, in 2027. This has already risen to the top of the GoE’s agenda, with structures and initiatives mobilised to deliver. This presents opportunities for engagement and partnership, especially on Ethiopia’s green growth – both the infrastructure required to execute COP32 as well as the domestic initiatives the GoE will want to champion as it invites the world to Addis in 2027. EIAF II will offer TA to the GoE for their financing strategy for COP and also look to use this moment to accelerate delivery of other key outputs and outcomes.

Internal context
There have also been significant changes within FCDO and the British Embassy Addis Ababa. Further UK ODA reductions on the one hand, and on the other the launch of the UK’s new Africa Approach, underpinned by a commitment to building modern development partnerships, have steered the Embassy towards a tighter economic development goal in its Country Business Plan - Green, inclusive and sustainable growth for Ethiopia underpinned by i) macro-economic stability, iii) a private sector led economy that creates jobs, and iii) greater access to climate finance. Our embassy strategy is shifting from supporting stabilisation to growth in Ethiopia, deepening our focus on system-level reform and strengthening, ensuring that gains are inclusive and sustainable. EIAF II is set to be our flagship programme delivering on these shifts over the coming years.

At the same time a stable and growing economy with a robust revenue base is fundamental to ensuring a long-term exit from humanitarian need and political instability. A return to economic instability, high inflation, and lack of job creation will prevent the government from investing at the scale required in essential services (health, education), humanitarian needs will grow further, and young Ethiopians will look for alternative routes to express their discontent (either through political instability or migrating abroad).

Programme developments over the last year

The most significant programme development this year was the contracting and mobilisation of the programme’s Public Investment and Asset Management (PIAM) facility, delivered by a consortium led by Cowater International. The activation of this component brings EIAF II more closely in line with the programme envisaged in the original Business Case, while accounting for the changes highlighted above. PIAM mobilisation faced significant hurdles this year due, in particular, to a challenging period in the UK-Ethiopia bilateral relationship slowed implementation with Government of Ethiopia agencies. With creativity and agility, the programme has navigated this relatively well and is now concluding the inception phase and has already begun implementation on the PAM/SOE pillar.

The programme team are currently procuring an independent Monitoring, Learning and Evaluation (MEL) function, to support results verification, evaluate programme impact and effectiveness, and – most importantly – to enable real-time learning to be captured and fed back into programme implementation. This component will have a particular focus on the new PIAM facility, as well as FSDE’s capital markets work.

Another important development came in the capital markets pillar, where our principal delivery partner, FSD Ethiopia, secured their local NGO license, establishing them as an independent, local entity, legally separate to but still closely partnered with sister company, FSD Africa. While FCDO’s Due Diligence Assessment and new Accountable Grant Agreement with FSDE are still being finalised, subject to an ongoing strategy review process in FSDE, this culminates two years’ worth of effort – led by the programme team – to support this localisation process. The programme initiated the Strategy review in order to focus FSDE’s capital markets work on the critical binding constraints in the ecosystem, and to hone-in on the 3-5 big shifts it wants to achieve over the next 3 years, accounting for a lower and reducing FCDO contribution.
EIAF II’s partnerships with the Global Green Growth Institute (GGGI) on climate finance, with Trade Mark Africa (TMA) on trade and logistics, and with the World Bank’s economic reform Multi Donor Trust Fund (MDTF) have all continued to evolve. The programme team have taken the decision to conclude the partnership with GGGI at the end of this (25/26) financial year. The component saw some strong results, but the programme management relationship proved inadequate to justify continuation in a resource-constrained future. We pivoted our climate finance efforts towards FSD Africa’s Carbon Accelerator Programme for the Environment (CAPE), aiming to unlock finance for high-integrity Nature-Based Carbon projects in Ethiopia – a relationship with a trusted partner that is already delivering well. We have continued to refine the partnership with TMA, testing what works and gains traction with beneficiaries and partners, and surging into that, while taking the decision to drop other project components, for example the work with the Horn of Africa Initiative (HOAI). With the MDTF, we - along with other donors – approved a two-year extension to enable this flexible TA modality to continue and align with the Bank’s Development Policy Operation (DPO) with the GoE; we topped up the UK contribution by £750,000, positioning us well to drive strategic direction at a critical juncture. Together with the larger PIAM and FSDE components, EIAF II is now well-positioned for the upcoming Spending Review period and ODA allocation exercise – with most of the programme’s prioritisation already determined and communicated to partners, except for the decision on the future of the trade and logistics work.
A new programme team structure introduced last year to meet the needs of this growing programme, with a lead adviser responsible for each component and bolstered programme management capacity, has also now bedded in. Though further internal resourcing transitions will continue to test the team.

For the review period (Jan/Feb 2025 to Jan/Feb 2026), a total budget of £6.32 million was initially allocated for EIAFII; however, the programme spent £6.8 million, which is £459k above the allocated budget, representing an overspend of 7% against the initial allocation. The programme secured this additional budget from across the office to cover tasks that were not planned at the beginning of the financial year, such as the UNDP High-Level Business Forum and CAPE Ethiopia.
The programme’s spending during the review period is detailed as follows:
- £2.5 million for financial market activities implemented by FSDE.
- £614k for embedded advisers assigned to the Prime Minister’s Office, Ethiopian Investment Holdings, and the Ministry of Finance. The payments for the adviser in the Prime Minister’s Office are managed by FSDA, while the advisers at Ethiopian Investment Holdings and the Ministry of Finance are managed by FSDE. However, during the last financial year, the payments for the adviser at Ethiopian Investment Holdings were managed by FSDA.
- £750k as a contribution to the World Bank MDTF (the payment was made in the last financial year, March 2025, but falls within this review period).
- £87k for the UNDP Development Partnership Group pooled fund for the delivery of the High-Level Business Forum in Ethiopia.
- £364k to the EIAF main supplier facility (the allocated budget to the main facility for this FY is £1.6 million, but this is the amount utilised during the review period).
- £642k for GGGI; part of this funding (£263k) is carried over from the previous financial year due to underutilisation.
- £1.3 million disbursed to TMA.
- £458k disbursed to FSDA CAPE via the budget buy-in mechanism (Option 1b)

Summary supporting narrative for the overall score in this review

Overall, the EIAF II programme scores an A for this reporting year. Of 13 output indicators, 9 met (4) or moderately exceeded (5) expectations. Considering impact weighting 65% of outputs scored an A, 35% scoring a B (partially meeting expectations). Underperformance was concentrated in the PIAM component, largely due to unforeseen political challenges, and in the climate finance component, due mostly to controllable delivery delays and programme management deficiencies. Nevertheless, the programme is on track to deliver currently specified targets by programme end, though EIAF II’s flexible approach and newly mobilised or mobilising components mean there are few of these.

The programme has expanded to deliver on a fuller set of objectives, more in line with the original Business Case. Outcome-level milestones were mostly achieved building on last year’s decisive contributions to major economic reforms undertaken by the Government of Ethiopia.

Major lessons and recommendations for the year ahead

The importance of carefully balancing Government stakeholder demands/buy-in with structured, strategic delivery planning. A key challenge for the PIAM Facility’s first 6 months of programming was the tension between delivering quick wins to meet GoE stakeholder expectations, securing their buy-in, whilst in parallel designing and standing up formalised structures and processes. This is a common challenge for flexible, demand-led TA (also documented in EIAF I’s Project Completion Report) and lessons here are applicable across the programme/portfolio. The strategy PIAM adopted was to emphasise iteration, putting Government partnership first – including offering more flexibility than scoped (e.g. working with a broader set of SOEs/sectors); this has been vindicated by the protecting and building of key relationships in a sensitive political economy putting the Facility in a decent place for its implementation period.

Early, formal engagement with key government stakeholders is critical to effective programme delivery, especially for demand-led facilities like PIAM, and even more so in such a centralized political economy. Delays (due to bilateral political challenges) in initiating structured, formal engagement—particularly at senior and technical decision-making levels—significantly constrained the programme’s ability to finalise governance arrangements, validate diagnostics, agree workplans, and define results frameworks and KPIs. While informal engagement helped sustain momentum in the short term, it could not fully substitute for formal counterparts and decision-making forums. Governance arrangements will be important for enabling clear, accountable GoE Leadership on PIAM. The recent signing of the PIAM MoU in the presence of the Finance Minister and Prime Minister during the Foreign Secretary’s visit to Ethiopia is a clear step forward, but careful handling and coordination will remain critical.

Logframe realism, KPIs, and political context. The PIAM inception period demonstrated that setting KPIs and co-developing jointly-owned workplans is a key tool for addressing the previous two lessons. However, this is challenging for a flexible, demand-led programme within a sensitive political economy, and requires an iterative approach. In addition, some logframe indicators (e.g. ownership policy under PIAM, or Berbera utilization on TMA) were not fully aligned with political and institutional realities.

FSDE needs to continue its transition from broad, foundational work to a sequenced, targeted, and high-impact set of initiatives for capital market activation. This shift should be guided by the outcomes of the FSD Ethiopia strategic refresh and the in-house strategic diagnostic work undertaken by FSDE and FSDA in collaboration with FCDO. This is the right time to transition from policy and regulation-focused workstreams to market activation, aligning closely with the shifts under FCDO’s modern development partnerships approach. In turn, this will improve FSDE’s chances of securing other donor funding.

There is a hierarchy of interventions and their potential impact under the trade and logistics component. The private sector strengthening and sector reform support came through the strongest; Berbera Corridor work remains high-potential but needs nuancing; WTO work is impactful, but its modalities need reviewing; while the Horn of Africa Initiative work is no longer VFM given the challenging institutional dynamics involved. The lifetime of this grant was short (1 year of implementation); while outcome results are yet to materialize, a strong foundation for impact is now there. TMA has built strong relationships with key stakeholders, including EFFSAA, EMA/LTO and MOTRI. The component’s progress with the private sector logistics ecosystem in particular, along with its trusted role advising GoE on logistics sector reform, and its history on the Berbera Corridor make it well placed to drive impact in this critical sector in the coming years. Taken together with PIAM’s work on SOE reform in the logistics space, this represents a strong package of work targeting reform and enhancement in this vital sector, a binding constraint to growth in the Ethiopian economy.

Accessing more climate finance and related TA remains vitally important for Ethiopia, especially in the context of reduced ODA-budgets and COP32. Therefore, having vehicles available, which can help with direct delivery and respond to priority GOE asks would be very beneficial for FCDO objectives, especially in the run-up to COP32 in 2027.

EIAF II has significant potential to leverage greater impact via donor coordination. Across four key components/their sectors – capital markets, logistics, climate finance and PIAM – EIAF II has established itself or its partners as the convenor of development partners, heightening coordination and in some cases leveraging greater inputs for programme objectives – for example, the Swedish development agency are now investing in Berbera Corridor enhancements on the back of our support under EIAF II.

Table 1 – summary of EIAF II recommendations
No.	Recommendation	Progress/comment
Last year’s (2025) recommendations
1.	Create and maintain a delivery chain mapping to track all downstream partners	In progress – due to new component/partner mobilisation and leadership turnover in existing suppliers (e.g. FSDE).
2.	Develop a gender and social inclusion plan for the programme, covering current and future components	In progress - decision taken to delay this until mobilisation of new MEL provider, procurement of which was delayed. This is a priority during finalising PIAM inception and mobilising new MEL facility.
3.	Enhance the strategy for FSDE’s capital markets and climate finance pillars, including developing a clear vision and meaningful measures of success, to be evaluated and adapted through monthly FCDO-FSDE meetings.	In progress – The substantive review of the FSDE ToC and Logframe largely achieved this recommendation. However, further work is required on the Financial Markets pillar 3-year strategy, and on shaping the new Climate Finance pillar.
4.	FSDE to develop a VFM strategy.	In progress – FSDE has improved its VFM approach (documented in VFM section below). However, it does not yet constitute a strategy, with FSDE still relying on FSDA’s VFM strategy.
5.	Continue prioritising the procurement and mobilisation of the new PIAM facility, which will be the programme’s key vehicle for helping GoE drive through these reforms. Deadline: mobilisation of PIAM by July 2025	Complete – new PIAM facility contracted July 2025. Successful mobilisation, nearing inception finalisation. Memorandum of Understanding with Ministry of Finance signed 1st February 2026.
6.	Design and mobilise a third-party MEL contract covering the whole programme. Deadline: mobilisation of new supplier by September 2026	On track – MEL facility procurement underway. Contracting due March 2026.
7.	Clear programme team resourcing and management plan in place. Programme team to consider managing EIAF II as an adaptive programme, including taking necessary training. Deadline: May, 2025 before key turnovers	Complete – new team structure with lead advisers for each component, supported by a dedicated PO, and cross-cutting support from wider team. Programme to be managed as a flexible programme (rather than adaptive).
8.	Programme team and partners to increase focus on financial management Deadline: initial message to partners by April, 2025; reiterated through monthly meetings.	Complete – EIAF II team has a monthly programme management and technical meetings with partners where component leads follow-up on budget utilization and workplans. Variance and underspend risks have been managed well this year.
9.	For TMA component, an emphasis on learning, risk and reflection (on what’s working/what’s not and political economy developments) should be incorporated	Comment – This approach was implemented well, dropping less impactful components (i.e. HOAI), picking up others (SL/Berbera interim transit work) and refocusing to where the political economy was most conducive to impact (from Berbera Govt-to-Govt negotiations to private sector strengthening).
10.	On TMA, continue working closely with embassy political teams (Ethiopian and regionally) to dovetail EIAF II programme objectives on trade/logistics and wider political objectives. Deadline: ahead of possible Berbera visit March 2025.	Completed: EIAF II team and the embassy’s political team have started holding monthly meetings with British Office Hargeisa and British Embassy Mogadishu to exchange updates, collaborate on events and coordinate on project implementation.
11.	Programme team to consider updating the theory of change (ToC) and associated output indicators on reform priorities. Deadline: April-June / PIAM inception phase.	In progress – PIAM mobilisation was delayed, and so ToC/KPI review still under way as part of Inception. The conclusive review will be timed with the inception of the independent MEL contract.
12.	Prioritise ecosystem development interventions in FSDE’s future strategy built on a deeper understanding of the political economy conditions.	Comment – given developments in the market, with key ecosystem functions (intermediaries etc.) beginning to fill out, the need for this support was less acute. FSDE has now shifted towards market activation and acceleration, which encompasses ecosystem support.
13.	Programme team to develop a plan with FSDE and co-funder Gates on resourcing the climate finance pillar for a trial period (18 months). Deadline: April as part of budget/pipeline approval for FY 25/26.	Complete - FCDO and Gates have reached an agreement, and recruitment is underway.
14.	Programme team and FSDE to develop and agree longer-term KPIs that enable better tracking of progress against strategic goals. Deadline: Initially by April as part of budget/pipeline approval for FY 25/26	In progress – logframe and component level ToC review conducted in-year, making substantial progress on this. Further work now underway as part of 3-year strategy review, to include KPIs for the next three years. / Procurement of independent MEL progressing well, and will further support FSDE ToC/LF.
15.	Driving progress with FSDE and FSDA on roadmap towards FSDE independence. Deadline: Ongoing, with review points in April and July/August.	Achieved - FCDO team has finalised the internal due diligence assessment (DDA). FCDO, FSDA and FSDA have done regular check ins on progress towards independence.
16.	On GGGI, add additional focus for next steps on voluntary and compliance carbon market initiatives. Deadline: April.	Achieved – Carbon Markets sub-component expanded on, with delivery underway if delayed.
17.	Enable GGGI to enhance donor coordination on carbon markets. Deadline: May 2025	Achieved - The draft Carbon Markets Proclamation is complete and mandates a donor coordination committee, which will be established upon approval of Proclamation.
18.	Accelerate GGGI recruitment of consultancy firms to finalize feasibility studies and streamline proposal preparation. Deadline: April	In progress - GGGI contracted a consultancy firm and the GCF full proposal is under development, targeted for submission by 31 March 2026.
This year’s key recommendations
Refining the ‘flexible, demand-led’ modality, particularly for the PIAM Facility. The Facility should instil and operationalise a culture of co-development with GoE counterparts e.g. on Proposals, Task Orders and KPIs. This may include use of embedded advisors, designated GoE technical leads, and/or principles of engagement. In addition, the whole programme should ensure delivery of the modern development partnership shifts, incorporating principles for Smart TA and Smart embedded TA articulated by FCDO HQ and BE Addis. Deadline: a plan for this on PIAM to be presented by April 2026. Follow-up check-in September. / At the same time, the Facility should finalise and stand up the Governance arrangements, considering the recommendations on governance from the Political Economy Analysis diagnostic – by April 2026. In addition, aligning communication between FCDO and EIAF2 on beneficiary expectation management, continuing to develop processes iteratively, including informal meetings amongst all counterparts to help develop visibility, ownership and access. / Planning for and evidencing impact of demand-led TA. With the support of the new MEL provider, prioritise the development of well-evidenced, ambitious but realistic KPIs that are co-owned with counterpart GoE Ministries. Ground these in the PEA findings, reflecting realistic pathways for reform given prevailing political and institutional constraints. Draw on evidence and best practice for balancing flexibility/responsiveness and long-term impact – including learning from other Embassies and relevant MEL research. This applies across PIAM, macro, capital markets components. Deadline – by April/May, subject to MEL mobilisation. / Concluding FSDE’s arc from start-up to free-standing. The programme team should continue to drive the strategy review process to conclusion, capturing key FCDO priorities and the Modern Development partnership ‘shifts’, especially system strengthening and reform, and ‘from donor to investor’ – this includes exploring new modalities such as fiscal CDEL/returnable grants for seed investments in the capital market. Then conclude the DDA and Grant Agreement processes, providing funding clarity and commitment over the next 3 years. Deadline - by April 2026. / Trade and logistics work should be renewed for another phase (subject to availability of funds), in particular to support the wider economic reform actions that the government of Ethiopia is undertaking under the HGER. This should be narrowed to focus tightly on private sector strengthening and logistics sector reform work, including tracking and shaping the IFI programme actions/conditions on the sector, and dovetailing with PIAM work. Space for Berbera Corridor support should be maintained, to respond to openings in the political economy. Deadline – decision by March; design and mobilisation by April. / On Climate Finance, the programme team should identify existing work and future opportunities for relevant support across the whole programme, articulating this as a coherent package, and assessing whether/how this – together with the FSDA CAPE work – can deliver on our full climate finance ambition in the run up to COP32, and if not whether/how to supplement it. Deadline – by June 2026

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Figure 1 – EIAF II Theory of Change

Super Impact: Poverty in Ethiopia is reduced

Impact: Export-oriented and private sector-led sustainable and inclusive growth

Overall Programme Outcome: Improved enabling environment for exporters, supported by strengthened effectiveness of growth-enhancing public investment and improved access to finance
Higher return on logistics investments and improved logistics performance

Higher return on investments of both private sector and Government in export-enabling sectorslogistics performance
Higher return on public investments, which address constraints to private investment

Outcome indicators

Intermediate outcomes

Reduce cost and time of imports and exports

More capital available to and allocated more efficiently by the private sector and Government

Improved selection, appraisal, and delivery of investment projects
Improve operations and financial performance of SOEs

Outputs
Delivery of relevant, timely and high quality TA outputs that meet expressed GoE needs

PIM/PPP - Support decision making on major investments and improve skills and processes on PIM/PPPs
SOE/PAM - Support GoE to strengthen SOE governance and performance and implement transformation plans
Capital markets and climate finance: support to MoF, ECMA, ESX and NBE to deepen capital markets and mobilise more capital – and climate finance – supporting inclusive growth
Logistics: Support the Ministry of Transport and others to develop and implement a well- informed plan to improve logistics performance

Activities
Input: Programme resources to TA delivery partners, supported by diplomatic influencing

The original EIAF II impact pathways and the proposed flexible approach remain largely valid. The current Theory of Change reflects – as documented in previous reviews – the shift in EIAF II’s emphasis away from manufacturing per se as set out in the Business Case. This was primarily due to a portfolio decision to proceed with two other programmes focused on the sector, Accelerate and Manufacturing Africa. Recently, this shift has been further solidified, and justified, by the context that despite efforts the share of manufacturing to GDP has declined and structural transformation towards manufacturing has not taken off.

Export-led growth remains the key priority in order to tackle macroeconomic imbalances in the Ethiopian economy and lead to sustainable growth in the long-term. This should remain core to BE Addis’ vision of how to drive long-term impact. However, there is a need to interrogate how/ whether EIAF II’s interventions contribute directly and indirectly to the impact-level changes we are seeking.

The Theory of Change should be further refined given the significant developments both in and outside the programme over the last year, most notably the mobilisation of the new PIAM facility and shifting FSDE strategy, which bring the programme up to near-full design scope. Last year’s review recommended such a ToC revision be undertaken – alongside a revised logframe and KPIs – as part of PIAM inception; we will continue to consider this option, but we also have the opportunity presented by the mobilisation of the third party MEL provider, whose Terms of Reference include an early deliverable for a comprehensive review of EIAF II’s logframe and ToC. This refinement should test whether the assumptions underlying the ToC still stand, given the rapidly changing political and economic context in Ethiopia especially coming into an election year. It should also more tightly define the strategic outcomes and impact we are seeking to achieve via the set of interventions under EIAF II, aligned with the Government of Ethiopia’s own vision for economic development and growth, and with the UK’s strategic objectives in Ethiopia (to be defined in the upcoming Country Plan and Portfolio Strategy exercise).

Here the programme team have identified issues and questions for consideration through such an exercise.

Programme impact to poverty reduction (super impact): EIAF II’s impact is ‘Export-oriented and private sector-led sustainable and inclusive growth’. The link between exports, growth, job creation and poverty reduction is well-evidenced, although the transmission mechanisms are sometimes indirect. Ethiopia’s recent history up to the original EIAF II business case showed strong correlation between growth and poverty reduction – Ethiopia was one of the fastest growing countries in the world while poverty rates fell from 44% in 2000 to 24% by 2015.
However, according to the latest research from the World Bank[1], poverty has significantly worsened in Ethiopia with the rate increasing by 9% between 2016 and 2021, and is now back up at 43%, eroding decades of gains. Ethiopia’s growth rates still outstrip regional peers. But the benefits of growth are not translating into reduced rates of poverty. The World Bank analysis shows this owed to declining living standards, explained by a combination of significant recent shocks – COVID, conflict, climate – and deterioration in the labour market: the economy created less than 1.2 million jobs during a period when the working age population expanded by 5 million. This deterioration, the analysis concludes, was at least in part, rooted in Ethiopia’s economic model during the ‘growth’ years, pre-crises. This state-led development model relied on suppression of market incomes, followed by redistribution that the government could no longer afford. Structural weaknesses and macroeconomic imbalances inherent in the growth model had started to bind.
[1] Ethiopia Poverty and Equity Assessment 2024 - Welfare at a Crossroads
These deficiencies are precisely what EIAF II targets – the need for a more competitive, private sector led economy less reliant on fiscally risky, inadequately managed public investments for growth. But EIAF II should continue to carefully consider its own transmission mechanisms to poverty reduction, including through the upcoming KPI/Logframe review. For now, regarding EIAF II’s impact pathways, it should be noted that while Ethiopia has had consistent growth, this growth has not (yet) been ‘export-oriented, private-sector led sustainable and inclusive’. So, the broader evidence base on these development linkages remain an important guide.
EIAF II’s impact indicators – value of exports and export-oriented jobs – are fully aligned with our economic diagnostics and team strategy under the Country Business Plan. However, this year’s developments – with rapidly rising gold revenues – have shown that rising exports are not necessarily indicative of either structural reform or sustainable and inclusive outcomes. Nor do exports per se drive the transformation to a more private sector-led economy. Recommendation: The programme should consider indicators that better target such impacts.
Impact to outcome: EIAF II’s outcome is an ‘Improved enabling environment for exporters, supported by strengthened effectiveness of growth-enhancing public investment and improved access to finance’. This conflates an outcome and intermediate outcome into one statement. The outcome – an improved enabling environment for exporters – has a clear and direct linkage to EIAF II’s desired impact. But as currently articulated, the intermediate outcome(s) – strengthened effectiveness of growth-enhancing public investment, and improved access to finance – do not: both of these intermediate outcomes could be achieved and yet do little to improve the enabling environment or export values themselves. Recommendation: This intermediate outcome-outcome link appears the weakest in the ToC logic and requires special consideration in the upcoming MEL review. There are options for resolving this – for example, tightening the PIM focus and/or finance focus on export-oriented interventions; or, alternatively, reviewing the impact and outcome focus to better reflect current delivery priorities, which are largely export-agnostic.
The outcome currently has six indicators, broadly corresponding to EIAF II’s components (PIAM has two indicators, one for each pillar):
1. Increased private investment into growth- and export-enabling sectors such as energy, logistics and infrastructure, including through new PPPs – this assumes that implementation of Ethiopia’s new PIM framework and improvements in the PIM system improves private sector investment; this should be reviewed. The PIM indicator may be improved by focusing on effectiveness or VFM metrics of public investment – for example, Return on Investment metrics or value of PIM-related savings (a continuation from EIAF I) – not a volumetric investment objective. The pathway for private investment needs specific consideration – a better indicator may be number of PPPs reaching financial close.
2. Improved oversight and governance of SOEs improves their operations and financial performance. The disconnect with the export-orientation of the outcome and impact should be reviewed – for example to focus on export-enabling or -oriented SOEs. As should the lack of indicators related to private sector access/involvement, reflecting the catalytic role SOEs can play in reformed sectors and HGER 2.0’s focus on private sector financing.
3. Enhanced Trade Environment in Ethiopia. As detailed in section B, high trade and logistics times and costs are a binding constraint on growth, especially for the private sector. This remains a strong link in the ToC.
4. Greater access to forex & macro-economic stability. Macro stability remains a precondition for inclusive growth and poverty reduction. It is also a core feature of an export-enabling environment. The indicator’s emphasis on forex remains a core mandate of the National Bank of Ethiopia. This is supported through our partnership with the Bank of England, which has recently been reactivated following leadership change at NBE. However, we should consider whether this fully captures the breadth and depth of the macro-economic stability improvements that are required.
5. Capital markets deepened. There is a general positive relationship between effective capital markets and exports – including private sector exports – as high-growth firms are able to secure the long-term risk capital that enables the leap to internationalisation, and the short-term trade finance gap is addressed. And capital markets directly improve access to investment capital for both the public and private sector. We could consider tightening the indicator linkages further, for example around more investment or export supporting modalities, policies, listings, products. We will maintain the focus on inclusive and sustainable capital markets, through work on Islamic Finance and sustainability-linked initiatives.
6. Increased GoE mobilisation of GCF finance. Improving access to capital for sustainability-focused public investment, with the disciplines associated with GCF funding, supports EIAF II’s intermediate outcome.
Outputs to outcomes: there are five outputs of the programme:
1. High quality technical assistance improves Ethiopia's public investment and asset management (PIAM) system
2. Improved capacity in logistics sector along key trade corridors, with tangible progress towards WTO Accession
3. Macro-economic reform (technical support for NBE and other government entities on macro-economic reform)
4. Strengthened capital market infrastructure and capacity in Ethiopia
5. Increased mobilization and improved access to climate finance
Many of the considerations above on outcome indicators also apply at this level. In addition, the cross-cutting assumption here is that EIAF II’s primary modality – high quality technical assistance provided to the GoE – is internalised by the GoE and, in turn, translates into effective change. While the modality, especially when demand-led and responsive, is recognised as essential to modern development partnerships, its effectiveness is not a given. FCDO HQ and BE Addis have both recently produced work on Smart TA, the principles of which – including the importance of rooting TA in system and institutional diagnostics, ‘Strengthening endogenous capacity and ownership’ and ‘Taking an organisational or systemic view’ – should be embedded in design and management of EIAF II’s TA.

Relatedly, the successful translation of outputs to outcomes across all components assumes a conducive political economy and alignment between programme and/with GoE objectives. Last year saw output-level efforts translate into substantive outcome-level achievements, including the exchange rate and other macro reforms in July 2024 and the launch of the Ethiopian Securities Exchange. This provided some validation of overall EIAF II’s Theory of Change – that quality technical assistance combined with sustained and senior GoE commitment leads to material changes in the policy and operating environment for investors and exporters. This year has seen continued commitment and progress on those reforms, and the expansion of the reform programme as outlined above – real-world changes here may be slower, but this is at least in part due to the nature of these more sticky, sectoral and structural reforms. The World Bank and IMF indicate that there is strong commitment from the Government to continued reforms.

Inputs to outputs: Suppliers respond to a clear demand from GoE for TA, maintaining trusted working relationships with key Government counterparts and have a good understanding of the operating context. During the review period, suppliers (Cowater, FSDA/E, TMA, GGG, and the WB) have maintained or built good relationships informing and improving areas of focus.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is broadly on track to achieve its outcome and outcome indicators, which are considered in detail below. Where components are more advanced, like capital markets and trade and logistics, there is greater confidence – relationships, deliverability and outcome trajectories are clearer. On the other hand, PIAM is new and still building relationships, credibility and direction – it also has ambitious, politically-sensitive objectives; it therefore carries greater risk of missing outcomes and impact and warrants greater attention by the programme team.

Table 2 – EIAF II Outcome confidence

Outcome Title	Improved enabling environment for exporters, supported by strengthened effectiveness of growth-enhancing public investment and improved access to finance
Outcome Indicator(s)		Milestone(s) for this review	Progress
Outcome Indicator 1: Increased private investment into growth- and export-enabling sectors such as energy, logistics and infrastructure, including through new PPPs.		Concrete progress on PPP/PIM pipeline projects.	Off-track. Limited formal engagement with relevant GoE stakeholders, largely due to the bilateral political context, hampering progress. Plus, internal changes within EIAF2—specifically delays in mobilising the PIM lead.
Outcome Indicator 2: Improved oversight and governance of SOEs improves their operations and financial performance.		EIH ownership policy agreed and in place.	On track. Strong, delivery-focused engagement with EIH. The programme demonstrated a high degree of flexibility and adaptability in mobilising delivery during the inception phase. / The EIH Ownership Policy draft is in place; however, final approval is pending Board endorsement. / Embedded advisor (Chief Strategy Officer) in EIH highly effective, leading EIH’s own reform work. An agreed exit plan is in place for end FY25/26.
Outcome Indicator 3: Enhanced Trade Environment in Ethiopia.		Overall, on track to attain all of the outcome indicator targets set for March 30 2026, with the exception of the second milestone on organizing a Business-to-Business (B2B) engagement between logistics operators in Ethiopia and Somaliland.
		1)100 operators complying with sector standards and norms.	The FIATA international model rules for freight forwarding have been adapted into the proposed revised freight forwarding regulation, which would align Ethiopia with international standards.
		2) B2B engagement between Ethiopia and Somaliland started	TMA engagements with Ethiopian and SL private sector but was not able to organize the formal exchange.
		3) Logistics private sector advocacy platform created and strengthened	Logistics sector advocacy platform was successfully launched in Ethiopia and parallel platform in Somaliland, advocating for the proposed logistics sector reforms.
		4) Two stages of the WTO Accession process completed	Ethiopia, for the first time in its 20+ years of accession history, has successfully completed two Working Party meetings in 2025
Outcome Indicator 4: Greater access to forex & macro-economic stability.		Implementation of macro reforms in line with IMF and World Bank benchmarks	On track – key macro reforms progressing well, validated by recent IMF/WB reviews.
Outcome Indicator 5: Capital markets deepened		6 new market participants (e.g., institutional investors, retail investors, etc)	Strong groundwork for bringing the two major institutional investors (private and public pension funds) onboard to participate in the CM. / Three licensed Investment Banks (Wegagen Capital, CBE Capital, and Ethio-Fidelity Securities S.C) have collectively opened 2,700 investor accounts / Approval-in-principle to 4 potential issuers in the reporting period, expected to list in Q1/Q2 2026
		40 financial institutions adopting guidelines, policy, and frameworks	Guidance documents such as the ESX rule book are already used by all (~70) market participants. / FSDE supported ECMA, the ESX, the Accounting and Audit Board of Ethiopia (AABE), the Ethiopia Capital Market Administrative Tribunal (ECMAT), and the CSD on developing manuals, guidelines and policies (13). Adoption requires time, and endorsement from key stakeholders. FSDE will use its donor convening position to hasten these decisions.
		5 (up to 11) draft shariah complaint instruments internal policies and guidelines implemented	The design of the instruments is in draft stage. A total of 9 money market instruments will be finalized by Q1 2026, whereas documentation for the Sovereign Sukuk will be completed by Q2 2026, aiming for issuance by Q3 2026.
		One SME finance instrument launched	The design and development of the crowd investment platform complete and awaiting approval from ECMA. The regulatory shift to the crowdfunding directive has delayed the launch.
Outcome Indicator 6: Increased GoE mobilisation of GCF finance		MoF mobilise $10 climate finance from AF.	MoF has successfully mobilised USD 10 million from the Adaptation Fund (AF) to support national climate resilience priorities. (in addition to the USD $45m from last year, not covered in this review period). ‑resilience priorities. (in addition to the USD $45m from last year, not covered in this review period).
		SAP $30m project prepared	MoF has submitted the USD 30 million SAP project to the Green Climate Fund (GCF), awaiting approval.
		Climate and disaster budget tagging and tracking fully integrated	Climate budget tagging and tracking have been fully integrated into the IFMIS system (Federal Government) and are now operational. A Budget Tagging and Tracking Directive has been developed, and training provided to relevant institutions.
		Roadmap Implementation framework for carbon market completed	Roadmap for carbon market has been completed, and MoPD is now using it to guide ongoing and upcoming carbon‑market activities.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Last year’s Review noted that the programme had affected major reforms in the Ethiopian economy, increasing the global competitiveness of Ethiopian exports and increasing exporters’ access to investment financing, in turn making a meaningful contribution to inclusive and sustainable growth (the IMF upgraded Ethiopia’s growth forecast from 6.1% to around 9.2% for 2025/6 post reform). As set out in section A, these macro reforms are proving their worth against key indicators.

But the reform agenda is evolving, focusing on sectoral reform, like logistics and the financial sector, and on public investment and asset management reforms; EIAF II is squarely and explicitly aligned to these priorities, and is FCDO’s best vehicle for supporting them. We continue to assess that for relatively small investments, EIAF II can unlock considerable investment and export potential.

Section A also set out how our portfolio was sharpening and evolving, in line with a modern development partnership approach. EIAF II is now our flagship programme designed to deliver on the majority of our objectives under the ‘Growth and climate’ Country Business Plan goal for 25/26, a position set to continue as the Embassy undertakes is business planning for 26/27 and beyond. And its modality– flexible, demand-led TA focused on system reform– as well as its strategic approach (partnership first) fully align it to the FCDO’s new Africa Approach.

Considering the wider donor landscape in Ethiopia, EIAF II continues to occupy an important and missing niche – a quality, highly flexible TA vehicle to support priority GoE reform initiatives, where many other donors focus directly on private sector capacity building or value chain development. Key changes in the donor landscape include:
- AFD and the IMF stepping up their own engagement on PIAM TA – we remain in close coordination with them to ensure EIAF II’s additionality (which comes through its flexibility, modality options, and skillset).
- The World Bank reducing its engagement on PIAM due to its own political/relationship developments. The removal of the MDTF from this space makes EIAF II’s position even more important.
- An increasing number of development partners supporting capital markets development. To mitigate this, we have successfully established our delivery partner, FSDE, as the development partner coordination entity.
This Annual Review
This review was undertaken by the programme team –led overall by the PRO, with component inputs from each associated advisor (PSD advisor 1/PRO on PIAM; PSD Adviser 2 on logistics; PSD advisor1/PRO on macro; economic advisers on capital markets; climate adviser on climate finance), and deputy programme manager and PRO on the remaining sections.

## . DETAILED OUTPUT SCORING

Output Title	High quality technical assistance improves Ethiopia's public investment and asset management (PIAM) system
Output number:		1	Output Score: B
Impact weighting (%):		25%	Weighting revised since last AR?	Yes – up from 15% last year, reflecting strategic prioritisation as well as increasing programme resource allocation.

Indicator(s)	Milestone(s) for this review	Progress
EIH and relevant SOEs benefit from high quality technical advice and strengthened capacity.	These were identical across both indicators. / Main PIAM TA facility contracted. / PIAM facility inception KPIs: / PIAM steering committee established and first meeting held. / MEL strategy developed; Bidding process finalised and contract awarded to a potential MEL supplier. / Stakeholder and donor mapping engagement plan developed. / Diagnosis reports: PEA report; GEDSI analysis; PPP/PIM diagnostics report / LF revised / Year 1 Work plan finalized, budget and forecast submitted to FCDO / Inception report finalised	Partially achieved - PIAM TA facility contracted, with inception nearing completion, amidst bilateral political constraints on engagement. The programme carried on informal engagement and finalised most inception deliverables, including the diagnostics and allied analyses. / PIAM TA partner also shows responsiveness to the context and initiated delivery under SOE pillar with EIH, where there has been high appetite and potential to demonstrate impact. / A significant exercise was also conducted to engage all donors and stakeholders to map out the work in a coordination matrix or a tracker. However, due to limitation of formal engagement with key government stakeholders, primarily due to the political barriers, some key deliverables, such as steering committee meeting, logframe revision and Y1 workplan, have been delayed. This doesn’t negate the major strides taken by the facility during its mobilisation – its evolving strategic approach, prioritising trust- and relationship-building, as well as delivery and impact, is a significant achievement in a difficult context.
PIM and PPP system benefits from high quality technical assistance

Briefly describe the output’s activities and provide supporting narrative for the score.

The modern PIM system recently legislated for by GOE’s PIM and PPP proclamations – and supported under EIAF I – is not implemented in practice, with limited capacity to assess and prioritise investment options and coordination deficits between lead Ministries. The GoE’s pipeline of PPPs – heralded as the key tool for enabling the new wave of private investment envisaged under HGER 2.0 – has remained stagnant, often deemed too risky by the private sector; there is yet to be a project reaching financial close. SOEs lack professionalism and transparency, with politically-appointed boards; public service obligations are often in conflict with performance objectives; and there is not always a level playing field between SOEs and private providers. The creation of EIH, the GoE’s holding company and strategic investment arm, and the consolidation of the Federal SOE portfolio under it marks significant progress towards effective stewardship and management of public assets (again supported by EIAF1).

This output therefore seeks to provide high quality TA to support EIH and key SOEs, and to support the PIM and PPP system in Ethiopia, in order to achieve two outcomes:
improved performance of growth-enhancing SOEs, and improved oversight and governance of SOEs which in turn improves their operations and financial, and
increased private investment into growth- and export-enabling sectors such as energy, logistics and infrastructure, including through new PPPs.

A new flexible PIAM facility was mobilised this year, becoming the main vehicle for this output to support a faster and more comprehensive set of reforms in the coming years. In addition, UK support to PIAM measures under EIAF II is delivered via: an embedded adviser in EIH, funded via FSD Africa (our tier 1 delivery partner for the FSDE capital markets work under output 4, although the programme team manage the advisor relationship directly); and projects delivered by the World Bank through the MDTF.

This output scores an B since some key indicator milestones for the Facility’s inception phase were not met. However, this should not be taken at face value. The component navigated some extremely difficult issues in the political/external context, which severely hampered mobilisation for several months (the majority of the inception period). The programme adapted well around these issues, managing to conclude most inception activities, pivot to early delivery on the SOE/PAM pillar meeting urgent demands from EIH, and emerge with strong relationships with GoE counterparts – the foundation of this component’s success over the coming years.

Notable achievements included:
- Completion of quality key inception outputs, including the primary diagnostic work and a set of analytical products underpinning the programme’s strategic direction and management approach. These comprised Political Economy Analysis (PEA), GEDSI analysis, Inception Report and high-level diagnostics on SOE/Public Asset Management (PAM) and PIM/PPP. All these deliverables have been completed but the scale of effort had to be recalibrated to enable delivery in parallel. Both pillar diagnostics will remain live documents and will be iteratively deepened through targeted sectoral analyses during the implementation phase.
- Successful positioning with key stakeholders, including EIH, the Ministry of Finance (MoF) and the Ministry of Planning and Development (MoPD); the facility is now deepening relationships with relevant division heads.
- Strengthened coordination with development partners and key stakeholders. A comprehensive coordination matrix and tracker was developed, mapping ongoing and planned donor activities to reduce duplication and enhance alignment. This tool has been incorporated into the inception report and will be used throughout implementation to support coordination and monitoring of reform efforts.
- A pivot to early delivery, kicking off 11 substantive task orders with EIH, building trust and credibility with a demanding counterpart, and adopting a learning-by-doing approach commensurate with such a demand-led, flexible TA facility.
- Substantive progress on key strategy processes (portfolio management, EIH org design, STP) driven forward by the EIH embedded advisor, with extremely positive feedback from EIH CEO, who is planning to bring the adviser onto EIH’s books come the end of the contract – a great example of sustainable TA provision.

The biggest challenge for this component was a slowdown in the overall bilateral relationship that affected engagement on the programme – this was a critical barrier for a demand-led facility. This was compounded by changes in MoF leadership, with State Minister of Finance, Dr Eyob, identified as the GoE Co-Chair for the facility, taking up the Governor position at the National Bank of Ethiopia. Together, these political issues affected Facility progress on key governance and planning deliverables. The Steering Committee has not yet convened, although governance arrangements have been articulated in the Terms of Reference for the Steering Committee and associated working groups. And, together with disruption due to (necessary) changes in the leadership of the Facility’s core team, there were delays to completion of the overall inception report, the development of facility KPIs to feed into a revised logframe, and the year 1 implementation plan. However, there has been recent, important progress. The Memorandum of Understanding was signed between the UK’s Foreign Secretary and H.E. Minister of Finance Minister of Shide, paving the way for projects to start with Ministry of Finance.

However, the PIAM facility and TA partner demonstrated strong adaptability and contextual awareness, proactively tailoring its approach to respond to these realities. It engaged through informal channels, and delivery was prioritised under the SOE pillar in collaboration with Ethiopian Investment Holdings (EIH), where reform appetite was strongest and opportunities for early, visible impact were clear. To maintain government engagement and delivery momentum, diagnostic and delivery activities were undertaken in parallel during the inception phase. Beyond opportunism, this represented a strategic shift in the Facility’s approach – away from heavy upfront external diagnostics and planning, to delivery-oriented, learning-by-doing, and a partnership-first approach. This stands us in good stead for the years ahead. The design of the new third-party MEL function has also been geared towards this approach, in order to strengthen focus on impact and responsiveness.

MDTF projects also delivered on EIAF II’s PIAM objectives through the review period, supporting the development of the WB DPO and associated projects, providing TA for the achievement of necessary prior actions and supporting achievement of the reforms listed in the DPO. This is covered in more detail against the macro output below.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The only substantive change to the output was the detailing of the inception deliverables under the milestones against which performance was being assessed.

We anticipate significant evolution of this output and its milestones and overall targets in the coming year. As outlined above, work is ongoing with the Facility partner to articulate a component level logframe, KPIs to be reflected in the programme level logframe, and a year 1 implementation plan which will set detailed milestones for the next Annual Review. We also plan to refine the output indicator descriptions, which are currently too input- and process-oriented. And we need, also, to better reflect public asset management under output indicator 1, which goes beyond the EIH and SOE support currently articulated.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lesson: the importance of carefully balancing stakeholder demands/buy-in with structured, strategic delivery planning. One of the key challenges of the Facility’s first 6 months of programming was the tension between securing early delivery wins to meet stakeholder (EIH) expectations and buy-in whilst simultaneously developing a formal structure and plan to deliver against. Whilst the Facility adapted well and took a strategic approach, prioritising key relationships over tight scope control, it was nonetheless challenging to meet the delivery demands of the beneficiary while attempting to formalise processes and ensure proper technical evaluation.
Recommendations:
  - The Facility should engender a culture of co-development of Proposals, Task Orders and KPIs (more on this below) with GoE counterparts. This is more important, even, than the formal idea-generation and approval procedures. The Facility to consider and define approaches for this including use of embedded advisors, designated GoE technical leads, or a set of principles of engagement. The Facility should articulate how it will operationalise the principles of Smart TA and Smart embedded TA articulated by FCDO HQ and BE Addis respectively. It should also prioritise governance mobilisation and onboarding of GoE counterparts to core processes and ways of working.
  - Develop a stronger feedback loop between EIAF2, FCDO and the beneficiary to allow for a more open discussion on critical evaluation on Task Order submissions; and ensure an aligned communication strategy between FCDO and EIAF2 on beneficiary expectation management, to create more space for systems and processes to develop and be tested in an iterative manner.

Lesson: Governance arrangements will be critical to enabling clear, accountable GoE Leadership. Owing to challenging bilateral political issues and the slow rollout of a proposed governance structure and mechanism, the programme has been operating without clear GoE leadership. Engagement from parts of GoE has been strong; however, there is not yet a harmonised governance structure capable of coordinating across GoE counterparts. This impacts the pace of delivery, which is moving rapidly in some pillars and too slowly in others; and beneficiary leadership, particularly the ability to articulate and execute a coherent vision for the programme.
Recommendation: Progress governance, considering recommendations set out in the PEA diagnostic, encouraging joint leadership of the Facility on the GoE side between MoF, EIH and MOPD. In the event of a delayed or partial roll out of a governance structure (including owing to issues in coordination between counterpart agencies) , consider setting up an informal meetings amongst all counterparts to help develop visibility, ownership and access; or, alternatively, establish adapted governance structures that are fit-for-purpose for all counterpart agencies.
Lesson: Logframe realism, KPIs, and political context. The inception period demonstrated that setting KPIs and co-developing jointly owned workplans is a key tool for managing demand-led flexible approaches. However, this is challenging within a politically-charged environment—particularly in the context of bilateral political issues – and requires an iterative approach. In addition, some logframe indicators, including those related to ownership policy, were not fully aligned with political and institutional realities on the ground.
Recommendation:
1. Prioritise the development of well-evidenced, ambitious but realistic KPIs that are co-owned with counterpart GoE Ministries. Ground these in the PEA findings and reflect realistic pathways for reform given prevailing political and institutional constraints.
2. Build greater flexibility into the logframe and work planning process to allow for iterative refinement of indicators as political conditions and counterpart engagement evolve.
3. Set up frequent review meetings to align the results with changing political and context priorities as advised by the PEA.

Lesson: Use of PEA and analytical tools to define Task Order viability. The inception period reinforced the importance of selecting and applying the right Political Economy Analysis (PEA) and analytical tools to assess the viability, sequencing, and appropriateness of proposed initiatives. In some instances, analytical tools were applied after delivery discussions had already progressed, limiting their ability to meaningfully shape initiative design or manage expectations around feasibility and timing. This created a risk of misalignment between ambition, institutional readiness, and political space for reform.
Recommendation:
1. Apply PEA and analytical tools earlier in the initiative design process, before delivery discussions are advanced.
2. Use analytical findings explicitly to inform prioritisation, sequencing, and scope-setting.
3. Share analytical conclusions clearly with FCDO and beneficiaries to align expectations on feasibility and risk.

Lesson: Early and formal engagement with key government stakeholders is critical to effective programme delivery, especially for such demand-led facilities, and in such a centralized political economy. Delays in initiating structured, formal engagement—particularly at senior and technical decision-making levels—significantly constrained the programme’s ability to finalise governance arrangements, validate diagnostics, agree workplans, and define results frameworks and KPIs. While informal engagement helped sustain momentum in the short term, it could not fully substitute for formal counterparts and decision-making forums.

This experience reinforced that operating “below the radar” can support continuity during periods of political sensitivity, but prolonged reliance on informal channels risks weakening ownership, slowing decision-making, and reducing the programme’s ability to establish clear causal links between interventions and intended outcomes.
Recommendation: Programmes should front-load formal stakeholder engagement wherever feasible and define minimum engagement milestones at inception. The programme should make sure that engagement is not completely delayed or prevented, in order to mitigate the impact on delivery. . Informal channels should be used only as a temporary measure, with clear transition points to formal engagement once conditions allow.

Recommendations from last year	Progress/comment
Continue prioritising the procurement and mobilisation of the new PIAM facility, which will be the programme’s key vehicle for helping GoE drive through these reforms. Deadline: mobilisation of PIAM by July 2025	Complete – PIAM facility contracted in July 2025, and nearing conclusion of inception phase.

Output Title	Improved efficiency and capacity in logistics sector along key trade corridors, with tangible progress towards WTO Accession.
Output number:		2	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of private sector logistics service providers benefitting from capacity building activities and international benchmarking exercises.	1) Governance framework deployed and adopted by logistics sector. / 2) 20 logistics operators trained. Sector advocacy platform launched. / 3) Partnership arrangement between sector body (EFFSAA) & international association in place by March 2025.	A - Met Expectations: / 1) Appropriate sector governance framework presented, and recommendations endorsed by key stakeholders. Already being translated into further deliverables for the sector. / 2) Training (using Certificate of Competence (CoC) framework) developed and piloted to EFFSAA members, including train-the-trainer for sustained impact. Capacity building training undertaken for >20 freight forwarders based on the capacity gap analysis findings of June 2025. Bespoke capacity building through one-to-one advisory to new MTOs. / - Sector advocacy platform launched in Ethiopia. / 3) Partnership arrangement for EFFSAA and the British International Freighters Association (BIFA) proposed and adopted. MoU signed in May 2025, with first exchange visit to UK November 2025.
2.2 Increased engagement and utilization along Berbera Corridor (as an alternative corridor to Djibouti)	1) Diagnostic study completed, challenges facing Multimodal Transport Operators (MTOs) clarified. / 2) MTOs skills enhancement, in-country facilitation and private sector network/ engagement create clarity on the major barriers in Somaliland.	B - Partially Met: / Logistics sector diagnostic study completed and validated. Key meetings with high-level officials in SL, including President. Skill enhancing support provided to MTOs. / Mid-July 2025 saw the successful launch of the SL Trade and Logistics Platform, parallel to Ethiopian counterpart.B-2-B engagement between Ethiopia and SL private sector players will take place in mid-February. / The project’s target of increasing BC utilisation by 10% is unlikely to be achieved by April 2026 due to external political factors.
2.3 Increased capability to undertake WTO accession	1) Questions from Member States on services and Non-Tariff Barriers (NTBs) adequately addressed. / 2) 6th Working Party meeting held successfully.	A - Met Expectations: / 2 experts embedded to MOTRI who led drafting, validating and submitting responses to 299 questions from WTO members on NTBs, Trade facilitation and Sanitary and Phytosanitary (SPS) issues. / Both 5th and 6th WP meetings for Ethiopia were held successfully, significantly advancing Ethiopia’s long journey to join the WTO. / Logistical support was provided to MOTRI to attend meetings in Geneva.

Briefly describe the output’s activities and provide supporting narrative for the score.
Ethiopia’s logistics costs are equivalent to 20% of its GDP, double that of India. The most recent World Bank assessments (2022/3) identify average consolidated dwell time for Ethiopian exports at 14 days, the third longest in the world. The sector remains largely monopolised by the State-owned Ethiopian Shipping Line (ESLSE). Ethiopia is heavily dependent on the Djibouti corridor, reducing competition and increasing costs. This creates an extremely inefficient operating environment for exporters. The logistics sector in Ethiopia is undergoing a reform process with strong political oversight but some hesitation about its pace and depth. WTO Accession would be a critical step for Ethiopia as it seeks to better integrate into the global trading system, consolidating its key domestic reforms and in turn attracting foreign investment, and driving export-led economic growth.

This output has the objective of enhancing the logistics and trade environment in Ethiopia by improving capacity of logistics service providers and their advocacy body, EFFSAA; supporting sectoral reform; promoting trade corridor diversification via increased utilisation of Berbera Corridor; and supporting Ethiopia’s WTO Accession process. The output is delivered by TradeMark Africa (TMA), which contracted TripleLine as a downstream supplier, under FCDO’s global MoU with TMA.

Key achievements include the launch of a long-term and already-productive partnership between EFFSA and its British counterpart the British International Freight Association (BIFA), with a first exchange visit for EFFSAA members to key logistics sites in the UK and return visits by BIFA. These activities included tailored training programmes, preparation of competency frameworks to global FIATA (International Federation of Freight Forwarders Associations) standards, and a train-the-trainer model to sustainably build EFFSAA’s internal capacity.

Beyond simply building capacity and improving logistics service provision, the partnership has produced a new framework for sector governance, including stronger self-governance by the private sector. This framework was validated by key stakeholders, and is already generating additional benefits in support of sector reform, shaping a new Directive to transform Modjo dry port to a common user facility (accessible to private sector operators) and an updated regulation for the freight forwarding sector which, if adopted, would align Ethiopia with international best practice, with a key role for EFFSAA.

Another key achievement was the work of the embedded technical advisors at MoTRI. They played a pivotal role in WTO multilateral negotiations, leading responses to nearly 300 technical queries from WTO members (>50% of the total queries). This marked a significant contribution to the success of two Working Party meetings this last year and has materially moved the country towards its ambitious WTO accession target, now ‘in 2026’. WTO accession has a potentially transformational impact on the export and private sector environment, assuming key GOE commitments – e.g. on level playing fields in SOE sectors and on transparent customs valuation – are adhered to. It is also a top political priority of the PM and Cabinet, and has a broader set of implications for Ethiopia’s role as a global player and supporter of the rules-based international system. UK’s support in this endeavour therefore is an important aspect of our repositioning as a modern development partner. Recommendation: the programme team should explore further synergies between WTO accession work with the PIAM facility, as well as more opportunities to highlight this work within broader political dialogue.
On activating Berbera Corridor, the project’s target of facilitating formal B2B engagements and increasing utilization of Berbera port by 10% were not met. The project achieved some progress, notably flexing to support private sector engagement in Somaliland, laying the ground for cross-border B2B partnership. But regional geopolitics involving Ethiopia, Somalia, Somaliland among others, hampered the political-level green-light needed to truly activate the corridor. GOE’s focus on ‘sovereign access to the sea’ also shifted their focus away from Berbera to alternative port options. These headwinds created an unpredictable environment that hindered progress and limited private sector confidence in using the corridor. Nevertheless, the project has established strong stakeholder platforms and technical groundwork and is positioned well to respond if the political situation improves and opportunities for corridor utilisation arise. The programme team remains in close coordination with the British Office Hargeisa, relevant stakeholders in Ethiopian and SL governments, private sector and development partners to take a coordinated approach.
Overall, the output scores an A. The project met expectations for two of the three output indicators, with very promising work on strengthening private sector logistics and supporting WTO accession, but only partially meeting the indicator on operationalizing the Berbera Corridor.

The project faced some challenges in terms of project management and delivery, which include communication gaps between TMA and FCDO regarding their activities and TMA introducing new activities in the middle of project implementation (at the request of partners) without prior approval from FCDO. TMA’s position as a multi-donor funded organization working on contiguous projects sometimes obscured or diverted focus. The delivery chain established by TMA which comprises TMA Ethiopia, TripleLine, external advisors, and the beneficiary partners (in addition to FCDO’s team), was long for a project of this nature. This raises value for money concerns and also drew some negative feedback from MoTRI, who found engaging across multiple layers cumbersome – the only spot on otherwise glowing feedback (particularly on the WTO advisers).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This project was designed to test and learn, adapting quickly based on what was working and what the political context enabled or didn’t. Berbera was a key focus, but we knew it was highly politically dependent; so the net was cast wide to test a range of initiatives, successes from which we would seek to take forward longer. We began the year with an indicator on the Horn of Africa Initiative (a country-owned, regional platform designed to help countries in the Horn of Africa solve common and interconnected challenges, including economic integration and trade). Following successive failures to gain traction on this work with a non-GOE key stakeholder, the programme team took the decision to close this sub-component. The work produced was of good quality and will still be fed into the HOAI process, but no further resources were directed to it and it was removed from the logframe.

Separately, in response to withdrawing USAID funding, a new sub-component was introduced to EIAF II to complete critical work on interim transit procedures for the Berbera corridor, helping bring together the new Somaliland government and key Ethiopian stakeholders, including both public agencies and private sector representatives, under the coordination of the Ethiopia Logistics Sectoral Association (ELSA). The platform’s objectives included raising awareness that Berbera was “open for business”, enhancing the confidence of Ethiopian private enterprises in utilising the corridor, and identifying as well as proactively addressing non-tariff barriers impeding transit operations. It was a good fit to EIAF II’s logframe and theory of change.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous year
	Recommendations from last year	Progress/ comment
1	Programme team and partners to increase focus on financial management	Completed – financial oversight and reporting has improved and very little variance and no underspend risks this year.
2	An emphasis on learning, risk and reflection (on what’s working/what’s not and political economy developments) should be incorporated into regular programme management engagements. Formally adopting an adaptive programme management approach to be considered. Ongoing.	Comment – As outlined above, this approach was successfully implemented, with the project dropping less impactful components (i.e. HOAI), picking up others (SL/Berbera interim transit work) and refocusing to where the political economy was most conducive to impact (from Berbera Govt-to-Govt negotiations to private sector strengthening).
3	Continue working closely with embassy political teams (Ethiopian and regionally) to dovetail EIAF II programme objectives on trade/logistics and wider political objectives. Deadline: ahead of possible Berbera visit March 2025.	Completed: EIAF II team and the embassy’s political team have started holding monthly meetings with British Office Hargeisa and British Embassy Mogadishu to exchange updates, collaborate on events and coordinate on project implementation.

Lessons learned and recommendations for the year ahead

This year generated clear lessons on what worked and what didn’t (covered above), and the delivery chain’s strengthen and weaknesses. TMA has built strong relationships with key stakeholders enabling it to deliver flexible, tailored and potentially impactful support. Downstream partner Tripleline has excellent analysis, insight and implementation capabilities, especially on the private sector work. The component’s promising progress with the private sector logistics ecosystem, trusted role advising GoE on logistics sector reform and history on the Berbera Corridor make it well-placed to deepening impact in this critical sector. However, the delivery chain is inefficient. Recommendation: in designing a next phase of this work, the programme team should carefully consider the delivery chain, and should continue to build or maintain its own relationships with key stakeholders in the sector including the Ministry of Transport and Logistics (MOTL), EMA/LTO, EFFSA, Ethiopian Shipping and Logistics Services Enterprise (ESLSE) and other SOEs in this space.

The main body representing and advocating for the private sector in the logistics sector (EFFSAA) needs strengthening. Ethiopia’s critical logistics sector remains dominated by SOEs like ESLSE and EDRC. Currently, EFFSAA has a relatively limited membership base, uncertain financial sustainability, and relatively weak institutional structure. Hence, targeted support to build its capacity, fund-raising capabilities and building upon the BIFA – EFFSAA partnership created with the support of the project are an important and niche contribution to ensure that there is a strong private sector participation in the sector, in turn supporting reform.

There remains strong potential to enhance the Berbera corridor ecosystem, regardless of high-level political dynamics/agreements. Public and private actors in both Ethiopia and Somaliland have shown strong desire to foster closer ties. The corridor also offers potential for a new competitive market for private logistics operators where the playing field is not dominated (monopolized) by SOEs. The project therefore should continue efforts to enable the private sector to play a leading role in policy designs, transit and transport negotiations and implementation (utilization) of the corridor. Recommendation: Future work on the Berbera Corridor should focus on practical interventions that build the corridor’s ecosystem and increase utilization and confidence. This should build on work this year establishing structures for cooperation between Ethiopia and SL stakeholders, while retaining flexibility to respond to positive political developments. In parallel, the embassy team should continue to deploy its diplomacy and influencing to encourage such conditions.

WTO accession support has been impactful and very well-received by MOTRI, as the ministry leading the negotiations for WTO accession. Discussions with MOTRI highlighted the importance of not relying on external experts, as the Ministry will need to implement agreements once Ethiopia accedes to WTO. Successful accession to the WTO is vital for securing a more open economy and facilitating trade, critical enablers to foster exports and job creation. Recommendation: Given the timeline extension for Accession, EIAF II should continue supporting until the end of 2026 at which point implementation support needs should be analysed.

The programme team’s regular forum with development partners operating in the logistics space has shaped project implementation and leveraged wider donor support. In addition, monthly internal engagements with the Political team of the embassy and FCDO offices in Hargeisa and elsewhere have maintained relevance.

Output Title	Macro economic reform
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
High quality technical support for MoF/PMO and other government entities on macro-economic reform	Continued provision of technical support and GoE demands appropriately met	Met expectations. Key macro reforms progressing well. Reports and feedback on advisers is positive; demonstrable impact between advisers is variable, but on balance remains strong.

Briefly describe the output’s activities and provide supporting narrative for the score.
Until recent reforms were launched with support of the IMF/WB, Ethiopia faced a severe and deteriorating macroeconomic environment with foreign exchange in crisis (the spread between the official and parallel rates was around 100%) and the country classified as being at high risk of debt distress due to the risks posed by the debt to export ratio. This output seeks to provide quality technical assistance to key GoE actors to stabilise the macroeconomy, a critical condition for the export environment.

EIAF II uses three channels to deliver this component. Two of these involve funding embedded advisers to support the GoE’s critical macroeconomic reforms. Under the FSDA MOU we fund an embedded senior macro adviser in the Prime Minister’s Office. Via FSDE, we fund an embedded macro lead in the Ministry of Finance’s Economic Management Team. The programme team manages these advisor relationships directly. Given the sensitivities of the reforms, and need for Government of Ethiopia ownership over policy decisions, our TA provision was designed to be largely confidential between GoE and the embedded advisers. The provision involved policy advice, analysis, and production and review of reform-critical documents, including IMF/WB programme review inputs; as well as ad-hoc support on reform efforts to fit GOE needs.

Key achievements are evident in ongoing macro reform progress, substantiated by successive IMF programme reviews, most recently review IV. An internal assessment of these advisers has been conducted to assess their VFM and alignment with new BE Addis principles on smart embedded technical assistance. One of the embedded advisers leads the coordination of GoE’s technical engagement on the IMF reviews, and the value addition is clear. This adviser has been singled out by other development partners, including the World Bank, as ‘the single most impactful intervention of any development partner on the macro reforms’. For the other, long-standing embedded adviser, we are now considering contract options beyond the end of this FY given wider budget pressures in the portfolio. The partnership has been positive, but no exit arrangements were made, so this now needs to be phased out responsibly, in line with DPO-3.

The third channel is the World Bank’s economic reform Multi-donor Trust Fund (MDTF), which FCDO has been a leading donor to. This is a flexible TA modality aligning with the Bank’s Development Policy Operation series with the GoE. Key achievements during this reporting period include the approval of the Development Policy Operation (DPO-2) by the World Bank Board, a $1 billion operation that builds on the macroeconomic and structural reforms initiated under an earlier $1.5 billion DPO-1. The MDTF was instrumental in shaping several DPO-2 prior actions, including reforms in financial sector restructuring and stability, trade liberalization, investment facilitation, domestic revenue mobilization, and public sector transparency. Key contributions included support for bank resolution frameworks, customs modernization, procurement reforms, and tax legislation reforming and modernizing corporate tax incentives, property tax and the excise tax regime. New reform priorities were identified with the support of MDTF grants, notably the reform of procurement of fuel imports – a macro-critical area with bearing for the functioning of FX market. The MDTF also supported logistics and rail sector reforms, including the operationalization of multimodal logistics and regional cooperation under the Horn of Africa Addis-Djibouti Corridor initiative, as well as technical support for WTO accession. This year, we also saw a marked improvement in programme/project management and donor engagement from the MDTF team, who have significantly improved their reporting and communications.

Despite these achievements, implementation challenges persist. Technical capacity constraints, leadership changes, and institutional fragmentation continue to hinder reform sustainability. Work is needed to strengthen relationships with critical stakeholders in priority reform areas.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This year the output was tweaked to reflect the key GoE counterparts we are supporting – away from the NBE, following the conclusion of the previous Bank of England work, and to Ministry of Finance and the Prime Minister’s Office.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Embedded TA can be an impactful tool if done well, but they bring added VFM and systemic risks which needs to closely managed – for example displacing rather than strengthening the systems they’re embedded in, or if managed too passively or without appropriate oversight of deliverables creating VFM concerns. These considerations for our existing embedded advisors – alongside the principles for a modern development partnership under the Africa Approach – prompted the embassy to draft new guidance for ensuring smart embedded TA.
Recommendations
  - Deep dive on smart embedded TA guidance with teams/partners overseeing embeds under EIAF to ensure good practice going forward.
  - Finalise decisions on existing embedded advisers ahead of the end of this FY.
  - Move all remaining embedded advisors to PIAM facility to ensure appropriate oversight and VFM.
Output Title	Strengthened capital market infrastructure and capacity in Ethiopia
Output number:		4	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Improve capital market infrastructure and institutions via quality TA to ESX, ECMA and other/new institutions.	3 improvements: / Delivery of Capital Markets Tribunal’s Rules of Procedure and guidebook; finalizing the guidance / TA to the NBE to support CSD / Crowd-Invest Platform support for go-live	Met, scoring an ‘A’– 3 significant enhancements to Ethiopia’s capital market infrastructure: / Initially designed to develop rules of procedure for the tribunal, the plan shifted to converting these procedures into a directive after consultations with the MoJ to make the rules enforceable. / All advisory deliverables for the Central Securities Depository (CSD) were met, except for the commercial model, to be finalized Q1 2026. / Crowd-Invest platform development finalised, and awaiting ECMAs approval. The vendor will continue the maintenance support for 1-year after launch.
4.2 Develop policies, regulations, guidelines and masterplans.	Financial institutions and regulators adopting 16 FSDE-developed guidelines, policies, and frameworks	Moderately exceeded, scoring an ‘A+’: 20 policies/regulations/guidelines adopted by the different institutions: / 7 manuals and Guidelines developed for and adopted by the Licensing, Supervision, and Investigation and Enforcement Directorates of the ECMA. / 4 CSD implementation documents developed and adopted by the CSD team. / AABE reform: 3 (Strategic plan, Institutional reform document with reform implementation plan and legislative and regulatory changes document produced). The reform plan will be adopted following its approval by both the Council of Ministers and the House of People’s Representatives. / 3 issuers (Wegagen Bank, Gadaa Bank, and Ethio Telecom) and 3 registered providers (Wegagen Capital, CBE Capital, and Ethio Fidelity Securities Brokers) have adopted the ESX rulebook.
4.3 Increased capacity of & collaboration between market participants / (Governments, private sector and civil society	3 ESX Academy capacity building platform roadshows to enhance take up/utilisation/ enrolment / 50 capacity building/collaboration activities / 15, Capacity building on tribunal / 4, capacity building sessions on Islamic Capital Markets to (NBE, MOF, ECMA, ESX) / 1, Risk Based Supervision training for ECMA	Moderately exceeded, scoring an ‘A+ / 4 ESX Academy capacity building platform roadshows to enhance take up/utilisation, resulting in a surge in registrations, with ~10% (1,500) of the total trainees (17,712) signing up after the events. / 67 workshops/collaborative platforms conducted: focused primarily on IFRS adoption (of green finance standards S1 & S2), training was delivered to key market players including the Accounting and Auditing Board of Ethiopia, ECMA, accountants and auditors, ESX, Ethiopia Investment Holdings (EIH), and private companies / Delayed. A directive must undergo consultation before approval, so the capacity building extended Q1 2026 / 8, capacity building on Islamic Capital Markets conducted by UK Islamic Finance experts IFAAS to NBE, MOF, ECMA, ESX, CSD; 8 financial institutions trained on Shariah-complaint monetary instruments and the Sukuk white paper findings, with a specific focus area on overnight lending and deposits and interbank money markets. / 1, Risk Based Supervision training for ECMA: currently, the ECMA employs a compliance-based supervision model. Capacity building supported ECMA on risk-based supervision to enhance the supervisory and market oversight capacity of the regulator.
4.4 Collaboration between market participants / Policy influences and taught leadership	Initiate platforms to facilitate effective governance of the Capital market.	Met, scoring an ‘A’ – indicators meeting target. / Securing and facilitating a new Capital Market Masterplan (CMMP), including – with FSDA – convening steering and technical committees. / In addition, FSD Ethiopia has secured a central role in donor coordination within Ethiopia’s financial sector development space, acting as the convenor of development partners (2 meetings conducted).
4.5 Enhanced capital market activation with new assets and products ready to list/launch	Supporting 5 assets to the IPO Clinic / Debt transaction facility launch	Moderately exceeded, scoring an ‘A+ / 7 assets supported to be admitted to the IPO clinic. / The Facility has been launched and call for applications is out.

Briefly describe the output’s activities and provide supporting narrative for the score
Capital markets are essential to strengthening Ethiopia’s investment and export competitiveness. By providing long‑term, risk financing beyond the banking sector, capital markets help firms in priority and export‑enabling sectors invest, expand, and innovate. This directly complements EIAF II’s objective of improving the enabling environment for investment, SOE reform, and export‑led, outward‑oriented growth.

EIAF II, through its implementing partners FSD Africa (FSDA) and FSD Ethiopia (FSDE), has played a pivotal role in shaping Ethiopia’s capital market from inception. Working closely with the Ethiopia Capital Markets Authority (ECMA), Ethiopia Securities Exchange (ESX), the National Bank of Ethiopia (NBE), and other stakeholders, FSDE provided technical assistance in market architecture design, policy formulation, and institutional capacity building—laying the foundation for a transparent and functional market.

Over the past year, Ethiopia’s capital market has shifted from achieving eye‑catching mobilisation milestones—most notably last year’s launch of the Ethiopia Securities Exchange—to undertaking the hard but essential work of turning frameworks, regulations, and institutional structures into practical, operational reality. And the foundational work supported by EIAF II and FSDE is beginning to bear fruit: active T-bill trading and interbank transactions exceeds ETB 1 trillion (£4.67 billion); there are two private listings (Wegagen Bank and Gadaa Bank) and Ethio Telecom’s partial SOE listing; 5 investment banks, 8 transaction advisors, and 2 securities dealers are now licensed intermediaries; 70 share registration applications have been submitted to ECMA; and work is underway to finalize regulations enabling foreign portfolio investment, signalling readiness for international participation.

FSDE’s work this year reflects those “hard yards”. Key achievements include pivoting support to activation of the Central Securities Depository – the post-trade clearing and settlement function (arguably the most critical function in the ecosystem), finalisation of the crowd‑investment platform, the launch of the IPO clinic and debt transaction support facility to encourage and coach new players to the capital market, with 7 assets now in the IPO pipeline, and ensuring policy adoptions by key institutions such as ECMA, NBE, and market players —ECMA adopted the recommendation from the FSDE’s thematic CM instruments scoping exercise to establish an Islamic Capital Market Unit; NBE adopted the recommendation to issue a Sovereign Sukuk following the recommendation of the scoping study on Islamic Finance. These have been concrete steps translating groundwork into market functionality. Yet sustained support is needed for the capital market to mature on a credible and investable foundation, particularly as challenges in investor confidence, issuer readiness, and market depth persist.

FSDE itself has also evolved significantly under the programme’s guidance: last year focused on internal corporate strengthening under strong new leadership; this year has been about building on that platform to create an independent, local FSDE – separate to but in close partnership with sister agency FSDA – with a clear strategic direction and sharper focus on a few high‑impact priorities that will meaningfully accelerate market activation and long‑term system development. The programme team have steered these efforts – initiating and guiding both the process of separation from FSDA and the new 3-year strategy review currently underway to align with HMG’s upcoming 3-year Spending Round. Internally, the programme has conducted a comprehensive Due Diligence Assessment (still draft) and is preparing an Accountable Grant Agreement which will establish strong programme management foundations for the coming 3 years with FSDE.

Looking ahead, the next phase of work requires sharpening focus on a smaller, more strategic set of catalytic priorities that can unlock capital at scale. On the product side, FSDE’s expanding climate‑finance portfolio positions it to drive the emergence of thematic bonds—green, climate, sustainable, and gender‑aligned instruments—leveraging its climate‑finance resource centre and earlier feasibility studies. COP32 next year will be a key milestone. On the investor side, FSDE’s support in developing a national pension‑fund investment strategy is pivotal: diversifying pension assets into corporate bonds, equities, real estate, and infrastructure can unlock the country’s most significant pool of long‑term capital. At the same time, improving market credibility, transparency, and deal preparation will be essential for attracting foreign institutional investors into Ethiopia’s emerging asset classes. Finally, accelerating real deal flow—both equity and debt—through stronger issuer preparation, transaction support, and pipeline development remains the most immediate lever for demonstrating market functionality.

To enhance this work, FSDE may require an investment‑capable function to seed early transactions, de‑risk issuers, and mobilise co‑investment. This would enable FCDO to gradually pivot from a pure donor role toward a catalytic investor approach—deploying capital in ways that crowd in private investment, unlock export‑driven growth and reinforce a resilient, inclusive, and climate‑aligned economy consistent with EIAF II’s Theory of Change.

FSDE now serves as the de facto convener of development partners in Ethiopia’s capital market, ensuring alignment and synergy. Strategic priorities include introducing innovative instruments—corporate bonds, green bonds, gender bonds, and Sukuk—while promoting governance and disclosure standards. These efforts align with Ethiopia’s reform agenda and FCDO’s vision to position the UK as an early investor and strategic partner, leveraging UK expertise and blended finance to unlock growth opportunities.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the AR period, FSD Ethiopia refined its Theory of Change (ToC) from a high-level framework encompassing both organizational pillars to a more targeted model centered on the financial markets pillar. The updated ToC explicitly identifies key challenges hindering capital market development in Ethiopia including regulatory gaps, limited infrastructure, limited private sector financing, and inadequate market information and seeks to address them primarily through targeted technical assistance programs. It clearly articulates the impact pathway designed to foster a resilient and inclusive green economy by strengthening market infrastructure, mobilizing sustainable and export- enabling investments, and building the institutional capacities required to improve private sector participation aligning with the transformation focused outcomes of EIAF II ToC.
To complement this evolution, FSDE is undergoing a strategic review process that will further sharpen the ToC. The independent MEL provider currently being procured for EIAF II will have a focus on FSDE – that inception period will be an important opportunity to further refine and strengthen FSDE’s ToC and especially logframe to ensure this is fit for purpose over the next 3 years.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

No.	Recommendation	Progress/comment
Last year’s (2025) recommendations
1.	Work with the FSDE to clarify and enhance the strategy for FSDE’s capital markets and climate finance pillars, including developing a clear vision and meaningful measures of success, to be evaluated and adapted through monthly FCDO-FSDE meetings.	In progress – The substantive review of the FSDE ToC and Logframe largely achieved this recommendation. However, further work is required on the Financial Markets pillar 3-year strategy, and on shaping the new Climate Finance pillar.
2.	FSDE to develop a VFM strategy to reduce cost drivers and/or maximise value of international roadshows/events etc. In particular, the amount spent on international travel (flights, accommodation and expenses) should be carefully managed by FSDE and the programme team – there should be a higher bar for approving this type of spend	In progress – FSDE has improved its VFM approach, including a more rigorous application of its procurement policy to ensure competitive bids, improved benchmarking including using FSDA comparisons, and close consultation with FSDA on specialized procurements. More scrutiny was given on travel and conference costs this year. However, these do not yet constitute a strategy, with FSDE still relying on FSDA’s VFM strategy.
3.	Programme team and FSDE to agree longer-term (up to 4-year) outcome-level and output targets and milestones that enable better tracking of progress against strategic goals / Prioritise ecosystem development interventions in FSDE’s future strategy and programming, built on a deeper understanding of the political economy conditions. Initially to be completed by April as part of budget/pipeline approval for FY 25/26. Further refining to be considered throughout the year.	In progress This has been prioritised, and a refreshed strategy is being conducted by an independent third party. This will be complemented by an additional strategic diagnostics/ assessment that will advise FSDEs short- and medium-term interventions. / KPIs for the next three years will be agreed and specified as an output of this strategic diagnosis document. / Political economy analysis (PEA) will be included in this diagnostic.
4	Regular check-ins with FSDE and FSDA on progress along the roadmap towards FSDE independence. Programme team to develop internal plan to ensure necessary actions are taken to prepare for direct FSDE oversight, including due diligence assessment.	Achieved / FCDO team has finalised the internal due diligence assessment (DDA). FCDO, FSDA and FSDA have done regular check-ins on progress towards independence.
5	Programme team to develop a plan with FSDE and co-funder Gates on resourcing the climate finance pillar for a trial period, say over 18months.	In progress FCDO and Gates have reached an agreement to resource the climate finance pillar.
6	Early planning before the start of the year is essential to ensure that projects are completed within the set timelines. To be completed by April as part of budget/pipeline approval for FY 25/26.	Achieved. This has been achieved, and budget execution rates have significantly improved.
This year’s recommendations
1.	Building on its new position as donor coordinator, FSDE should continue its effort to ensure financial sustainability through exploring additional funders beyond FCDO and Gates Deadline: Mid 2026
2.	FCDO needs to explore innovative modalities (including capital) to enable shift from donor to key investor. Deadline: 1st Quarter or latest by Mid 2026
3.	Three-year/ medium term KPIs that are aligned with the existing results framework/LF need to be agreed between FCDO and FSDE/A as a result of the refresh strategy and 3rd part MEL review. Deadline: April 2026
4.	FSDE need to develop its own robust risk register and refresh its VFM matrix accordingly (separate to that of the FSDA). Deadline: 1st Quarter of 2026

Output Title	Increased mobilization and improved access to climate finance;
Output number:		5	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	Yes, down from 20% last year.

Indicator	Milestone (this review)	Progress
5.1 Greater access to global climate funds	Green Climate Fund Simplified Approval Process (SAP) project submitted and approved / Adaptation Fund project submitted and approved / Full SAP project proposal submitted and approved, including Environmental and safeguard report, Gender assessment report, Financial and economic analysis report	Moderately did not meet expectation (B) due to delay with 2 outputs. / GCF SAP ($30m) submitted (approval targeted June 2026). / Adaptation Fund ($10m) approved. / The zero draft of the feasibility study and economic analysis has been prepared as part of the mandatory annexes for the USD 250 million Green Climate Fund medium-sized project proposal.
5.2 Improved transparency and reporting on domestic public investment on climate actions and better tracking of international climate finance flows to Ethiopia	Climate and disaster budget tagging and tracking fully integrated in Integrated Financial Management Information System (IFMIS) / Climate and disaster risk integrated into Integrated Budget and Expenditure (IBEX) system of regional states / Climate and disaster risk budget tagging and tracing system for non-state actors established	Met, scoring an ‘A / Climate budget tagging and tracking integration into IFMIS and is now fully operational. / A Climate Change & Disaster Risk Management Budget Tagging and Tracking Directive has been developed and disseminated to all federal budgetary institutions. / 55 experts from eight federal entities implementing the Climate Resilient Green Economy (CRGE), along with relevant departments from the Ministry of Finance (MoF), participated in workshop on Climate Change & Disaster Risk Management budget tagging and tracking. / CRGE sector institutions have developed profiles of projects they are currently implementing, to support better planning, coordination, and reporting. / MoF has initiated the development of a new system to replace the Aid Management Platform (AMP), which will also incorporate climate budget tagging and tracking capabilities. Discussions have commenced on how Civil Society Organizations (CSOs) can utilize the new system.
5.3 Carbon markets legal framework created/enhanced	Article 6 Steering Committee established. / Architecture for REDD+ Transactions – The REDD+ Environmental Excellence Standard (ART-TREES) documentation developed. / 3 consultations on Carbon Market Proclamation with Federal Government, regional Government and non-sate actors. / Draft carbon Market Proclamation. / Develop Roadmap Implementation framework for carbon market.	Moderately did not meet expectation (B) / First draft of a Carbon Market proclamation (only English); final draft expected to be delivered by end of contract. / ART-TREES registration, document prepared. / Delivered Carbon Market Policy Implementation Roadmap for Ethiopia. / 2 trainings on Coordination of National Carbon Trading under Article 6 of the Paris Agreement delivered by GGGI CPU experts; delivered on April and September 2025. / 1 CRGE Forum meeting facilitated / Article 6 Steering Committee established, but not functional.

 Briefly describe the output’s activities and provide supporting narrative for the score.
For Ethiopia to achieve its global climate commitments it needs to generate a 12-fold increase in climate finance by 2030. This output aims to support Ethiopia to secure more climate finance flows and lay the groundwork through strengthening public information management systems, which is a prerequisite to access global climate funds. In turn, this funding will be deployed by GoE – including through Joint Ventures, PPP and other mixed modalities – for climate finance projects in Ethiopia, improving investment management and, where relevant, the enabling environment.

This component, initiated in June 2024, has three core pillars -
1. Enhance access to climate finance through public funds
2. Enhance transparency and reporting on climate finance in Ethiopia’s national budget
3. Support the establishment of carbon market activities in Ethiopia (voluntary and compliance)

The original one-year time frame was extended three times due to delivery delays. During this AR period, the implementing partner, the Global Green Growth Institute, finalised the following outputs:
1. Approval for Adaptation Fund proposal and finalising a large feasibility study for the $250m GCF proposal.
2. Finalisation of implementing a digital budget tagging and tracking system across key line ministries to enhance reporting on climate finance flows.
3. Draft proclamation on carbon markets, and final carbon market strategy.

Notable achievements including the significant progress made on climate finance mobilisation. In this Annual Review period, $10m was leveraged with our funding through an approved Adaptation Fund Proposal. This is in addition to the $45m GCF proposal, which was approved in the last reporting period, taking the total fund leverage to about $55m through climate funds. Another $30m climate finance proposal is under review, and likely to be approved within 2026. With our support, the GoE is currently developing a $250m GCF proposal; the feasibility study, which is the core of the proposal, is now near completion. And we assess there is a high chance this proposal will also come through at the GCF next board meeting in November 2026.

Transparency and financial tracking have advanced considerably, particularly the Budget Tagging and Tracking Directive having been issued and disseminated as well as the IFMIS tagging integration. Governance and carbon market readiness have also progressed. The roadmap implementation framework has been completed, and a new carbon markets proclamation drafted. This process will be finalised at the end of the MoU period (March 2026). The draft text for the proclamation will then be handed over to the MoPD.

While the project’s overall output was impactful, delivering on a long-term ambition of the GoE to be accredited to a higher GCF window (with a first large GCF funding proposal almost finalised), and representing good VFM through a high cost-benefit-ratio, the project was severely delayed in delivering outputs within the original timeframe – particularly due to delays with the carbon markets proclamation. It required three consecutive no-cost extensions. The largest deliverable—the GCF medium-size proposal—remains incomplete and is now scheduled for submission by March 2026. These delays, coupled with reliance on extensions for activities largely within GGGI’s control, indicate that timely performance has not fully met expectations.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
During the past year, the GGGI budget was reduced by 11%. The budget reduction was a reflection of wider ODA reductions and resulting reprioritisation within the programme. The impact on the project component was minor, changing the scope of the information management interventions (only federal ministries).
In addition, three no-cost extensions were awarded due to severe delays in project delivery, particularly on the GCF feasibility study and the carbon legal framework. Both were key deliverables to unlock development impact, so it was deemed strategic to extend the time frame at no cost. Both will be completed by the end of the contract period by March 2026.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No.	Recommendation	Progress/comment
Last year’s (2025) recommendation
1	Consider a multi-year agreement with GGGI and design a longer-term project component, including more ambitious and strategic support. To start with the FY 25/26 and be completed by April 2025	Comment: A multiyear agreement was considered and decided against due to ODA budget cuts, underperformance and a need to reprioritise across the portfolio.
2	Develop next steps for voluntary and compliance carbon market initiatives in Ethiopia, By April 2025.	Achieved: The roadmap implementation framework for the carbon market has been completed, and the Carbon Markets Proclamation has been drafted.
3	Enable GGGI to enhance donor coordination on carbon markets in Ethiopia. By October 2025	Comment: The context has shifted, and the MoPD together with the co-chairs of the CRGE Forum have taken more interest in donor coordination. Therefore, GGGI was not seen as best placed to deliver this.
4	Accelerate the recruitment of consultancy firms to finalize feasibility studies and streamline proposal preparation for new projects, already with an extended contract in mind.	Achieved: A USD 30 million GCF SAP proposal has submitted. A USD 10 million Adaptation Fund proposal approved. / In progress: A USD 250 million GCF medium‑sized proposal is under development.
This year’s recommendations
5	FCDO should closely monitor progress on remaining deliverables during the final no-cost extension period, ensuring timely completion of critical outputs and backed-up by detailed monthly reports from GGGI to ensure timely delivery/reporting.
5	FCDO should collect and consolidate all project documentation, including legal drafts, feasibility studies, financial analyses, training materials, and meeting reports, to create a comprehensive record for closure and future reference.
6	FCDO should prepare a detailed end-of-project report capturing achievements, lessons learned, and strategic recommendations for future programming beyond March 2026.

Lessons learned:
Repeated no-cost extensions signal weak programme management and planning. While some delays were justified by external factors—particularly consultant recruitment—the fact that slippage continued even after consultants were hired indicates internal issues and inefficiencies with the delivery partner. Persistent delays in sharing key documents and progress updates hampered FCDO oversight. We addressed poor programme management through:
- Commissioning an independent audit - a critical corrective measure. The audit confirmed that programme management standards were below expectations and highlighted systemic weaknesses in financial compliance, documentation, and internal controls. This demonstrated the audit’s value as a governance tool.
- In response to the audit findings, the FCDO climate team embedded regular orientation and guidance into day-to-day engagement and monthly programme management meetings with GGGI, improving the quality of programme deliverables. FCDO also adopted a monthly financial reporting timeline, enabling closer tracking of expenditure and strengthened financial oversight. Future programming should include stronger planning, realistic timelines, and clear accountability to avoid similar situations.

Recommendation: Multi-year planning and programming mitigates risks around resourcing and delivery delays. Setting realistic timelines for milestones and challenging delivery partners on the ability to deliver will help avoid future delays. Accessing more climate finance remains vitally important for Ethiopia, especially in the context of reduced ODA-budgets and Ethiopia’s upcoming COP32 Presidency. Therefore, having a supplier on hand, which can help with direct delivery and respond to asks on technical assistance would be very beneficial for the UK’s support to the COP32 effort. For this work, we will consider a mini-tender to ensure best VFM and delivery outcomes.

Recommendation: We should make the most of the considerable opportunity presented by Ethiopia’s upcoming COP32 Presidency to deliver ambitious objectives on climate and climate finance. We should increase our bilateral engagement on climate finance as we seek to influence the multilateral finance elements of COP and links across to the UK’s concurrent G20 Presidency. Moreover, we should be incorporating objectives on climate finance across the whole of the EIAF II programme.
## D: VALUE FOR MONEY
Overall, the EIAF II programme remains good VFM, with the potential to be excellent VFM if its systemic outcomes continue to be realised. The programme targets major economic reforms in Ethiopia – the best buy in economic development according to FCDO’s Best Buys research. Such outcomes are, by their nature, lumpy and will not occur consistently across the programme lifecycle. Last year’s review documented major achievements under EIAF II, including significant contributions – acknowledged publicly by Ethiopian Ministers – on macroeconomic and capital market reform, which have been critical to improving the enabling environment and generating the exports and investment needed for growth. The sustained implementation of these reforms with EIAF II support through this reporting year, along with mobilisation of support for new reform areas, strengthens EIAF II’s VFM: export receipts have doubled year on year and the IMF growth projections for Ethiopia are multiple percentage points above the no-reform counterfactual. This demonstrates the programme’s overall effectiveness and, given its relatively small spend (less than £7m this year), strong VFM.

EIAF II suppliers have continued to use the VFM matrix created for the programme last year, providing data for comparison and evaluation across the programme, for example average day rates of international and local consultants, equivalent day rates for key staff roles, management fees/non-programme associated costs, and overheads. More active VFM management using this matrix is required at component level, however, including benchmarking against comparable development programmes in Ethiopia.

Economy: EIAF II is driving good economy for the programme’s key costs, relative to expectations. Across the programme, by far the largest cost is technical assistance in the form of hired consultants. For FSDE for example, EIAF II’s largest component and delivery partner (this year), ~63% of the total programme cost was procured consultants. The PIAM facility is set to become the largest EIAF II component and spends almost entirely on consultant TA (core team and flexible pool). And this is the primary modality and cost across the other components as well.

The EIAF II business case identified expected day rates based on benchmarking of similar programmes and relevant experience in Ethiopia – set out below:

Team Leader	£650 – 1000
Deputy Team Leader	£450 – 750
Sector Lead	£600 – 1000
Senior Technical	£700 – 900
Mid-level technical	£585 – 700
Junior Technical	£300 - 525

While the Business Case rates were illustrative and focused on a design most closely aligned to the PIAM facility (which could warrant higher rates), day rates for the significant majority of comparable roles across all components (including PIAM) are actually below the lower bounds identified in the Business Case. All comparable roles – with one exception – are within the upper bounds identified.

FSDE conducted benchmarking against other capital markets work in Ethiopia but also against comparable work of sister FSDs across the region. They have continued to prioritise competitive procurement (over single sourcing) and, building on last year’s recommendation for a more coherent approach to procurement, use framework agreements with pre-qualified suppliers, which has contributed to faster sourcing, reduced administrative burden, and discounted pricing. In addition, FSDE introduced a structured method for assessing consultancy pricing in line with the programme level VFM matrix – meaning downstream consultants are now required to provide a clear breakdown of daily rates and estimated days of work, ensuring transparency, comparability, and adherence to reasonable costing principles.

For the PIAM facility, the programme team chose a direct procurement route using the FCDO’s Global Development Delivery Framework, which helped constrain economy day rates and contract terms. And, since mobilization, the tier one partner, Cowater, has continued to drive down costs with the downstream consortium – in particular, additional scrutiny and constructive challenge has ensured the ‘right-sizing’ of proposed task orders: nearly all live projects are being delivered for around half of their original budgeted cost. This is leading to a recalibration (lowering) of downstream partner input proposals, freeing up resources for other work.

Regarding the embedded advisers, contracts were moved from FSDA to FSDE to reduce tax liability (FSDA’s withholding tax exposure in Kenya is double the liability of Ethiopia) and thereby reduce the total contract values. The one exceptional case that exceeds Business Case indicative rates was recently presented for detailed consideration to the Embassy’s senior leadership and a decision taken to review the contract at FY-end.

Effectiveness: of the programme’s 13 output indicators, 9 met (4) or moderately exceeded (5) expectations. Considering impact weightings, 65% of outputs scored an A or higher, 35% scoring a B (partially meeting expectations). Underperformance was concentrated in the PIAM component, largely due to unforeseen political challenges, and in the climate finance component, due mostly controllable delivery delays and programme management deficiencies.

The programme is broadly on track to achieve its outcome and outcome indicators. Where components are more advanced, like capital markets and trade and logistics, there is greater confidence – relationships, deliverability and outcome trajectories are clearer. On the other hand, PIAM is new and still building relationships, credibility and direction.

Overall, successes in key reform areas where EIAF II has prioritised its TA indicate the programme is performing effectively. The macro reforms, supported by EIAF II over successive years, are progressing well; with glowing recent reviews from both the IMF and World Bank, unlocking further disbursements. In the capital market, the most significant area of support in recent years (in programme resource terms), the active T-bill and interbank money market, hosted by a successful ESX, as well as significant and growing appetite for market participation (based on IPO pipeline) shows our investments in the market framework over recent years are paying off; and adoption of recent recommendations (e.g. on Islamic finance/capital markets at both ECMA and NBE) show TA is converting into concrete change. For the year ahead, new capital market product development outcomes will be a key test.

How effective EIAF II’s climate finance and trade/logistics components are remains to be seen. GGGI was highly effective in leveraging additional climate finance for the GoE. For this programme period, $10m was leveraged through an approved Adaptation Fund Proposal. This is in addition to the $45m GCF proposal, approved last reporting period. Another $30m climate finance proposal is under review, and likely to be approved within 2026. If the $250m GCF proposal the programme is also supporting succeeds (likely at GCF’s next board meeting in November 2026), our £1.3m funding to GGGI will have leveraged a total of $335m over 18 months (this reporting year it is $800k: $10m). However, carbon markets legal framework finalisation and adoption is a key TA unknown. As are logistics reform and logistics operator performance metrics under the TMA component.

The programme team has initiated cross-mission work on ensuring that TA, especially via embedded advisors (a key modality under PIAM), has sustainable impact beyond the life of the TA. This draws heavily on FCDO HQ work on ‘Smart TA’ and applies it in an Ethiopia context and gears it towards the UK’s new Africa Approach. The programme team are now embedding these principles of ‘smart TA’, including strengthening – rather than displacing – endogenous capability in our GoE counterpart ministries, into all programme components. We are using the upcoming contract review points for existing embeds to incorporate KPIs on institutional capacity strengthening alongside embed TA duties and tightening the focus on system strengthening/reform. This work acknowledges, though, that for TA to be properly owned by Government counterparts, we may sometimes need to compromise on reporting requirements – for example, where outputs are commercially or politically sensitive. In such a context, the best proxy for effectiveness is change in the outcome environment, as documented above.

Efficiency: the majority of EIAF II outputs for the review period have delivered the expected outputs within time and budget, indicating good efficiency across the programme. The biggest exception to this was GGGI’s work on carbon markets, which required a triple-no-cost extension to allow more time for the work, indicating poor planning and lower efficiency than FCDO had anticipated. The amount of management time this generated also represented an inefficiency. Corrective actions were taken however, requiring an external audit of GGGI and, ultimately, a decision taken by the programme to wind down this partnership at the end of this FY.

For FSDE, significant variances were observed mainly within programme budgets (47%), reflecting timing shifts, activity redesign needs, and external factors affecting implementation schedules - mainly around stakeholders’ competing commitment and capacity. The climate finance strategy has been delayed for months even after IC and board approval. For AABE reform, the project end date has been rescheduled for end of January as AABE to allow team to review deliverables. This implies the need for improved forecasting as well as mitigation plans for effective utilization of planned budget by FSDE.

Using EIAF II’s nascent VFM matrix, the programme team continued to monitor and put downward pressure on non-programme attributable costs (NPAC)/admin fees of our partners to maximise FCDO funds for programme delivery. For example with FSDE this included three key workstreams: 1) driving the separation process from FSDA, which will save EIAF II 3-5% of admin fee that FSDA claim as the tier 1 partner, on top of FSDE’s NPAC; this is set to conclude by the end of the FY; 2) investigating and revising the NPAC split between FCDO and co-funder Gates; the MoU states that NPAC/admin fees will be shared equally between the funders – given Gates’ larger programme budget for their work on Financial Inclusion, in practice this meant that FCDO took on a higher share of admin fees relative to the programme budget of each partner. FSDE’s overall NPAC has remained below the 15% guideline set by both funders; but this has not been apportioned according to programme inputs and so the proportion of FCDO funds to FSDE going to admin fees has been slightly greater than 15% (and Gates’ lower) – although, this is an improvement on last year’s figure. We now have a three-way agreement that admin fees will represent no more than 15% of each funder’s programme contributions, beginning from next FY. And 3) the introduction of framework agreements for procurement, to reduce the amount of staff time bound up with individual procurements.

The PIAM component is still designing its KPIs, but these will have an emphasis on efficiency in GoE investment management. For now, PIAM promotes efficiency through its flexible facility model, which enables rapid, nimble mobilisation of targeted TA through a partner drawdown process. The average time to draw down a partner has been under 21 days which is good given the size and scale of projects and the profile of our implementing partners. The team has been able to avoid long-term idle capacity by agreeing efficient drawdown protocols and pre-agreed rate.

Equity:
Last year’s recommendation to devise a GESI strategy for EIAF II in line with the mobilisation of the new PIAM facility and third-party MEL provider still holds. This will be a priority during the inception of the new MEL contract currently under procurement.

FSD Ethiopia strengthened its approach to gender and inclusion by embedding gender considerations across programme design, budgeting, and implementation. A dedicated Gender Team now supports project design to ensure intentional integration of gender objectives, and all technical reports are required to include gender-disaggregated data. FSD Ethiopia is also preparing to support Enat Bank’s debut gender bond, and remains committed to promoting sustainable, gender-responsible financial instruments that expand access for underserved groups.

Women in Capital Market Training / FSDE organised a workshop on how to better serve women’s access to finance needs through the capital market. A call to action highlighting the potential of Ethiopia's emerging financial markets in addressing barriers that limit women's economic participation was prepared. One of the recommendations of the call to action was to accelerate capacity building efforts to equip women-owned SMEs with the essential financial management skills and knowledge needed to expand their businesses. / Based on the recommendation, FSDE designed a targeted capacity building program to help market participants better understand gender integration and women’s empowerment in the financial sector, with a strong focus on women’s participation in capital markets. The Call to action can be accessed through: https://fsdethiopia.org/wp-content/pdf/FSD_call_to_action.pdf

GGGI is addressing equity by 1) ensuring inclusive recruitment of consultants as well as gender-balanced training participation; 2) the programme output is establishing socially-equitable resource distribution. Currently, Ethiopia does not have an equitable benefit-sharing mechanism for income from carbon credits. The GGGI work will be instrumental in providing technical assistance to the Ethiopian government to devise such an inclusive and socially equitable benefit sharing mechanism. This will ensure future money generated from carbon credits will benefit local communities, the regions as well as the federal government.

E: RISK

Overview of risk management

Following a recent review of the risk register, the programme is assessed to have a moderate overall risk rating, encompassing thirteen identified risks, including one severe, one major, seven moderates, and four minor residual risks. The programme maintains both an offline and an online risk register accessible via AMP, and suppliers also maintain their own registers, which are updated at least quarterly. The programme team holds monthly internal meetings to assess risks and update mitigation measures, with the most recent update completed in December.

Table below shows that all residual risks, except for the People risk (after mitigation), remain within the programme’s risk appetite.

EIAF II risk profile

Risk category	Number of Risks	Risk Ratings	Programme risk Appetite	FCDO Risk Appetite	Risks Outside Appetite
Strategy & Context	1	Moderate (1)	Receptive	Receptive	0
Safeguarding	1	Moderate	Cautious	Receptive	0
Policy & Programme Delivery	7	Major (1), Moderate (3), Minor (3)	Receptive	Receptive	0
Reputational	1	Minor	Cautious	Cautious	0
Public Service Delivery & Ops	1	Moderate	Cautious	Cautious	0
Financial & Fiduciary	1	Moderate	Cautious	Receptive	0
People	1	Severe	Cautious	Cautious	1
Other	0	-	N/A	N/A	N/A
Total	13

Distribution of residual risks in relation to appetite

Overall, the programme’s risk is increasing – particularly with the launch of the PIAM facility and the often-sensitive issues this seeks to engage on, and the relationships with senior leaders in the GoE it needs to develop and maintain. This raises reputational/political risk for the programme, whether through perceived conflict of interest (for example where we have a vested commercial or development finance interest) or poor performance or poor relationship-management. This should be added to the risk register and managed carefully by the programme team and Development Director.

The main people risk relates to the programme team experiencing significant stretch due to the growing scale and complexity of the programme and gaps created during team transitions. To address this, mitigation measures have been introduced, including moving to a whole-of-team resourcing model, with lead advisers for each component, as well as cross-cutting advisory input from sectoral/thematic leads; roles and responsibilities are clearly defined, and effective cross-team working methods are being introduced to ensure comprehensive coverage. Additional economic resource was also brought into support the mobilisation of MEL and the new facility. While these measures have reduced the severity of the residual risk, the increasing complexity of the programme and ongoing staff transitions mean this risk remains outside the programme’s risk appetite. It has been escalated at the team level, and efforts continue to reduce its impact through workload prioritisation and enhanced coordination.

Another major risk arises from delivery delays in mobilising the programme’s main PIAM facility. Although inception is now nearly complete and operations have commenced, challenging bilateral dynamics between the UK and the Government of Ethiopia earlier in the year prevented the formal introduction and launch of the facility, resulting in delays. The inception phase, originally planned for four months, has been extended by several additional months, with reliance on informal networks to deliver outputs. Despite mitigation measures such as informal engagement channels and timely communication with the Government of Ethiopia, the residual risk remains high.

A further risk arises from political developments in Ethiopia and the wider Horn of Africa, including conflict in Oromia and Amhara regions, Ethio-Djibouti relations, the Ethiopia-Somaliland MOU, the Ankara declaration, and continued tensions with Somalia and Eritrea. These factors could slow regional engagement and cross-border trade and logistics activities, making it difficult to achieve programme outcomes. Mitigation measures include interventions through TMA, with its offices in Addis Ababa and Hargeisa maintaining awareness of political developments and providing regular reporting to FCDO. TMA retains its technical focus on trade facilitation, and monthly reviews with FCDO Ethiopia are held to update on trade and logistics issues. The programme also collaborates closely with the wider Embassy team and other embassies across the Horn to develop approaches aligned with Ministerial guidance to help de-escalate tensions.

There is a risk that advisory support may be sub-standard or fail to respond to the Government of Ethiopia’s requirements, which could undermine programme objectives and damage FCDO’s credibility. To mitigate this risk, the programme team is mobilising downstream partners under PIAM to accelerate delivery and introduce innovation; while also developing creative approaches to idea-generation and governance that ensure the facility is co-owned with GoE and that advisory support can track evolving GoE needs.
Safeguarding risks involving delivery partner staff—such as exposure to or perpetration of harassment, abuse, or other forms of social harm—could have damaging human consequences, and result in serious reputational and operational consequences for the programme. This risk increases as the programme seeks to embed more advisers in GoE Ministries, which typically involve exposure to certain power dynamics at the same time as reducing programme oversight. Mitigation measures include reinforcing safeguarding obligations with all partners during monthly meetings, maintaining regular communication on whistleblowing channels, engaging more closely with higher-risk partners, and screening out high-risk requests from the Government of Ethiopia.
There is a moderate risk to ensure that the programme delivers on inclusion and poverty reduction objectives. EIAF II’s primary focus on systemic economic reforms (particularly the PIAM facility), means that this link can be indirect. This should be examined further by the independent Monitoring, Evaluation and Learning provider and through fuller assessment of the programme’s Theory of Change. This assessment should then inform decisions about selection of programme activities, especially as we adapt to lower ODA budgets in the coming years.
Finally, a moderate risk arises from the programme’s support for domestic economic actors, which could inadvertently reinforce Ethiopia’s anti-reform agenda. For example, providing support to certain state-owned enterprises or private logistics providers could – or could be seen to – contradict the programme’s objectives and undermine efforts to promote market-oriented reforms. To mitigate this, the programme continually tests the theory of change that supporting domestic entities contributes to the reform agenda by building confidence in their ability to compete internationally, while maintaining close engagement with beneficiaries and the Government of Ethiopia to adapt the programme approach in line with the evolving reform narrative.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Financial Performance During the Review Period
During the review period, a total of £6,779,347 was disbursed to EIAFII suppliers. The largest share went to FSDA/E (FSD Africa and FSD Ethiopia combined), which received £3,178,000 (47%), followed by TMA for corridor efficiency work with £1,300,272 (19%), and climate-related components—GGGI and CAPE Ethiopia—with £1,100,075 (16%). For a detailed breakdown of all disbursements, please refer to Table 1 below.

The programme performed strongly in utilizing its allocated budget, with limited risk of underspending. However, its flexible nature meant additional funds were needed for activities not planned at the start of the financial year, such as the High-Level Business Forum organized by UNDP and the CAPE Ethiopia. To finance these activities, additional funds were secured from the office budget.
Most of the programme’s implementing partners also demonstrated strong financial management throughout the review period. They provided us with forecasts and workplans at the beginning of the financial year, communicated any forecast revisions well ahead of payment processing cycles, and avoided unnecessary advance payment requests, such as requesting payments while having sufficient funds, before fully utilizing previous disbursements, or without planned activities.

We held periodic programme and financial management meetings with these suppliers, bi-monthly or at least monthly, to discuss areas such as work progress, revised workplans, payments, fund utilization, and potential spending or fraud risks. This proactive approach from both sides enabled timely execution of payment requests and ensured compliance with the variance threshold set by FCDO. The exception to this strong performance was GGGI, which struggled to spend funds as per their initial agreed plan and finally led to the carryover of unutilized funds to the next financial year, creating the issue of prepayment.

The ODA budget pause started during the last months of the previous financial year and ran into the first quarter of the current financial year, posing challenges. We could not access and were not certain about the current financial year’s budget until July 2025, which led to delays in planned activities, inability to make payments to our suppliers, except for a few payments with business-critical needs that were approved through exemption, and inability to make project time and cost extensions until the pause was lifted.

For instance, FSDE needed funds to operate in the very first month of the current financial year. We secured special approval to release funds from the previous financial year for use at the start of the current year. We covered their costs for the initial months until the exemption approval was granted and payments were processed. Without this intervention, FSDE would not have been able to operate, which could have had serious implications for its staff.

Table 1. Component Expenditure Breakdown

Project	Component Code	Spend (£)	% of Total	Implementing partner	Status
Financial Sector Deepening	300588-103	3,178,000	47%	FSDA &FSDE	Ongoing
Enhancing Corridor Efficiency in Horn of Africa	300588-104	1,300,272	19%	TMA	Ongoing
Climate Finance Access for Ethiopia	300588-401	642,075	9%	GGGI	Ongoing
CAPE Ethiopia	205226-407	458,000	7%	FSDA	Ongoing
Public Investment & Asset Management.	300588-101	364,000	5%	Cowater	New/Ongoing
Development Partnership Group	300588-405	87,000	1%	UNDP	Completed
Ethiopia Reform Support MDTF	300588-102	750,000	11%	World Bank	Ongoing
Total		6,779,347

Programme Delivery Performance by Component
Financial Sector Deepening (FSD Africa and FSD Ethiopia).

FSD Africa and FSD Ethiopia delivered key activities under the financial sector reform portfolio, supported by our four advance payments totalling £3.18 million. Of this amount, £614k, or 19% of the funds, was used for embedded advisers managed by FSD Africa, while £2.56 million, or 81%, supported capital markets work, and embedded advisers managed by FSD Ethiopia. While they demonstrated good financial management overall, we received irregular payment requests from FSDA. Our agreement was to make payments on a quarterly basis; however, their requests came on a bi-annual basis. There has also been a delay in channelling funds from FSDA to FSDE, which hindered FSDE’s ability to execute planned activities on time. The progress reports we received from FSDE were inconsistent; the reporting period mentioned in the agreement was quarterly, but we did not receive them on that basis. In addition, the financial data in the reports did not align with FSDA’s financial report. While FSDA’s report shows the funds as utilised, FSDE’s reports show them as unutilised or committed.

To address these challenges, we are working on the split of FSDE and FSDA, as recommended in last year’s annual review, and we will establish a separate funding agreement with FSDE. As a prerequisite to sign a new agreement with the FSDE, we have conducted a Due Diligence Assessment on FSDE, and the draft is awaiting PRO / SRO quality assurance and sign off. In parallel to this we have drafted the accountable grant agreement which will be signed with the FSDE based on the outcomes form the DDA and FSDE’s ongoing strategy review process. Signing a separate agreement with the FSDE will enable direct payments to FSDE, eliminate delays, and clearly define payment schedules, reporting timelines, and quality standards for progress reports.

Enhancing Corridor Efficiency in the Horn of Africa (Trademark Africa):
During the review period, we extended the TMA Ethiopia project’s MoU end date from December 2025 to March 2026. TMA’s financial management remains strong: they consistently submit timely monthly financial reports on utilization and forecasts and proactively alert us to potential spending risks.

We made five advance payments totalling £1.3 million to TMA, ensuring that these payments were not in advance of need. Each disbursement was verified against the costed workplan, financial reports, forecasts, and progress reports. FX gains and VAT refunds created unplanned variances, which were managed through agreed additional tasks to absorb these funds efficiently. No payment slippage or spending risks were observed. One improvement identified is the need to shift TMA’s costed workplan from lump-sum allocations to a milestone-based format with clear outputs, timelines, and amounts.

No new assets were purchased during the period; instead, we transferred a vehicle and office equipment from closed projects, which TMA has utilized and recorded in the FCDO-format asset register. TMA has recently requested to return the vehicle, and we are working on this process.

Enhancing Access to Climate Finance for Ethiopia (GGGI):
This project component was designed to be one year only but required three no-cost extensions, which were needed to complete all remaining outputs. Although we had explored the possibility of extending the work into a multi‑year agreement, last year’s ODA budget reductions and the resulting strategic shift – combined with poor programme management performance of the partner – meant EIAF II reprioritised, and chose not to continue with a longer‑term partnership, and the project is now closing as planned at the end of its final no‑cost extension period.

Public Investment & Asset Management (Cowater):
During the review period the programme team completed procurement for the EIAFII main supplier facility and signed a £17.5m contract with Cowater International for a 42-month implementation period. The project remains in its inception phase, originally planned for four months but extended by few months for reasons outlined in this annual review Outputs section.

Following the procurement of the main supplier, an MoU agreement for technical cooperation on PIAM between FCDO and the Government of Ethiopia was signed on the Foreign Secretary’s recent visit to Ethiopia (January 2026). As a new supplier, we established a Contract Purchase Agreement (CPA) in the system for the full contract value, raised the purchase order, and processed four payments to date totalling £364k, all made in arrears. While payments were initially planned on a quarterly basis, we shifted reimbursable payments (expenses and fees) to a monthly cycle during the inception phase to enable more frequent spot checks on selected transactions and ensure contract compliance. Milestone payments will continue to be made upon verified delivery against agreed acceptance criteria, and payment frequency may be adjusted during implementation if required.

The contract is delivered under the Global Development Delivery Framework terms and conditions, including clauses on duty of care, break points, and termination rights for poor performance or funding constraints.

Key performance indicators are being finalized during the inception phase, and payments are linked to milestone delivery and performance, with a proportion of fees held at risk. The supplier is required to comply with the Supply Partner Code mandates mainstreaming GESI across all activities. Open Book Accounting is applied for cost transparency; non-programme attributable costs total £119,755 and profit is £39,918, with any variance subject to challenge. Performance is monitored through the Strategic Relationship Management scorecard.

CAPE Ethiopia (FSDA): We agreed on a dual-lock arrangement with the Centrally Managed Programme team (FSD Africa programme) for the Carbon Credit Accelerator (value: £537,250). Payments are processed via the budget buy-in mechanism (Option 1b), where the CMP raises the component and purchase order, while charges flow through our cost centres. Under this arrangement we have so far facilitated payments of £458k to FSD Africa. Our programme management responsibilities include delivery oversight, forecasting, and budget allocation to ensure the project achieves its objectives. This activity does not fall under the EIAF log frame; instead, it is reflected in CMP’s log frame and assessed through CMP’s annual review process.

Development Partnership Group (UNDP): The embassy signed a contribution agreement with UNDP to support the DPG pooled fund for the delivery of the High-Level Business Forum in Ethiopia. Under this agreement, we released a one-time payment of £87k to UNDP.

Ethiopia Reform Support MDTF (WB): During the review period, an amendment was made to the Ethiopia Reform Support Multi-Donor Trust Fund (WB MDTF, 300588-102) administrative agreement, extending its end date to December 31, 2027. In addition, we contributed £750,000 to the trust fund as part of our agreed commitments.
Delivery Chain Map (DCM):
The programme developed its Delivery Chain Map and has continued to update it throughout the programme’s implementation period to reflect any changes in downstream partners and the risks linked to them. The DCM helps the team to clearly understand the full route of FCDO funds and ensure they are used in a way that supports the programme’s objectives. It also helps us identify where risks may sit in the delivery chain, including potential areas for fraud. All EIAF II suppliers have their own delivery chain maps, which they update whenever they add new downstream partners or when risks change. The programme team is also discussed about the delivery chain map as part of one agenda item in the monthly programme management meeting and update it whenever there are changes.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

The programme team is currently procuring a supplier to provide independent monitoring, evaluation, and learning (MEL) support for the EIAF II programme. The scope includes independent results verification, evaluation of process and impact, and an embedded approach to learning and adaptation that will strengthen EIAF II’s delivery, real-time learning and course correction, with a primary focus on the PIAM and FSDA/FSDE components.

At the time of this Annual Review, the ToR has been issued to the market, bids have been received, and proposals are under evaluation. Our original intention was to have the MEL provider mobilised in time to contribute to this review and assess some inception-phase outputs from the PIAM facility. However, delays in finalising and publishing the ToR prevented this, and the MEL provider was not in place for the current assessment period.

Monitoring and Evaluation
Supplier performance reports were interrogated based on in-depth knowledge and close relationships (with partners and beneficiaries) in all key sectors and verified via follow-up workshops and via beneficiary feedback and triangulation with other key stakeholders. The programme team has strong relationships with senior GoE stakeholders benefitting from/overseeing the PIAM, capital markets, macro and climate finance pillars – less so on trade/logistics. Feedback gathered in the run-up to this review was overwhelmingly positive. In addition to feedback covered in earlier sections, the ECMA’s encouragement for FSDE to become the convening development partner on capital markets in Ethiopia is a tangible endorsement of their work. We received positive feedback from senior stakeholders in MoF, EIH (although PIAM’s first phase of deliverables are yet to land), MOPD and PMO.

Evidence
The deployment of the independent MEL provider is expected to significantly improve the quality, credibility and usefulness of evidence generated across the PIAM and Financial Sector components of EIAF II. Through strengthened logframes and theories of change, more systematic and SMART indicators, and regular independent verification of partner‑reported results, the MEL provider will enhance FCDO’s ability to track progress toward outcomes and identify system‑level behavioural changes within Government of Ethiopia institutions.

Learning
The Terms of Reference for the new MEL provider have a particular emphasis on continuous learning. Quarterly learning products, monthly sessions with the PIAM facility, and a consistent challenge‑function will enable more agile and evidence‑driven adjustments to tasking, delivery and adapting. The MEL provider’s analysis of VFM will help the programme better identify cost drivers, efficiency gains and high‑return modalities, supporting better allocation of resources across both components. Cross‑component learning will also deepen coordination between PIAM and the Financial Sector reform activities, ensuring synergies—such as links between SOE reforms, public investment management and capital market development—are better understood and leveraged. Overall, the MEL provider will help shift EIAF II toward a more adaptive, coherent and strategically managed programme with stronger oversight, clearer decision‑making and increased reform impact.

Date of last narrative financial report	FSDA – 31/12/2025 / GGGI – 31/12/2025 / TMA – 31/12/2025 / PIAM – not completed yet, as programme is yet to finalise inception phase. / World Bank MDTF – June 2025	Date of last audited annual statement	FSDA – 31/03/2025 / GGGI - 31/03/2025 / TMA – Audit pending early 2026, date TBC / PIAM – audit to be finalised in 2026 (following first year of delivery) / World Bank MDTF- June 2025