## Annual Review

Title: SheTrades Commonwealth Programme
Programme Value £ (full life): £19,800,000		Review date: 31/08/2025
Programme Code: 300593	AMP start date: 30/04/2018	AMP end date: 31/03/2026

Summary of Programme Performance

Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A+	A+	A	A	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Log Frame

A. SUMMARY AND OVERVIEW

Description of programme

The SheTrades Commonwealth+ (“SheTrades”) Programme, funded by the UK Government, is a flagship Aid for Trade (AfT) initiative that aims to support inclusive economic growth and job creation in Commonwealth countries and beyond through the increased participation of women-led businesses (WLBs) in trade. Launched in 2018, the programme aims to increase women’s participation in trade by creating a more supportive business ecosystem, enhancing competitiveness, and facilitating market access. The programme’s four main outputs are:

- Output 1.1 – Governments are supported to implement commitments to make trade related policies more gender responsive
- Output 1.2 – Business Support Organisations are supported to provide better services for women-led businesses in target countries
- Output 2.1 – Competitiveness and capacity of women-led businesses and women suppliers to participate in trade is enhanced in target countries
- Output 2.2 – Private sector partners supported to adopt business practices that create economic opportunities for women-led businesses -
SheTrades is implemented by the International Trade Centre (ITC) and is part of ITC’s wider SheTrades Initiative. The programme is delivered in line with the FCDO’s strategic objectives on Women’s Economic Empowerment (WEE) and trade and offers targeted investment in gender equality and inclusive growth, delivering against UN SDGs 5 and 8.

No further work was undertaken under output 2.2 - Private sector partners supported to adopt business practices that create economic opportunities for women-led businesses, which was concluded in FY23/24 resulting in the launch of the step-by-step guidebook for private sector companies to mainstream gender in their value chains. Under output 2,1, linking UK importers with WLBs increases market access opportunities for and encourages private sector partners to actively include women suppliers in their supply chains, thereby advancing the Output 2.2 approach in practice.

Summary supporting narrative for the overall score in this review

This annual review covers the period from 1st April 2024 to 31st March 2025 (FY24/25). In line with previous years since the programme started in 2018, the Shetrades programme continued to deliver high-quality results, strategic influence, and strong value for money across the defined outputs in FY24/25. The overall score reflects a programme that is on track, impactful, and well-positioned for scale and sustainability.

In this reporting year, with a total budget of £2.66 million, the SheTrades programme mobilised resources to support WLBs, strengthen institutional ecosystems, and influence trade policy reform. The programme delivered high-impact interventions across 19 countries including: Bangladesh, India, Nepal, Mongolia, Pakistan, Sri Lanka, Ghana, Kenya, Nigeria, Rwanda, Zimbabwe, Mozambique, The Gambia, South Africa, Brazil, Chile, Peru, and the ASEAN and Caribbean regions.

The programme facilitated 14 trade missions and fairs, connecting 564 WLBs to international buyers and generating over £13 million in business leads and deals which is a clear indicator of export engagement. These missions not only opened new markets, but also led to tangible changes in business practice, such as product redesign, packaging upgrades, and progress towards certifications. They helped WLBs build buyer relationships, challenge gender biases, and position themselves for long-term trade partnerships. Key highlights include:
- SIAL Paris: £5.82 million in leads; £411,000 in confirmed sales.
- Manchester Trade Mission: £1.1 million in leads; 48 WLBs from 10 countries.
- UK–Sri Lanka Trade Mission: £604,000 in leads; £150,000 deal secured.
- UK–ASEAN Trade Mission: £465,000 in leads.
- Fruit Logistica: £1.48 million in potential sales.
- Salon du Chocolat: £123,000 in leads.
2,904 WLBs received capacity-building support with 483 WLBs making measurable changes to improve their competitiveness to trade. This translated into action such as businesses improved their offerings, aligned with international standards, and became better equipped to enter global markets.

21 SheTrades Hubs reported improved services to WLBs, including digital access, export readiness, and green transition support and 27 business support organisations (BSOs) were supported through training and peer learning. These institutions are now better equipped to deliver gender-responsive services, ensuring sustainability and local ownership of support systems for women entrepreneurs.

The programme’s global component, SheTrades Outlook (STO), was rolled out to more countries – Brazil, Cambodia, Indonesia, Thailand, Ghana, and Sri Lanka to name a few – offering partner governments and other relevant stakeholders opportunity to create a more inclusive policy and business environment by providing comprehensive data and analysis on barriers to gender-responsive trade. Policy technical assistance was also provided to countries such as Sri Lanka and Bangladesh, leading to the adoption of inclusive policies. These efforts contributed to systemic change, embedding gender considerations into trade policy and public procurement.

ITC continued to manage delivery effectively throughout the reporting year despite delays to ODA allocations as well as demonstrating flexibility in responding to demand from post with additional ‘buy-in’ funds.

As the programme enters the final year, the focus should move towards capitalising on results achieved so far and capture lessons learned to inform future trade and development programming. A mid cycle review of targets is recommended to ensure they remain ambitious and aligned to the programme’s scope. Emphasis should also be placed on exit strategies, knowledge transfer and transition to partner institutions to ensure long-term impact beyond programme closure.

The table below sets out results achieved across key indicators for the programme in FY24/25.

Level	Indicator(s)	FY24-25 / Targets	FY24-25 Results
Programme Outcome 1: More supportive business ecosystem for women-led businesses	Number of inclusive policies governments commit to adopt and implement	2	2
	Number of Hubs delivering new and/ or improved services to women-led businesses to boost their competitiveness (including on digital access & literacy and the green transition), as well as to other institutions	10	21
	Number of private sector partners improving their services to women and/ or making changes to their supply chain management to create more opportunities for women	0	0
Output 1.1: Governments are supported to implement commitments to make trade-related policies more gender responsive	1.1.1. Number of governments collecting/ updating SheTrades Outlook data	5	6
	1.1.2. Number of policy briefs and publication prepared	5	5
	1.1.3. Number of countries taking part in events of the SheTrades Outlook Network to share and build on learning & best practices between countries	20	22
	1.1.4. Number of male and female beneficiaries with greater awareness of gender and international trade as a result of ITC support	550	1265
	1.1.5. Number of policy measures reviewed with stakeholders with ITC support	2	4
Output 1.2: Business support organizations (BSOs) are supported to provide better services for women entrepreneurs in target countries	1.2.1 Number of SheTrades Hubs established	3	3
	1.2.2 Number of SheTrades Hubs and associated BSOs supported through information, tools and training (including on digital access & literacy and on the green transition)	20	27
	1.2.3 Number of SheTrades Hubs and associated BSOs sharing best practices on measures to support womenled businesses as part of national/ international support networks	20	26
	1.2.4 Number of women-led businesses benefitting from the improved services of SheTrades Hubs	750	1567
Programme Outcome 2: Women-led businesses in target countries are more competitive and ready to trade	Number of women-led businesses and women suppliers making changes to their business practices to increase their competitiveness to trade	250	483
Output 2.1: Competitiveness and capacity of women-led businesses and women suppliers to participate in trade is enhanced in target countries	2.1.1. Number of women-led businesses trained and supported with tools and information to improve their competitiveness	800	2904
	2.2.2. Number of women-led businesses connected to markets	100	564

Major lessons and recommendations for the year ahead

One of the key lessons for future programming is the importance of market access interventions that are specifically tailored for women-led businesses. The success of SheTrades can be attributed to its aim on giving WLBs support and direct exposure to buyers and markets. This highlights the need for dedicated programming that can support inclusive trade. As the programme enters its final year, emphasis should be placed on exit strategies, knowledge transfer and transition to partner institutions to ensure long-term impact beyond programme closure. This should begin in earnest in Q3 at latest to ensure sufficient time and planning of handover activities.

The table below sets out the main lessons learned in FY24/25 and recommendations for FY25/26 specifically relating to output delivery, in addition to the recommendation above.

Lessons Learned (FY24/25)	Recommendations (FY25/26)
Embedding STO data collection within national institutions enhances evidence based policy reform, sustainability and ownership.	Expand this model to other countries to ensure long-term tracking and improvements to gender-responsive trade policies in FY24/25
Governments need support not just in drafting inclusive policies but also in implementing and monitoring them effectively.	Develop a strategy that includes implementation support, monitoring frameworks, and stakeholder engagement.
Certification and compliance support must be tailored to WLBs' readiness levels.	Encourage Hubs to provide phased technical assistance based on initial assessment of WLB’s capacity and commitment.
Trade missions are highly effective when structured with pre- and post-engagement support.	Continue sector-specific trade missions with strong pre/post strategies including buyer mobilisation and follow-up.
Training on digital marketing and branding boosts WLBs’ competitiveness.	Continue digital and branding support, integrating AI tools into training packages.
SheTrades Hubs benefit from targeted support in M&E, practical tools and service delivery.	Continue capacity-building, refine M&E frameworks, and embed tools into Hubs or national institutions.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change (ToC) for the SheTrades programme outlines how the initiative aims to achieve its long-term goals of increasing women’s participation in international trade, fostering inclusive economic growth, and facilitating job creation. This is achieved through working with multiple stakeholders on technical assistance, capacity building, and the development and implementation of gender-responsive trade policies.

The ToC is based on several key assumptions:
- Governments are willing and able to adopt and implement inclusive, gender-responsive trade policies.
- WLBs can increase their competitiveness and market access through targeted support and training.
- Business support organisations (BSOs) and SheTrades Hubs can sustainably deliver services to WLBs.
- Private sector partners are open to adapting supply chains and services to be more inclusive of women entrepreneurs.
- Data and evidence are essential to inform policy reform and track progress on gender and trade.

In FY24/25, the programme continued to deliver against its defined outputs in the ToC, building on previous years’ achievements and expanding its reach and impact. The programme remained centrally managed, with budget allocations coordinated between the FCDO, ITC, and UK Posts in partner countries. Expansion of the programme’s geographic focus beyond the Commonwealth in the previous fiscal year did not change the programme logic, and the overall ToC and logframe remains valid and relevant.

The programme’s interventions in FY24/25 demonstrated the continued relevance of the ToC, with tangible results across policy reform, institutional strengthening, and market access for WLBs. The programme also contributed to testing and informing the logic for the Trade COE through its inclusive trade approaches and gender-focused technical assistance.

The SheTrades ToC is presented in the diagram below:

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The Programme continued to make strong progress in FY24/25 toward its defined impact (Women-owned businesses in target countries increase their participation in export trade) and two expected outcomes (1. More supportive business ecosystem for women-led businesses and 2. Women-led businesses in target countries are more competitive and ready to trade).

Impact: A range of WLBs supported through the programme are not only participating in export trade but are also securing leads, deals and partnerships – clearly demonstrating progress towards the SheTrades programme impact. Overall, the Programme has effectively managed to achieve its intended impact by increasing the participation of WLBs in export trade since its launch. WLBs are gaining greater exposure to export markets, building the skills and confidence to promote their businesses for export, and accessing new opportunities to trade that results in business deals, leads, and partnerships. For example, Karakuta Farms in Kenya has grown from establishing its first avocado orchard with Programme support in 2019, to participating in various market-related trainings and market access opportunities with Programme support, to now successfully export avocados internationally, with a projection of 76 containers in 2025 to the UK, EU, China and India.

Under Outcome 1 on progress towards a more supportive business ecosystem for WLBs, targets on the adoption and implementation of inclusive trade policies also continued to be met, demonstrating the programme’s appeal to governments in partner developing countries and supporting progress in the development and adoption of gender-responsive frameworks across the globe. The programme has influenced global platforms, including the WTO Trade Policy Reviews and G20 discussions. She Trades Outlook has been the go-to resource of intergovernmental bodies such as the WTO, G7 and G20 to guide discussions on trade and gender, including the B20 Women in Trade Initiative.

The number of SheTrades Hubs and BSOs delivering new or improved services to WLBs also significantly exceeded the target in FY24/25 (21 vs. 10). The SheTrades Hubs Annual Meeting in Geneva provided institutional strengthening, including training on impact measurement and gender-specific indicators, which enabled Hubs to better align their services with strategic goals. The programme introduced new digital resources to improve data collection and service delivery, helping BSOs track and increase their support to WLBs more effectively. Strong peer-to-peer learning and collaboration among Hubs and chambers of commerce (e.g. Pakistan, Mauritius, Sri Lanka) promoted successful practices. The launch of new Hubs in Brazil, India, and Sri Lanka strengthened the SheTrades Hub network and enhanced delivery in developing markets. High-quality Training-of-Trainers programmes boosted capacity, with a significant number of participants reporting confidence in duplicating training independently. These efforts created a ripple effect, enabling more institutions to deliver impactful services and exceed the original target.

Under Outcome 2 on increased competitiveness of WLBs in target countries. 114 WLBs reported implementing improvements following training in branding, negotiating and product positioning. Training interventions across five countries enhanced compliance with international quality standards, reducing rejection rates and improving readiness for global supply chains. These results reflect the SheTrades programme’s strategic focus on strengthening institutional capacity and expanding service delivery for WLBs, particularly through SheTrades Hubs.

The Programme will continue to 31 March 2026, and the indicators will remain unchanged, ensuring consistency in measurement and reporting. Continued facilitation of buy-in from Post will allow the programme to build on successful partnerships with BSOs and continue delivery of high-impact interventions.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The SheTrades programme continues to demonstrate strong performance and relevance, within the context of the UK’s wider trade and development portfolio and is currently EDPD’s only programme with a principal Gender Equality Marker score. The SheTrades programme has delivered strong results and in many cases exceeded its core indicators, such as, supporting 483 WLBs to make changes to improve competitiveness; training of 2,904 WLBs through targeted interventions; facilitating over £13 million in business leads through trade missions and fairs; and supporting governments in Sri Lanka, Cambodia, and Bangladesh to adopt and/or implement inclusive trade policies.

The SheTrades programme has built a strong global reputation in trade and gender inclusivity. Demand for technical support remains high, particularly for establishing new SheTrades Hubs, rollout of the STO tool, and delivering certification and compliance support to WLBs. The expansion of the SheTrades Hubs and STO networks is already delivering results, collaborations, peer learning, and gender-responsive policy reform. The SheTrades programme directly contributes to the UK’s commitment to inclusive trade, particularly trade that benefits women, particularly strengthening women’s economic empowerment and leadership. The extension of the programme to 31 March 2026 on a continuity basis ensures alignment with the upcoming Trade Centre of Expertise (COE) launch.

A key priority for FY25/26 will be gathering additional learning to inform the development of the Trade COE. Any new interventions will be strategically considered to ensure their feasibility in the short-time frame remaining and contribution to the long-term vision of inclusive and sustainable trade. The continuation of Post buy in activities will enable the programme to deepen partnerships with BSOs, expand support to private-sector partners to adopt business practices that create economic opportunities for women-led businesses, and deliver high impact sustainable interventions.

## C. DETAILED OUTPUT SCORING

Output Title	Governments are supported to implement commitments to make trade related policies more gender responsive
Output number:		1.1	Output Score:	A+
Impact weighting (%):		35	Weighting revised since last AR?	No

Indicator(s)	FY24/25 targets	FY24/25 results
1.1.1: Number of governments rolling out SheTrades Outlook	5	6
1.1.2: Number of policy briefs and publications prepared	5	5
1.1.3 Number of countries taking part in events to share and build on learning & best practices between countries	20	22
1.1.4 Number of male and female beneficiaries with greater awareness of gender and international trade as a result of ITC support	550	1265
1.1.5 Number of policy measures reviewed with stakeholders with ITC support	2	4

Briefly describe the output’s activities and provide supporting narrative for the score.

The primary aim of this output remained focused on supporting governments, policymakers, and stakeholders with tools and information to assess trade-related policies through a gender lens. The STO tool continued to be central to this effort, enabling country-specific assessments and regional comparisons to identify best practices and priority areas for policy reform. Technical assistance was provided to review policy measures and facilitate workshops to share learning and gather stakeholder input.

In FY24/25, STO was rolled out or updated in six countries: Thailand, Brazil, Peru, Chile, Ghana, and Sri Lanka, bringing the total number of countries to have onboarded the tool to 61. Thailand became the seventh ASEAN country to join STO, and Brazil leveraged its G20 chairmanship to promote STO as a knowledge resource. In Ghana and Sri Lanka, SheTrades Hubs led STO data collection, integrating it into their institutional mandates marking a significant step toward local ownership and sustainability. This workstream also oversaw the production of five policy briefs for Cambodia, Indonesia, Philippines, Brazil, and ASEAN, which can be accessed at this link: https://outlook.shetrades.com/resources/65/publications.
These briefs informed STO workshops and were disseminated to stakeholders, providing targeted recommendations for gender-responsive trade policy reform. The ASEAN brief was updated to include STO results from Indonesia, with plans to incorporate Thailand’s data in the next version. The STO Network expanded to include seven new focal points, bringing the total to 42 countries. ITC organised four online workshops with participation from 22 countries, covering topics such as women’s participation in e-commerce, gender mainstreaming in trade policy, and access to finance and skills. These sessions facilitated peer learning and fostered collaboration between countries.

Through STO workshops, policy dialogues, and training sessions, the programme engaged 1,265 participants, significantly exceeding the target of 550 participants. These activities raised awareness of the connection between gender and international trade and built capacity among policymakers and stakeholders.

Policy technical assistance was also provided to four countries:
- Cambodia: drafting support was provided on the inclusive trade chapter for the National Trade Policy Framework.
- Sri Lanka: Two draft bills on gender equality and women’s economic empowerment were reviewed.
- Bangladesh: a needs assessment was conducted to support implementation of the Sustainable Public Procurement (SPP) Policy.
- Indonesia: support was provided towards efforts to standardise definition of WLBs and mainstream gender in trade agreements.

Planned changes for the next phase include scaling institutional ownership of STO across more countries, aligning STO Network activities with SheTrades Hubs, and expanding thematic coverage to include digital trade, climate resilience, and inclusive finance.

Progress against previous Annual Review Recommendations is reflected in the integration of STO into national institutions, expanded policy technical assistance, and enhanced regional analysis.

These interventions demonstrate the SheTrades programme’s facilitation in shaping inclusive trade policy and its commitment to supporting governments beyond data collection, focusing on implementation and institutional capacity building.

Describe any changes to this output during the past year, and any planned changes as a result of this review

In FY24/25, the output remained focused on supporting governments to implement gender-responsive trade policies through STO rollout, country peer learning and related technical assistance. While the core structure of the output was maintained, some enhancements were introduced to strengthen the effectiveness and sustainability of interventions.

A key change was the integration of STO data collection into the mandates of national institutions hosting SheTrades Hubs, notably in Ghana and Sri Lanka. This shift from consultant-led data collection to institutional ownership marks a strategic evolution in the programme’s approach and activities, demonstrating achievement of a higher level of ambition and transformative approach to gender equality, by aiming to embed gender-responsive trade monitoring within national systems for long-term sustainability and impact.

No new output-level indicators were added in FY24/25, but the programme continued to track and report on the indicator introduced in FY23/24: “Number of policy briefs and publications prepared and disseminated.” This indicator remains relevant and useful for capturing the visibility and influence of STO outputs.

Output Title	Business Support Organisations are supported to provide better services for women entrepreneurs in target countries
Output number:		1.2	Output Score:	A+
Impact weighting (%):		35	Weighting revised since last AR?	No

Indicator(s)	FY24/25 targets	FY24/25 results
1.2.1: Number of SheTrades Hubs established	3	3
1.2.2: Number of Hubs and BSOs supported through information, tools, and training (including on digital access & literacy and the green transition)	20	27
1.2.3: Number of SheTrades Hubs and associated BSOs sharing best practices on measures to support women-led businesses as part of national/ international support networks	20	26
1.2.4: Number of women-led businesses benefitting from the improved services of SheTrades Hubs	750	1567

Briefly describe the output’s activities and provide supporting narrative for the score.

The primary aim of this output remained to equip BSOs and other key institutions with tools, training, and information to strengthen their capability and improve their membership offer to WLBs, thereby enabling more women to participate and benefit from international trade. This continued to be a key focus area for the programme in FY24/25, particularly as the SheTrades Hubs network expanded and matured, with three new Hubs launched in Brazil, India, and Sri Lanka. The growing profile of the Hubs attracted interest from additional countries and regions, reinforcing their role as trusted facilitators of training, trade missions, and policy engagement.

The launch of three new SheTrades Hubs takes the total number of Hubs round the world to 21 with Hubs situated in Africa, Asia, South America, and the Caribbean and Middle East regions. The expansion of the Hub network has served to build new partnerships and collaborations, helping WLBs access new markets across the network. For example, the SheTrades Hubs in India and Ghana were already in discussions about trade missions between their respective countries for FY25/26. The SheTrades Hub launch in Sri Lanka was attended by the Trade Minister of Sri Lanka – marking a milestone in political endorsement of the SheTrades model.

Institutional strengthening of the BSOs continued through several interventions. The SheTrades Hubs Annual Meeting in Geneva (September 2024), was attended by representatives from 17 existing Hubs and two upcoming Hubs (Brazil and Sri Lanka), along with UK-based and Pakistani chambers of commerce. The meeting featured sessions on impact measurement and data collection, with Hubs identifying new gender-specific indicators and action plans to improve service delivery for women entrepreneurs.

Training-of-Trainers (ToT) programmes were delivered across Pakistan, India, Bangladesh, Sri Lanka, Mongolia, and Zimbabwe, covering digital marketing, branding, export pricing, and certification. Trainers gained proficiency in using tools like Canva, UK DCTS Visualization Map, and ITC’s Standards Map, enabling them to replicate training and support WOBs more effectively.

The SheTrades Hubs were instrumental in delivering deeper impact through their strong relationships with stakeholders and members. The SheTrades Hubs played a key role in delivering deeper impact by leveraging their local networks and institutional relationships. For example, Ghana and India Hubs initiated joint planning for a bilateral trade mission, demonstrating cross-border collaboration; the Sri Lanka Hub launch was attended by the trade minister, showing high-level political and national ownership. At the SheTrades Hubs Annual Meeting in Geneva, 17 Hubs co-developed gender-specific indicators and action plans to improve service delivery. Training-of-Trainers (ToT) sessions led by Hubs in Pakistan, Bangladesh, and Sri Lanka resulted in replication of training at local levels, such as in Sialkot, where chambers independently organised follow-up sessions. These activities included peer-to-peer learning, targeted capacity-building, and strategic collaborations that helped WLBs access markets and improve competitiveness, for example instance Hubs in Ghana, India, and Sri Lanka have begun sectoral analysis to identify high-potential sectors for WLBs.

Peer-to-peer collaboration sessions were held at the World Women’s Forum in the Absa Inspire Me Conference in Kenya, and bilateral exchanges between Hubs in Mauritius and India, Ghana and South Africa, and The Gambia and Ghana. These sessions fostered cross-border learning, joint planning, and the development of collaborative roadmaps to support women entrepreneurs.

Institutional strengthening workshops were organised for The ASEAN Women Entrepreneurs’ Network (AWEN) this was delivered over a three-day workshop in	Phnom Penh to develop a strategic plan for the next decade, with support from ITC.

An online session in March 2025 helped Hubs refine their monitoring frameworks, align indicators with strategic goals, and improve data-driven storytelling.

By March 2025, 1,567 women-led businesses had benefitted from the improved services of SheTrades Hubs, including
- Bangladesh (356)
- Kenya (165)
- Mauritius (69)
- South Africa (214)
- Philippines (120)
- The Gambia (100)
- Caribbean (543)

These interventions have significantly strengthened the institutional capacity of BSOs and SheTrades Hubs, enabling them to deliver high-impact support to women entrepreneurs across Asia, Africa, and the Caribbean.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no structural changes to this output during FY24/25. However, the programme has made progress in leveraging the SheTrades Hubs to contribute to other components, particularly on policy. Specifically, SheTrades Hubs in Ghana and Sri Lanka played a role in representing women’s priorities in government policymaking by integrating SheTrades Outlook tracking into their institutional frameworks.

In FY24/25, the programme strengthened the capacity of BSOs and SheTrades Hubs to deliver more consistent and impactful support to women-led businesses. A key focus was on building gender-specific indicators, action plans, and monitoring frameworks. These tools helped BSOs better track their impact, gather feedback from WLBs, and improve the quality of services offered.

To support this, the programme facilitated peer learning and technical workshops, including the SheTrades Hubs Annual Meeting in Geneva, where Hubs co-developed practical tools for service improvement.

Output Title	Competitiveness and capacity of women-led businesses to participate in trade is enhanced in target countries
Output number:		2.1	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	FY24/25 targets	FY24/25 results
2.1.1 Number of women-led businesses trained and supported with tools and information to improve their competitiveness	800	2904
2.2.2 Number of women-led businesses connected to markets	100	564

Briefly describe the output’s activities and provide supporting narrative for the score.

The SheTrades programme’s interventions under Output 2.1 were comprehensive, well-targeted, and impactful. The significant overachievement of both output indicators—2,904 WLBs trained (target: 800) and 564 WLBs connected to markets (target: 100)—demonstrates the effectiveness and scalability of the approach. The activities not only built capacity but also led to meaningful changes in business practices, positioning WLBs to overcome market knowledge and access barriers, for success in international trade

1. Export Procedure Handbooks

In FY24/25, the SheTrades Programme developed nine sector-specific export procedure handbooks tailored to the regulatory and export priorities of Bangladesh, Cambodia, Ghana, Indonesia, Pakistan, the Philippines, and Sri Lanka. These handbooks offered step-by-step guidance on exporting to the UK in relation to key sectors with high WLB and SME participation, including how to leverage the UK Developing Countries Trading Scheme (DCTS), navigate customs procedures, and meet sustainability and compliance standards. In Bangladesh, the handbook launch was co-organised with the SME Foundation and featured high-level participation from the British High Commission in Dhaka, alongside UK FCDO trade policy advisors WIPO Division Director for Asia and the Pacific, also joined the event, which was livestreamed to over 2,500 viewers. In Pakistan, a five-day Training of Trainers was held for four chambers of commerce, covering topics such as sales contracts, sustainability certifications, and legal market access. The training included interactive sessions using the UK Integrated Online Tariff and ITC Standards Map and featured a session on exporting fresh produce to Europe. In Sri Lanka, 45 women-led businesses participated in handbook-based training sessions, using the resource to strengthen their documentation and tariff navigation skills. In Indonesia, two women entrepreneurs used the handbook to prepare for the UK–ASEAN Trade Mission, demonstrating its practical utility in real-time business engagement.

2. Digital Marketing and Branding Trainings

Digital marketing and branding trainings were delivered across Ghana, India, Sri Lanka, Bangladesh, Mongolia, and Pakistan, reaching over 150 women-led businesses. These workshops focused on enhancing visual identity, optimising social media presence, and using AI tools for content creation. In Ghana, 42 WLBs took part in a two-day training that included collaborative brand audits and peer-to-peer discussions. Participants reported improvements in branding strategy and the use of tools like ChatGPT to refine their messaging and digital outreach. In Pakistan, a Training of Trainers session held in Karachi brought together 20 trainers from four chambers of commerce. Post-training surveys showed that 60% of attendees felt the training exceeded expectations, and over half expressed confidence in replicating the training independently. In Sri Lanka and Bangladesh, trainers from EDB Sri Lanka and SME Foundation participated in joint sessions, fostering cross-border learning and collaboration.

3. Export Readiness and Business Skills Development

In FY24/25, the Programme delivered a range of export readiness and business skills development activities aimed at strengthening the capacity of women-led businesses to access international markets. In South Africa, a two-day training held in collaboration with the Small Enterprise Development and Finance Agency (SEDFA) supported 19 women entrepreneurs from the textiles, agriculture, manufacturing, and tourism sectors. The training focused on go-to-market strategies, leadership and productivity skills, and personal branding. Participants engaged in practical exercises using the Business Model Canvas to analyse value propositions and assess export potential. Feedback from participants highlighted the usefulness of deeper market research tools and the clarity gained on how to build strategic relationships for international growth. In Ghana, a two-day workshop on export pricing and logistics for 33 women-led businesses in the cocoa and agribusiness sectors helped participants understand competitive pricing, customs procedures, and international trade logistics. The sessions also included advisory support from DHL experts, enhancing participants’ readiness to meet global market standards.

4. Trade Missions and Fairs

A total of 564 women-led businesses participated in 14 trade missions and international fairs, including Ambiente in Germany, Fruit Logistica in Berlin, Beauty Istanbul, and the Manchester Trade Mission. These engagements generated over £13 million in business leads. At Ambiente, WLBs from Bangladesh, Saint Lucia, Mauritius, Kenya, Barbados, Indonesia, and the Philippines showcased products and engaged with buyers from seven countries. The Manchester Trade Mission brought together 48 WLBs from 10 countries and was attended by representatives from eight High Commissions and Embassies, as well as UK-based chambers of commerce. Participants reported changes in business practices such as product reformulation, packaging upgrades, and pursuit of certifications to meet buyer expectations. These events not only facilitated market access but also strengthened the visibility and credibility of WLBs in global trade.

5. One-to-One Coaching

Tailored one-to-one coaching sessions were delivered to women-led businesses in Kenya, Nigeria, and Ghana to enhance their branding, marketing assets, and buyer engagement strategies. Each business received customised support, including new or improved branding materials and digital marketing guidance. The coaching helped WLBs refine their products and communicate their brand identity to target audiences. Participants reported increased confidence in approaching buyers and a clearer understanding of how to position their products in competitive markets.

6. Green Performance Toolkit

Twenty women-led businesses from Bangladesh and Kenya adopted the Green Performance Toolkit to improve sustainability tracking and operational efficiency. The toolkit enabled businesses to monitor water, power, and waste usage, facilitating better decision-making and audit readiness. Participants valued the toolkit’s functionality, noting that it helped reduce paperwork and streamline internal processes. This intervention supported long-term competitiveness by embedding sustainability into core business operations.

7. Export Logistics and Supply Chain Workshops

In Ghana, the Programme partnered with DHL to deliver a workshop focused on export logistics, pricing, and supply chain management. The session equipped WLBs with practical knowledge on navigating international shipping and meeting buyer expectations. In Kenya, workshops were held in collaboration with Absa Bank Kenya, the host of the SheTrades Kenya Hub. These sessions focused on corporate supply chains, supplier contracts, and procurement strategies. Participants reported changes in how they approach partnerships, tackle supply chain gaps, and expand their supplier bases. The workshops were part of the Absa Inspire Me Conference, which also featured peer learning among SheTrades Hubs from across Africa.

Overall, the evaluation forms and feedback from Q4 show that WLBs made tangible changes to their business practices because of Programme activities such as:
- Improved branding and digital presence
- Adoption of sustainability practices
- Enhanced export readiness and market research capabilities
- Strategic engagement with buyers and corporate partners

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned

The Programme remains on track to contribute to the expected outcomes and impact under Output 2.1. It significantly exceeded its targets for training and market access, with 2,904 women-led businesses supported through capacity-building initiatives and 564 connected to markets via trade missions and fairs. These interventions have led to tangible improvements in business practices, including enhanced branding, packaging, certification pursuit, and strategic use of market intelligence tools. However, while progress has been strong overall, some areas require further work. Certification support in the shea and essential oils sectors revealed that many businesses are still in the early stages of compliance readiness, with limited access to conformity assessment services such as testing laboratories and certification bodies. In Nigeria, for example, only three out of ten WLBs made significant progress, while others faced operational constraints. To address these gaps, the Programme will continue supporting the same businesses in the next phase, scale up packaging and certification coaching, and engage national quality infrastructure institutions to build awareness and capacity. Additional focus will be placed on regional market requirements where readiness is more achievable, and the number of supported businesses will be expanded to increase impact. These actions aim to strengthen the Programme’s contribution to sustainable competitiveness and ensure that WLBs are better positioned to access international markets.

## D: VALUE FOR MONEY

Key cost drivers and performance

For the SheTrades programme, ITC assessed i results across the programme’s outputs against the logframe. It is important to note that the outputs for FY24/25 have progressed to reflect both quantitative and qualitative contributions. This change reflects that in addition to measurable results, the programme is adding value through collaborative dialogue, sharing of best practices, and knowledge transfer to help WLBs businesses succeed in trade.

Economy:
In FY24/25, £2.662m was mobilised to drive inclusive trade by supporting WLBs in 19 countries to increase their participation in international trade. Compared to FY23/24, spending was roughly £0.8m higher due to both secondary ODA and non-ODA funding, which enabled expanded delivery through 14 trade missions; improved training and institutional strengthening of 21 SheTrades Hubs and BSOs.

The overall FY24/25 funding included an initial ODA allocation of £2.2m, channelled through global and country-specific programming. A further £310,000 in ODA funding was received to scale interventions in priority countries, including through post-allocation in Sri Lanka and Rwanda. Furthermore, £152,000 in non-ODA funding was dedicated to strategic initiatives, including UK trade missions in target countries and the development of bilateral export handbooks to enhance bilateral trade between the UK and partners. Figure Two below summarises the relative contributions from different channels and partners.

Figure Two: Total SheTrades Commonwealth+ allocation by funding channel (£)

Source: ITC SheTrades Commonwealth+ Programme Annual Reports FY24/25

To ensure that the programme maintained Value for Money cost delivery, the team coordinated post-funded buy-ins and implemented efficient planning and procurement practices such as early booking of travel and trade fairs. Furthermore, the Programme leveraged strategic partnerships with BSOs, SheTrades Hubs, and UK-based chambers to maximise reach and minimise duplication. The use of Post funded projects enabled targeted interventions in priority countries.

Efficiency
The programme demonstrated high efficiency in converting resources into tangible outputs, with many examples of outcomes exceeding planned targets for FY 2024-25. The SheTrades Commonwealth+ Programme equipped 2,904 women-led businesses across Asia, Africa and the Caribbean with critical skills and knowledge through 31 tailored capacity-building initiatives, far exceeding the FY target of 800 WLBs. Similarly, the Programme managed to connect 564 women-led businesses to markets, far exceeding the target of 100.

The launch of three new SheTrades Hubs – in Brazil, India, and Sri Lanka – further expanded the programme’s footprint and institutional capacity. Collaborations with 21 SheTrades Hub host institutions and four UK-based chambers of commerce amplified the programme’s reach and impact, demonstrating efficient use of partnerships to deliver results.

Effectiveness
The programme has demonstrated effectiveness by achieving several positive outcomes, with notable examples of progress in institutionalising the SheTrades Outlook tool and in informing intergovernmental dialogue on trade and gender. The activities have contributed to its overall goals of empowering women in trade and promoting gender equality:
- Policy reform support in Sri Lanka, Cambodia, and Bangladesh integration of SheTrades Outlook (STO) into national institutions like GEPA (Ghana) and EDB (Sri Lanka), ensuring sustainability and local ownership.
- SheTrades has facilitated valuable networking and knowledge-sharing opportunities for both companies and women-led businesses, promoting peer learning and collaboration.
- Training and mentoring activities have equipped women-led businesses with improved knowledge and skills related to navigating corporate supply chains, negotiating contracts, and meeting export requirements.
- High-impact trade missions, such as the UK–Sri Lanka and UK–ASEAN missions, which generated £101,500 and £110,000 in business leads respectively within the first three months. Substantial business leads and established long-term relationships between UK companies and WLBs.
- SheTrades Outlook (STO) has been the go-to resource of intergovernmental bodies such as the WTO, G7 and G20 to guide discussions on trade and gender, ranging from the G20 – B20 Women in Trade Initiative, to collaboration with partners like Malawi to directly feed into WTO Trade Policy Reviews. This has positioned SheTrades as a leader in inclusive trade.

Equity
Equity is fully embedded in the SheTrades programme’s objectives, design and delivery. By focusing on women-led businesses in developing countries, the programme directly addresses gender inequalities in trade Activities were tailored to meet the needs of diverse WLB groups, including rural entrepreneurs, SMEs, and those in underrepresented sectors such as agrifood, textiles, and essential oils.

The programme has supported inclusive policymaking, helping governments mainstream gender in trade frameworks and public procurement systems. Despite logistical challenges the inclusion of regions like Jaffna in the UK–Sri Lanka trade mission demonstrated a commitment to reaching marginalised communities and aligning with diplomatic priorities. In Pakistan, Training-of-Trainer's sessions included participants from ethnic minority communities facilitated through local chambers. In Bangladesh, the SME Foundation supported outreach to widowed, and single women workers, particularly in the textiles and agrifood sectors.

The embedding of STO data collection within national institutions marks a shift toward sustainable impact, reducing reliance on external consultants and fostering local accountability. The technical assistance directly supported gender mainstreaming in trade frameworks, for example:
- Cambodia: ITC drafted the inclusive trade chapter for the National Trade Policy Framework.
- Sri Lanka: ITC reviewed two draft bills on gender equality and women’s economic empowerment.
- Bangladesh: ITC conducted a needs assessment to support implementation of the Sustainable Public Procurement (SPP) Policy.
- Indonesia: ITC supported efforts to standardise the definition of women-owned businesses and integrate gender into trade agreements.

The Training of Trainers model has already led to replication at regional levels, such as in Sialkot, Pakistan, where local chambers organised follow-up training independently. Partnerships with companies like Unilever and Absa Bank Kenya have led to improved corporate policies on gender-inclusive procurement and supply chain management, showcasing the programme’s influence beyond the public sector. High satisfaction rates and testimonials from participants and partners underscore the programme’s relevance and impact, reinforcing its value for money.

The SheTrades Programme continues to deliver excellent value for money. It has scaled its reach, deepened its impact, and maintained a strong focus on equity and sustainability. Its strategic alignment with the UK’s Aid for Trade (AFT) portfolio and its ability to generate learning for future programming further justify its continuation. As the programme transitions into its final phase, these strengths position it as a flagship model for inclusive trade development.

E: RISK

Overview of risk management

The overall risk rating for the SheTrades programme in FY24/25 remained moderate, consistent with the nature of the programme’s operating environment across multiple regions and sectors. ITC maintained a strong and proactive risk management process throughout the year, with regular updates to the risk register and quarterly reporting to FCDO. Risks were escalated to the Programme Responsible Officer (PRO) and Senior Responsible Owner (SRO) as needed, with mitigation measures promptly implemented.

Delivery Risk – Moderate (within appetite)

The risks in FY24/25 were largely related to coordination and delivery across a growing number of countries and activities. The programme’s expansion and increased in-person engagements required careful logistical planning and stakeholder management. ITC mitigated these risks by strengthening collaboration with technical and operational teams within host institutions, which tend to remain stable despite political transitions. This approach ensured continuity in implementation and safeguarded programme momentum.

While the short delivery window (due to late funding approvals) posed challenges, the programme adapted well through flexible planning and prioritisation. No major delivery failures occurred.

Fiduciary Risks – Low to moderate (within appetite)

The programme continued to operate with a low risk of fraud or financial mismanagement. ITC maintained strong financial controls and worked closely with FCDO and Regional Trade Policy Advisors to ensure transparency and accountability. Currency exchange fluctuations posed a fiduciary risk, but this was effectively mitigated through regular financial assessments and close coordination between ITC’s finance team and programme leads.

The risk of funding delays, which had impacted previous years, was lower in FY24/25 due to improved planning and early engagement with stakeholders. However, the programme remained vigilant in managing financial uncertainties, particularly in light of potential changes to FCDO funding allocations.

Safeguarding – Low (within appetite)

No safeguarding incidents were reported. All delivery partners were required to adhere to ITC’s safeguarding policies, and training was provided where needed. Safeguarding remains a standing agenda item in partner onboarding and monitoring.

Political Risk – Moderate (within appetite)

The programme maintained delivery through collaborative partnerships and flexible planning and no major disruptions occurred. Political changes were managed by ITC remaining agile and responsive to the situation on the ground. In Ghana ITC responded by engaging in policy advocacy with the Ghana Cocoa Board to improve access to cocoa beans for artisanal processors, aligning with national industrialisation and export diversification priorities. In Bangladesh, changes were made to planned activities to enable delivery through other means e.g. virtual training.

In Cambodia, WLBs faced challenges in offering competitive pricing during the UK-ASEAN Trade Mission due to structural issues in the textiles and footwear sector, which is dominated by foreign-owned firms. ITC mitigated this by strengthening the competitiveness of domestic WLBs through targeted capacity building, branding, and market access support.

These examples reflect the SheTrades programme’s ability to respond to external risks through adaptive programming and strategic partnerships.

 F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Financial Management

In FY24/25, the SheTrades programme maintained strong financial discipline and met its central spend targets, with total invoicing reaching £2.66m. The programme operated across 19 geographies, with delivery concentrated in the second half of the fiscal year following mid-year expansions and late-stage budget approvals. Despite these challenges, forecasts and invoicing were managed effectively, and all financial reporting was completed on time.

ITC provided timely and detailed quarterly reports to FCDO, including risk updates and mitigation actions. Spending was in line with forecasts, with no significant under- or over-delivery. Strong leadership and resource management ensured financial control and value for money.

Programme Management and Delivery

Delivery in FY24/25 remained efficient and aligned with agreed plans, building on previous years’ achievements and reinforcing long-term sustainability of programme impacts. ITC and FCDO maintained a strong collaborative relationship, with regular programme management meetings enabling agile responses to emerging challenges. The programme successfully navigated political instability in several target countries. Mitigation strategies included virtual workshops and flexible delivery models, ensuring continuity and impact.

Key delivery highlights include trade missions and fairs that generated £13 million+ in business leads and deals. The UK-Sri Lanka Trade Mission alone yielded £604,000 in estimated annual business value. Participating UK companies reported successful deals and increased engagement with women-led suppliers.

Inward trade missions were piloted to promote UK imports from WLBs. Collaborations with UK Chambers of Commerce (London, Birmingham, Manchester, West Yorkshire) and in-country chambers (e.g. Karachi, Lahore, Sialkot) facilitated B2B events that strengthened UK-Pakistan trade ties and improved perceptions of Pakistan as a viable supplier. Across the portfolio, the programme continued to deliver results in line with its strategic objectives, demonstrating operational effectiveness, financial accountability, and a commitment to inclusive, sustainable trade development.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and evaluation (M&E)

In FY24/25 M&E remained a core element of programme management. The SheTrades programme maintained a strong monitoring framework aligned with logframe indicators and outcome targets, enabling evidence-based decision-making across policy engagement, ecosystem support, private sector partnerships, and WLB competitiveness.

The programme tracked the adoption and implementation of gender-responsive trade policies in Bangladesh, Sri Lanka, and Cambodia, including technical support for monitoring and evaluation frameworks in Bangladesh’s Sustainable Public Procurement (SPP) policy.

Evidence and Learning

SheTrades programme learning has been an ongoing process throughout the implementation phase, mainly achieved through direct collaboration with supported SMEs and institutions, capturing feedback through monitoring visits and interactions in trade events. Key Learnings from FY24/25 include:

1. Collaboration and partnerships remain central to success, especially between SheTrades Hubs, BSOs, and government institutions.
2. Capacity building and training continue to be essential for empowering women entrepreneurs and improving export readiness.
3. Tailored support and networking opportunities for WLBs are important for supporting growth and market access.
4. More gender-focused market interventions have helped change the perspective of private sectors in diversifying their supply chains and bringing more women-led businesses into their supply chains. These interventions have highlighted private sectors with good women-led businesses. Integrating Output 3 into practical interventions in Output 4 has been an effective in leading to positive results, for instance, Ologia Ltd, a UK importer, has included women-led businesses as their suppliers since engaging with SheTrades Commonwealth+ programme
5. Data collection and results measurement are critical for demonstrating impact and guiding future interventions. Countries with outdated SheTrades Outlook (STO) data are encouraged to pilot updates to maintain policy relevance.
6. Leveraging international platforms such as the WTO Trade Policy Reviews and G20 forums has amplified the programme’s reach and influence.
7. Monitoring results through FCDO and ITC platforms is recommended to enhance visibility and advocacy for inclusive trade policies.

Date of last narrative financial report	10 June 2025	Date of last audited annual statement	11 September 2023