## Annual Review Template

Title: Just Transitions for Water Security
Programme Value £ (full life): £39.1m		Review date: 17/06/2025
Programme Code : [AMP ID#] 300596	AMP start date: 17/06/2024	AMP end date: 30/09/2029

Summary of Programme Performance
Year	1
Overall Output Score	A
Risk Rating

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006014.odt
DevTracker Link to results framework:	Results Framework 2.0.xlsx

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

This programme aims to help transform water management by tackling key gaps and barriers to water security through a coordinated set of systemic interventions, designed to complement and ensure synergy with other programmes and always based on strong political economic analysis. The programme goal is to strengthen governance and increase investment in sustainable water use in land-based value chains, to increase resilience and environmental benefits for people, nature and climate. This programme planned to partner with 5-10 lower income countries, over five years, however breadth of the programme is now under review with anticipated ODA cuts. The programme aims to enable vulnerable people in partner countries to access the quantity and quality of water needed to thrive, adapt to climate change and protect their environment. The programme integrates the work of three initiatives: the Water Resilience Tracker (WRT); Fair Water Footprints (FWF); and the Resilient Water Accelerator (RWA).

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The programme has mobilised effectively in its first year. Four out of five components are fully contracted and the fifth component, Programme Management Support is in the process of recruitment. The MEL component was awarded to NIRAS 6 months later than planned due to limited time of key FCDO staff and the GEMFA Framework companies (see below for more detail). Across the three workstreams - the Water Resilience Tracker (WRT), Fair Water Footprints (FWF), and Resilient Water Accelerator (RWA) - there are good early indications of proof of concept and of consolidation of the three initiatives into a single integrated programme.
- The FWF initiative has seen strong demand emerging across sectors with partners, stakeholders, and countries participating in research and advocacy, in particular with the tea sector in Malawi and fruit and vegetables in Morocco, meeting expectations and so justifying an A score.
- The WRT has set the stage for deeper engagement, country-led implementation, and measurable contributions to climate-resilient water governance. Work has focused on expanding and deepening the initiative in specific countries including Malawi, Egypt and Nepal building knowledge products and analytical tools, and collecting evidence for country-led action planning. Country-led demand for the WRT continues to grow. This justifies an A score.
- A strategic review of the RWA operating model [when?] concluded that RWA should become a separate entity outside Water Aid. This, together with some key staffing changes, slowed the pace and impact of RWA in the first half of 2025. Nonetheless the RWA has established high-level buy-in for work in Nigeria, including inputs that have unlocked public funding for water-related investments and strengthened the climate for private investment; in Bangladesh, RWA identified several force factors and potential investment models with relevance for the textiles sector. Overall, we assess this component to score a B for the current year whilst RWA now has a stronger platform for delivery in year 2.

At the country level, the most advanced country partnership is with Malawi, building on a strong UK-Malawi relationship on water since COP26 (FWF and WRT) and strong country presence of Water Witness (FWF). Due to limited government capacity and a weak investment climate in the country the RWA will focus initially on supply chain investment in tea and one other crop.​

WRT and FWF have also made a good start in Morocco, where there is strong political leadership on water, and good capacity, governance arrangements and conditions for investment. However, given the ODA cuts and reprioritisation of geographies at the centre, we anticipate the Morocco programme is unlikely to have financial resource from FY26/27 onwards. Delivery partners are working on an accelerated programme of work with existing partners for the remainder of FY25/26 focused on good value for money and impact. The FCDO team visited Malawi and Morocco and found consortium partners, posts and governments fully supportive. The consortium prepared five Country Entry Strategy Reports to help plan work in Tier 1 countries, which is where at least 2 components are operational); Malawi, Morocco, Brazil, Bangladesh and Peru. Tier 2 countries include Nepal, Egypt and Panama (WRT), Colombia, Chile, India, Lesotho, Zambia, and Kenya (FWF); and South Africa and Vietnam (RWA). The operating model in Tier 2 countries will be reviewed once the Spending Review is complete.

Major lessons and recommendations for the year ahead [1/2 page]

It has been challenging to bring together a diverse set of experts and organisations into a coherent programme using systems thinking. There is strong evidence, such as the recent consortium leaders planning retreat in Washington DC that delivery partners now have a platform to working together towards the programme goal rather than individual workstreams. An example of this is RWA’s focus on investment in the textiles industry in Bangladesh using supply chain analysis and relationship-building work by FWF and drawing on WRT support to national climate policy.
The NIRAS MEL team has accelerated this knitting together through their collaborative work with the consortium on the Theory of Change (ToC), the Results Framework (RF), Value for Money (VfM) and Learning.
The delay procuring a MEL supplier was due to a particularly busy period for both a) key FCDO staff to finalise the ToRs and run the procurement, and b) MEL GEMFA framework companies who were bidding for the next framework contract. This delay means there will not be enough evidence to make decisions about Phase 2 in the original time frame (Jan-June 2026).
Financial forecasting by some delivery partners was weak with a significant (approximately £400k) underspend reported just one month before year end. Programme Management measures and procedures have been tightened up to make sure this does not happen again.
In addition, unanticipated changes to ODA budget, priorities and geographic focus means that the JTWS programme strategy and resource need to adapt and be more tightly focused. We are therefore proposing a 6-month extension to Phase 1 to enable more effective, evidence-based decision-making to shape the remainder of the programme. WRT and FWF both recruited in house MEL coordinators once their grants were awarded and were thus able to benefit most from the NIRAS support. RWA are about to recruit.
Rationale for extending JTWS Phase 1 by six months
A key objective of the midline evaluation of JTWS is to generate evidence that usefully informs the design and delivery of Phase 2. The midline evaluation will therefore be conducted at the end of Phase 1. Under the current scenario, Phase 1 of the programme ends in June 2026 at the latest, with the implication that midline data collection will need to take place between February - April 2026.
The evaluation is taking a case-study approach focussing on Tier-1 countries to test the Theory of Change. Joint planning and mobilisation has begun in the three Tier 1 countries, and is expected to be fully operational in the second half of 2025. This leaves too little time for JTWS partners to work together in country before midline evaluation data collection starts in early 2026. This means the evaluation would be unlikely to collect many meaningful outcome-level results which could in turn potentially limit the ability to meaningfully assess the programme's VfM - another key factor for the design and delivery of Phase 2. As above, evidence-based decisions are all the more salient given anticipated need to pivot towards a sharper programme focus in Phase 2.
Alternatively, the evaluation could conduct more in-depth assessments in Tier 2 countries where more progress will have been made within individual workstreams by early 2026, but this would then limit the ability to assess the effectiveness of bringing the JTWS workstreams together under one programme.
Key Recommendations
1. Extend Phase 1 by 6 months from 24 to 30 months so Phase 1 will end in December 2026 to enable collection of good quality data in Tier 1 countries, facilitating effective decisions on the future of the programme.
2. Sharpening focus: Use evidence from the annual evaluation in December and emerging ODA priorities to make best use ODA to catalyse systemic change. Options to consider should include cutting the number of Tier 1 countries from five to three, limiting Tier 2 countries to those JTWS is currently working and adapting to a lighter touch operating model.
3. Continue the MEL focus on testing the programme theory of change in Tier 1 countries.
4. Deepen understanding of the materiality of water risk to financial stability and the role central banks, supervisors and other parts of the financial system in adapting to water risk in through better regulation and guidelines.
5. Reinforce processes to further improve financial reporting and forecasting.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The ToC rationale is that the challenges to increasing water security and improving water governance that benefit vulnerable people and restore nature are complex and wide-ranging, mean that no single institution, government or other stakeholder can do it alone. Changing the dynamics require systemic change at several levels. The integrated programme approach of the WRT, FWF and RWA components, aims to strengthen policy, accountability and investment to catalyse the systems change needed to increase water security in the face of economic, environmental, and social challenges. Whilst it is early to identify clear causal pathways the country entry strategies set out the many options that will be tested during the rest of Phase 1, such as a) whether better national climate policies matter at catchment level, b) can the strength of buying power in supply chains to improve water management by growers, and c) if the market might pay for investment in reliable clean water to consumers.

Changing Context
The original business case, Theory of Change, and Results Framework were developed during a period of relative momentum for ESG action, official development assistance (ODA), and global consensus around the sustainable development goals (SDGs). That context has changed. A reduction in global ODA, weakening international political support for SDGs, and a growing backlash against ESG, have all contributed to a more challenging environment for water stewardship and climate-nature action. There is diminishing corporate focus on ESG through branding and reputation, but businesses are still highly engaged in managing water-related impacts, even if the focus is shifting. Whilst there is no doubt that water remains a critical issue due to its direct effect on operations, supply chains, and financial risks – i.e. the materiality of water risk to businesses - nonetheless it is anticipated that recruiting and retaining corporate signatories to the Fair Water Footprints initiative will be more challenging.

Geopolitical shifts together with economic uncertainty have seemingly shifted the attention of governments, investors, and companies away from long-term sustainability goals, with water risks often deprioritised, to shorter term growth and national security. Yet at the same time there has been a growing understanding of nature risk (and within that water) to economies and national security which is felt directly through food and energy supply chains. This has brought in a new set of powerful stakeholders - those in charge of financial stability and economic growth, who are taking a growing interest in water.

As a result a number of governments and sub-national authorities (e.g. Spain, the Netherlands, UK, Malawi, Morocco, Brazil, Lagos, Sao Paolo) are starting to prioritise water, investing in water resilience as an economic opportunity, taking tough decisions such as increasing water tariffs, improving conditions for investment through legislation and strengthening regulation of water abstraction. Governments are looking beyond their own budgets to other levers to increasing investment in water resilience.

Theory of Change main developments

In June 2024, the JTWS partners submitted a revised version of the Theory of Change. This update captured the impact of “improved resilience of communities, ecosystems and economies” and this version was included in the Accountable Grants.

The MEL team further revised this ToC, in close collaboration with FCDO and partners, to rationalise inputs and outputs, add in a layer of intermediate outcomes, restructure the outcomes to align with the three workstream result areas and to clarify the programme’s sectoral contribution to climate resilience.
Supported by the MEL team, this review process ensures a shared measurement approach and strong linkages between the intermediate outcomes and transformational goals of the programme. This new approach will be reflected in the next annual review.

Revised Programme Outcomes
1. Improved policy and regulatory environment for inclusive climate and water resilient development
2. National and international market actors adopt and promote fairer, more sustainable and resilient water use practices in global trade and supply chains
3. Financial flows for climate resilient water initiatives are mobilised
The Intermediate Outcomes set out the changes expected in key stakeholder groups; policy makers, civil society, corporations, financial institutions/investors and project developers.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The programme is in the early stages of implementation and has not begun reporting on the expected programme-level outcomes. A revision of the Results Framework will be completed in July. This will include changes across the results chain and the associated indicators and will incorporate clear milestone targets throughout which will be used for future impact and outcome-level reporting, once agreed. Early indications are that the policy and supply chain workstreams are on track whilst the investment work has been delayed somewhat by the establishment of a separate company and a change in leadership.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The programme is in the early stages of implementation, and this annual review has been unable to report of programme-level outcomes. However, assumptions are generally holding, context is still relevant and expected progress is on track making a strong case for continuation. The programme should be ready to report against all outcomes and indicators by the next AR. The JTWS ToC remains valid and highly relevant to the FCDO’s climate and nature objectives with its focus on transformational change through systems thinking and the use of technical assistance. Water insecurity continues to be the most severe consequence of climate change on the poor and on nature, whilst at the same time the water sector is also a significant cause of climate change (10% of emissions). This in turn undermines growth and stability.

Given the importance of this programme in the wider FCDO ICF portfolio and the performance of partners in the mobilisation stage, the programme should continue with a focus on driving coherence between components and speeding up delivery, particularly by the RWA.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	(FWF): Evidence, data, guidance, pathways, and tools provided to a critical mass of countries and industry partners to incentivize, act on, and jointly pursue equitable, fair, and sustainable governance of water demand, use, and supply across sectors and throughout supply chains.
Output number:		1	Output Score:	A (NB: there is no milestone for the second indicator and no population size for the third indicator)
Impact weighting (%):		33%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone (MS) for this review – MS1 June 2025	Progress
Systemic change in governance, policy, and practice to incentivise Fair Water Footprints in at least 8 ‘producer’ and 8 ‘consumer’ countries by 2027. For example: mandatory disclosure, business licensing, subsidy, regulatory and trade policy reforms.	4 Producer countries & 4 Consumer countries engaged, with key governance/policy/practice reforms planned or underway in at least 2 countries	Engagement with five producer countries (Peru, Malawi, Morocco, Zambia and Zimbabwe), and one producer and consumer country (Brazil), plus a number of consumer countries through the G20 / Four countries with key governance/policy/practice reforms planned or underway
A combination of 200 highly impactful and influential companies and investors are making and disclosing demonstrable contributions towards Fair Water Footprints including through systemic change at enterprise, sector or portfolio scale.	Set annual milestones using CDP 2024 disclosure dataset	CDP dataset was cleaned in Q2 and analysis begun in Q3. By the end of Q4 it is planned to present an analysis of the data with key recommendations for use to benefit FWF objectives.
Action to achieve Fair Water Footprints by stakeholders drives material change for improved water security for at least 20 million people	Target populations (10M) scoped and action underway	Target populations scoped and collective action underway in key regions in Peru, Malawi, Zambia and Zimbabwe (not yet possible to calculate total population size)

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Results reflect efforts to engage countries and key stakeholders within countries through a variety of approaches, with numerous countries engaged and action underway. This is a demand-driven programme that has been seeing high levels of engagement and commitment from country counterparts. There are some issues of definition and coherence with indicators and milestones, including the need to adapt the approach as it has developed and since the indicators and milestones were defined. These are being addressed as part of the ToC and results framework revisions described above.

Engagement with producer and consumer countries to promote systemic change in governance, policy, and practice to incentivise Fair Water Footprints: Scoping is ongoing in a number of producer and consumer countries, at FWF level as well as at JTWS level, where the approach will differ. At JTWS level a joint programme value proposition is being developed, with a specific role for FWF, to be tested firstly in Morocco,. FWF are engaging with a number of other countries separately, working to identify where activities are most needed and relevant. Six countries have been engaged individually alongside a collective engagement with the G20, plus some related bilateral engagements.

Global: The G20 engagement came through CDP’s role as a knowledge partner to the G20 Sustainable Finance Working Group (SFWG), which has been extended through 2025. The SFWG met in South Africa in March 2025. The engagement focussed on embedding water security into transition planning, relationships with financial regulators and positioning FWF within global sustainable finance dialogues. A closed-door roundtable, “Synergies for Sustainability: Streamlining Disclosure for Earth-Positive Transition,” was convened by CDP on the margins of the SFWG in South Africa, bringing together financial institutions and policymakers, including central banks and regulators from Brazil, Indonesia, and South Africa. Bilateral meetings were held with the Hong Kong Monetary Authority (HKMA) and Brazil’s Securities and Exchange Commission (CVM) to explore the integration of CDP data tools, including SME water data, into sustainable finance strategies—supporting resilient transition planning.

The following describes the individual engagement with five producer countries:

Malawi: Water Witness led a JTWS Leadership Forum workshop in Malawi, between 4–5 March 2025. This brought together over 100 stakeholders from government, business, finance, civil society, and academia. The forum spotlighted both the urgency and opportunity to strengthen national water governance, with promising developments including the launch of the WASH Compact and new ESG disclosure requirements for companies listed on the Malawi Stock Exchange. Opportunities were identified for FWF to support coordinated national engagement through a sector review and plan, document local stewardship case studies, and collaborate with financial institutions—including the Reserve Bank of Malawi—on ESG standards. JTWS is a core partner in the sector plan, and FWF has work plans to deliver the case studies and engage with the central bank.
Morocco: a scoping mission convened 62 stakeholders from government, civil society, academia, the private sector, and finance to examine the country’s shift from traditional dams to desalination and inter-basin transfers. The mission highlighted key concerns around affordability, energy use, and environmental sustainability, and revealed strong interest in collaboration from major UK and French importers such as Azura, Driscoll’s, and Fresca. A detailed mission report was submitted to FCDO. A collective action initiative will focus on the Souss Massa basin facilitated by the Agadir University.
Peru: In Quarter 2 there was a mission to Peru to engage with and set up an FAO-led taskforce to bring forward recommendations from the earlier Ica Valley report. The FAO-led FWF Taskforce — strategically advised by Water Witness — gained interest from six new stakeholders. The Taskforce aims to align with government priorities (MIDAGRI/ANA), engage development partners, and reflect the needs of civil society, academia, and communities in Ica.
Zambia: In Quarter 3, an FWF scoping excursion was conducted in Zambia. It engaged with 24 stakeholders representing government, civil society, international development partners and academia. The key issue was water pollution from collapsed copper mine tailings dams, (of which there had been a recent incidence at the time of the visit) and the potential to reduce future environmental damage in light of the Zambia Government’s objectives around increasing mineral outputs.
Zimbabwe: The Community Water Alliance, who are researching the impacts of mining on water resources in Zimbabwe, held an inception meeting which resulted in the formation of a cross-ministry steering committee to take the research reports finding forward in subsequent policy reviews.
Promoting contribution to FWF from highly impactful and influential companies and investors: The indicator for this is behind schedule due to the timing of the disclosure cycles. The target for this reporting period was to set annual milestones from analysis of the CDP 2024 disclosure dataset. This is ongoing. The key deliverables to date are development of water-related Key Performance Indicators (KPIs) aligned with Fair Water Footprints principles, processing of 2024 disclosure data, and finalisation of the 2025 CDP disclosure cycle timeline. The 2024 data will provide a baseline of corporate and FI performance against FWF principles which can be assessed against. The 2025 data will be used to assess the impact of engagement in 2024 (the disclosure cycle runs April - September 2025). The Water KPIs are in the process of being finalised and will be published in autumn 2025. The KPIs define best practice across five key areas in order to track progress on the core pillars of the FWF approach: disclosure coverage, governance and processes, metrics and targets, implementation, and stakeholder engagement.
Scoping and action to drive material change for improved water security amongst target populations: The engagement activities described above in relation to the first indicator are the key mechanism for driving improved water security for target populations, alongside the Rapid Action Fund, a competitive small grant scheme. During the reporting period the Rapid Action Fund grant process was launched and funding awarded to two prioritised projects:
- WRAP will conduct a scoping study of WASH needs in communities around the Lake Naivasha basin, identifying opportunities for UK businesses to contribute through collective action alongside WWF.
- The Water Integrity Network will co-develop a Handbook on a Just Water Transition/Fair Water Footprint in collaboration with civil society representatives from Bangladesh, Peru and Malawi who are active in water stewardship and water rights.
At present it is not possible to establish the size of the population reached, in part because the exact target geographic areas and populations are not finalised. This will be revisited and a target date set at the next PESC[1].
[1] Programme Executive Steering Committee, the programme governing body that chaired by the FCDO
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no changes to this output in the past year. Changes are expected as a result of an ongoing programme-wide review of the ToC and results framework led by NIRAS.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
- No previous recommendations.
- Recommendations – ensure the revised Results Framework has clear impact weightings, baseline data, and targets.
Lessons learned:
- Emphasise Water Stewardship as a Risk and Resilience Priority: To maintain corporate engagement in a challenging ESG environment, FWF should more clearly align its value proposition with business risk management, supply chain resilience, and financial materiality.
- Adapt to a Shifting Global Context Through Strategic Advocacy: Given the political and financial headwinds facing the SDG and ESG agendas, FWF needs to focus on smart, diplomatic advocacy, meaning shifting from reputation risks to security of supply and contributions to growth through international leadership and alignment with broader priorities such as food, energy and national security. FWF needs to pivot to using the materiality of water risk to business and economies to generate momentum for water stewardship.
- Strengthen JTWS Coordination and Internal Alignment: Internal communication gaps and lack of clarity has affected delivery; improving clarity, responsiveness, and shared ownership across the programme is essential for efficiency and collective impact with clear roles and responsibilities, and delivery plans, in the governance structures at programme and country level.
- Support Civil Society and Grantees to Deliver in Hostile Operating Environments: Shrinking civic space and financial pressure require more robust risk management, safeguarding, and oversight mechanisms to protect partners and sustain grassroots delivery.
- Bridge the Gap Between High-Level Commitments and Local Action: To deliver lasting outcomes, FWF must ensure national policy wins translate into tangible, on-the-ground change, especially through better alignment between regulatory frameworks and implementation support.

Output title	(WRT): Knowledge base and capacity for designing integrated plans, policies, programmes, and strategies for inclusive, accountable, climate and water resilient development.
Output number:	2	Output score:	A
Impact weighting (%):	33%	Weighting revised since last AR?	No

Indicator(s)	Milestone for this review – MS 1 June 2025	Progress
Number of governmental organisations (ministries) and Non Governmental Organisation are actively participating in identifying how to improve plans by mainstreaming water resilience.	Overall = 24 / Government Ministry = 12 / NGOs = 12	Total = 51 / Governmental organisations/ministries (GOs) = 24 / NGOs = 27
Number of stakeholders participating in technical capacity building workshops and training programmes as a result of support from the programme.	Overall= 100	Total = 311 / Brazil[2] – 67; Malawi–96, Nepal–46, Egypt-40, Morocco-62
Number of new knowledge and communications products (including trainings) - on designing integrated plans and strategies for accountable, climate resilient, sustainable, and inclusive water basin management at basin, national and international levels - produced and disseminated	Total = 7 / Training Reports = 3 / Deep Dive Report = 1 / Country Report = 3	Total = 3 / Deep Dive Report = 3 / Country reports and training reports = 0 (now to be delivered in Q1 2025-26)
Number of countries in which the Water Resilience Tracker is applied or used in regular national planning cycles by country stakeholders	Total = 4	0 (but initial foundations laid in 4 countries: Brazil, Egypt, Malawi, Nepal)
[2] Note that IDB were the main funder of work in Brazil. FCDO funding started in March 2025.

The results reflect the extensive work done to engage stakeholders in countries where the WRT has been introduced. Initial engagement has also been made in countries new to WRT, but this has not yet produced results. Milestones for governmental and non-governmental stakeholder engagement have been substantially exceeded. The knowledge products/reports milestone has also been exceeded, although the other knowledge products related targets have been narrowly missed (Country reports and training reports). The WRT aims to ultimately advocate for the inclusion of water resilience in national and sub-national climate strategies and policies so the application of the WRT for use in planning cycles will take time. However, through extensive country engagement and consultations in program countries, the WRT is on track to meet the milestones set out in the overall programme period,
Engagement and participation of governmental organizations/ministries and NGOs in identifying how to improve plans by mainstreaming water resilience: Substantive progress was made during the reporting period in engaging key governmental and non-governmental national stakeholders across four countries: Brazil[3], Egypt, Malawi and Nepal. Inception workshops and bilateral consultations have been held in all countries (albeit in Egypt it was more of an inception meeting), laying the foundation for integrating of WRT into national climate and water planning systems. A summary of progress in each country is described below.
[3] Idib
Brazil[4]: Results from initial engagement were presented to partners in December and to other ministerial representatives in March (approximately 50 in-person attendees and 17 online attendees). WRT held a validation workshop and published a Phase I report in January 2025 and set the basis for an ambitious Phase II programme
[4] Note that IDB were the main funder of work in Brazil. FCDO funding started in March 2025.
Egypt: A scoping mission was conducted in January 2025 in which in-depth discussions were held with the Ministry of Water Resources and Irrigation (MWRI) and the Ministry of Environment (MoE) to determine priority areas of collaboration and support. Both ministries expressed strong commitment to integrating water security into climate adaptation planning and on-the-ground actions.
Malawi: key relationships have been established with the Ministry of Water and Sanitation, the Department of Climate Change and Meteorological Services, and the Ministry of Finance.
Nepal: the WRT team are closely involved in the NDC 3.0 update alongside the Government. A one-day workshop was organized to introduce the WRT project and discuss possible avenues for engagement on the 20th of March 2025, attended by diverse stakeholders including Government, Bilateral partners, Private sector, IO (International Organization), Media, civil society and others. Following the workshop the team has participated in provincial level consultations that feed into national planning processes.
Participation in technical capacity building/training: Inception meetings included sessions to familiarise participants with the WRT tool and key concepts related to climate and water resilience terminology and indicators. The workshops also had technical sessions in which participants broke into smaller groups for discussion and presentations on specific topics. Training reports will be integrated into the respective country reports.
Knowledge and communications products and tools: Three key knowledge products were developed to inform national planning and international dialogue. These knowledge products cover the following: a Water General Trends Report, a report on Integration of Water Resilience in NDCs, and an Evaluation of Investment Strategies in Water Resilience, and a revision and Summary of the WRT Guidance. The annual milestone target has been exceeded. Delivery of country reports and training reports is slightly behind the milestone target: these are in development and will be delivered in Quarter 1 of year 2025-26.
Additional knowledge products include a Partner Stocktake report (draft) and revised WRT questionnaire, Joint Country Entry Studies (JCES) are underway and in advanced stages for priority countries. Participation in various high-level events to engage with stakeholders and disseminate information and findings related to WRT, including COP 29, UNCCD COP 16, Africa Water Week, and Cairo Water Week.
Application of the Water Resilience Tracker in regular national planning cycles by country stakeholders: While implementation of WRT country activities has commenced during this period, full application of the recommendations from these activities has not happened yet. Scoping and inception activities have laid the foundations for integration of WRT into national climate and water planning systems. Draft Country Action Plans are being developed in Nepal, Brazil, Malawi, and Egypt, with priorities identified through inclusive consultations. These plans will guide technical assistance, financing strategies, and policy integration aligned with national goals.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
- There have been changes to the output indicator, based on an RF update by WRT in March 2025 focused on strengthening WRT impact level (JWTS) output level indicators, including making more specific and measurable.
- There are further plans to update these based on the overall changes to the results framework currently underway by the MEL team.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
- No previous recommendations.
- Speed up delivery of outputs at country level.
- WRT to continue to engage with the NIRAS team on further updating their RF indicators and, based on that, develop/update targets and baseline data and to update/develop data collection and aggregation guidelines for each indicator.
Lessons learned:
- Need for flexibility in implementation - regular assessment and realignment of timelines can mitigate delays and help achieve progress even in challenging circumstances.
- Collaboration enhances impact: participation in high-level events (e.g., Africa Water Week, Cairo Water Week, COP29) reinforced the value of collaboration and visibility. These engagements not only raised the profile of the WRT but also fostered meaningful connections that can facilitate future uptake of the tracker in national planning processes, evidenced through written requests from approximately 50 countries for assistance.
- To have impact WRT needs to now focus on implementation in selected countries, including capacity building and knowledge sharing, in order to empower governments and other stakeholders to better understand WRT, and with it the climate water risks they face, and to strengthen planning to reflect this.
Output title	(RWA): Increased number of multi-sector, innovative, and adaptive projects with the potential to generate financial and non-financial returns in climate resilient water management, infrastructure and services directed to benefit vulnerable people and restore nature. Improved enabling environment for private sector financial flows, which can be leveraged to invest in water resilient adaptation measures. Long term pipeline of investment opportunities created and financial flows underway.
Output number:	3	Output score:	B
Impact weighting (%):	33%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review – MS 1 June 2025	Progress
Number of local contexts ('local markets') identified as 'primed' for acceleration, with consideration for e.g. high-level policy/government buy in to water-related climate resilience; water security needs; climate or adaptation potential; and financial/economic outlook for private investment, and completion of a standardized format / method for conducting these assessments.	At least 4 contexts/countries screened and 2 selected as primed for engagement / Assessment tools developed / 1 brief published	10 local contexts screened; 1 selected as primed, with 3 in the pipeline / Screening tool and methodology updated / Market Brief on the garments sector to be published in June 2025
Number of private and commercial investors aware of discrete investment opportunities in local contexts, including but not limited to investing in water resilient adaptation measures using NbS.	>50 new investors signed up to the newsletter mailing list / 100 investors directly engaged / +15 investors engaged with RWA's deal-oriented programming.	120 new subscribers to RWA newsletter mailing list / 123 stakeholders directly engaged (Bangladesh – 39, Nigeria – 54, global - 30) / Number investors engaged with RWA’s deal-orientated programming is not applicable due to a change in approach
Number of in-country project developers with skills and know-how to design and develop investment opportunities with potential for private / commercial investing.	100 participants undertaking training with / ≥20 undergoing intensive skill development​ / Reflections on training and development of tools underway	For now, this is still at the preparation and planning stage. This milestone should have been set for Year 2 and is due to be updated following the strategy review held in Year 1.

Briefly describe the output’s activities and provide supporting narrative for the score.
This is probably the most ambitious workstream and the one that has undergone the most learning and adaptive programme since the grant was awarded, resulting in a shift away from targets around actual investments, towards using those investment pipelines to identify the shifts in policy and regulatory environment that will attract investment. This learning has impacted on the relationship between RWA and its incubator, WaterAid and resulted in the confirmation of the original intent of spinning off RWA as a separate but wholly owned subsidiary of Water Aid. However, this has happened at the expense of the original targets in the first Results Framework and this is reflected in the score of a B for this workstream.
That said other targets have been considerably exceeded: markets screened, investors signed up to the newsletter and directly engaged. In 2024 RWA identified two markets as ‘primed’ for engagement: Bangladesh’s textile supply chain, and Lagos’ municipal services market. In practice, RWA’s work in Bangladesh has been fully selected as ‘primed’ for acceleration, while Lagos, with the loss of USAID’s US$42 million LUWASH program, which focussed on municipal service strengthening, meant the RWA can no longer leverage those reforms, and so the municipal services market was not selected. With greater uncertainty over ODA spend globally RWA should continue its shift to other sources of water investment. Work is underway to assess three other markets: Agricultural supply chains in Morocco and Malawi, and data centres in Brazil. There has been particular learning and adaptation on the approach to engagement in deal-orientated programming, which has rendered the milestone on this not applicable (see below).
Identifying acceleration primed local contexts/markets: The reporting period was focused on understanding local contexts/markets and identifying those that are ‘primed’. Primed for engagement means there is demonstrated potential for the RWA to operate in a clearly defined market facing water risk and apply its tools and approaches to rapidly building market intelligence to identify “force factors” and potential investment models to motivate investment.
Early in the reporting period RWA updated its screening tool and methodology then went on to test it. Screening was undertaken for 10 countries: Brazil, Colombia, Egypt, India, Malawi, Morocco, Peru, South Africa, Tanzania, and Viet Nam. This exceeded the target of at least 4 countries screened.
In Bangladesh countrywide scoping work, which sought to identify opportunities for impact informed by the RWA decision to focus on opportunities for water efficiency and water effluent treatment opportunities in the textiles and garment sector. The Bangladesh garment sector has now been assessed as primed for acceleration, demonstrating tangible opportunities for resilient water investment. The RWA will be publishing initial findings about the opportunity space, aimed at engaging garment industry brands and investors, by July 2025.

Having conducted extensive work in the municipal water market in Lagos, Nigeria including setting up the Lagos Water Partnership, the RWA concluded that there is significant work required to develop investment opportunities and therefore this specific market is not currently primed for acceleration. The RWA is now working with partners to explore different markets in the Lagos area, and a report on watersheds is currently underway.
Meanwhile, in the new locations work is underway to identify opportunities and assess acceleration primed status in locations/markets in three countries: Malawi, Morrocco and South Africa. These are all places where the RWA has identified market structures, where there’s clear water security risk and where private/commercial actors are more likely to engage.

Promoting awareness of discrete investment opportunities in local contexts to investors: The value proposition of the RWA is to move beyond traditional “water sector” boundaries and actively engage with investors and developers to understand the barriers and drivers they face when it comes to water investment. The RWA has exceeded the newsletter mailing list sign up and direct engagement milestones: 120 new subscribers have been added to the RWA newsletter mailing list in the reporting period and there has been direct engagement with at least 143 investors, developers and other stakeholders.

Regarding direct engagement, RWA had in-person engagement with 54 investors in Nigeria in Q3, building on previous direct engagement throughout the year through the Lagos Water Partnership (LWP). These consultations confirmed that there is real appetite for investing in Lagos’ water sector, but only where projects are well prepared, de‑risked, and supported by credible public‑sector commitments. Investors value stable structures and predictable risk allocation over high returns, prefer blended finance anchored by DFIs, and welcome the LWP as a coordination and de‑risking platform. The Partnership’s current emphasis on prefeasibility, PPP structuring, and regulatory clarity is therefore well aligned with investor expectations.

Lagos Water Partnership is a vehicle formed and led by the RWA to build consensus around action on water and unlock new sources of financing for climate-resilient projects. Actors engaged ranged across development financial institutions, private investors, and public Government financial authorities, including EY, DLA Piper, Howdens, ARM Harith, AFC, Climate Fund Managers, Nestle, AfDB, and the Federal Ministry of Finance.

There has also been direct engagement in Bangladesh with a range of investors. The RWA had face to face meetings with 39 investors in Bangladesh exploring opportunities for action on water resilience and the garment sector, ranging from development financial institutions, private investors, and public Government financial authorities, including Standard Chartered Bank, City Bank, HSBC, JICA, H&M, Primark, Bangladesh Apparel Exchange, and the Bangladesh Central Bank. In June, findings will be presented to a further 30 investors, developers and brands in London.

These consultations confirmed strong awareness of escalating water risk and broad interest in financing solutions—but also revealed a coordination failure between brands, factories, and financiers. Capital was available, but investment was constrained by weak demand signals, short sourcing horizons, uncertain returns, and limited blended‑finance mechanisms. RWA’s early consultations successfully reframed water as a financial risk and laid the groundwork for a more deal‑oriented approaches based on this market building rather than transaction execution work.

Building in-country capacity to design and development investment opportunities: Limited results have been achieved in this area to date, and following a mid-year review learning showed that, in contrast to original assumptions, the markets where the RWA operates are not sufficiently advanced to make rapid progress on deal development without starting further back in to the development process than original envisaged. In response, the RWA is now reaching further “upstream” into the project development pipeline to reshape markets for investment and is also shifting to become an engagement mechanism to build and support networks, and showcase the deals, opportunities and business models being developed in response to climate-related water risk.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
- No changes to the output in this reporting year.
- Outputs and related indicators for this workstream will be revised based on the overall changes to the results framework currently underway by NIRAS; RWA had also planned to update its results framework based on its strategy revamp in early 2025.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
- This is the first AR so no previous recommendations.
- Recommendations are to ensure the revised Results Framework has clear impact weightings, baseline data, and targets.
Lessons learned:
- There are limited benefits to addressing a whole water system through the RWA’s model – results are better when focusing on a discrete market. There is a strong demand for collaboration from investors when focussed on working with specific markets to develop clear detailed business cases for water deals.
- There is a high ‘finance demand’ for pre-feasibility funding for projects that aren’t designed for climate resilience or financial viability. The RWA needs to focus on lowering transaction costs and shortening time horizons for deal development, avoiding/mitigating the risk of conducting pre-feasibility studies to advance poorly conceived projects with low potential for success or working on 'system strengthening’ efforts relating to water policy with no measurable effect on investment flows.
- Assumptions by some project backers around market readiness proved not to hold - the markets were not sufficiently advanced to make rapid progress on deal development without significant work early in the project development timeline.
- Investor engagements showed strong awareness of water risk but more conditional and uneven appetite to invest, with demand‑side constraints and coordination challenges emerging as key barriers.
- This learning has informed a shift towards greater emphasis on market‑building and demand anchoring alongside project acceleration.
- Strong formal and informal relationships are critical across various stakeholder interests required to approve a deal to accelerate the development process.
- Across the 10 countries screened there are significant climate resilience risks and investment gaps and common barriers for investment.
- The private sector has high potential to support climate-resilient water interventions through innovation, investment, and service delivery.
- Better measurement metrics and more accurate valuation of water resources are critical for attracting broader investment. There is an opportunity explore better ways to automate risk assessment, financial modelling, and feasibility analysis, lowering costs and accelerating investment, based on largely existing available data across the water sector.
## D: VALUE FOR MONEY (1 page)

Value for Money Assessment
The programme has mobilised effectively during its first year but remains in the early stages of delivery. Delays in procuring the MEL supplier have limited data availability for a full VfM assessment. Nonetheless, this assessment uses the FCDO’s 5E framework, drawing on available results and testing business case assumptions.

Economy:
Using grants to not-for-profits already embedded in the three initiatives has helped secure high-quality inputs at low cost compared to the market rates for service providers[5]. However, risks of scope creep - where some aspects of the project expand beyond initial requirements leading to delays and potential increased cost—evident in MEL procurement delays—could lead to cost overruns and reduced economy.
[5] Fees, fees, fees: How much can I charge as an independent consultant? Impact Consulting Hub Nov 2022 survey.

Efficiency:
All 5 components have been mobilised except for the Programme Management Support: Accountable Grants for the Water Resilient Tracker and Resilient Water Accelerator were issued in July, and for the Fair Water Footprints in August (delayed for due diligence). MEL contract with NIRAS began in February ‘25. However, delays in MEL procurement and the absence of robust metrics have limited our ability to quantitatively assess programme efficiency. Further delays in delivery have resulted from restructuring of the consortium. For instance, RWA’s is currently becoming independent from Water Aid, a process which has resulted in less bandwidth for engagement with programme delivery.

Effectiveness:
The programme is leveraging existing networks through its implementing partners.
- FWF has generated strong engagement and cross-sector participation, with nearly 400 change agents trained including CSOs, citizens, and community representatives. Key activities included outreach and research in Zambia, and training for grantees in Zimbabwe.
- WRT has laid foundations for country-led implementation and measurable contributions to climate resilient water governance through expanding work with countries, building knowledge products and analytical tools, and data collection to make the case for country action planning
- RWA has secured high-level buy-in in Nigeria to engage on both water security planning and engagement with investors. It has also made significant inroads into Bangladesh’s textiles sector, identifying a good case for addressing water risk. It is too soon to say whether the tools and methods RWA is working on can be used across market structures and locations to develop deal pipelines. These will be tested in FY26 as part of programme expansion to new countries. Overall effectiveness of RWA has, however, been affected by the spinout of RWA from Water Aid.

Equity:
The programme will be active in at least 3-5 tier 1 countries with partners scoping local markets and engaging disadvantaged groups through participatory research and outreach. Equity approaches, particularly on GEDSI, vary among partners – those well-established development organisations performing better than the more recently established, notably the RWA. FWF is focussing on introducing equitable principles in multilateral organisations and private companies’ management and use of water, while WRT is working with governments to introduce a GEDSI lens to policy-making processes. RWA takes a ‘do-no-harm’ approach to GEDSI, given that investment deals aim to address root causes of water insecurity, with the intention to benefit vulnerable sections of the population. RWA is expected to address this comparative weakness in the next year.

Cost-Effectiveness:
The programme is designed to achieve cost‑effective outcomes by prioritising upstream, systems‑level interventions that have the potential to deliver large‑scale and sustained benefits relative to expenditure. By working through established partners and existing national, market and institutional processes, JTWS seeks to influence policy, investment flows and private‑sector behaviour in ways that extend beyond the direct impact of programme spending. Early delivery has focused on a limited number of Tier 1 countries, enabling concentration of resources where political commitment, institutional capacity and demand for reform are strongest, thereby reducing delivery risk and maximising the likelihood of results. While it is too early to quantify cost per beneficiary or leverage ratios, early evidence suggests the programme is on track to deliver favourable cost‑effectiveness by avoiding stand‑alone investments, reducing duplication with other donor programmes, and using relatively modest technical assistance to catalyse wider public and private action. Robust assessment of cost‑effectiveness will be strengthened as outcome‑level data and financial leverage metrics are generated through the revised results framework and midline evaluation.

Overall Assessment:
Despite early-stage limitations including delays and poor financial forecasting, the programme demonstrates strong potential for delivering good VfM. Most components are operational, business case assumptions remain valid, and VfM metrics (both ‘core’ and ‘extended’) are under development with the MEL team. The implementation of these should be prioritised, aiming for preliminary estimates by December and a full assessment in next year’s Annual Review and beyond.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The current overall risk for JTWS is Moderate.

This programme has a cautious appetite to risk because most activities carry a moderate degree of residual risk.

This year a due diligence assessment was carried out for CDP. We identified a few risks that we noted in the DDA. CDP created an Action Plan and the recently updated one shows that they have completed most of the actions and some are ongoing.

Existing DDAs were already in place for other lead partners. However, now that RWA is becoming its own entity separate from WaterAid, a new DDA for them will need to be conducted this year.

A comprehensive risk register was developed as part of the programme start-up process and is reviewed quarterly on AMP alongside the risk appetites which have been set per category (see above). No risks have been identified outside of the directorate’s risk appetites. During the International Fraud Awareness Week in November, we sent letters to partners asking them to communicate the FCDO’s requirements on counter-fraud to their staff and downstream partners which they actioned. During Q4 CDP approached us regarding onboarding 2 Downstream Partners in Malawi and Peru. We discussed with the Due Diligence Hub and Country offices for extra precaution. As a result, we could not proceed with the first one as we do not fund the Malawi government directly. The Peru one was put on hold until solutions were found. We have added Risk as one of the outstanding items on the Quarterly Reports and also discuss it at the regular PESC Meetings.

We have a receptive appetite to policy and programme delivery, and strategy and context risks which are considered moderate to high as systems transformation, as well as governance, policy, and market reform historically has been challenging to deliver and brings a set of risks in managing political economy and to maintain coalitions of support for reforms to take hold. A receptive profile recognises these inherent risks but acknowledges the potential benefits to reform taking hold in delivering triple win outcomes for people, climate and nature - and the space for mitigating some of the risks. Recognises complex political economy behind driving policy reform.

We have a minimal appetite for safeguarding risk, in line with departments risk appetite for Safeguarding. This reflects our zero tolerance for safeguarding issues and our commitment to effective safeguarding, whilst recognising willingness to accept only the risks necessary for effective delivery.

We have a cautious appetite for people risk, Limited acceptance of risk in order to build a high-performing, common culture with diversity and inclusion.

We have a cautious appetite for financial and fiduciary risk, aligned with the directorate and FCDO risk appetite. financial and fiduciary risks are a key element of monitoring and stakeholder management. There have been no reported instances of aid diversion.

We have a cautious appetite for reputational risk, aligned with FCDO risk appetite. Failure of the programme or significant safeguarding or fiduciary risks emerging present a reputational risk. As per ECED's risk register - this reflects our limited acceptance of the reputational risk necessary to pursue our national interest overseas and strategic goals for people planet and nature, with public resources. Strong mitigation actions in place and act early to escalate reputational risks up the risk management chain.

Update on Partnership Principles

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

The programme has been managed effectively during its first year of delivery, following approval of the Business Case in June 2024. Two Accountable Grants (AGs) were issued within one month of approval, demonstrating strong initial mobilisation. The third AG was subject to delay due to the requirement to complete a Due Diligence Assessment (DDA) on the delivery partner, which, while affecting early delivery across one workstream, this was appropriate to manage fiduciary and delivery risk. This experience highlighted the importance of sequencing commercial assurance processes realistically within ambitious mobilisation timelines.

At the point of issuing the AGs, FCDO ensured that all partners met core commercial and compliance requirements, including publication of Supplier Code of Conduct documentation, submission of Delivery Chain Maps and Delivery Chain Risk Assessments, confirmation of downstream DDAs, and signature of the UK Aid Visibility Statement. Given the complexity of the consortium model, with three consortia each comprising multiple delivery partners, additional clauses were included in each AG to clarify partners’ respective roles and responsibilities. This proved necessary to reduce ambiguity in early delivery and strengthen accountability at consortium and partner level.

Delivery management, coherence and collaboration

Managing delivery coherence across three consortia has been a core programme management challenge and a key risk to delivery and value for money. While the breadth of expertise across partners is a strength, differences in organisational cultures, incentives and delivery approaches required greater hands‑on stewardship by FCDO than initially anticipated. Early implementation revealed a tendency for partners to focus on individual workstreams rather than collective programme outcomes, increasing the risk of fragmentation and duplication if left unmanaged.

In response, FCDO strengthened central coordination and governance arrangements, including regular programme‑level engagement and structured consortium meetings. Weekly Programme Executive Steering Committee meetings were established initially to build coherence and have since moved to a fortnightly cadence. This shift reflects improved collaboration and learning across partners, but ongoing oversight and direction remains necessary to ensure alignment with programme‑level impact.

Reporting quality has improved over the review period. While the first quarterly progress report was largely a compilation of separate consortium submissions with limited consistency, FCDO introduced a common reporting template to improve coherence, comparability and focus on outcomes. Partners engaged constructively in refining this template, and subsequent reports are of significantly improved quality and timeliness. This demonstrates both partner responsiveness and the value of more directive programme management in complex delivery models.

Financial management and forecasting
Delivery commenced in Q2 of the financial year, with early spend lower than forecast due to partner recruitment processes and delays in Business Case approval. Against an original planned spend of £8m for FY 2024/25, actual spend was approximately £6m. Further underspend resulted from delayed mobilisation of Components 3 and 4. FCDO responded appropriately by re‑profiling budgets into future years to protect value for money rather than accelerating expenditure prematurely. All payments have been made quarterly in arrears.

While partners submitted invoices on time for Q2 and Q3, there was initial inconsistency in the level of financial detail provided. In consultation with partners, FCDO developed a standardised invoicing template to improve clarity and transparency. This has been complemented by the introduction of monthly finance meetings with individual partners to review spend, forecasts and emerging risks. This approach represents a clear improvement in financial oversight and has increased confidence in forecasting accuracy, although it has required additional management effort from both FCDO and partners and highlights the transaction costs associated with a multi‑partner delivery model.

Accountable Grant amendments were issued to all three partners to incorporate joint country entry strategy work, with approximately £250k reallocated from the Programme Management Support component where no spend occurred in the financial year. This reflects adaptive financial management in response to delivery realities.

Commercial performance and partner management
Commercial management across components has been conducted in line with FCDO requirements. For Component 1 (WaterAid) and Component 2 (IWMI), existing DDAs and engagement with Commercial Directorate ensured appropriate assurance without unnecessary duplication. Component 3 (CDP) required a full DDA, completed in six weeks with additional internal support, significantly mitigating delay risk while maintaining assurance standards. The MEL contract (Component 4) was competitively procured, with TORs rated ‘Excellent’ by the EQUALS Helpdesk; delays reflected the complexity of TOR finalisation and commercial processes rather than supplier performance. Component 5 (Programme Management Support) has progressed more slowly, primarily due to internal FCDO capacity constraints and the temporary freeze on Programme Funded Posts following ODA reductions.

Overall, partner performance to date is satisfactory, with compliance demonstrated against contractual terms, supply partner requirements, delivery chain transparency, and gender equality expectations. However, the programme has learned that coherence, collaboration and cost control in a multi‑consortium model do not arise organically and require active, ongoing management. FCDO’s role as a more assertive steward—providing clearer direction on priorities, sequencing and performance expectations—has been central to addressing early challenges and will remain critical to safeguarding delivery, commercial and financial performance as the programme scales.

Summary of Programme Component spend:

Component Name	Delivery partner	Financial Arrangement	Value	Forecast this FY	Spend this FY
Design & Build	GDI	Accountable Agreement	£1m	No spend this FY	Spend was in 23-24
Component 1 - Resilient Water Accelerator	WaterAid	Accountable Agreement	£11m	£2.2m	£1.75m
Component 2 - Water Resilience Tracker	International Water Management Institute (IWMI)	Accountable Agreement	£11m	£2.2m	£1.98m
Component 3 - Fair Water Footprints	CDP	Accountable Grant	£11m	£2.2m	£2.13m
Component 4 - Monitoring, Evaluation and Learning	NIRAS	Commercial Contract	£2.4m	£800,000	£96,691
Component 5 – Programme Management Support	Programme Funded Posts to come onboard		£2.7m	£600,000	£0

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

This Annual Review was led by an internal FCDO team and drew on inputs provided by delivery partners, summarised by NIRAS. The annual review team drew upon the JTWS quarterly reports July-September 2024, October-December 2024 and January-March 2025, as well as the original and prospective results framework, RWA’s updated strategy (February 2025), the partner ToC in the joint JTWS proposal (June 2024), and the programme risk register.
NIRAS was contracted as the MEL partner on 4th February 2025 and submitted its draft inception phase report in mid-June 2025. The MEL supplier has updated the programme ToC together with programme stakeholders and is in the process of reviewing the results framework and doing a rapid appraisal of partner MEL systems. The new programme results framework will reflect the latest ToC, and fully incorporate ICF KPI reporting (see recommendations below).
Monitoring and Evaluation
Monitoring: The current version of the programme Results Framework (RF) nests partner results frameworks at the programme output level, thereby creating a lack of coherence within the overall RF structure. For this annual review, partners are reporting against overall impact milestones; in future years, the partner RF will be integrated into the programme RF via portfolio indicator baskets so that results can be assessed from a programme perspective. Partners will still report progress against their individual results frameworks in quarterly reports, thereby allowing FCDO to track partner-specific performance, as well as programme-wide performance.
Evaluation: NIRAS has developed draft evaluation questions and an evaluation framework, which will be submitted as part of the inception report. The evaluation is theory-based and employs a case study approach using outcome harvesting and contribution analysis for data collection and analysis. The evaluation focus is on JTWS Tier 1 countries in line with the objective to assess whether the sum of partners working in the same country is greater than them implementing their components individually. Baseline and midline evaluation have a strong process evaluation element, and midline and endline evaluations will assess performance against intended outcomes and impact. NIRAS recommends using an extended VfM element at midline to assess anticipated likelihood of outcomes to facilitate adaptation and redesign as the programme moves into phase 2. The midline evaluation is planned for July-December 2026 to enable the assessment of early outcomes in Tier 1 countries (see recommendations).
Evidence
NIRAS will develop an evidence repository for the programme, which will bring together partner monitoring data, evidence produced by the evaluation and external evidence relevant to the programme ToC. The programme’s evidence base will form the basis for internal learning and programme adaptation and also contribute to the wider evidence base on how and under which circumstances governance and technical assistance contributes to transformational change towards climate-resilient water security.
Learning
This year, whilst the programme has been in start-up phase, there have been limited opportunities for dedicated programme-wide learning. In the coming year there will be regular learning events, combining the development of a shared understanding of what is working and what isn’t (level 1 learning), deeper reflections on successes and challenges via most significant change (level 2 learning) and annual events to identify opportunities for adaptation (level 3 learning). In addition, there will be opportunities for thematic learning around programme outcomes.

Date of last narrative financial report	NA	Date of last audited annual statement	NA