Programme Completion Review

Title: The UK Action to Support Developing Countries Fight Corruption Programme (UKACT)
Final Programme Spend £ (full life): 32,150,687	Review Date:	30 Sept 2025
Programme Code: 300597	Start Date: 1 April 2020	End Date: Programme system end date 31 January 2026 but delivery ended on 30 September 2025

Summary of Programme Performance

Year	2021	2022	2023	2024	2025
Programme Score	A	A	A+	A+	B
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	DevTracker Programme GB-GOV-1-300597 Documents
DevTracker Links to all logframes used during programme lifetime:	DevTracker Programme GB-GOV-1-300597 Documents

GLOSSARY

AC	Anti-Corruption
AFO	Asset Freezing Order
AML	Anti-Money Laundering
BCIU	Bribery and Corruption Intelligence Unit
CKC	Combatting Kleptocracy Cell
COLP	City of London Police
CPS	Crown Prosecution Service
CRT	Civil Recovery and Tax Team
FCDO	Foreign Commonwealth and Development Office
HMG	Her Majesty’s Government
IACCC	International Anti-Corruption Co-ordination Centre
IFAC	Illicit Finance and Anti-Corruption Team
ICU	International Corruption Unit
LMIC / LIC / MLA	Lower Middle Income Country / Lower Income Country / Mutual Legal Assistance
NCA	UK National Crime Agency
OACU	Overseas Anti-Corruption Unit
ODA	Official Development Assistance, City of London Police
OGD	Other Government Department
PCR	Project Completion Report
PEPs	Politically Exposed Persons
POCD	Proceeds of Crime Division, CPS
SDGs	Sustainable Development Goals
SFO	Serious Fraud Office
ToC	Theory of Change
UK ACT	UK Action to Support Developing Countries Fighting Corruption Programme
UKCA	UK Central Authority
UWOs	Unexplained Wealth Orders

A. Summary and Overview (1-2 pages)

The UKACT Programme funds UK law enforcement authorities to pursue and investigate money laundering and bribery cases in the UK which relate to developing countries. UK ACT and predecessor programmes have been running since 2006, and this programme was originally scheduled to conclude in March 2025. However, due to uncertainty about ODA budgets, an exemption was requested to extend the programme by 3 months initially and then by a further 3 months for one of the partners. Therefore due to the extensions, change in personnel and system issues, the last AR has been combined with the PCR. This phase 2 Programme which ran from 1 April 2020 to 31 September 2025 spent £32,150,687. Logframe targets are set annually for the financial year but for the purposes of this PCR, targets for the last 6 months have been apportioned between this Phase 2 programme and the new Phase 3 programme where appropriate.

The aim of UKACT is to reduce incentives for corrupt individuals to use the UK to launder money stolen from developing countries and to reduce incentives for UK companies and nationals to bribe in developing countries. The Programme is delivered through funding to the International Corruption Unit (ICU) and Bribery and Corruption Intelligence Unit (BCIU), both at the National Crime Agency (NCA); and the Proceeds of Crime Division (POCD) in the Crown Prosecution Service (CPS). The main effort of the Programme is through BCIU and the ICU which identify and investigate cases, progressing them towards criminal prosecutions or to asset seizure through civil asset recovery. The POCD deals with asset restraint during an investigation, and the confiscation of assets following conviction. The Programme supports these key parts of law enforcement in order to achieve impact in the following ways: firstly by tackling impunity by taking criminal and civil action in the UK to bring corrupt individuals to justice; secondly by returning recovered funds for use in sustainable development; and thirdly by preventing and disrupting corrupt activity. Together these actions aim to make the UK a more hostile place for corrupt individuals, and increase international economic and border security. UKACT has become a globally recognised example of innovative anti-corruption work, unique in the OECD.

The operating context has been difficult and uncertain throughout the five and a half years of this phase of the Programme. When this phase began in April 2020, funding was due to gradually increase by 25% over the five years of the Programme. However, because of the COVID19 pandemic, the Government reduced the ODA budget in 2020 from 0.7% to 0.5% of UK GNI. As a consequence, plans for expansion of the Programme were stopped halfway through the year and the UKACT budget was reduced to 2019-2020 levels. At the beginning of the Programme, the budget was expected to be up to £39 million for 5 years, however, by the end of the five and a half years, annual budget reductions brought the final allocation to £32,150,687. This represents a reduction of 17.6% from the original budget. The 2020-25 phase of the programme also had to be extended for six months to ensure continuity for programme partners given the decision in February 2025 to reduce the ODA budget to 0.3% GNI, which led to a delay in funding for the next phase of UKACT, due to start in April 2025.

As well as impacting the budget, the pandemic had an impact on the work, with most travel curtailed and most work moving online, which slowed some of the investigations. More significantly, the pandemic had an impact on the wider criminal justice system and the capacity of the court system to process cases, with some hearings still being listed for up to two years ahead. These delays have been a major factor in the challenges of delivering the Programme outputs in a timely way.

The impact of the pandemic and budget cuts has meant that the Programme has been unable to fulfil all of the original ambitions of the 2020-25 Business Case. As well as the 25% expansion of the ICU being stopped, plans to recruit additional staff on civil recovery work also had to be shelved, and the new outreach work on Mutual Legal Assistance (MLA) by the UK Central Authority (UKCA) could only be funded until 2022/23. Other planned work on outreach and communications, which could have contributed to the Programme’s deterrent effect, were also not possible to deliver in this phase.

Another challenge for the Programme has been recruitment constraints and staffing levels. For most of this phase, the ICU has been successful in maintaining a low turnover of staff, despite pressures such as recruitment freezes and better-paid opportunities for staff in the private sector. However, there were further challenges with two surges of ICU staff to higher priority NCA teams. In 2022, 10 ICU staff were surged to the Combatting Kleptocracy Cell (CKC), and in January 2025, 15 ICU staff were surged to the Organised Immigration Crime Team (OIC). Although in many cases the staff returned to the ICU, the loss of staff, even on a temporary basis, slowed delivery of the work, and at the time of this Review, the ICU is still recruiting replacement staff.

Despite this challenging context, there have been significant achievements in the five and half years of the Programme, and most targets have been met, with the Programme scoring A or A+ every year. During the 5 and a half years between 2020 and 2025, 29 money laundering and 22 bribery cases have been concluded and £603,892,811.29 assets have been frozen, confiscated or returned to developing countries.  Over the past year alone, the ICU has secured bribery charges against high-profile individuals including the former Minister for Petroleum Resources for Nigeria, a dual British/Malawian national accused of bribing many members of the Malawian Government, and the conviction of the Chief of Staff to the President of Madagascar for bribery offences.

The Programme has achieved good results across the five and half years of the programme but missed some targets in the last 18 months. This Review scores the last 18 months of the Programme as a B.

Lessons Learned

A Learning Review[1] commissioned in 2024 during the preparation of the Business Case for 2025-2030, assessed the success of this phase of the Programme and explored how to improve impact in the future. The Learning Review confirmed the high performance of the Programme against its log-frame output targets and this was also confirmed by the 2024 Annual Review.
[1] The Learning Review contains sensitive data on the NCA and so is for internal use only.

The main findings of the Learning Review were that, given the scale of the global corruption problem and the comparatively small size of the Programme, a significant increase in impact would only be possible if Programme achievements are leveraged in new ways. This could mean the use of a wider range of anti-corruption tools and more effective communication grounded in a systematic and coordinated whole-of-Government strategy with a greater focus on communication. It is recommended that the Programme Team further consider these findings and how best they can be taken forward.

Recommendations

1. That the Programme Team consider how the findings of the Learning Review can be taken forward in order to leverage the wider UK government and civil society anti-corruption ‘ecosystem’[2] and increase the impact of the next phase of the Programme.
  [2] By ‘ecosystem’, the Learning Review refers to the range of organisations within the broader UK anti-corruption network ranging from government departments and agencies to professional regulators and civil society.
2. That the Programme Team develop the strategic, co-ordinated approach to outreach and engagement planned in the 2025-30 Business Case, in order to increase the deterrent impact of the Programme.
3. That the Programme Team develop a plan for engagement across FCDO posts, to contribute to the overall engagement and outreach strategy, leveraging the successes of UKACT in the communications and narrative products available for use by Posts.
4. That the Programme Team and Programme partners consider the review of new developments in asset recovery[3] conducted by the U4 Anti-Corruption Helpdesk, and whether these, or any other developments could enhance the work of the Programme.
  [3] A selection of emerging practices in asset freezing, tracing and confiscation
5. That alternative Value for Money measures are explored for the new phase to replace existing measures 2 and 3 which have become outdated.
The following recommendations are also identified but will only be possible with sufficient funding and resourcing and are therefore unlikely to be able to actioned in the short term:
1. That in order to support Recommendations 1-3, the Programme Team work to ensure the outreach and communications roles in ICU and FCDO are filled as soon as resources allow.
2. That the Programme Team and Programme partners explore how data on referrals (Output 2) could be collected and used as case studies, and consider whether sample preventions and disruptions could be publicised more widely to compound their deterrent effect.
3. As the last external evaluation of UK ACT was in 2018-19, the work of evaluation should start as early as funding allows in the next phase of the programme to ensure maximum lesson-learning and include identification of better metrics to measure the deterrent impact of action in the UK on corruption relating to developing countries.
4. It is recommended that the Programme Team continue to press for a fully staffed ICU and BCIU in line with available funding, to enable the Units to function at full capacity; and that additional staff are recruited when funding allows to increase civil recovery work, as planned under the new phase of the Programme.
5. That if budgets allow, the Programme Team explore reinstating the MLA work under the new business case, or whether other approaches should be considered.

Specific recommendations on the Log-frame
The following recommendations will only be possible with sufficient funding and resourcing and will be considered if resources allow:

1. That the log-frame indicators on Output 4 are revisited to include appropriate targets for BCIU on both disruption and outreach work to reflect their capacity to act as an intel ‘hub’.
2. With the continuing challenges of competing priorities across Government and within the NCA, the ICU should continue to track staff retention rates. It continues to be critical to retain a good ratio of experienced staff to lead and deliver on both casework and outreach, and to maintain a low level of staff turnover.
3. In the new phase of the Programme, the indicator on outreach work should be reconsidered, potentially with a focus on professional enablers to ensure this area is covered, and that the work is complementary to the Professional Enablers Practitioners Group.

This Review was conducted by the PCR Team and involved consultation with implementing partners as well as an assessment of Annual Reviews for 2020-2024, the Learning Review and the Helpdesk Review on Asset Recovery by the U4 Resource Centre.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result
Budget	£39.5million	£32,150,687
Timeframe	5 years - 1 April 2020 – 31 March 2025	5 years, 6 months – 1 April 2020 – 30 September 2025
Outcomes	Incentives are reduced for corrupt individuals in developing countries to use the UK to launder money; or for UK business and UK nationals or their agents to bribe in developing countries.	No change

Overall assessment of programme outcomes, sustainability and VfM [1/2 – 1 page]

The desired Programme outcome is that incentives are reduced for corrupt individuals in developing countries to use the UK to launder money; or for UK business and UK nationals or their agents to bribe in developing countries. The desired Programme impact is that the culture of impunity for corruption is reduced by the UK taking action to recover and return assets stolen from developing countries; and by pursuing companies and nationals who bribe in developing countries.

Over the five and half years of the Programme, partners have consistently met most targets against logframe indicators. These have been reported quarterly at the output level and annually at the outcome level. Key achievements over this phase of the programme include:

- £603m restrained between April 2020 and the end of September 2025;
- The highest number of successful trials since the Programme began with twelve prosecutions reported in the 2023 Annual Review period, and a total of 28 individuals or entities between 2020 and 2025.
A number of significant cases during the review period include the bribery conviction in the UK of the President of Madagascar’s Chief of Staff and her associate, the charging of a dual British and Malawian national for bribing the Malawi government,[4] the return of assets stolen by James Ibori, a former governor of Delta State in Nigeria; and the charging of the former oil minister of Nigeria.
[4] Former Aide to Madagascan President Sentenced for Soliciting Bribes From UK-Based Company | Latham.London

These successes at the output level are important evidence that the programme is achieving the desired outcome of deterring corrupt individuals and companies from laundering money in the UK, or from bribing in developing countries. The PCR Team consider that this is an appropriate level of outcome statement for a programme of this cost, technical capability, and sustained political and financial investment. However, it is important to note that one of the findings of the Learning Assessment, is that it is difficult for the Programme to measure fully the big picture of how much corruption, bribery and money laundering from developing countries actually takes place within the UK, and whether UKACT is having an impact on such corruption. As part of the analysis, the Learning Assessment found that there are ‘no adequate metrics on trends in serious financial crime in developing countries over time, nor any data on the likely deterrent impact of a criminal conviction in the UK.’ In the absence of such systematic data, the Learning Assessment relied on the opinions of informed experts, including those within the NCA, CPS, other law enforcement agencies, and of regulators and civil society organisations working on international anti-corruption.

It is therefore recommended that in the first year of the next phase of the Programme, the Programme Team identify better metrics to measure the deterrent impact of action in the UK on corruption relating to developing countries.

Even with improved metrics, the Review Team support the view of the Learning Assessment that fully achieving the programme’s desired outcomes, would require a strategic change, going beyond operational improvements or an increase in the number of cases at the ICU. The challenges of accelerating prosecutions and making a measurable impact on international bribery and corruption in developing countries remains immense. Given the scale of the problem globally, even a substantial increase in ICU cases reaching prosecution, whilst necessary and important, is in and of itself unlikely to make a significant difference to the incentives of corrupt individuals and companies, nor the culture of corruption.

To have such an increased impact would require a wider strategy involving more actors across the anti-corruption ‘ecosystem,’ complementing other cross-government work such as the Anti-Corruption Strategy and the Economic Crime Strategy. According to the Learning Assessment, such an ecosystem approach could leverage more tools for disruption and deterrence to complement both BCIU’s intelligence work and ICU’s criminal investigative work. Potential disruptive measures range from a wide variety of disciplinary measures available to professional regulators as well as sanctions referred through the Sanctions and Money Laundering Act, passport confiscation, tax investigations via HMRC, without the need for a criminal standard of proof. This menu could also be widened by including the range of preventive and disruptive work around strengthening in-country initiatives on beneficial ownership and PEPs, monitoring high value procurements (especially in strategic minerals, oil and gas, energy and transport) and supporting extractives industry transparency initiatives, strengthening parliamentary oversight and media outreach assisted by civil society.  More structured engagement and intelligence sharing by delivery partners within the NCA could be a win-win, improving the effectiveness of partners across the anti-corruption ecosystem through improved intelligence, while helping the UKACT progress towards its desired impact without significant additional effort on its part. Leveraging the capabilities of the wider system is a key opportunity that could help the Programme achieve its goal.

It is therefore recommended that the Programme Team consider how the findings of the Learning Review can be taken forward in order to leverage the wider UK government and civil society anti-corruption ecosystem and increase the impact of the next phase of the Programme.

Whether or not it is possible to develop and implement such a wider strategic approach, the commitment of successive UK governments to tackling corruption through this Programme is clear. The Programme has continued to be well-supported, even through the difficult period of COVID19 and the subsequent cuts to the ODA budget. UK ACT is viewed as a flagship programme in the UK’s fight against anti-corruption, and the December 2025 Anti-Corruption Strategy continues this commitment into the future. With this level of priority and commitment, and the scale of the continuing corruption problem, the work of the Programme will be required for many years to come.

The Programme provides excellent value for money by providing a major return on investment through the proceeds of corruption that have been frozen, confiscated or returned. Since this Programme phase began in 2020, over £603million of assets have been subject to restraint or detention and nearly £210million returned to developing countries with a programme spend of just over £32million. It is also a significant VFM measure that the return on the investment during this Programme phase includes the charging of 27 individuals/entities with corruption offences, and the successful prosecution of 28 individuals or entities, 4 since the last Annual Review.

These achievements are particularly significant, taking into account the COVID-19 pandemic and the budget cuts which have affected progress throughout the five and a half years of this Programme phase.

## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Output 1	The sustained and increased level of investigation of grand corruption (the theft of significant public assets by senior foreign officials) and international bribery impacting Lower Income Countries (LICs) and Lower Middle Income Countries (LMICs) with a connection to the UK. This includes the investigation of related activity by professional enablers and efforts to recover assets using civil powers
Output Score	B
Impact weighting (%)	25%			Impact weighting revised since last AR?	No change.

Output Indicator	Starting Target	AR Target (March 2025)	AR Result Achieved	Final Logframe Target (Sept 2025)	Final Result Achieved
1.1 / Cumulative number of MONEY LAUNDERING cases (a) concluded over duration of programme since 2006 and (b) cases currently under investigation and (c) cumulative number of file submissions to the CPS	44 / 11 / 1	66 / 8 / 40	73 / 9.75 / 37	75 / 8 / 38	73 / 8 / 37
1.2 / Cumulative number of BRIBERY cases (a) concluded over duration of programme since 2006 ; (b) cases currently under investigation and (c) number of file submissions to the CPS	79 / 11 / 1 / 1.2 (b) replaced by non-cumulative indicator, baseline no longer required / Output 1.3 which covered Unexplained Wealth Orders and civil recovery work was removed in FY20/21 due to a reduction in budget to fund this work.	100 / 15 / 9	99 / 13.25 / 7	101 / 12 / 8	101 / 10 / 1
1.4 / Cumulative number of foreign mutual legal assistance requests supported by the ICU	Not previously compiled / Output 1.4 was removed for FY22/23 but reinstated in FY23/24.	51	48	51	51

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

Whilst not all targets have been fully achieved in the last 18 months, in the five and a half years of the Programme, there has been an impressive increase in cases charged and concluded by ICU. The excellent results are due to a combination of cases naturally maturing and reaching a charging decision, and operational teams adopting approaches that have adapted to lessons learned from previous years. In the words of the Acting Head of ICU in 2024, “This is the most successful year the ICU has ever had, with more cases charged and more people arrested than in any previous year.” (Annual Review 2024).

At that point in 2024, 20 money laundering and 19 bribery cases had been concluded, and 21 individuals had been charged and successfully prosecuted. 18 months later at the end of the Programme, there have been further successes and now the overall total is 29 money laundering and 22 bribery cases concluded. 10 new cases are currently under investigation and 28 suspects have been charged.

Notable successes include the bribery conviction of the Chief of Staff to the President of Madagascar, and her associate; the charging of the former oil minister of Nigeria with 16 counts of bribery, and corruption; and charges brought against a Malawian/British dual national for bribing members of the Malawian Government. In addition, in a high profile auction at Sothebys, the ICU auctioned a Frank Auerbach painting for £620,000. The painting was seized during an investigation into Lenn Mayhew-Lewis, a money launderer who was convicted in 2023 but absconded ahead of his sentencing.

In the 2024 Madagascan case, the nature of the case meant that ICU and CPS were able to act quickly and the perpetrators were brought to justice within months. This contrasts with many of the other cases which are large and complex and can take several years to go through the justice system. Although it’s not possible to deliver such speedy outcomes on many cases because of their complexity, NCA and CPS are considering how the lessons from the Madagascar case can be taken forward.

At the end of the previous phase of the Programme in 2020, ICU was still in the early stages of building a portfolio of cases from a wide range of ODA eligible countries. Although many investigations were under way, only four suspects had been charged and no cases had been concluded. One of the reasons for the delay in charging and concluding many of these cases, was because of delays in the CPS process, often to do with the requirement for DPP approval of bribery cases. In order to address these delays, the 2020 PCR recommended that ICU and CPS needed to strengthen their relationship, with the ICU engaging CPS prosecutors at an earlier stage in the development of cases. (Recommendation 3) This increased engagement with CPS has enabled the ICU to better target its resources at cases with the greatest chance of success, and to facilitate the prosecution process. A closer working relationship between ICU and CPS, and establishing a High Level meeting between FCDO, NCA and CPS, has contributed to the results seen by the end of 2025.

On Outputs 1.1 and 1.2, a few indicators have narrowly missed in the final year of the Programme. However, targets have been reached in most years of the Programme and many of the successful cases have been large and high profile. However, with the ICU being understaffed for much of this phase of the Programme, it’s important that the Programme Team continue to press for a fully staffed ICU to enable the Unit to function at full capacity.

On Output 1.4, the nature of ICU’s investigations means that international requests for evidence are an essential part of the work. These requests work both ways and Indicator 1.4 measures requests made by overseas law enforcement from developing countries to the UK. Many of these requests and the evidence provided by ICU have led to successful outcomes in the requesting countries. In the first 2 years of this phase of the Programme, UKACT supported this work by funding two staff at the UK Central Authority (UKCA) to do outreach and training on MLAs. Although the UKCA made good progress in those years, this work was cut in 2022/23 because of the budget reductions. It is likely that the timelag in cutting this area of work is is one of the factors in the reduction in MLA requests in the final year of the progamme. If funding allows, it is recommended that the Programme Team explore whether reinstating a similar approach to MLA is appropriate or whether other approaches should be considered.

This output also included the legacy work of the City of London Police (CoLP) which was a former partner under this Programme. Until 2015, CoLP was responsible for investigating cases of bribery and corruption and when the remit of the work was moved to the ICU, CoLP worked to complete its portfolio of legacy cases, with funding ending in FY21/22 when its final case was closed.

This indicator has narrowly missed the target in March 2025. This output has been very successful over previous reporting periods with the ICU exceeding or achieveing the targets set against each milestone. The log-frame has been reviewed on an annual basis to ensure the indicators are realistic and to effectively measure the diversity of the ICU’s effort.

Output 2	The sustained and increased level of prevention and disruption of grand corruption (the theft of significant public assets by senior foreign officials) and international bribery impacting LICs, LMICs and UMICs and with a connection to the UK. This includes prevention and disruption activity targeting professional enablers and efforts to deny access to proceeds of corruption and recovery of assets using civil powers.
Output Score	B
Impact weighting (%)	25%	Impact weighting revised since last AR?	Unchanged

Output Indicator	Starting Target	AR Target (March 2025)	AR Result Achieved	Final Logframe Target (Sept 2025)	Final Result Achieved
2.1 / Cumulative number of referrals by ICU & BCIU to other UK authorities or overseas authorities	98 / The original output 2.1 measured the cumulative number of developing countries where there had been cases was removed as it was no longer useful to keep a record once 30+ countries had been reached.	175	175	179	175
2.2 / Cumulative number of instances where other law enforcement agencies in UK or overseas have taken on new work or broadened the scope of existing activity due to referrals, engagement, advice or support from ICU/BCIU	10	55	59	65	61
2.3 / Cumulative number of outcomes resulting from [POCU, ICU case disposals: / (a) number of individuals / entities charged with offences / (b) number of individuals/ entities successfully prosecuted / (c) number of minor disruptions / (d) number of moderate disruptions / (e) number of major disruptions	(a) 4 / (b) 3 / (c) 2 / The following indicator was replaced in FY23/24: / (c) number of alternative disposals/disruptions/other significant outcomes (including asset recovery and Deferred Prosecution Agreements - DPAs) / (d) and (e) were also added from 1 April 2023 (FY23/24)	a) 33 / b) 32 / c) 36 / d) 20 / e) 20	a) 31 / b) 31 / c) 19 / d) 22 / e) 16	a) 32 / b) 30 / c) 24 / d) 27 / e) 21	a) 38 / b) 31 / c) 32 / d) 24 / e) 17

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

This output covers the referral of cases to UK and overseas law enforcement authorities and the prevention and disruption of corrupt activity in the UK.

Referrals to other law enforcement agencies in the UK or overseas often involve significant work by the ICU to advise and support other agencies, and often leads to new cases and broadening of the work of these agencies. A key example of this collaboration was in 2023 when the President of Malawi sacked a number of cabinet ministers for corruption and bribery on the basis of evidence from ICU. This evidence led to criminal investigations in Malawi and charges have now also been brought in the UK.

Prevention and disruption of corrupt activities is another key aspect of the work of ICU and BCIU. Although the covert nature of this work means examples cannot be shared publicly, the figures show a significant number of disruptions in total this phase of the Programme. In 2023, it was decided that the output did not adequately measure the work of prevention and disruption and Indicator 2.3c (see the table above) was removed and replaced with three new indicators that record the number of disruptions of criminal activity at minor, moderate and major levels of effort. Such activity, can add significantly to the overall deterrent impact of the Programme, as well as the impact of the disruption itself.

Increased co-ordination with overseas law enforcement and ‘on the job’ capacity building which is often involved in referrals, has demonstrated success. Outreach work by ICU, and by UKCA in the first two years of the Programme (measured under Output 5), has also contributed to collaboration on referrals and disruptions. As a result, there have been 51 instances where other law enforcement agencies in UK or overseas have taken on new work or broadened the scope of existing activity due to referrals, engagement, advice or support from ICU/BCIU in this phase of the programme. Although the target has been narrowly missed in the final year, this is a significant result over the last five years, particularly given the difficult context of the pandemic and budgetary constraints; and that the exact number of referrals and disruptions being difficult to predict.

Lessons learned through this output, and recommendations for future programming
In this phase of the Programme, the importance of referrals and disruptions to the impact of the work, has been much better recognised. However, it remains challenging to publicise this area of work when data on the results of referrals is difficult and time-consuming to collect, and when much of the work of disruptions must remain behind the scenes. However it is recommended that the new phase of the Programme should explore how data on some referrals could be collected and used as case studies, and consider whether sample preventions and disruptions could be publicised more widely to compound their deterrent effect.

Output 3	Sustained and increased level of stolen assets frozen, recovered and returned to developing countries by HMG or leading to referrals to other agencies
Output Score	B
Impact weighting (%)	20%	Impact weighting revised since last AR?	Unchanged

Output Indicator	Starting Target	AR Target (March 2025)	AR Result Achieved	Final Logframe Target (Sept 2025)	Final Result Achieved
3.1 / Cumulative £ of assets since 2015: / (a) subject to restraint; / (b) confiscated (value of confiscation orders) / (c) enforced (value of funds received) / (d) returned to developing world from confiscation work	(a) £370m / (b) £202,662,246 / (c) £74,197,460 / (d) £74m / Original output indicator 3.1 measuring number of restraint orders and confiscation orders obtained was removed in FY22/23. / Change in methodology on how (b) and (c) are measured from FY23/24	£850,000,000 / £250,000,000 / £260,000,000 / £209,000,000	£811,556,470 / £286,799,541 / £297,075,289 / £204,000,000	£1,200,000,000 / £900,000,000	£1,304,031,166 / £973,892,811
3.2 / Cumulative number of civil asset denial / recovery instances (NOT CRT): / (a) number of account freezing orders obtained / (b) number of account forfeiture orders obtained / (c) number of cash detention orders obtained / (d) number of cash forfeiture orders obtained / (e) number of listed asset detentions / (f) number of listed asset forfeitures / (g) number of restraint orders / (h) number of confiscation orders	(a) 12 / (b) 3 / (c) 5 / (d) 5 / (e) 1 / (f) 1 / (g) 11 / (h) 6 / (g) and (h) added in from 1 April 2023. ICU have provided baseline figures as the team have maintained a record of these indicators over the years, though not formally included in logframe until now.	a) 32 / b) 10 / c) 34 / d) 24 / e) 6 / f) 5 / g) 17 / h) 8	a) 28 / b) 9 / c) 27 / d) 21 / e) 5 / f) 4 / g) 17 / h) 7	N/A	N/A
3.3 / Cumulative £ of assets: / (a) frozen under AFO / (b) forfeited or settled further to AFO / (c) detained under cash detention order / (d) forfeited as a result of seized cash proceedings;	(a) £750k / (b) £139m / (c) £46k / (d) £145k / Original output 3.3 measuring cumulative number of referrals to the Civil Recovery Team, was removed in FY21/22.	£12,500,000 / £177,000,000 / £1,200,000 / £1,500,000	£10,379,603 / £175,899,354 / £1,110,000 / £1,428,945	N/A	N/A

This Output measures the action taken to recover and return stolen assets since ICU was created in 2015, as well as during this phase of the Programme. The nature of anti-corruption cases is that it can take several years for cases to be investigated, brought to trial and for assets to be confiscated and returned to developing countries. Court delays and backlogs over the past few years have been compounded by the pandemic and subsequent budget cuts, and this means there will be further delays before cases reach the trial stage.

An example of the slow court process is the case of James Ibori, former Governor of Delta State in Nigeria, who was convicted and imprisoned by UK courts in 2012. It wasn’t until 2021/22 that £4.2million was finally confiscated from his associates and returned to Nigeria; and not until 2023, that he was finally ordered by a UK court to pay approximately £101.5 million or face a further eight years in prison. Ibori and his lawyer associate, Gohil, have appealed every part of the legal process, and it could still take two or more years before the confiscation order is finally enforced and the bulk of the funds can be returned to Nigeria.

The results for Output 3.1. reflect this situation. The figure for the freezing of assets, which happens at the beginning of a case, remains high, and the figures for confiscated, enforced and returned assets remain low. However, this should not detract from the very significant amount of £1,304,031,166, frozen since ICU was created in 2015, and £934,031,166 which has been frozen since 2020. Freezing of funds is in itself an important disruption to individuals involved in cases of alleged corruption.

The targets for the confiscation, enforcement, and return of stolen funds have taken into account the difficult operating environment, and the known dates for trials. Nonetheless, the results for confiscated and enforced assets have increased more than expected in the last 18 months of the Programme. This is because in early 2025, the ICU conducted a major exercise to review the way restrained, confiscated and enforced assets had been recorded, and they found the successes had been under-reported. The Programme Team updated the targets and now the final results for 3.1. show higher than expected figures. This also explains the differences between the Output results in this report and in previous Annual Reviews.
Indicators 3.2 and 3.3 focus on civil recovery. At the beginning of this phase of the Programme in 2020, funding had been allocated for civil recovery staff in order to boost the capacity of the NCA’s Civil Recovery Team (CRT). However, before this part of the Programme could be implemented, the budget was cut and this increase in the work was not possible. ICU continues to work on civil recovery and there have been significant successes in asset denial and recovery through the civil recovery process. The indicators under 3.2. show the high numbers of multiple account freezing orders, forfeiture orders, and confiscation orders, and indicators under 3.3. show that just under £176 million was forfeited or settled further to Account Freezing Orders. Although these are important results, it is likely that more could have been done with additional staff and it is recommended that the Programme Team continue to push for additional fuinding to civil recovery under the new Programme.

During this phase of the programme, there have been several amendments to the logframe indicators: budget cuts early in the programme meant that funding for CRT work could not go ahead, and the relevant log frame targets were reduced to zero. Two indicators were also removed: one recording the number of referrals to the Civil Recovery and Tax Team (CRT) in FY21/22, and one recording restraint orders and confiscation orders obtained in FY22/23. The current indicators in 3.2. and 3.3. were revised along the lines of ICU’s own reporting in NCA, in order to streamline the reporting process. These align with the FCDO’s own requirements.

Although a few of the Output indicators have been narrowly missed, many have been substantially exceeded. With a wide basket of indicators, it is not expected that all will be achieved every year. However, the overall results over the five and a half years are excellent, and are a considerable achievement against the backdrop of the pandemic, budget cuts and lengthy court delays.

Output 4	Enhanced tactical and strategic intelligence on UK-linked corruption affecting developing countries to initiate new investigations and to inform existing ones
Output Score	B
Impact weighting (%)	20%	Impact weighting revised since last AR?	No change

Output Indicator	Starting Target	AR Target (March 2025)	AR Result Achieved	Final Logframe Target (Sept 2025)	Final Result Achieved
4.1 / (a) Cumulative cases received by BCIU for assessment / (b) Cumulative cases developed by BCIU for assessment (NN or NT cases) / (c) Cumulative cases passed by BCIU to investigation team	n/a not compiled / Original output indicator 4.1 related to number and quality of intelligence packages to ICU removed from FY22/23.	431 / 92 / 6	593 / 87 / 7	630 / 105 / 9	651 / 94 / 11
4.2 / Number and quality of strategic intelligence outputs relating to LIC, LMIC or UMIC jurisdictions or specific sectors/thematic areas, which are supplied to the ICU and FCDO in order to generate tactical work or strategic insight for NCA or other law enforcement agencies/HMG.	32	57	58	60	58

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

This Output measures the role of the Bribery, Corruption and Intelligence Unit (BCIU) in contributing to new and existing investigations by ICU. The BCIU have a strong relationship with the ICU and also with ICU’s sister unit, the International Anti-Corruption Co-ordination Centre (IACCC) as well as the wider International Liaison Officer (ILO) network of the NCA. These relationships are crucial to the work of the ICU and mean the BCIU can tap into networks overseas, enhancing the quality of the intelligence packages it triages for ICU. This activity helps to fuel the pipeline of investigations for the ICU and other economic crime units and is a key component of the Programme.

However, staffing constraints across the NCA during this phase of the Programme have affected BCIU particularly badly and for much of this phase, BCIU has been working with less then half the required staff. This pushed the Unit into a reactive mode, only able to respond to essential ICU requirements on ICU’s criminal cases, and unable to function fully as an ‘intel hub’ providing a strategic approach to intelligence and delivering intelligence-based disruptions themselves. It is only in the last year of the Programme when the BCIU has been better-staffed, that it has started to become more proactive and strategic in its intelligence work, and able to do more outreach work. At the time of this Review, ICU is only down by three staff and has NCA approval to go ahead with recruitment for the remaining posts. A senior position in NCA has now been recruited to oversee and champion the intelligence function, so this brings a more positive outlook for BCIU. With more staff and new senior leadership, BCIU now has the potential to act more as an intelligence ‘hub’, increasing the impact of ICU’s work and the UKACT Programme. A stronger BCIU could also help the ICU by taking on some of the outreach work on stakeholder engagement communications.

Given the staffing difficulties over this phase of the Programme, it is not surprising that BCIU has not fully achieved the Output indicators on 4.1.(b) and 4.2.

The purpose of Output 4.2 is to draw on intelligence, insight, and expertise from teams across the NCA more broadly than those funded by FCDO. Restrictions enforced during the pandemic meant agencies involved in intelligence outputs, such the National Assessment Centre had to scale back their activities, thus impacting on the achievement of this indicator. It is therefore positive that 4.2 was only narrowly missed.

There have also been changes to the indicators over this phase of the Programme. The original Output indicator on the number of intelligence packages was removed in FY22/23 as it was decided this was not the best method of assessing the quality of materials provided to ICU. This was reviewed by the Programme Team and a new indicator 4.1. was added to capture BCIU’s efforts.

Although the indicators have not been met, these results must be set against a difficult operating context where BCIU was particularly badly affected by staffing constraints and recruitment freezes and still provided an intel service for ICU.

Lessons and recommendations for future programming [1-2 paragraphs]

One of the lessons of this phase of the Programme, is the importance of a fully staffed and functioning BCIU. With the low level of BCIU staffing, ICU had to cover some of the work themselves, and the strategic ‘intel hub’ work of BCIU could not be done effectively. Although the situation is now much better, it will remain important to monitor staffing levels and invest in additional technology to alleviate potential capacity constraints in future.

It is therefore recommended that staffing levels in BCIU are closely monitored by the Programme Team; and that the log-frame indicators are revisited to include appropriate targets for BCIU on both disruption and outreach work to reflect their increasing capacity to act as an intel ‘hub’.

Output 5	Increased ICU capacity and leadership enhances UK and developing country capacity to fight global corruption and the effectiveness of international law enforcement activity in AC
Output Score	B
Impact weighting (%)	10%	Impact weighting revised since last AR?	No change

Output Indicator	Starting Target	AR Target (March 2025)	AR Result Achieved	Final Logframe Target (Sept 2025)	Final Result Achieved
5.1 / Stock of human capital, measured as: / (a) an annual calculation of the % of permanent ICU personnel who have been on the unit for less than 12 months / (b) ICU staff annual attrition rate better than the industry average	(a) 45% / (b) 37% / Prior to FY23/24, 5.1(a) was measured as more than 12 months)	Less than 45% / Less than 13.6%	28.24% / 16.47%	Less than 45% / Less than 13.6%	a) 20% / b) 25.88%
5.2 / Cumulative instances of ICU/BCIU/CRT being called on to deliver: / (a) training / (b) capacity building / (c) other substantive support to any other partner in UK or overseas	Original indicator measuring ICU visibility was removed in FY21/22. / The NECC was originally meant to take over this training, capacity building and outreach from ICU but when this did not go ahead, this indicator and 5.3 (a), (b) and (c) were included in 2022	a)24 / b) 8 / c) 41	a) 29 / b) 8 / c) 32	a) 30 / b) 9 / c) 35	a) 34 / b) 9 / c) 37
5.3 / ICU outreach work with business and civil society, targeting the risks posed by professional enablers. / (a) number of regulatory bodies engaged with (non-cumulative); / (b) number of trade bodies / associations engaged with (non-cumulative); / (c) instances of potentially actionable intelligence on professional enablers being generated or shared (non-cumulative).	5.3(a) and (b) moved from cumulative to non-cumulative measures from FY23/24. / 5.3d on the number of Mutual Legal Assistance requests was removed from FY22/23 when the work of UKCA was cut.	a) 21 / b) 31 / c) 14	23 / 39 / 21	24 / 44 / 23	a) 25 / b) 43 / c) 21

This Output measures two different things: first the capacity of ICU in terms of its staffing levels and length of staff experience; and second, the capacity building and outreach work of the ICU.

Although the first phase of the Programme from 2015-20 easily achieved the recruitment and retention targets, indicator 5.1. has been a challenge during this phase. The ICU management team has worked hard to retain staff and maintain a pipeline of staff for ICU, when the NCA was subject to recruitment freezes. Much of the success of the Unit over this phase can be attributed to having a highly motivated team, who were fully trained and operational, and proud to be playing a role in recovering funds stolen from lower income countries. This is in a context where recruitment and retention of experienced anti-corruption staff can be challenging, particularly as staff can secure substantially bigger salaries elsewhere, particularly in the private sector.

However, for reasons beyond the ICU’s control, ICU have twice had to face the challenge of staff being surged to wider NCA teams working on priority policy areas: the Combatting Kleptocracy Cell in in 2022; and the Organised Immigration Crime Team in 2025. Although a proportion of staff have returned on both occasions, both surges left gaps in ICU staffing and slowed the progress of some of the work. This type of staff surge may well happen again, and although corruption and illicit finance are a Government priority, they are not as high a priority as other areas, such as Organised Immigration Crime.

For the reasons above, ICU met indicator 5.1(a) but missed 5.1(b), mainly because of the surge of staff in the final years of the Programme.

On capacity building, training and outreach work, there have been several changes to the indicators over this phase of the Programme. It was originally planned that the NECC and NAC would take over some of this outreach work, but when this didn’t go ahead, indicators 5.2 and 5.3. were revised and re-introduced in 2022. The pandemic meant that some of the activities under the original indicators 5.2 and 5.3 had to be cut. These included the work on Mutual Legal Assistance by UKCA, cut in 2022 because of pandemic-related budget reductions; and indicators on the number of new meetings with developing country partners and on positive ICU references in media reporting, cut for the same reason. These were all removed from the log-frame.

Despite these challenges, ICU have delivered 34 training sessions, assisted nine partners with capacity building, and provided substantive support to 37 partners, mostly in the final three years of the Programme. The ICU has also worked with 25 regulatory bodies and 43 trade bodies to increase ICU’s visibility and successfully reaching target audiences.

Although the Programme Team reviewed Output 5 with the ICU over the phase of the Programme and amended the logframe to take into account the impact of the pandemic and consequent budget cuts, the indicators have been narrowly missed, largely due to external factors in the final year.

Lessons and recommendations for future programming [1-2 paragraphs]

The impact of the staffing constraints and the surges of ICU staff make it clear that it is important to continue monitoring staffing levels in the log-frame, work with NCA to ensure that surges of the specialised ICU staff are only used as a last resort, and that ICU has sufficient notice to ensure proper arrangements can be made.

Training, capacity building and outreach are always the first to go when budgets are under pressure, and this has been the case in this phase of the Programme, as it was in the previous phase. However, the consistent message from the reviews and evaluations over the last ten years, is that outreach and communications are essential to increase the impact of the Programme. For this reason, the Phase 3 business case has taken an ambitious approach and budgeted for two outreach and communications roles: one in ICU and one in FCDO. It is therefore recommended that the Programme Team ensure these roles are filled as soon as budgets allow.

D: Value for Money [½ - 1 page]

VfM performance compared to the original VfM proposition in the business case

1. Cumulative total of assets frozen compared to cumulative total of money spent to fund the units.
2. Average length of time for corruption cases from inception to prosecution as compared to OECD average of 7 years.
3. Progress in cases from tasking through to charge.

VFM Measure 1: On this measure, the Programme has demonstrated excellent value for money. Since this phase began in 2020, over £603 million of assets have been restrained against a current Programme spend of approximately £32million up to the end of September 2025. This result is particularly notable taking into account the impact of the COVID-19 pandemic and subsequent budget cuts which particularly affected the work in the first three years of this phase of the Programme. The Review Team consider this to continue to be a useful measure of VFM.

VFM Measure 2: As referenced in the 2023 and 2024 Annual Reviews, the study undertaken by OECD was completed over 10 years ago and has not been updated, so it no longer provides a realistic comparison. It is recommended that an alternative VFM measure to VFM2 should be found for the next phase.

VFM Measure 3: The pandemic has had the effect of delaying the progress of cases through to charge, particularly in the early part of this reporting period. Even so, there has been considerable success during this phase, with 34 individuals/entities charged with offences since 2020, and 13 of those charged within the last 18 months.

It is recommended that VFM3 is reviewed to consider including a wider range of progress measures. Depending on the stage of the portfolio of cases, progress may need to be measured from tasking to charge, or it may be better measured by cases moving from charge to conviction. In this phase for example, 28 individuals or entities have successfully been prosecuted, with 7 since the last Annual Review. By including additional stages as a measure of progress, it would better reflect the lifecycle of a case. The NCA has also suggested that measuring the number of minor, moderate and major disruptions might be a suitable alternative, and more within the control of ICU.

E: Risk [½ - 2 pages]

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]

Overall, the programme risk is moderate. In line with the FCDO overarching risk appetite statement, UKACT has a cautious appetite for external context risks (reputational, policy and programme delivery, strategy and context, and people) as it works in challenging circumstances to end corruption. This risk appetite is complemented by a minimal appetite for fiduciary, safeguarding, and public service delivery risks, which are managed through active engagement with programme partnerships, consistent documenting of our successes and adherence to PrOF rules.

The Programme’s latest Risk Register is set out below:

Risk Description	Gross Risk	Mitigation	Residual Risk
Progress of cases slow and / assets not returned in a timely way because of delays in the justice system caused by the pandemic and other factors.	Major	Regular high-level meetings between FCDO, CPS and NCA will provide evidence to monitor the delays and level of risk. However, the delays are outside the control of the Programme and partners, so the risk remains high. / Escalate risk to cross-HMG / fora.	Moderate
Staff in the ICU are surged or otherwise moved by the NCA into other roles because of high demand on other policy areas, thus undermining the work of ICU.	Major	High level meetings between FCDO and NCA keep the situation under review. Issues escalated to Ministers where necessary.	Moderate
Difficulties in recruitment due to small pool of financial investigators, and current staff moving to private sector. Headcount restrictions in NCA.	Moderate	ICU have explored expanding remote working options and posting staff living outside of London. Exploring potential to use technology to mitigate.	Moderate
Uncertainty of resourcing for the Programme (FY25/26 – 29/30).	Moderate	High ministerial priority; strong concept notes from ICU/CPS	Minor
Prioritisation of geopolitical and strategically important countries, to the detriment of LMICs. An increased focus on Russia and Ukraine, could detract NCA resources away from LMICs.	Minor	Ensure ODA criteria and focus on LMICs continues. Ensure that OGDs non-ODA contributions to NCA and CPS maintained despite resource constraints. / Monitor staffing levels in ICU.	Minor
Lack of communication on impact of programme reduces deterrent impact	Minor	NCA and CPS has continued to publish press releases on progress of cases. Programme team has monitored potential opportunities to publicise UKACT funding but must take into account potential international relations implications. FCDO, with NCA, develops a new communications strategy for the Programme and seek to employ a ICU focused communications officer. FCDO work to facilitate communications in countries where possible.	Minor
Fraud and corruption risk from partners misusing programme funds.	Minor	Both partners are government departments, and therefore also have zero tolerance to fraud/corruption. There are safeguards in place for approving payments and ensuring SRO approval. The Programme Team provide any conflict of interest returns as and when they arise. We alert partners to Aid Diversion Standards and encourage regular discussion about risk.	Minor
Partner organisations do not have robust safeguarding procedures in place, and this results in staff being at risk.	Minor	Although enhanced due diligence checks are not required due to partners being OGDs, the Programme Team regularly engage with partners to check understanding and compliance; and to request regular updates of partner risk registers and review. NCA staff are required to be subject to regular and detailed vetting.	Minor

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]

The Programme is a complex, multi-stakeholder, multi-year operation, and the strong message from partners over this phase is that predictable, stable, long-term funding that reflects the need to expand slowly is a critical factor in planning future programming.
Throughout the five and a half years of this phase of the Programme, the operating context has been difficult and uncertain throughout. During this Programme phase, previous and current Governments operated one-year spending reviews between 2021 and 2025, rather than the usual three year reviews which provide greater certainty and ability to plan ahead. When this phase began in April 2020, funding was due to gradually increase by 25% over the five years of the Programme. However, because of the COVID19 pandemic, the Government reduced the ODA budget in 2020 from 0.7% to 0.5% of UK GNI. As a consequence, plans for expansion of the Programme were stopped halfway through the year and the UKACT budget was reduced back to 2019-2020 levels. At the beginning of the Programme, the budget was expected to be up to £39 million. However, by the end of the five years in March 2025, annual budget reductions brought the final allocation to £29,130,776. This represents a reduction of 25.3% over the five-year period.

In February 2025, the Government decided to increase spending on defence to 2.5% of GDP from 2027, funded in part by reducing the ODA budget to the equivalent of 0.3% of GNI by 2027. Because of the transitional timescale, this reduction has not further impacted on the budget for this phase of the Programme. However, this decision led to a delay in funding for the next phase of UKACT, due to start in April 2025 which meant the 2020-25 phase of the Programme had to be extended to ensure continuity for the programme implementers. The Memorandum of Understanding (MoU) with CPS was therefore extended to end of Q1 FY25-26, and NCA’s was extended to end of Q2 FY 25-26.

The new phase of the Programme has been allocated an increased budget in line with the new goals in the 2025 Business Case and reflecting the priorities of the Foreign Secretary. However, the 2025 reduction in ODA has resultedin a reduced ODA allocation for Phase 3 of this programme for 2026 – 2028. Discussions are underway with programme partners on what impact this will have on the Phase 3 programme.

All partners performed well over the five and a half years of this phase, with most log-frame targets being met or exceeded in most years and the Programme scoring A or A+ each year. During the pandemic, the partners worked in challenging circumstances through the travel restrictions, remote working, and increased court delays, due to lockdown. The pandemic also resulted in the reduction and reprioritisation of the ODA budget, with the additional budget reduction in ODA funding in 2025 causing uncertainty in long-term planning. Delays in charging decisions and court processes have also been identified as major risks to programme performance. While log-frames were amended to reflect changes required due to the pandemic, partners still produced impressive results.

Commercial Performance and Financial Management
UKACT provides funding to the NCA and the CPS and, as partners across government, they are subject to the same financial and accountability reporting requirements as FCDO.

The Programme Team has maintained regular dialogue with partners to ensure accuracy of forecasting and invoicing, and also implemented a forecast and invoice schedule to ensure financial management stayed on track. The CPS quarterly forecast and timely submission of invoices has been excellent. NCA forecasting is harder to predict given that UK ACT funds travel and overtime as well as salaries. Staff surges and under-resourcing in the NCA’s finance team contributed to delays in receiving forecasts and invoices over this reporting period. However, despite some payments being delayed, partners have continued to deliver against targets. Regular meetings have helped to ensure both partners remain on target with spend.

Overall, the Programme has an underspend of £553,869.92 against a total budget of £32,150,687. This is a moderate underspend of less that 2% when considering the overall revised programme budget allocations over the five and a half years.
Across all Programme partners, salaries are the major programme cost driver and staff vacancies continue to have the most significant impact on spend. The financial proposals in the 2020 business case recognised this and budgets were due to be tapered up over the 5-year period to account for teams building up to their full complement. However, the impact of the pandemic meant that the planned expansion could not go ahead in the reporting period.

The Programme Team and partners have maintained a good rapport throughout the reporting period, with regular contact on progress and any issues of concern, as well as partners responding quickly to ad hoc queries (such as briefing requests). In addition, quarterly meetings with both partners ensured issues and risks were flagged and monitored. However, the FCDO was not informed in a timely manner of the decision to surge staff from the ICU to the OIC team. This was of particular concern given the potential impact the surge would have on the Programme, and became a key topic for discussion during the quarterly high-level meetings.

Both Programme partners have produced a high standard of narrative reports for each quarter and each monitors progress quarterly against the log-frame. Quarterly meetings at a higher level were put in place in FY23/24 to increase visibility of Programme outcomes at a senior level and offer opportunities to discuss key risks such as delays in the justice system, budget constraints and, more recently, staff being surged from the ICU. These issues were addressed and mitigated by holding early and frequent discussions.
The ICU are the only partner with physical assets and there is an asset register which ICU and the FCDO monitor. Annual visual checks could not take place during restrictions enforced under the pandemic but were reinstated from FY23-24.

The Programme Team ensured the Programme has been compliant with PrOf Rules throughout the reporting period.

Programme-level approach to monitoring and evaluation [1/2 page]

A study was originally planned in FY2020/2021 to gather evidence to provide a baseline for reports on strategic outcomes in relation to changed perceptions and behaviour by PEPs. However, this study was put on hold because of the impact of Covid-19 and because the funding for this work had to be prioritised due to budget cuts.

Similarly, with the continuing pressure on budgets, the external mid-term evaluation of the Programme was also cancelled. However, it remains important to assess the impact of the Programme in deterring corruption and tackling impunity. Gathering more evidence on this will help the Programme to demonstrate impact.
Monitoring of the Programme continues through quarterly reports and regular meetings with each partner. There has also been significant additional engagement with senior staff in NCA and FCDO, particularly with regards to reprioritisation of budgets, and risk management.
Learning has been an ongoing process through this year of the Programme:
- Quarterly Reports have led to adjustments to the Programme and log-frame, additional meetings, and action as appropriate.
- The Programme Team have monitored key risks to the Programme, and where necessary, escalated these to FCDO senior management at the regular NCA/CPS/FCDO high-level meetings for discussion and review.
- The Programme Team commissioned TripleLine through the EQUALs process, to undertake a ‘Learning Assessment’ of UKACT. This Assessment was in lieu of a full evaluation and did a light touch review of the work of the 2020 UK ACT programme and provided advice on how the Programme could be modified for the next phase beyond 2025.
- The Programme Team also commissioned the U4 Anti-Corruption Helpdesk to conduct a review of new developments and best practices in asset recovery to be considered for the next phase of the Programme beyond 2025.

Date of last narrative financial report	n/a for OGDs	Date of last audited annual statement	n/a for OGDs