## Year 6 Annual Review (October 2024- September 2025)

Invest Salone: Private Sector Development, Trade and Job Creation in Sierra Leone
Programme Value: £19.95 million (Phase 1: £12.5m, Nov 2018 -Sep 2023, Phase 2: £7.5m, Oct 2023- March 2026		Review Date: 30/01/2026.
Programme Code: 300601	AMP Start Date: November 2018	AMP End Date: 31 March 2026

Summary of Programme Performance

Year	2019	20/21	2022	2023	2024	2025	2026
Overall Output Score	A	A	A+	A	A	A+	A
Risk Rating	Moderate	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300601/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300601/documents

A. SUMMARY AND OVERVIEW

Description of programme

Invest Salone is FCDO’s flagship private-sector development and investment facilitation programme in Sierra Leone, designed to tackle two binding constraints to inclusive growth: a largely informal, low-productivity private sector and a weak domestic revenue base that entrenches aid dependence. Operating in a fragile, climate-vulnerable context with low incomes, limited infrastructure, and domestic private credit of less than 4% of GDP[1], the programme aims to raise incomes and create jobs by catalysing domestic and foreign investment into non-extractive sectors such as agriculture, tourism, fisheries, manufacturing, renewable energy, and emerging opportunities like carbon markets. The programme combines firm-level technical assistance with systemic investment climate reforms to help established firms attract investment, expand domestic and export market share, and improve investment readiness, while complementary support to investors helps de-risk entry into the Sierra Leone market. Delivery is structured around three pillars:
[1] Sierra Leone - Domestic Credit To Private Sector (% Of GDP) - 2026 Data 2027 Forecast 1960-2024 Historical

Pillar One
Two facilities offering direct support to firms: / Technical Assistance Facility (TAF): Provides technical assistance to firms to become investment-ready, including by helping them with project prioritisation and linking them to investors. / Compete Salone: Provides matched grants to firms to become investment-ready or diversify their supply chain.
Pillar Two
Investment and export promotion: Developing a pipeline of investable businesses, leveraging engagement with impact investors, and supporting access to trade finance. There is one grant facility: / Prosper Salone: Provides grants to impact investors to enter or intensify their footprint in Sierra Leone, bringing down investor risk and helping with pipeline development.
Pillar Three
Investment climate. Drawing from direct experiences under Pillar 1 and 2, Invest Salone is working with government institutions to tackle key barriers holding back trade and investment. Invest Salone works with the government to reduce the cost of doing business, levelling the playing field for all firms including responsible, long-term investors.

The Business Case for Invest Salone was approved in December 2019 with an original budget of £30 million; subsequent ODA reductions resulted in a revised budget of £19.95 million. Programme delivery by Cadmus has been strong overall, particularly given the complex political economy constraints and market failures characterising Sierra Leone’s private sector. As an adaptive programme, Cadmus has managed key trade-offs effectively across firm size, sectoral focus, market orientation, and the balance between transaction‑level support and sector‑wide reforms. Learning across programme pillars has generated impacts beyond a linear results chain, underpinned by an experienced delivery team. However, the programme has faced challenges in robustly evidencing employment effects attributable to programme interventions.

This Annual Review was prepared by an FCDO Private Sector Development Adviser external to the Africa Directorate with input from the locally based team, with the review period covering October 2024 to September 2025. The Adviser conducted eight days in-country visit, engaged with Cadmus teams in London and Freetown, and interviewed business owners, impact investors, and government officials, alongside site visits to investee businesses.

Summary supporting narrative for the overall score in this review.

Invest Salone has delivered strong performance in Year 6, meriting an overall A score. The programme demonstrated progress across all outputs, with a clear shift from pipeline building to tangible results. Firm‑level technical assistance, targeted grants, and proactive investor engagement translated into significant investment mobilisation and improved competitiveness among supported firms. For instance, ISL facilitated £35 million in additional investment during Year 6, bringing cumulative mobilisation to £57 million, significantly outperforming the target of £28 million. Outputs on investment and export promotion performed particularly well, while the programme also made progress in facilitating structured public-private dialogue (PPD). Overall, ISL’s output delivery, and its contribution to reform processes and investment outcomes justify the A rating.

Major lessons and recommendations for the year ahead

Key lessons include:

- Integrated firm-level support and investment facilitation deliver the highest returns and should be prioritised over stand‑alone engagement. A central lesson that emerged from Year 6 is that the programme’s strongest investment results occurred where firm-level TA, matched grants, and investor facilitation were deliberately combined. Transactions advanced most effectively when TA helped firms refine business models, governance systems, financial structures, and export processes while ISL (sometimes through ARIA) brokered investor introductions and due‑diligence processes. Examples include So Pure, where ISL provided legal due diligence that enabled Zvilo to deploy working capital financing, and Bengal Agro with Leo Universal, where export-readiness support immediately unlocked joint cocoa exports. In contrast, businesses that only received investor introductions without accompanying TA or transaction preparation were less able to move beyond initial interest. New pipelines created late in the programme cycle showed diminishing returns, reinforcing the need to avoid spreading resources too thinly in the final phase.
- Investor confidence grows through structured engagement and credible pipelines: Another key lesson from Year 6 is that well-planned coordinated investor engagement strengthens investor confidence. As with the similar missions co‑hosted in the previous review period, the ARIA delegation again showed that bringing multiple DFIs and impact investors together through a single, organised visit is far more effective than ad‑hoc outreach. These missions work because ARIA provides a collective platform for DFIs, while Invest Salone ensures that firms presented are investment-ready, with strengthened governance, financial models, and due-diligence materials.
- Structured PPD is helping to build stronger reform momentum. Year 6 showed that when dialogue between government and the private sector is organised and formal, it creates much better momentum for future reforms than ad‑hoc meetings. The MoU between MoF, NRA, MTI, NIB, and the Chamber of Commerce is an example of this, as it gives discussions a clear structure. Under this arrangement, the Chamber was able to convene internal private sector discussions to review reform areas in previous Finance Acts, with outcomes to inform upcoming Finance Act 2026 engagements with government. Similarly, the new PPD Framework and Toolkit developed by ISL is helping improve how ministries conduct their dialogue sessions. For example, the Ministry of Gender and Children’s Affairs (MGCA) used the framework to guide a high‑level roundtable with the Bank of Sierra Leone, which contributed to identifying priority actions aligned to driving better implementation of the country’s financial inclusion strategy. However, limited staff capacity within the Ministry continues to pose challenges and buy-in from the government will be essential for long‑term success.
- Employment and income effects require more time to materialise than programme cycles allow, demanding realistic expectations and alternative evidence approaches. This review confirms a longstanding lesson from similar investment-led programmes: even with strong investment mobilisation and firm productivity gains, measurable job, and income effects lag significantly behind investment commitments. For example, early employment gains such as So Pure hiring 50 new staff following Zvilo’s investment demonstrate potential impact pathways, but these occur only once capital is deployed and operations are scaled. Given MEL constraints following ODA reductions, systematic quantification remains challenging for the programme. However, qualitative case studies and light-touch firm follow‑ups could be effective at illustrating the programme contribution to more jobs and income. The programme should therefore prioritise case-based evidence rather than seek large-scale employment numbers in the final months.

Recommendations
Recommendation	By when	Who
Prioritise finalising the high‑probability transactions already in negotiation or due diligence, as these represent the strongest opportunities for measurable investment mobilisation before closure. Focus on progressing deals with GLS, Capitol Foods, ManoCap Energy, and ACTB, while maintaining close coordination with BII, Proparco, FMO and other DFIs.	Q2Y7	ISL
Prioritise operationalising the national PPD Framework and embedding structured dialogue within GoSL systems, working with the Public Sector Reform Unit, MoF, NIB and MTI to apply the PPD Toolkit and ensure PPD mandates and accountability indicators are integrated into the forthcoming Public Service Act.	Q2Y7	ISL
Convert export readiness into concrete contracts by providing final brokerage and market‑linkage support to Bengal Agro, Leo Universal, Jam Jay and Mountain Lion. These firms are now well‑positioned for regional and UK/EU markets but require targeted introductions to buyers.	Q2Y7	ISL
Capture and package key programme learning to inform successor programming and support GoSL systems, as ISL is in its final phase and has generated insights that should be documented while evidence is still fresh. Prioritise concise learning products on structured PPD, sustainable and inclusive finance, early-stage investment, and firm‑growth models, complemented by practical tools that GoSL can apply to sustain reforms post‑programme.	Q3Y7	ISL
Prioritise proportionate, mixed‑methods evidence of employment and income effects, recognising that these impacts take longer to materialise than the programme’s remaining timeframe allows. Focus on light‑touch case studies, targeted follow‑ups with firms such as So Pure that are already expanding their workforce, and voluntary post-support reporting to illustrate credible pathways to job creation.	Q3Y7	ISL
Update the programme’s cumulative output targets to reflect the fact that all existing targets have now been exceeded, including several that were already surpassed in the previous review period. Revised targets should strike a careful balance - ambitious enough to reflect the programme’s robust performance trajectory, but realistic and proportionate to available resources in the final delivery phase.	Q1Y7	SRO/PRO
Ensure that learning products generated by ISL are proactively and systematically disseminated across FCDO, GoSL counterparts, development partners, and relevant private sector networks. This should include establishing a clear dissemination plan - covering target audiences, channels (e.g., email briefs, learning events, internal knowledge platforms), and timelines - to maximise uptake of insights before programme closure.	Q3Y7	SRO/PRO
Conduct a comprehensive asset check once Invest Salone has submitted assets disposal plans.	Q3 Y7	PRO
Continue to strengthen oversight of financial and fiduciary risks and respond proactively to emerging risks in the delivery environment.	Q1 Y7	SRO/PRO

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change diagram and key assumptions are provided below and can be summarised as follows: Persistent poverty and fragility in Sierra Leone are driven by low firm productivity, chronic under-capitalisation, weak financial intermediation, and an unpredictable investment climate, which together constrain private sector growth, job creation, and domestic revenue mobilisation. The programme assumes that addressing these constraints simultaneously - through firm-level technical assistance and grants to improve productivity and investment or export readiness, targeted support to de-risk and crowd in domestic and international investment, and evidence-based investment climate reform and PPD - can unlock private-sector-led growth. These interventions are expected to increase investment flows, exports, and domestic sales, strengthen firm competitiveness in non-extractive sectors, and improve confidence in Sierra Leone market. Over time, this should contribute to higher incomes, more and better jobs, and a broader domestic revenue base, enabling increased public investment in infrastructure and human capital, while recognising that progress will be non-linear and requires an adaptive approach in a fragile and volatile macroeconomic and political context.

The programme logframe was revised in July 2024 in response to recommendations from the Year 4 Annual Review. While the outcome indicators were retained, the definitions, scope, and targets of the output indicators were revised, as reflected in the detailed output scoring section below. These definitions and targets have remained unchanged since July 2024, and performance during this review period (October 2024 - September 2025) have been assessed based on the incremental progress achieved in this year relative to the cumulative results from Years 1 - 5.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Overall, Invest Salone is on track to deliver its intended outcomes, particularly in mobilising investment and improving firm productivity and competitiveness in non‑extractive sectors, despite ongoing macroeconomic and fiscal constraints. In Year 6, the programme supported over £63 million in investment deals, with £35 million attributed to Invest Salone, reflecting strong performance against outcome-level expectations. This was driven by continued firm‑level technical assistance that advanced businesses towards investment and export readiness, alongside sustained engagement with DFIs through ARIA that converted earlier pipeline building into advanced and closed transactions. Progress on investment climate reforms, including PPD, sustainable finance, and regulatory advances on intellectual property and carbon markets, suggests positive momentum towards systemic improvements that reduce the cost and risk of doing business and underpin longer‑term income and employment impacts.

The programme focused on helping businesses secure investment rather than supporting them to grow without new capital, in this review period. As noted in the previous Annual Review and in line with this Review, most outcome results came from firms in the financial sector, agro-processing, and food and beverage industries, which also align well with investors priorities in Sierra Leone. Sectors like tourism and textiles are still important for economic diversification and long‑term growth, and some engagements are justified, but only at a proportionate level. ISL provided limited support to smaller firms in these sectors during the review period and their contribution to outcome indicators remained minimal due to the small size of firms, high travel costs, limited air connectivity, and fragmented coordination. For these reasons, ISL phased out its technical support to businesses in tourism and textiles.

However, the programme remains off track in robustly evidencing direct employment and income impacts. While firm growth, investment commitments, and strengthening of reform processes are evident, the conversion of these gains into measurable and attributable job and income effects has been difficult to demonstrate within the programme timeframe. This partly reflects time lags between investment and employment creation, the capital‑intensive nature of several supported investments, and wider macroeconomic and structural constraints. In addition, ODA reductions have required changes to the programme, including scaling back ISL’s MEL activities. This has reduced the amount of evidence collected, particularly on the programme’s effects on employment and income.

In the year ahead, the programme should consolidate the results achieved so far, including those expected in Year 7 and gather proportionate evidence on how outcomes may lead to future jobs and income gains. Employment and income effects often appear only after investment has been fully deployed and firms have scaled their operations; for example, So Pure hired more than 50 staff only after receiving $250,000 investment from Zvilo that ISL helped facilitate. With limited time left in the programme, the most realistic approach is to prioritise high‑probability transactions, provide targeted post‑investment support, and strengthen monitoring around a smaller group of growth‑oriented firms. The programme should use light‑touch follow‑ups, and qualitative evidence to help illustrate early signs of employment and income pathways.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

ISL made good progress in Year 6 and contributed to the programme’s objectives. The programme continued to help businesses improve their competitiveness, access export markets, increase productivity and attract investment in non‑extractive sectors. ISL also helped strengthen parts of the enabling environment, but momentum now needs to be maintained, especially in improving how the public and private sectors work together on reform issues. Continued government buy‑in and political support will be essential for long‑term success, including addressing capacity gaps within key ministries.

## C. DETAILED OUTPUT SCORING

Output performance for this review period is assessed based on the incremental progress achieved in this year (Year 6) relative to the cumulative results from Years 1 - 5. This approach is required because the programme’s cumulative targets were last updated in July 2024, and several of these targets had already been met by September 2024, which fell within the previous review cycle. Assessing Year 6 delivery against cumulative historic performance therefore provides a clearer and more accurate measure of additional progress made during the current review period.

Output Title	Pillar 1: Market Development. Market Development. Enterprises strengthened (improved productivity/ competitiveness) to grow, become export ready and/or investment ready.
Output number:		1	Output Score:	A
Impact weighting (%):		33%	Weighting revised since last AR?	No

Indicator(s)	Year 5 actual	Milestone(s) for this review	Progress
1.1 Number of Sierra Leonean businesses with high or strategic growth potential identified and 'internal' or 'external' TA agreed and provided to either become export and/or investment ready or achieve accelerated growth (cumulative).	63 (16 women-owned)	65 / (16 women-owned)	72 (21 women-owned) / 14% increase in Year 6 over the cumulative Year 1- 5 results
1.2 Number of Sierra Leonean businesses that have adapted their business practices as a result of ISL activities (cumulative).	38	30	46 / 21% increase in Year 6 over the cumulative Year 1 - 5 results
1.3 No. of downstream supply/value chain partnerships between the formal private sector (businesses, producer groups, business associations) and marginalised groups, including rural communities, smallholder farmers, informal traders, women, and youth (cumulative)	18	18	20 / 11% increase in Year 6 over the cumulative Year 1 - 5 results

Briefly describe the output’s activities and provide supporting narrative for the score.

This Output focuses on increasing the competitiveness, efficiency, and productivity of growth‑oriented businesses in Sierra Leone by strengthening their capacity and market readiness. It achieves this by developing innovative market linkages and delivering tailored technical assistance, matched grant support through COMPETE Salone, and facilitation of value-chain connections.

Output indicator 1.1. During the reporting period, nine businesses received support to become export or investment ready and to advance along a growth trajectory that would not have been attainable without ISL assistance delivered through both the TAF and COMPETE Salone windows. This represents a 14% increase in Year 6 compared to the cumulative achievement from previous years. Of these nine businesses, five were women owned or women led. The supported firms operate across a range of tradable sectors, including agribusiness, food and beverage processing, renewable energy, logistics and financial services.

ISL’s support combined follow-on assistance to existing firms and new work with a pipeline of small, medium, and large companies. TA was tailored to each business and delivered either in‑house or through external consultants. For investment readiness, ISL helped companies develop business plans, financial models, and investor‑facing documents. A key example is So Pure, which received legal due diligence support that enabled it to secure additional working capital loan from Zvilo. For export readiness, ISL helped firms address business improvement challenges, strengthen supply chain partnerships, and manage export processes. One major result was a partnership between cocoa companies, Leo Universal Plantation and Bengal Agro Limited, leading to the joint export of three containers (37.5 MT) of cocoa, with 25 MT more planned.

Output indicator 1.2. During this review period, 8 businesses improved their business practices because of ISL’s support - representing a 21% increase in Year 6 compared to the cumulative achievement from previous years. Support included helping businesses develop new business models and products, strengthen internal systems for investment readiness, and build market linkages. For instance, ISL worked with Ecobank Microfinance to strengthen its loan portfolio and build staff capacity for agricultural lending. This TA aimed to improve portfolio quality so the bank could better attract investment. Ecobank Microfinance has since developed new SME loan products with reduced collateral requirements, and while it is too early to confirm increased agricultural lending, there are early signs of strong interest to lend to businesses in the agriculture sector. ISL also helped businesses improve their sexual exploitation and abuse and sexual harassment (SEAH) prevention and response systems by updating the national referral map, participating in the Safeguarding Community of Practice, and running a two-day safeguarding workshop for supported firms. The programme also developed a practical, private-sector-focused safeguarding toolkit aligned with national legislation and international standards to address widespread gaps in employer safeguarding measures.

Output indicator 1.3. ISL facilitated two additional downstream supply chain partnerships between formal firms and marginalised groups, particularly smallholder farmers. This includes supporting Jam Jay to source rice directly from smallholder farmers and helping Wangu Holdings integrate forest-edge smallholders into passion-fruit supply chains using regenerative agricultural practices. These interventions demonstrate viable inclusive business models with strong potential for replication. However, the scale of partnerships this year remains modest compared with the previous review period, when six new partnerships were facilitated.

Overall score for this output was A. Outputs 1.1, 1.2 and 1.3 have all exceeded their targets; however, these targets were last updated in July 2024, and several had already been met by September 2024, which fell within the previous review cycle. The output is assessed as meeting expectations against actual incremental progress over the year in terms of contribution to improved firm productivity, competitiveness, and readiness for investment and export. Delivery was driven by tailored TA, targeted grant support through COMPETE Salone, and sector-specific interventions. The output has continued to develop the pipeline that underpins the programme’s outcome performance on investment mobilisation, although the strategic pivot toward fewer, larger, and more capital-intensive firms has reduced the number of firms supported compared with earlier years.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The output targets were revised in July 2024, but many had already been met or exceeded during the previous review cycle (October 2023 - September 2024). For example, the target for Output 1.2 was raised from 22 to 30 in July 2024, yet by the end of the previous review cycle, ISL had already supported 38 businesses to improve their practices - well above the July 2024 target. Because most targets were reached before this review period began, assessing Year 6 cumulative progress against the July 2024 targets was no longer appropriate, nor would it be useful for future reviews. This review therefore recommends updating the output targets, so they remain meaningful, ambitious enough to reflect the strong programme trajectory, but realistic and aligned with the resources available in the final phase.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead.

S.N.	Annual Review 2025 Recommendations	Progress
1	Final year should focus on learnings from the programme. Learning products should be discussed with the SRO and completed before the PCR.	ISL has developed its Year 6 Comms and Learning Strategy which has been discussed, reviewed, and approved by SRO.
2	ISL should generate learnings from gender markers and the opportunities or challenges in supporting inclusive growth models.	As part of ISL’s Comms and Learning Strategy, the programme’s work on gender, equality and social inclusion is one of the four priority case studies. This case will include key learnings from the programme’s adoption of the gender marker as an evaluation tool while also analysing efforts to support inclusive growth models.
3	ISL should continue to seek to support companies with a focus on export development in line with the Business Case, recognising the importance of export led growth in the medium term.	ISL remains committed to supporting export led growth and has prioritised firms with export potential, including Falcon, Green Roots, Shea & More, LEO and Bengal Agro. While ISL continue to actively explore new opportunities, the current pipeline beyond these firms is limited and small-scale. Nonetheless, ISL remains responsive and should continue to provide catalytic support (or identify for other initiatives) where credible export prospects emerge.

Recommendations
Should the programme be extended for another year, ISL should prioritise consolidation of firm-level gains and documentation of learning. Specifically:
- ISL should prioritise completing and consolidating TA for high‑potential firms such as Bengal Agro, Leo Universal, Wangu Holdings, and Jolaks, to sustain productivity gains and deepen Year 6 supply-chain linkages. Support should also focus on translating export-readiness and feasibility work into concrete trade deal.
- Businesses that have developed investor-facing documentation (e.g., So Pure, Hotel Barmoi, Frontline Chickens) should receive post-TA coaching to finalise financing arrangements. ISL should focus on translating readiness into transactions by aligning firm support with investor outreach under Pillar 2.
- ISL should better align COMPETE Salone’s firm‑level TA with PROSPER’s co-financing and de-risking tools so that firms receiving export or investment support can access the right financial products and partnerships.

ISL should systematically capture lessons from its export‑ and investment‑readiness work and develop case studies that highlight scalable models of SME growth and market change.

Output Title	Investment and Export Promotion. Increased engagement of domestic and foreign investors and buyers with SL enterprises
Output number:		2	Output Score:	A
Impact weighting (%):		34%	Weighting revised since last AR?	No

Indicator(s)	Y5 / Actual	Milestone(s) for this review	Progress
2.1 No. of substantive working relationships generated between ISL and key investment and buyer ecosystem actors (cumulative).	68	78	78 / 15% increase in Year 6 over the cumulative Year 1- 5 results
2.2 No. of working relationships established between businesses (B2B) and/or between investors and businesses operating in Sierra Leone (cumulative).	86	75	111 / 30% increase in Year 6 over the cumulative Year 1- 5 results
2.3 No. of investment practices that have been adapted by international or national investors as a result of collaborating with ISL (cumulative).	14	14	22 / 57% increase in Year 6 over the cumulative Year 1- 5 results

Briefly describe the output’s activities and provide supporting narrative for the score.

The objective of this output is to facilitate increased domestic and international investment into Sierra Leone and to strengthen linkages between Sierra Leonean businesses and national, regional, and international buyers. ISL delivers this through targeted investor outreach, structured facilitation of business to business and investor to firm relationships, collaboration with DFIs, and the use of instruments such as the PROSPER Salone matching-grant facility.

Output indicator 2.1. ISL has strengthened its relationships with key ecosystem actors, particularly DFIs and impact investors. In Year 6, it engaged closely with BII, Proparco, FMO, IFC, DFC, Symbiotics, FSDA and emerging players such as Zvilo and Small Foundation. A major milestone was co‑hosting the largest ARIA investor delegation to Sierra Leone, involving 18 representatives from eight DFIs and four impact investors, which helped expand the pipeline and triggered several follow‑on due diligence missions. These partnerships have progressed from initial introductions to sustained collaboration, with ISL providing deal‑specific TA, coordinating due diligence, and supporting post‑investment engagement. Many of these relationships are expected to continue beyond programme closure, supported by ARIA and BII’s commitment to grow their Sierra Leone portfolios.

ISL also delivered high‑profile events, including the Sierra Leone Investment Forum in London, a Sierra Leone panel at AFSIC 2025, and the Agriculture Investment Conference with FAO and the Ministry of Agriculture, which highlighted new opportunities and enhanced the country’s visibility among global investors. While ISL has maintained investor interest across sectors such as energy, agriculture and financial services, engagement remains concentrated among a relatively small group of DFIs and impact investors due to the limited number of investors active in Sierra Leone.

Output indicator 2.2. ISL facilitated 25 new partnerships between Sierra Leonean businesses and investors or buyers in Year 6 – a 30% increase compared to cumulative achievements in previous years. Much of this progress was driven by ISL’s collaboration with ARIA, which enabled targeted introductions to DFIs, support to firms in refining investment propositions, and brokering of follow-up engagement. This resulted in concrete interest from BII in Truestone, from DFC in Capitol Foods, as well as a new relationship between BII and LAPO Microfinance. In one case, ISL connected a DFI with no previous presence in Sierra Leone to an agribusiness firm, with the engagement now in the final stages of due diligence.

PROSPER Salone played a critical role in brokering and strengthening these relationships by funding feasibility assessments, legal and financial due diligence, and ESG advisory services. Buyer linkages were more targeted and sector-specific and, while not always resulting in immediate transactions, they contributed to export readiness and future deal flow. Some partnerships, such as Truestone’s engagement with BII, did not progress to investment due to structural market constraints such as limited exit options, reflecting ecosystem limitations rather than delivery shortcomings. Buyer relationships were also more challenging to track cumulatively due to their integration across multiple interventions.

Output indicator 2.3. During this review period, 8 investors adapted improved investment practices because of ISL’s support, contributing to shifts in how they assess and operate in the Sierra Leone market. Through PROSPER-funded TA, investors have adapted their approaches to deal structuring. For example, Truestone revised its investment structures and exit strategies and several DFIs have shown greater willingness to engage earlier in the pipeline with tailored due‑diligence support. The development of local-currency bond transactions (e.g. LAPO and the proposed ACTB gender bond) has encouraged domestic banks to participate in capital markets, with some local banks now exploring the opportunity to invest in ACTB who is seeking to raise between $8 million and $10 million. In addition, ISL’s work on sustainable finance principles, ESG guidance, and climate‑finance frameworks has further shaped how financial institutions integrate sustainability and risk considerations into lending and investment decisions. However, practice change tends to be incremental and is often difficult to attribute solely to ISL, requiring qualitative rather than purely quantitative assessment. Moreover, some adaptations, such as enhanced ESG integration and broader uptake of local‑currency instruments, are expected to fully materialise only after programme closure.

Overall score for this output was A. Output 2.1 met its target, while Outputs 2.2 and 2.3 exceeded theirs. However, these targets were last updated in July 2024, and Outputs 2.2 and 2.3 had already been achieved by September 2024, which fell within the previous review cycle. Overall, this output is assessed as meeting expectations. The programme facilitated £35 million in new investment by combining investor outreach, transaction preparation, and risk-sharing through PROSPER Salone while deepening relationships with DFIs and impact investors.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Like Output 1, the targets for this output were also revised in July 2024, and this review recommends updating them for the same reasons - most had already been met or exceeded in the previous review period, making the current targets no longer appropriate for assessing Year 6 and Year 7 performance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

S.N.	Annual Review 2024 Recommendations	Progress
	Consider providing post investment TA to support compliance to DFI and impact investment requirements.	ISL TA Facility allows for pre- and post- investment TA and ISL are currently discussing support for BII upcoming initiatives in Sierra Leone.
	Consider working with more financial institutions to support DFI investment strategy and improve supply of capital - a key bottleneck to growth in Sierra Leone.	In partnership with ARIA, ISL has developed a dedicated Financial Sector TA Facility and recruited a specialist to work with financial institutions to assess their technical and investment needs and help prepare them for DFI investment
	Consider scaling up the LAPO transactions by designing a de-risking facility with BII and/or other DFIs focused on unlocking international capital from DFI/ impact investors.	Under the financial institution TA Facility co-implemented with ARIA, a basket facility has been designed for DFIs to invest in, enabling on‑lending to financial institutions requiring smaller ticket sizes. ARIA is currently socialising the concept with its member DFIs.

Recommendations

- Focus on finalising transactions already under due diligence or negotiation, such as those with BII, Proparco, and FMO, to ensure that pipeline firms like GLS, Capitol Foods, and ManoCap Energy reach financial close before programme closure. This would convert strong pipeline development into tangible investment inflows.
- Building on the success of ARIA missions and investor engagement events, ISL should maintain and expand collaboration with BII and ARIA’s DFI network to institutionalise investor presence in Sierra Leone. A stronger DFI coordination framework will improve alignment on pipeline sourcing, technical assistance, and climate-finance priorities.
- To safeguard investor confidence and ensure firm-level sustainability, the programme should consider providing targeted post-investment TA, particularly for firms that have secured or are finalising DFI funding (e.g., Ecobank, Jolaks, Vista Bank, and So Pure). This will help firms comply with investors and DFI requirements on governance, ESG, and financial reporting.
- ISL should help firms that received export TA (e.g., Bengal Agro, Leo Universal, Jam Jay, and Mountain Lion) to establish concrete export contracts and partnerships. Collaboration with regional trade platforms and UK or EU importers would help operationalise these export-readiness achievements.

Output Title	Pillar 3: Investment Climate Reform. Effective dialogue and collaborative capacity built in targeted sectors across GoSL, private sector and civil society
Output number:		3	Output Score:	A
Impact weighting (%):		33%	Weighting revised since last AR?	No

Indicator(s)	Y5 / Actual	Milestone(s) for this review	Progress
3.1 Number of targeted institutions and organisations that are adapting practices to address investment climate and business enabling environment constraints as a result of collaborating with ISL (including GoSL ministries, BMOs, other government bodies or organisations, and development partners).	7	10	12 / 42% increase in Year 6 over the cumulative Year 1- 5 results
3.2 No. of reform-oriented products developed and used to inform investment climate activity such as policy recommendations, PPD, media engagement, accountability strengthening (includes roadmaps, surveys, plans, publications, research, etc, videos, media briefing papers). (cumulative)	48	56	59 / 23% increase in Year 6 over the cumulative Year 1- 5 results
3.3 No. of activities that facilitate improved collaboration, coordination, and cohesion across private and public sector actors to address business enabling and investment climate constraints (activities include facilitating PPD events, coordination roundtables with private or public sector actors, workshops, trainings, capacity building activities, senior champion engagement, and facilitating and institutionalising dialogue) (cumulative).	65	66	75 / 15% increase in Year 6 over the cumulative Year 1- 5 results

Briefly describe the output’s activities and provide supporting narrative for the score.

This Output covers ISL’s work on investment‑climate reform, aimed at reducing the cost and risk of doing business in Sierra Leone. It delivers this by supporting PPD and producing research and policy analysis that address barriers to trade and foreign direct investment, promote responsible investment, and strengthen coordination across the enabling environment.

Output indicator 3.1. ISL supported five institutions to adapt how they identify, prioritise, and address business environment constraints during the reporting period. A major achievement in Year 6 was the signing of a formal MoU between the Ministry of Finance, National Revenue Authority, Ministry of Trade and Industry, National Investment Board (NIB), and the Sierra Leone Chamber of Commerce, establishing a structured mechanism for consultation on fiscal and investment policy. Under this arrangement, the Chamber now leads private‑sector pre‑consultations that feed directly into IMF engagements and inform the forthcoming Finance Act 2026, marking a shift from reactive lobbying to evidence‑based, institutionalised dialogue. Additional examples of practice change include the Ministry of Justice initiating a formal review of the Copyright Act following ISL‑supported intellectual‑property working groups, and the Ministry of Gender and Children’s Affairs developing an action matrix on women’s access to finance aligned with the National Financial Inclusion Strategy. However, institutional capacity remains uneven, with some MDAs still dependent on ISL facilitation. Full adoption of new practices, such as independently funding and hosting PPDs, will take time to fully consolidate.

Output indicator 3.2. ISL produced 11 reform-oriented products that directly shaped policy dialogue and institutional coordination in Year 6. Key outputs included the National PPD Framework and Toolkit, intellectual property (IP) reform diagnostics, a political economy and commercial feasibility analysis for dry port development, studies on angel investment and the tech startup ecosystem, and guidance materials for sustainable finance adoption. These products saw active uptake - for example, the dry-port analysis informed DFIs' engagement with Global Logistics Services (GLS), contributing to BII's due-diligence mission and progress toward a $10 million co-investment with Proparco. The PPD Toolkit is also being used by ministries and BMOs to structure and track dialogue. ISL advanced IP reform through a commissioned review that led to the creation of an inter-ministerial Technical Working Group and a series of PPDs. Its angel-investment study, presented at Freetown Innovation Week, helped catalyse the launch of the Freetown Angel Investor Network, a platform mobilising capital for high-growth startups. A companion study on the tech-startup ecosystem identified regulatory gaps and investment opportunities. Overall, these products demonstrate not just research generation but clear downstream use in reform processes, investment facilitation, and coordination.

Output indicator 3.3. ISL facilitated 10 activities in Year 6 that significantly strengthened collaboration between public and private actors. These included regular sector-specific PPDs, inter-ministerial working groups, a PPD training series, and high-level coordination forums such as the Public Sector Champions Roundtable on Institutionalising PPD, convened jointly with the NIB. This roundtable resulted in agreement on anchoring PPD within government systems, clarifying institutional mandates and embedding PPD principles in the forthcoming National Public Service Act. ISL also embedded a technical adviser within the Ministry of Agriculture to support coordination of the Feed Salone programme, which the Minister credited with improving alignment and delivery across government, donors, and the private sector. These activities indicate a clear move from fragmented engagement to more predictable, coordinated reform processes. However, sustaining momentum will require continued government leadership and budget commitment, as some coordination gains remain person dependent.

Overall score for this output was A. Outputs 3.1, 3.2 and 3.3 have all exceeded their targets; however, these targets were last updated in July 2024, and several had already been achieved by September 2024, which fell within the previous review cycle. In Year 6, Output 3 has met expectations, showing a shift from ad-hoc engagement to more coordinated reform processes. ISL’s continued work on PPD, reform analytics and coordination mechanisms has begun to take shape as formal structures with potential to be embedded in government and private sector systems.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Similar to Outputs 1 and 2, the targets for this output were also revised in July 2024. and this review recommends updating them for the same reasons - most had already been met or exceeded in the previous review period, making the current targets no longer appropriate for assessing Year 6 and Year 7 performance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year.

S.N.	Annual Review 2024 Recommendations	Progress
	Consider policy reform from a system strengthening approach. This may entail deeper support to one or more sectors/ areas rather than small support to multiple areas. These should be tied to unlocking transactions and originated in close consultation with investors.	This approach is reflected in the programme’s investment climate work in Year 6, which focuses on specific sectors such as carbon markets to address systemic policy constraints. A more systemic approach has also been applied to investment promotion and facilitation, including support to the NIB.
	Draft a clear strategy for NIB support in consultation with the SRO and BHC’s Economic Development team. There should be a clear approach to help unlock investments to Sierra Leone.	ISL, in collaboration with the SRO, has engaged with the NIB to address challenges affecting its ability to unlock investment, though progress has been constrained by institutional and coordination issues. ISL has also explored complementary support through upcoming initiatives, including BII engagement and a forthcoming EU‑funded project.

Recommendations

- Support the Public Sector Reform Unit, MoF and NIB to operationalise the PPD Framework and Toolkit. Embedding structured dialogue mandates and accountability indicators within the forthcoming Public Service Policy and Act will ensure continuity of PPD post-programme.
- Reinforce public-public collaboration by supporting follow-up from the Public Sector Champions Roundtable. This includes clarifying overlapping mandates among ministries and developing a coordination plan for cross-sector reforms (e.g., investment, trade, gender, environment).
- Year 7 should focus on consolidating the capacity built through the PPD Training Series, ensuring ministries and business associations can independently convene and document dialogue processes. A short learning module or e-resource could institutionalise best practices for future use.
- Ensure that policy reforms, especially those under trade facilitation, IPR, and finance, directly support investment opportunities emerging under Pillars 1 and 2. Coordination between reform and investment pipelines will enhance private-sector confidence and systemic impact.
- Develop concise learning products and case studies on PPD institutionalisation, sustainable finance, and gender-inclusive financial reform, to inform FCDO’s successor programming and provide the GoSL with practical reference tools for reform replication.
## VALUE FOR MONEY
The programme continues to deliver value for money across all five dimensions of FCDO’s Value for Money framework: Economy, Efficiency, Effectiveness, Cost-Effectiveness, and Equity. Across the components, results indicate that the programme is contributing towards intended outcomes, inclusive growth, and sustainable economic impact.

Economy – level of programme input costs.

ISL demonstrates adequate economy, with evidence of active cost management and stable overhead ratios despite operating in a fragile market. Overhead spend - covering management time and operational costs - remained broadly unchanged between Year 5 and Year 6. The programme also maintains good transparency on fee structures and cost ratios. However, there is limited evidence of systematic cost-reduction measures such as procurement savings, benchmarking of day rates, or reductions in unit costs. The weighted average day rate increased slightly across all staff levels, and fee expenditure rose to 47.40% of total spend in Year 6 (up from 44.67% in Year 5). This level of fee spend is high and should continue to be closely monitored and managed going forward.

Efficiency – extent to which the programme is converting inputs into outputs.

Efficiency is mixed but broadly credible. The rise in costs is well explained by milestone payments from earlier grant rounds, showing that costs are being actively monitored rather than drifting out of control. Output productivity is evidenced by continued delivery across pillars - for example, in Year 6 the programme provided export TA to seven firms and investment‑readiness support that contributed directly to transactions and pipeline development. However, unit costs for reform‑oriented products rose from £26,698 in Year 5 to £30,253 in Year 6, reflecting higher costs within Pillar 3. While this may be due to the increasing complexity of later-stage analytical work rather than inefficiency, the programme should ensure that this is managed in the next review period.

Effectiveness – extent to which the programme achieved its intended outcomes.

Effectiveness remains strong, particularly at the outcome level, with clear evidence of investment mobilisation, pipeline conversion, and reform traction. In Year 6, the programme supported over £63 million in deals, with £35 million attributable to ISL, demonstrating that firm‑level and investor engagement is translating into real transactions and reinforcing market confidence in line with the programme’s theory of change. The programme also contributed to credible enabling environment shifts, including an MoU between the Ministry of Finance and the Sierra Leone Chamber of Commerce that formalises fiscal policy consultation and embeds more structured PPD processes. The main effectiveness gap relates to final impacts. Evidence is stronger for intermediate outcomes - such as transactions, reform progress, and strengthened institutional capability - than for end-line impacts on jobs and incomes. This is a common challenge for market‑systems programmes, but ISL would benefit from a clearer articulation of when employment and income effects are expected to materialise and how these will be evidenced.

Cost-Effectiveness – outcomes relative to inputs

ISL’s interventions continue to leverage high returns relative to cost. The ratio of investment mobilised to cumulative programme cost reached 312%, meaning every £1 spent facilitated over £3 in investment, more than doubling Year 5 performance. Export promotion interventions achieved a 20.9% ratio of exports to programme cost, highlighting greater efficiency in translating programme expenditure into real trade outcomes. Partner co-investment ratios remained strong: 160% overall, with COMPETE Salone at 220% and PROSPER Salone at 138%, demonstrating ISL’s catalytic role in leveraging external resources.

Equity – outcomes among target groups

Gender and inclusion remain integral to ISL’s VfM approach. In Year 6, 64% of interventions were assessed as having a targeted or transformative Gender Equality and Social Inclusion (GESI) lens, an increase from 58% in Year 5. These interventions went beyond basic gender sensitivity to intentionally address structural barriers to women’s economic participation, including through inclusive finance initiatives such as gender themed bonds and angel investments in women owned businesses, reinforcing ISL’s contribution to more equitable growth. Women-owned businesses accounted for over half of firms supported, and gender-responsive dialogues, such as the financial inclusion roundtable, translated into a national action matrix to expand women’s access to finance. ISL’s deliberate inclusion of women, youth, and micro-entrepreneurs in value chains continues to strengthen equitable access to economic ‑opportunity themed bonds and angel investments in women owned businesses, reinforcing ISL’s contribution to more equitable owned businesses, reinforcing ISL’s contribution to more equitable‑owned businesses, reinforcing ISL’s contribution to more equitable growth.

E: RISK

Overview of risk management

During this review period, risk management has improved, reflecting a more collaborative and transparent approach between Invest Salone and FCDO. A jointly maintained risk register updated quarterly captures fiduciary, reputational, safeguarding, operational, delivery, and external context risks, with clear ownership and mitigation measures assigned. Emerging risks identified outside the quarterly cycle are examined during bi‑weekly meetings and escalated promptly through the SRO and team leadership.

The overall risk rating for ISL has remained ‘major’, driven by a higher external context risk appetite. This is because the programme objectives require approaches that navigate political economy dynamics, vested interests, and evolving global economic trends. The programme monitors risks across eight categories, five have cautious risk levels, and three are receptive. A summary of the main risks over this year are outlined below:
Safeguarding:
Invest Salone maintains a cautious risk appetite and a zero-tolerance approach to safeguarding risks. Recognising that safeguarding risks and requirements continue to evolve, ISL has shown strong commitment to raising awareness of responsibilities and ensuring partner firms review their safeguarding practices.
In February 2025, ISL delivered a Safeguarding and GESI training workshop, prioritising firms involved in monitoring activities. During this process, a key gap was identified: the lack of safeguarding tools tailored to the private sector. Most existing resources are designed for non-profit organisations and are not easily adaptable to commercial business environments.
To address this, Invest Salone has developed a Private Sector Safeguarding Toolkit to help firms and businesses better understand the importance of preventing sexual exploitation, abuse, and harassment in the workplace, while supporting them to develop and strengthen effective policies and systems to address SEAH and to improve how these firms can communicate and work together on safeguarding, both internally and with their partners and the communities in which they operate. As an indicator of sustainability, one partner self-financed an additional training for its staff across its other branches.

Additionally, during the review period, ISL updated its Safeguarding Referral Map targeted at Invest Salone grantees, downstream delivery partners, and staff to reflect current services and institutions, ensuring effective and appropriate referrals in safeguarding cases.
In line with FCDO guidance, Invest Salone has maintained zero tolerance for fraud and safeguarding incidents. this is monitored through creating awareness and online trainings covering key concepts related to bribery and corruption and outlining Cadmus’s policies and responsibilities.
ISL follows a multistage due diligence process for all contracts, Memoranda of Understanding (MoUs), and grant agreements. This process ensures that all individuals, firms, and organisations are vetted for integrity, compliance, delivery capability, and safeguarding standards This process is embedded throughout the delivery chain, with identified risks appropriately captured and mitigation actions implemented and enforced in downstream partner contracts and through regular awareness sessions.
Financial and fiduciary:
Fiduciary risk is inherent in the operating environment, where there may be a perceived reputation for weak financial governance and alleged links to illicit actors. These factors could have consequences for responsible investments, increase due diligence costs, and limit access to responsible finance, affecting financial integrity and broader economic stability. Strengthening ISL’s partnerships with DFIs is expected to reduce fiduciary risk by reinforcing robust due diligence and strong delivery chain controls.
DFI investments such as DFC’s assessment of Capitol Foods have provided deeper financial, ESG and governance scrutiny that complements ISL’s own checks, feasibility studies, legal and financial due diligence for firms to further strengthen pre investment assurances. DFIs’ milestone-based payments and post investment monitoring, including ongoing compliance requirements for firms have reduced the risk of aid diversion and improved transparency across ISL’s delivery chain.
For example, there is no direct evidence of illicit financial flows, but ISL continues to monitor emerging risks closely and has put mitigation measures in place. This vigilance is particularly important given indications that some financial institutions may be increasingly exposed to vulnerabilities, including the potential for a growing share of funding to form illicit activities a trend which, if sustained, could undermine legitimate investment and weaken the overall integrity of Sierra Leone’s financial system.
FCDO maintains a cautious appetite for fiduciary and financial risks.

Policy and programme delivery:
FCDO has a receptive appetite to policy and programme delivery risks. While Invest Salone has made significant progress in advancing PPD and embedding these mechanisms in recent years, sustainability remains a concern, particularly in turning dialogue into tangible actions that deliver lasting reforms and institutional change. There is also a risk that some long-term outcomes may not be fully achieved, albeit there is now a strong collective will within government and among stakeholders to shift towards implementation.

Mitigating this risk requires strengthening PPD mechanisms, enhancing government capacity, clarifying roles, adapting tools for businesses, and closely monitoring progress prior to programme closure to ensure sustainable impact.
Update on Partnership Principles
The UK’s development assistance in Sierra Leone is underpinned by an assessment of the government’s commitment to Partnership Principles: commitment to reducing poverty; respecting human rights; strengthening financial management; and strengthening domestic accountability.

There has not been a recent assessment of the Partnership Principles, and this programme does not provide on-budget support.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Quality and timeliness of reporting and audited financial statements.

A challenge faced in Year 6 was the delayed confirmation of the programme’s overall budget. With final figures not approved until August, ISL operated on provisional assumptions. This impacted budget planning and forecasting accuracy. In November, FCDO identified that certain Invest Salone activities had been over-classified as CDEL, according to HMT and FCDO guidance, only expenditures that directly create or enhance tangible assets should be recorded as CDEL. A process to address this misclassification has commenced, with approval from FCDO’s Finance function. This adjustment will ensure compliance, accurate financial reporting, and alignment with central guidance.

A financial deep dive and invoice spot check conducted by FCDO assessed timely submission of the forecast and spends reports, with clarity in the rationale for variances and measures to address them and categorising invoices by cost heads to ensure transparency.

In August 2025, a contract amendment was signed following FCDO’s decision in 2023 to reduce Invest Salone’s budget by 26%, from £27 million to £19.95 million, and to extend the programme’s end date from December 2025 to March 2026. The key changes included a reduction in contract profit and a decrease in the flexible fund value (the main facility that provide financing to match and/or incentivise private sector investments), which led to a slight increase in non-project attributable costs. Despite the budget cut, overall outcome targets including those linked to Payment by Results (PbR) remained unchanged.

Each month, 10% of fees incurred is retained, payable on satisfactory delivery of key performance indicators which are linked to the outcomes of the programme and assessed by an FCDO 10% Adviser who is external to the programme. The assessment concluded that Invest Salone meets the threshold as it has demonstrated good performance against all PbR linked outcomes, with particularly good results in investment mobilisation, firm competitiveness, export growth, and inclusive impacts for women owned/led firms.
An annual audited financial statement covering up to December 2024 was submitted to FCDO in July 2025, indicating an unqualified opinion i.e. Invest Salone ’s financial statements were assessed to present a true and fair view and comply with relevant accounting standards.

The programme maintains a comprehensive asset register and is reviewed quarterly. Annual physical checks are conducted, with the 2025 verification confirming all assets accounted for and in good condition. Minor improvements are required, such as ensuring all assets including faulty laptops are consistently tagged to improve visibility and tracking. A final asset check will be conducted following submission of the disposal plan and ahead of programme closure.

The partnership between FCDO and the Invest Salone team has been marked by open, honest communication and a shared commitment to raising and addressing risks early. Both sides have consistently taken corrective actions when needed and followed them through. Delivery expectations were met, as were the agreed workplans.
Quarterly narrative and financial reports were good quality, submitted on time, and includes regular updates on risks, safeguarding, value for money and other key areas.
Although communications have improved, the partnership would benefit from stronger better coordination and communications to better amplify the impact of FCDOs support through Invest Salone.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Throughout the review period, ISL team maintained a strong Monitoring, Evaluation and Learning (MEL) function focused on quality assurance, rigorous evidence generation, and continuous engagement with programme partners. In August and September 2025, the MEL team conducted an extensive data collection and verification exercise, including 35 Key Informant Interviews with supported firms, investors, and government institutions, using tailored templates aligned to outcome indicators and triangulating responses with term sheets, financial accounts, portfolio data, and policy documentation to strengthen attribution and contribution analysis. MEL activities were integrated with delivery, involving field engagement during investor missions, diagnostics with MFIs such as ACTB and LAPO, and regular interactions with ministries to verify progress on PPD institutionalisation and reform implementation.

Joint monitoring visits with the BHC programme team to firms in Mile 91, Kamalo and Makoth (including Jam Jay, Green Roots Agro and Planet Solar) provided direct insight into productivity improvements and investment‑readiness gains resulting from ISL support, such as Jam Jay’s ongoing investment discussions and Green Roots’ milestone achievement as the first Sierra Leonean company to export cashew nuts and butter internationally. These combined monitoring efforts directly informed programme decisions, reinforcing the value of linking TA to transaction readiness and guiding the refocusing of lower‑priority technical assistance areas such as tourism and textiles.
As part of the Annual Review, further monitoring visits, spot check interviews, and meetings were held with grant recipients and stakeholders in Port Loko and Freetown to verify results, assess delivery quality and capture beneficiary feedback.
Evidence

In the absence of the results verification mechanism described in the Business Case, the programme has implemented an alternative approach whereby an FCDO Private Sector Development Adviser independently verifies results reported by the supplier throughout the year. This includes conducting systematic checks against indicators, requesting clarifications and evidence, and interviewing implementing partners to confirm reported results. It also includes a review of Invest Salone’s pre collected data from its partners, iterative evidence checks, and partner interviews to validate outputs and outcomes.

This arrangement has provided an additional layer of assurance and has confirmed a consistent pattern of strong delivery. Evidence submitted for Payment-by-Results has been rigorously reviewed and shows a positive trajectory across all outcomes, demonstrating credible performance against the programme’s intended outcomes.

Learning

ISL has generated lessons that will shape its extension. For example, success in a fragile market requires an integrated approach, pairing pre and post investment technical assistance, deploying blended‑finance structures to unlock capital, and sustaining policy dialogue so firm‑level progress is reinforced by enabling environment reforms.

It will be important in the final period to systematically document and disseminate lessons learned and programmes impact to inform policy makers, investors, other stakeholders including FCDO to inform future programming.

Site visit to Invest Salone grantees at Green Roots Agro (Kamalo) and Jam Jay Agriculture (Mie 91)

Date of last narrative financial report	October 2025	Date of last audited annual statement	July 2025