## Annual Review Template
Title: UK Trade Partnerships Programme
Programme Value £ (full life): £29,000,000		Review date: 31/07/2025
Programme Code: 300602	AMP start date: 01/04/2019	AMP end date: 31/03/2026

Summary of Programme Performance
Year	2019	2021	2022	2023	2024	2025
Overall Output Score	A	A	A+	A+	A	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-300602/summary
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-300602/summary

A. SUMMARY AND OVERVIEW
Description of programme
The UK Trade Partnerships Programme (UKTP) programme, funded by the Foreign, Commonwealth, and Development Office (FCDO) is a flagship Aid for Trade (AFT) initiative to increase sustainable trade between developing countries and the UK and EU. The programme supports small and medium-sized enterprises (SMEs) and business support organisations (BSOs) in developing countries to access international markets, improve competitiveness and create jobs, including for women and underrepresented groups. While the UKTP programme’s primary focus is on UK and EU market access, it also facilitates engagement with other regional and international markets, including the United States and the Middle East, where relevant opportunities arise. It operates in countries eligible under the Economic Partnerships Agreements (EPA) and the Developing Countries Trading Scheme (DCTS), offering high quality trade-related technical assistance in priority export sectors. While the programme also delivers non-Official Development Assistance (non-ODA) activities such as support to the Caribbean countries under the EPA framework, these are not included in this review as per previous practice.
Implemented by the International Trade Centre (ITC), the UKTP programme’s overarching goal is to promote economic development through trade. Outputs 3-5 focus on enhancing the export readiness of SMEs in priority sectors and strengthening the institutional capacity of BSOs and Trade and Investment Support institutions (TISIs). Further, the programme facilitates access to UK and EU markets through targeted support such as trade fairs, buyer missions, and market intelligence while also promoting and supporting inclusive growth by prioritising women-led enterprises and underserved regions.
Output 1 “Firms and institutions are aware of how to use EPA preferences and potential benefits” and Output 2 “Business Environment more transparent and conducive for exports to UK/EU markets” have remained inactive since FY2022/23 due to budgetary constraints, with flexibility to reactivate should there be scope and opportunity to do so.
Summary supporting narrative for the overall score in this review
During the FY2024/25 reporting period, the UKTP programme continued to deliver strong results across outputs 3-5, despite a tight delivery window and budget uncertainty. ITC worked with national trade ministries and export development boards to harmonise trade regulations, reduce non-tariff barriers, and improve customs procedures under the programme, for example, through regulatory alignment with Drug Regulation Authority of Pakistan (DRAP) in Pakistan and mango certification in Senegal. Over 100 BSOs were reached with advisory services with 25 institutions reporting changes in operations and management. There was also a concerted effort to increase collaboration with the SheTrades Commonwealth+ (STC+) programme.
In this reporting year the programme achieved an increase in enhanced business capabilities for 597 (262w) SMEs that were supported in export readiness, quality standards, and digital trade tools. It demonstrated successes of the inclusive approach and collaborations with STC+ where over 50% of beneficiaries were women-led businesses (WLBs). Through trade fairs and trade missions, 3,500+ new business contacts were established. These achievements underscore the UKTP programme’s role in supporting resilient inclusive trade systems.
Overall, the programme’s impacts include 72,909 jobs supported, well exceeding the target of 27,000 set for this year, and trade value generation with UK and EU markets for the enterprises assisted to the value of £86m, surpassing the target of £8m set for this year. These strong performances indicate the programme, and its targets can be more ambitious, as noted in the recommendations below.
As the programme enters the final year, the focus should move towards capitalising on results achieved so far and capture lessons learned to inform future trade and development programming. A mid cycle review of targets is recommended to ensure they remain ambitious and aligned to the programme’s scope. Emphasis should also be placed on exit strategies, knowledge transfer and transition to partner institutions to ensure long-term impact beyond programme closure.
The table below sets out the targets and results achieved across key indicators, including for programme impact and outcome, in FY2024/25 and cumulatively since programme inception in 2019.
Level	Indicator(s)	Previous Results to FY2024-25	FY2024-25 Targets	FY2024-25 Results	Cumulative Results from 2019-2025
Programme Impact: Contribute to Job Creation	Number of men and women whose jobs are created, maintained or improved as a result of UKTP support	20,421 / (12,652w)	27,000 / (22,500w)	72,909 / (42,142w)	93,330 / (54,794w)
Programme Outcome: Increased trade between developing countries and the UK/EU	Value of increased trade with UK and EU reported by assisted SMEs in beneficiary countries (including women business enterprises)	£68,448,869 / (£34,504,526w)	£8,835,750 / (£4,340,875w)	£86,774,378 / (£62,730,726w)	£155,223,247 / (£97,235,252w)
	Number of enterprises having transacted business (trade or investment) with UK/EU for the first time as a result of ITC's support (including women business enterprises)	90 / (50w)	64 / (34w)	42 / (32w)	132 / (82w)
	Value of trade expected to be facilitated indirectly as a result of UKTP support including trade with UK/EU)	£22,891,000	N/A / (Inactive component	N/A / (Inactive component)	£22,891,000
Programme Output 3: BSOs extend and improve their services to the focus sector for UK/EU market entry	Number of cases of institutions having improved operational or managerial performance in serving SMEs to enter UK / EU as a result of UKTP support	27	16	25	52
	Number of workshops/coaching sessions delivered to strengthen the managerial and operational capacity of institutions	44	41	62	106
	Number of institutions participating in workshops/coaching sessions to strengthen the managerial and operational capacity of institutions	43	44	116	159
Programme Output 4: Targeted firms have increased capacity to export to UK/EU market	Number of enterprises in beneficiary countries having made changes to their business operations for increased competitiveness toward UK/EU markets as a result of UKTP support (including women business enterprises)	582 / (268w)	72 / (32w)	150 / (86w)	732 / (354w)
	Number of enterprises reached with advisory services (including women business enterprises)	1,163 / (439w)	196 / (61w)	597 / (262w)	1,760 / (701w)
	Value of financing facilitated as a result of UKTP support	£11,150,000	£1,000,000	£5,744,113	£16,894,113
Programme Output 5: Market opportunities activated	Number of business contacts established (including for women business enterprises)	6,829 / (1,145w)	2,775 / (1,210w)	3,852 / (2,040w)	10,681 / (3,185w)
	Number of enterprises that have made business contacts as a result of UKTP support (including women business enterprises)	228 / (88w)	120 / (62w)	135 / (68w)	348 / (156w)
	Number of market studies completed (Only ODA studies should be counted)	10	0	2	12

Major lessons and recommendations for the year ahead
The UKTP programme has significantly outperformed several of its key performance targets during FY2024/25. Jobs supported and export sales to the UK and EU markets exceeded the annual targets. These results reflect both the continued rapid expansion of the programme, benefits realisation of interventions delivered in previous years, and the adoption of a revised results-counting methodology that more accurately captures short-term impact.
In earlier years, the programme applied a conservative methodology for counting jobs. It focused on businesses that had received at least one year of support and demonstrated an increase in UK or EU sales with the outcome captured in year two. This approach was designed to ensure that reported results reflected sustained and measurable outcomes.
As the programme continued in FY2024/25, the original two-year target was retained, and a new methodology was introduced for more transparent and annual results as it became clear that many businesses were realising meaningful improvements much earlier after joining the programme. Interventions such as marketing, improved operational processes, and digital presence often led to immediate gains in jobs and sales. The programme now counts all jobs from the point of a business’s participation in the programme.
Recommendations:
The UKTP programme should continue using the updated job counting approach introduced in FY2024/25. This method better reflects the immediate impact of programme support and ensures more transparent and timely results of the programme’s contributions to increase in export sales and job creation.

It is also recommended that the programme adopt a mid-cycle target review mechanism. This would allow for the adjustment of key performance targets during the implementation period to ensure they remain ambitious, based on actual scale and scope following any in-year adjustments to the programme. Any revision to the original targets should capture mid-year onboarding of new country projects and increase in budgets, if applicable.

Entering its final year, the programme should also place emphasis on exit strategies, knowledge transfer and transition to partner institutions to ensure long-term impact beyond programme closure. This should begin in earnest in Q3 at the latest to ensure sufficient time and planning of handover activities.
The table below sets out the main lessons learned in FY2024/25 and recommendations for FY2025/26 by each output, in addition to the main recommendations above.
Output	Lessons Learned (FY2024/25)	Recommendations (FY2025/26)
1. Firms and institutions are aware of how to use EPA preferences and potential benefits	Although this component was inactive, EPA-related awareness was indirectly enhanced through institutional engagements, trade missions, and steering committees. These forums discussed rules of origin and market access, contributing to stakeholder understanding without direct EPA-focused activities.	Maintain the inactive status unless new geographies or policy shifts demand renewed efforts and budget is made available. Where relevant, integrate EPA messaging into broader institutional capacity-building initiatives to ensure continued awareness.
2. Business Environment more transparent and conducive for export to UK/EU Markets	Despite the absence of direct activities, improvements were observed through institutional strengthening. For example, regulatory alignment efforts with DRAP (Pakistan) and Association Sénégalaise de Normalisation (ASN) (Senegal) indirectly supported a more transparent business environment.	Continue monitoring opportunities to reactivate this component, especially where regulatory reform or trade facilitation can be supported through existing partnerships.
3. Trade and Investment Support Institutions (TISIs) and trade/business support providers extend and improve their services	The programme delivered 62 services to 116 BSOs across multiple countries. Tailored support included benchmarking, certification alignment, and branding. Institutions like SIMAP (Pakistan), ASN (Senegal), and LCA (Lao PDR) embedded UKTP methodologies. The Lao Coffee Brand initiative is a standout example of systemic change driven by institutional support.	Continue prioritising institutional partnerships, especially in underserved regions. Expand support for regulatory alignment and certification bodies to facilitate smoother market access.
4. Targeted firms have increased capacity to export to the UK/EU Market	597 SMEs received 657 services, including tailored coaching, certification support (e.g. BRCGS, ISO), and digital marketing. The programme expanded into new sectors (e.g. nutraceuticals) and geographies (e.g. South Africa, Jordan), demonstrating adaptability. Sector-specific interventions (e.g. in cocoa, coffee, fashion) revised counting methodologies improved impact measurement.	Maintain a diverse and flexible SME support portfolio. Strengthen investment readiness and matchmaking, especially in high-growth sectors. Refine SME selection criteria to ensure export readiness and maximise the results on support.
5. Market opportunities activated	Buyer missions and support for WLBs were fully implemented. Missions took place in Sri Lanka, Cambodia, Ethiopia, and Solomon Islands. Over 50% of supported companies at trade events were women-led. Sector-specific strategies (e.g., cocoa, tea, fashion) and participation in awards (e.g., Great Taste, Nourish) enhanced visibility and credibility. However, Q4-heavy event scheduling limited deal closures, and visa/logistical issues persisted.	Transition eligible WLBs to STC+. Increase awareness of SheTrades Hubs. Secure strategic trade fair placements early, especially for Q1 events. Continue leveraging awards and recognition platforms. Proactively address visa and logistical challenges with country offices to ensure full participation.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The UKTP programme continues to operate under a Theory of Change (ToC) that aims to promote more prosperous, inclusive, and resilient economies by enhancing trade between the UK and ODA-eligible countries. Previous Annual Reviews (2022, 2023, and 2024) have summarised how changes in levels of funding have led the programme to concentrating on institutional strengthening and export promotion technical assistance activities. Reactivating support for ToC Outputs 1 and 2 when opportunity, policy shifts and funding permit remains feasible and consistent with the overall programme ToC. The overall ToC therefore remained valid and unchanged in FY2024/25.
The ToC focused on three core components:
1. Strengthening BSOs to improve services for export readiness.
2. Enhancing SME capacity to meet UK/EU market requirements.
3. Activating market opportunities through trade fairs, missions, and buyer engagement.

Whilst the overall ToC and logframe indicators have not changed, the programme introduced significant changes to its results measurement methodology, particularly in how impact and outcome indicators are tracked and reported to reflect real time impact and scale.
Employment Impact –The programme revised its methodology to count all jobs created, maintained, or improved from the first year of SME support, rather than waiting until the second year. This change acknowledges the immediate benefits of capacity-building interventions and better reflects the programme’s scale and impact.
Trade value Outcome – Sales increases are now measured against the previous year’s results rather than the original baseline year. This provides a more accurate and timelier picture of annual progress.
SMEs – The definition of “SMEs reached with services” was expanded to include all SMEs engaged through webinars, public events, and institutional partnerships – not just those in the core beneficiary cohort. This change captures the broader reach of the programme’s activities
WLBs – The threshold for WLBs was also raised from 25% to 34% women ownership or management, aligning with international standards and improving the accuracy of gender inclusion reporting.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The UKTP programme remains firmly on track to deliver its intended outcomes and impact i.e. to increase SME competitiveness, strengthen trade ecosystems (Programme Outcome) and to support job creation, increase trade with the UK and EU and increase inclusive economic growth (Programme Impact).
In FY2024/25, the programme significantly expanded its reach and impact, operating across 18 national and regional projects. The programme supported 597 SMEs and 116 BSOs, delivering over 1,300 tailored services. This expansion, including the addition of new countries and sectors, contributed to a substantial increase in results across all key indicators. The programme created, maintained, or improved 72,909 jobs (42,142 for women), far exceeding the annual target and bringing the cumulative total to 93,330 jobs supported. This reflects the maturing impact of capacity-building and market access activities initiated in FY2023/24, as well as the inclusion of larger firms in high-value sectors such as pharmaceuticals and nutraceuticals.
Export sales performance also exceeded expectations, beneficiary SMEs reported an increase of £86.8 million in trade with the UK and EU, a 35% rise over the previous year and nearly 10 times the FY2024/25 target. This brings the cumulative total to £155.2 million. The number of enterprises transacting with UK and EU markets reached 132, with 42 new market entries this year. While only Outputs 3-5 remain active due to ODA budget constraints, the original UKTP programme design to include policy support, business networks, and firm-level assistance continues to guide implementation. The programme has been extended to 31 March 2026 on a continuity basis, ensuring sustained support to SMEs and BSOs and enabling further consolidation of results.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The UKTP programme has once again demonstrated strong performance and value for money in FY2024/25, delivering impactful results across a diverse portfolio of countries and sectors. The programme expanded into new geographies (e.g. South Africa, Jordan) and sectors (e.g. nutraceuticals), while refining its data collection and impact measurement methodologies to better reflect real-time outcomes.
The programme’s aims and objectives remain central to the Trade Centre of Expertise (COE) under the “Making Trade Happen” pillar. Its strategic alignment with the COE approach ensures that UKTP activities and interventions are key for delivering UK technical expertise to developing countries, supporting trade facilitation, regulatory alignment, and market access. The programme contributes directly to the UK’s development goals under relevant EPAs, promoting trade-led growth and job creation.
As the Trade CoE model is embedded, the UKTP programme is positioned to provide valuable insights and learning, informing future interventions and enhancing the effectiveness of UK trade support. Its interventions benefit UK buyers and businesses by presenting alternative sourcing networks, reducing supply chain risks, and introducing innovative products to UK markets.
In conclusion, the programme should continue.

## C. DETAILED OUTPUT SCORING
In FY2024/25, activities did not take place under Output 1: Firms and institutions are aware of how to use EPA preferences and potential benefits and Output 2: Business Environment more transparent and conducive for exports to UK/EU markets. No financial resources were available for these outputs due to ODA budget reductions. However, results for outcomes on Output 3, Output 4, and Output 5 are set out below.
Output 3
Output Title	Trade and Investment Support Institutions (TISIs) and trade/business support providers extend and improve their services to the focus sector for UK / EU Market entry
Output number:		3	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of cases of institutions having improved operational or managerial performance in serving SMEs to enter UK / EU as a result of UKTP support	16	25
Number of workshops/coaching sessions delivered to strengthen the managerial and operational capacity of institutions	41	62
Number of institutions participating in workshops/coaching sessions to strengthen the managerial and operational capacity of institutions	44	116

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 3 focuses on strengthening the institutional capacity of TISIs and BSOs to better serve SMEs aiming to access UK and EU markets. This output is key to the UKTP programme’s ToC, as BSOs act as multipliers of impact in delivering services, market intelligence, and promoting export-readiness practices across sectors.
In FY2024/25, the programme significantly expanded its support to TISIs and BSOs, reaching a total of 116 institutions across its global portfolio. These institutions included national trade bodies, sector-specific associations, chambers of commerce, and local cooperatives. The programme delivered 62 distinct services and activities, including benchmarking assessments, performance improvement roadmaps, and targeted workshops and trainings. A total of 25 institutions confirmed operational or managerial improvements as a direct result of UKTP programme support, with written evidence provided to ITC.
The improvements ranged from enhanced service delivery and strategic planning to adoption of international standards and better client engagement practices. These figures not only reflect the scale of engagement but also the programme’s ability to deliver meaningful institutional change.
Examples of institutional support
Pakistan: Support to The Surgical Instruments Manufacturers Association of Pakistan (SIMAP) and Sialkot Chamber of Commerce and Industry (SCCI) to establish accredited testing labs for surgical instruments and develop a national quality mark for “Made in Sialkot” products.
Sri Lanka: Continued collaboration with the National Organic Control Unit to align Sri Lankan organic standards with IFOAM – Organics International (formerly known as the International Federation of Organic Agriculture Movements) a worldwide organization advocating for organics, with over 700 affiliates in more than 100 countries and territories and UK guidelines.
Pacific Islands: Strengthening of informal networks among women-led beauty care businesses and institutional diagnostics for Samoa Association of Manufacturers and Exporters SAME and Investment Fiji.
Jordan: Capacity building for nine institutions including chambers of commerce and industry, with tailored coaching on export market analysis and development of Quantitative Export Factsheets (QEFs).
Uganda: CRM system design and implementation support for coffee sector associations.
Côte d’Ivoire and Cameroon: Training on ISO and food safety standards for national standards bodies and regulatory agencies.
Senegal: Development and rollout of national certification schemes for mango-derived products in collaboration with Association Sénégalaise de Normalisation (Senegal Standards Association) ASN and Directorate of Plant Protection DPV.
These activities have contributed to systemic improvements in institutional capacity, helping BSOs to better serve SMEs in accessing UK and EU markets. The scale, diversity, and depth of engagement justify the A+ score and reflect the programme’s strategic role in strengthening trade ecosystems globally.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Building on the success of FY2023/24, the UKTP programme planned to provide more sustained support to selected BSOs to ensure long-term institutional transformation. The programme strengthened its verification processes for institutional change, ensuring strong documentation and impact tracking. Future support should increasingly target BSOs in high-potential export sectors (e.g. pharmaceuticals, nutraceuticals, ICT, and fashion) to align with demand and market opportunities. The programme could expand its support for digital tools such as customer relationship management (CRM) systems to help BSOs improve how they track, manage and follow-up with SMEs they help. This would enable BSOs to deliver more tailored services and build sustainable relationships with the SMEs. These changes reflect the UKTP programme’s commitment to systemic impact through institutional strengthening, ensuring that BSOs are equipped to sustainably support SMEs in accessing UK and EU markets.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Substantial progress has been made in implementing recommendations from the previous reporting cycle, particularly in refining its data collection methodologies, expanding sectoral and geographic reach, and deepening institutional partnerships.
Lessons learned this year underscore the importance of early engagement with BSOs and SMEs to ensure readiness for international market access, as well as the need for flexible delivery models to accommodate mid-year project expansions. The programme’s revised approach to impact measurement – now capturing employment and trade gains from the first year of support – has provided a more accurate reflection of the UKTP programme’s scale and effectiveness.
Looking ahead, the programme should focus on strengthening sustainability and inclusivity across its interventions, enhancing digital marketing and e-commerce capabilities for SMEs, and supporting BSOs to deliver more targeted, high-value services. Regulatory alignment, certification readiness, and market intelligence will be critical to sustaining momentum and unlocking new trade opportunities.

Output 4
Output Title	Targeted firms have increased capacity to export to UK/EU market
Output number:		4	Output Score:	A+
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of enterprises in pilot countries having made changes to their business operations for increased competitiveness toward UK/EU markets as a result of UKTP support (including women business enterprises)	72 (32w)	150 (86w)
Number of enterprises reached with advisory services (including women business enterprises)	196 (61w)	597 (262w)
Value of financing facilitated	£1,000,000	£5,744,113
Number of advisory services provided	262	657

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 4 is key to the UKTP programme’s mission of enabling SMEs in developing countries to become export-ready for UK and EU markets. By providing tailored technical assistance, certification support, and market preparation services, the programme helps firms overcome barriers to trade, improve competitiveness, and unlock new commercial opportunities. This output carries one of the highest impact weightings at 40% and received an A+ score, reflecting exceptional performance across all key indicators. Notwithstanding this achievement, a higher score has not been awarded because the new methodology for capturing results allows better tracking of outcomes.
In FY2024/25, the programme significantly expanded its support to SMEs across 18 countries and regions, delivering a total of 657 unique capacity-building interventions. These included group trainings, webinars, and intensive one-on-one coaching tailored to the specific needs of each enterprise. The programme also began counting all SMEs reached with services, not just those in the core cohort, capturing the full scale of its impact. As a result, the programme reached 597 SMEs, of which 262 were women-owned or led, reflecting a strong commitment to inclusive trade. Businesses made tangible changes to their business operations to improve competitiveness such as adopting international standards, improving production processes and branding. Beneficiaries won 15 Great Taste awards and secured deals through inward trade missions and participation in Natural & Organic Products Expo (NOPEX) and the International Food & Drink Event (IFE).
The approach to WLBs for the programme was also updated to reflect the international definition for WLBs, meaning those with at least 34% ownership or leadership by women were included in the programme. Of the 150 SMEs that reported making changes to their business operations, 86 were WLBs.
The table below is a summary of delivery partnerships and activities. While not all listed partners are direct beneficiaries, many institutions, such as BSOs and trade agencies, played a critical role in delivering services to SMEs. Their inclusion reflects the collaborative and systemic approach of the programme.

Country	Sector	Key Partners	Activities Delivered	Outcomes / Results
Cambodia	Organic agriculture, food	Cambodia Organic Agriculture Association, Kampot Pepper Promotion Association, Ministry of Commerce, British Embassy	Certification support (BRCGS), ICS training, EU organic regulation workshops, trade fair participation, inward mission	SMEs improved compliance; new export leads; increased visibility at UK trade fairs
Cameroon	Cocoa, chocolate	National Standards Agency (ANOR), Soctracao, Chocolateries Nohi, Fire Mountain	ISO training, trade finance support, chocolate production training, Chocoa and IFE participation	£125k export deal; Great Taste award; Centre of Excellence for specialty cocoa
Côte d’Ivoire	Cashew nuts, tropical fruits	Ivorian Standards Association (CODINORM), Chamber of Commerce, Ministry of Commerce, labs	ISO/FSSC training, trade finance diagnostics, Fruit Logistica participation	£1.88M in potential sales; strengthened quality infrastructure
Lao PDR	Coffee	Lao Coffee Association, Lao National Chamber of Commerce and Industry, Ministry of Industry and Commerce	National coffee brand development, digital marketing coaching, trade fair participation	£39M in export growth; national brand roadmap agreed; stakeholder alignment
Pakistan	Surgical instruments, pharma, nutraceuticals	Surgical Instruments Manufacturers Association of Pakistan, Drug Regulatory Authority of Pakistan, Pakistan Pharmaceutical Manufacturers’ Association, Health & OTC Manufacturers Association of Pakistan, Pakistan National Accreditation Council, Pakistan United Workers’ Federation, Workers and Employers Bilateral Council of Pakistan	OSH and labour rights training, branding, PIC/S accession support, regulatory coaching, MEDICA participation	$2.7M in potential deals; joint ventures formed; improved compliance
South Africa	Agriculture & processed food, greentech	Department of Trade, Industry and Competition, Department of Agriculture, Land Reform and Rural Development, WESGRO, SAMAC, South African Chamber of Commerce and Industry, Johannesburg Chamber of Commerce and Industry	Scoping mission, beneficiary selection, programme design	Programme launched; sector mapping completed
Sri Lanka	Tea, specialty food, beauty care	Ceylon Artisanal Tea Association, AMBA Estate, Export Development Board, UK Tea Academy	Great Taste awards, inward tea mission, certification support, trade fair participation	UK hotel deals; inclusion in UK Tea Academy curriculum; bespoke blends developed
Zimbabwe	Horticulture, nuts	Horticultural Development Council, ZimTrade, Surrey Farm, Kacholo	Trade fair participation, packaging coaching, digital marketing	£2.96M in potential sales; improved packaging and branding

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Over the past year, Output 4 continued to evolve in response to the needs of beneficiary enterprises and shifting global market conditions. The programme expanded into new countries and sectors, a broader and more inclusive definition of export readiness. This meant supporting not only firms already exporting but also those with strong potential to enter international markets. As a result, the UKTP programme was able to better support businesses helping them to meet standards, improve branding and packaging to better compete in global markets.
The programme continued with targeted support in thematic areas such as organic certification, digital marketing, and sustainable packaging reflecting the growing importance of compliance and branding in international trade. For example, in Sri Lanka, food safety certification support helped SMEs meet BRCGS standards, while in Samoa and the Solomon Islands, tailored digital marketing and social media coaching empowered women-led beauty brands to reach new suppliers. In Uganda, coffee quality training was expanded to include consolidation models that reduced export costs for small producers. Meanwhile, in Pakistan, the inclusion of ILO-led missions on labour conditions in the surgical instruments sector marked a significant step toward embedding social responsibility into export strategies. These improvements demonstrate the programme’s agility and responsiveness to meet businesses needs and UK and EU market demand.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The UKTP programme’s journey this year has been another period of growth, learning, and adaptation. The programme continues to validate the importance of tailored, sector-specific support. Lessons from FY2024/25 shows the benefits of understanding the unique challenges and opportunities within each country and sector. This year’s activities that included chocolate tasting training in Cameroon to hand-spinning workshops in Nepal, highlights the value of combining technical capacity building with market access facilitation and regulatory support.
The programme’s approach to branding, certification and trade fair participation has proven essential in helping SMEs overcome barriers to international trade. The programme will continue to refine its methodology, expand its reach, and deepen its impact. Recommendations for the coming year include further integration of sustainability and labour standards into export readiness, enhanced support for digital transformation, and continued emphasis on inclusive trade, particularly for women-led enterprises.
Output 5
Output Title	Market opportunities activated
Output number:		5	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of business contacts established (including for women business enterprises)	2,775 (1,210w)	3852 (2040w)
Number of enterprises that have made business contacts as a result of UKTP support (including women business enterprises)	120 (62w)	135 (68w)
Number of market studies completed	0	2

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 5 focuses on activating market opportunities for SMEs by connecting them with buyers, distributors, and partners in the UK and EU. This output is key to the UKTP programme’s goal of facilitating commercial connections and enabling firms to translate export readiness into tangible trade outcomes. Activities under this output include participation in trade fairs, inward and outward buyer missions, B2B matchmaking events, and digital platforms.
In FY2024/25, the programme continued to offer opportunities for SMEs across the globe, connecting them to buyers, distributors, and partners in the UK and EU. With an output score of A, this year’s performance reflected both the opportunity for engagement, as the programme facilitated 3,852 business contacts, including 2,040 for WLBs, and supported 135 enterprises in making business connections. A higher number of trade events naturally resulted in more visibility and more exposure, allowing the programme to exceed its targets more easily.
The programme supported 27 market access opportunities through trade fairs, buyer missions, and networking events. The trade events ranged from the International Food and Drink Event (IFE) in London to Chocoa in Amsterdam, where UKTP-supported businesses showcased their products, built networks, and gained critical insights into market trends and buyer expectations.
In the fashion and textiles space, companies from Tanzania, Ethiopia, and Madagascar met with major UK retailers at Source Fashion and Pure London. In the food and beverage sector, Pacific Island chocolatiers and Sri Lankan tea producers earned recognition at the Great Taste and Nourish Awards, while Caribbean firms introduced their products at the Food & Drink Expo in Birmingham and Specialty and Fine Food Fair in London (for Great Taste Awards winners), London Coffee Show (for Uganda) and World of Coffee (for Pacific). In the medical sector, Pakistani surgical instrument manufacturers generated over USD 2.7 million in potential deals at MEDICA in Düsseldorf.
Inward trade missions proved equally effective. The programme brought UK buyers to the producers whether it was cocoa farms in the Solomon Islands, tea estates in Sri Lanka, or fashion studios in Ethiopia. In addition, the programme achieved excellent results from an inward mission to Cambodia in February 2025, resulting in rice and cashew nuts orders over USD 2.5m. These opportunities build trust, transparency, and long-term partnerships. The Sri Lanka tea mission alone led to deals with UK hotel chains, retailers, and even inclusion in the UK Tea Academy’s training programme.
Digital platforms also where successful trade events for example six Pacific beauty brands were listed on The Brand Book, a year-round digital trade show for the beauty industry, while Caribbean tech companies attended the Digital Transformation Week in London, a physical event to build partnerships and explore UK market entry opportunities. Due to the timing of events, many trade fairs occurred late in the fiscal year, with deals still under negotiation the results will be realised over the course of the next period.
Output 5 in FY2024/25 was focused on visibility, credibility, and connection. It aimed at helping businesses to attend trade events and tell their story. The preparation and participation for the trade event ensured that the businesses were ready to avail any opportunity to export.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
In FY2024/25, the UKTP programme deepened and diversified its approach to activating market opportunities for SMEs, building on the strong foundation laid in previous years. The programme not only expanded the number and variety of trade events but also introduced new formats and platforms to connect businesses with buyers in more targeted and impactful ways.
Key changes this year was the increased focus on inward buyer missions. These experiences allowed buyers to engage with producers in their own environments, and an in-depth understanding of the challenges faced by the producers that may affect the long-term commercial relationships. The success of these missions has resulted in plans to continue this model further in the coming year.
The programme also broadened its reach in the last financial year by supporting SMEs to participate in consumer-facing events for the first time. Participation in the BBC Good Food Show and the Manchester Coffee Festival gave SMEs direct exposure to UK consumers, helping them understand preferences, gather feedback, and refine their products accordingly. This shift toward consumer engagement continued, with more emphasis on retail readiness and brand storytelling.
The programme also continued to effectively participate in side-events for example, market tours and visits to UK retailers gave SMEs firsthand insights into pricing, packaging, and consumer trends. Looking ahead, the UKTP programme will scale up inward buyer missions across a broader range of sectors and geographies to deepen commercial engagement and market entry for SMEs. It will also enhance support for digital trade platforms and e-commerce readiness, enabling firms to leverage technology for improved market access. The programme will further focus on sustainability and ethical sourcing principles into its market access strategies, aligning with regulatory requirements. These strategies are designed to consolidate the programme’s impact, ensuring that market linkages are resilient, inclusive, and commercially viable over the long term.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
In FY2024/25, the programme made significant steps in expanding market access for SMEs, yet the year also brought important lessons, particularly around the complexity of scaling impact across diverse geographies and sectors. While the programme achieved strong results overall, including a record number of business contacts established and an increase in WLB participation, some challenges persisted. Due to the timing of trade fairs – many of which occurred late in the fiscal year – and the natural lag between initial contact and confirmed sales were not available in some instances by the end of the reporting period.
Visa challenges continued to affect participation in UK and EU-based events, particularly for SMEs from Uganda and Cambodia. Despite early planning and support, several companies were unable to travel, limiting their exposure to UK buyers. In response, the UKTP programme has begun working more closely with FCDO and local partners to improve visa preparation in future trade events.
In Pakistan, the programme continued to support SMEs in sophisticated manufacturing sectors such as surgical instruments and pharmaceuticals. As in the previous year, these sectors generated fewer, but higher-quality, business contacts. In technical industries, success is measured not by volume of contacts, but by the depth and potential of each lead.
Across several country projects, last-minute cancellations by SMEs also impacted participation rates and these companies were removed from the programme to maintain accountability and ensure resources were directed to committed participants.
Despite these challenges, the programme’s overall trajectory remains positive. The number of business contacts established increased reflecting the programme’s growth and increasing reach. The integration of digital platforms, consumer-facing events, and inward buyer missions has diversified the ways in which SMEs engage with international markets. The programme will continue to streamline the approach by strengthening visa support and early engagement with consular services, expanding the use of digital matchmaking and hybrid trade platforms, and engage with pre-event coaching to reduce last-minute dropouts and improve readiness.
These lessons and adjustments will help the UKTP programme deliver even greater impact in the year ahead, ensuring that SMEs are not only introduced to new markets but are well placed to avail opportunities.

## D: VALUE FOR MONEY
Key cost drivers and performance
The UKTP programme has continued to demonstrate strong Value for Money (VfM) in FY2024/25, managing spend whilst delivering across 18 national and regional projects. Over this period, the programme delivered impressive results, generating significant economic and social benefits which reported well against the defined targets.
Across the financial year, £5,924,297 was spent out of a budgeted £5,897,500, resulting in a spend of 100%. This reflects effective budget execution and alignment with planned activities.
Programme Budget Performance FY 2024-25
Pacific, Pakistan and Uganda recorded the greatest expenditures of £913,694, £889,845 and £517,403 respectively. The average project expenditure was £256,413.
Key Cost drivers
The delivery of the programme’s results in FY2024/25 was underpinned by a structured cost framework, reflecting the complexity and breadth of the global operations. The primary cost driver was the programme’s extensive technical assistance and capacity building work with SMEs and BSOs. Providing tailored advisory services, one-on-one coaching, and sector-specific training across 16 national and two regional projects required a significant allocation of resources to secure high-quality expertise and sustained engagement.
A second major cost component was the facilitation of trade promotion activities designed to active market opportunities and build global linkages. This included organising and supporting participation in 20 major international trade fairs and four inward buyer missions. Cost associated with these activities encompassed travel and logistics, booth design and branding, shipment of sample products, and pre-event market readiness support, all of which are crucial to ensuring SMEs meet the standards and expectations of UK and EU buyers.
Further cost drivers included investments in certification and compliance support, enabling SMEs to meet international standards such as BRCGS, ISO, EUDR compliance requirements. Such investments are essential to enhancing competitiveness but entail substantial upfront costs related to audits, system upgrades, and staff training. Programme management and coordination costs also remained significant, driven by the need to oversee a rapidly expanding portfolio across diverse geographies and new sectors, including pharmaceuticals and nutraceuticals in Pakistan.
Finally, targeted gender and inclusivity initiatives contributed to the overall cost profile.
1. Economy
The UKTP programme maintained a strong focus on cost-conscious delivery, ensuring that programme inputs were procured and utilised in a way that upheld quality while remaining cost aware. The programme’s procurement processes, delivered in partnership with local BSOs and trade institutions, enabled access to technical expertise and market services in a more locally grounded and financially prudent manner. / Significant cost economies were achieved through strategic partnerships with BSOs and trade institutions. By working closely with these partners, the programme reduced delivery costs associated with international consultancy and logistics while simultaneously strengthening local capacity and ownership. For example, in Cambodia and Laos, collaboration with national coffee and agricultural associations allowed for tailored training programmes and certifications to be delivered at substantially lower costs compared to using solely external technical experts. / Economies of scale were also realised through the consolidation of activities across multiple country projects. Joint trade missions, regional workshops, and shared marketing resources allowed the UKTP programme to maximise outreach while reducing per-unit delivery costs. For example, participation in major trade fairs such as the Natural and Organic Products Expo (NOPEX) and the World of Coffee was coordinated across several countries, enabling shared logistics and branding investments and enhancing collective market visibility. / Furthermore, the programme’s approach to adaptive management and continual performance monitoring enabled timely reallocation of resources to high-impact areas, avoiding unnecessary expenditure and minimising financial risk. This included the flexible reprioritization of activities when facing delays in funding approvals or operational constraints.
2. Efficiency – are we spending well?
The UKTP programme demonstrates good operational efficiency in FY2024/25, successfully converting resources into high-impact outputs across a growing and complex portfolio. A key enabler of efficiency was the integration of activities across multiple geographies and sectors, leveraging shared trade promotion events, regional workshops, and local institutional networks to reduce delivery costs. The shift in reporting methodology to capture first-year impacts and year-on-year sales changes further strengthened the programme’s ability to assess and adapt inventions in real time. / Output 3 – BSO Extend and Improve Services / Efficiency under Output 3 was driven by a strategic focus on institutional strengthening rather than creating parallel delivery structures. Across the financial year, the programme delivered 62 services to 116 BSOs across diverse markets, exceeding the annual engagement target. These interventions included benchmarking assessments, performance improvement roadmaps, and targeted training workshops – all designed to embed export readiness capacities within local systems. By partnering with existing BSOs, the programme maximised reach and avoided duplication, ensuring that support cascaded efficiently to a wider base of SMEs. / Output 4 – Firms Increase Capacity to Export / Efficiency under Output 4 was evident in the scale and focus of support delivered to SMEs. In FY2024/25, the UKTP programme provided tailored advisory services to 597 SMEs, including one-on-one coaching, certification assistance, and market entry preparation. The use of blended delivery methods (combining in person and online support) further improved cost efficiency and enabled flexible adaption to diverse country contexts. Investments in certification and compliance, although resource-intensive, were streamlines by integrating collective workshops and leveraging group technical support, resulting in lower per-enterprise costs. / Output 5 – Market Opportunities Activated / Under Output 5, the UKTP programme demonstrated strong efficiency in activating market access. The programme supported participation in 20 international trade fairs and organised four inward buyer missions, resulting in 3,582 new business contacts and 135 SMEs establishing new commercial relationships. The programme was able to reduce logistics and branding expenses, enabling more SMEs to access high-profile events than would have been possible through isolated efforts. The timing and sequencing of events, although concentrated in later quarters, were designed to maximise exposure and build momentum for beneficiary firms.
3. Effectiveness – are we spending wisely?
The UKTP programme demonstrates strong effectiveness in achieving its intended outputs, converting support and technical assistance into meaningful improvements for SMEs and BSOs, and activating market opportunities at scale. The programme exceeded or met the vast majority of its targets, showing that resources were successfully converted into tangible economic outcomes. / Output 3 – BSO Extend and Improve Services / A total of 62 workshops were fulfilled across the period, exceeding the annual target of 41 and bringing the cumulative total to 106. / The number of institutions participating in workshops/coaching sessions was 116, greatly exceeding the target of 44. / As a result of these sessions, 25 institutions reporting operational or managerial improvements in serving SMEs to enter UK/EU. This exceeded the annual target of 16 and brought the total to 52. / Output 4 – Firms Increase Capacity to Export / Across FY2024/25, the UKTP programme provided tailored advisory services to 597 SMEs, significantly exceeding the target of 196. Of these, 262 (44%) were women-led which surpasses the target of 61. / 150 enterprises made direct changes to their business operations as a result of UKTP programme support, over double the target of 72. Of these 86 were women-led compared to the target of 32. This brought the total to 732 enterprises having benefitted, with 354 (48%) of these being women-led. / Additionally, a total of £5,744,113 of financing was facilitated as a result of UKTP programme support, greatly surpassing the target of £1,000,000 and bringing the cumulative total to £16,894,113. / These outcome measures demonstrate the programme’s success in translating technical assistance into concrete improvements in business readiness and market competitiveness. / Output 5 – Market Opportunities Activated / Effectiveness under Output 5 was evident in the activation of new trade linkages and market exposure for SMEs. 135 enterprises made business contacts as a result of UKTP programme support against a target of 120. This included 68 WLBs against a target of 62. / 3,852 business contacts established across the financial year against a target of 2,775, with more than half (53% (2040)) for WLBs. This brought the cumulative total since the programme’s inception to 10,681. / Two market studies were completed across the period, bringing the total to 12.
4. Equity – are we spending fairly?
Equity remains a core pillar of the UKTP programme’s approach, ensuring that programme benefits are distributed fairly and inclusively, with a strong emphasis on supporting WLBs and undeserved groups. In FY2024/25, equity considerations were embedded across all outputs, reflected in both the design and delivery of interventions and the selection of beneficiaries. / Output 3 – BSO Extend and Improve Services / Under Output 3, the UKTP programme worked to embed gender-responsive and inclusive practices within institutional partners. Many of the 116 BSOs supported adopted improved approaches to better serve WLBs and marginalised groups, including targeted outreach strategies and the integration of gender considerations into service offerings. / Output 4 – Firms Increase Capacity to Export / Equity was strongly prioritised in Output 4, with a focus on empowering WLBs and increasing their export readiness. Of the 597 SMEs supported through tailored advisory services in FY2024/25, 262 were WLBs, representing more than 43% of the total and exceeding internal inclusivity targets. / 92% of the £5.7 million in financing facilitated was directed towards WLBs, illustrating the UKTP programme’s success in addressing barriers to finance for underrepresented entrepreneurs. These outcomes demonstrate the programme’s effectiveness in enabling equitable participation in trade, supporting women to expand market access, and enhancing their competitiveness in high-value export sectors. / Output 5 – Market Opportunities Activated / Equity considerations were also central to Output 5, with more than 2,040 of the 3,852 business contacts established for WLBs, showing a strong commitment to ensuring that market access opportunities reached diverse groups. / While the programme met or exceeded most inclusion targets, the conversion rate of women-led business contacts into active trade deals remains an area for ongoing focus. Addressing structural constraints, such as access to networks, trade finance, and regulatory support will be critical to improving this conversion in future cycles.
5. Overall cost-effectiveness.
In FY2024/25, the programme demonstrates strong cost-effectiveness through its contributions to inclusive job creation and increased trade between partner countries and the UK/EU markets. / Contribution to Job Creation – / Across the period, the UKTP programme supported the creation, maintenance, or improvement of 72,909 jobs, including 42,142 for women, significantly exceeding the annual target of 27,000 jobs (by over 170%). The cumulative total since programme inception has now reached 93,330 jobs, including 54,974 for women, underscoring the programme’s sustained contribution to inclusive economic growth. / Increased Trade between partner countries and the UK/EU – / The programme facilitated £86.8 million in new export sales to UK and EU markets during FY 2024-25, surpassing the annual target of £8.8 million by nearly tenfold. This achievement reflects a 35% increase compared to the previous year’s results and demonstrates the programme’s effectiveness in unlocking high -value market opportunities. / One outcome metric that did not reach its desired target was the number of enterprises doing business with the UK/EU for the first time as a result of UKTP programme support, recording 42 against a target of 64. A significant number of trade fairs and events took part in Q4, and so a number of promising leads are in place that are not yet recorded.

Overall, the UKTP programme demonstrated robust Value for Money in FY2024/25, effectively balancing cost-conscious delivery with ambitious and inclusive outcomes. Across economy, efficiency, effectiveness, equity, and cost-effectiveness, the programme consistently greatly exceeded its targets, reflecting strong performance and disciplined resource management.
The programmes achievements, including the creation, maintenance, or improvement of over 72,000 jobs, the generation of £86.8 million in new export sales to UK and EU markets, and the extensive support provided to 597 SMEs and 116 BSOs – illustrate a clear and defendable return on investment. The strategic focus on gender equity, demonstrated through targeted support to women-led enterprises and inclusive institutional strengthening, further reinforces the UKTP programme’s alignment with FCDO prioritise for inclusive growth.

E: RISK
Overview of risk management
Over the past year, the UKTP programme operated well within its overall risk appetite, with no risks assessed as high or very high at the programme level. The risk profile remained stable, with moderate exposure in areas like delivery, fiduciary, and reputational risk, mainly due to the scale and geographic spread of operations. The main pressure point was the late approval of funding and mid-year expansion of country components, which compressed delivery timelines. This was mitigated through agile planning, prioritisation, and strong monitoring systems.
Risk is monitored on a monthly basis as part of programme management or more frequently if an issue is flagged. Where needed, risks are escalated to senior management for further action. This approach helps the team to respond and address issues early, before they impact delivery.
Delivery Risk – Moderate (within appetite)
The programme expanded to near 20 geographies and delivered over 1,300 services to SMEs and BSOs. While the short delivery window (due to late funding approvals) posed challenges, the programme adapted well through flexible planning and prioritisation. No major delivery failures occurred.
Fiduciary Risk – Low to Moderate (within appetite)
Financial delivery was strong, with 100% budget spend and minimal variance. Where underspend occurred (e.g. Senegal, Ghana), it was due to external factors such as visa rejections.
Safeguarding – Low (within appetite)
No safeguarding incidents were reported. All delivery partners are required to adhere to ITC’s safeguarding policies, and training was provided where needed. Safeguarding remains a standing agenda item in partner onboarding and monitoring.
Reputational Risk – Moderate (within appetite)
The programme’s high visibility and success in international trade fairs and awards (e.g. Great Taste, Free From, Nourish) enhanced its reputation. Risks related to selective engagement in the Caribbean were managed through clear communication and stakeholder engagement.
Climate and Environment Risk – Low (within appetite)
The programme’s environmental footprint is low, but climate risk was reassessed in line with the Paris Agreement. Several activities actively supported climate resilience, including sustainable sourcing in fashion, organic certification, and compliance with the EU Deforestation Regulation.
Political Risk – Moderate (within appetite)
Political and economic volatility in some countries (e.g. Pakistan, Ethiopia) was monitored closely. The programme-maintained delivery through local partnerships and flexible planning. No major disruptions occurred.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Financial Management
In FY2024/25, the UKTP programme maintained strong financial discipline and met its central spend targets, with total invoicing reaching £5,897,500. The programme continued to operate across 18 geographies, with delivery concentrated in the second half of the fiscal year following mid-year expansions and late-stage budget approvals. Despite these challenges, forecasts and invoicing were managed effectively, and all financial reporting was completed on time.
The programme demonstrated resilience in the face of global financial pressures, including exchange rate volatility and uncertainty around future ODA allocations. During Q3 and Q4, the FCDO team worked closely with ITC to manage delivery risks, holding regular coordination meetings to ensure transparency and alignment on budget execution. ITC showed flexibility in adapting activity schedules and reallocating resources to maintain momentum and impact.
Overspend in specific components – such as South Africa and Nepal – was managed within tolerance limits and reflected strategic ramp-up of activities in anticipation of expanded work plans. Underspend in a few country components, such as Senegal and Ghana, was attributed to visa-related cancellations and timing constraints, with residual funds unable to be redirected meaningfully before year-end.
Programme Management – Delivery
Programme delivery continued to benefit from strong collaboration between ITC and FCDO teams. Regular programme management meetings ensured alignment on work plans, risk mitigation, and in-year adjustments. Improvements in financial and risk management, implemented following previous Annual Review recommendations, contributed to smoother operations and more agile decision-making.
In line with recommendations from FY2023/24, the FCDO teams expanded direct engagement with beneficiaries to assess programme impact. Country visits were conducted to meet SMEs, BSOs, and government stakeholders, providing valuable insights into the effectiveness of UKTP interventions.
In Côte d’Ivoire, for example, government officials and SME representatives highlighted the programme’s tangible contributions to export growth, job creation, and competitiveness. The Ministry of Commerce expressed strong interest in extending the UKTP programme’s duration and deepening collaboration with the UK, particularly in areas such as packaging sector development and digitalisation. These reflections reinforced the programme’s relevance and impact at both the institutional and enterprise levels.
Across the portfolio, the programme continued to deliver results in line with its strategic objectives, demonstrating operational effectiveness, financial accountability, and a commitment to inclusive, sustainable trade development.

G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
In FY2024/25, the UKTP programme continued to strengthen its monitoring and evaluation (M&E) systems to ensure robust tracking of programme performance and impact. Quarterly reporting remained essential to the programme’s M&E framework, providing detailed analysis of activities, progress against milestones, and feedback from beneficiaries. This feedback loop has been instrumental in shaping interventions and refining delivery approaches.
Additionally, refined methodologies for data collection and impact measurement were adopted for the programme. These changes were designed to better capture programme results, particularly in relation to job creation and export growth. For example, employment figures now reflect the total jobs supported from the point of programme enrolment, rather than waiting for a second year of support. Similarly, export sales increases are now measured against the previous year’s sales rather than initial baseline figures, providing a more accurate and timely reflection of programme impact.
These methodological updates have enabled the UKTP programme to report more meaningful results and better demonstrate the programme’s value. They also align with best practices in results-based management and ensure that the programme remains responsive to the dynamic realities of international trade.
Evidence and Learning
UKTP programme learning has been an ongoing process throughout the implementation phase, mainly achieved through direct collaboration with supported SMEs and institutions, capturing feedback through monitoring visits and interactions in trade events. For example, feedback from SMEs following participation in UK trade fairs led to follow-up support, ensuring that future interventions were more targeted, practical, and sector focused. In addition, lessons were also captured through case study’s, success stories, and the UKTP newsletter, which showcased examples of market access activities availed and the results achieved.
In addition to routine quarterly reporting, ITC conducts post-intervention “wash-up” sessions following key activities such as trade fairs, workshops, and technical training events. These sessions provide opportunities to reflect on delivery effectiveness, gather participant feedback, and assess the impact and quality of support provided. As part of the annual review process the FCDO teams carry out on the spot evaluation of the activities by attending trade missions and engaging with beneficiaries through site visits. Observations through these engagements, site visits and interviews inform future programming design and also help gauge the effectiveness and impact of the programme delivery mechanism.
These activities helped identify both immediate outcomes and areas for improvement. For example, feedback from SMEs has informed changes in training content, delivery formats, and follow-up methods. The value of post-event reviews has strengthened the programme’s overall effectiveness and contributed to more sustainable, high-impact outcomes. It also ensures that activities remained adaptable to changing global factors and SME needs.
Regular engagement between ITC, FCDO London, and country-level teams ensured that implementation remained aligned with strategic objectives. Notably, the ITC team for the UKTP programme and FCDO representatives met in Geneva during the SheTrades Hubs Annual General Meeting in September 2024 to review progress and discuss strategic priorities. These engagements reinforced a shared commitment to continuous improvement.

Date of last narrative financial report	10 June 2025	Date of last audited annual statement	11 September 2023