ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	UK Trade Partnerships (UKTP) Programme
Country or region targeted	Developing countries with preferential trade arrangements with the UK, including but not limited to countries in Economic Partnership Agreements (EPAs) and the Developing Countries Trading Scheme (DCTS)
Type of cost extension (if applicable)	Cost extension
Original project budget	£29 RDEL million
Original project start and end dates	01.04.2019 to 31.03.2026
Cost extension value (if applicable)	£3 RDEL million
New reduced budget (if applicable)	Not applicable
New project end date (if applicable)	Not applicable
Business Case Quest Document No.

INFORMATION
What is the project’s purpose?
The UK Trade Partnerships (UKTP) Programme aims to increase UK trade with developing countries. From 2018 to 2023 countries in scope included those in Africa, the Caribbean, and the Pacific with Economic Partnership Agreements (EPA) with the UK. From FY2023/24, this included all developing countries covered by the Developing Countries Trading Scheme (DCTS). / The programme aims to maximise the benefits of preferential UK market access, contributing directly towards fulfilling the UK’s development cooperation commitments in EPAs and realising the ambition of the DCTS. The programme focuses on the business environment for international trade and export promotion in relevant countries, directly supporting firms’ capabilities to trade more effectively with the UK and facilitate market entry. / Increased trade is expected to contribute to economic growth in developing countries, achieving development impact through more and better jobs, including for women. Secondary benefits for UK businesses and consumers include more reliable and diverse, high-quality imports, including inputs that can be used to support opportunities to export goods and services that strengthen export-focused supply chains in developing countries.
What is the objective of the cost extension or other changes?
The objective of this cost extension is to maintain and increase the results already achieved by continuing the programme’s approach and extending it to new countries seeking to benefit from its interventions ahead of programme closure in March 2026 and transition towards the Trade Centre of Expertise (COE). / The UKTP Programme has demonstrated successful delivery of projects, attracting a substantial stream of interest and buy-in demand from Posts in countries the programme is already operating in as well as new geographies. This cost extension will increase the capacity of the programme to respond to the buy-in demand from Posts and deliver activities, contributing to the ongoing development of the Trade COE. / The extension will continue to have a greater focus on the mutual benefits of UK trading arrangements for developing country partners. Leveraging the UK business community and other UK trade and development programmes can provide UK businesses with connections to some of the world’s fastest-growing economies, whilst also supporting poverty reduction.
What is the additional and total support the UK will provide?
The value of this cost extension is £3m, changing the overall value of the programme from the £29 million agreed in the previous addendum to £32 million. / Total programme expenditure by the end of FY2024/25 reached £22.6m. ODA allocations for the programme for FY2025/26 have reached £7.8m, of which buy-in demand is approximately £6.2m. The UK is also providing non-ODA funding to support objectives that are not ODA eligible.
What are the expected results?
The UKTP Programme is a high performing programme and has demonstrated it can deliver export promotion results within a short period of time. It achieved an A+ score in its most recent Annual Review, and has consistently delivered strong value for money, achieving intended outcomes and impacts. Programme results to date include: / Supporting the creation, maintenance, or improvement of over 90,000 jobs, including c.54,000 for women employees. / Generating over £155million worth of exports by SMEs directly supported. / Establishing 10,681 business contacts for 348 beneficiary enterprises to facilitate deals and exports. / Supporting 1,760 MSMEs with advisory services, 701 of which are women business enterprises. / Supporting 732 MSMEs, 354 women-led, improve business practices and operational performance for increased competitiveness toward UK/EU markets. / These results are expected to continue to deliver increasing impacts over the next couple of years, as the passage of time provides more opportunities to accrue amongst the beneficiaries. / With the cost extension, the programme aims to: / Implement a new project in the Democratic Republic of Congo, targeting interventions in the agri-foods and tech sectors. / Continue to provide support to further establish buyer trust in SMEs to help the realisation of business deals in the UK for existing SME beneficiaries. / Identification of total expected results will be finalised to reflect all ODA allocations, including from other sources.
What is the approach to implementation?
The UKTP Programme delivers technical assistance to prepare beneficiaries to succeed in UK/EU and other markets. The programme will continue to work with sector organisations and beneficiaries in target countries to encourage them to adopt business practices that yield trade benefits. Technical assistance includes tailored training and coaching, such as improving product quality, marketing, branding and/or packaging and support to make links with potential buyers, including though trade fairs. EPA and DCTS awareness-raising, trade data updates and embedding ITC Market Access Tools (MAT) are also delivered by the programme. There is evidence that the programme has delivered enterprise-level uptake of new practices in resource efficiency, lean manufacturing and product design and development. / The extension to the programme will be delivered through agreed workplans. The logframe will be revised to include additional activity and trade facilitation ambitions.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The primary change introduced by this cost extension is an increase in the overall programme value, alongside continued support for DCTS countries. The geographic expansion to DCTS countries in FY2023/24 prompted a revision to the programme’s theory of change. Traditionally, the UKTP Programme has focused on direct trade with the UK and EU, and—specifically for the Pacific and Caribbean regions—other relevant markets. The generous rules of origin provisions under DCTS now offer new opportunities to foster transnational supply chains that ultimately connect to the UK. / The overarching theory of change for the UKTP Programme remains highly relevant, with ongoing learning continuing to shape programme priorities. Experience to date has highlighted several key insights: / Output 1: “Firms and institutions are aware of how to use EPA preferences and potential benefits” alone has proven insufficient to generate additional trade without the market linkages established under Output 5. / Output 2: “Business environment more transparent and conducive for exports to UK/EU markets” has shown that foundational reforms yield impact only over the longer term. / Output 3: “TISIs and trade/business support providers extend and improve their services to the focus sector for UK/EU market entry (pilot countries only)” revealed the importance of selecting BSOs with both commitment and capacity for change. While some BSOs demonstrated institutional weaknesses, others showed strong capability, prompting the programme to adopt digital transformation as a key theme. / Due to budgetary constraints, Outputs 1 and 2 have remained inactive since FY2022/23. However, there is flexibility to reactivate these components should scope and opportunity arise.