## Annual Review Template

Title: UK Trade Partnerships Programme
Programme Value £ (full life): £29,000,000		Review date: 31/07/2024
Programme Code: 300602	AMP start date: 01/04/2019	AMP end date: / 31/03/2026

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A+	A+	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-300602/summary
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-300602/summary

A. SUMMARY AND OVERVIEW

Description of programme

The UK Trade Partnerships (UKTP) Programme is a UK-Government funded programme implemented by the International Trade Centre (ITC), a joint body of the UN and the WTO.

The programme aims to increase trade from developing countries to the UK and the European Union (EU) by maximising the benefits of UK and EU Economic Partnership Agreements (EPAs) and the UK's Developing Countries Trading Scheme (DCTS). It works in partnership with government agencies, private sector organisations, public sector institutions, small and medium-sized enterprises, and other local stakeholders.
The programme is funded by the Foreign, Commonwealth, and Development Office (FCDO) as part of its portfolio of Aid for Trade (AFT) programmes. EPA and DCTS countries participating in the UKTP Programme have access to high quality trade-related technical assistance through sector initiatives. Target beneficiaries are supported to be export-ready small and medium sized enterprises (SMEs) that are committed to securing new trade opportunities with the UK and beyond.

This annual review covers the fifth year of implementation of UKTP from 1st April 2023 to 31st March 2024 (FY23/24), during which UKTP operated in 15 countries and two regions that are party to EPAs with the UK or eligible for preferential access to UK markets through the DCTS. These are: Cambodia, Cameroon, Cote d’Ivoire, Ethiopia, Ghana, Laos, Madagascar, Nepal, Nigeria, Pakistan, Senegal, Sri Lanka, Tanzania, Uganda, Zimbabwe, the Caribbean, and the Pacific Islands.

During FY23/24, UKTP focused delivery on Output 3 “Trade and Investment Support Institutions (TISIs) and trade/ business support providers extend and improve their services to the focus sector for UK / EU Market entry”, Output 4 “Targeted firms have increased capacity to export to UK/EU market” and Output 5 “Market opportunities activated”, the deliverables of Output 4 helping to make Output 5 a greater success. Activities mainly focused on market linkages for enterprises that benefitted from technical assistance in the previous years of the programme. UKTP pursued a mixed approach involving direct facilitation of market linkages, capacity development for market engagement and sponsoring participation in trade fairs and market tours. UKTP also supported the creation of sectoral business networks and strengthened the capacity of established business support organisations. Output 1 “Firms and institutions are aware of how to use EPA preferences and potential benefits” and Output 2 “Business Environment more transparent and conducive for exports to UK/EU markets” have remained inactive since FY22/23 due to budgetary constraints.

Summary supporting narrative for the overall score in this review

UKTP continued to deliver a strong performance across Outputs 4 and 5 contributing to the overall Programme Impact (Contribute to job creation) and Programme Outcome (Increased trade between EPA and DCTS partner countries and the UK and the EU). ITC continued to manage the shift towards Outputs 3-5 effectively and demonstrated its ability to flex and respond to demand created by funding through the British Investment Partnerships Directorate (BIPD) voucher scheme. This scheme made available funding for post to bid for an spend through programmes working in the economic development space across the Directorate. The table below sets out the impact and outcomes achieved across key indicators for the programme in FY23/24 and cumulatively since programme inception in 2019.

Indicator(s)	Previous Results till FY23- 24	FY23-24 / Results	Cumulative Results since Inception	Programme Target by March 2025
Number of men and women whose jobs are created, maintained or improved as a / result of UKTP support	14,046 (9,126w)	6,375 (3,526w)	20,421 / (12,652w)	16,046 (10,126w)
Value of increased trade with UK and EU reported by assisted SMEs in pilot countries (including women / business enterprises)	£60,229,192 (£28,379,589w)	£8,219,677 (£6,124,937w)	£68,448,869 (£34,504,526w)	£65,610,000 (£32,816,000w)
Number of enterprises having transacted business (trade or investment) with UK/EU as a result of ITC's support (including women / business enterprises)	50 (18w)	40 (32w)	90 (50w)	100 (35w)
Value of trade expected to be facilitated indirectly as a result of UKTP support / (including trade with UK/EU)	£22,891,000	N/A (inactive)	£22,891,000	£25,000,000 (£2,500,000)

*figures in brackets indicates attribution to Women

A summary of the main activities and achievements include:

- UKTP created, maintained or improved employment for an additional 6,375 people this year, including 3,526 women. This makes for a cumulative total of 20,421 jobs created, supported or maintained through the programme since inception, delivering strong Programme Impact (Contribute to job creation).
- Systemic changes to business ecosystems were pursued on a selective basis, working in focus sectors and select countries under Programme Output 3/Project Output 1 (Institutional advisory services to improve membership services provided to business support organizations). For example, in the Pacific, at a regional level UKTP implemented efforts to organise the business ecosystem for the beauty care industry, particularly among women business leaders. As a result, an informal sector association has formed and is now operating independently of direct ITC support and coordination. At a national level, commitment was secured from Investment Fiji to strengthen their organisation, including its change-and-improvement process. Work undertaken to date include a benchmarking assessment, a planning workshop with board members to review the benchmarking assessment, and a workshop with staff members to develop a more carefully designed set of performance measurement indicators to help them assess, understand and report on performance more effectively. A draft report and recommendations are being finalised for implementation in the next fiscal year. UKTP also supported business support organisations in Cambodia, Madagascar, Sri Lanka, Uganda and Fiji.
- UKTP achieved excellent progress implementing Programme Output 4/Project Output 2 (Advisory services to increase capacity to export to UK/EU market provided to firms) delivering training and tailored coaching to beneficiaries across UKTP countries. FY23/24 saw the expansion of UKTP into new geographies and sectors, with the programme active in areas such as marketing, branding, and packaging. In total, UKTP reached 318 SMEs including 211 women-led businesses and provided 316 advisory services. Of the total 318 SMEs reached with services, 124 represent new companies which have confirmed making changes to their business practices for the first time as a result of UKTP.
- The programme also delivered numerous tailored capacity building trainings and one-on-one coaching programmes for beneficiaries to better access UK and EU markets. In total, 123 SMEs surveyed (including 83 women-led businesses) made 1,415 business contacts (including 902 contacts established by women-led businesses).
- Under Programme Output 5/Project Output 3 (SMEs introduced to UK and EU markets), UKTP pursued an intensive schedule of trade events in the UK and Europe during the reporting period across the spectrum of food products, beauty care, fashion, health, and creative industries attending 20 trade fairs and shows. UKTP also held major business to business side events to the Rugby World Cup for Pacific businesses.
Major lessons and recommendations for the year ahead

Output 1: Firms and institutions are aware of how to use EPA preferences and potential benefits
Inactive component since FY22/23.
Output 2: Business Environment more transparent and conducive for export to UK/EU Markets
Inactive component since FY22/23.
Output 3: Trade and Investment Support Institutions (TISIs) and trade/business support providers extend and improve their services to the focus sector for UK/EU Market entry
Response to FY22/23 recommendations: As part of the re-structuring of the programme for the FY23/24 cycle, it was initially envisaged that this component would continue in a far more limited manner than in previous cycles of the programme. As such, no specific recommendations for this output were provided in the FY22/23 Annual Review, and targets for Output 3 were set conservatively for the FY23/24 cycle.
Lessons Learned in FY23/24: As FY23/24 progressed, more opportunities arose to deliver deeper impact with and through local institutions than previously anticipated. The programme capitalised on these opportunities in multiple geographies, including the Pacific, Cambodia, Madagascar, Sri Lanka and Uganda. The interventions represented cost-effective services to deliver impact at an institutional level, thereby multiplying the overall reach of the programme. This further provided mechanisms to embed learning through the programme that would outlast any single fiscal year delivery cycle providing a degree of continuity.
Recommendations: Opportunities to build links with local institutions should continue to be maximised to deliver deeper interventions, including in any new geographies.
Output 4: Targeted firms have increased capacity to export to the UK/EU Market
Response to FY22/23 recommendations: Recommendations in FY22/23 Annual Review acknowledged the transformative impact of facilitating financing for SMEs, whether in the form of loans, grants, equity sale, or other mechanisms. Recognising the serious challenges in guaranteeing or confidently assuming successful facilitation of investment, targets for investment were set only in geographies with specific planned activities focussing on investment.
Lessons Learned in FY23/24: Capacity building support to SMEs continued to be one of the core modes of impact delivery for the UKTP Programme. In FY23/24, the programme expanded substantially into multiple new geographies (DCTS countries) and sectors, allowing a much wider set of goals and approaches as well as meaningful opportunities for learning. Numbers of firms targeted in each country varied considerably based on objective, level of sophistication and the way markets work. For instance, the programme supported the development of sophisticated manufacturing in Pakistan’s pharmaceutical and surgical instruments sectors resulting in significant increased trade. Engaging with the tech services sector in the Caribbean demonstrated considerable potential for impact with over £1.5m worth of market opportunities being realised following a technology event, despite services not being explicitly covered by the EPAs.
Furthermore, the programme managed to outperform expectations in terms of investment. In some cases, UKTP facilitated introductions to potential investors in geographies beyond the programme’s core investment-focussed activities. Moreover, several beneficiaries, while securing investments independently, acknowledged that UKTP's capacity-building activities played a pivotal role in their success.
Recommendations: Continue to support firms with technical assistance to build capacity for participation in market opportunities and other export promotion activities. Explore scope for introducing new firms to the programme, with clear visibility of export readiness to support effective market contacts and secure trade deals.
Output 5: Market opportunities activated
Response to FY22/23 recommendations: It was highlighted in the FY22/23 Annual Review that the organisation of inward buyers’ missions to beneficiary countries could be an impactful mechanism to drive impact. In FY23/24, the programme delivered multiple such missions to positive effect, including in Uganda and Nepal.
The FY22/23 Annual Review also acknowledged underperformance on targets for women-led businesses participation and success at market events (e.g. trade fairs and market tours). It was recommended that for the subsequent year a deeper focus be placed on supporting women-led businesses. In particular, it was recommended that UKTP leverages ITC’s in-house expertise in building women-led businesses through its SheTrades Initiative.
In FY23/24, the programme responded strongly to this recommendation. In two countries (Zimbabwe, Ghana) beneficiary cohorts were reformulated to focus on women-led businesses, and deeper collaboration with ITC’s SheTrades initiative. In addition, the activities in newly added Nigeria were directly managed by SheTrades. In FY23/24, more than half of all companies supported to participate in trade events were women-led, nearly doubling the year’s target. In terms of performance, women-led businesses shone at these events, and number of business contacts established by women-led businesses outperformed the target. In order to support the development of more export-ready women-led businesses, which could be connected to markets (through trade fairs or other events) in the future, a dedicated “Women in Export” workshop was organized and delivered for six Pacific Islands in Samoa in January 2024.
Lessons Learned in FY23/24: FY23/24 demonstrated the value and impact of organising inward trade missions to beneficiary countries. The previous years’ experience underscored the significant time investment required for effective mission preparation and execution. Some challenges were encountered in organizing and delivering missions within a single fiscal year, especially when time-bounded by specific harvest seasons. Nevertheless, the programme plans to continue providing this type of impactful market-access support in FY24/25.
Trade fair experiences vary significantly by sector. In Pakistan, where UKTP supports mature companies in sophisticated sectors like surgical instruments and pharmaceuticals, competition at fairs is intense and ensuring a strategic location is a key. This can be only achieved by very advance planning (often 6-9 months prior to the show) and sufficient resources to upgrading the UKTP pavilion's visual presentation. "Success" metrics also differ across sectors. While numbers of business contact for surgical instruments manufacturers fell short of expectations due to limited public attendance, the quality of these contacts was exceptional. Most evolved into valuable leads, with some culminating in substantial deals.
Recommendations: The programme should rationalise some elements of the programme, particularly where capacity-building support is being offered to firms that are women-led, and may also work in sectors with a heavy concentration of women-owned businesses by moving these firms to the SheTrades Commonwealth+ programme.
The programme should also seek creative ways to secure strategically advantageous and competitively priced positions at trade fairs for FY23/24, working with the FCDO London team were these events fall in quarter one of the fiscal year to maintain continuity and impact.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change (ToC), including any changes to outcome and impact indicators from the original business case.

The UKTP ToC sets out how the programme will contribute towards building more prosperous, inclusive and resilient economies to the mutual benefit of citizens and businesses. It does this through trade and investment between the UK and ODA-eligible countries, increasing the number of export-ready companies ready to trade with UK and other markets, increasing the number of quality jobs, both formal and informal, within small and medium-sized enterprises (SMEs), and increasing export promotion opportunities via attendance at trade fairs and other activities.

Previous Annual Reviews (2022 and 2023) have summarised how changes in levels of funding have led to UKTP concentrating on export promotion technical assistance activities (ToC component 3). Re-activating support for ToC Components 1 and 2 when funding permits remains feasible and consistent with the overall programme ToC.

The new operating model introduced changes to decision-making on where available funding was allocated. UKTP is principally funded as a centrally-managed programme i.e. with budget allocation decisions managed by a UK department which consults with UK High Commissions and Embassies (Posts) located in developing countries. In FY23/24, funds potentially available to UKTP were allocated to Posts in selected priority countries, which then decided which economic development and trade programmes best met priorities in each country. This “buying-in” process by Posts significantly influenced the geographic and sectoral focus of the UKTP portfolio and allowed the programme (together with other programmes in the “buying-in” pilot) to contribute to testing the logic for the planned future Trade Centre of Expertise (COE).

The inclusion for the first time of DCTS-eligible countries did not change the programme logic, and the overall ToC and logframe remains unchanged and valid.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track to contribute to an increase in value of trade with the UK and EU (Programme Outcome) and the number of jobs created, maintained or improved in the businesses that achieve those expected exports (Programme Impact).

Following the expansion of the programme to DCTS countries, the logframe was updated for greater granularity of results.

For country-level monitoring the logframes were “nested” i.e. the impact level results and indicators for each country correspond with the outcome level results and indicators for the overall programme. Since the major ODA spending cuts in 2022, only Outputs 4 and 5 have been in use – the ones focused on export promotion support directly to firms. But the original UKTP design remains valid i.e. outputs for policy change, support to business networks and support to firms.

The impact of capacity building and market access activities for firms, predominantly taking place in the second half of FY23/24 will be reflected in increased sales in FY24/25. Similarly, the numbers of jobs supported for these companies is not reflected in results for FY23/24.

The programme has been extended to 31st March 2026 on a continuity basis.

Programme	Indicator	Cumulative to / 31 March 2023	FY23/24 results	Cumulative to / 31 March 2024	Programme target for 31 March 2025
Impact: Contribute to job creation	Number of men and women whose jobs are created, maintained or improved as a result of UKTP support	14,046 / (9,126 women)	6,375 / (3,526w)	20,421 / (12,652 women)	16,046 / (10,126 women)
Outcome: Increased trade between EPA and DCTS partner countries and the UK and the EU	Value of increased trade with UK and EU reported by assisted SMEs (including women owned SMEs)	£62,280,000	£8,219,677 (£6,124,937 / women)	£68,448,869 (£34,504,526 women)	£65,610,000 (£32,816,000 women)
	Number of enterprises having transacted business (trade or investment) with UK/EU as a result of ITC's support (including women-owned enterprises)	50 / (18 women-owned/led)	40 / (32 women)	90 / (50 women-owned/led)	100 / (35 women)

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

On its own merits, UKTP has demonstrated strong results and value for money and is delivering interventions at pace with corresponding inputs. ITC has demonstrated its capabilities not only in delivering the planned programme, but also adapting to changing funding levels for UKTP and expanding geographies through the BIPD voucher scheme, whilst retaining the overall aims of the programme to boost trade and sustain jobs to meet its mandate set out in section A of this review. Continuing the programme will consolidate the outcomes achieved thus far and facilitate further trade and job creation/sustainability as the benefits of activities carried out in FY23/24 mature over the coming years. The programme also built up a good reputation in its years of operation both with internal HMG and external stakeholders including partner governments. It will also help the UK meet its development commitments set out in relevant EPAs.

In the context of the wider portfolio, UKTP is a key programme in the Trade COE theme “Making Trade Happen” and interventions undertaken by UKTP will continue to be an important element of support under the Trade COE. The Trade COE is one of five COEs and the COE approach is emerging as the principal mechanism for delivering technical expertise from the UK to developing countries. Therefore, a priority for the programme for the next fiscal year will be gathering learning for the Trade COE and commencement of new interventions where value for money and benefits realisation is low will be limited in anticipation of the Trade COE launch.

## C. DETAILED OUTPUT SCORING

In FY23/24, no UKTP activities took place related to Output 1: Firms and institutions are aware of how to use EPA preferences and potential benefits and Output 2: Business Environment more transparent and conducive for exports to UK/EU markets. No financial resources were available for these outputs due to ODA budget reductions.

Emerging outcomes on Output 3, Output 4, and Output 5 are set out below.

Output Title	Trade and Investment Support Institutions (TISIs) and trade/ business support providers extend and improve their services to the focus sector for UK / EU Market entry
Output number:		1	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of cases of institutions having improved operational or managerial performance in serving SMEs to enter UK / EU as a result of UKTP support	2	11 / Exceeded expectations
Number of workshops/coaching sessions delivered to strengthen the managerial and operational capacity of institutions	2	8 / Exceeded expectations
Number of institutions participating in workshops/coaching sessions to strengthen the managerial and operational capacity of institutions	2	11 / Exceeded expectations

FY2023/24 represented a significant shift in the way-of-working for the UKTP Programme. When the logframe for the year was initially designed, the intent was to focus primarily on shorter-term sales impact through supporting export-ready SMEs to connect to markets through trade fairs and other market access services. As such, it was not initially envisaged that there would be significant focus on delivering support to BSOs and other institutions. For this reason, the targets for these institution-related indicators were set conservatively and focussed on legacy countries where UKTP had a history of delivery, such as Fiji and Madagascar.
Through the course of the year, however, opportunities arose to deliver cost-effective, impactful services for institutions in several UKTP countries. Recognising the potential for systemic impact through institutional support, the programme capitalised on these opportunities to strengthen business-support ecosystems surrounding the programme and impart lasting benefit despite the project’s short-term delivery cycles.
Looking forward, the programme has realised the potential impact of supporting institutions and has appropriately increased targets to more accurately represent the programme’s focus on this Output.

Briefly describe the output’s activities and provide supporting narrative for the score.

In FY23/24, activities to support various types of TISIs and business support organisations (BSOs) and other networks took place in Madagascar, the Pacific region and Sri Lanka, benefitting 11 BSOs. UKTP also engaged with BSOs in Cambodia, Pakistan, Tanzania and Uganda.

In Madagascar, UKTP provided institutional support to the Export Processing companies and Partners Association (GEFP) through its transition to a new executive team and delivered capacity building training sessions to GEFP and the Economic Development Board of Madagascar (EDBM).

In the Pacific region, UKTP supports a group of mostly women entrepreneurs in the beauty care sector. In FY23/24, UKTP convened these entrepreneurs to assess options for formal or informal networking. After several sessions, initially with UKTP coordination and then independently, the group decided to continue as an informal discussion and networking organisation, rather than formalising into an official sector association at this time. In Fiji, UKTP provided organisational diagnostics assessment to Investment Fiji, which helped the organisation identify how to adapt from a primarily regulatory body for investors, to a new role including supporting businesses to develop and prepare for international trade. In Samoa, UKTP supported an initial organisational diagnostic with the Samoa Association of Manufacturers and Exporters (SAME), which has already made recommendations including for the procurement of video- conferencing equipment to enable the organisation to engage more effectively with stakeholders around the world. Recent overtures by the government to the exporting and business community to establish a more formal approach to support means SAME would be potentially well positioned to increase its links to government and to be a service provider in this area.

In Sri Lanka, UKTP supported the National Organic Control Unit of the Economic Development Board (EDB) of Sri Lanka to uplift the country’s organic standard to match IFOAM – Organics International (a worldwide organisation advocating for organics) and UK guidelines. UKTP support included an evaluation of standards equivalency and awareness raising effort among organic farmers, operators and exporters regarding organic requirements and certification processes. A well-received public-private stakeholders’ validation workshop on the assessment of the Sri Lankan organic standard was held in March in Colombo.

In Cambodia, UKTP carried out institutional assessments for two BSOs in organic foods and speciality pepper. These diagnostics provide a roadmap for the development of these two institutions, to be implemented in FY24-25 and beyond.

In Uganda, organisational bench-marking assessments were conducted for three coffee sector associations, to inform comprehensive reports setting out a holistic view of the strengths and weaknesses of the BSOs, strategic guidance for improvement.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Changes to the output during the year include increased support to TISIs and BSOs. In FY 23/24 UKTP supported a wider range of institutions in Madagascar, The Pacific region, Sri Lanka, Cambodia, Pakistan, Tanzania and Uganda. UKTP team collaborated with SheTrades Commonwealth+ programme during the SheTrades Hub launch in Ghana. UKTP supported the National Organic Control Unit of EDB in SL to uplift the country’s organic standard to match IFOAM and UK guidelines. UKTP carried out institutional assessments for two BSOs in Cambodia.

These changes demonstrate the UKTP’s continued proactive approach in supporting TISIs and BSOs in their efforts to enhance their capacity and effectiveness.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

UKTP is making significant strides towards fostering systemic change in business ecosystems, particularly focusing on the cosmetics sector in the Pacific region. By supporting women business leaders and enhancing business support organisations (BSOs) in nations such as Fiji, Cambodia, Madagascar, and Sri Lanka, strong BSOs play a crucial role in empowering businesses to take calculated risks necessary for expansion and internationalisation. They provide essential resources such as knowledge, networking opportunities, and enhanced credibility, all of which are vital for minimising risks.
With further capacity-building initiatives, these organisations can perform more strongly. This will not only improve access to global value chains but also attract investment and contribute to economic growth. See recommendations in Section A.

Output Title	Targeted firms have increased capacity to export to UK/EU market
Output number:		4	Output Score:	A+
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of enterprises in countries having made changes to their business operations for increased competitiveness toward UK/EU markets as a result of UKTP support (including women business enterprises)	106 (39 women- owned/ led)	124 (98 women-owned/led) / Exceeded expectations
Number of enterprises reached with advisory services (including women business enterprises)	148 (57 women- owned/ led)	126 (101 women- owned/led) / Partially met expectations
Value of financing facilitated	£705,000	£5,455,000 (£5,295,000 to women-owned/led enterprises) / Significantly exceeded expectations
Number of advisory services provided	298	316 / Exceeded expectations

Briefly describe the output’s activities and provide narrative for the score.

During the FY23-24, UKTP delivered training and tailored coaching to beneficiary enterprises across UKTP countries. The table below sets out key activities.

Country	Sector	Key partners	Activities
Cambodia	Organic agricultural products. Geographic Indication Kampot pepper	National ministries. / Business support organisations	These activities focused on improving market access and building brand awareness which included a competitive call for applications, site visits, marketing and branding support: individual technical advice and support for participation in international trade fairs in November 2023, March 2024)
Cameroon	Cocoa	Interprofessional Council of Cocoa and Coffee (Cameroon) / International Institute of Chocolate and Cacao Tasting (UK)	Two-month capacity building course focused on chocolate tasting, two companies graduating to intermediate level. Specialist strategic analysis on access to finance for four companies.
Caribbean	Services – music production/ songwriters	Professional producers. Artists and Repertoire (A&R) representatives from record labels/ music publishers (UK)	Jamaica song writing residential camp, leading to 40+ original compositions, discussions with major labels for 7+ songs (3 well-advanced in negotiation)
Cote d’Ivoire	Fresh fruit, cashew	Certification bodies (Cote d’Ivoire, France, UK)	Technical assistance to 5 fruit companies and 2 cashew companies to align with international standards. Technical advice for participation in international trade fair in February 2024
Ghana	Artisanal, women-led chocolate makers	Ghana Export Promotion Agency (GEPA) / Financial institutions including Wangara Green Ventures, Rural Development Fund and key banks	Two-day professional skills development workshop in parallel with the Aspen Network of Development Entrepreneurs Annual Conference (ANDE) in September 2023. National forum on access to finance, with 46 women-led businesses and 10 financial institutions (FIs) (November 2023) / With GEPA, 3-day onsite workshop on Export Pricing for 35 women-led businesses. / Tailored coaching for 4 businesses to develop UK route-to-market strategies, including identifying suitable sales channels and creating a UK-specific pitch deck (January 2024)
Lao PDR	Coffee	Department of Trade Promotion / Ministry of Industry and Commerce Ministry of Agriculture and Forestry. / Lao Coffee Association.	Two International Coffee Day events to promote the Laotian coffee sector to international participants, networking for local producers (29th September 2023) / On-site training workshop for 10 SMEs, followed up with tailor-made support on brand image, marketing content and visual identity (November 2023)
Madagascar	Textile and clothing	Fashion & Design Institute of Mauritius. Cluster ANJAIKA (a collection of women-led businesses) / Financial institutions.	Analysis and networking support on access to finance. Networking between women-led businesses and academic institute. / Capacity development on corporate social responsibility and on lean management.
Nepal		Nepal Pashmina Industries Association (NPIA) / Nepal Fibre Processing Private Limited (NFPPL)	Technical assistance on product and design development and UK marketing support October/November 2023). Technical support to cashmere fibre processing capabilities. Technical advice for participation in international trade fair in February 2024. Site visits to Scottish cashmere goat farmers.
Nigeria	Shea butter	Nigerian Export Promotion Council (NEPC)	17 online training sessions including marketing, pricing, traceability). Packaging workshop with NEPC (October 2023). Workshop on digital marketing and international buying processes (October 2023). Before and after technical advice to SMEs that participated in international trade fair (February 2024)
Pacific / (Fiji, Papua New Guinea (PNG), Samoa, Solomon Islands)	Specialty foods, ingredients, coffee, beauty	Business support organisations. / Ministry of Foreign Affairs and Trade and Ministry of Commerce, Samoa. / Samoa Association of Manufacturers and Exporters	Coaching support, including packaging, negotiations skills. Before and after technical advice to SMEs that participated in international trade fairs / Women in Export Leadership Workshop (January 2024) / Pilot training programme for digital marketing and social media
Pakistan	Surgical instruments	Trade Development Authority of Pakistan (TDAP). / Surgical Instruments Manufacturers Association (SIMAP) Pakistan Pharmaceutical Manufacturers Association (PPMA). / Surgical Instruments Manufacturers Association of Pakistan.	5-day workshop focused on marketing strategy, branding and European regulations (September 2023) / Comprehensive advisory support to improve branding and marketing and other technical advice for participation in international trade fair in November 2023. / Joint ITC/International Labour Organization (ILO)-Pakistan missions on labour conditions in the surgical instruments sector (November 2023, March 2024)
Senegal	Agribusines, home décor, black soldier fly breeding, beauty care		Support to food technology company for participation in Black Soldier Fly Conference (BSFCON23) in September 2023. / Two-day marketing and branding workshop (November 2023) and individual company coaching. / Packaging coaching (October 2023)
Sri Lanka	Organics	Export Development Board of Sri Lanka	Digital branding workshop. / Individual company technical support on branding materials / Two-day workshop on organic standards, plus 1-day site visit to organic coconut farm (March 2024) / Food safety certifications (March 2024) / Support to make submissions to Great Taste Awards.
Tanzania	Textile and clothing	Tantrade (government export promotion body). Textiles manufacturers association (TEGAMAT)	4-day training on lean manufacturing (October/November 2023), followed by individual company coaching on-site
Uganda	Speciality coffee	Uganda Coffee Federation. / Africa Coffee Academy (ACA).	Two-day training on branding and marketing, followed by individual company support. / Six-day training programme on coffee quality, with all Coffee Quality training modules delivered by a certified trainer / UK coffee roasters’ tour of Ugandan coffee growers (January 2024).
Zimbabwe	Women-led businesses in apparel, accessories, home décor, jewellery, cosmetics	ZimTrade (government export promotion body) / Ministry of Women’s Affairs	22 training sessions on market access, pricing strategies, marketing, traceability, sustainability, negotiating and interpersonal skills (July 2023/ March 2024) / Before and after technical advice to SMEs that participated in international trade fair in February 2024 / Creation of networking group for peer-to-peer learning, sharing lessons on assignments provided by trainers.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The programme has expanded to new countries and new sectors such as organic products, women led-chocolatiers. Existing activities have been revised and expanded such as the inclusion of ILO-Pakistan mission on labour conditions in the surgical instruments sector and the expansion of the coffee quality training in Uganda. Additions of activities in digital marketing and social media in Samoa and Solomon Islands and food safety certification in Sri Lanka demonstrate the flexibility and adaptability in responding to the needs of beneficiary enterprises and changing international markets.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The UKTP Programme effectively demonstrates the value of providing tailored support to businesses in different sectors and countries. Recognising the unique needs and challenges of each sector and country is crucial for UKTP’s success. This is evident in the diverse range of activities implemented, from chocolate tasting training in Cameroon to hand-spinning techniques in Nepal. The programme effectively combines various interventions, including capacity building, market access facilitation, and addressing barriers to trade. This multi-faceted approach is essential for effectively supporting businesses in overcoming the various challenges they face in entering new markets. See recommendations in Section A.

Output Title	Market opportunities activated
Output number:		5	Output Score:	B
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of business contacts established (including for women business enterprises)	3015 (715 for women-led businesses)	2415 (902 for women-led businesses) / Partially met expectations
Number of new enterprises that have made business contacts as a result of UKTP support (including women business enterprises)	113 (40 for women-led businesses)	91 (72 for women-led businesses) / Partially met expectations
Number of market studies completed	0	2 / Met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

UKTP pursued an intensive schedule of trade events in the UK and mainland Europe across the spectrum of food products, beauty and fashion industries, creative industries, and medical equipment. UKTP also held major side events to the Rugby World Cup for businesses in the Pacific region to present their products to potential buyers from the UK and other major international markets. By March 2024, the cumulative results achieved since the start of the programme were 228 enterprises (88 women-led businesses) making such business contacts as a result of UKTP support.

During the year, UKTP delivered 221 opportunities for SMEs (83 being for women-led businesses) to participate in trade fairs, trade missions, exhibitions or inward buyer visits to their country by UK companies. Some firms participated in more than one opportunity during the year, so the total number of individual SMEs is lower, but represents a significant achievement, given the investment and expertise needed to support an SME’s successful participation in an international trade fair or event, especially for those businesses new to exporting to major international markets like the UK. In many instances, UKTP-supported SMEs were the only representatives of enterprises from developing countries, which minimised competition from similar source countries but also invite challenge about the suitability of trade fair selection and should be explored further in the next fiscal year. As already noted, the benefits of business contacts made in trade fairs and other events in FY23/24 will only be realised in FY24/25, as many events take place in the second part of the financial year, including the final months of the reporting year.

The participants said the international experience also enhanced their local market presence, by sharing their international venture on social media it generated excitement among local clients, encouraging them to view and purchase the new conscious collections.

The major international trade fairs where UKTP-supported SMEs participated in FY23/24 were:

Textile and clothing
- Paris Premiere Vision (July 2023) - four companies from Madagascar, the companies established 173 business contacts (among which 10 UK buyers). 51 of these established relationships are now in sampling stage.
- Pure London Trade Show (February 2024) - seven designers from Tanzania.
  - The most successful collection was from Imaqulet Designs with her upcycled trench coats and puffer jackets.
  - Chuwa received an order from a store in Australia and had four different orders from private clients
  - Mkwandule’son had two orders from private clients,.
  - Handmade from Tanzania sold to one store in Zimbabwe and another store in Ireland and received an inquiry from Liberty London to send fabric swatches to their head office.
  - The other designers are in conversations with both stores and private clients in different countries.
- Source Fashion London (July 2023) - 18 SMEs from Ethiopia, Tanzania and Madagascar, plus the Nepal Pashmina Industries Association. ITC organised three information sessions during the show. Two highlighted Madagascar and Ethiopia as new sourcing destinations. A third session focused on the UK Government’s Developing Country Trading Scheme (DCTS).
“Participating in the London and Paris Trade Shows proved invaluable, yielding quality networking opportunities and a substantial revenue boost. The events not only benefited our company's operations but also propelled strategic progression, enabling us to refine business strategies and adapt to market dynamics. Additionally, the increased demand for our offerings led to 100’s job creations and skill development among team members. Overall, the trade shows served as a catalyst for growth, solidifying our market presence and paving the way for future success. Thanks a lot Camila and ITC, you are essential to us and Madagascar development.”
-Narindra Robin, Founder, Anaka

Coffee
- World of Coffee Athens (June 2023) - five companies from Papua New Guinea, five from Laos. World of Coffee allowed PNG coffee companies to generate around US$575,000 and possibly as much as US$840,000 in new business transactions.
  - Molok Terry renewed his relationship with Matahari Global Trading, and was able to commit to supplying them 2 to 3 containers of certified organic coffee every year. Two containers would be worth around US$165,000, while three would be around $250,000.
  - Esther Vialeahy expects to complete her negotiations imminently with Vincent Ballot from France over the purchase of 50 to 70 bags of specialty A grade coffee - which would be worth between US$14,500 to US$20,000.

Food Products
- Speciality and Fine Food Fair London (September 2023) - three chocolate companies from Ghana, two from Jamaica, one from Senegal, one from Dominican Republic
- Salon du Chocolat Paris (October/November 2023) - four companies from Cameroon, two from Fiji, one from Papua New Guinea and one from Madagascar, with the Cameroonian and Pacific firms being first-time exhibitors in an international trade fair.
- Chocoa, Amsterdam (February 2024) 21 firms, including three from Ghana
- Food Ingredients Europe in Frankfurt (November 2023) - 12 firms from Cambodia, Senegal, Solomon Islands, Papua New Guinea and Fiji, bringing a diverse range of ingredients including ginger, cassava flour, hibiscus, gourmet pepper and dried mango. Ten firms were first-time exhibitors at an international fair.
- Fruit Logistica (February 2024) - three firms from Cote d’Ivoire
- International Food and Drink Event (IFE), London (March 2024) - 16 companies from Jamaica, Trinidad and Tobago, Madagascar, Cameroon, Senegal, Cambodia, Sri Lanka, PNG, Fiji, and the Solomon Islands

Beauty Care
- Olympia Beauty, London (October 2023) - eight firms from Fiji, PNG, Samoa and Senegal
- Professional Beauty London (March 2024) - four firms from Fiji, two from Samoa, one from PNG and one from Seychelles
- COSMOPROF, Bologna (March 2024) - 5 Pacific firms (2 from Fiji, 2 from Samoa, and 1 from PNG), all first-time exhibitors in an international trade fair

Gifts
Spring Fair, Birmingham (February 2024) - firms from Nigeria and Zimbabwe

Health
- Medica, Dusseldorf (November 2023) - 10 companies in Pakistan’s surgical instrument manufacturing industry
- CPHI Barcelona (October 2023) - one firm from Pakistan, the country’s only UK GMP certified compliant manufacturer

As well as these trade fairs, (i.e. large annual events for business to business buying), UKTP helped exporters increase their understanding of UK markets through consumer-facing fairs.
- BBC Good Food Show Winter, Birmingham (November 2023) - eight agri-food companies from Cameroon, Jamaica, Dominican Republic, Fiji and Papua New Guinea
- Manchester Coffee Festival (November 2023) - five companies from Laos

UKTP also helped exporters increase their understanding of UK markets and gain access to potential buyers through a range of structured visits.
- UKTP organised a UK coffee buyers’ origin tour to Uganda (January 2024)
- UKTP side events took place at Rugby World Cup matches, Bordeaux and Lille (September/October 2023) for five Fijian firms and four Samoan firms to meet potential buyers from the United Kingdom and EU
- Four UKTP supported producers were involved in a European buyers’ tour for clothing sector companies, in Africa Sourcing Week, Ethiopia (November 2023)
- A Nepalese delegation visited cashmere manufacturing plants in Yorkshire and Scotland (July 2023)
- Five Papua New Guinean coffee firms visited German importers (June 2023) and five Laotian coffee firms visited UK importers and roasters (November 2023)
- Three Ghanaian chocolate firms visited UK chocolate makers (February 2024)
- in cooperation with Pacific Trade Invest, UKTP organised a visit for eight Pacific beauty firms to Naturally Tiwa Skincare, a UK woman owned company (March 2024)

UKTP supported 16 beneficiary companies to submit applications for the Great Taste Awards (7 from Sri Lanka, 3 from Fiji, 2 from Papua New Guinea, 2 from Jamaica, 1 from Cameroon, 1 from Dominican Republic, and 1 from Solomon Islands). Great Taste recognition is a highly respected seal of approval which can drive significant business success (results announced in July 2024).

UKTP also supported six Pacific beauty companies (3 Fiji, 2 Samoa, 1 Papua New Guinea) to target UK and EU markets by listing on The Brand Book, an online platform that operates as a year-round digital trade show for the beauty industry, by connecting beauty, personal care and wellness brands from all over the world with a global retail and distributor network.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

UKTP actively facilitated enhanced market access and opportunities for SMEs to connect with potential buyers through various mechanisms the participation in major international trade fairs contributed and provided direct access to buyers and industry professionals. UKTP also explored the impact of inward UK buyer visits organising visits by UK companies to the countries of the participating SMEs and enabled direct engagement with potential clients.

In addition, UKTP proactively targeted side events to connect suppliers with wholesalers and distributors such as facilitating Pacific coffee producers to attend a major sporting event the Rugby World Cup the participation created unique opportunities to showcase products to a wider audience. At the same time UKTP organised visits to UK companies and markets that allowed SMEs to gain valuable insights into the UK market and build relationships with potential buyers.
UKTP supported initiatives to help SMEs gain an improved and deeper understanding of the UK market. For the first time UKTP supported beneficiaries to attend a consumer-facing fair, the BBC Good Food Show and Manchester Coffee Festival to connect with UK consumers and understand their preferences.
UKTP supported the use of digital platforms to connect SMEs with buyers. For example, supporting Pacific beauty companies to list on The Brand Book, an online platform connecting beauty brands with a global retail and distributor network. UKTP focused on an increased emphasis on Quality and Standards evidenced by the support for submissions to the Great Taste Awards and the focus on food safety certifications.

A significant number of business contacts were established, leading to new sales and export opportunities. SMEs successfully entered new markets, with some achieving significant sales at trade fairs and through direct-to-consumer channels.

SMEs gained a better understanding of the UK and EU markets, enabling them to adapt their products and strategies to better meet consumer demands. Enhanced Brand Visibility: Participation in trade fairs and market tours increased the visibility and brand awareness of participating SMEs.

These changes demonstrate UKTP's proactive approach in supporting SMEs to enhance their export capacity and effectiveness in the UK and EU markets in a sustainable way.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Notwithstanding strong individual examples of successes achieved by some of women owned/led companies that UKTP supported, it is notable that the reported results under-achieved on its overall targets for women owned/led businesses.

The 1-year target of 3,015 was set ambitiously high at the beginning of the fiscal year, due to the significant expansion of the programme into new geographies and sectors. In particular, targets were set ambitiously high in 3 countries: Pakistan, Uganda, and Cambodia (400, 400, and 300, respectively).

In Pakistan, the project supported just 10 companies in a novel sector to go to a single trade fair (MEDICA). The project assumed that numbers of contacts generated at fairs would be similar in the surgical instruments sector as for other UKTP sectors such as food or apparel. With the MEDICA trade fair being the largest industry event in the world, the target was set high. The reality was, however, that companies in these more sophisticated manufacturing sectors tended to make a lower number of higher-quality contacts. While the absolute number of contacts was just half of what was targeted, the majority of those contacts were legitimate business leads.

In both Uganda and Cambodia, company participation at the scheduled events ended up being much lower than expected. One major factor in this was difficulty in securing visas for participating companies. Particularly in the case of Uganda this had a major impact on fair participation in the UK, and it also impacted participants from Cambodia.

Across novel country projects multiple SMEs cancelled their participation at fairs at the last minute, or failed to embark on the scheduled travel. Any company that did not give due notice, or legitimate reason for failing to travel was subsequently dropped from the programme.

It is important to note, that actual results did increase in proportion to the expansion of the programme. Over the previous 4 years, the programme reported a total of ~5,000 contacts established. Split over 4 years, that works out to ~1,250 contacts established per year. The size of the programme roughly doubled in FY2023/24 (slightly less), representing a proportional increase in the number of contacts established to 2,400+.

The programme can be further enhanced to achieve even greater impact in supporting the growth and development of SMEs in accessing and navigating international markets. See recommendations in Section A.

## D: VALUE FOR MONEY

Key cost drivers and performance

UK provides technical assistance to increase the capabilities of firms, business support organisations and government policy makers. The main cost drivers relate to the supplier providing and contracting professional expertise delivered through a wide range of formats, including training, coaching, and mentoring, as well as participation in events such as trade fairs and market study visits. In FY24/25, support was delivered in-person as well as online.

Results in FY23/24 at outcome and impact level (trade, jobs) depend significantly on output level results achieved in previous years, with cumulative results increasing more quickly as the programme runs for longer. This has a positive effect on VfM over time.

VfM performance compared to the original VfM proposition in the business case

By focusing on strengthening BSOs and supporting systemic change within business ecosystems, UKTP aims to create lasting, sustainable benefits that extend beyond the program itself. This long-term impact can lead to increased economic growth, job creation, and improved livelihoods for businesses and communities. This approach can maximise the impact of the program by multiplying the reach and effectiveness of support provided to businesses.

By concentrating on sectors with high growth potential, such as the cosmetics industry and organic agriculture, UKTP can maximise the economic and social benefits of its interventions. The program provides tailored support to each country on specific needs and priorities identified through assessments and consultations. This ensures that resources are allocated effectively and that interventions are relevant and impactful.
UKTP uses data-driven approaches, such as benchmarking assessments and performance monitoring, to track progress and measure the impact of interventions. This allows for continuous improvement and ensures that resources are being used effectively to achieve desired outcomes.

The program has clearly defined objectives, such as enhancing business competitiveness, and increasing access to markets. These objectives provide a framework for evaluating the program's success and demonstrating value for money.
By addressing systemic challenges such as limited access to finance, inadequate infrastructure, and lack of market information, UKTP is creating an enabling environment for businesses to thrive. This can lead to significant economic and social benefits for the countries involved.

Output 1 - Firms and institutions are aware of how to use EPA preferences and potential benefits

In FY23/24, no UKTP activities took place related to Output 1: Firms and institutions are aware of how to use EPA preferences and potential benefits.

Output 2 - Business Environment more transparent and conducive for export to UK / EU markets

In FY23/24, no UKTP activities took place related to Output 2: Business Environment more transparent and conducive for exports to UK/EU markets.

Output 3 - Trade and support institutions and trade/ business support providers extend and improve their services to the focus sector for UK / EU Market entry

Economy
The total indicative spend for this output thus far is £0.9m, of which £73,800 was spent this year. 8% of the total spend thus far was spent this year and all the end-of-programme targets have been achieved.
Efficiency
As part of the budget cuts, this component was deprioritised and did not continue significantly in FY22/23, except for Comoros on national quality infrastructure.
Effectiveness
The Comoros weights and measures service (Office National de la Métrologie) received metrology equipment in June 2022 which supported the opening of the office after the government had committed the personnel and physical infrastructure.
Cost Effectiveness
The host Government commitment of personnel and physical infrastructure allowed the opening of the office.
Equity considerations
As part of the budget cuts, this component was deprioritised and did not continue significantly in FY22/23, except for Comoros in the context of the national quality infrastructure. It is not reported on whether participants to the workshops were from male or female led businesses.

Output 4 - Targeted firms have increased capacity to export to UK/EU market.

Economy
The total indicative spend for this output thus far is £5.3m, of which £595,600 was spent this year. 11% of the total spend thus far was spent this year. While the cumulative results exceeded the total targets, for one of the three indicators the target for women was not met, and for another the results for women was not reported.
Efficiency
The activities focused on delivering enterprise-level change this year by engaging through training and advisory services, particularly to enterprises actively participating in the market linkages activities under output 5. The team worked with beneficiaries to strengthen their export competitiveness, for example by improving the quality of packaging through coaching delivered to Ivorian companies.
Effectiveness
This output works towards improving the ability of firms and support institutions to export to UK/EU market across diverse sectors. UKTP supported firms in a diverse range of sectors during the year. This output works towards improving the ability of firms and support institutions to export to UK/EU market across diverse sectors. UKTP supported firms in a diverse range of sectors during the year. In specific countries, support to date to access to finance has facilitated about £3,450,000 of loan financing, mainly for smallholder producers.
Cost Effectiveness
UKTP facilitated coaching and training sessions to increase export competitiveness both in-person and remotely, however there is no cost data available to compare against.
Equity considerations
The end-of-programme targets for women business enterprises were exceeded. In FY22/23, 126 women business enterprises made changes to their business operations as a result of UKTP support with 338 women business enterprises accessing advisory support.

Output 5 – Market opportunities activated

Economy
The total indicative spend for this output thus far is £2.2m, of which £799,900 was spent this year. 36% of the total spend thus far was spent this year and two of the three end-of-programme targets have been achieved. For the third target, the cumulative target has been exceeded, but the target for women-owned/led SMEs has not been met.
Efficiency
The £799,900 spent this year enabled 1,619 business contacts to be established by 48 businesses. This was through UKTP taking beneficiary companies to a wide range of trade fairs (as reported in Section C, output 5).
Effectiveness
Spending on taking beneficiaries to food fairs is effective in helping establish businesses contacts. In this year 1,619 business contacts were established.
Cost Effectiveness
As an example, UKTP supported eight companies from eight countries participate in the Food & Drink Expo in Birmingham, which established 369 contacts for beneficiaries.
Equity considerations
UKTP achieved the end-of-programme target of 15 for number of enterprises that have made business contacts as a result of UKTP support, including the target for women business enterprises. However, UKTP has not met the target of 500 for number of business contacts established by women-owned/led SMEs.

Assessment of whether the programme continues to represent value for money

The programme continues to represent value for money and to align with UK priorities for trade for development. UKTP has been extended for FY24/25, with central funding at broadly the same level. Strong appetite from Posts and other Directorates within the FCDO has encouraged additional funding for buy-in services, expanding geographic and sectorial scope.

E: RISK

Overview of risk management

During the reporting period, the overall risk rating remained at moderate which is within FCDO’s risk appetite.

The risk management process and approach internally and externally with the delivery partner ITC ensures effective mitigation of risks that could otherwise prevent the UKTP Programme from achieving its objectives. This includes: -
- A quarterly review of the risk register, led by the PRO. High risks and those that are outside appetite are escalated to the SRO and the relevant Programme leads in FCDO country offices.
- Any risks deemed outside the risk appetite are then flagged to Deputy Director level.

Funding availability risk was elevated from Low to Medium. This elevated risk level comes from two key sources. The first concerns budget confirmation, and the programme’s ability to implement activities within a single Fiscal Year. If funding confirmation is consistently delayed it stalls project delivery and results in a sudden pause of the programme. This in turn impacts the ability of the programme to deliver consistent impact, build trust with stakeholders, and puts pressure on the programme to fit a year of delivery into a reduced number of months.

The 2nd factor is the fluctuating exchange rates between the British Pound and the US Dolar. Interest rates in the US have been at an elevated level compared to those in the UK and Europe. Recent developments and announcements from central banks suggest this trend will continue and even exacerbate as European rates stand poised to drop while USD rates are expected to stay high. This impacts exchange rates making the US Dollar more expensive, reducing the purchasing power of the GBP. In effect, each Pound of funding could potentially purchase less delivery. While the project does incur some costs directly in GBP for events in the UK, the majority of programme expenditure is conducted in USD, including staffing and international activities.

Related to Funding but impacting many areas including Long-term sustainability; stakeholder engagement; and personnel capacity, recruitment and retention, is UKTP’s short, 1-year funding cycle. While funding availability is solid each FY, without clarity on budgets beyond the 1-year horizon, it is difficult to plan future activities and reassure stakeholders. UKTP has also begun receiving feedback from several partners in multiple countries that the short 1-year cycle has a negative impact on the trust and reliability of the project year-over-year from local stakeholders. Without guarantee of funding beyond each fiscal year, some stakeholders are hesitant to commit their own time and efforts to a project that cannot guarantee its continuation beyond a number of months.

Furthermore, short timelines present a challenge to realizing sustainable change in each country, especially when the project has only just begun working in the country and multiple years of programme activities have not already been carried out. For these reasons the outlook for “Strategic Stakeholder Engagement” and “Long-Term sustainability” are rated at medium. The short funding cycle is also impacting UKTP’s own personnel. It is more challenging to recruit quality staff when contracts are uncertain beyond a 1-year cycle, and once onboarded, retaining staff can be a further challenge as opportunities arise for staff to work on projects with a longer-term guarantee. For these reasons, the risk for Personnel capacity, recruitment and retention has been maintained at Medium.

Beneficiary selection and engagement risk decreased from Low to Very Low as beneficiary selection proceeded across countries was finalized.

Partner financial management remained Low. UKTP in FY23-24 is currently only using a grant agreement in Pakistan with ILO. Inherent risk rating was raised to a Medium, because, like previous years, several low-value grants are planned for FY24/25, particularly in Nepal and Samoa (Pacific project). The residual risk rating was maintained at Low.

We also rate gender equality and women’s empowerment risk at Medium. In Pakistan, representation in leadership and middle management in the surgical instruments sector is male dominated, as well as throughout the workforce. UKTP will reinforce its gender equality plan in Pakistan for future programming. In the Pacific, although UKTP mostly works with women-led businesses, ITC will explore how to expand gender equality work at other levels of beneficiary company operations.

Reporting risk is also being actively managed. Reporting across 17 countries added to the complexity of tracking progress with beneficiaries. To avoid an increase in project execution risk, UKTP has added additional staff members to the core coordination team. UKTP onboarded a new programme management assistant, hereby returning to the original team structure prior to the ODA reprogramming. UKTP has also added a professional staff member to manage a surge in activities, particularly on non-ODA support.

To avoid an increase in project execution risk, UKTP is adding additional staff members to the core coordination team (see above).At a country level, some level of risk has presented itself in both Lao PDR and the Caribbean, although neither of these factors have elevated overall programme risk.

In the Caribbean there is a degree of political risk and strategic stakeholder engagement risk arising from the decision to selectively engage with specific Caribbean islands, rather than all islands. This decision was made intentionally, as delivering quality and meaningful impact across the entire region was not within the project’s scope or funding capabilities. Selection for FY 24/25 activities was made strategically, aiming to work in the countries where UKTP programming could have the greatest impact, and where existing companies and markets were the most prepared and primed to benefit from UKTP support. Nevertheless, regional competition and sensibilities make any selection potentially politically unpopular with un-selected countries. This, in turn, could result in friction with institutions, government, and civil society organizations from non-selected countries, or present challenges in the future if UKTP enters those geographies.

In Lao PDR, in previous years UKTP has been able to leverage a significant ITC presence in the country through a major EU-funded programme, including the maintenance of a country office. The loss of this base of operations will increase the cost of delivery, as well as pose further challenges including stakeholder engagement and beneficiary recruitment. From May 1, the project will have a strong National Coordinator based in-Country; however, one individual cannot replace the human and technical resources of a staffed field office.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Financial Management

Effective planning and delivery ensured reaching FCDO’s spend targets of £4.85m. In the first half of the fiscal year, plans were being put in place and new beneficiaries on-boarded in multiple countries. The core of expenditure and delivery occurred in the last two quarters of the fiscal year. Forecasts and invoices were received and processed on time.

	FY 2023-24 Progress Report / Forecast Expenditure % spent		Inception till current period June 2019 – March 2024 / Total Forecast Total Variance / Expenditure		Estimated Total Programme Budget	% / spent
US$ / GBP	6,134,641 6,223,077	101%	21,253,501 21,341,818	0.30%	21,253,501	100%
	4,847,000 4,918,929		16,603,447 16,653,595		16,603,447

This reporting period was again challenging for financial management. With challenges faced at a global level the programme spend levels also came under pressure. During the latter part of Q2 FCDO temporarily froze a portion of ODA budgets. The delivery risks were carefully managed, with results and activities prioritised effectively and ITC demonstrating flexibility in adapting and supporting activities. The FCDO programme team held regular meetings to keep ITC informed of developments and to manage expectations on release of funds. The Programme Management and Coordination project overspends during the first quarters were managed by the core team accounting for part of the costs of its direct country project work to the relevant country.

Programme management - Delivery

ITC and FCDO teams continued to work effectively together to deliver the programme, with regular programme management meetings to discuss progress against work plans and manage any necessary in-year adjustments. There were notable improvements to programme management overall following implementation of previous years’ recommendations, including on financial and risk management.

The previous Annual Review recommended that the UKTP team establish direct contact with UKTP beneficiaries to evaluate programme interventions and impact. The purpose of the visit was to meet beneficiaries and understand the impact of the programme activities by UKTP support in the country. The team met a range of trade officials and UKTP beneficiaries.

Representatives from the Ivorian government on several occasions noted that UKTP had already demonstrated tangible impact in the country in terms of SMEs’ international competitiveness, exports and job creation

The Ivorian Ministry of Commerce praised the multi-year collaboration so far with ITC through the programme and were keen to sustain results achieved. Interest was expressed in extending UKTP’s duration and deepening the partnership with the UK, and a reference was made to further digitalisation interventions, and to support Cote d’Ivoire’s potential in setting up a central packaging sector. These reflections provided insights and evidence of the successful running of the programme by ITC and achievements at the outcome and output levels.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The programme’s quarterly reporting process provided in-depth analysis of all activities undertaken during the period, how this maps to the programme’s key milestones, and also beneficiary feedback which has helped to shape future activities. The programme SRO and PRO also took the opportunity to meet with ITC to discuss overall workplans and milestones and assess progress when in Geneva for the SheTrades Hubs Annual General Meeting in November 2023. Regular engagement and check-in between ITC, the FCDO London team and relevants teams at Post had also ensured progress remained on track and outcomes delivered.
From March to October 2023, the ITC internal independent evaluation unit carried out a review of UKTP for the period from March 2019 to March 2023 (Microsoft Word - UKTP_Final Report_22.12.2023 (intracen.org)). Countries covered by UKTP in this period were Cameroon, Comoros, Côte d’Ivoire, Dominican Republic, Fiji, Ghana, Jamaica, Madagascar, Papua New Guinea, and Zimbabwe. This was before expansion to include DCTS countries that was implemented from April 2023 onwards.
The review included a desk study, field mission to Madagascar, and stakeholder consultations with different departments of ITC, FCDO and private sector beneficiaries. Data collection and analysis included two surveys – one specifically for the review, targeting Trade and Investment Support Institutions (TISIs), and one being the enterprise survey implemented as part of the UKTP programme to monitor progress on outcome and impact. Assessment criteria used were relevance, coherence, effectiveness, efficiency, impact and sustainability.
The review found that UKTP performed well. Stakeholders found the activities relevant and there was good coherence between UKTP activities and other ODA-funded programmes. The programme was effective, often over-achieving its milestones and targets, which raises the important issues of risk appetite and level of ambition. The programme was efficiently implemented, including communications products, such as YouTube clips. Impacts, in terms of trade volume/value showed some impressive quantitative headlines, although gains were not evenly distributed, with Ghana, Madagascar and Cameroon contributing most to the results. The review found that, for each dollar of aid for trade funding, “The overall programme is estimated to generate an average additional USD 5.7 in exports across all the countries. The highest returns were generated in West African countries.” At outcome level (jobs maintained or created) the biggest contributor to results was the ready-made garment sector support in Madagascar, with jobs going to women as well as men. The review found that “UKTP benefits are likely to be sustained over time” and that “the knowledge and techniques transferred through the program have elevated the professionalism and competitiveness of participating companies.”
Whilst the business case originally planned an independent evaluation component, this was cut due to budgetary constraints. The programme should seek other internal opportunities to commission deep impact and value for money evaluations, potentially combining these evaluations with other trade and investment programmes to ensure detailed learnings from the portfolio are captured.
Evidence and Learning

Following the expansion of the programme to DCTS countries, the logframe was updated for greater granularity of results. For country-level monitoring the logframes were “nested” i.e. the impact level results and indicators for each country correspond with the outcome level results and indicators for the overall programme. Since the major ODA spending cuts in 2022, only Outputs 4 and 5 have been in use – the ones focused on export promotion support directly to firms. But the original UKTP design remains valid i.e. outputs for policy change, support to business networks and support to firms.

Date of last narrative financial report	31/12/2023	Date of last audited annual statement	31/12/2023