## Annual Review Template

Title: Support to the Geneva Centre for Security Sector Governance
Programme Value £ (full life): 3,009,247.88		Review date: 11/03/2026
Programme Code: 300614	AMP start date: 01/10/2019	AMP end date: 31/12/2026

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025	2026
Overall Output Score	A	A	A	A	A	A	A
Overall programme risk rating	Minor	Minor	Minor	Minor	Minor	Minor	Minor

DevTracker Link to Business Case:	ISSAT Business Case and Summary
DevTracker Link to results framework:	ISSAT Logical Framework

## A. SUMMARY AND OVERVIEW

Description of programme

This project supports the Geneva Centre for Security Sector Governance (DCAF)[1] to improve security and justice outcomes globally, with a focus on Security Sector Governance and Reform (SSG/R), supporting capacity building of state, civil society and private sector stakeholders. The project funds DCAF to help the UK and other bilateral and multilateral organisations to deliver effective and politically informed SSG/R interventions, based on lessons from the field. DCAF provides training and in-country technical support, and helps set policy and best practice. The operating context for this work has changed considerably in recent years. DCAF’s focus - as the global leader in security sector governance – remains critical, underlining the importance of effective and accountable security institutions to address protracted conflict and growing instability, and associated challenges like irregular migration, terrorism, and hybrid threats. Support to DCAF is channelled through a pooled multi-donor fund, providing: support for individual donor priorities (often co-funded); support to multilateral institutions like the European Union, World Bank, and International Peace Support Training Centre (Kenya); and the development and sharing of thematic expertise and learning.
[1] Formerly known as the Center for the Democratic Control of Armed Forces, DCAF is a Swiss Foundation based in Geneva with a global country office network.

Major changes to the programme this year:
1. Previously this programme specifically supported the International Security Sector Advisory Team (ISSAT). The multi-donor Pooled Fund remains in place, but has been fully integrated into DCAF rather than operating as it did with ISSAT as a separate structure. This has enabled the Pooled Fund to draw more readily on the full array of DCAF’s central and country office activities, a step that the UK as a core group member has encouraged.
2. The business case was extended from 31 December 2025 to 31 December 2026 on a no-cost basis to retain access to DCAF’s unique capabilities, including in priority contexts, during a period of portfolio review. It was also extended to maintain the UK’s strategic influence over the direction of DCAF’s policy shaping and cutting-edge expertise on emerging global challenges.

Summary supporting narrative for the overall score in this review

This project has scored an A. DCAF continues to provide a unique source of internationally-recognised expertise, analysis and impact in SSG/R, playing a vital role in convening international partners, building multilateral capacity, engaging actors in the Global South and supporting evidence-based SSG/R interventions. The programme has balanced immediate field-level needs and longer-term policy influence and thematic learning. DCAF has continued to meet and improve on output expectations within the project, and as a result of its restructuring has delivered a 30% increase in the number of projects it has delivered in 2025, delivering greater efficiency in its operations. DCAF has ensured FCDO is better equipped to deliver effective, politically-informed and gender-sensitive security and justice interventions (outcome goal), and is helping ensure donor interventions lead to improved stability (impact goal).

The programme’s overall risk level continues to be minor and demonstrates value for money due to the cost-sharing nature of the programme and recent efficiencies gained through restructure. Further details on value for money are explained in section D of this report.

Major lessons and recommendations for the year ahead

Early joint DCAF-FCDO review of the overall project, its performance, and ways of working, with a view to developing a more strategic partnership approach to reflect a rapidly evolving operating context.

The FCDO has maintained a longstanding partnership with DCAF. As this project is expected to end in December 2026 there is now an opportunity to reflect on several years on investment, including what has worked well (both in terms of our partnership as well as in security sector governance and management), and what shifts in approach might help inform the UK’s new modernised approach to development; including building partnerships, moving from donor to investor, innovation, and international system reform.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Figure 1

The programme’s theory of change as illustrated above sets out that the FCDO will work with DCAF to contribute specialist staffing and programme funding (inputs). In return, FCDO receives advisory support to Security & Justice programming in a range of country contexts; benefitting from improved knowledge, professional development, and improved coordination; and consensus between donors and multilaterals (outputs). The FCDO is correspondingly better equipped to deliver more effective, politically informed and gender-sensitive security and justice interventions (outcomes).

The theory of change remains valid, and no changes are required. We plan to review the theory of change for the partnership with DCAF, in conjunction with other members of the pooled fund, in preparation for the phase to follow the end of this project cycle (December 2026).

DCAF has been responsive to UK priorities, fostering collaboration, lesson learning and good practice across the international SSG/R community, and continues to perform in line with the objectives of the programme and theory of change. DCAF also continues to:
1. emphasise improved security and justice outcomes for people as the ultimate objective of SSG/R, particularly in conflict-affected and fragile states; and
2. commit to gathering evidence to help assess the contribution it makes to delivering SSG/R interventions.

DCAF has continued to balance the range of demands across the pooled fund and to develop its approach to measuring impact.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Outcome 1- FCDO is better equipped to deliver effective, politically-informed and gender-sensitive security and justice interventions
Outcome indicator 1.1 - % of recommendations to GBMs that are partially or fully accepted in mandate reports, accompanied by a narrative on how the mandates have influenced bilateral and multilateral GBM decision-making around interventions.

DCAF is assessed as being on track to achieve the outcome of the FCDO being better equipped to deliver effective security and justice interventions. Feedback has indicated that DCAF’s work and recommendations are relevant and contribute to effective interventions and policy making, while DCAF’s expanded training offer to the FCDO has delivered more advanced courses to improve HMG security and justice work. DCAF projects contributed to supporting FCDO priorities on issues including international system reform (for example through a World Bank SSG session), emphasis on conflict prevention (for example through a training session on SSG and conflict prevention) and Euro-Atlantic security (through advisory reports).

In 2025, 90% of the recommendations formulated for Governing Board Members (GBMs) through mandate reports were either fully or partially accepted, demonstrating the strong policy relevance and operational value of the analysis and advisory support provided through the Pooled Fund. Recommendations developed through DCAF engagements have drawn on field-level experience, comparative analysis and consultations with national and international partners.

Throughout the reporting period, mandate reports informed bilateral and multilateral decision-making across several thematic areas, including human resources management reform, integrity and anti-corruption measures within security institutions, and regional cooperation on internal security governance. In a number of cases, recommendations emerging from Pooled Fund engagements helped shape the design or adjustment of donor-supported interventions, particularly in fragile and reforming contexts.

For example, support from DCAF has helped the FCDO to shape the approaches taken by key institutions like the World Bank and NATO. This support is often long term and iterative, but is helping to broaden the network of influential global actors who recognise the importance of well governed security institutions to their work, as well as for peace, stability, and prosperity. This is amplifying collective impact with a modest injection of resources and the targeted use of their expertise.

In addition, recommendations generated through the Pooled Fund’s work on human resources management reform informed discussions among donor partners on how to strengthen institutional oversight and performance management in partner-country security institutions. Similarly, regional exchanges facilitated through Pooled Fund mandates contributed to the identification of practical reform entry points aligned with NATO/Euro-Atlantic standards, enabling participating governments and partners to refine their engagement strategies.

In the year ahead, DCAF plans to continue its SSG/R training provided to core members and other IPG staff, helping to fulfil output 2 on the original business case (knowledge and professional development for members). Another key focus will be its continued high-level engagement to shape the work of multilateral institutions including the World Bank and the Organisation for Economic Co-operation and Development. DCAF plans to continue supporting states undergoing complex transitions, particularly in Africa, where it will prioritise community security dialogues, civic engagement and the strengthening of oversight and governance frameworks. It will also continue to focus on the prevention of violent extremism, and continue to provide tailored interventions on FCDO priorities in Ukraine, the Western Balkans, and the Middle East. It will further develop interventions on migration governance and tackling organised crime.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Promoting effective and accountable security provision, within a framework of (democratic) civilian control, rule of law and respect for human rights, remains directly relevant to FCDO goals to prevent conflict, reduce humanitarian need, increase resilience, and tackle instability, fragility and emerging threats (as set out in relevant Business Plans). FCDO support to DCAF’s multi-donor funding programme remains a cost-effective way to deliver greatest impact in our security work globally; giving us the capabilities we need, joining up international partners, supporting in-country impact, and shaping the approach of international bodies so they also push for accountable security and justice organisations with their additional reach and resources. At a time of increasing complexity in security and justice engagement and geopolitical contestation, continued investment would ensure that UK-funded SSG/R interventions remain politically informed, gender-responsive, and effective.

## C. DETAILED OUTPUT SCORING

Output Title	Advisory Field Support (AFS) for Members' missions
Output number:		1.1	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Level of performance - percentage of Members report that ISSAT's contribution met or exceeded their expectations	80%	90% (based on mandate feedback forms and an annual survey of Members).

Briefly describe the output’s activities and provide supporting narrative for the score.

In 2025, 90% of Members reported that the Pooled Fund contributions met or exceeded their expectations, reflecting the continued relevance, responsiveness, and technical quality of the support provided through the Pooled Fund[2]. This level of satisfaction highlights the value placed by Members on DCAF’s ability to deliver timely advisory services, facilitate policy dialogue, and generate evidence-based analysis that directly supports decision-making around Security Sector Governance and Reform (SSG/R).
[2] Output indicator 1.1 reflects the previous ISSAT structure which was valid prior to the DCAF restructuring in April 2025. As such, reporting on this indicator draws from data provided by mandates that have delivered in-country advisory services.

Throughout the reporting period, Pooled Fund engagements were largely demand-driven and responded to operational needs and evolving policy priorities. Core Group Members drew on DCAF’s field advisory support and technical expertise, allowing them to design or refine bilateral and multilateral interventions in complex political and institutional environments.

DCAF’s work in human resources management reform, integrity and anti-corruption in security institutions, and regional dialogue on internal security governance provided Members with practical entry points for engagement in priority partner countries. Improving the human resource management of security institutions is fundamental to their effectiveness; ensuring they enjoy the trust and confidence of citizens, and can be both effective in protecting them and exercising their powers over the use of force proportionately and in the public interest.

The high satisfaction rate may also reflect that DCAF’s restructuring has enabled the mandates to draw more systematically on DCAF’s broader institutional expertise and in-country presence.

Output Title	Knowledge and professional development for member staff
Output number:		1.2	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.2.1 Percentage of training participants who report that ISSAT's training met their expectations ("agree" / "strongly agree")	80%	99% (based on end of course questionnaires)
1.2.2 Percentage of participants (out of responses obtained) who report the ISSAT training contributed to their work performance, as a result of ISSAT training (longer-term).	70%	90% (based on DCAF reporting, member feedback forms, and DCAF annual training impact survey).

DCAF has delivered a structured programme of Security Sector Governance and Reform (SSG/R) training in support of UK government priorities, combining online and in-person courses. In 2025, 78 participants were trained through four courses, primarily from UK government departments, alongside international organisations and partner institutions engaged in SSG/R policy and practice. Participants consistently reported high relevance and direct applicability of the training, including the use of SSG/R analytical tools in policy and programme work, strengthened cross-departmental coordination, and improved integration of gender perspectives into programme design and delivery. DCAF provides a range of training support to core group members and other missions.

2024 served as a foundation year for the training, in which two entry level (Level 1) courses were delivered. In 2025 DCAF focused on increased participation, delivery through more diverse formats, the piloting of a Level 2 advanced course, a thematic focus on conflict prevention, and broader geographical reach. Evidence from feedback and impact data indicates that 2025 training strengthened individual and institutional capacity for FCDO delivery on SSG/R policies and programmes (contributing to this project’s outcome goal). Participants found that the training was highly relevant, supported their learning, and was translated into action.

Key learning outcomes identified from the two courses included:
- Improved understanding of SSG/R principles, political dynamics, and reform processes.
- Learning across all course objectives, particularly in applying SSG/R across contexts and planning for long-term impact.
- Consistent participant course satisfaction (average session ratings of 4.5/5).

Impact data and participant feedback indicate that learning translated into behavioural change and professional development:
- Participants were applying SSG/R tools in policy, programme design, and training contexts.
- Training strengthened professional and cross-departmental networks across UK institutions.
- Participants reported improved integration of gender and prevention into their work.

On the pilot Level 2 in-person training, there was a 49% improvement in learning objective 5 (enhanced practical skills in planning for long-term impact). At the conflict prevention workshop, a 43% improvement was observed in learning objective 4 (practical entry points to operationalise SSG/R in prevention programming). At the Level 1 online training across November-December 2025, a 58% increase was noted in learning objective 4 (capacity to engage on SSG/R though applying analysis, knowledge, processes and tools provided by the course).

Overall, the trainings strengthened individual and institutional capacity to design, assess, and adapt UK-supported SSG/R interventions, supporting more politically informed, prevention-oriented, and context-sensitive engagement. The FCDO found DCAF to be responsive and engaged in meeting customer needs, making good use of technology and mixed training formats. The FCDO will work with DCAF to ensure their training continues to focus on in-country application of best practice.

Output Indicator 1.2.1: Percentage of training participants who report that ISSAT's training met their expectations.

The 11 training courses delivered in 2025 reflected a mix of in-person, online and e-learning courses. Out of eight where such evaluations were undertaken, 7 had 100% of participants agreeing that the training met expectations, with 1 reporting 94% satisfaction, giving an overall average of 99%. Those reporting 100% satisfaction included the Level 1 SSG/R training in March 2025 delivered primarily to UK Government staff, the UK-funded Level 2 SSG/R training, and a prevention-focussed SSG/R training also delivered primarily to UK Government staff. In the same surveys, an average of 50% of respondents gave the highest rating in overall course satisfaction. Notable figures include the UK Level 1 training (60%), the UK Level 2 in-person training (69%) and the UK prevention-focussed SSG/R training (60%).

Output Indicator 1.2.2: Percentage of participants (out of responses obtained) who report the ISSAT training contributed to their work performance because of ISSAT training (longer-term)

DCAF commissioned further surveys 3-6 months after course completion to measure how the training had contributed to participants’ work. Some training was conducted near the end of 2025; data collected for review here is therefore for four courses. On average, 88% of respondents agreed the training contributed to their work longer-term, with 44% giving the highest rating. For example, 95% of respondents agreed that the introduction to SSG/R e-learning course had contributed to their work in the long term, with 61% giving it the highest rating. The comparable figures for the SSG/R online training in March were 100% (agree) and 50% (highest rating).

Output Title	Improved co-ordination and consensus between donors, and with multilaterals
Output number:		1.3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.3 % of ISSAT mandates that bring together multiple bilateral and multilateral Governing Board Members.[3]	50%	57% (based on DCAF financial and narrative reporting; ToRs; member feedback forms; annual survey; feedback from Governing Board Meetings).
[3] Since revised to ‘International Partner Group Members’ (IPGMs).

A total of 31 mandates were undertaken in 2025 through the Pooled Fund, of which 19 (57%) brought together funding from multiple governing board members.

In 2025 DCAF continued to champion collaborative working across Board Members through its mandates as well as providing support to shape the approach of multilateral institutions to enhance their contribution to good governance in the security sector. DCAF has continued to host a community of practice: a secure, online platform connecting all IPGM representatives to one space dedicated to learning, knowledge generation and experience sharing.

DCAF has supported and shaped the work of a number of important multilateral institutions in 2025. It assisted the Development Assistance Committee (DAC) of the Organisation for Economic Co-Operation and Development in its refresh of its Handbook for Security Sector Governance and Reform (SSG/R), sharing evidence and learning to shape the debate on the future of SSG/R in a rapidly evolving global context. DCAF has also provided targeted, effective and collaborative high-level policy support to the World Bank as it refreshed its Strategy for Fragility, Conflict and Violence, bringing together the Bank, UN, and Core Group Members. More work is planned to facilitate strategy implementation, and the initiative has demonstrated wider potential to shape the work of international financial institutions.

Overall, bringing multiple Governing Board Members together for mandates encourages greater cohesion and integrated approaches between partners, as well as burden sharing on cost.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation	Narrative	Progress
Implement process to better monitor how reports and findings produced from ISSAT [now fully merged into DCAF] are being made useful for practitioners	ISSAT [DCAF] has continued to strengthen its efforts to improve dissemination and uptake of evidence through training, dialogue with partners, requesting feedback, convening discussions. This needs to continue, and FCDO should continue to support this through regular engagement with ISSAT [DCAF] and by: FCDO gathering and sharing feedback with ISSAT [DCAF] to evaluate the usefulness of the reports and findings. / Both ISSAT [DCAF] and FCDO should continue to engage practitioners from early concept stages. / ISSAT [DCAF] should ensure that clear executive summaries and recommendations are being brought forward into concept note stage so practitioners have a clearer overview of the contents of the report and can decide how the report will be useful to them and their teams. FCDO should ensure key points and recommendations are made clear when disseminating ISSAT [DCAF] products. / Both FCDO and ISSAT [DCAF] should take account of emerging lessons from the OECD DAC SSR handbook refresh process.	Project concept notes are disseminated to practitioners by DCAF and FCDO to ensure early engagement and shaping to priorities and needs on the ground. This has helped to shape the portfolio of DCAF’s work in 2025. The FCDO and DCAF will continue to strengthen the feedback loop, including within the FCDO. / DCAF reports contain clear executive summaries, and key points are made clear when disseminating DCAF products. / Any specific lessons from the refresh of the OECD DAC Handbook on SSG/R will be captured and reflected by FCDO and DCAF.

## D: VALUE FOR MONEY

 Key cost drivers and performance

The key costs associated with the pooled fund are salaries and associated costs (e.g. travel, accommodation and subsistence) for DCAF’s staff and advisers. Rates are aligned with DCAF’s general financial procedures. Whilst under ISSAT, daily fixed spot rates were used for Senior Staff and SSR Advisers, accounting for the rapid deployment unique to that structure. As of January 2026, DCAF has transitioned to using actual daily rates, not only to align with wider DCAF policy and simplify administrative and budgetary management, but also to ensure that financial reporting accurately reflects operational realities.

VfM performance compared to the original VfM proposition in the business case

Economy:
DCAF continues to drive value for money by pooling donor funding through its Pooled Trust Fund, which has enabled economies of scale. Following DCAF’s restructuring and the integration of ISSAT across DCAF’s operational entities, the organisation’s absorption capacity has increased significantly. In practical terms, DCAF’s broader institutional structure has demonstrated an implementation capacity at least 30% higher than the previous model (which was based on a single dedicated unit), enabling a larger number of engagements to be delivered efficiently and within the same financial framework. Pooling DCAF activity between members has helped keep FCDO costs down on priority interventions at a time of reducing ODA.

Efficiency:
The support that DCAF provides to multilateral organisations on a cost-sharing basis has boosted the impact of UK funding and avoided duplication of effort. DCAF’s restructuring efforts have also helped it implement an increase in the delivery of Pooled Fund mandates.

Effectiveness:
DCAF has continued to deliver against project objectives and milestones set and reviewed under the results framework.

Equity:
DCAF has continued to focus in particular on the linkages between gender and security, including in its bilateral and multilateral support, policy engagement, capacity building, and work on the Women, Peace and Security (WPS) agenda. One of the four strategic objectives in DCAF’s 2025-2030 Strategy is to use SSG to work with security sector actors to promote gender equality and address discrimination and injustice. In 2025 the Pooled Fund allocated more than one-third of its contributions to advancing the WPS agenda. FCDO will work with DCAF to identify where best to focus our support on equity.

Overall cost-effectiveness:
The project provides a relatively low-cost source of a range of services which harness the world’s leading body on Security Sector Governance and Reform: from bespoke training for HMG; bilateral support; policy engagement and shaping of multilateral institutions; through to convening of international partners.

Assessment of whether the programme continues to represent value for money
The pooled funding structure is an advantage over single investments, and the involvement of likeminded partners improves donor coordination. This is particularly crucial in priority contexts for the UK. Furthermore, DCAF provides a unique source of expertise on SSG/R that is internationally recognised. It can also reach countries where the UK has less access, such as Francophone African countries. DCAF’s access to these contexts can assist with tackling instability upstream, a far better value for money proposition that responding to conflict and crisis. DCAF’s restructuring has also enabled a considerable growth in the number of mandates it is able to implement, a considerable boon for efficiency.
DCAF and the FCDO should continue to ensure their work is targeted and coordinated across donors, aligned to strategic priorities, and delivers real-world impact that we can measure.

E: RISK

Overview of risk management

There has not been a significant change in the programme-level risk, and we continue to rate the overall net risk as minor.

Whilst under ISSAT, a comprehensive risk register was created, which is updated as required. The risk register remains in line with Humanitarian Directorate’s risk appetite. Risk appetites have also been refreshed in early 2026.

A Due Diligence Assessment was published in July 2024, which covered the breadth of DCAF’s work. The findings showed that overall, sufficient controls were present and we were satisfied with the policies it had in place.

In addition to project level risk management, DCAF’s risk policy outlines DCAF’s general risk management approach, defining the structures and accountabilities DCAF maintains to manage risk throughout the organisation.

On safeguarding, the net risk was previously rated as moderate but has now been downgraded to minor. A comprehensive safeguarding policy was shared in 2024, including an updated approach to harassment and the creation of a safeguarding committee.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

DCAF will share an annual financial statement in the next pooled funders’ report, due in March 2026, and the audited financial and narrative report will be available to all donors in June 2026. Throughout the year, DCAF share reporting to evidence delivery and the contribution being made by UK funding, as well as financial reporting. The FCDO contributes to the Pooled Fund on an annual basis to support flexible management and delivery of the Fund as a whole and payments continue to be made on a timely basis.

Financial and narrative reporting is complicated by the range of approaches from donors to the Pooled Fund, and this can make some aspects of project oversight challenging for both parties. We will continue to work with DCAF to ensure project management is as seamless as possible, and further develop our joint approach to risk management.

DCAF’s workplan is aligned to its 2025-2030 strategy, further embedding the ‘one DCAF’ approach. A central priority is ensuring that all mandates place partnerships and donor coordination at the core, reflecting synergies with the UK’s wider approach to development. The ability to respond quickly to emerging security challenges and crises has been maintained, whilst not losing sight of strategic coherence. The FCDO and DCAF will continue to work on ensuring we deliver the greatest long-term impact from the range of DCAF’s activities.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
In addition to the monitoring of evidence generated under the results framework for this project, monitoring activities throughout the reporting period have included:
- UK participation in International Partners Group and Core Group meetings
- Direct engagement between Humanitarian Directorate and DCAF to set and review our strategic priorities and guide DCAF’s work.
- Active programme delivery monitoring and engagement with country and thematic teams to align priorities to DCAF project activity.
- Quarterly regularised risk/programme management meetings, both in-person and online.

FCDO and DCAF will continue to improve feedback mechanisms throughout the programme cycle.

Evidence
In addition to regular updates providing evidence against delivery, outside the period of this review DCAF will also prepare an annual narrative report which will provide comprehensive evidence concerning performance last year.

Learning
The risk matrix/management has been a key process for capturing and sharing lessons directly with DCAF. This has been supplemented by the Living Overview document, ensuring that topics have become broader and align with the FCDO’s objectives. These processes have resulted in active engagement and responsiveness, though there is more that the FCDO can do in priority contexts to link our organisations’ work effectively.

Furthermore, the ‘One DCAF’ approach is fully embedded, with ISSAT no longer acting as a semi-autonomous entity. The 2026 Programme of Work is aligned with DCAF’s 2025-30 strategy. By harmonising the Pooled Fund’s model with DCAF’s broader strategic objectives, a more holistic and impactful delivery for stakeholders is expected.

Date of last narrative financial report	12/06/2025	Date of last audited annual statement	12/06/2025