ADDENDUM TO BUSINESS CASE

INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Support to the International Security Sector Advisory Team (ISSAT)
Country or region targeted	United Kingdom
Type of cost extension (if applicable)	Cost extension
Original project budget	£2.6 million
Original project start and end dates	01/10/2019-31/12/2024
Cost extension value (if applicable)	£232,200
New reduced budget (if applicable)	-
New project end date (if applicable)	31/12/25
Business Case Quest Document No.	FINAL BUSINESS CASE 51871720 (1).odt (sharepoint.com)

INFORMATION
What is the project’s purpose?
To deliver effective security and justice interventions, through the International Security Sector Advisory Team (ISSAT), by providing guidance and targeted training to help bilateral donors and multilateral organisations deliver effective, evidence-based and politically informed security and justice responses, based on lessons from the field. / The project’s desired impact is that: / FCDO will deliver better security and justice interventions, in key conflicts/stabilisation efforts, leading to greater international stability. / Co-ordination between donors, and their engagement with multilateral organisations, will improve, leading to better interventions on the security and justice sector. / FCDO and its HMG partners will benefit from SSR training, leading to improved interventions. / The project outcomes are: / The FCDO will be better equipped, through guidance, coordination and training, to deliver effective, politically informed and gender-sensitive security and justice interventions, in key conflicts/stabilisation efforts. / Project outputs include: / Advisory field support for members missions. / Knowledge and professional development for members. / Improved co-ordination and consensus between donors and multilaterals.
What is the objective of the cost extension or other changes?
The ISSAT programme currently provides guidance, tools, technical support, and co-ordination for international donors and multilateral organisations working on security and justice issues. The programme exists to provide quick analysis on key international events, including international emergencies. / The objective of the cost extension is to continue this high performing programme (it’s last AR scored A) with a key delivery partner, without a gap, allowing time it to be incorporated into a new successor programme starting January 2026. / The extension will continue to support Security Sector Reform and Governance through 3 ISSAT pillars. 1) UK priority projects delivering against specific UK priorities, such as Ukraine and Moldova 2) work with multilateral organisations and 3) work on knowledge development, including SSR training (1 virtual and 1 in person). ISSAT will support better UK and international expertise in preventing and reducing conflict through effective security sector governance, with the aim of piloting new approaches in an evolving global context, assessing their impact, informing design of the new successor programme. / The current programme ends in December 2024 and the successor programme, due to start January 2026, is currently under design. We are seeking a 1-year extension of £232,200, in addition to the existing budget of £2.6m, totalling £2,832,200. This extension offers VfM by using ISSAT as a multiplier for UK’s multilateral engagement.
What is the additional and total support the UK will provide?
To date, we have spent we have spent £2,322,320 out of the initial £2,600,000 budget of the business case, leaving £277,680 unspent. With underspend and a costed extension of £200,000, this will take the overall BC to £2.8m. / Business Case Allocations Actuals / FY19/20 600,000 218,660 / FY20/21 500,000 502,207 / FY21/22 400,000 658,970 / FY22/23 400,000 302,482 / FY23/24 400,000 400,000 / FY24/25 300,000 240,000 / TOTALS 2,600,000 2,322,320 / PROPOSED / FY24/25 250,000 / FY25/26 260,000 / TOTALS 2,832, 320 / Below is a budget breakdown for programme activities under the extension across FY 2024/25 and FY 25/26: / Activity Allocated budget FY24/25 Allocated budget FY25/26 / UK priority projects £0 £150,000 / Support to multilateral organisations £150,000 £0 / Knowledge Development, incl training and overhead costs £100,000 £110,000
What are the expected results?
The expected results remain consistent with the original business case: / Advice provided to support and guide SSR policy and programmes in several key countries and international partners. For example, engaging and supporting impact with practitioners from the ISSAT delivered assessment of international support to Security Sector Governance and Reform in Ukraine. / Advisory support providedto multilateral partners to support their SSR agendas and inform their best practice, consistent with evolving global context – for example to UN peacekeeping missions. / Security Sector Reform training and development to HMG and other officials from partner countries and organisations working on SSR. / Amplification of lessons learned and provision of bespoke training and a programme scoping, design, monitoring and evaluation capability which will be available to all HMG actors. This will include 2 virtual and 1 in-person training course. / Provision of guidance and useful insight into other donors’ workstreams, policies, and positions on issues of interest OGDs – including new global south actors. / Help-desk facility’ responding to information requests. / These results are reflected in the log frame.
What is the approach to implementation?
Risk management / The programme risk rating will remain at Minor under this extension and risks will continue to be managed within the SSD risk appetite and monitored on a quarterly basis. / Current risks include challenges in operationalising policy, strategic risks owing to uncertainties in future nature and scope of conflicts and shifts in HMG country priorities, which could mean ISSAT’s priorities no longer match ours, although we consider this unlikely. / Quarterly discussions on risk will continue to feed into an overall programme risk matrix stored on AMP and will guide how we continue to deliver future activities. These will continue to be reviewed with mitigation measures adjusted as required and follow the SSD and OCSM risk escalation process if risks evolve outside of our appetite. / Programme management / Programme activities continue to be implemented primarily through the mandates that are drawn up each financial year. We meet with ISSAT on a quarterly basis to discuss the progress of the mandates which include both joint and single proposals. This means that the activity is managed in house with both programme managers (FCDO and ISSAT) working closely together alongside technical advisors. The activities undertaken with ISSAT are delivered under an MOU agreement. / Gender equality / No changes have been made to the programme’s impact on gender equality and this extension will remain compliant with FCDO’s obligations towards gender equality. / Safeguarding / Safeguarding risks for this programme are assessed as minor, owing to the standalone safeguarding policy that is place by the implementing partner.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The main purpose of this cost extension is to continue activities until a successor programme is in place, there is no change to the business case and its theory of change.