ADDENDUM TO BUSINESS CASE FOR NO-COST EXTENSION

SUMMARY INFORMATION
Project Name	Support to the Geneva Centre for Security Sector Governance (DCAF)
Country or region targeted	United Kingdom
Type of extension (if applicable)	No-Cost time extension
Original project budget	£3,039,248
Original project start and end dates	01/09/2019 - 31/12/2025 (The BC was previously extended to 31/08/2024 and then to 31/12/2025)
No-cost extension value (if applicable)	£250,000
New reduced budget (if applicable)	nil
New project end date (if applicable)	31 December 2026
Business Case Quest Document No.	FINAL BUSINESS CASE 51871720 (1).odt (sharepoint.com)

INFORMATION
What is the project’s purpose?
DCAF provides research, analysis, guidance, technical advice, training and coordination to the UK and other Governments – and wider international community (including key multilaterals and Global South partners) to improve the effectiveness of security and justice interventions and build accountable and capable security sectors able to provide security for their citizens and counter security threats. Co-funded by several likeminded donors, including Germany and Switzerland, it provides a critical platform to cohere donor engagement, policy lessons and multilateral capacity-building efforts. / The project’s desired impact is that: / FCDO and its partners or multilateral institutions will have better security governance/management (SSG/M) interventions which will lead to greater security. / To improve the co-ordination and technical support between donors and their engagement with multilateral organisations in the security and justice sector. / The project outcomes are: / The FCDO and its partners and multilateral institutions will be better equipped to deliver effective, politically informed and gender-sensitive security and justice interventions to prevent or respond to conflict. / Project outputs include: / Advisory field support FCCO, international partners and multilaterals / Knowledge and professional development for members / Improved co-ordination and consensus between donors and multilaterals
What is the objective of the no-cost extension or other changes?
DCAF remains our primary implementing partner on Security Sector Governance/Management (SSG/M) – a critical and strategic capability in today’s contested geopolitical environment. Through its work, DCAF strengthens legitimate, accountable, and resilient security sectors, helping to prevent and reduce conflict, counter hybrid threats, and tackle serious organised crime. Its programmes amplify UK impact by leveraging cutting-edge expertise and fostering collective capability and burden-sharing, including with partners in the Global South. / Failing to extend this programme would leave the FCDO (and wider HMG) without access to DCAF’s unique capabilities, at a time when the future portfolio is still under design. This would weaken FCDO’s ability to maximise ongoing DCAF efforts that deliver guidance, tools, technical support, and donor coordination on Security and Justice – including in Ukraine and the Eastern Neighbourhood. We would also lose a cost-effective, high-quality training and capacity-building offer for HMG and partner officials on SSG/M. / In addition to funding DCAF, we play a strategic role in shaping programming and mandates through our seat on DCAF’s Core Group and International Partner Group, where the UK is an influential voice. Non-extension would mean losing this influence, reducing our ability to steer priorities and access cutting-edge external expertise on emerging areas such as AI, new technologies, and hybridity. It would also impact DCAF’s global work, where UK thought leadership is a recognised asset. / The proposed no-cost extension is within the remit of the business case and the total spend does not exceed or change the total allocation. / The extension would have three main outputs: / specific SSG/M projects to deliver on conflict priorities – these are still being scoped but are likely to include advice/capability and donor coordination on Ukraine, Syria and possibly West Africa or Moldova. We expect these will contribute to implementing the UK-Germany Kensington Treaty conflict partnership under which we are exploring join funding with DCAF on shared priorities which are likely to include Ukraine and possibly Syria. This might include support to NATO capability building. / building SSG/M capability, influence and knowledge with international partners, including global south partners and multilateral organisations – this includes support to the UN, OSCE and African Union SSR units. Looking ahead this could include support to UN Peacebuilding institutions as they implement UN80 reform proposals on SSG. We also expect to work with DCAF to support the OECD-INCAF initiative to reboot its SSG approach including through our hosting of DCAF’s International Partner Group meeting in March 2026 / building HMG SSG/M capability, through delivering virtual and in person training sessions, which may include offers to international partners. This may allow us to pilot new elements to these partnerships as we transition to a new portfolio around a centre of expertise and in a context where we expect a greater focus on national security issues, risks & threats, including in an overall context of reduced spend.
What is the additional and total support the UK will provide?
As this is a no-cost extension, the total support that the UK provides will remain the same, We will now have added time to fulfil our anticipated deliverables as indicated above. / To date, we have spent £2,782,320 out of the total £3,039,248 budget of the business case, leaving £282,319 unspent. With a no-cost extension of £250,000, this will take the overall BC to £3.03m. / Business Case-Component 2 Business Case (Core funding) - Component 1 Component 2 actuals Component 1 actuals / FY19/20 100,000 500,000 18,660 200,000 / FY20/21 100,000 400,000 102,207 400,000 / FY21/22 100,000 600,000 58,970 600,000 / FY22/23 100,000 300,000 2,482 300,000 / FY23/24 100,000 300,000 100,000 300,000 / FY24/25 300,000 200,000 / FY25/26 500,000 / FY26/27 250,000 / TOTAL 500,000 2,650,000 282,320 2,500,000
What are the expected results?
The expected results remain the same as that in the original business case: / Advice provided to support and guide SSR policy and programmes in a number of key countries. / Advisory support provided, where necessary, to key multilateral partners to support their developing SSR agendas and inform their best practice. / Security Sector Reform training and development to HMG and other bilateral/multilateral officials working on SSR. / Amplification of lessons learned and provision of bespoke training and a programme scoping, design, monitoring and evaluation capability which will be available to all HMG actors. / Provision of guidance and useful insight into other donors’ workstreams, policies, and positions on issues of interest OGDs. / Help-desk facility’ responding to minor information requests. / These results are reflected in the log frame.
What is the approach to implementation?
Risk management / The programme risk rating will remain at Minor under this extension and risks will continue to be managed within the remit of the PROF. The risks have developed over the course of the programme, and these are carefully monitored on a quarterly basis. Current risks include challenges in operationalising policy, the risk of competing priorities overwhelming the available resources and changes in the international and geopolitical context. These quarterly discussions will continue to feed into an overall programme risk matrix stored on AMP and will guide how we continue to deliver future activities. These will continue to be reviewed with mitigation measures adjusted as required, and following the SSD and MCD risk escalation process if risks evolve outside of our appetite. / Programme management / Programme activities continue to be implemented primarily through the mandates that are drawn up each financial year. We meet with DCAF on a quarterly basis to discuss the progress of the mandates which include both joint and single proposals. This means that the activity is managed in house with both programme managers (FCDO and DCAF) working closely together alongside technical advisors. The activities undertaken with DCAF are delivered under an MOU agreement. / The UK plans to host one of the quarterly International Partner Group Meetings (IPG) in Spring next year to shore up like-minded consensus on SSG’s contribution to national and global security and identify priority areas for like-minded collaboration on SSG as a security tool. / Gender equality / No changes have been made to the programme’s impact on gender equality and this extension will remain compliant with FCDO’s obligations towards gender equality. / Safeguarding / Safeguarding risks for this programme are assessed as minor, owing to the standalone safeguarding policy that is place by the implementing partner. / The current DDA is valid until July 2026, so will need extending to cover the full period of the extension.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The main purpose of this no-cost extension is to bring us in line with other conflict programmes in the Directorate, enabling us to implement the proposed direction of merging into a broader, integrated conflict portfolio focused on access to specialist expertise and critical capabilities. It is within the remit of the business case, there is no change to the business case and its theory of change, and the total spend does not exceed or change the total allocation. / Supporting DCAF contributes to supporting national and global security through advancing democratic and civilian oversight of security sector governance (SSG) globally in support of more legitimate, accountable and resilient security sectors. Through its work, DCAF empowers national partners to uphold international norms and good practices, placing good governance at the heart of responses to emerging security challenges. It identifies innovative pathways to promote SSG even in highly adverse environments, including those facing democratic backsliding, hybrid threats and violent conflict. DCAF also engages directly with security sector actors to champion gender equality and intersectional approaches, addressing systemic discrimination and injustice. Furthermore, it plays a critical role in shaping international engagement on SSG, ensuring that global efforts are informed, inclusive, and effective.