## Annual Review Template

Title: Strategic Impact Evaluation and Learning (SIEL)
Programme Value £ (full life): £13m		Review date: August 2025 (covering April 2024 – March 2025)
Programme Code: 300623	AMP start date: 10 August 2023	AMP end date: 31 March 2030

Summary of Programme Performance
Year	2023/24	2024/25
Overall Output Score	A	A
Risk Rating	Minor	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0005273.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006876.xlsx

# A. SUMMARY AND OVERVIEW [1-1 ½ pages]

## Description of programme [1-2 paragraphs]

Strategic Impact Evaluation and Learning (SIEL) is the Evaluation Unit’s flagship programme that will fund impact evaluations in priority areas for the Foreign Commonwealth and Development Office (FCDO). It is a six-year learning partnership in collaboration with Innovations for Poverty Action (IPA) and the Abdul Latif Jameel Poverty Action Lab (J-PAL). It will tell policymakers about the effectiveness of their interventions and why they work (or not) by employing a set of rigorous techniques, including randomised controlled trials, like those used to test new medical treatments.

SIEL aims to achieve an impact evaluation portfolio which provides value for money for FCDO through three key outputs:
#### Strategic and rigorous impact evaluations
#### Follow-up evaluative activities to assess programmes’ impact and sustainability in the long run
- Capacity Building, Engagement and Dissemination

## Summary supporting narrative for the overall score in this review [1-2 paragraphs]

In this programme’s first year of implementation, it has over-performed against the majority of its outcome indicators and has met most of its output milestones. A great deal of learning-by-doing has taken place. The programme has responded well to stay relevant given shifting departmental priorities following the July 2024 election, but this has caused delays to some outputs. The programme team propose to build in adaptive principles to the programme going forward, in particular quarterly reflection sessions which could help sense-check logframe targets and refocus attention on what is being formally tracked.
[note] This year, 2024/5 was the second financial year after the approval of SIEL’s business case in May 2023. However, the inception period did not begin until March 2024 following a competitive grant procurement process, making this the first year of delivery.

SIEL has broken new ground in 2024/5, running for the first time an Expressions of Interest (EOI) process uniquely focussed on providing funds and technical support for impact evaluation for FCDO-supported programmes. The call received 13 applications representing a broad spread of FCDO directorates, regions and all of SIEL’s priority areas. While the review process took longer than anticipated, it provided key learning e.g. around the type of information collected at EOI stage, that will streamline future rounds.

During 2024/5, SIEL completed its first two ‘learning agendas’- sets of research questions in policy priority areas which impact evaluations could answer. The first was on Humanitarian, followed by Conflict which was ready for senior sign-off by the end of the year. The growth learning agenda was in final editing and review stages with FCDO at the time of this review. FCDO, IPA and J-PAL decided together to prioritise ensuring the final product reflected the evolving narrative in FCDO on growth, following the election of the new government in July 2024. There has been high engagement with FCDO staff, as well as external experts in the production of these, helping to ensure the agendas are relevant, evidence-informed, and well aligned with FCDO’s priorities.

SIEL’s capability-building work has generated considerable interest, with well-attended training sessions in which participants engaged well indicating strong demand. This can be attributed (at least in part) to the SIEL programme itself through the ‘motivator’ activities including well-attended presentations at professional conferences, online drop-in sessions and a launch featuring a Nobel-prize winning economist, the FCDO chief economist and chief scientist. Satisfaction with the training was high (feedback forms were positive), which is a considerable achievement given these were piloting new content and delivery methods delivered by IPA, JPAL and FCDO in collaboration.

During this financial year, the SIEL team delivered an ‘Evidence Use Diagnostic’ which provided thoughtful reflections on evaluative capacity and barriers to evidence uptake in FCDO. This work stimulated internal conversations in Evaluation Unit and should provide a good grounding for creating templates for Evidence Use Plans in 2025/6.

Overall, SIEL is delivering its outputs and is on track for end-of-programme targets. Most milestones for this review have been met or exceeded (J-Pal’s evaluating social programmes course was short on attendance, as was the SIEL launch event), giving an overall score of A.

Major lessons and recommendations for the year ahead [1/2 page]

In the first year of SIEL, FCDO, IPA and J-PAL have sought to nurture and meet the department’s demand for evidence about ‘what works, how and why’ among FCDO activities. Receiving 13 Expressions of Interest (EOIs) for impact evaluations, we discovered considerable latent demand. However, with the reduction in ODA budgets from 0.5% to 0.3% of GNI announced in February 2025, two of these proposals withdrew due to budgetary uncertainty. The programme has already needed to be flexible to elicit demand and stay relevant, e.g. by extending the timeline and engagement on the growth learning agenda, and it will need to continue to do this given the context in 2025/6 and beyond. This could include modifying programme priorities and timelines to reflect shifting departmental aims- reviewing the logframe on a quarterly basis, by having reflection sessions to ensure the programme stays relevant. SIEL might also consider evaluation opportunities which we have previously given less attention: non-ODA, evaluating behavioural nudges involving minimal ODA spend, and evaluating multilateral spend, for example where FCDO has contributed to a multi-donor trust fund with one of the International Financial Institutions. In an environment of budgetary uncertainty, the quicker and less expensive pilot and nimble studies which SIEL offers may be of particular interest and worth promoting to a greater degree to the department.
Some of the questions in Round 1 EOIs could not be addressed using the quantitative evaluation methods in which SIEL is specialised. We will add additional communications in the outreach and instructional materials to clarify the types of interventions for which SIEL can generate evidence.

FCDO has established a collegiate working partnership with the IPA and J-PAL teams, helped in part by the in-person inception workshop, motivator sessions and impact evaluation 101 course in 2024/5. This is a great asset for the programme and the teams should continue to nurture and develop this in 2025/6. Working together, this team has piloted and developed concepts for how to deliver learning agendas (short research agendas), an impact evaluation training course, motivational engagement at FCDO conferences and an EOI round. The models developed during this year can now be rolled out with greater ease in the second year of delivery.

There has been considerable progress in the administration of the project, including IPA signing a subaward with J-PAL for delivery of the learning agendas and capability building work. However, this took considerably longer than expected. IPA now has a much better understanding of FCDO’s project management requirements, and we expect to get into a good rhythm of financial forecasting, reporting and invoicing over the next year. We currently report the budget by activity but will look to also include outturn cost data (forecasts) by activity (e.g. learning agendas, capacity strengthening, EOIs) which will help FCDO to assess value for money as we progress with the programme.

While SIEL has been very successful at engaging at the working level and building a community of impact evaluation practice, there is more work to do to engage seniors in FCDO beyond Analysis Directorate and Research and Evidence Directorate. With a new chief economist and Director-General overseeing both directorates joining in 2025, these are opportunities to recruit powerful champions. We will brief them at an early opportunity and look for ways for them to champion the programme. We will also seek opportunities to engage with new senior leadership following internal restructuring; as portfolios and priorities bed down, there may be new opportunities to leverage SIEL to support learning and delivery.

We shall revisit output three (Increased awareness and sharing of evidence use through SIEL within FCDO) and agree a new series of indicators to reflect the organisational context and programme maturity.
# B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The programme’s Theory of Change (ToC) aims to address the following key issues:
- Impact Evaluations (IEs) are not systematically happening in areas of strategic priority for the organisation and/or where the evidence gap is larger;
- To conduct an impact evaluation, dedicated technical expertise is needed from pre-pipeline stage; not all teams have this expertise available, and
- Evaluation budget is linked to programme budget, meaning that rigorous impact evaluations are only happening in programmes with a more generous budget. But this is not necessarily where interesting and important evaluation questions are.
To overcome these issues, the SIEL programme will provide dedicated expertise and funds.
Once strategically relevant programmes for collaboration with SIEL have been identified, technical support will be flexibly deployed to help develop the ToC for the programme or activity and identify key assumptions and supporting evidence. This will create a better, shared understanding of what the programme aims to achieve and identify key gaps where there is little and/or anecdotal evidence supporting assumptions.
An impact evaluation provides evidence of whether the theory underlying the intervention(s) was right and holds true in the operating context of the intervention. In other words, an IE will tell if the programme worked and “how much” it worked. It can also enable estimation of cost-effectiveness of activities.
To maximise the value for money (VfM) of programmes and to increase the chances of IE results, SIEL will promote an adaptive approach to programme management and IEs: the programme will evaluate the overall impact of the intervention but before that it will also increase the chances the intervention is made as effective as possible through adaptive learning.
To achieve this, technical experts will support programme teams to develop not only the overall IE design for the programme (or one or more of its components) but also an evidence and learning plan to generate evidence needed at the beginning and along the lifetime of the programme to enable evidence-based, adaptive decision making able to maximise VfM of the intervention along its life-cycle.
Publishing IE results and pro-active communication and dissemination of findings will give the opportunity to influence programmes and policies operating in strategic areas of FCDO interest on a global scale. This will not only magnify the impact of IE investments, but it will also develop the UK’s reputation as a science power and an evidence-committed force for good in the world.
This theory of change still holds as the time of writing of this report (July 2025). We propose to change Outcome 1 in the logframe to ‘Enhanced generation and use of impact evaluation evidence as a result of SIEL evaluation projects’ to ensure that learning outside of SIEL research programmes is captured. There have been minor changes to Outcome indicators set out in the accompanying logframe ‘Change Frame’ but these result from measurement issues and small changes to delivery modalities and not fundamental changes to the Theory of Change.
Behind this theory of change are a number of assumptions, set out in detail in the Business Case. A key assumption that has been tested over the past year is ‘SIEL can adapt to shifting FCDO priorities.’ In late 2024, the SIEL team decided to carry out further engagements to ensure that the growth learning agenda which was in draft captured emerging FCDO thinking after the change of government. This change resulted in a greater incorporation of UK growth interests and ensured the document has greater relevance to current political priorities and so leads to more interest in the research. The upcoming second EOI round will provide an opportunity to test whether this is the case.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The programme has overachieved on progress towards its intended Outcomes and ultimate Impact in 2024/5. This is particularly the case for its highest priority Outcome 1: ‘Enhanced generation and use of impact evaluation evidence as a result of SIEL research projects:’

- The programme received 13 Expressions of Interest (EOIs) in SIEL’s first funding round which concluded in January 2025 (Outcome indicator 1.1). This greatly exceeded expectations, with none expected by March 2025 and only 11 EOIs expected by March 2026, a full year later.
  [note] Wherever possible, unsuccessful EOIs were signposted to other sources of evidence support better suited to their particular needs.
- For Outcome Indicator 1.3 (iii), the website has recorded approximately 1,100 engaged sessions, since the website launch in October 2024. We anticipate this number will continue to grow as we expand the website’s content.

SIEL has also over-performed against most indicators under Outcome 2: ‘Strengthened capacity of FCDO staff to commission, manage, interpret and identify opportunities for future impact evaluations.’

- For Outcome indicator 2.1 (i), 100% of respondents (n=21) to the post-course feedback survey indicated that they either agree or strongly agree that as a result of the Impact Evaluation 101 course, they have improved their understanding of how and when to conduct quantitative impact evaluations. This exceeded the planned level of 80%.
- For Outcome indicator 2.1 (ii), 86% of respondents to the post-course feedback survey indicated that they either agree or strongly agree that as a result of the Impact Evaluation 101 course, they have experienced an increased appreciation of the need for using evidence to inform decision-making and policy. This exceeded the planned level of 80%.
- For Outcome indicator 2.2 (i), 59% of participants who completed the feedback survey agreed or strongly agreed with the statement ‘I am likely to apply for funding for impact evaluations through SIEL (as a result of the IE 101 course)’. This exceeded the planned level of 50%.
- For Outcome indicator 2.2 (ii), one participant from the Impact Evaluation 101 course submitted an EOI. This is one less than planned. However, the training took place after the EOI window closed, not during or before as was originally planned.
- For Outcome indicator 2.2 (iii), 11 FCDO staff reached out to the SIEL help desk with evaluation ideas, compared to a planned 20. However, the figure does not reflect the full extent of engagement with the SIEL programme to discuss evaluation ideas, as staff also directly approached the FCDO PRO and wrote to the Evaluation Unit’s helpdesk. Our records indicate that at least 5 staff approached the EVU helpdesk in 2024-5, which if incorporated would bring this indicator much closer to target. Going forward we recommend this indicator be amended to reflect approaches to both helpdesks.

Looking ahead to next year, the SIEL team is well positioned to consolidate the learning from developing and piloting successful concepts for staff engagement, learning agendas, impact evaluation training and an EOI round. The focus will be on embedding what has worked well in the first year, streamlining delivery timelines, and continuing to adapt to FCDO’s evolving needs and priorities.

We hope to see continued demand for training activities and SIEL plans to continue to deliver high quality courses—either in person or virtually—tailored to the needs of FCDO staff. We plan to issue two calls for EOIs and engage more actively with FCDO staff to co-develop evaluation ideas that align with SIEL’s scope and methodological focus areas. SIEL also aims to explore opportunities for long-term follow-up studies.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Based on the above analysis of outcome and output achievement, theory of change and VfM analysis, there is enough evidence that the programme is on track to deliver its objectives. These objectives remain highly relevant for the organisation. In an environment of reduced ODA budgets, a programme which can generate evidence about impact and value for money can inform tough choices about where we invest. The goals align with FCDO’s priorities and, as a demand driven programme it is able to reflect the needs of the department at the time, through a series of EOI rounds. Delivery should continue.

# C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Increased quantity, quality and relevance of evidence available to improve policy design and implementation in SIEL's priority areas
Output number:		1	Output Score:	A
Impact weighting (%):		60%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of completed learning agendas on SIEL's priority areas	2 planned	2 achieved
1.2 Number of SIEL-funded research projects for high-quality, policy-relevant research proposals that address SIEL's priority areas (unique projects count only once, includes all types of research activities)	0	0

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Learning agendas are brief sets of evaluation questions in key areas where there are gaps in the evidence, which are being compiled by J-PAL in consultation with FCDO staff. They are intended to guide SIEL’s evaluative work.

The Humanitarian agenda was published in December 2024 and by March 2025, the final draft of the Conflict and Fragility agenda incorporating FCDO comments was shared for SCS sign-off.

Progress on the Growth agenda was slightly delayed due to the FCDO’s ongoing work formalising its broader growth strategy, which was initiated following the July 2024 election. By December 2024, the draft of the Growth agenda was ready for review by FCDO, but it was decided to hold off for a few months to ensure that the final product reflected the evolving narrative in FCDO on growth. Additionally, the internal review of both the Growth and Conflict agendas by FCDO teams took longer than originally anticipated, and the documents at 10-15 pages are considerably longer than originally envisaged. FCDO supports this longer format, given the extent of interest in the agendas from the department.

The first draft of the Climate and Nature agenda is nearly complete, with finalisation expected in September of 2025, which will complete the set of four learning agendas.

The output is on track for end of programme targets, and the milestone has been met, achieving an overall score of A.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There were no changes to Indicator 1.1 during the past year. FCDO expects J-PAL and IPA to deliver all four learning agendas comfortably by March 2026.

Output indicator 1.2 ‘Number of SIEL-funded research proposals’ will be reported on in the next Annual Review. However, given that SIEL’s first EOI round has resulted in 1-2 full proposals received by June 2025, and the launch of the second EOI round was delayed due to the impact of the reduction in ODA budgets, it is unlikely the programme will generate eight funded EOIs (cumulative total) by March 2026. We expect a rolling EOI round from Summer-Autumn 2025, and an additional round in spring 2026 will be too late to generate more funded EOIs in 2025-6. As a result, this milestone should be revised down for March 2026 (exact figure to be determined in discussions following the completion of this review).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Political developments in 2024/5 led to unavoidable delays in the development of SIEL’s research agenda and created uncertainty for both SIEL’s budget and the (ODA) programmes it seeks to fund. The 2024 Annual review foresaw some but not all of these challenges and the programme has performed very well in adapting, by engaging the department extensively to understand the changing context and modify deliverables and timelines to remain relevant. There is little that we recommend it does differently in this area.

In SIEL’s first Expression of Interest (EOI) exercise, we observed high demand (13 proposals) but many of the proposals proved technically infeasible, with only three projects invited to produce full proposals. This in part reflects a lack of understanding of what types of interventions can be evaluated using quantitative impact evaluations by FCDO staff, something which ongoing capability strengthening work aims to address. Future EOI rounds could clarify the strengths and limitations of impact evaluation methodology. For example, communications could emphasize that without the ability to compare sufficient numbers of individuals or units receiving an intervention with those not receiving the intervention, quantitative impact evaluation methods become infeasible. The ability of the methods to deliver ‘quick wins’ at the piloting or nimble RCT stage could also be further emphasised in EOI materials and drop-in sessions.

Two teams who had submitted proposals in the first round cancelled their EOIs after the announcement of UK ODA funding cuts created budgetary uncertainty for them. This highlights a risk for the evidence generation workstream going forward. A possible mitigation is to seek to ‘over programme’, accepting more proposals in the expectation that some may not continue due to budgetary constraints.

Output Title	Increased capacity of FCDO policymakers to incorporate impact evidence/tools into policymaking
Output number:		2	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
2.1 (i) Number of FCDO staff participating in practitioner training ("Impact Evaluation 101," in person)	25 planned	25 achieved
2.1 (iii) Number of FCDO staff participating in J-PAL's Evaluating Social Programs course	5 planned	2 achieved

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

SIEL’s first training course in February 2025 was attended by 25 people in-person, with an additional 39 joining virtually. The course generated a great deal of interest and participants contributed actively. Feedback following the course was very positive and indicated staff increased their understanding and appreciation of impact evaluation methods (see Outcomes section).

Two FCDO staff have participated in J-PAL’s Evaluating Social Programmes training, relative to a target of 5. This initiative received little promotion inside FCDO in 2024/5, relying on word-of-mouth.

The output is on track for end of programme targets. However, although indicator (i) is on track, indicator (ii) has missed the milestone for this review so the overall score is B.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

2.1 (ii): Number of FCDO staff who participating in advanced training ("Impact Evaluation 102," virtual): We have revised the March 2025 target to “zero,” as following the Q2 progress report it was already clear that the training would be organized just outside of this reporting period (May 2025). IPA and J-PAL are confident that the annual target for March 2026 will be achieved as over 100 people had already subscribed by mid-April.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

This year we have learned that demand for impact evaluation training in FCDO is considerable, and we have confirmed that J-PAL are able to deliver high-quality courses which met the learning needs of attendees. In order for this output to fully reflect achievements next year, we must ensure logframe milestones are realistic and targeted. We propose in 2025/6 to provide greater internal promotion of the ESP offer, including using the SIEL mailing list and including promotion within the impact evaluation 101/2 courses. If by December 2025, uptake does not equal or exceed 3, the March 2026 milestone for Indicator 2.1 (iii) should be revised downward.

Output Title	Increased awareness and sharing of evidence use through SIEL within FCDO
Output number:		3	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
3.1 (i) Number of stakeholder consultations conducted during the development process of the four learning agendas	20 planned	47 achieved
3.2 (i) Number of FCDO staff participating in SIEL's launch event	200 planned	120 achieved
3.2 (ii) Number of FCDO staff participating in SIEL's motivator sessions	200 planned	200 achieved

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

In 2024/5, the partner completed 47 consultations with FCDO staff to discuss evidence gaps and questions of interest across the four learning agendas. These figures exclude input from Evaluation Unit (EvU) staff and J-PAL/IPA sector staff, who have also contributed to the review process.

While participation in SIEL’s launch event in November 2025 reached an extensive audience, it fell short of its up-front ambition of 200 attendees. The event featured a high-profile panel, hybrid options and was marketed heavily, which suggests the target may have been over-ambitious. However, this does not have a bearing on the long-term impact of the programme.

The programme met its target for participation in motivator sessions, including the Evaluation and Statistics Professional Development Conference, Project Delivery Conference and Economic Leadership Programme. These engagements were well received, with many staff coming forward with questions and wishing to get more information to engage with the programme.

The output overall is on track for end of programme targets. Given overachievement on the first indicator is greater than underachievement on the second, and the third milestone was reached, we think an overall score of A is justified.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

3.1 (i) Indicator amended from 'Number of consultative workshops to develop the learning agendas attended by 7-10 stakeholders' to ‘Number of stakeholder consultations conducted during the development process of the four learning agendas’. This change reflects learning during the course of producing the Humanitarian learning agenda that engagement was effective in small groups and individual video calls, rather than larger scale workshops.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

In 2024/5, the combined efforts of J-PAL, IPA and the FCDO SIEL team have managed to generate considerable interest in SIEL’s impact evaluation offer. This should stand the programme in good stead as we go forward accompanied by a ‘community of practice’ who both understand and can advocate for impact evaluation methods.

In the current logframe, work on this output is complete at the end of year 1. We think that further work with FCDO staff will be needed to maintain and build engagement with the programme going forward. This is particularly the case as the context in FCDO is currently changing rapidly. We propose an early conversation with IPA and J-PAL to design a set of activities to continue this work, which could include communications (e.g. a video bringing to life the SIEL offer to accompany the launch of the second EOI round, webinars to promote the learning agendas).

# D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

#### Economy:

In 2024/5 SIEL was initially allocated £1.6m ODA and £0.41m non-ODA based on the Business Case. During the inception period a costed budget was produced, which reduced the total budget to £0.74m (not yet divided between ODA and non-ODA). Ultimately the programme spent £226,850 ODA and £406,765 non-ODA by March, falling 14% short of the initial costed budget. This may be in large part because it was decided to delay the second impact evaluation course (Impact Evaluation 102) to 2025/6.

Given the majority of expected outputs were delivered over the year, this lower than expected spend is some indication that the project kept costs under control during 2024/5. As we proceed into the second year of the programme, we will require that IPA disaggregates cost data for project components such as capability building, learning agendas and research projects to enable further analysis of VFM.

#### Efficiency and (Cost) Effectiveness:

Much of this first year of delivery consisted of piloting the core components of SIEL- learning agendas, training courses and EOI exercises. We expect unit costs to reduce in future years as ‘learning by doing’ enables efficiencies to be realised. Nevertheless, there are some indications that the programme worked adaptively to improve efficiency even in the early stages. For example, the SIEL team decided to carry out engagement for the conflict and growth learning agendas through 1:1 and small group Teams calls, where initially a workshop was held for Humanitarian. This reflected a perceived improvement in the efficiency of communication when moving to smaller engagements. Similarly, the SIEL PRO was able to reach large numbers of advisors very quickly to advertise the EOI by giving 5-minute presentations at cadre meetings for climate, conflict, humanitarian and evaluation.

The greater than expected number of applications to the first EOI exercise and learning gains from the impact evaluation course (outcome indicators 1.1 and 2.1) provide good evidence that these activities are effective. With outturn cost data per EOI round and course we could assess the cost effectiveness of them accurately but based on the budget of £237,148 for capacity strengthening we can say that each FCDO staff member trained in impact evaluation methods likely cost less than £3,705 . Similarly, in addition to conflict and humanitarian, the growth learning agenda was likely 75% complete by March 2025, we could say SIEL may have achieved a cost per agenda of less than £60,000. We can refine these benchmarks when we are able to obtain accurate actual cost data from IPA and monitor them against future spend.
[note] £237,148 budget/25 in person +39 virtual participants
[note] 2.75 learning agendas were achieved for less than the year 1 budget for that component of £160,869.

VFM continues to be measured throughout the programme with evidence being gathered from: Reports from IPA, regular dialogue with IPA and stakeholders, and from evidence gathered for annual reviews throughout the programme lifecycle.

#### Equity:

The focus of the programme is to improve the lives of people living in poverty around the world and improve the UK’s influence. The selection of geographies, themes and partners for evaluation are based on need and data disaggregated by sex, disability, location, and other relevant characteristics will be collected. Gender equality and social inclusion expertise and objectives are embedded across all the activities, including the implementing partner for SIEL. The 13 EOIs received in the first round of SIEL reflected all major regions in which FCDO works outside of OECD countries and covered all four of the programme’s priority topics. Participants in Impact Evaluation 101 were 62% from UK, 22% Asia, 13% Africa and 4% Americas. We expect the 102 course in 2025/6 to reach more participants overseas and will continue to collect and disaggregate this data for SIEL activities.

Assessment of whether the programme continues to represent value for money

Based on the above analysis, we believe that the programme continues to represent value for money and therefore should continue.

# E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The overall risk rating for SIEL is moderate. This is within the risk appetite for the programme which is receptive.

SIEL has seven open risks that are categorised into three areas:
- Policy & Programme Delivery
- Public Service Delivery & Operations
- Financial & Fiduciary
The risks currently identified relate to demand for impact evaluations from FCDO, and high-level financial risks. As SIEL moves through the delivery stage the risks will be further developed with strong mitigations put in place. All risks will be reviewed quarterly and updated where required.

The residual risk ratings are:

Residual risk rating	Number of risks
Major	2
Moderate	2
Minor	4

There are two risks classed as major after mitigation, both of which have worsened over the past year. They are ODA budget cuts, which threaten SIEL’s budget and evaluation and programme budgets more broadly, and strength of demand (for impact evaluation) which follows from this. The mitigations for these are to be flexible with the timing and duration of future EOI windows, and to consider sources of programming for evaluation which we have previously given less attention: non-ODA, evaluating behavioural nudges involving minimal ODA spend, and evaluating multilateral spend, for example where FCDO has contributed to a multi-donor trust fund with one of the International Financial Institutions. We are also pushing forward with delivery at pace, to prove the SIEL concept and establish the programme’s reputation. Nevertheless, given these risks are driven largely by factors external to the programme, the residual risk cannot be further reduced, though they remain within the programme’s ‘receptive’ risk appetite.

There are two risks rated as moderate. They are the quality and timing of demand and the duration of potential programmes and evaluations. These risks have appropriate mitigation strategies in place to ensure they are minimised (discussed above).

There are four risks rated as minor which is an increase of one from the last annual review. These are: whether evidence generated by SIEL will have impact, staff turnover, negative evaluation results causing demotivation and timing of engagement. The risks have appropriate mitigation strategies in place to ensure these risks are minimised.

With regards the Paris climate Agreement, the climate and environment risk is low.

# F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

Financial

Accurate and timely invoicing and forecasting remains important as always, to fulfil FCDO’s accountability obligations and to enable efficient management of funds by the department. FCDO has highlighted this to IPA and reporting on expenditure and forecasting is a key part of IPA’s quarterly reports.

After a somewhat slow start, IPA increasingly understands FCDO’s requirements in this area, and we recently agreed on the timing of future quarterly reports, forecasts and invoices to be received within six weeks of the end of the previous quarter. It is important that SIEL sticks to this schedule, for FCDO to effectively manage the programme, especially in the current fiscal environment. We also expect IPA to provide outturn costs by activity (e.g. learning agendas, courses, EOIs) to assess VFM for the programme going forward more accurately.

Assets

IPA confirmed one additional laptop on their asset register since March 2024, taking the total to two. The laptops are in their possession and functioning. The condition is fair.

Commercial

Over the year, it took much longer than anticipated for IPA to agree the wording of their sub-award with J-PAL. This could have caused major problems for the programme but was finally agreed within the reporting year.

The FCDO SIEL Programme Responsible Owner (PRO), and Programme Manager have had regular meetings with IPA and J-PAL staff over this year, currently on a weekly basis. Quarterly reports provide detailed monitoring on progress and expenditures whilst providing excellent opportunities to review risks and next steps.

FCDO as a partner:

Feedback from the partner was positive. There is a shared vision for SIEL. Stakeholders understand the purpose of the programme and how they fit into it. Collaboration and communication between the SIEL and EvU team has been strong. Regular weekly check-ins, combined with in-person engagement during the inception meetings in March 2024, the motivator sessions in the autumn of 2024 and the Impact Evaluation 101 training in February 2025, contributed to strong team cohesion while also ensuring that all team members remain aligned on shared goals and informed about developments across workstreams.

# G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

FCDO’s Senior Responsible Owner (SRO), Programme Manager and other staff have had weekly meetings with IPA and J-PAL staff over this year to coordinate delivery.

The partner produces quarterly reports that allow for detailed monitoring on progress updates. These are followed by discussions to review risks, finances and learning. The programme has a logframe which has been tweaked during the course of the year to reflect learning and adaptations to how it will deliver its objectives. It will be formally reviewed following SIEL’s first quarterly report of year 3 (second year of delivery) in August 2025.

The SIEL team have collected feedback data from training course attendees, and about the profiles of EOI applicants (DG area, team, location etc). This has enabled the team to tailor and refine its outputs as we move from piloting SIEL’s way of operating to sustained delivery in year 3.

This Annual Review was written during June and July 2025. It was conducted by FCDO staff: the PRO for SIEL (Evaluation Adviser, Evaluation Unit) and the Programme Manager. FCDO carried out a document review as part of this process. Interviews were conducted with IPA. The Head of Evaluation Unit, Deputy Head of the Evaluation Unit and Deputy Director for the Analysis Directorate have all reviewed and approved the Annual Review.

Evidence

In producing the learning agendas on humanitarian, conflict, and growth, which are at advanced stage or finished by March 2025, the SIEL team has brought together considerable evidence which can guide the implementation of the programme. Each learning agenda contains evidence snapshots indicating where there are gaps. These will help EOI applicants tailor their applications and help target the programme to where there is greatest need.

To our knowledge, there have been no significant changes to the evidence base about the transformative potential of impact evaluation evidence for policy making since March 2024.

Learning

As indicated in this report, there has been considerable learning by doing over the course of year. All deliverables were piloted for the first time, and the team now has working models of these concepts which can be delivered at scale in year 2. These included the production of learning agendas with extensive engagement with FCDO staff, other motivational engagement with the department (launch, presentations at professional development conferences and cadre meetings), the impact evaluation training courses, and the first EOI round.

IPA hosted a ‘pause and reflect session’ in June 2025 which has informed this report. This consisted of an online workshop in which the FCDO, IPA and J-PAL SIEL teams reflected on the year’s successes and challenges. We suggest it will be valuable to repeat this again in the year ahead and have ‘mini’ reflection sessions on a quarterly basis, with a formal opportunity to revise the logframe at 6 months into the year (October).

Date of last narrative financial report	March 2025	Date of last audited annual statement	December 2023