## Annual Review Template

Title: Private Enterprise Programme Zambia Phase II (PEPZ II)
Programme Value £ (full life): 85 million		Review date: 7 July 2025
Programme Code: 300635	AMP start date: April 2020	AMP end date: March 2029

Summary of Programme Performance
Year	2021	2022	2023	2024	2025	2026	2027
Overall Output Score	A+	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	Link
DevTracker Link to results framework:	Link

A. SUMMARY AND OVERVIEW

Description of programme
The Private Enterprise Programme Zambia Phase Two (PEPZ2) aims to enable small and medium sized enterprises (SMEs) in Zambia to scale up and become an engine of job creation in the economy. Initially launched in 2020 and recently extended to run through 2029, the programme supports inclusive economic growth by helping SMEs access finance and improving the enabling environment for sustainable power and regional trade. PEPZ2 contributes to two key British High Commission Lusaka outcomes: promoting green and responsible investment and expanding renewable energy. Over the last year the programme has significantly shifted its approach to supporting SME’s and through this Annual Review will further adapt its delivery modality guided by a convening ‘coalitions for change’ approach.

In the 2024/25 year two new delivery partners were included in PEPZ2 and one previous partner was withdrawn:
- Aceli Africa is a non-profit that incentivizes private sector lending to Agri-SMEs by providing first-loss coverage for loans in the $10k-$1.75M range and deal origination incentives for lenders. Its aim is to transform the market for agricultural finance by unlocking capital supply, building demand and strengthening the enabling environment.
- The Zambia Tanzania Interconnector Project (ZTIP) is a 600km power interconnection project between the East and Southern African Power Pools, which will enable regional trade and improve power supply across multiple countries. The $300m World Bank-led project received a £15m grant through PEPZ2 funding in FY24/25 along side a EUR30m grant from the EU
- In 2024/25 FCDO withdrew its funding through Prospero Ltd and completed design of a new service provider led SME support project (discussed in more detail under the lessons learnt section below)
The PEPZ2 programme funds two additional projects; Cities and Infrastructure for Growth Zambia (CIG Zambia) – Providing technical assistance in the power sector and TradeMark Africa (TMA) – Promoting trade-led prosperity. Together these provide a broader, more integrated approach to private sector development that align with the UK and Zambian strategic priorities of trade, investment, climate and energy. The strong UK-Zambia partnership enables the programme to join up policy influence, technical assistance, and catalytic capital across these priority areas and target systemic impact greater than the individual interventions. This is exemplified by Zambia accepting the UK’s invitation to join the Supply Chains Mission of the UK’s Global Clean Power alliance, an initiative that blends UK support through the PEPZ2 Programme for energy, trade and SME growth.

Summary supporting narrative for the overall score in this review
The programme aims to drive systemic change across the economy – particularly around productive jobs, green growth, with a growing focus on economic transformation. The component projects and their relation to the pillars of inclusive growth are set out in the diagram below.

With the incorporation of new partners in 24/25 the PEPZ2 programme scaled up its activities considerably, committing a total of £28m of ODA spend during the year, which was 90% capital spending. The Logframe outputs and scores are tabulated below and discussed in detail in section C. The projects have individually performed well, mostly meeting or exceeding expectations and resulting an overall ‘A’ score for the project.
Output title	Weight	Score
Prospero demonstrates sustainability by building strong pipelines, investing in SMEs, facilitating investments of commercially viable and impactful businesses and complying to FCDO project closure requirements.	5%	B
CIGZambia: Policies, regulations, plans and strategies that support inclusive climate compatible growth are designed and/or implemented and improve capacity of CIGZambia's clients	15%	A+
CIGZambia: Projects and interventions are inclusive and climate resilient by integrating screening for GESI[1] and climate change considerations in their design and implementation	15%	A
TradeMark Africa: Construction of Nakonde One–Stop–Border-Post	15%	A+
TradeMark Africa: Installation of Nakonde One-Stop-Border-Post Cargo Scanner	15%	A
Aceli Africa: Mobilising investment for job-creating agri-SMEs ($15k-$1.75M ticket size), through (1) financial risk-sharing and (2) technical assistance to businesses and local/regional financial institutions	5%	A
Zambia Tanzania Interconnector: Completion of targeted preparatory works	30%	A
Total output score	100%	A
[1] GESI is Gender, Equity and Social Inclusion

Major lessons and recommendations for the year ahead [1/2 page]
The 2020 business case originally envisaged delivery through a special purpose vehicle (SPV) Prospero Ltd to provide market development; advisory services and investment to SMEs. However, in 2024, following a mid-term review of PEPZ2 and a sustainability review of Prospero, the decision was made to transition away from the SPV model towards a supplier-led model. Therefore, at the start of the 24/25 financial year, FCDO stopped funding Prospero activities and worked towards a responsible exit. In parallel FCDO developed a programme alternative design for supporting SME’s, through this process several lessons have been learnt for future programme design –
- The SPV model operated by Prospero was designed to manage financial assets and had high management and transaction costs for FCDO. The Prospero sustainability study recommended that SPV model should be reserved to deliver DevCap investments at scale, since financial investments cannot be managed under a supplier-led model. For market development activities that don’t directly hold financial assets a supplier-led approach will normally deliver better value for money and be lower risk for FCDO posts to manage.
- Where the SPV model is deployed, FCDO needs to ensure consistent advisory expertise to oversee Development Capital (DevCap) funding managed by the SPV. To avoid disproportionate FCDO staff time allocation, DevCap instruments should be selected carefully, operate at scale, and ideally be managed by a financial institution. This may preclude single country- SPV’s unless they are in large and dynamic economies.
- Legal advice was essential to establish basis for FCDO’s withdrawal, and the treatment of the assets and staff. However, the advice received was often complex, ambiguous and sometimes contradictory which resulted in delays and a considerable amount of staff time to achieve a responsible withdrawal. Focussed effort is needed when establishing and managing SPV’s to minimise exposure to legal risk, including having a strong grasp of local laws regarding assets and staff treatment in the event of FCDO withdrawal.
Some of the most impactful work that the PEPZ2 programme has done this year has been low-cost targeted technical assistance and advocacy to senior decision makers under a ‘coalitions for change’ approach. Examples include supporting power and fuel sector reforms, through seeking collaboration and alignment with partners and stakeholders. In coming years, the budget for the PEPZ2 programme is likely to fall in line with the UK’s reduced ODA from 0.5% to 0.3% of GNI, which may require a further evolution of the how projects operate to maximise impact without large expenditure.

In FY24/25, PEPZ2 benefitted from a large capital allocation of over £25m which was announced well in advance during the previous financial year, allowing the team time to align a series of projects which could utilise the funding effectively. Without a full year of preparatory time, it would not have been possible to mobilise the activities, particularly for the £10m Nakonde OSBP and £15m ZTIP contribution. Both projects built on many years of prior studies, many funded by FCDO, showing that large capital projects can be successful with systematic and sustained preparation.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Zambia’s population is set to double over the next 20 years. With an estimated 1,000 young people joining the labour force every day, the country needs to create productive jobs. Industries such as copper mining are driving overall economic growth but are not creating jobs at scale. The PEPZ2 Theory of Change identities Zambia’s SME sector as a key engine of large-scale job creation in the economy, and a key contributor to the Inclusive Growth pillar in FCDO’s Zambia Business Plan. The impact and outcome statements are unchanged from the original business case however by introducing additional modes of delivery the programme is evolving towards a more flexible, catalytic platform that aims to deliver high-impact, low-cost interventions, attract other funders, and align with other UK foreign policy tools. In particular, the programme is aiming to focus on supporting reforms which are aligned with Zambian political and social priorities and work more closely Zambia change makers.

Theory of Change for SME Support The 2025 update of the PEPZ2 Mid-term review found that the strategic case for continuing to invest in SMEs was still strong, with demonstrated need and demand for PEPZII services both from the Government and the private sector. In the last year the SME support landscape has shifted with the unexpected closure of the USAID funded SME financing and business environment programmes. The UK supported the launch of Aceli Africa, and BII supported launch of Zambia Investment Support Project (ZISP) and its new lending instrument, Growth Investment Partners (GIP). The EU private sector programmes have continued to provide matching grants in the agriculture and circular economy sector.

ZSTP is a pipeline project currently being designed to fit in this changing landscape (subject to funding availability) with a more cost-effective delivery mechanism and without offering direct business financing. VfM analysis that informed FCDO’s withdrawal from Prospero indicated that the most impactful results can be achieved without the complexity of an SPV structure. If approved the project is expected to drive economic transformation by supporting “high-potential” Small Growing Businesses (SGBs) through three components:
1. Policy and Learning Support - Enhancing the regulatory environment through a ‘coalitions for change’ approach and fostering adaptive learning to guide project interventions.
2. Growth-Oriented Advisory Services - Enabling SGBs to innovate, diversify, and access finance to scale up more complex products and services that can increase productivity.
3. Small Firm–Large Firm Linkages - Creating structured market access for SGB’s through partnerships with large firms that require complex inputs in key sectors.
ZESP would aim to identify “high-potential” SGBs through performance assessments and adaptive support, building on lessons learnt from previous support to Prospero. The project would aim to work closely with the BII’s GIP and ZISP projects without duplicating the offer.

CIGZambia Theory of Change: Lack of reliable access to power remains a significant barrier to economic development in Zambia, particularly for SMEs. This challenge has been exacerbated by a prolonged drought throughout 2024, highlighting the country’s heavy dependence on hydropower. To address this, with CIGZambia support, the power sector is embarking on a series of complex reforms to transparently open the grid for private power transmission which, if implemented well, should dramatically increase investment. The reforms are personally driven by the President and have the potential for catalytic impact on long-term green growth and energy security, unlocking reform and crowding in investment.

High quality technical assistance from CIGZambia is expected to improve policies, regulations and plans which in turn are expected to facilitate increased power generation and access, unlocking private sector potential leading to climate-compatible economic growth, and ultimately driving employment at scale which is key to broader poverty reduction in Zambia.
TradeMark Africa Theory of Change: Zambia is a landlocked country bordered by eight nations, strategically positioned at the crossroads of six major regional transport corridors that link East, West and Southern Africa. Among these, the Dar es Salaam, Beira, and North-South corridors are particularly vital due to the high volume of cargo they handle. 70% of Zambia’s exports and 80% of its export revenue come from copper mining, making these corridors essential for sustaining the economy.
Zambia’s participation in regional and global trade is hindered by a weak trade and logistics environment. The country faces numerous non-tariff barriers (NTBs), such as restrictive customs procedures, technical and sanitary regulations, and poor infrastructure at border posts. These barriers increase compliance costs, especially for small-scale traders, and contribute to some of the highest transport and logistics costs in the region. Border crossing delays—averaging 25 to 64 hours at key points like Chirundu, Kazungula, and Nakonde—further exacerbate the problem. By reducing transport and logistics costs by 10% along critical corridors, Zambia could increase trade by 3% and GDP by 1%.
To address these challenges, Trademark Africa has been upgrading the Nakonde border and has proposed a trade facilitation programme aimed at streamlining cross-border processes, introducing digital trade solutions, supporting policy reforms, and enhancing sanitary and phytosanitary compliance. The programme also emphasizes inclusive trade by supporting small-scale traders, particularly women and youth. Expected outcomes include a 10% reduction in trade time and costs, a 15% decrease in border crossing times, and a 20% reduction in trade document processing times at key border posts. These interventions are projected to boost regional trade, support SME growth, and create jobs. The new programme needs to consider adapting to ‘coalitions for change’ approach to improve its impact.
ZTIP Theory of Change: FCDO’s £15m contribution out of a total project value of $300m – through the Energy Sector Management Assistance Program (ESMAP) will catalyse the completion of Zambia’s side of Zambia-Tanzania Interconnection linking the Southern and East African Power Pools. This will enable Zambia to import surplus clean energy from Tanzania’s 2GW Julius Nyerere Hydropower Project, increasing access to reliable electricity in a country where 80% of supply depends on vulnerable domestic hydropower. By strengthening regional connectivity, the project helps mitigate the impact of climate shocks like the 2024 drought and supports integration of more variable renewables across borders. In doing so, it will address a critical constraint to industrial growth in Zambia and southern DRC—unreliable power supply—thereby boosting mining output, supporting UK-Zambia trade ambitions under the Green Growth Compact, and laying the foundation for Zambia to become a regional clean energy trading hub.
ACELI Africa Theory of Change: Agricultural SMEs hold significant promise for reducing poverty, especially among smallholder farmers and low-skill workers, including women and youth. These enterprises can serve as a bridge into the formal economy, but many struggle to reach their potential due to limited access to finance and management capacity. A major obstacle is the “missing middle” financing gap—SMEs that are too large for microfinance but too small or risky for commercial banks. This gap is estimated at $65 billion across Sub-Saharan Africa. Aceli’s 2025 benchmark assessment revealed that commercial banks often face negative profitability when issuing smaller loans (between $10K and $50K), highlighting the need for incentives to make such lending viable.
To address these challenges, Aceli provides financial institutions with a suite of incentives: Portfolio First-Loss Coverage, Origination Incentives, and Impact Bonuses. These tools are designed to align the risk-return profile of lending to agricultural SMEs with the realities of the market. Aceli also supports policy reform to improve the business environment The short-term goal is to stimulate more lending to high-impact SMEs, expand the pool of viable borrowers, and strengthen the broader financial ecosystem. Ultimately, these efforts aim to influence a change in lender appetite and create a robust financial market that supports agricultural SMEs in improving livelihoods, enhancing gender inclusion, bolstering food security, and promoting environmental sustainability.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Prospero outcome: The Prospero SPV did not meet the outcome originally intended in the pre-Covid business case design due in part to budget reductions which meant the high fixed costs of the SPV model no longer represented value-for-money. Operational challenges, including weak financial management and high staff turnover, further constrained delivery. In this context, FCDO’s reduced risk appetite for overseeing complex Development Capital instruments - especially in smaller markets - reinforced the decision to transition away from the SPV model. FCDO withdrew from Prospero on the 31st March 2025 and lessons learnt have been incorporated into the design of a leaner successor project under the same PEPZ2 business case subject to funds availability. If approved, the new project is expected to focus support on high potential Small Growing Businesses and will be launched in the FY25/26 financial year subject to budget availability.

CIGZambia lead outcome 2.1: The CIGZambia model of trusted and strategic technical assistance has been highly successful to influence positive reforms. It has become a model of what UK funding can achieve when there is strategic alignment with government counterparts and the private sector. During the year under review, CIG Zambia exceeded their outcome targets largely through the pivotal role it played in updating the Environment & Social safeguard documents for the Zambia-Tanzania interconnector project. CIG activities mobilised investment commitments totalling £382 million for the energy sector, surpassing its cumulative target of £350 million. Of this, £381 million came from public sources—including government and donor funding—while £1 million was privately financed. The public investment was attributed to the $300 million ZTIP with CIGZambia’s attribution assessed to be 32.5% of this investment. Looking ahead, private investments of about $150m from the GETFit programme are anticipated in the next year. More significantly, and harder to quantify is the emerging impact of CIGZambia’s catalytic technical advice on long-term green growth and energy security, through unlocking reform and crowding in expertise and investment from other partners.

Trademark outcome: The outcome target of increasing the capacity for cargo scans conducted per hour from 12 to 100 once the new modern drive through cargo scanner is installed remains valid and logical with the expectation of the final result later in the year FY25/26. The intervention of upgrading the border post remained largely on track to achieve this outcome target with the project sightly extended to June 2025 to account for the delays caused by heavy rains in the 2024/2025 wet season and the protracted processes during the relocation of project affected persons.

ZTIP lead outcome: FCDO mobilised and disbursed $17m (£15m) in public sector finance to the World Bank to support Zambia’s side of the Zambia-Tanzania Interconnector, contributing to a total project value of $300 million. This investment, of which £9.75 million is International Climate Finance (ICF) eligible, is helping address Zambia’s acute energy deficit—exacerbated by climate-induced drought—by improving access to reliable, clean, cross-border electricity. The first tranche of funds amounting to £4m enabled the contracting of the Owner’s Engineer, a crucial milestone to secure technical oversight for the ZTIP.

Aceli Africa outcome: The outcome target of having SMEs supported to develop a viable investment pipeline to enable greater access to finance, growth in productivity, and establish the private sector as the engine for jobs is on track. Aceli has already partnered with several Zambian financial institutions and was expected to support 30 loans totalling $5.3 million by March 2025.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]
Based on the above analysis of outcome and output achievement, theory of change and VfM analysis, there is strong evidence that the programme continues to represent good value for money and should continue subject to budget availability.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Prospero: Prospero builds strong pipelines and invests in SMEs and facilitates investments of commercially viable and impactful businesses for investment facilitation. Number of SMEs linked to investors
Output number:		1	Output Score:	B
Impact weighting (%):		5%	Weighting revised since last AR?	Yes, down

Indicator(s)	Milestone(s) for this review	Progress
Number of TA trainings conducted by Prospero to improve SME capabilities, attract investments and financing.	17	17
Number of SMEs linked to investors	60	60
FCDO withdraw from Prospero by 31st March 2025. Management & Board collaborate with FCOO to close the SPV properly	Financial close out, HR Management, , Financial and fixed asset management	Partially achieved, all staff contracts and two out of four financial assets transferred.

Briefly describe the output’s activities and provide supporting narrative for the score.

Recognising that Prospero was limited in its ability to implement activities during the closure year, the weighting and scope of measurement was scaled back and the project’s log-frame was revised to focus on just one output and three indicators, instead of the broader set of indicators previously tracked. The initial two outputs milestones were set to match the activities Prospero could accomplish in the reporting year, the final output related to FCDO’s withdrawal from Prospero and was partially met resulting in an overall B score.

Output 1.1 Captures the number of Technical Assistance trainings conducted to enhance SMEs capacity and growth. Prospero staff conducted 17 training sessions between September 4 and December 6, 2024. These sessions aimed to enhance the viability of SMEs and improve their attractiveness to investors. The trainings covered a wide range of topics[2]
[2] Training topics include investment Readiness, Business Planning and Marketing, Financial Management, ESG Standards, Proposal Writing, Supply Chain and Out-grower Scheme Development, Digital Marketing and Branding, Proposal Writing, Environmental, Social and Governance, Environmental, Social and Governance, Human Resource Management, Safeguarding, Risk Management, Mastering Packaging, Branding and Labelling, Digital Marketing & Social Media Strategy, Successful Out-grower Management, Occupational Health and Safety
with a cumulative attendance of over 800 participants. The sessions received positive feedback, prompting Prospero to enhance its TA materials by aligning them with international standards. This initiative also laid the foundation of the development of the “Prospero Academy”, a forthcoming online platform designed to offer tailored courses and learning resources to SMEs.

Output 1.2 Prospero facilitated strategic partnerships with Impact Capital Africa (ICA) and the Zambian Business Angels Network (ZBAN) to connect SMEs with potential investors. key outputs of this effort was the number of SMEs successfully linked to investors through strategic partnerships with both ICA and ZBAN. Similar to last year, Prospero co-hosted the successful annual ICA summit in June 2024 which attracted over 300 delegates from 17 countries linking 12 SMES to investors. In parallel, Prospero provided ongoing support to ZBAN’s monthly pitch sessions, providing a platform for early-stage and growth-oriented businesses to present their ideas to local angel investors. During the review year, 48 SMEs were linked to investors under this network. Out of the 60 SMEs who were linked to investors, 10 successfully closed investment deals, while 5 remained pending at the time of reporting.
Output 1.3 This output focused on key deliverables related to Prospero’s transition process. The transition plan encompassed financial close-out, disposal of physical and financial assets, and human resource (HR) management. The output was partially achieved by the target date of 31st March.
Capital funding (CDEL) activities were suspended during the reporting period, only salaries and overhead costs were funded. Despite continuous efforts, Prospero’s financial management remained weak throughout the transition, with associated risks falling outside FCDO's risk appetite. This was primarily attributed to high turnover within the finance department, which adversely affected the quality of financial reporting. Notably, the audited financial statements for the financial year ending March 2024 were significantly delayed, further impacting the transition process.

Staff turnover continued to be a major challenge, largely driven by the uncertainty surrounding FCDO’s planned withdrawal. Key personnel from the Investments and Finance teams resigned, creating a transition challenge. While Prospero did recruit a Head of Finance and an HR Manager, both individuals failed to pass their probationary periods, leaving these critical roles vacant once again, this led to FCDO engaging an external accounting firm to support financial and HR management. This measure allowed FCDO to achieve greater assurance regarding these functions.

Negotiations between FCDO and the Prospero Board were prolonged, particularly around critical matters such as the disposal of financial assets, staff contracts and gratuity, and the continuity plan which were essential to informing key decisions. Despite FCDO deploying a combination of formal and informal communication channels with Prospero Board and management, progress on these issues remained slow ultimately delaying aspects of the transition process.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Significant changes were made to the Prospero logframe during the year under review, driven by the termination of funding. FCDO made a strategic decision to stop the creation of new financial assets and instead focus on asset disposal. As a result, the number of log-frame outputs was reduced from three to one. The remaining output captured technical assistance and training provided to SMEs, as well as their linkages to potential investors. In addition, a new indicator was introduced to measure the effectiveness of the transition. This included risks and financial management, asset disposal, and staff turnover.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Last year's recommendation related to safeguard screening of investments and has not been applicable this year due to withdrawal of FCDO funding from Prospero.

Output Title	Policies, regulations, plans and strategies that support inclusive climate compatible growth are designed and/or implemented and improve capacity of CIGZambia's clients
Output number:		2	Output Score:	A+
Impact weighting (%):		15	Weighting revised since last AR?	Yes, down

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of policies, regulations, plans and strategies that are (A) scoped; (B) agreed with the client; (C) designed with CIGZambia's clients that support either or both inclusive, climate-compatible growth	Cumulatively / A:9; B:8; C:6	Exceeded expectation / A:10; B:9; C:8
4.2 Sustainable improvements in individual and organisational capacity of CIGZambia's target clients measured using CIGZambia's Capacity Building Scorecard – disaggregated by number of improvements and extent of improvements across categories	Number: 30 / Extent of improvement score: 60	Exceeded expectation / Number: 30, Extent of improvement score: 80

Briefly describe the output’s activities and provide supporting narrative for the score.
CIGZambia has played a pivotal role in strengthening Zambia’s power sector through improved planning, renewable integration, and institutional coordination. In early FY24–25, it facilitated the engagement of WSP Canada to support ZESCO on the Zambia–Tanzania Interconnector (ZTI), ensuring alignment with World Bank environmental and social standards. This included updating critical assessments like the ESIA, ESMP, RAP, and biodiversity studies.

CIGZambia is advancing the operationalisation of Zambia’s Open Access electricity market by supporting the Ministry of Energy in establishing the Independent System and Market Operator (ISMO), launching technical workstreams, and fostering collaboration among key stakeholders. Complementing these efforts, CIGZambia supported the Ministry of Energy in launching the Centre for Sustained Energy Modelling (CSEM) to enhance long-term planning and implement the Integrated Resource Plan (IRP). It developed a governance framework, business plan, and national data repository, while also advancing energy storage research. Notably, the establishments of the CSEM and ISMO are on-going.

CIGZambia aided the Rural Energy Agency to update the Rural Electrification Master Plan (REMP) using GIS and optimisation tools. Additionally, it co-led the development of the IRP Financing Strategy with CCG, engaging stakeholders and delivering capacity-building programs using open-source tools like MINFin, FinTrack, and FINPLAN. Through its Thought Leadership workstream, CIGZambia also established the IRP Steering Committee, which now drives sector reforms under the leadership of the Permanent Secretary for Electricity.

Output 2.1 The narrative below provides evidence for the cumulative results achieved under Output 2.1. The 2024/25 targets were exceeded in all categories:

- (A) Scoped Policies/Plans/Strategies (Target: 1 | Achieved: 2):
  - IRP Financing Plan – Developed under Data-to-Deal (Intervention 3.2) in partnership with CCG. It details 5-year financing needs and aligns with macro modelling. Scoped in Q2 and launched in October 2024.
  - Independent System Operator (ISMO) – Scoped under Workstream 4 through a workshop (26–27 Sept 2024) and ToRs were developed for MoE validation.

(B) Agreed with Client (Target: 1 | Achieved: 2):
1. IRP Financing Strategy – Finalised through consultations with MoE, ZESCO, and others. Validated and adopted by the FCDO Steering Committee in March 2025. Training on FinPlan and MinFin models followed.
2. ISMO for the Energy Sector – Merged with the Open Access Project. Workplan approved (7 Feb 2024); CIGZambia’s role formalised at the launch (14 Feb 2025). CIGZambia is leading 5 of 7 workstreams, aiming to launch ISMO as a corporate entity by July 2025.

(C) Designed with Clients (Target: 1 | Achieved: 2):
1. Updated REMP – Final draft supported by CIGZ and under review by REA CEO before Board submission.
2. Social Safeguards Framework (SSF) – Training concept note developed for MoE’s internal rollout to build institutional ownership.

Output 2.2 Following FCDO approval, a revised approach was implemented across this indicator tested via the two capacity-building trainings on Variable Renewable Energy (VRE) Transmission Modelling and contributing to significant capacity gains. In Module 1 (24–28 February 2025), 21 participants completed baseline and endline scorecards, achieving an average final score of 3.0 (sufficient capacity) out of 4 (strong impact). Organisational assessments rated ZESCO and UNZA at 3 (sufficient capacity) and 1 (modest capacity) respectively, with ZESCO benefiting from institutional PowerFactory licences and initiating the institutionalisation of training using reusable materials. UNZA, currently without PowerFactory access, is exploring open-source alternatives for student training. In Module 2 (3–7 March 2025), the same participants recorded an average score of 2.6, with organisational scores remaining unchanged—ZESCO continuing to maintain an advantage due to ongoing access to PowerFactory. Overall, the programme exceeded expectations, achieving 30[3] sustainable improvements in individual and organisational capacity—meeting the target number—while the extent of improvement score reached 80[4], surpassing the expected 60. This reflects a deeper-than-anticipated level of capacity strengthening, as measured by CIGZambia’s Capacity Building Scorecard.
[3] The score of 30 is the summation of all the individual and organisational scores. Notably, for individual scores the weighting is 1 while organisational scores weigh 2 each.
[4] This score is calculated by multiplying the number of improvements by the average score (30*2.7=80.3) - refer to capacity building scorecard tab

Fuel Sector Technical Assistance: Zambia imports all its fuel which is essential for the economy to function. The PEPZ2 project funded a study on fuel pricing in 2023 which identified ways to reduce the cost of overland transport. In 2025 the Energy Regulation board requested further technical support to assess the margins that Oil Marketing Companies are mandated to include in the fuel price. CIGZambia engaged a consultant to advise on how margins can be significantly minimised. This technical support led to a request from the ERB for a full study on Petroleum Downstream Margins in FY25/26. The CIGZambia consultant also provided advice on mechanisms for dealing with the price differential on fuel transportation costs between the TAZAMA pipeline and road transport which informed the government’s selection of IMF benchmarks.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

As recommended by the previous Annual Review, the capacity-building assessment methodology under CIGZambia has been updated to improve relevance and accuracy. These changes have been integrated into the log frame and updated scorecard templates. There are no changes proposed to the output from this review. Looking ahead, further adjustments to the scoring scale are anticipated.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
CIG Zambia is positioned to provide critical advice at time of rapid and consequential change in the power sector. As such CIG Zambia has launched a dedicated thought-leadership workstream which has begun analysis on current and future sector reforms. The workstream needs translate analysis into actual impact by including political economy analysis to identify and advocate on reforms that are most likely to get traction ahead of the election in 2026.
In FY24/25 CIGZambia collaborated closely with the new FCDO-funded Green Cities and Infrastructure Programme, which began work on a procurement framework for the IRP. CIGZambia’s reputation and experience was an invaluable foundation to enable GCIP to establish its credibility and work programme with government counterparts.
Similarly CIG’s inclusive approach—working with both industry and academia on energy modelling bridges the skills gap and offers graduates practical, hands-on experience relevant to real-world energy challenges.

Output Title	CIGZambia: Projects and interventions are inclusive and climate resilient by integrating screening for GESI and climate change considerations in their design and implementation
Output number:		3	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	Yes, down

Indicator(s)	Milestone(s) for this review	Progress
3.1 % public/private CIGZambia TA projects and/or capital projects supported by CIGZambia achieving a score of (A) 2 or more in the CIGZambia G&I marker; and/or a score of (B) 3 or more in the CIGZambia Climate Resilience marker.	GESI: 60-80% / Climate: 60-80%	Achieved / GESI: 78% / Climate: 74%
3.2 Evidence of CIGZambia supported projects (either own TA projects/interventions or client projects/interventions) integrating GESI and/or Climate considerations in the design/implementation.,	At least 2 examples evidence (qualitative)	1) ZTIP Enviro-Social Safeguards Framework updated, including GESI considerations 2) GESI inputs were incorporated by CIGZambia into the REMP final version

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Output 3.1.a During FY24/25, CIGZambia focused its Gender Equality and Social Inclusion (GESI) mainstreaming efforts on three key interventions, the update of the Rural Electrification Authority’s (REA) Rural Electrification Master Plan (REMP), the Zambia–Tanzania Interconnector (ZTI) project and the implementation of the Social Safeguards Framework (SSF) in the Integrated Resource Plan.

All CIGZambia projects are assessed using the G&I marker, requiring a minimum score of 2 (empowerment) to proceed. This threshold ensures interventions are designed to enhance the assets, capabilities, and opportunities of women and marginalised groups. In FY24/25, 78% of CIGZambia-supported interventions met or exceeded this threshold, surpassing the internal target of 60–80%.

Output 3.1.b Zambia continues to experience the impacts of climate change, including prolonged droughts, rising valley temperatures, flash floods, and erratic rainfall patterns. These challenges are worsening water scarcity and reducing hydroelectric generation capacity, contributing to widespread load shedding.

It was against this background that the CIGZambia projects were assessed using the Climate Resilience marker, with a goal for interventions to achieve a minimum score of 3 out of 5. In FY24/25, 74% of CIGZambia-supported interventions met or exceeded this threshold, surpassing the internal target of 60–80%, indicating strong integration of climate risk management in project design and implementation. Key contributions included support to the Zambia–Tanzania Interconnector (ZTI): CIGZambia’s subcontractor, WSP Global Inc., updated the Environmental and Social Impact Assessment (ESIA), Environmental and Social Management Plan (ESMP), and Resettlement Action Plan (RAP). These updates enabled the World Bank to approve £228 million in climate finance, with £74 million (32.5%) directly attributable to CIGZambia. The project will make a vital contribution to improving power trade and resilience of the entire region.

Output 3.2 CIGZambia has integrated GESI and climate considerations into both its technical assistance and client-supported interventions and met the target for FY2024/25. This is evidenced by the adoption of the Social Safeguards Framework in the development of the Environmental and Social Management Plan for the Zambia-Tanzania Interconnector Project and the incorporation of GESI inputs by CIGZambia into the final REMP version.

Notably, CIGZambia continues to demonstrate its agility in knowledge sharing and enhancing visibility of its work and issues in the power sector for instance by representing the Ministry of Energy at the IEEE Power Africa Conference in Johannesburg, where the SSF was showcased. This led to new connections with the IEEE Standards Unit for possible future collaboration on standardising social safeguards. In terms of engagement in national platforms, CIGZambia participated in the annual Zambia Gender Equality Network (ZGEN) meeting, where it delivered a presentation on the SSF, reinforcing its commitment to GESI mainstreaming and stakeholder engagement. These efforts demonstrate CIGZambia’s commitment to embedding inclusive and climate-sensitive approaches across its programming.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes are planned to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

CIGZambia played a key role in the development and rollout of the SSF, approved by Cabinet as part of the Integrated Resource Plan (IRP). However, the framework currently lacks legal enforceability and a formal monitoring mechanism. To address this, CIGZambia initiated discussions with the Zambia Institute for Environmental Management (ZIEM) to integrate social safeguards into Environmental Impact Assessment (EIA) training. A draft MoU is under review to formalise the partnership.

Output Title	Construction of Nakonde One-Stop-Border-Post (OSBP)
Output number:		4	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	Yes, up

Indicator(s)	Milestone(s) for this review	Progress
4.1 Procurement processes for Phase 1 Nakonde OSBP Civil works finalised	Nil (this was reviewed in the last reporting year)	Met expectations: tenders for works & construction supervision were published, evaluated and suppliers contracted.
4.2 Progress towards construction and completion of Phase 1 Nakonde OSBP	Completion of earthworks for access roads	Met expectations: earthworks for access roads were completed.
	Completion of earthworks for truck parking yard	Met expectations: earthworks for truck parking yard were completed.
	Completion of earthworks for buildings	Met expectations: earthworks for buildings were completed.
	Completion of substructures for buildings	Met expectations: substructures for buildings were completed.
	Completion of subgrade layers for road and parking	Moderately below expectation: subbase and base layer for road and parking at 60% completion rate.
	Completion of super structures for buildings	Moderately below expectation: super structures for buildings at 60% completion rate.
	Completion of subbase and base layer for the access road	Moderately below expectation: subbase and base layer for access road are at 40% completion rate.
Additional Milestone added during the year: / 4.3 Progress towards the rehabilitation of Sanitary and Phytosanitary Laboratory including equipping it with diagnostic equipment and power back up system.	Supply, delivery, installation, user training and after sales service of laboratory equipment and reagents for sanitary and phytosanitary maize import compliance.	Met expectations: supply, delivery, installation, user training and after sales services of laboratory equipment and reagents were completed.
	Supply and installation of solar back up system.	Met expectations: supply and installation of solar back up system was completed.
	Contracting and onboarding of temporary technical assistants.	Met expectations: contracting and onboarding of temporary technical assistants was completed.
	Rehabilitation of phytosanitary services laboratory and installation of a water reticulation system.	Met expectations: rehabilitation of phytosanitary services laboratory and installation of a water reticulation system was completed.

Briefly describe the output’s activities and provide supporting narrative for the score.

Nakonde border post remains one of Zambia’s busiest border posts handling approximately 20% in trade volumes which include a bulk of fuel, building materials, food items, chemicals, fertilisers and timber. It is an important regional cargo transiting route with 65% of cargo passing through this facility from Democratic Republic of Congo (DRC) and Zimbabwe destined for other countries. The border post is also an important passage for trade in grain especially with the surge in maize imports from neighbouring Tanzania in response to drought induced domestic shortfalls during the reporting period. The border post is only second to Chirundu border post in terms of revenue generation with capacity to rise to three times the current revenue once fully developed and interfaced with the upgraded border facility on the Tanzania’s side - also funded by FCDO in 2021.

To facilitate increased trade flows and volumes across countries, including turnaround time for grain imports, the Nakonde project aims to reduce time and cost of crossing the border and ensuring imported food is safe from disease contamination. The upgrade of the border post is being funded by three development partners which include the World Bank’s support on the core border post under the TRACER programme, the African Development Bank which has supportted a bypass road and the FCDO funded element amounting to £11m of the project will upgrade the cargo scanner route for trucks with its associated infrastructure including the sanitary and phytosanitary laboratory - equipping it with diagnostic equipment and power back up system.

Having successfully completed the preparatory works in 23/24 reporting period, Trademark made significant progress with implementation works for the project during the 24/25 reporting period. Milestones on the completion of subgrade layers for roads and truck parking yard, super structures for buildings and subbase and base layer for access road were moderately delayed and assessed at around 53% completion rate at the time of reporting. The delays were attributed to reworks and downtime caused by heavy rains on site as well as the protracted conclusion to the issue of PAPs. Between October 2024 and March 2024, 77 out of 182 days experienced rainfall totalling to 834mm. However, a number of significant milestones were met which included earthworks and substructures for access roads, truck parking yard and buildings. The project successfully advocated for additional budget and a time extension with completion due on the 30th June.

During the course of the year an additional project was added to support emergency importation of Maize due to drought conditions in Zambia – justifying an A+ score for this indicator. An additional indicator was introduced to the log frame during the reporting period to measure progress towards the rehabilitation of the Nakonde border phytosanitary laboratory, installation of a power back up system and equipping the lab with the requisite diagnostic equipment. TradeMark managed to meet all the milestones under this indicator which included the supply, delivery, installation, user training and after sales service of laboratory equipment and reagents for sanitary and phytosanitary maize import compliance. Additional milestones met were supply and installation of solar back up system, contracting and onboarding of temporary technical lab assistants, rehabilitation of phytosanitary services laboratory and installation of a water reticulation system.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

During the reporting period a three-month delay was caused by slow relocation of Project Affected Persons leading to late site possession by the contractor. This was outside the control of TMA and justified a revision of the milestone timings.

Following the outcomes of a design review process which was triggered by insights from the actual traffic counts, site specific analyses the need for architectural and engineering variations were identified leading to an overall project addendum to increase and realign the project scope. While the log frame output indicator remained the same, the end target milestones were moved to next reporting period supported by an approved additional budget.
In FY 24/25, Zambia’s maize imports surged in response to drought-induced domestic shortfalls and Nakonde OSBP emerged as an important lifeline for trade in grain, especially, maize. This gave rise to a justifying need to enhance testing and infrastructure capacity of the sanitary and phytosanitary services laboratory to prevent disease contamination and reduce turnaround time. An additional indicator related to this intervention was included and assessed in the log frame.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Previous AR recommendations recommended that Trademark ensure thorough due diligence assessments on prospective winning bidders. Trademark’s procurement policy requires a due diligence be carried out on a prospective winning bidder which has not worked with them before.

The progress on this recommendation is encouraging as Trademark have been subjecting all bidders to desk-based reviews using subscribed databases from CSI – a financial crimes screening application and World PEP KYC electronic screening system. Further, Trademark has now upgraded enlisted services from a fraud screening management system called Lexis Nexis.

Trademark’s approach to resolving site issues with the local government leadership proved to be efficient demonstrating a strong ability to resolve issues in as prompt a manner as possible. For instance, instead of using the bureaucratic process of engaging the mother ministries to relocate utility services on site, Trademark approached the utilities companies directly cutting down on the time spent.

During the year under review, Trademark also demonstrate the ability to quickly take on and absorb an emergency maize testing project in an efficient and effective manner including conducting a design review exercise prompting an addendum to the original budget which was commendable.

While Trademark used workaround approach to resolving Nakonde site issues, they would need to shift their approach to formal stakeholder engagement and influencing for the new trade facilitation programme. Trademark seemed to have not consolidated their relationship with relevant government counterparts well enough to get seamless buy-in for the future trade facilitation programme in the year. To have improved traction and impact, the new programme should adapt to ‘coalitions for change’ approach. The recommendation therefore is for:

- Trademark to develop a systematic relationship with key stakeholders, including the Ministry of Commerce and Trade, a Ministry in charge of Trade facilitation programmes to ensure quick buy-in of planned programmes and implementation model.
- Trademark to identify reform-minded local leaders in government, civil society and the private sector and build informal coalitions around specific policy or service delivery challenges. Using political economy analysis to understand the incentives, power dynamics and institutional barriers to reform is critical while adopting a flexible, adaptive management style allowing for learning with an ultimate focus on measurable policy or institutional change and not simply activities or outputs.

Output Title	Installation of Nakonde One-Stop-Border-Post Cargo Scanner
Output number:		5	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	Yes, up

Indicator(s)	Milestone(s) for this review	Progress
5.1 Progress towards installation of the cargo scanner at Nakonde OSBP	Nil (this was reviewed in the last reporting year)	Met expectation: The tender for supply of the cargo scanner was published in the last reporting period.
	Nil (this was reviewed in the last reporting year)	Met expectation: The evaluation of bids for the tender to supply cargo scanner was completed in the last reporting period.
	Scanner manufacturing and factory inspection	Met expectation: Scanner manufacturing and factory inspection was completed.
	Shipment and delivery of the scanner to the site	Met expectation: Shipment and delivery of the scanner to the site.
	Commerce installation of the scanner	Output moderately did not meet expectation: Installation has been delayed due to ongoing construction of scanner shed and control room.
5.2 Number of Border official trained on OSBP procedures and scanner operations	Training of cargo scanner maintenance engineer	Output moderately did not meet expectation: Training has been delayed due to delays of installation works at site.
5.3 Progress towards installation of IT facilities and equipment in the New Buildings	Prioritisation of ZRA IT equipment needs	Met expectation: Following design review of all ICT equipment in the civils contract, gaps were identified and prioritised in consultation with ZRA.

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall progress remains on track with some milestones particularly on operator training, completion on installation and commissioning of the scanner pushed to the next reporting period.

A review of ICT facility requirements was carried out in the period under review where additional ICT components were identified. It was further noted that some of the specifications for ICT equipment and accessories were outdated and, in this regard, the contractor has since reviewed and initiated procurement of ICT facilities. Arising from the review was additional budget and time extension to June 2025 to complete scanner and ICT installation to account for the delays.

Trademark was initially delayed in commencing the installation of the scanner due delays to the main contractor mobilisation. As a result, training of four border officials on advanced maintenance operations was postponed also as they were expected to participate in the installation process. However, Trademark successfully coordinated for a factory inspection check with government counterparts at manufacture’s site and confirmed the shipment and delivery of the cargo scanner.

The ICT installation proposes to interface with the customs management system in Zambia and subsequent connectivity with Tanzania customs and port systems aiming to facilitate timely and seamless capture and sharing of data and images for analysis and decision making by all involved in customs and security controls. Interfacing eliminates the need for manual handling of images which are prone to delays and forgeries. Officers operating the scanner will no longer be required to print and upload results into the customs system (ASYCUDA) as it will be done automatically. This will in turn expedite the clearance of the scanned vehicles as results will be easily interpreted.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The overall output in tracking progress on installation of the Nakonde OSBP remains the same as in the previous AR with only some milestones targets which include those of operator training, completion of installation of ICT and commissioning of the scanner being pushed to the next reporting period. The decision arose from the delays on civils contractor mobilisation and ICT review whose outcome justified the need to have an extended period for additional ICT works and complete installation and testing of the scanner.

It is recommended for Trademark to consider developing new indicators that build upon the upgrade of the Nakonde border post to enhance the broader trade facilitation environment.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

In the previous AR, a recommendation was made for Trademark to ensure efficient necessary preparatory works are concluded promptly. Initial procurement outcomes revealed unforeseen shortfalls in the estimated budgets from the actual bid amounts for the cargo scanner showing the importance of pre-project planning; comprehensive market research and benchmarking, including prompt resolution of land acquisition processes.

The addendum in December 2024 that Trademark undertook demonstrated good progress on reliable market benchmarking efforts, quick budget absorption ability including the delivery of an emergency testing project that emerged. This is a clear demonstration of improved pre-planning efforts.

The delays in site mobilisation and implementation of works by the civil contractor for the cargo scanner could be sign that they were not a strong fit for the job as Trademark engaged in a number of corrective measures.

Output Title	ZTIP: Preparatory works and technical assistance towards the Zambia-Tanzania Interconnector Project, managed by the World Bank, to improve regional power trade are completed
Output number:		6	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	New

Indicator(s)	Milestone(s) for this review	Progress
Completion of targeted preparatory works	Recruitment of Owner's Engineer / Project Appraisal approval / ZTIP Board approval / Completion of the issuance of EPC [5]package 1 and 2	100% completion for all
[5] EPC is the Engineering Procurement & Construction Contract

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 6: All milestones have been successfully met, laying a strong foundation for implementation of the Zambia-Tanzania Interconnector Project and positioning Zambia to benefit from regional energy trading and enhanced energy security. The UK gained considerable visibility for its role in co-funding the project during the launch event and in subsequent high-level meetings with government, including anchoring a new Zambia-Tanzania renewable energy MoU

Recruitment of Owner’s Engineer (OE): The contract for the Owner’s Engineer was awarded to Swedish firm, SWECO, and signed on 31 October 2024, becoming effective on 10 January 2025. This forms part of the UK’s £4 million technical assistance to ZESCO, aimed at building the utility’s capability to supervise project delivery and mitigate implementation risks. SWECO conducted an inception site familiarisation visit between 31 January and 6 February, and submitted a draft inception report to ZESCO on 5 March 2025, which was reviewed by the World Bank. Adequate field presence from SWECO’s key personnel is expected to support ZESCO’s Project Implementation Unit (PIU), while recruitment of an individual consultant for Detailed Voltage Stability Devices (DVSDs) is underway. The draft Terms of Reference for this consultant were submitted to the Bank for no-objection.

Project Appraisal Approval: Project appraisal was successfully achieved on 24 November 2024. This marked a key preparatory step towards implementation, following a comprehensive assessment of technical design, safeguards, financial viability, and readiness criteria. Appraisal unlocked internal clearance and paved the way for Board-level consideration.

ZTIP Board Approval: On 22 January 2025, the World Bank Board approved Phase 1 of the Multiphase Programmatic Approach (MPA) for the Zambia–Tanzania Interconnector Project (RETRADE–Zambia), with a total International Development Association (IDA) financing of US$245 million. This was a critical milestone that enabled signing of the financing agreement with the Government of Zambia and formal declaration of project effectiveness. The approval included co-financing from the European Union and FCDO (through ESMAP).

Completion of EPC Package Issuance: The project achieved timely issuance of the first two contract packages under Component 1, which will finalise Zambia’s segment of the 330kV Zambia–Tanzania–Kenya (ZTK) Interconnector. This will complete the 913 km northeastern branch of the country’s transmission backbone. Site visits and pre-bid meetings were successfully held on 18–19 March 2025 with interested bidders.

- Package 1: entails design, supply and installation of the 186km Pensulo–Mpika 330kV overhead transmission line (OHTL), along with associated substation works at Pensulo and Mpika, was issued on 3 March 2025
- Package 2: entails design, supply and installation of the 200km Mpika–Kasama 330kV OHTL, including substation works at Mpika and Kasama, was issued on 5 March 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review. None are planned for the year ahead.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead Encourage documentation of lessons learnt to inform future phases and transmission investments under the Green Growth Compact.

Output Title	ACELI Africa: Mobilising investment for job-creating agri-SMEs ($15k-$1.75M ticket size), through (1) financial risk-sharing and (2) technical assistance to businesses and local/regional financial institutions
Output number:		7	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	New Output

Indicator(s)	Milestone(s) for this review	Progress
7.1 Number of businesses receiving technical assistance (cumulative) / This indicator includes disaggregated targets on (a) gender inclusive businesses and (b) climate change purposes	Total businesses receiving TA: 20	Output moderately exceeded expectation: 27 (135%)
	Total businesses receiving TA that are gender inclusive: 10	Output moderately did not meet expectation:09 (90%)
	Total businesses receiving TA that are climate resilient: 05	Outputs moderately exceeded expectation / :09 (180%)
7.2 Number of financial institutions actively lending in partnership with Aceli (cumulative)	Number of accredited lenders: 04	Output moderately exceeded expectation: 06 (150%)
	Number of lenders receiving gender lens investing capacity building:01	Output did not meet expectation:00
7.4 Number of loans approved as a result of Aceli's financial incentives (cumulative) / This indicator includes disaggregated targets on (a) gender inclusive businesses and (b) climate change purposes	Total loans registered:30	Output met expectation :32 (107%)
	Loans registered to gender inclusive businesses: 15	Outputs substantially did not meet expectation: 08 (53%)
	Loans registered for climate change purposes:08	Output substantially exceeded expectation: 16 (200%) : 16 (%)

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Output indicator 7.1: The output activities included building capacity (Technical Assistance) to eligible Agri-SMEs in business management and investment readiness. Aceli exceeded the target relating to the indicator that measures the number of Agri-SMEs receiving TA. A total of 20 businesses were targeted, but Aceli successfully managed to offer TA to a total of 27 businesses, a 135% achievement.
On the number of businesses receiving TA that is gender inclusive, Aceli prioritized inclusivity from the outset of the Technical Assistance (TA) program by designing selection criteria that actively encouraged the participation of women-owned SMEs and supported businesses creating positive impact for women. As a result, 10 women-owned businesses were targeted and onboarded into the program, 9 out of the 10 completed the full cycle. This affected the results achieved, hence 93% achievement. On the number of businesses receiving TA that are climate resilient, Aceli had planned to offer TA to 5 businesses but achieved 9 businesses, 180% over achievement.
The TA ensured that Agri-SMEs received assistance to improve their creditworthiness, operational efficiency, and long-term financial stability, and ultimately enhancing their access to critical financing and credit.
Output 7.2: The output activities included recruiting and accrediting financial institutions to the Aceli incentive program and lenders actively lending in partnership with Aceli. The total number of financial institutions accredited to the Aceli incentive program achieved was 6 compared to the planned 4, a 150% achievement. These lender partnerships are crucial in increasing access to finance for agribusinesses, and further strengthen the ecosystem for SME agricultural financing
Output 7.3: The output activity included building capacity to financial institutions. The indicator relates to the number of financial institutions receiving capacity building through Aceli support. Aceli did not plan on offering capacity building to lenders in FY 2024/25 as they were looking to first activate lending and therefore did not achieve anything in the year under review.
 On the number of lenders receiving gender lens investing capacity building, Aceli initiated the onboarding process for 1 lender into the Gender Capacity Building Program. However, the lender was unable to proceed due to limited personnel availability to actively engage in the program. There are plans however, to re-engage the lender, along with others, for participation in the 2025/26 cohort.
Output 7.4: This output indicator measures the number of loans registered by lenders in Zambia and approved to receive incentives. Aceli had planned to register a total of 30 loans and had focused its efforts on promoting more inclusive lending among partner lenders by conducting refresher trainings on the incentive program and the loan registration process with Aceli. 32 loans translating to 107% achievement, were registered out of the 30 planned and about 9 were still in the approval pipeline, pending the submission of required documentation from the lenders. On the number of loans registered to gender inclusive businesses, Aceli had planned for 15 and only achieved 8, a 53% achievement rate. Aceli had also targeted a total of 8 loans registered for climate change purposes and achieved 16 instead, an overachievement of 200%.
Some of the planned milestones could not be achieved during the period under review due to the Aceli model. There is a lag from when loans are initially registered with Aceli by lenders and when they are 1) officially approved and 2) verified by a third party for meeting climate & environment standards. Therefore, the results Aceli presents immediately at the end of a quarter are likely to change as approvals and verifications are executed over proceeding months. The lag was acknowledged, and it was agreed that this lag will not present issues any other time of the year, except when calculating targets for inclusion into the annual review. Aceli has committed to proactively share updates to logframe results as loans are approved and verified after March.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Aceli started implementation of activities in the last quarter of FY2024/25. No changes were made to the output in the year under review and no changes are planned for the coming year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Aceli was added to the PEPZII as a recommendation from the previous 2024 AR and there were no recommendations on Aceli from the previous AR.
In 2024 & 2025 the PEPZ2 programme onboarding additional partners (Aceli, CIGZambia, TMA, and the World Bank) who had a strong track record from previous collaboration with FCDO. FCDO Zambia assigned dedicated project leads which enabled the projects to be integrated into PEPZ2 rapidly and meet FCDO compliance requirements without undue delays. In a future ODA constrained scenario FCDO should build on prior experience and flex existing business cases to take advantage of opportunities that may arise.

E: VALUE FOR MONEY

Key cost drivers and performance

Prospero
Established as a Special Purpose Vehicle (SPV) under PEPZ1, Prospero’s model was designed to provide strategic, locally anchored SME support. While the rationale for SME-focused interventions remains strong, the SPV structure has presented ongoing challenges. The complexity and cost of the model have reduced its economy and required substantial FCDO oversight. In the year under review, a full VFM analysis was not conducted as funds were limited to salaries and overheads. Below are some key findings of the sustainability review, a detailed VfM report is annexed in the Programme Completion Report (PCR).
Operating Costs and Delivery Model:
Prospero’s SPV model has led to high operating costs due to complex governance, bespoke systems, and a large internal team. Board fees were once up to 3% of the annual budget but have since been reduced. High staffing costs stem from the need for in-house expertise to manage grants and performance.

Governance and Strategic Direction:
Dual accountability between the FCDO and the Board has caused strategic inefficiencies. Board members, mainly from the private sector, have lacked development expertise, limiting strategic guidance. The Investment Committee has focused more on financial returns than developmental goals, misaligning with Prospero’s dual mandate.

Sustainability and Strategic Outlook:
Achieving financial self-sufficiency through investments has been challenging due to the risks of supporting early-stage SMEs. Attempts to diversify income have had mixed success
CIGZambia

Against the 4Es framework, CIGZambia has made a significant contribution to reforms in the energy sector, delivering results with a budget of £2.3 million during the review period.

- Economy: CIGZambia has delivered strong VfM by achieving cost savings on consultant day rates across most expert levels, compared to the FCDO Rate Card. Sharing key resources with the GCIP, CCG and Supporting Preparedness for Article 6 Cooperation (SPAR6C) programmes respectively, has also enabled the project to achieve cost savings to the tune of £164k while collaboratively producing deliverables. Additional savings were realised through strategic accommodation planning—achieving reductions of 11% in Lusaka and up to 30% outside Lusaka by securing corporate rates in advance and limiting non-essential travel. Project Management Unit (PMU) costs were maintained at 20% of the allocated budget—below the planned 28%—a level that is favourable compared to similar programmes and represents good value for money for FCDO.
- Efficiency: CIGZambia maximises efficiency by prioritising local procurement and leveraging internal and pre-approved expert pools. During the year under review, 58% of the 19 key procurements were awarded to Zambian-based suppliers, reducing costs and supporting local capacity. The use of in-house expertise and restricted pools of vetted consultants further streamlines delivery and ensures quality. Strategic partnerships with institutions such as CCG, Strathclyde, and USAID have enhanced data management and project implementation. For example, collaboration with CCG ensures strong control of core data and efficiency through shared resources and expertise.

Effectiveness: CIGZambia has effectively supported key reforms by facilitating the contracting of WSP to update the ESIA and ESMP for the ZTI project—unlocking access to $200 million in regional funding for ZESCO. The programme also advanced implementation of the Integrated Resource Plan through a joint governance structure endorsed by the Ministry of Energy. Key initiatives, including the Energy Storage Research activity and ISMO, have strengthened national energy planning. CIGZambia’s adaptive management approach enables regular review and adjustment of project design and delivery, ensuring responsiveness to evolving needs and continuous improvement through learning and evaluation. Lower effectiveness was achieved on the Strategic Thought Leadership workstream which has not been sufficiently focussed on immediate opportunities to influence positive reforms despite considerable effort to scope future interventions.

Equity considerations are embedded throughout the project, ensuring that benefits reach marginalised and underserved groups. Gender and inclusion principles are reflected in programme design, delivery, and monitoring. Of the 33 staff and consultants currently engaged on CIGZambia, 61% are men and 39% women. Although some technical roles in energy and engineering tend to be more challenging to recruit qualified women, the programme has made steady progress in improving gender representation. Female participation has increased from 28% in years 1 and 2, to 35% in year 3, and 39% in the current year. The PMU team comprised 20% men and 80% women, and CIGZambia continues to take proactive steps to further improve gender balance across the project.

Additionally, CIGZambia has worked closely with the WSP Canada to integrate the Social Safeguard Framework (SSF) into the revised Environmental and Social Impact Assessment (ESIA) and Environmental and Social Management Plan (ESMP)—including embedding these standards into procurement documents for the Owner’s Engineer for the Zambia-Tanzania Interconnector (ZTI) project. These efforts have also supported the internal implementation of the SSF within ZTI, helping ensure that marginalised communities in the project area are protected and supported.
Trademark Africa

Trademark’s Nakonde project performed well against 4E’s. Economy was achieved through competitive tendering for all major work packages to ensure the lowest compliant prices. A design review was completed to make sure the project was still fit for purpose and that the initial design assumptions, environment and market conditions still held. During the project review, Trademark adapted the design further to the conditions and makes savings. For instance, it became apparent that the persistent heavy rains that continued to impact construction activities into late March 2025 would lead to project delays, reworks and additional project costs. As a mitigation measure, Trademark proposed for a change in material use for the truck parking yard from cement stabilised subbase layer which could not be done in the rain season to crushed stones layer saving on $166k in costs.

Trademark’s approach in getting site issues resolved quickly leveraging on relationships at local government and stakeholder level rather than using the long bureaucratic processes was a demonstration of efficiency. For example Trademark initiated joint material monitoring measurements with the contractor and technical teams from the government before payment certificates were approved. At the tail end of the project moving over into next FY, there has been increased and constant monitoring of the project by Trademark team to avoid any slippage beyond the new end date.

Once completed the project is expected to reduce the time required for trucks to cross the border from 60hours to 10hours, resulting in annual economic benefit of approximately $90m, which far exceeds the total intervention cost of $14m and demonstrates high effectiveness.

With regards to equity consideration, Trademark ensured that a greater proportion of the workforce at around 54% was recruited within Nakonde to cater for the locals and marginalised communities. Due to the nature of work, only 14% of the total workforce constituted women as it was labour intensive and required night shift operations. Trademark followed their Safeguarding and Social guidelines closely ensuring dust suppression was maintained and air quality was at the required standard including waste management. Safety and safeguarding measures were consistently monitored and adhered to as minimal number of incidences were recorded and followed up including raising HIV/awareness in the surrounding communities.

The Zambia-Tanzania Interconnector Project (ZTIP) is a large-scale, capital-intensive regional infrastructure investment, with key cost drivers including high-voltage transmission line construction across remote terrain, substation upgrades, specialist technical expertise (such as Owner’s Engineer and environmental and social safeguards specialists), procurement of quality-assured materials, and adherence to international environmental and social standards.

Applying the 4Es VfM framework, the programme demonstrates economy through competitive procurement processes managed by the World Bank and ZESCO, ensuring quality inputs at the best possible price. It has promoted efficiency by aligning technical assistance and infrastructure financing under one coordinated platform, enabling streamlined decision-making and reduced transaction costs. Effectiveness is ensured by targeting a key regional energy gap—connecting the Southern and Eastern African Power Pools—and unlocking access to Tanzania’s 2GW Julius Nyerere Hydropower Project, thus addressing Zambia’s acute energy shortages and supporting mining sector expansion. Finally, the programme embeds equity by including social safeguards (RAP, ESMP) and ensuring communities affected by transmission routes are adequately consulted, compensated, and supported—ensuring the benefits of power infrastructure development are shared more inclusively.

ACELI Africa: Considering the 4Es framework:
Economy
The Aceli incentives model is a streamlined and cost-effective approach to increasing financial access for agricultural SMEs. It consists of three core components.
- First, Portfolio First-Loss Coverage offers lenders 2–9% coverage at the portfolio level for loans between $10,000 and $1.75 million. This mechanism helps absorb the additional risk of lending to underserved SMEs while ensuring lenders remain financially invested. Lenders accumulate funds in a reserve account for each loan that meets specific impact criteria, such as supporting food crop value chains or first-time borrowers.
- Second, Origination Incentives compensate lenders for the lower profitability and higher operational costs associated with smaller loans ($25K–$500K), particularly to early-stage SMEs. To further promote inclusion, Aceli has reduced the minimum loan size to $10K for women- and youth-owned businesses.
- Third, Impact Bonuses enhance the incentives for loans that deliver elevated social and environmental benefits—such as improving food security, empowering women and youth, or promoting climate resilience. The total combined incentive a lender can earn is capped at 9%. To ensure effective implementation, Aceli also conducts regular training sessions for lenders, helping them understand the benefits and processes of the incentive model.
Taken together the interventions offer a leverage ratio of over 1:10 which represents good economy relative to comparable programmes.

Efficiency: The efficiency of the Aceli programme hinges on the participation of accredited lenders, which Aceli does not directly control. As of March 2025, the number of accredited financial institutions in its network grew from four in 2024 (Absa, EFC, FNB, and Zanaco) to six, with the addition of Agleaseco and ZICB—exceeding the initial target. Promising discussions are also underway with Stanbic Bank and Indo Zambia Bank, both of which have strong agricultural finance capabilities. Once accredited, these banks are expected to significantly boost loan registrations and improve SME access to finance. Together, these eight institutions represent the bulk of agricultural lending in Zambia, highlighting the potential for widespread impact.

Effectiveness: Aceli has successfully facilitated a total of 16 loans verified/approved with an additional 27 loans currently undergoing internal review and approval. This brings the cumulative total to 43 loans disbursed as of March 2025. Of the 16 loans booked by Aceli 5 are gender inclusive and 7 are climate change purpose. At this stage the SMEs are mainly returning borrowers to the commercial bank's portfolio, as the project matures it is expected that the proportion of first-time borrowers will increase. As the Aceli model is in its infancy stages, we have not been able to measure the growth in revenues for repeat SME borrowers to the Aceli model, however, the model is suitable to measure this indicator successfully by the next annual financial reporting of the SME businesses.

Equity: The Aceli results indicators are disaggregated by gender and climate. $4,566,147 total investment has been mobilized against a planned investment of $5,250,000, representing an 87% achievement. Of this the Investment mobilized for gender inclusivity is $2,137,672 against the planned investment of $2,625,000, representing 81.4% achievement. Investment mobilized for climate change purposes were planned at $1,312,500 and have been achieved at $3,337,672, which is 254% achievement.
VfM performance compared to the original VfM proposition in the business case

Prospero: The 2024 Prospero sustainability assessment reviewed that Prospero demonstrated strong effectiveness and moderate efficiency in delivering SME support and leveraging investment. However, the SPV model has proven costly and complex, undermining economy and requiring significant FCDO oversight so did not meet the Value of Money proposition in the business case. FCDO took the decision to withdraw from Prospero and ceased to fund it from the 31st March 2025 (apart from final external audit costs which continue into FY25/26)

CIGZambia: CIGZambia remains one of FCDO’s most impactful technical assistance programmes, playing a critical role in unlocking the power needed to support Zambia’s energy reforms and the UK’s mining pipeline. The programme continues to deliver strategic value and innovation, particularly through its support to ZESCO on financial modelling and investment decision-making, playing a pivotal role in securing World Bank funding for the Zambia-Tanzania Interconnector and shaping the future of Zambia’s electricity market while fostering alignment across key donor partners.

Trademark: During the implementation period under review, Trademark demonstrated a strong adherence to the VFM considerations in progressing with the Nakonde border construction despite the challenging circumstances such as persistent heavy rains and procurement delays. With some flexibility on FCDO’s budget allocation for the next FY, Trademark proactively realigned project components and agreed an extended end date to account for the delays caused by heavy rains and late site handover due to the protracted process of relocating the project affected persons. In this regard, the project remains largely on track to achieve its log-frame targets and meet the VFM propositions of the business case.

The Zambia-Tanzania Interconnector Project (ZTIP): The drought and power crisis in 2024 provided strong evidence that implementing the ZTIP project continues to offer good value for money. Had the interconnector been in operation Zambia would have been able to avert considerable economic damage across the country by importing power from Tanzania where good rains meant that it had a such a large power surplus that it turned off their hydro-electric plants.

ACELI: During the period under review, Aceli has demonstrated an effective approach to VfM, providing sufficient evidence and assurance of results and plans for further growth to continue given its infancy stage. The project continues to provide value for money with effective programme management and an evidenced incentivised model that catalyses financing to the SMEs in Agriculture.

Assessment of whether the programme continues to represent value for money

During the year, the programme demonstrated strong evidence of achieving value for money and that assurance that monitoring and learning processes are effective at continuing to maintain value for money going forward.
E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The PEPZ II programme maintains an overall risk rating of major, consistent with the previous annual review. Risk management is embedded across multiple levels of programme governance. Internally, risks are regularly reviewed through monthly internal board meetings between the Senior Responsible Owner (SRO) and programme staff, office-wide monthly programme finance meetings, and quarterly scrutiny board sessions.

At the delivery level, risk is a standing agenda item in monthly and quarterly progress meetings with implementing partners. For Prospero specifically, the programme also maintains quarterly updates of delivery chain risk maps and conducts annual fraud risk assessments to ensure continued oversight and mitigation.

Since the last annual review, the appetite for some of the seven risk categories have changed or not to align with the FCDO Zambia risk appetite and are detailed below;

Category	Appetite 2024	Appetite 2025
Strategy and Context	Receptive	Receptive
Policy & Prog delivery	Receptive	Receptive
People	Cautious	Cautious
Financial and Fiduciary	Cautious	Cautious
Reputational	Cautious	Cautious
Safeguarding	Cautious	Cautious

Key programme risks during in the reporting year:

Prospero

Risks during FCDO withdrawal from Prospero: The transition period presented several risks including financial, reputation and delivery related risks. FDCO developed a comprehensive transition and fraud response plan to closely monitor and manage these challenges. Local legal advice was procured to ensure that FCDO’s exit from Prospero SPV was conducted in full compliance with legal obligations and responsibilities. In addition, the most critical communications between FCDO and Prospero was subjected to legal review prior to issuance.

Financial Management: Weaknesses in Prospero financial management continued even during the transitional phase. These were largely due to the staff turnover in the finance department which negatively affected the quality of financial reporting. Additionally, the audited statements for the year ending Marh 2024 significantly delayed posing risks that exceeded FCDO risk tolerance.

Policy and programme delivery: Another risk that emerged was staff turnover due to uncertainties caused by FCDO withdraw from the SPV. This remained a critical challenge as departures of key staff from the investment and Finance teams disrupted continuity and hindered progress during the transition period. To mitigate both financial and delivery risks, FCDO contracted an external firm to manage Prospero’s financials and HR function which has largely been successful at keeping risk with appetite.

CIGZambia

Leadership transitions and staff exits: There was a risk that the changes at Project leadership level and the exit of three personnel including an Energy Modelling specialist (with very niche experience, the Project Delivery manager and M&E Adviser, and the Communications Consultant will impact on the project delivery. This risk did not materialise as CIGZambia actively recruited new personnel and re-allocated key tasks to existing personnel within the organisation to reduce task slippage and foster continuity.
Context and programme delivery: During the reporting year, the Government of Zambia faced significant pressure to respond to an escalating energy crisis, which diverted attention and political capital away from longer-term structural reforms. This created a challenging environment for progressing sector reforms, with competing priorities and fragmented decision-making. To remain effective in this context, CIG should continue to strengthen its political economy analysis to better anticipate and navigate vested interests and institutional constraints in the energy sector. This will help the programme identify practical entry points and capitalise on moments of political alignment to drive forward reform.
The environmental and social safeguards component under the ZTIP experienced scope expansion and time pressures, creating a funding risk. This was mitigated by securing rapid additional financing from FCDO after the USAID ESA shutdown, ensuring biodiversity surveys proceeded without major delay.
Anticipated risks in the year ahead: Programme and project delivery: the complexity and scale of ISMO implementation poses significant risks related to institutional restructuring and multi-stakeholder alignment. This requires continuous engagement with key actors (MoE, ZESCO, ERB, IDC) and adaptive planning to ensure reform momentum is maintained.
Financial and fiduciary: with low UK budgets going forward, coupled with the dismantling of USAID that had committed to funding legal and regulatory reform in the power sector, key workstreams face a funding risk in FY25/26. If a substantial budget allocation is not secured, CIGZambia will need to reprioritise activities to align with available resources while preserving core outputs.
Trademark Africa

TradeMark’s large capital disbursal target in FY24/25 was a significant risk during the period under review. This meant that Trademark needed to significantly progress all project milestones within the one-year timeframe to avoid any slippage into the next FY. Major risks were late handover of site to the contractor due to government delays in relocating the project affected persons and delays caused by persistent heavy rainfall. Fortunately, there was some flexibility in UK Government’s spending round to minimise carry over of funding to the next FY. Trademark managed this risk well, completing most of the activities within the financial year, with some project components rescheduled to the next FY.

The project Fiduciary, Reputational and Safeguarding risks were moderate during the period under review with some cases of safeguarding and harassment allegations reported that were managed according to standard processes. Tragically there were three fatalities caused by an off-site road traffic accident between one of the contractor’s trucks and a private motorcycle. The case was closely monitored by TMA as it progressed to court where the driver was found culpable for dangerous driving. TMA and the contractor continue to follow up on the case. Fraudulent activities by partner and contractor posed a risk to timely delivery and quality work but the joint material measurement approach which included government technical teams to endorsing payment certificates was an effective way of circumventing the risk.

Anticipated risks in the year ahead:

- The risk of TMA not delivering its planned activities in FY25/26 is high as there appears to be a protracted iterative process between Trademark and the relevant government Ministry to agree the proposed interventions.
- To mitigate this risk, FCDO is closing monitoring progress and challenging Trademark to update on the realistic scope of activities for the year ahead.
- The project Fiduciary, Reputational and Safeguarding risks are moderate as Trademark will leverage on the already established networks, systems and guidance from other partners implementing in a similar space. Further assessment will be needed during implementation as risks could exceed the project risk appetite -this will be monitored closely by FCDO and Trademark.
- The possible delay in onboarding new staff, any staff movements and setting up an office in-country could impact the effective delivery of the new programme. TMA has in place thematic leads who will provide support during the transition phase and programme implementation.
The Zambia-Tanzania Interconnector Project (ZTIP) UK funding is managed by the World Bank who apply the same risk management processes as apply to the larger IDA grant. Key risks during the year were delays completing the update of the Environmental Social Framework, which was mitigated by focused delivery from CIGZambia.

ACELI Africa
Aceli’s programme delivery faces several operational and strategic risks, particularly in influencing lender behaviour and ensuring inclusive SME support. Aceli’s partnership with Kudu Consulting to provide technical assistance (TA) to 27 SMEs is a positive step, though the reliance on virtual sessions raises concerns about excluding SMEs in areas with limited internet access.

On the regulatory front, Aceli Africa is not yet legally registered in Zambia. It is however, completely compliant to be operating in Zambia and have no compliance or tax risk due to their current structure. However, the organization is actively pursuing legal registration to mitigate compliance related concerns. Financially, Aceli experienced delays in receiving funds from FCDO in December 2024, creating a risk of under delivery due to the shortened implementation window.
To manage safeguarding risk Aceli rigorously screens partners to ensure they uphold ethical standards. Aceli is not involved in SME vetting, there is a risk of banks approving ineligible SMEs to access incentives. This is being addressed through Aceli’s independent verification process before disbursing any lender incentives.

Other risks include challenges in accurately measuring impact—particularly on gender and employment—since data is collected only at the outset via ESG forms. The absence of an in-country Monitoring and Evaluation (M&E) officer poses a delivery capacity risk, as M&E is managed remotely from Kenya. However, all Aceli countries of operations are managed by the same M&E/Impact team domiciled in Kenya and hiring an M&E team member in Zambia would create duplicative work. The field visit also revealed difficulties in verifying job creation claims as the methodology used was based on regional sampled figures and not the actual jobs created in Zambia. As the Aceli scales up its programme in Zambia it expects to be able able to sample figures from within Zambia and not rely on regional estimates. The FCDO MEL adviser will continue to engage closely with Aceli, to get further assurance on the rigour of the results reporting.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

Programme delivery

The programme is overseen by a Senior Responsible Owner (SRO), supported by a PSD Adviser and four Project Leads, each closely managing the day-to-day operations with individual suppliers. Strong working relationships between the programme team and implementing partners were central to the programmes’ success with regular communication and oversight helping to keep delivery on track and responsive to emerging issues. Throughout the year the team reviewed monthly financial forecasts, quarterly progress reports, funding requests, and invoices and maintained accurate records and updates across internal FCDO systems consistently. Monthly internal board meetings chaired by the SRO provided a platform to review delivery progress, financial performance, compliance with the delivery plan and update risk registers ensuring that challenges were identified early and addressed promptly. All invoices underwent thorough scrutiny by the programme team, with mandatory SRO approval required prior to payment processing, ensuring robust financial control.

Prospero: Prospero suffered high staff turnover, the finance department was not spared. This posed a big challenge in financial reporting and compliance with FDCO rules, including the FY 2024/25 audited statement that have delayed. FCDO engaged BGS a consulting firm to support with Prospero financial management and deliver the 2025 audit by June 2025.

CIGZambia: In July 2024, FCDO and CIGZambia signed Contract Amendment 08 (CA08), securing a programme extension through to June 2026. This amendment increased the total budget by £2.87 million, bringing the overall contract value to £16.65 million. Despite significant leadership changes during the reporting period—including transitions at both the Programme Director and Programme Manager levels—the supplier, Cowater, scaled up delivery effectively. Many workstreams reached full implementation, and the programme consistently performed strongly across all contract KPIs and milestones introduced in CA08. Each quarter, the programme earned a performance rating of Fully Achieved (A) and received an 83% score in the most recent Strategic Relationship Management (SRM) assessment. This performance has been supported by the timely onboarding of new delivery managers and the strengthening of the technical team to ensure adequate coordination and management capacity. To accommodate growing operational needs and enhance collaboration, CIGZambia and GCIP jointly relocated to the Agora Africa Works office space in January 2025. Looking ahead, discussions are underway for a potential further contract amendment. Options being considered include a £500,000 budget uplift for the 2026 financial year and a possible time and cost extension that could raise the total budget to £20 million and extend implementation through or beyond 2027.

Trademark Africa: For the Nakonde project, TMA established a small office in Lusaka with one in-country adviser working alongside a project Director in Dar es Salaam and supported by two project staff based in the Malawi office. At Nakonde Trademark was represented by a resident engineer who provided day-to-day supervisory oversight. The in-country advisor was engaged to handle the project stakeholder engagements and contract management processes. The technical aspects of the project were handled through the respective subcommittees on ICT, Civil works and cargo scanner focusing on assessing project implementation progress, identifying risks and mitigation measures. Two project steering committee meetings comprising relevant heads of government departments were held during the review period. The Trademark project team updates FCDO in fortnightly meetings during which emerging risks, safeguarding issues and financial reporting are a standing agenda.
ZTIP: The World Bank has a strong track record of delivering FCDO programmes in Zambia and beyond. Following central and local due diligence assessments, FCDO signed a £15 million financing agreement with the WB to implement the Zambia-Tanzania Interconnector Project (ZTIP). The funds, disbursed from the PEPZ II programme in FY24/25, are administered through the World Bank’s Energy Sector Management Assistance Programme (ESMAP) under the ASET (Accelerating Sustainable Energy Transition) window of the Umbrella 2.0 Multi-Donor Trust Fund. ZESCO remains the lead implementing agency, with the World Bank providing oversight. As a co-financier, FCDO engages regularly with the Bank—initially bi-weekly and now quarterly—to monitor implementation and plan next steps. The Bank team shares progress updates between missions and includes FCDO in key meetings as needed. FCDO participated in the WB’s implementation support mission in Lusaka and project sites from 17–31 March 2025. The project is broadly on track, with the first annual progress reports on FCDO-supported components expected in summer 2025.
Aceli Africa: Aceli has maintained a lean team of two in country personnel supported by colleagues operating in Kenya and USA which is suitable given the budgeted business operations. The Country Director and Business Manager are based in country and run the day-to-day operations and engagements.
Aceli Africa has demonstrated strong compliance and effective delivery of FCDO programmes, as confirmed by a due diligence assessment referencing its operations in Uganda and Tanzania. Aceli Africa, under the Global Development Incubator, signed a two-year £2 million accountable grant with FCDO, with potential for extension based on performance and funding availability. To enhance coordination and streamline reporting across its multi-country operations, Aceli and FCDO agreed to hold quarterly coordination calls and regular check-ins focused on finances, risks, and fraud. Despite a delayed start due to the late signing of the grant in 2024, Aceli Africa has made solid progress, meeting key milestones and staying on track with programme implementation.
Financial and Commercial performance
Prospero: Prospero budget decreased significantly during the review period. Primarily due to suspension of capital expenditure to avoid the creation of financial assets in the final year. Additionally, the Board approved FCDO proposal to utilise cash balances (returns from investments) to cover staff and overhead costs, thereby reducing the need for additional FCDO funding during the final year as a result, FCDO disbursement were further reduced. The initial planned budget of £3.5m was revised to £1,196k following the suspension of CDEL expenses. However, only 38% of the revised budget was ultimately utilised as most salary and operational costs were covered by alternative income sources.
FCDO closely monitored expenditure by reviewing cash balances, forecasts and actual spending, and approved all funds requests accordingly. BGS provided monthly progress reports including progress on finance and human resource functions.

CIGZambia: For the April 2024 to March 2025 financial year, a budget of £2.342 million (100% ICF) was allocated to CIGZambia. By year-end, £2.33 million had been spent, with a minor underspend of £9k. Capital (CDEL) spending increased significantly during the year as activities under the Zambia–Tanzania–Kenya (ZTK) Interconnector, led by WSP and ZESCO, gained momentum. The programme maintained strong financial discipline, with monthly forecasts submitted on time and spending variances kept below 1% as agreed in the KPIs. Notably, project management unit (PMU) costs were reduced to 20% of the total budget, down from 28% the previous year—bringing them in line with comparable FCDO programmes. Additionally, reporting on Technical Assistance Fund categories commenced during this period, in line with the requirements set out in Contract Amendment 08.

Trademark Africa: In FY24/25, a total budget of £10.422m was allocated to Trademark for the implementation of the Nakonde border project out of which £785k was estimated to be potential foreign exchange gains only accessible in FY25/26 for justified additional costs effectively resulting into actual budget of £9.637m for FY24/25. In November 2024, Trademark took on a short-term emergency maize testing project with a budget of £136k which was implemented in the current reporting period. Following the outcomes of a design review process architectural and engineering variations were identified leading to an overall project addendum of an additional £910k in budget. Given the delays from the disruptive weather conditions and initial delays from the protracted site possession by the contractor, it become apparent that the project would not be completed in this reporting period. As a result, FCDO approved a 3-month extension period based on Trademark proposal to realign project components leading to a reallocation of £9.193m in FY24/25 budget and £2.206m for the 3 additional months in the next reporting period.

Of the £9.193m disbursed in FY24/25, £4.687 was disbursed by Trademark with the balance of £4,506 entirely committed in binding contracts and retention. It is expected that Trademark will fully spend the budget allocated after the extended period when the 5% project retention is paid and any exchange rate gains are accounted for.

ZTIP: For the April 2024 to March 2025 financial year, £15 million in capital funding (100% CDEL) was disbursed to the World Bank in two tranches to support the Zambia–Tanzania Interconnector Project (ZTIP). The bulk of the funding - £9.75 million - were (ICF funds). These disbursements primarily facilitated the contracting of the Owner’s Engineer for the projects. Both payments were made following satisfactory assurance from the World Bank confirming the project’s approval status, ensuring alignment with FCDO’s financial assurance protocols.

Aceli Africa: Aceli was allocated a budget of £500k (100% CDEL ICF) for the Dec 2024-March 2025 financial year. FCDO and Global Development Incubator (GDI)/Aceli signed an Accountable Grant (AG) agreement in November 2024. The AG agreement amount was £500,000 (100% CDEL ICF) for December to March 2024. With about £377, 029.0 spent by year end and £122 971.0 recorded as an underspent. The delayed disbursement of funds due to internal compliance processes resulted in Aceli lagging on their timelines on lender engagement, onboarding of lenders and other activities and this resulted in the reported variance.
Capital spending had been relatively slow due to the structure of Aceli’s current accounting system that only allows pay out of incentives to registered loans after the quarter has ended. At the end of the FY, some loans were still awaiting approval.

PEPZ 2 finances FY24/25 (GB £000s)

Project	Resource budget	Capital budget	Total / budget	Resource spend	Capital spend	Total	ICF Spend	Under/over-spend
CIGZambia	1,527	814	2,340	1,526	813	2,333	2,333	9 / (under)
Trademark	648	8,545	9,193	330	4,357	4,687	0	4,506 / (under)
Prospero	1,196	0	1,196	452	0	452	0	744 (under)
ZTIP	0	15,000	15,000	0	15,000	15,000	9,750	0
ACELI Africa	0	500	500	0	377	377	377	123
Procurement of services -Prospero related	179	0	179	179	0	179	0	0
Totals	3,550	11,359	28,408	2,487	20,547	23,028	12,460	5,382 / (under)

Assets management

The FCDO programme team collaborated closely with all partners to update asset registers and conduct physical asset verification. Spot checks were carried out by FCDO to ensure accuracy and accountability. All implementing partners participated in this process, except for ACELI which had not yet procured any programme assets.

Trademark procured essential equipment and rapid test kits to strengthen the diagnostic capacity of the Plant Quarantine and Phytosanitary Services laboratory at the Nakonde border. Among the key items supplied was a PCR machine – critical for the accurate, rapid and sensitive detection of Maize Lethel Necrosis Disease (MLND), particularly Maize Chlorotic Mottle Virus (MCMV). Additionally, equipment included a compound microspore, a centrifuge and three MCMV rapid test strips. Infrastructure upgrades were also undertaken, including the installation of an air conditioning system, a solar power backup solution, and water storage facilities to support uninterrupted laboratory operations. At the time of this review, preparations were underway to formally transfer the procured assets to the Ministry of Agriculture through the PQPS Nakonde laboratory.

As this was Prospero’s final year, the asset management process was notably comprehensive, covering both physical and financial assets. FCDO engaged a consultant to support the valuation of all financial assets and conducted an analysis that helped inform disposal decision. FCDO also maintained close consultation with PMCD and financial accounting, ensuring that all necessary approvals were properly obtained. For physical assets, a comprehensive asset list including depreciation values and net book values was compiled by Prospero, with support from BGS. All asset disposal submissions were reviewed and approved by the Deputy High Commission in line with FCDO guidance.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring

Programme performance and progress were closely monitored throughout the review period using a combination of regular reporting, partner engagement, and field-level verification. Monthly progress meetings between the FCDO programme team and implementing partners provided continuous oversight of delivery, helped identify emerging issues early, and enabled timely course corrections. These were complemented by more in-depth quarterly progress meetings, where results were assessed against log frame indicators and annual milestone targets. Supplier reports submitted quarterly included dedicated monitoring sections, forming the basis for performance discussions. In addition to these meetings, the FCDO team undertook targeted field visits with Aceli to observe implementation on the ground, engage directly with beneficiaries, and verify reported results.

CIG Zambia: In the case of CIGZambia, a beneficiary feedback loop is embedded in the quarterly report with CIGZambia’s clients (MoE/ZESCO) enriching FCDO’s understanding of delivery contexts and helping validate progress claims. Stakeholder engagement—across government, private sector, and civil society—was also a key component of the monitoring approach. These interactions helped triangulate findings, assess relevance and impact, and ensure continued alignment with national development priorities. Together, these monitoring activities enabled responsive, evidence-based programme management throughout the year.
As recommended in the previous Annual Review, CIGZambia updated its capacity-building assessment methodology to enhance relevance and accuracy. The institutional capacity scorecard was removed due to overlap with the more suitable organisational scorecard, whose weighting was increased to reflect the greater emphasis on organisational development. Assessments are now conducted by trainers or MEL staff for a more qualitative approach, and longer training sessions are evaluated as multiple units. These updates have been incorporated into the log frame and scorecard templates, with no changes to the review’s output. Looking ahead, the individual capacity scoring scale is proposed to shift from 0–4 to 0–3, redefining the top score to reflect strong, organized impact, acknowledging that short-term assessments may not capture sustained individual change.

TradeMark: FCDO ensured that Trademark implemented a robust monitoring and oversight mechanism. A resident engineer was stationed on-site to provide daily live updates, which were compiled into comprehensive fortnightly reports/sessions with FCDO and other relevant supervisory teams. Progress claims were validated through live video updates and on-site inspections, often conducted in collaboration with government technical teams. The fortnightly meetings with FCDO offered timely insights into site progress, enabling the early identification of emerging issues. The regular feedback loop made the monitoring approach highly adaptive and response to evolving project conditions.

Aceli Africa has a robust loan management system called Salesforce. However, concerns were raised on lack of accuracy on impact measurement, for example, impact on gender, on new jobs created or on gender sensitivity as measurement was only done once at the beginning when borrowers fill in the Environment, Social and Governance (ESG) form. During the field visit, it was found challenging to verify the new jobs created attributed to Aceli support as the SMEs could only provide information on the total labour force without isolating the new from the old jobs. Aceli Africa does not have an in-country M & E person to systematically monitor progress and share data. The M&E function is managed from Kenya and it wasn't established on how M&E related supportive supervision and results verification is conducted.

Evaluation and Evidence: The PEPZ2 Mid-term review was updated during the AR process and findings incorporated into the AR.

Learning CIGZambia maintain a Lessons Learned Log to encourage ‘pause and reflect’ moments and enable CIGZambia to adapt. This complements key lessons identified by FCDO for the programme and wider development work and include:
- Collaboration boosts Value for Money when priorities are aligned early: The IRP implementation revealed opportunities for efficiency through collaboration—particularly the CIGZambia–GCIP partnership, which helped reduce duplication and improve coordination.
- Realistic timelines are essential where political urgency is high. The ongoing energy crisis has increased demand for rapid delivery. However, setting achievable timelines remains critical to maintaining delivery quality, especially amid uncertain funding flows.
- Stakeholder engagement takes longer than expected and requires sustained coordination. Elevating the IRP as a key planning tool has deepened interest across government and partners but also added layers to the process. The time needed for revised demand projections and broader validation was underestimated, affecting timelines.
The above lessons inform several programme adjustments planned for next year including testing effective models of collaboration and balancing technical quality with political timelines.

Trademark: The Nakonde OSBP project highlighted the importance of pre-planning, which embedded mitigation measures against issues such as disruptive weather condition, mobilisation and resettlement delays resulting into overall project efficiency. A key lesson was the value of continuous assessment and adaptive project management which allowed for real time adjustments and scaling based on evolving needs and opportunities. Through regular reviews and close engagement with stakeholders and partners, the project was able to progressively increase its scope and resourcing. However, with anticipated budget cuts in the coming year and beyond, there is uncertainty around Trademark’s ability to adapt its delivery model to align with reduced funding while still maintaining a high impact programme.

During implementation, Trademark faced several constraints and often relied on workaround solutions facilitated through local stakeholders and informal networks, rather than formal communication channels and protocols. While this approach proved effective in advancing the Nakonde project, it may not be sufficient for the successful delivery of the upcoming trade facilitation programme. As Trademark transitions to a more integrated programme approach in the year ahead, strong convening power and strategic influence will be essential for effective implementation. A clear and nuanced undertaking of Zambia’s political economy will also be critical to navigating complex stakeholder dynamics and ensuring programme success.

Aceli Africa: One of the lessons learned especially from the field visit was that Aceli had great potential to achieve influencing objectives. For example, short loan tenure was cited as a challenge by both the financial institution and the SMEs but the policy environment needed to be conducive and enabling. Another potential influencing area is the project focus on encouraging financial institutions to provide support to SMEs that they would not have considered under the standard criteria. These and other influencing areas needed to be systematically captured and disseminated. However, changing the policy environment requires engagements at various levels with both public and private sectors to have a clear understanding of the existing gaps with the current policies and lobbying for a change. A change in lender behaviour may require a little more time.

Prospero: Throughout the implementation of the SPV, several valuable lessons were learned. These insights have been systematically incorporated into the design of a potential successor project (ZSTP) subject to funds availability. A detailed account of the lessons learned is annexed in the Project Completion Report.

Projects	Date of last narrative financial report	Date of last audited annual statement
Prospero	To be added	To be added
CIGZambia	14 April 2025	May 2025
TMA	April 2025	June 2025
ZTIP	2025	2025
ACELI Africa	21 April 2025	TBC

Annex 1: Prospero SPV (Zambia Private Enterprise Project Phase II)

Project Completion Review

Title: Prospero SPV (Zambia Private Enterprise Project Phase II)
Final Project Spend £ (full life): 8.6 million	Review Date:	7 July 2025
Project Code: 300635 / Component Codes: 102,104,107,109	Start Date: April 2020	End Date: 31st March 2025

Summary of Project Performance

Year	2021	2022	2023	2024	Overall PCR
Project Score	A+	A	A	A	B
Residual Risk Exposure Rating	Major	Major	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	Link
DevTracker Links to all logframes used during Project lifetime:	Link

Description of the project and what it has achieved [1/2 page]

This Project Completion Report (PCR) focuses on Prospero, one of the key projects under the PEPZ2 Project Prospero, for which an early closure decision was made following the findings of the mid-term and sustainability review.

Prospero a company limited by guarantee, was established in April 2020 by the Foreign, Commonwealth & Development Office (FCDO) formerly DFID, to implement the PEPZ2. Originally created under PEPZ1 in 2015 as a Special Purpose Vehicle (SPV), Prospero was designed to receive and recycle FCDO grant funding to support SME development in Zambia. From the outset, it was envisioned as a platform that could attract additional funding from impact investors and donors.

The original PEPZ2 Business Case envisioned two suppliers: (i) Prospero Ltd, responsible for market development and SME advisory and investment support, and (ii) a supplier for Policy and Learning Support (PLS). However, due to budget constraints, the PLS component was deprioritised and ultimately not implemented. Funding for Prospero also fell short of initial projections. In early 2021, budget uncertainties forced Prospero to pause or cancel several workstreams. The PLS component was suspended and later cancelled in 2023. Some of its functions, such as business environment reform and research, were absorbed internally.

Prospero focused on two core areas; market development in key sectors (tourism, agriculture, and mining local content) and the mobilisation of catalytic finance for high-potential SMEs. Its overarching goal was to foster SME growth, job creation, and sustainable economic development in Zambia. The Business Case outlined three primary objectives: (1) increase capital flow to SMEs, (2) enhance SME capacity to utilise finance effectively, and (3) improve the business environment in the targeted sectors. The intended outcome was a vibrant, sustainable investment ecosystem that would attract new investors and support SME access to finance, while also strengthening the policy and regulatory framework.

Despite consistently strong performance ratings, including an A+ in its first year, Prospero faced several challenges. The COVID-19 pandemic and reductions in FCDO’s Official Development Assistance (ODA) budget created uncertainty and affected implementation. These issues were compounded by delays in fund disbursement due to FCDO funding pause and internal financial system transition in 2022/23.

The Project received only £8.6 million of the £48 million originally anticipated over five years (£4.7m in Year 1 and £3.9m in Year 2, £4m year 3, £2m year 4 and 1.2m year 5). The significant funding reduction impacted Project delivery. In response, Prospero revised its strategy, scaling back resource-intensive market development activities to focus on building a robust SME pipeline. The Project’s logframe was also adjusted to reflect the reduced budget.

In 2024, a Sustainability Review was conducted which identified key limitations of the SPV model, including high operational costs and strategic ambiguity. Initially Prospero was expected to become self-sustaining, using returns on investment to cover operational costs and attract external funding. The review concluded that ongoing grant funding would be needed to sustain Prospero and a supplier-led model would offer better value for money. As a result, FCDO decided to exit Prospero in March 2025 and transition to a new supplier-led approach. Prospero’s leadership decided to continuing operations through independent project delivery.

Summary of Prospero Project Performance

Overall, Prospero had shown strong performance in investment facilitation, climate and nutrition outcomes, and SME innovation, but needed to strengthen its approach to gender inclusion, SME growth tracking, and formalisation support. However, several structural and operational constraints significantly limited the Project’s ability to achieve the breadth of outcomes set out in the original Business Case.

Investment Services: Interventions aimed at improving the investment climate performed well and should be scaled up in future programming.
Financial Readiness & SME-Investor Matching: Strong results with high investment leverage achieved at modest cost.
Nutrition & Climate Resilience: Exceeded all relevant output targets, showing that SMEs can effectively contribute to broader FCDO strategic objectives, including improved nutrition and climate resilience.
Private Sector Investment: Successfully attracted private equity and UK-linked impact investors. The partnership with ICA could be improved through better alignment of contracting timelines with business needs.
Job Creation: Targets for total jobs created and sustained were met, but results for women, marginalised groups, and people with disabilities were slightly below target. Evidence-based learning is needed to enhance inclusion, particularly among women.
SME Growth & Formalisation: Difficult to assess due to data and framework gaps. While innovation targets were exceeded, SME growth remains implied rather than evidenced. For future programming, incorporating indicators on compliance and formalisation would be valuable for tracking growth more effectively.
Support for Women-Owned/Managed SMEs: Consistently fell short of the 30% support target. Improving performance requires an evidence-based strategy to understand the sectors, constraints, and business types women operate in. A differentiated approach including targeted mentoring, networking, tailored financial/business services, and better engagement with financial institutions is recommended to better support growth in women-led enterprises. These underperforming areas were identified repeatedly across annual reviews and were not fully resolved due to the absence of the planned Policy and Learning Support (PLS) function.

Overall, while Prospero delivered strong achievements in investment facilitation, SME support, and climate resilience, the Project faced structural and financial constraints that limited its sustainability. The mid-term and sustainability reviews concluded that the SPV model was not cost-effective was no-longer aligned with FCDO’s risk appetite. FCDO’s decision to exit Prospero in March 2025 ensures ODA resources are aligned to a more efficient delivery model while building on lessons learned from Prospero’s implementation. These constraints have been considered alongside the Project’s positive results when assessing overall performance.

Major lessons learned, evidence generated and recommendations [1/2 page]

The Project generated several important lessons, particularly on governance, delivery model choice, learning systems and inclusion, which should inform future programming and the design of successor initiatives.

A continued involvement of FCDO in Prospero governance and oversight was necessary to ensure compliance with its requirements and to bring an international development perspective to strategic discussions. However, this placed a significant burden on BHC staff, including the Deputy Development Director, Head of Finance, SRO/PRO, and project lead.

Governance challenges further hindered Prospero’s performance. The dual lines of authority between FCDO and the Board resulted in confused accountability and undermined strategic direction. Board members, appointed largely for their private sector and financial expertise, had limited capacity to guide Prospero in achieving its development mandate. This lack of alignment between governance structures and development objectives, combined with Prospero’s dual mandate of delivering both economic returns and development outcomes, led to strategic conflict. For future programming, governance arrangements should be simplified, with clear lines of accountability. Board structures, if used, should be composed of members with strong development expertise as well as private sector experience, to ensure an appropriate balance of perspectives and capacities.

The SPV non-intervention costs were high, ranged from 26% in 2020/21 to 43% in 2022/23 against a target of 33%. These high costs reflect the SPV delivery model’s higher requirements for staffing, board oversight, and audits, which are not justified for a low ODA spending scenario. Notably, these figures exclude the substantial input of FCDO staff time required for governance, oversight, and risk management. In future programming, transitioning from an SPV model to a third-party contracted delivery approach could enhance cost-efficiency, reduce the burden on FCDO staff, and increase flexibility in adapting to budget changes although it would limit the ability to recycle Project funding. These high structural costs ultimately undermined economy and form a central consideration when assessing the overall VfM of the Project.

The cancellation of policy learning support (PLS) component weakened Prospero’s ability to influence systemic change and reduced the adaptability of interventions. Without an embedded (PLS) function, intervention designs were often sub-optimal and opportunities for iteration and adaptation were missed. Future Projects should ensure that a policy and learning component is integral to Project design, with dedicated resources for evidence generation, dissemination, and adaptive learning to strengthen systemic impact.

The delivery mechanism of Prospero, structured as a Special Purpose Vehicle (SPV), did not deliver the intended benefits that were set out in the business case. While the SPV model was meant to combine independence with development objectives, in practice it created unnecessary complexity, high costs, and challenges in achieving value for money. Future programming should carefully weigh the trade-offs between “build” and “buy” models, recognising that establishing a new entity comes with significant governance, fiduciary, and operational costs that may outweigh the potential advantages of independence.

Management capacity also emerged as a critical weakness. Despite building valuable networks and sectoral knowledge, Prospero struggled to attract and retain high-quality management and to establish fit-for-purpose internal systems. This was compounded by high compliance requirements, FCDO funding cuts during COVID, and the governance challenges noted above. Weak management systems exposed the Project to fiduciary risks and diverted significant time away from strategic delivery. Future Projects should invest early in establishing robust management capacity and systems proportionate to the size and scope of the intervention, while avoiding unnecessary complexity. Where possible, delivery mechanisms should be aligned with existing institutional structures to minimise duplication of functions and costs.

The design of some of the Development Capital instruments was rushed, with inadequate through given to exit strategies. Complex operations further constrained management attention and limited Prospero’s ability to focus on delivering investment impact. In future programming, the decision to deploy Development Capital should be reserved for larger and better resourced Projects. Contractual models that outsource specialised functions, while retaining strong oversight, can achieve impact without the high overheads associated with a stand-alone SPV.

The original sustainability strategy proved unrealistic. Prospero was tasked with achieving financial sustainability through cost recovery and returns from investments in early-stage, high-risk SMEs. Given the early stage of the Zambian SME ecosystem, grant funding and technical assistance are needed to support SME’s and this business model was not viable. The focus on achieving financial sustainability diverted attention away from Prospero’s core development objectives and created tension between developmental and commercial imperatives. A more appropriate sustainability strategy for future programming would be to focus on achieving systemic change within market systems, rather than financial independence of the delivery vehicle. Sustainability should be defined in terms of lasting market outcomes, with Projects designed to catalyse systemic change and then exit, rather than to build self-sustaining institutions.

How this report was conducted

Prospero PCR was led by the Senior responsible Officer (SRO) supported by the Project Manager.

Actions following approval of this report

The following will be the actions taken upon completion of this report:

The PCR will be annexed to the PEP2 2024/25 Annual Review report, to be included in the final closure of the PEP2 Project in 2029.
- Lessons learnt will be used to inform future programming such as the ZSPT
- To ensure transparency and accountability, the annexed PCR will also be published on the Devtracker
- Ensure completion of transfer of the remaining ZICB financial asset to an approved third party.
- Finalise the nearly completed 2025 audited statements
- Receipt and uploading of the final financial audited statement on AMP

## B: Theory of Change and Outcome Assessment (1-2 pages)

Overall assessment of Project revised outcomes, sustainability and VfM [1/2 – 1 page]
Outcome

Original Business Case Outcomes
	Starting point	Final result
Budget	£47m	£8.6
Timeframe	April 2020 to January 2027	April 2020 to March 2025
Outcomes	The outcome statement for the Project was : “SMEs supported are able to access new sources of finance, grow their business, and create paid jobs”. / The initial outcome targets if the Project continued to operate to the anticipated end-date of 2026/7 were; / More vibrant SME investment climate, with at least 5 new SME finance vehicles entering the Zambian market; / Leverage of at least £100 million of private finance, with at least 10% of this from domestic Zambian sources. / At least 30,000 jobs created, including at least 50% for women (and other groups such as people with disabilities, targets to be determined) / Number of people supported to cope with the impacts of climate change (ICF KPI 1). / Scaled up Zambian SMEs will improve nutritional outcomes and climate resilience of populations that access their goods and services. / Research and evidence generated by the Project is used to inform adaptive programming and influences the design of other private sector Projects (in Zambia and beyond)	Prospero engaged and supported two partners in creating a more vibrant investment climate. Key institutional support included ZICB, which introduced a dedicated climate-smart lending operation; Zambia Business Angel Network (ZBAN), which improved efficiency and increased angel membership and investment activity. / By 2024, Prospero leveraged £95m, close to the BC target. investment facilitated from investors accounted for 80 percent of the total investment leveraged by the Project during this period. / Prospero did not meet its original target for jobs created but did meet revised targets in light of the budget reductions. Over the period 2020/24 Prospero created 2,233 jobs. Of the total jobs created, 740 were for women. / Between 2021 and 2023, PEPZII helped over 63,000 people build resilience to climate in line with ICF KPI1, the Project demonstrated strong leverage of climate finance, 55% of all additional funding mobilised was ICF-eligible. / Over the period 2020 to 2023, Prospero supported 63 SMEs to develop products that promote more nutritious food and nutrition outcomes. The supported SMEs were making their products available in affordable package sizes. On a cumulative basis, Prospero exceeded performance targets against all indicators related to the promotion of improved nutrition over the period 2020/23, However, there was no set target in the BC. / From 2021 to 2023, Prospero produced eight research studies to strengthen Zambia’s business environment and hosted workshops to share findings with stakeholders. Notable outcomes include a goat sector assessment by IAPRI, which showed that targeted interventions increased smallholder farmers’ herd sizes to 10–15 goats and boosted revenues by 76 percent. Prospero also partnered with NABII to commission the Zambia Impact Climate Survey, providing insights into investor attitudes and informing efforts to engage pension funds as a potential source of impact investment.

Overall Prospero did not fully achieve the original Business case outcomes, primarily due to substantial changes during Project implementation. These included the COVID-19 pandemic and reductions in ODA budget which necessitated revisions to most outcome indicators to align with the revised strategy as reflected in the revised outcome table below.

Over the four years of implementation, the project met its annual targets for its revised outcome indicators, although it fell short on jobs created.

Revised Outcomes
	NON-CUMULATIVE	Apr 2020-Mar 2021	Apr 2021- Mar 2022	Apr 2022-Mar 2023	Apr 2023-Mar 2024	Cumulated /Achieved
Outcome 1.1: SME investment facilitated by Prospero (of which is ICF eligible)	Target (GBP)	2,500,000	1,500,000	9,000,000	11,000,000	24,000,000
	Achieved (GBP)	38,500,000[6]	13,000,000	15,446,700	28,073,871	95,020,571
	Achieved/Target %	1540%	867%	172%	255%	396%
Outcome 1.2: Jobs Created (of which are women)	Target	535 (268)	395 (197)	570 (170)	280 (84)	1,780 (719)
	Achieved	640 (247)	623 (309)	628 (117)	342 (67)	2,233 (740)
	Achieved/Target %	120% (92%)	158% (157%)	110% (69%)	122% (79%)	148% (102%)
Outcome 1.3: Jobs Sustained (of which are women)	Target	2,987(1494)	913 (456)	1,200 (350)	700 (225)	5,800 (2,525)
	Achieved	3,270(951)	1,090 (369)	1264 (408)	599 (131)	6,223 (1,859)
	Achieved/Target %	109% (64%)	119% (81%)	105% (117%)	86% (37%)
Outcome 1.4: Number of people supported to cope with the impact of climate change (ICF KPI 1)	Target	770	6000	14000	5000	25,770
	Achieved	4000	17,673	45,800	7105	74,578
	Achieved/Target %	519%	295%	327%	142%	289%
[6] Note: 2020/21 includes investments stimulated during the final period of the earlier PEPZI phase but realised during this period.

Outcome 1.1:
Throughout its implementation, the Prospero Project played a central role in catalysing private and impact investment into Zambia’s SME ecosystem. It achieved this by:
- Providing risk reduction and capital enhancement mechanisms through grants and returnable capital;
- Supporting investment readiness and transaction facilitation for high-potential SMEs;
- Organising targeted events such as pitch workshops, matchmaking sessions, and the Zambia Impact Investment Forum to directly link SMEs with investors.
Performance Against Targets; The Project consistently exceeded its targets for facilitating and mobilising additional investment. Based on Logical Framework results, Prospero leveraged over £95 million in cumulative private and impact capital, outperforming its cumulative £24 million target. Approximately 80% of total leveraged investment was directly facilitated via investor engagement, with the rest mobilised through blended finance instruments such as grants, debt and returnable capital.
The contributions from different pathways to investment stimulation
Financial year	Leverage through grants	Facilitated from investors	Total investments
2020/21	£ 2,554,554	£ 35,945,446	£ 38,500,000
2021/22	£ 7,626,200	£ 5,373,800	£ 13,000,000
2022/23	£ 5,449,780	£ 9,996,920	£ 15,446,700
2023/24	£ 2,581,941	£ 26,139,020	£ 28,720,961
	£ 18,212,475.00	£ 77,455,186	£ 95,667,661

Outcome 1.2 and 1.3: Overall, the Project achieved its targets for jobs created and sustained; however, this was largely due to the downward revision of targets for women’s employment. After failing to meet the original Business Case (BC) commitments, Prospero adjusted its logframe target for jobs created for women to 30%. The BC had originally committed PEPZII to conduct a comprehensive gender analysis and develop an action plan to help partners address restrictive norms and regulations that limit women’s participation in enterprise development, while actively promoting opportunities for female entrepreneurs.

The shortfall in jobs sustained and created for women likely reflects structural features of the Zambian economy, as well as constraints on PEPZII’s learning capacity due to FCDO budget reductions, which prevented the rollout of the Policy, Learning and Support facility. Available data suggests that SMEs supported by PEPZII were concentrated in sectors dominated by male employees, while women-owned or managed businesses continue to face systemic market barriers that limit their attractiveness to investors and restrict growth. Strengthening evidence-based learning would have been critical to achieving the Project’s revised target of 30 percent of all jobs created and sustained for women (down from 50 percent in 2020/21 and 2022). This would have required deeper analysis of the sectors generating the most jobs for women and the demand- and supply-side constraints affecting female labour force participation, to inform future intervention strategies.

Outcome 1.4: This indicator reports into the FCDO’s ICF KPI1. All annual outcome indicators demonstrate that Prospero significantly exceeded targeted performance in supporting SMEs coping with the impact of climate change. This was achieved by providing training for improved production, diversifying income opportunities and improving access to markets for rural or peri-urban communities/MSMEs. The big initiative was Prospero partnering with Zambia Industrial Commercial Bank (ZICB) to provide cash cover for loans to SMEs that deliver climate resilience initiatives. Prospero support to ZICB invested approximately £1.1m to eleven businesses with recovery rates of approximately 80% reflecting the challenging environment for SME growth.

Sustainability and VFM
The Business Case laid out FCDO’s vision that Prospero would become self-sustaining, the aim was to build an independent institution with a unique set of capabilities, including staff skills, systems, local knowledge, and networks that would continue to exist as a vehicle for SME support in Zambia, beyond the lifetime of the Project. Prospero would use return on investments to finance its management and operational costs, and over time would serve as a platform attracting funds from other impact investors.

A sustainability assessment and mid-term review (MTR) was conducted in 2024 and reviewed that Prospero demonstrated strong effectiveness and moderate efficiency in delivering SME support and leveraging investment. However, the SPV model proved to be costly and complex, undermining economy and requiring significant FCDO oversight. Below are the key findings of the sustainability assessment.

Governance and Strategic Direction
A review of Board and committee records suggests that Board members were selected primarily for private sector experience in finance, law, and audit and had limited development expertise. This constrained Boards ability to provide strategic guidance on Prospero’s development mandate. Furthermore, the Investment Committee largely prioritised financial sustainability and return on investment, with limited documented discussion of alternative approaches better suited to the needs of early-stage, high-risk SMEs. This imbalance between financial and developmental priorities at times misaligned with Prospero’s dual mandate: to catalyse economic returns through SME growth while also aiming for long-term financial sustainability.

Sustainability Strategy:
FCDO’s original vision was for Prospero to achieve long-term financial sustainability by recovering funds disbursed through intermediaries and generating returns from interest and equity investments. However, this model proved unfeasible in practice. Prospero targets early-stage, high-risk SMEs that typically require grant funding and have high failure rates. Additionally, the organisation provides technical assistance either in-house or through its partnership with Impact Capital Africa (ICA), without cost recovery from beneficiary SMEs. As a result, Prospero operated a high-cost, low-revenue model, and the original cost recovery expectations set out in the FCDO business case were ultimately unrealistic.

Alternative Revenue and Sustainability Strategy:
To support its financial sustainability goals, Prospero explored alternative revenue streams and achieved some success in securing consultancy contracts from mining companies and donors. Its sustainability strategy, approved by the Board in 2022 and followed by a policy in 2023, aimed to leverage Prospero’s local registration and technical expertise to attract new funding primarily through grants and consultancy work enabling continued operations beyond 2027 without further core FCDO funding.

However, an independent review raised concerns on the viability of this approach. Key concerns included:
(i) A lack of detailed financial analysis; (ii) Underestimation of the significant resources required to identify and manage consultancy projects; (iii) A skills gap between Prospero’s technical Project delivery team and the capabilities needed for commercial consulting. The review concluded that operating as a sub-contractor in a competitive consultancy market would offer limited value and risk diverting resources from Prospero’s core mission.

Summarise the Project’s theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]

The original theory of change was that by addressing constraints to SME growth (low capabilities, limited access to finance and unfavourable business environment) through strengthening the investment ecosystem; business development services; analysis, research and evidence, and these strategies once employed were to promote job creation, increased domestic credit and improvements to policy and programming in Zambia and beyond.

Activities for the above strategies were to immediately result in outputs that include establishment of investment funds and innovative finance vehicles, access to Business Development Services, linkages to anchor firms by SMEs, government implementation of regulatory and policy reforms and the dissemination of research outputs and evidence leading to expanded access to finance for SMEs, improved capacity in business development and effective business operation founded on value for money principles and adaptive programming.

The intermediate outcomes were to translate into increased revenue for SMEs, additional paid jobs and a more vibrant SME investment ecosystem. For the program, learning from monitoring and research was to inform adaptive programming and inform future Project designs

Ultimately, the interventions were to positively impact wider social benefits such as nutrition and climate, SME-led contribution to the economy including job creation and improved programming for similar initiatives.

Prospero specifically supported, innovation in finance and investment; new and improved business services; stronger business linkages within focus sector value chains; Government policy making relevant to focus sectors; and improved private sector collaboration through business membership organisations to achieve business environment reforms.

In 2021, Zambia’s worsening debt situation, inflation and currency devaluation, along with the COVID pandemic, challenged the theory of change assumptions related to the level and interest of Zambian and international investors to work in Zambia and set up long-term operations. Many businesses had gone into survival mode. The theory of change impact relied on firms supported by the company creating jobs as a result of scale up and while this remained valid, the number and quality of jobs created varied significantly between different sectors.

Overall, the business case assumptions remained unchanged throughout the Project, including that there exists a pipeline of SMEs that were looking for financial and business development support. It is worth noting however, that whilst the pipeline of SMEs looking for support exists, the intensity of effort required to make them investible was higher than originally expected.

In 2022, the Theory of Change was refreshed, in part to reflect additional FCDO interest and funding for action against climate change, so that the Project can track progress towards sustainable climate action. During the process, the intended impacts of the logframe were amended, reflecting more prominence of the climate work. At the same time, the ToC refresh resulted into a reduced prominence of learning and evidence interventions for the program. This was due to the lack of implementation of the Policy, Learning and Support facility. The intended outcomes of the Project were also adjusted to a stronger impact investment ecosystem; jobs created and sustained; and an improved investment climate and business enabling environment.

In 2023/24, Prospero faced a significant budget reduction from £4 million in 2022/23 to £2 million. In response, the Project scaled back its market systems development activities and concentrated on three core areas: (1) Investment Pipeline Enabling, (2) Investment Pipeline Development, and (3) Investment Facilitation Services for Zambian SMEs. This strategic shift aimed to sustain support for SME competitiveness and improve access to growth capital, thereby reducing the financing gap for credible and investable businesses.

Despite the change in approach, the objective of Prospero did not materially change. The project still focused on enabling and facilitating SME performance and investment to deliver inclusive, scaled-up impact for broad-based economic growth and sustainable poverty reduction. However, the transition from market system strengthening to building robust investment pipelines required revisions to the PEPZII logframe, particularly at the output level. Major adjustments were made under output two, where impact investment ecosystem strengthening was replaced with indicators capturing progress under the newly introduced initiatives; pipeline enabling and pipeline development.

## C: Detailed Output Assessment

Output Number and Title		1: Prospero invests in SMEs and facilitates investments in commercially viable and impactful businesses For investment facilitation
Output Score		A
Impact weighting (%)		40	Impact weighting revised since last AR?	Yes – up from 25%

Output Indicator 1	Updated Target		Updated Results Achieved	Milestone Results
1.1 £ Investments made by Prospero funds in intervention partnerships (Returnable grants)	2023/4 target - £215,000 / (£150,000)		£410,905 (£246,289)	Milestone Met
1.2 £ leveraged by Prospero including ICF eligible.	2023/4 target - £150,000 / 2022/3 target - £180,000 / 2021/2 (ICF) - £160,000		£800,000 / £410,2455 / £217,000	Milestone substantially exceeded:
1.3 Number of SMEs linked to investors.	2024/5 target – 60 / 2023/4 target - 15		60 / 17	Milestone met

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]

Due to budget reductions, the output indicators were revised throughout the implementation period to align with budget allocation for each year. Significant adjustments were made in 2023/24 following a shift in strategy. One of the key changes was that Prospero would no longer engage a financial facility to support ICF interventions which necessitated the amendment of the output indicators.

Output 1.2:
The returnable grants portfolio, established in 2023, aimed to support small businesses that had demonstrated capability to progress beyond pure grants and technical assistance but were not yet eligible for commercial loans[7]. These grants provided both working capital and capital expenditure. By making the grants returnable, Prospero intended to create a revolving pool of funds that could be recycled and accessed by other businesses in the future. The indicator was revised in 2023/4 due to the shift in strategy. A significant portion of the funds was allocated as returnable grants to businesses involved in regenerative agriculture, climate adaptation, and agri-processing.
[7] Topsoil, a company that exports unprocessed leather hides were able to buy machines that enabled them to increase value addition and expand their workforce. Western honey in its expansion stage was awarded a returnable grant for a period of 4 years to purchase honey processing equipment that will increase production and create employment. Legacy Manufactures received a returnable grant for working capital over a four-year period to purchase 72 MT of soybeans through aggregators in its difficult start-up period, to create and sustain jobs; others included, Twala, Kalef Lit, Super valley, Goat and Sheep Header, Mansanvu, Evonia, Bwando and Maima enterprise

Repayments were highly challenging due to a significant scaling down of business operations, primarily caused by power outages resulting from the 2024 drought calamity. Some companies whose production heavily relied on power completely ceased operations during the financial year 2024/5. Following FCDO withdraw from Prospero, the best value-for-money disposal approach was explored, and the decision was made to convert the returnable grants into full grants.

Output 1.3 tracks the volume of investment and technical assistance mobilised by Prospero-supported partners from external sources to contribute to interventions aligned with Prospero’s objectives. Across the three-year period, the Project consistently exceeded its annual targets, demonstrating strong leverage of private and development finance towards climate-resilient and inclusive growth.

In 2023, the output was revised further focusing on capturing additional impact investment facilities triggered through the Impact Capital Facility (ICF). A sum of £410,245 of private finance was mobilised for climate change this is additional money that SMEs raised through other facilities or their own money that contributed to the interventions supported by Prospero. In 2024, Prospero surpassed its targets by mobilising over £800,000 in private finance and technical assistance to complement its interventions.

Benchmarking against the UK’s International Finance KPI 12, Prospero mobilised £217,000 in private finance against a target of £160,000 in the year 2022. These investments supported climate change mitigation and adaptation goals, demonstrating Prospero’s catalytic role in mobilising climate-aligned private capital. The funds were directly invested in interventions co-financed by Prospero[8].

Output 1.4: Over the implementation period, Prospero made significant progress in strengthening Zambia’s investment ecosystem by building and sustaining strategic partnerships with key players such as Impact Capital Africa (ICA) and the Zambian Business Angels Network (ZBAN). These partnerships were instrumental in connecting local small and medium enterprises (SMEs) to investors, both locally and internationally, and enhancing the visibility of Zambia as an emerging destination for impact capital.
In 2023, Prospero co-hosted the Zambia Impact Investment Summit (ZIIS) in collaboration with the National Advisory Board for Impact Investment (NABII) and ICA. The event convened over 240 participants and 20 investment organisations and provided a platform to showcase 12 high-potential Zambian businesses. A targeted investor roundtable with 20 global investors culminated in confirmed investment commitments amounting to £8 million. These investments were channelled into businesses such as Good Nature Agro, Shais, Vitelite, and Farm Depot, facilitated by leading international financiers including Oikocredit, KIVA, Renew Capital, and XSML Capital.

In 2024, Prospero continued to leverage these partnerships to deliver similar successes. The annual ICA Summit, co-hosted in June, attracted over 300 delegates from 17 countries and served as a key platform for linking 12 SMEs to prospective investors. Prospero also deepened its collaboration with ZBAN by supporting regular monthly pitch sessions, which enabled early-stage and growth-oriented businesses to engage with angel investors. These efforts were instrumental in enhancing investment readiness and expanding investor networks for Zambian SMEs.

By 2025, Prospero’s sustained engagement with ICA and ZBAN had yielded tangible outcomes. A total of 60 SMEs were linked to potential investors during the year, of which 10 successfully secured investment deals and an additional 5 were under negotiation at the time of reporting. The 2024 ICA Summit, again co-hosted by Prospero, built on the momentum from previous years, maintaining strong international interest and deal-making potential for Zambian enterprises.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

Lessons learned
Macroeconomic challenges, including depreciation of the Kwacha, increasing fuel prices, high inflation rates and drought, have reduced economic growth and made it harder for Prospero to find potential business and investment partnerships. A finding of the mid-term review is that there is still a critical need for support to early-stage SMEs, however the funding modalities Prospero currently use of returnable grants and 100% cash cover for intermediary loans do not leverage large amounts of additional private capital. Prospero’s value for money could be increased by considering more innovative products that can be offered by financial intermediaries with a lower proportion of Prospero grant cover.

A key challenge faced by SMEs that received returnable grants or financing under the Prospero PDF was the national power deficit. Unreliable electricity supply disrupted production cycles, increased operational costs, and limited the ability of these businesses to scale. This directly affected their revenue generation capacity, making it difficult for them to service their loans or meet agreed repayment terms. In several cases, the energy-related constraints undermined the intended catalytic effect of the financing support. Future Projects should incorporate an assessment of infrastructure related risks particularly energy access when selecting and supporting SMEs. Where feasible, blended finance facilities should consider complementary investments in alternative or off-grid energy solutions to reduce operational vulnerability.

Notably, the cancellation of PLS limited learning that would have enhanced the Projects impact beyond financial leverage. Future interventions should explicitly track not only financial leverage but also technical assistance, policy influence, and systems change catalysed by Prospero-like interventions.

Output Number and Title		2: Prospero builds strong pipelines of commercially viable and impactful businesses for investment facilitation.
Output Score		A+
Impact weighting (%)		40	Impact weighting revised since last AR?	Yes – up from 25%

Output Indicator 2	Updated Target		Updated Results Achieved	Milestone Results
2.1a: Number of partners in priority sectors introducing new products, services or business models as a result of Prospero support. / 2.1b: Number of micro enterprises & SMEs (formal or informal) in priority sectors accessing new products and services to help them grow their business (Women)	2022/3 target – 40 / 2021/2 target – 41 / 2020/1 target - 82 / 20222021/2 target – 8,000 (2400) / 20212020/1 target – 7,728 (3864) / 2022/3 (SMEs) target 200 (60) / 2021/2 (SMEs) target 25		51 / 49 / 118 / 9,447 (4,603) / 9,900 (468) / 455 (77) / 32	Milestone met / Milestone met / Milestone met
2.2 Number of SMEs closing compliance gaps.	2023/4 target - 15		7	Milestone met
2.3 Number of partnerships formed targeted at promoting more nutritious food and improving nutrition outcomes.	2023/4 target – 5 / 2022/3 target – 20 / 2021/2 NA (output was removed) / 2020/1 target - 21		11 / 23 / 14 / 26	Milestone met
2.4 Co-investment in products, services or business models by partners.	2023/4 target - £1,000,000 / 2022/3 target - £2,450,000 / 2021/2 target - £ 750,000		£2,581,941 / £5,449,780 / £7,833,920	Milestone met

Output 2.1: Between 2021 and 2023, Prospero signed 218 partnerships introducing new products and services to the Zambian market. This strong performance was primarily driven by SME recipients of the Investment Services sector’s debt facility and international climate finance initiatives.

Examples of SMEs introducing innovative products included Good Nature Agro, a local agribusiness supported to raise investment for producing high-quality legume seeds. These seeds attract premium prices for smallholder farmers, ultimately increasing their incomes.

Prospero worked with 487 SMEs between 2021 and 2023 who accessed new products and services, more than double the annual target of 225 SMEs. A group of partners that identified an opportunity to improve groundnut production in the Copperbelt area shared resources to hire an extension officer to help the farmers access Spanish groundnut seed and improve farming practices. 1,500 farmers were trained in Good Agriculture Practices (GAP) for production of the Spanish groundnut variety this year

Output 2.2: This output was introduced in 2024 resulting from the strategy shift. The output focused on the number of SMEs supported to close business compliance gaps. 7 businesses were supported which was below the set target of 15 businesses, primarily because the process of formalising a business took longer period than anticipated. Some SMEs that were supported will only be able to close the gaps in the next review or beyond depending on the lead time require. The most common gaps that were identified include financial management, accounting software packages, ZABs certification, export licenses[9].
[9] SME supported to close business gaps include - Western honey, Fresh Point and Akashya were supported with financial management skills and ERP accounting resource system. Munsamvu was supported with, financial, HR and procurement training including out-grower scheme training. Eunimos and Weetagold were supplied with lab equipment and training to enhance food safety and to comply with ZABs standards.

Output 2.3: Over the period 2020 to 2024, Prospero supported 74 SMEs[10] to develop products that promote more nutritious food and nutrition outcomes. Changes to the logical framework introduced in 2022/23 established additional indicators designed to further unpack Prospero’s contribution to improved nutrition through support to agricultural SMEs, including improved pro-poor access to nutritious food through the introduction of more affordable package sizes, and the total volume of nutritious food produced by supported SMEs, which will enable a better understanding of production trends. Supported SMEs produced 110,000Kgs and 250,000 litres of nutritious foodstuffs in 2022/23, and 12 supported SMEs were making their products available in affordable package sizes.
[10] Mbezi Enterprise, an agro-processing company specializing in the production of nutritious soy blend cereal such as soybeans, maize, millet, and groundnuts into ready-to-eat (instant) cereal meals. WeetaGold Milling focusing on wheat milling and processing, Eunimos investment in produces soy porridge blend, Mpongwe Bulima provides certified seed and aggregates groundnuts for processing into peanut butte

Notably, Covid grants helped Zambian SMEs meet demand from local supermarkets when imports were disrupted. Prospero supported businesses to produce nutritious foods, for example providing £10k to Panuka for solar-powered irrigation to enable it to increase volumes of fruit and vegetables, £8k to Tukuza Associates to produce common beans, and linked Tukuza with Mushili Beans as the primary off-taker and processor. Grants to Twala to start producing green banana flour and Mountain Sun Enterprise for tomato processing, helped businesses innovate as well as take advantages of disrupted international supply chains. Further, 11,200 agricultural MSMEs accessed new products and services to help them grow their businesses. This large number was achieved through support to a few large businesses, such as New Rotation Zambia to supply groundnut seeds to over 2500 farmers. On a cumulative basis, Prospero has exceeded performance targets against all indicators related to the promotion of improved nutrition over the period 2020/24.

Output 2.4: Over the three years from 2022 to 2024, Prospero successfully mobilised substantial co-investment from private sector partners and SMEs already supported through its financial and technical assistance mechanisms. This output measures the amount of additional capital either from investors or from SMEs themselves invested into businesses that have already received Prospero grants.

In 2022, Prospero facilitated a significant injection of follow-on capital into businesses that had already benefited from its support, totalling £7,833,920. This figure far exceeded the original target of $750,000. A substantial portion of this investment £4.74 million was directed to investees of the Debt Facility and the International Climate Finance Facility, while an additional £2.07 million was mobilised in the food and agriculture sector.

A noteworthy example is again, Good Nature Agro, a Zambian agribusiness that attracted follow-on investment to expand production of high-quality legume seeds. This development enabled the company to offer premium products to smallholder farmers, thereby increasing both their productivity and income potential.

In 2023, the output focused specifically on co-investment, defined as the capital that SMEs commit when partnering with Prospero. This excludes any in-kind contributions and is a direct reflection of the financial commitment made by businesses themselves. The milestone was exceeded by 122%, demonstrating that the SMEs Prospero engaged were already at a growth stage, typically able to contribute around £100,000 of their own capital. This performance affirmed that Prospero’s partnerships were effectively targeted at firms with both the ambition and the financial base to scale operations, but that needed further support to catalyse transformation and attract external investment.

The final year of implementation further cemented the relevance and catalytic effect of Prospero’s co-investment model. In 2024, the Project facilitated £2.58 million in co-funding against a target of £1 million, once again exceeding expectations. During this period, Prospero signed catalytic grants with several companies to support their readiness to raise future rounds of investment. For example, Plastic for Change, a recycling enterprise, used Prospero’s co-investment to scale its operations. The support allowed the company to expand its network to over 1,500 waste pickers and significantly boost collection capacity, targeting 200 metric tons of plastic waste monthly. This intervention is expected to triple their monthly revenues, while promoting inclusive green growth and sustainable livelihoods for informal workers.

Lessons Learnt and Recommendations for Future Programming

SMEs that had already achieved a degree of operational scale and financial stability were better positioned to contribute significant co-investment, thereby amplifying the impact of Prospero’s grants. For future programming, it is recommended that SMEs be supported with tailored business development services focused on investment readiness, including financial modelling, governance, and investor pitching skills.

The evidence from PEPZII’s internal monitoring and evaluation data that links PEPZII SME support to SME growth is limited i.e. whilst the wider empirical evidence is positive and there is limited evidence from PEPZII itself around how access to finance and business advisory support impacts on firm performance. This is partly a result of the lack of the Policy and Learning Support Facility. The lack of evidence suggests that significantly more analysis needs to be undertaken to better target future Project support to those SMEs that have the most potential to grow and ultimately to create jobs.

Providing relatively small but well-targeted catalytic grants helped enterprises position themselves for future private investment, especially in capital-intensive sectors like renewable energy.

Encouraging SMEs to commit their own resources fostered ownership, improved accountability, and signalled a strong market validation for their business models, this approach should be promoted in future programming.

Enterprises like Plastic for Change demonstrate that pro-poor and green investment models can be both socially impactful and commercially scalable. Future Projects should continue to prioritise inclusive business models that benefit marginalised groups.

Output Number and Title	3: Prospero generates and utilises research focused on improving business and investment climate for SME growth.
Output Score	B
Impact weighting (%)	20		Impact weighting revised since last AR?	Yes – up from 18%

Output Indicator 3		Updated Target	Updated Results Achieved	Milestone Results
3.1 Number of learning, evaluation and evidence pieces generated and disseminated.		2024 target – 2 / 2023 target - 1 / 2021 target -1	0 / 1 / 1	Milestone not met / Milestone met / Milestone met
3.2 Number of research and analysis activities designed to provide evidence to strengthen the impact investing ecosystem.		2024 target – 1 / 2023 target – 8 / 2022 target - 2	0 / 7 / 1	Milestone not met
3.3 Partnerships formed with business membership organizations and other representative bodies.		2024 target – 3 / 2023 target – 5 / 2022 target - 4	3 / 5 / 3	Milestone met / Milestone met / Milestone not met

In early 2021, Prospero’s work was disrupted by significant uncertainty around the available budget, resulting in Prospero having to delay or stop certain workstreams. The Policy, Learning and Support Facility (PLS) was put on hold and later cancelled, and some elements of the PLS such as business environment reform and research were internalised within Prospero.

Between 2022 and 2024, Prospero’s Output 3.1 focused on strengthening Zambia’s enabling environment for impact investment by promoting stakeholder engagement, conducting market intelligence studies, and addressing investment barriers for scalable businesses.

In 2022, Prospero, in partnership with the Zambia National Advisory Board for Impact Investment (NABII), commissioned the Zambia Impact Climate Survey. This survey sought to understand investor perceptions of Zambia’s investment landscape, particularly from an impact investment perspective. The findings were used by NABII to engage key domestic stakeholders such as pension funds with the goal of unlocking domestic sources of capital for local impact-focused enterprises.

In 2023, the Impact Climate Survey findings were officially published in a joint report with NABII. The report revealed that investors maintain a generally optimistic view of Zambia as an investment destination. However, a recurring challenge identified was the lack of a strong pipeline of scalable, high-impact businesses ready for investment. Despite Zambia’s macroeconomic constraints especially linked to national debt investors were reportedly ready to deploy capital if investable opportunities could be identified and de-risked appropriately. These findings offered critical insight into Prospero’s ongoing work of aligning SMEs with suitable investment partners, both locally and internationally.

In 2024, Prospero implemented two feasibility studies under its Pipeline Development initiative, aimed at assessing the investment potential of specific business proposals. The first focused on a proposed coffee production initiative by Lunga Coffee in Mwinilunga District, while the second examined a macadamia export project proposed by North Route Nursery. The studies were designed to inform future investment decisions and deepen understanding of value chains with growth potential. However, the findings were not sufficiently robust for wider public dissemination, and the milestone target related to knowledge sharing was not met. The macadamia study, in particular, revealed systemic challenges in the sector such as a nascent industry base and regulatory constraints around exports.

Lessons Learnt and Recommendations
Data sensitivity and dissemination barriers was one of the challenges. Some feasibility findings could not be shared widely due to commercial sensitivities or limitations in the evidence base, which hampered Prospero’s ability to generate broader ecosystem learning.

Weak Investment Pipeline: While investor appetite exists, the supply-side constraints, i.e., limited investable SMEs, remained a persistent barrier across the three years.

Working with multiple stakeholders, such as NABII and private actors, required ongoing coordination and often moved slower than expected due to institutional capacity limitations.

D: Value for Money [½ - 1 page]

VfM performance compared to the original VfM proposition in the business case

Overall VFM analysis

The past Annual Reviews reported strong VfM performance for the Project based on (i) a comparison with the original VfM targets set out in the business case, and (ii) time series data that compares VfM performance over the first three years of the Project. However, the Annual Reviews did not provide any assessment of Prospero VfM in comparison with alternative Project activities and delivery models. Analysis of the VfM undertaken during the MTR suggests that significant improvements could be achieved in all VfM indicators through the restructuring of intervention activities and the Project delivery mechanism, and (ii) improved intervention targeting based on better MEL systems.

While Prospero performed strongly against its revised output indicators, the Project was unable to demonstrate corresponding outcome‑level change, particularly in SME growth, inclusion and systemic impact. This gap between high output delivery and limited outcome evidence ultimately raised significant VfM concerns. Effectiveness in FCDO’s VfM framework is ultimately measured by outcomes rather than activity delivery.

Actual progress against VfM targets

Indicator	2020/21		2021/22		2022/23
	Target	Actual	Target	Actual	Target	Actual
Economy
The overhead costs as a share of total Project spend. %	(15)	12	(15)	18	(15)	20
Delivery costs as a share of total Project spend.	(18)	14	(18)	19	(18)	23
Efficiency
Partner co-investment ratio	1:1	1:1.2	1:1	1:6.27	1:1	1:1.18
Cost pr SME reached £	£47,612	£30,625	£47,612	£86,394	£47,612	£50,005
Cost per MSME reached £	£369	£339	£369	£427	£369	£392
Effectiveness
The cost per job created £	£6,836	£5,715	£6,836	£6,793	£6,836	£5,892
The cost per job sustained £	£365	£333	£365	£3,888	£365
Equity
The share of Prospero Directors, Management and staff that are female and Zambian %	50% female / 50% Zambian	55% staff / 60% Board / 45% s/managers / 80% Zambian board / 70% s/ managers	50% female / 50% Zambian	56% staff / 50% Board / 60% s/managers / 67% Zambian board / 65% s/ managers	50% female / 50% Zambian	61% staff / 75% Board / 56 % / s/managers
SME partners that are women-owned and operate in and/or serve rural communities.	50% women / 50% rural	35 / 57	30% women / 30% rural	22 / 34	30% women / 30% rural	28 / 47
Number of jobs created and sustained for women, youth, and persons living with a disability.	268 jobs created / 1,494 jobs sustained	247 jobs created / 950 jobs sustained	197 jobs created 456 jobs sustained	309 jobs created 369 jobs sustained	170 jobs created / 350 jobs sustained	117 jobs created / 408 jobs sustained

Economy

The core economy indicator for PEPZII relates to total non-intervention costs as a percentage of the annual Project budget. This percentage has varied between 26 percent in 202/21 (12 per cent fixed, 14% variable) and 43 percent in 2022/23 (20 per cent fixed and 23 per cent variable). A target of 33 percent (15 percent fixed and 18 percent variable) was established for PEPZII based on PEPZI actuals.
In practice this percentage appears high, this is a result of the following factors:
1. The selection of an SPV delivery and creation of the Prospero CLG required (i) the establishment of a Board of Directors and related sub committees (ii) a staffing quota aligned to the operation of company, including senior staff across key management systems such as finance, and HR (iii) complex management and monitoring systems related to the fiduciary and reputational risk from company operations
2. Limited flexibility within a company structure to adapt staffing levels and other fixed costs to changes in the available budget. The current structure was established to manage a much larger budget - £85 million over 7 years (peaking at £17m per year in years 3 – 6). As a result of FCDO budget costs, the actual budget has been reduced significantly. Table 15 shows the original budget forecast from the Business Case and the actual budget.

Prospero original budget Vs actual budget

	2020/21	2021/22	2022/23	2023/24	2024/25
Original budget £M	5.5	13	17	17	17
Actual budget £M	5.5	4	4	2	1

The selection of in-house delivery models utilising full time staff e.g. for the provision of technical support to SMEs and limited reliance on short-term draw down support.

In addition to the above factors, the reported non-intervention costs do not include the costs of FCDO oversight. The selection of the SPV delivery model has required significant levels of FCDO engagement in governance and oversight of the Prospero company equivalent to about 40% of the time of the Head of Economic Development and Green Growth (Funders’ Representative on the Board of Prospero), as well as the SRO and Project staff. The requirement for a high level of FCDO engagement not only increases operating costs, but more significantly has an opportunity cost to other influencing and Project activities. The original business case envisaged FCDO recruiting two Project funded advisers and a Project manager specifically to oversee Prospero but that has not been possible after 2022 due to budget cuts and headcount restrictions.

Effectiveness

PEPZII measures effectiveness primarily through the cost per job created and sustained. The Project set a target of £6,836 per job created, achieving £5,715 in Year 1, £6,793 in Year 2, and £5,892 in Year 3. For job sustainability, the target was £365 per job, with actual costs of £333 in Year 1 and a significantly higher £3,888 in Year 2, largely due to the transition away from COVID-19-related interventions.

Evidence shows that job creation costs vary widely by sector and context. For example, IFC reports costs per job ranging from $715 in agriculture to $20,000 in services, with a weighted average of $8,600 per job. USAID uses a benchmark of $10,000 per job. PEPZII’s costs fall within these ranges but could improve through; Better learning to target SMEs with high job creation potential, and Diversifying intervention mechanisms to meet the varied needs of SMEs.

Current limitations include a lack of data for learning and reliance on a narrow set of financing instruments. Tailored support based on SME segmentation could significantly enhance effectiveness.

Overall, PEPZII’s cost per job is comparable to similar projects, but effectiveness could be strengthened through better targeting and a broader range of interventions. For example, reliance on returnable grants has limited growth for high-potential ventures, while fixed-term structures lack flexibility compared to revenue-based loans. Budget constraints have restricted intervention diversity, but in future programming, PEPZII should prioritize financing through intermediaries rather than direct grants for greater impact.
### Efficiency
### Prospero’s efficiency in SME financing is primarily assessed through its leverage factor, the extent to which Project funds mobilise additional private capital. The 2022/23 Annual Review reported a co-investment ratio of 1:1.2, indicating some grantee contribution. However, this is significantly lower than benchmarks from other blended finance Projects, where leverage ratios commonly range from 1:4 to 1:8 (e.g. Convergence studies, IFC, and Aceli Africa).A key reason for Prospero’s relatively low leverage lies in its capital-intensive approach, relying on grants and matching grants rather than more efficient tools like returnable grants or performance-based incentives. For instance, Aceli’s performance-based subsidies achieved a 1:6 leverage ratio in Tanzania by incentivising lending through financial intermediaries. Prospero, by contrast, often used costly matching grants even where returnable finance would have sufficed raising the cost of SME support to £86,000 per SME in 2021/22 and £50,000 in 2022/23.
The ZIBC £1 million full-cash coverage model for green SME lending appears less efficient when compared to approaches such as FCDO Tanzania’s Green Growth Fund, which links grant disbursements to lending performance milestones. Additionally, the absence of PLS limited Prospero’s ability to analyse and adopt more cost-effective financing mechanisms.
Conversely, PEPZII’s investment readiness and matchmaking services delivered through in-house staff, Impact Capital Africa (ICA), pitching sessions, and the Zambia Impact Investment Forum (ZIIF) have demonstrated strong efficiency. According to the 2022/23 Annual Report, ICA-supported deals have generated over £7 in additional investment for every £1 of PEPZII funds, with this figure expected to grow as older grantees close deals. This aligns with academic evidence that financial readiness and matchmaking typically achieve higher leverage than direct financing.
E: Risk [½ - 2 pages]

Overview of Project risk during the past year and over the life of the Project, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]

Throughout its implementation under the PEPZ II Project, Prospero maintained an overall ‘Major’ risk rating, reflecting a persistently challenging operating context. Risks were identified, tracked, and managed using the Aid Management Platform (AMP) risk register, and reviewed during monthly internal Board meetings. Two principal risks, COVID-19 and FCDO ODA reductions significantly shaped Project planning, delivery, and outcomes throughout the implementation period. These risks, alongside operational, financial, contextual, and human resource challenges, were managed through adaptive strategies and active oversight by both the Prospero Board and FCDO.

Contextual Risks

The broader Zambian operating environment remained highly unpredictable due to macroeconomic volatility, political transitions, and policy instability. Persistent inflation, currency depreciation, and rising public debt created an adverse environment for private sector growth.

High Government Turnover and Policy Uncertainty: Frequent changes in Government leadership and regulatory frameworks disrupted coordination with public institutions and created uncertainty for private sector actors. Although mitigating this risk was challenging, Prospero and FCDO engaged consistently with Government agencies and policymakers to maintain alignment and manage transitions. Ongoing contextual monitoring informed adaptive programming.

COVID-19 Pandemic: At the start of Project, the pandemic disrupted Prospero’s implementation strategy. Partner businesses faced operational threats, reduced market activity, and financial strain. To mitigate this risk, Prospero implemented a £1.2 million COVID-19 relief strategy, supporting 91 SME partners to sustain operations, preserve jobs, and develop resilience measures.

Delivery Risks

COVID-19: Delivery of interventions and business model support to SMEs was delayed or restructured due to Covid-19. Prospero changed its strategy to focus on stakeholder engagement, facilitation and advocacy to mitigate this risk.

ODA Reductions: Budget reductions in FCDO allocations from £4 million in FY22/23 to £2 million in FY23/24 led to paused or scaled-down interventions. In the 23/24 reporting year, Prospero revised their delivery strategy pausing Market Systems Development activities and focusing on investment pipeline development and technical assistance for investment readiness.

Financial Risks
Financial Management: Prospero encountered financial management challenges throughout the implementation period mainly attributed to high staff turnover in the finance department. Prospero’s financial processes needed strengthening and were closely monitored by FCDO. To manage this risk, FCDO developed a performance improvement plan (PIP) for Prospero in 2021/22 and in 2022/24 with agreed key performance indicators. The Board and FCDO provided close oversight on progress made as well as contracting an internal audit function which tracked implementation of FCDO recommendations.

Audit Delays: Prospero’s audits for FY2022/3 were delayed beyond the timeline stipulated in the Accountable Grant resulting in a temporary pause in FCDO disbursements from October 2023 to February 2024. Similarly, the 2023/4 audit was substantially delayed – having still not been completed almost two years after the end of that financial year.

People Risks

Finance Team Turnover: Over the reporting period, Prospero experienced high turnover in the finance department, including vacancies in all roles supporting the COO. This posed a challenge on Prospero financial management which led to FCDO providing scrutiny and close monitoring of Prospero financials. In the final year, FCDO engaged an external accounting firm to bridge gaps in financial management.

Leadership Gaps: Turnover in the Senior Leadership Team, including the CEO, affected strategic oversight. The Board provided interim leadership and accelerated recruitment for key roles. Several staff members took on expanded responsibilities to maintain operational continuity.

Early closure Risks
FCDO withdrawal from Prospero presented several risks including financial, reputation and delivery related risks. FDCO developed a comprehensive transition and fraud response plan to closely monitor and manage these challenges. Local legal advice was procured to ensure that FCDO’s exit from Prospero SPV was conducted in full compliance with legal obligations and responsibilities. In addition, the most critical communications between FCDO and Prospero were subjected to legal review prior to issuance.

F: Project Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]

Project Governance and Oversight

Prospero was overseen by a Senior Responsible Officer (SRO), supported by the Project lead who managed the day-to-day operations of the Project. The Project was governed by a Board of Directors composed of three member professionals with expertise in law, accounting, business, investment, and included representation from FCDO. The Board provided strategic direction and fiduciary oversight throughout the Project’s duration. Three standing committees - Project Investment, Finance, HR and Admin, Audit and Risk, and Nominations and Governance (ad hoc) met quarterly to guide decision-making and manage specific areas of Project performance.

Reporting and Due Diligence

Prospero consistently submitted monthly and quarterly reports detailing financial performance, progress towards results, implementation of annual review recommendations, and compliance with accountable grant requirements. Over time, the format and substance of reports were enhanced following feedback from FCDO and the Board, ensuring improved utility and accountability.

A due diligence refresh was conducted in 2023, complemented by spot checks and independent audits, served to validate reported results and assess organisational performance. Notably, in 2023, financial management weaknesses identified by FCDO led to the introduction of a Performance Improvement Plan (PIP), jointly implemented with the Board and monitored through quarterly internal audits. The plan contributed to improvements in financial reporting and internal control mechanisms.

Project Management Challenges

- The Project experienced significant management challenges, particularly related to staffing. High turnover in key positions including the CEO, COO, and Finance team created leadership and operational gaps that impacted strategic oversight and delivery consistency. In response, the Board played an active interim role, stepping in to manage the transition and fast-track recruitment. Several staff also took on expanded roles to cover gaps, ensuring continuity of operations. The capacity gaps also led to increased engagement from FCDO. This intensive oversight, while necessary, placed additional demands on FCDO resources and detracted from broader programming and influencing activities.
- Weaknesses in financial management continued to be a challenge throughout the Project lifecycle. This was predominantly due to high staff turnover in the finance department coupled with financial systems inefficiencies. This resulted in FCDO providing intensive oversight including risk based financial spot checks, heavy scrutiny of financial reports and monthly financial catch-ups.
- Annual external audits were conducted and the audited statements for the past audits were unqualified. The audit for the financial year 2022/23 delayed beyond the stipulated timeline in the accountable grant agreement leading to FCDO pausing funding to Prospero from October 2023 to February 2024 when the audit was completed. Notably, the audit for 2024/25 was equally delayed.
VFM
The FCDO choice of a “build rather than buy” option as a delivery mechanism has resulted in high operating costs: The creation of the SPV has necessitated (i) the development of sophisticated management systems. The financial management system should have been aligned with Prospero’s CLG status, enable effective financial control and reporting related to the disbursement and recycling of funds, and mitigate fiduciary risks. The HR management system should have also been aligned with Prospero’s CLG status and in-house delivery model; (ii) High staff costs, including staff across key management functions, internal appraisal related to both grants and financial facilities managed by third parties, disbursement and portfolio monitoring, the management of technical workstreams, monitoring and evaluation and the in-house and sub contracted delivery of business support services. The level of Board fees plus overheads in terms of staff costs, rent, SAGE, internal audit, and external audit mean greater scale was required to achieve VFM.

Project-level approach to monitoring and evaluation [1/2 page]

Monitoring
Throughout implementation, Project performance was monitored regularly through structured and multi-layered mechanisms. Quarterly progress meetings enabled FCDO and Prospero’s leadership to track progress against the logframe targets, risk management and financial performance. Regular reporting, combined with the review of quarterly progress reports, monthly expenditure and forecasts, ensured that decisions were based on up-to-date operational insights.

Internally, FCDO provided close external oversight. The SRO, supported by the Project lead engaged with Prospero regularly. FCDO held monthly internal boards to review progress, compliance, risk, and financial performance. Project performance was also reviewed quarterly by the FCDO Zambia Project portfolio scrutiny board, ensuring timely identification of issues and enabled responsive course correction.

Formal annual reviews were conducted to assess progress against the logframe, evaluate impact and identify risks and lessons learnt. These were carried out by the Project team and reports were shared across the office and published on the Development tracker.

In addition to formal oversight processes, FCDO and Prospero maintained strong engagement with field-level stakeholders. Regular field monitoring was conducted by FCDO to engage with beneficiaries and assess Project impact. Beneficiaries noted the value of Prospero’s technical and financial support, which enabled business expansion and job creation. These visits provided qualitative insights into the effectiveness of Prospero’s support and informed strategic adjustments. Gaps in visibility of UK Aid branding at beneficiary sites were observed, with Prospero advised to address this as per grant requirements.

Date of last narrative financial report	30th September 2025	Date of last audited annual statement	31st March 2024