Business Case
Summary Sheet

Department CDD/Portfolio/ Business Plan Summary: / The United Kingdom’s Business Plan for Kenya has the following vision, aligned with the UK’s new Strategic Approach to Africa: A prosperous, safer, healthier Kenya which sees the UK as a partner of choice for peace, trade and economic development, is less reliant on aid and more resilient to shocks and stresses. The Kenya Country Development Diagnostic (CDD) 2019 identified corruption and patronage, lack of effective government coordination, a lack of county-level capacity/will and a concentration of poverty in the arid lands as key barriers to development and poverty reduction. It further identified devolution as an important entry point for improving incentives for service delivery and reducing corruption, building county capacity to manage public funds and natural resources, raise revenue, and be accountable to citizens for service delivery. This programme will contribute to SDG 16: Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective accountable and inclusive institutions at all levels.

Title: The Kenya Devolution Support Programme II
Programme summary (100 words maximum): / This is the successor programme to the Kenya Devolution Support Programme (KDSP), 2015-19. It will aim to strengthen the effectiveness of Kenya’s devolution process, specifically to improve development results by strengthening effective, open and accountable County Governments that improve service delivery and reduce poverty. The programme aims to achieve the following outputs: / Intergovernmental relations support devolution / County governments effectively manage public finances, staff performance and county planning / Government and citizens collaborate effectively to address key problems in service delivery and poverty reduction. / Evidence generation, learning and digital approaches improve county government delivery. / The UK development portfolio is better aligned with county government priorities. / A combined set of interventions is required to have a maximum development impact. The programme will provide technical assistance to national and county government and also support civil society to build accountability. Citizens in target counties will benefit from improved service delivery by county government. The deployment of a limited number of programme-funded staff will further strengthen the depth of UK partnership with county governments. This business case includes a break clause which will be replicated in all partner agreements. Funding from March 2024 will require additional approval in 2023.
What is the rationale for UK Aid spending? (200 words maximum): / The full potential of devolution may not be realised with widespread repercussions for Kenya’s development prospects. Effective devolution is a pre-requisite for government delivery of services and a sustained reduction of poverty in Kenya. Effective devolution is also an essential enabler for the wider DFID strategic portfolio, in particular for our priorities of health, disaster risk reduction, climate change governance and urban economic development. This programme will also support a favourable investment environment and our wider prosperity strategy. It will contribute to stability and in the medium term reduce Kenya’s dependency on aid. This programme will support cross-HMG efforts to deepen UK relationships with increasingly influential county governments. The UK is the co-chair of the Sector Working group on Devolution with the Kenyan Ministry of Devolution and the ASALa, and as such we lead development partner coordination. This programme supports the UKAID strategy and Kenya Business Plan.
Programme Value: £38.5m		Country/Sector: Kenya Governance
Country Office Contact name
Threshold for Approval of Business Case: <£40m		DD/ HoO:
Date of Approval of Concept Note:	26/06/19	Name of Approver:
Date of Approval of Business Case		Name of Approver:
Programme Code: 300645	Start Date: Jan 20	End Date: 30 June 2025
Overall programme risk rating:	Moderate
Vault Number:

Strategic Case

Context

Kenyans approved a new constitution in August 2010, which fundamentally changed the Kenyan governance system from a highly centralised state. Devolution was a monumental change with the establishment of 47 new county governments.[1] The National and County levels of government are distinct but inter-dependent and are required under the constitution to consult and co-operate. Devolution is arguably the single most important governance reform since the reintroduction of multiparty politics in Kenya. It came about as part of reforms to resolve the underlying causes of the 2007/8 post-election violence. It enjoys huge public support and is widely viewed as an opportunity to address underlying causes of conflict, inequality within society (e.g. ethnic divisions; and issues for women; youth; persons with disabilities) and improve accountability.[2]
[1] County governments consist of the County Executive headed by a governor, and a County Assembly made up of elected and nominated ward representatives and headed by a speaker.
[2] Poor governance post independence had led to the alienation of large portions of society and geographical areas from the mainstream economy; wasteful public investments; massive poverty and ethnic animosity; and cut-throat political competition and intolerance: Republic of Kenya (2011), Final Report of the Taskforce on Devolved Government

The overall purpose of shifting to a devolved system of government is best captured in articles 174 and 175 of the 2010 constitution. These articles emphasise that devolution should: allow for self-governance by the people; promote the democratic and accountable use of state power as well as public participation in decision making; promote and protect the rights and interests of minorities and marginalised groups and; promote social and economic development and the provision of easily accessible services throughout Kenya. Translating these objectives into reality is an enormous challenge especially since Kenya has had to create an entirely new tier of government.

Except for primary and secondary education, the constitution devolved most other service delivery functions, such as health and agricultural services, to counties while retaining policy functions such as health policy, agricultural policy, macro-economic policy, internal security and defence at the national level.[3] New laws and policies have been approved and enacted,[4] existing ones amended, independent offices and commissions established, and county governments, assemblies and a Senate formed.[5] Devolution is now one of the 24 Medium Term Plan sectors and aligned to the National Capacity Building Framework.[6] Over the last 6 years, £13.3 billion has been disbursed to County Governments.[7] This is about 20% of total government spending. 93% of this comprises the unconditional equitable revenue share for which counties have autonomous budgeting, expenditure and accountability responsibilities and 7% is conditional grants from national government and development partners.
[3] See Schedule 4 of the Constitution.
[4] Key laws and policies relevant to devolution include: The Public Financial Management Act; the County Governments Act; the Inter-Governmental Relations Act, the Urban Areas ad Cities Act and the Devolution Policy.
[5] Independent Commissions and Offices established include: The Commission for Revenue Allocation (CRA); the Council of Governors (CoG); the Inter-Governmental Relations Technical Committee (IGRTC); the Inter-Governmental Budget and Economic Council (IBEC); the Ministry of Devolution and ASALs; and the Controller of Budget (CoB) amongst others.
[6] Political pressure from counties saw Kenya forego the planned phased and asymmetrical approach, and instead adopt a “big-bang” approach, with most devolved functions being devolved to counties by July 2013, less than 6 months after the county governments came into office.
[7] http://www.crakenya.org/information/revenue-allocation-formula/

There has been variable progress with devolution overall. There have been some successes but also examples of waste, mis-management and corruption, as evidenced by reports of the Auditor General and Controller of Budget. The full potential of devolution may not be realised, with widespread repercussions for Kenya’s development prospects. Counties had very different levels of development at the outset of devolution due to geographical and historical factors. Counties did not start from a level playing field and some will need far greater levels of assistance than others. Devolution also created new centres of power and new minorities.[8] Several laws and policies have recentralized devolved functions resulting in constant disputes over the extent of devolving the resources of functions such as roads, agriculture and water[9] and health.[10] Our approach to date has recognised the opportunities and challenges and we have seen concrete results from our investments. As county government systems are only six years old, there is an opportunity to set new standards in establishing public financial management PFM systems.
[8] Intra-governmental conflicts affect service delivery especially where Governors are from minority parties/coalitions compared to the majority in the assemblies. New minorities within counties including in urban settings generate new tensions especially where their economic activities are seen as competition for the county elite. Such tensions have been reported in Mandera County where non-local teachers are consistently under threat and have boycotted classrooms in Mt. Elgon/Bungoma County where militias have re-emerged. Additionally, inter-county competition has grown where national or regional projects fall along county boundaries making these border towns and minority communities from rival counties residing there vulnerable to conflict. Examples include the disputes over Maseno town between Kisumu County and Vihiga County; between Machakos and Makueni Counties over Konza City; Turkana , West Pokot and Baringo counties over the resource rich Kapedo region; Kisii and Nyamira counties over Keroka town and Isiolo and Meru counties over the Isiolo International Airport
[9] This was highlighted in the State of Devolution Report 2017 by the then Chairman of the Council of Governors Hon. Peter Munya
[10] A DFID funded study on county hospital autonomy under devolution in Kenya found that while Kenya’s healthcare system was fairly well decentralized with some autonomy over key functions (human resource management, financial management, procurement, strategic management and hospital administration), they experienced significant reductions in autonomy in these functions because they were transferred from the hospitals to the county health departments Barasa EW, Manyara AM, Molyneux S,Tsofa B (2017) Recentralization within decentralization: County hospital autonomy under devolution in Kenya.

Supporting devolution is in the UK’s interest and is in line with the National Security Strategy and the cross-HMG business plan. The UK is considered by the Government of Kenya as an important partner in the governance sector as a whole and devolution specifically. Investing in subnational governance is essential for Kenya to build the systems and processes to sustainably raise revenue and pay for (and oversee) the delivery of services and support an eventual exit from aid. It is important that we engage over a longer period to embed institutional reforms and enable county governments to raise revenue and sustainably deliver public services. This programme can also support the wider UK aid programme in Kenya to be well coordinated with county government priorities.

Supporting devolution presents an opportunity to

Reduce poverty: Kenya’s 2010 constitution devolved important functions that have a direct impact on development and poverty reduction such as health, water, agriculture[11] and local environmental management. For example, in historically marginalised regions of northern Kenya, the first tarmac roads have appeared (supporting economic growth) and maternal health indicators which were among the worst globally have improved (but are still amongst the worst in the world). The 2017 Economic Survey of the Kenya National Bureau of Statistics reported growth in the agriculture sector since devolution, the biggest contributor to Kenya’s GDP, jobs and livelihoods. The challenge remains significant however and 36.1% of Kenya’s population still live on under $1.25 a day, higher than in Ethiopia or Uganda. Due to population growth, the overall number of poor[12] remains largely unchanged at 16.4 million compared to 16.6 million a decade ago.[13] There are 3.9m people in extreme poverty[14] in Kenya, an estimated 8.6% of the total population. Over the past decade rural poverty declined from 50 percent to 38 percent whereas urban poverty stagnated. The number of urban poor increased from 2.3 million to 3.8 million; Nonetheless, the majority (almost 80 percent) still reside in rural areas.
[11] Anecdotal evidence from KDSP implementing partners suggests positive impacts from County government extension initiatives in several counties including Kitui (ndengu - green gram), Makueni (dairy and fruit processing) and Muranga (diary and AI). A recent study in Wajir was also positive. However, awareness of devolved agriculture extension services – and hence ability to benefit from them – is limited; a 2017 study in Meru found that slightly less than half of farmers knew that the County provided extension services.
[12] Overall Poverty: households and individuals whose monthly adult equivalent total consumption expenditure per person is less than Ksh 3,252 in rural and peri-urban areas and less than Ksh 5,995 in core-urban areas are considered to be overall poor or live in “overall poverty”.
[13] Households surviving on less than Ksh 3,252 per month in rural and peri-urban areas and less than Ksh 5,995 in urban areas.
[14] Ultra or Extreme Poverty: households and individuals whose monthly adult equivalent total consumption expenditure per person is less than Ksh 1,954 in rural and peri-urban areas and less than Ksh 2,551 in core-urban areas respectively are considered to be hardcore poor or live in “hardcore or extreme poverty”. Extreme poverty incidence remains highest in rural areas, with 11.2 per cent of residents (3.2 million individuals) extremely poor.

Reduce inequality: Development particularly lags behind in the northern arid lands, with the highest depth of poverty and lowest scores against a range of development indicators, particularly for women and children.[15] Kenya is urbanising rapidly beyond the capital. Devolution provides an opportunity to improve the allocation of public expenditure and deliver services based on local rather than national priorities.
[15] Women and children in the North and East are severely disadvantaged compared to the rest of Kenya. Only 21% of women in Wajir give birth with the help of a skilled birth attendant, compared to the 62% national average. Furthermore, only 28% of children in Mandera receive all basic vaccines, compared to the 71% national average.

Improve accountability: Early evidence suggests that under devolution, communities are more able to demand better services and hold government to account.[16]
[16] Kenya Devolution Support Programme Annual Review 2018, also Deepening Democracy programme 2019 Annual review

Reduce instability: inequality, a lack of opportunity, poor service delivery and weak management of natural resources (water, energy, land, forests) are drivers of insecurity and conflict, which in turn negatively affects livelihoods, investment and service delivery. Devolution provides an opportunity to better understand and manage the root causes of conflict. It also provides an opportunity to address historic grievances of different regions of Kenya including historical secessionist movements in the coast, north east and north west, contributing to longer term stability.

Reduce aid dependency: Having reached lower-middle income status, growing at over 5%, Kenya is a regional powerhouse and the trade gateway to the region and beyond. Kenya has made some progress on reducing multidimensional poverty[17] and collecting revenue.[18] Kenya is less aid dependent than many countries.[19] However, revenue collection at the sub-national level is sub-optimal. The Controller of Budget reports in 2019 that overall counties have improved in generating own source revenue but are still short of the potential estimated by the National Treasury.[20] Own source revenue increased by 24% during financial year ended June 2019 to reach Ksh40.3B compared to the previous four-year low of Ksh32.49B This is attributed to efficiency in collections, especially in counties that partnered with the Kenya Revenu Authority (KRA).[21] Building the systems within the Kenya government at the sub-national level to raise revenue and effectively manage public finance and deliver services, is a pre-requisite for a self-financed exit from poverty.
[17] 51% of the population suffers multiple deprivations of wellbeing in 2008, down from 60% in 2003.
[18] 15.9 % GDP in revenue collection in 2012.
[19] Although 30% of health financing still comes from development partners such as for drugs for HIV/TB, Malaria, vaccines and family planning commodities.
[20] https://cob.go.ke/reports/consolidated-county-budget-implementation-review-reports/
[21] Fifteen counties recorded at least 50% increases, while 38 counties meet at least 50% of the budgeted collection targets. Lamu, Vihiga, Taita Taveta, Narok, Elgeyo Marakwet, Isiolo, Nakuru, Bungoma, Tana River, Kwale, Laikipia, Kirinyaga and Kiambu exceeded their annual targets. Homa Bay, Kisumu, Samburu and Wajir are not meeting targets.

Address extreme poverty. As mentioned above Kenya has 16m absolute poor, and almost 4m extreme poor. DFID has led on the development of social protection systems and is now exploring pilot ‘graduation programmes’ which aim to support the extreme poor to graduate from humanitarian / social protection support. Beyond individual projects, this requires strategies at the county level to ensure better targeting and coordination of development programmes to create graduation pathways that effectively foster livelihood and employment opportunities for the extreme poor. This programme will invest in sub-national knowledge generation and strengthening the coherence of county policies and programmes to improve service delivery impacts on poverty.

Support sustainable urban development. Kenya is rapidly urbanising. The Urban Areas and Cities Act has bestowed upon 45 county headquarters (excludes Nairobi and Mombasa) the status of municipality and 14 additional towns also met the threshold for classification as a municipality when this act was amended. All 59 municipalities must establish a Municipal Board that oversees urban development.  DFID has initiated a Sustainable Urban Economic Development Programme (SUED) which supports urban development in secondary towns in 12 counties. Urban development is devolved, and the Devolution programme team has worked closely with the SUED team providing political economy advice. The Devolution programme’s planned technical assistance to county governments can ensure that our investments in county capacity and urban development re-enforce each other and are poverty focussed.

Improve Health and Nutrition: The impact of devolution in the health sector has been mixed. Historic inequities have been addressed to some extent, with historically marginalized counties benefitting from increased financial resources and autonomy over how these are spent, resulting in improved access to health services across the country.[22] However, recent evidence suggests that in some counties devolution has resulted in weakened hospital management and leadership, reduced community participation in hospital affairs, compromised quality of services,[23] reduced motivation among hospital staff, and compromised the quality of care.[24] Delays in financial flows from National to County governments has also resulted in many health workers going for months without pay leading to repeat health worker strikes. Despite county level investments in health increasing, there has been a reduction of overall public financial investment in health in the last few years.[25] The speed of devolution has led to poor management and confusion regarding roles and responsibilities between the different levels of government. Both immunisation and family planning, two of the most cost-effective best-buys in health, have been adversely affected by devolution and both remain heavily dependent on donor funding. [26] There is a risk of stagnation in key areas, such as: maternal and neonatal mortality decline; uptake of modern contraception; and reduction in HIV prevalence.
[22] World Bank report, The Kenya Devolution Study; Health Sector report, forthcoming 2019 (still being finalized): this report as found that there have been some significant investments in the health system since devolution (2014 – 2019). There has been a massive investment in infrastructure (the number of government health facilities increased by 33.6% from 4,456 to 5,953 nationally) and an impressive increase in the numbers of health workers (e.g. a 72% increase in Kilifi and a 42% increase in Kwale). Investments like these have contributed to a much greater access to health services for the average Kenyan. 95% of the population now lives within 5km of a health facility (although there remain significant regional inequities).
[23] Large-scale investments have not always represented good value for money. For example, limited rationalization of where new health facilities were built (no obvious rationalized linkage between construction of new facilities and actual need) and examples of over-investment in tertiary level care and high-end equipment (eg MRI scanners, siting unused in facilities) at the expense of essential primary-level care
[24] Recentralization within decentralization: County hospital autonomy under devolution in Kenya Edwine W. Barasa, Anthony M. Manyara, Sassy Molyneux, Benjamin Tsofa
[25] Pre-devolution in 2011/2012, 8% of the national budget was allocated to health (the highest reached in the last 20 years). This has since steadily fallen, to 7% in 2013/4, 6% in 2015 and 2016. Kenya has, like many other African nations, signed up to the Abuja declaration in 2001 to allocate 15% of the national budget to health. Another very visible example is national childhood immunisation coverage rates which were at 96 and 94% in 2011 and 2012 respectively, then fell to 87% in 2013 and remained between 87% and 92% from 2013 to 2018 and are still not back to pre-devolution coverage rates. See WHO immunization data for DPT3 (standard coverage indicator). https://www.who.int/immunization/monitoring_surveillance/data/ken.pdf
[26] Pre-devolution (in FY 2012/2013), GoK was financing almost half of all national commodity costs (DPs met the other half) and their contribution was increasing year on year. For the last six years post-devolution, FP commodities have been almost 100% financed by DPs. This is mostly because counties thought FP commodities were a national level responsibility (like some other programmes which remained centralised such as HIV/AIDS, TB, malaria) and central GoK thought purchasing FP commodities was a county level responsibility.

Counties require support to ensure that service delivery is inclusive and county health budgets and plans need to reflect the priorities of women, children and other vulnerable groups. Our previous support to planning has led to the establishment of sector working groups at the county level for health and these have coordinated public participation in the budget development process which has improved targeting of service delivery. In Mandera, for example, this has led to increased government budget allocations for maternal and newborn health which has in turn seen a significant improvement in a reduction of maternal deaths. A greater emphasis should be placed on service delivery outcomes and robust measurement of our contribution through supporting devolution.[27]
[27] This programme will work closely with the DFID health team and health programmes to help develop capacities and systems needed to ensure counties can sustainably manage and deliver quality health services. A key priority remains maintaining investment in prevention and in primary health care services to sustain and build on previous health gains.

Improve Natural Resource Management, Climate Change Governance and Disaster Risk Reduction: Demographic and climatic pressures make Kenya susceptible to disasters and fragility. Drought currently costs 2.4%[28]of GDP per annum and may rise with the effects of climate change. Kenya’s vulnerability to climate change is further affected by governance issues, including: relatively weak institutional capacity, low resource management capabilities, inadequate technology and information infrastructure as well as land degradation, which combined, pose serious hurdles to effective climate change responses. Inequity in access to natural resources often leads to conflict over resources. If not addressed, climate change will hamper progress towards the SDGs and disproportionately impact vulnerable groups, especially women and those living in the arid and semi-arid lands and coastal regions. County governments have a key role to play in supporting climate change adaptation and natural resource management. UK support to date has helped a number of counties legislate on climate change and disaster risk reduction, as well as to improve coordination on management of the environment and community land.
[28] The World Bank calculates that on average, every seven years Kenya experiences a flood that costs about 5.5 percent of GDP), and every five years experiences a drought that costs about 8 percent of GDP. This translates to a direct long-term fiscal liability of about 2.4 percent GDP.

Evidence

Global evidence on devolution is extensive, especially from countries such as the UK, Nigeria, South Africa and India. A growing body of global evidence and experience indicates that devolution itself does not guarantee that public finances, services, and decision-making will become more responsive to the people.[29] In many contexts, decentralization is accompanied by service delivery disruptions, and increased waste, leakage, and inequity. Surveys and case study research suggest that a serious impediment to effective devolution is the weakness of local institutions intended to play a major role in the accountability framework. Local officials (even more than their national counterparts) may be subject to the risks of capture and clientelism. Oversight institutions at the local level generally lack the independence and capacity to check these risks. Nonetheless, evidence from Kenya shows that devolution is starting to deliver results, and that long-term patient approaches are required for the gains of devolution to be sustained.
[29] Scott, Z. (2009), Decentralisation, Local Development and Social Cohesion: An Analytical Review, GSDRC Research Paper, May 2009, Governance and Social Development Resource Centre and Admad, J., Devarajan, S., Khemani, S., and Shah, S. (2005), Decentralization and Service Delivery, World Bank Policy Research Working Paper, 3603, May 2005, World Bank.

Kenya’s devolution experience is now six years old. There is a rich repository of data and analysis at the Controller of Budget Office in Nairobi and published annual and quarterly reviews of national and county government expenditure. Kenyan universities, NGOs, public policy research institutions in different sectors such as health and agriculture are generating extensive data now disaggregated by county, and increasingly by sub-county.[30] DFID is part of a World Bank steering committee that is designing and managing qualitative studies on the impacts of devolution in Kenya to date. The World Bank, with DFID support, has also published the Gross County Product (GCP) 2019 in conjunction with the Kenya National Bureau of Statistics (KNBS). DFID has provided technical assistance to the Council of Governors’ Maarifa Centre, a repository of county government reports and studies.
[30] These include the University of Nairobi’s Institute for Development Studies and Strathmore University’s Centre for Devolution Studies, Kenya Institute for Public Policy Research and Analysis (KIPPRA), Commission for Revenue Allocation, Kenya National Bureau of Statistics (KNBS), civil society organizations like the Institute for Economic Affairs, Africa Centre for Open Governance and International Budget Partnership. Development partner programme reviews and evaluations are also shared and discussed extensively in Kenya, providing valuable lessons, including the World Bank, UNDP, DANIDA and EU.

With KDSP support, the Institute for Development Studies of the University of Nairobi commissioned the County Capacity Assessment (CCA) Index in 2016 which is now in its fourth year. This index has provided annual data on the impact of its capacity building interventions. Average capacity and performance assessment scores increased from 33% in 15/16 to 64% in 17/18. And the number of disclaimed county audits reduced from 22 to 5 from 16/17 to 17/18. Additionally, the Devolution Study Group regularly convenes devolution experts and practitioners to discuss and distil lessons from the Kenyan devolution experience under Chatham House rules. KDSP invested modestly in digital, technology and innovation.[31] There is mixed evidence to date on the effectiveness of digital approaches in supporting devolution. More will be generated through this programme.
[31] Examples include: an SMS platform in Meru County for citizens feedback to the county government; a GIS laboratory in Makueni County; the Maarifa Centre information portal in the Council of Governors; performance management system in Kericho county. Each of these digital projects improved service delivery and the new programme will scale up these interventions guided by Kenya’s Digital Economic Blueprint 2019 and DFID’s Digital Strategy.

There is emerging evidence that devolution in Kenya is already delivering results, but has the potential to deliver many more. For example, local economies have grown significantly since devolution (see the County Domestic Product assessments) and there is growth in the agricultural sector (see the annual KNBS economic survey). Devolution programmes have played a key role here, for example in promoting county and regional livestock sector policies, which have had a most significant impact in historically marginalised counties.

DFID’s support to Devolution in Kenya to date

The UK has supported devolution in Kenya since 2013 and has so far invested more than £28m.[32] The £23.5m Kenya Devolution Support Programme (KDSP) will close in December 2019. It was implemented through three pre-existing devolution programmes: The World Bank’s Kenya Accountable Devolution Programme (KADP), a multi-donor trust fund also funded by USAID, EU-Delegation in Kenya, Sweden, Finland, Denmark and Norway; the UNDP’s Devolution Support Programme also funded by Finland, Norway, Sweden and the USAID; and the USAID initiated Agile and Harmonised Assistance for Devolved Institutions (AHADI) programme. DFID Kenya invested in innovation and efficiency by including a component on learning and coordination between county governments and development partners to help identify and build on approaches that work well.
[32] Through the following programmes: World Bank Kenya Accountable Devolution Programme (£4.8m, 2012-15) - USAID-managed Bridge Devolution Programme (£1.2m 2013-14) - UNDP Devolution Support Programme (£0.5m 2014-15) - Kenya Devolution Support Programme KDSP (£22.5m 2015-19) implemented by the World Bank, UNDP and SUNY/AHADI.

Implementing devolution across 47 counties is an enormous task, however evidence suggests that as a result of DFID support, capacity in the counties is increasing[33] and DFID support has made contributions in the policy and regulatory framework that underpins devolution, county capacity and public participation (involving special interest groups such as people with disabilities, women and youth) has improved as counties made more deliberate efforts to engage citizens in planning processes.
[33] For example, results of the DFID funded County Capacity Assessment (CCA) indicate that the county capacity has increased from 70.3% to 77.7%.

DFID’s experience of supporting devolution for the last three years has faced a number of setbacks and challenges. Most critically in some counties, political disputes between the county executive and legislature have caused delays in budget approvals and expenditure. A number of counties have had corruption scandals and received adverse audit reports. There has also been public dissatisfaction in a number of counties where minority groups perceive they have been excluded from the benefits of development programmes.

In relation to the above challenges, DFID Kenya has made a series of politically informed decisions to steer KDSP towards greater partnership with counties that are making progress on institutional collaboration, accountability and equity. For example, the programme has scaled up support to Makueni county based on high performance and the first unqualified audit report from the Auditor General. In Nairobi County, the programme has scaled down support for a year owing to multiple political disputes between the executive and legislative disrupting progress. The High Commissioner has publicly called for governors who have been implicated in alleged corruption scandals to step aside while investigations are concluded. We have also supported, though other programmes, the work of the Ethics and Anti-Corruption Commission (EACC) and office of the Auditor General (OAG) in this regard. DFID Kenya has approved annual workplans of implementing partners and has ensured Value for Money (VfM) by increasing funding allocations to those partners that have been most responsive to the challenges described above.

The 2019 KDSP annual review scored an A. It found that
There have been some significant changes in policy and practice as a result of DFID support. KDSP made contributions in the policy and regulatory framework that underpin devolution, including for public financial management,[34] procurement, public sector remuneration, performance management, planning, public participation, human resource management, climate change and disaster risk mitigation.
[34] The World Bank has improvements in public financial management (PFM) in the counties with two counties receiving unqualified audits for the first time since devolution began. There is “a gradual improvement in the number of counties with disclaimed and adverse audits decreasing compared to previous years” according to the 2016/17 records.
- County Integrated Development Plans (CIDP) are becoming more service delivery focussed and gender-responsive and have increased budget allocations and use of performance indicators for climate change.
- Civil society organizations and county assemblies have strengthened civilian oversight over county governments and legislative oversight over the county executive.
- The Maarifa Centre, at the Council of Governors, serves as a repository of lessons and coordinates peer learning events.
- Regional Economic Blocks of Counties are increasingly recognised by county and national governments as playing a potentially highly significant role in development policy.[35]
  [35] KDSP has supported the Frontier Counties Development Council, the Lake Region Economic Block, the North Rift Economic Block and the Coast (Jumuiya ya Kaunti za Pwani) blocks. The programme also supported the National Ministry of Devolution and the ASALs to develop an overarching policy and legal framework and the Inter-Governmental Relations Technical Committee (IGRTC) in convening national and county government organs to continuously improve devolution processes.
- DFID[36] has a key role to play in shaping the next generation of devolution programmes.
  [36] DFID currently chairs the devolution donor working group and convenes meetings amongst the devolution donors (EU, Sweden, Denmark, Finland, US, UNDP, World Bank, GIZ) and also between the donors and government stakeholders. The donors have a joint implementation matrix which the track monthly to ensure that the interventions are coordinated. DFID’s devolution programme is aligned to the government’s national capacity building programme and guided by the devolution policy.

The KDSP Annual Review recommended that the new DFID devolution programme should
Increase emphasis on achieving measurable improvements in priority sector specific service delivery results (such as health) and advance also the UK’s role in promoting digital approaches and solutions to improve impact and inclusion.
- Develop further the UK’s role in championing the inclusion agenda, with a focus on the opportunities devolution provides for the empowerment of youth, women and persons with disabilities.
- Undertake a thorough review of VFM methodologies available for assessing governance programmes and their potential to strengthen management and measurement of devolution support interventions.
- Continue to strengthen intergovernmental relationships, and the new regional economic blocks, aligning with priority reform commitments such as those made at the Annual Devolution Conference and Annual Legislative Summit.
- Conduct Political Economy Analysis in counties where political constraints have caused major variations in progress.
- Continue to shift towards a greater influencing role for the UK on devolution, including through more direct staff time spent with key senior government representatives.
- The DFID Kenya governance team should increase their advisory support to other DFID teams including Human and Social Development (health, disaster risk reduction) and Sustainable Economic Development (urban development and value chains).

DFID has also implemented a Deepening Democracy Programme (DDP) which is now drawing to a close. This programme supported a wide range of local civil society efforts to hold county government to account for service delivery. The DDP August 2019 Annual Review scored this workstream an A+ and found that it has effectively promoted engagement between citizens and government in accountable service delivery and climate change governance across the country.[37] It further recommended that DFID build learning from the social accountability and oversight workstreams into the design of the new Devolution programme in order to better facilitate information flows and relationships between county based civil society organisations (CSOs) and county government decision-makers.[38]
[37] Progress was variable across the wide range of interventions across the country, and will be more assessed again at the end of next year
[38] See DDP August 2019 annual review. See also DDP independent Mid-Term Review September 2019

In recognition of the significance of devolution, DFID Kenya has developed a sub-national strategy which this programme will resource. DFID has recruited an A2 advisor to lead this strategy. Two programme funded county based A2L advisors are currently based in Kisumu and Turkana and recruitment has been recently completed for Isiolo and Mombasa. The DFID’s sub-national strategy’s purpose is to:
Improve the coherence and relevance of the full DFID aid portfolio at the sub-national level in Kenya and join up individual programmes for greater impact.
- Increase the impact and VfM of our portfolio by strengthening coordination with other development partners and ownership by county government.
- Enhance our political influence by building strategic relationships at the county level, with national and county government, private sector and civil society.
- Improve our knowledge of the subnational context and political economy, and our ability to supervise, monitor and audit our programmes, manage risk and achieve value for money.

A significant amount of UK aid is spent in counties on priority sectors and can be supported and amplified by this programme
In the health sector, for example, DFID’s support to the World Health Organisation (WHO) helped establish, orientate and build capacity of county health management teams (CHMT) and development of county level tools for strategic planning, annual planning and annual performance monitoring that were subsequently used by all counties.[39] This programme can re-enforce these gains by supporting counties to plan, budget and manage resources to the health sector more efficiently.
[39] WHO also undertook a survey to look at ‘Service Availability and Readiness Assessment Mapping’ (SARAM) that provided valuable information for counties on the availability and capacity of their health facilities to provide basic health services.
- DFID Kenya has also supported 14 counties in helping communities cope with the effects of climate change.[40] This has involved the creation of County Climate Change Funds to support climate resilience projects, in line with the Government of Kenya’s 2010 National Climate Change Response Strategy and 2013 National Climate Change Action Plan. This devolution programme can support counties to address the climate change challenges (in climate sensitive sectors like agriculture, energy, water, livestock).
  [40] Under the Stark+ and DDP programmes.
- The DFID Kenya Sustainable Urban Economic Development Programme (SUED) is supporting urban development in 12 counties. KDSP has worked closely with SUED to reinforce strong county planning.

Through our role in the Devolution Donor Working Group we are aware of the investments and future plans of other development partners. The World Bank remains by far the largest contributor to devolution through grants and loans, including for capacity building, development interventions in northern counties (the NEDI initiative) and support to urban development. USAID has been a lead donor in the devolution sector and appears likely to increase support to civil society and social accountability. The EU is planning a programme of financial aid, and the Danish government have been implementing one for a number of years. UNDP has developed a new multi-donor fund for devolution and has received initial pledges to it. Other key development partners supporting devolution include GiZ, Norway, Finland and Sweden.

The UK’s comparative advantage lies in our role as the largest donor to capacity building for devolution and our ability to a) invest in a shape the programmes of others, while b) promoting innovation and knowledge management (such as through our sub-national strategy).

Future Priorities

Whilst there has been significant progress in improving the capacity of county government, there remain gaps. DFID recognises there is a need to engage over a longer period to embed institutional reforms and enable the county governments to raise revenue and sustainably deliver public services. Long term patient approaches are required to help build the systems (e.g. public finance, including revenue raising and service delivery/oversight) that can unlock devolution’s full potential to significantly address poverty in Kenya.

To support Kenya’s Devolution process to better address poverty, future priorities include:
Strengthening inter-governmental collaboration
- Enhancing public expenditure management,[41] financial management and[42] internal audit[43]
  [41] Planning, budgeting, fiscal discipline, allocative efficiency and operational efficiency
  [42] According to the Auditor General (2015/16) and Controller of Budget (2016/17) reports. There has been an increase in qualified audit reports from the counties according to the Auditor General with 3 reported in 2013/14, 5 in 2014/15 and 13 in 2015/16.
  [43] And county fiscal units modelled after the Parliamentary Budget Office
- Strengthening performance management and contracting
- Tackling corruption and wasteful expenditure
- Strengthening county government revenue collection
- Addressing significant human resource and revenue gaps.
- Strengthening county assembly oversight[44]
  [44] Involving County Assemblies early in climate change and disaster risk management planning has ensured that when the Executive propose an increase in the budgetary allocation to mitigate climate change impacts, assemblies have not objected to this increase.
- Improving civil society access to information and county government officials.
- Addressing fragmented donor activity at the sub-national level
- Ensuring improvements result in measurable improvements in service delivery
- Supporting service delivery targeting better impact on poverty

This programme will contribute to making devolution more effective in Kenya, with a focus on poverty reduction. It will aim to improve development results at county level by strengthening effective, open and accountable County Governments and effective civil society to hold government to account.

The overall impact this programme will aim for is: Improved development results at county level.

The expected outcomes by 2025 are that:
More effective, open and accountable County Governments
County Governments improve service delivery and reduce poverty

The main risks the programme present for HMG are political and reputational. The programme will work closely with national and county government and this will associate HMG with the devolution process in Kenya. The process of devolution itself may become politicised (for example through the potential constitutional review process). A more direct risk would stem from political contestation within counties (i.e. in the upcoming 2022 elections) or major scandals in target counties (i.e. corruption scandals). We will mitigate these risks through a robust and live (cross-HMG) political economy analysis, close monitoring on the ground including through programme funded posts and a regular review of our partnerships and targeting of counties.

Gender equality impact statement
A gender analysis will be conducted during the mobilisation phase to inform a gendered approach to the programme and will consider the impact on gender equality of all interventions. The results framework will include both sex disaggregated indicators as well as indicators to measure increases in women leadership across key areas of governance (executive and county assemblies). This programme will be fully compliant with the Gender Equality Act. This programme will ensure compliance with legal and constitutional requirements for equality, non-discrimination and inclusion. It will conduct gender audits of county government budgets and plans. It will support disaggregated gender data in the county performance management system and support county governments to use these data to better target service delivery (e.g. that health services respond to the different needs of men and women).

Disability[45]
[45] 3.5% of the Kenyan population (approximately 1.3 m people) have a disability. Kenya has taken steps to address disability inclusion, for example, in 2003, the Persons with Disabilities Act was enacted, providing a comprehensive law on rights, rehabilitation and equal opportunities for people with disabilities. Kenya also ratified the UN protocol on the Convention on Persons with Disabilities in 2008. Since then, Kenya has taken steps to introduce legislative, policy and administrative measures including: a review to mainstream disability in all laws and policies; annual targets so that 5% of employment opportunities go to people with disabilities; 30% of public contracts to people with disabilities. However, the situation of disabled and vulnerable people is still fragile, and many services need to be provided, such as education, preventative care, and protection against sexual violence.
The programme will undertake a disability audit to ensure that the issues disabled citizens face are incorporated into programme design, in both county management (e.g. planning; budgeting) as well as service delivery. The results framework will consider disability as well as indicators to measure persons with disabilities leadership across key areas of governance (executive and county assemblies). This programme will be fully compliant with Kenyan disability legislation.

Youth[46]
[46] 65% of Kenya’s population are under 35 and 40% under 15 years old. This provides both an opportunity for Kenya’s growth, but also a challenge, in terms of education; employment opportunities; and stability. Engaging young people in a meaningful way to identify and address issues they face, is key to harnessing the youth bulge in a productive way to support stability. The programme will have a core focus on youth, both in urban and rural contexts, seeking to involve youth
The programme will be guided by the DFID Kenya youth strategy as well as the Kenya National Youth Policy and will offer analysis from all target counties on youth demographics and patterns of youth participation in governance. The programme will support youth in leadership roles especially in public participation interventions aimed at improving government responsiveness.

Terrorism and financing
The risks of terrorist financing in this programme are low and acceptable. Nonetheless the programme will be operating in areas where violent extremists radicalise and recruit. The main risks include: a) Unintentionally directing funds to a terrorist organisation that purports to be an aid organization or promotes causes and/or carries out activities in support of terrorist organisations (false representation); and b) Unintentionally directly funding organisations that have been infiltrated or have links with terrorist groups (affiliation). A thorough risk management framework will be applied to all implementing partner (IP) staff recruitment and downstream partner selection. In addition, DFID Kenya will ensure:
Regular oversight of implementing partner systems for due diligence and risk management;
- Coordination with other donors and programmes on downstream partners and their performance;
- Oversight of regular IP due diligence and audit of all downstream partners;
- Inclusion references to relevant terrorism legislation in all downstream partner agreements.
- Collaboration across government and reporting of any suspicions to the Counter Fraud, Whistleblowing Unit (CFWU) and National Crime Agency.
- DFID Kenya is also exploring the use of third party monitoring to cover the DFID Kenya portfolio and to ensure robust monitoring in less accessible areas.

Public Sector Equality Duty.
There are likely to be significant positive impacts from DFID’s work in Kenya in terms of ‘Advancing equality of opportunity’ and eliminating prohibited conduct’ and against the protected characteristics (notably, age, disability, sex/gender, and race and ethnicity). The programme will support this through investments in government human resource systems.

Climate and Environment.
Kenya is highly vulnerable to drought, which currently costs 2.4%[47]of GDP per annum and may rise with the effects of climate change. The programme will build on the previous KDSP programme to strengthen county government laws, policies, plans and budgets to support climate and environment priorities, and expand this work to regional economic blocks.
[47] The World Bank calculates that on average, every seven years Kenya experiences a flood that costs about 5.5 percent of GDP), and every five years experiences a drought that costs about 8 percent of GDP. This translates to a direct long-term fiscal liability of about 2.4 percent GDP.

Partnership Principles.
We will use partnership principles throughout the programme to guide our partnership with government. Being closely associated with county governments that may engage in practices that breach our partnership principles poses a set of risks, including reputational risks for HMG that we will monitor closely. The programme will work with county governments that demonstrate commitment to open government and preventing and addressing corruption, as well as commitment to poverty reduction. We will assess county government performance and risk on a regular basis and ensure this informs decisions on partnership with county governments. We will ensure implementing partners deliver UK aid funded components of their programmes in line with our partnership principles. We will continue to regularly review whether this programme should use pilot the use of government systems.

Safeguarding.
The programme will comply with DFID’s Smart Rules on safeguarding and adopt a do no harm approach. The programme will work in contexts where violence against children is a social norm and where sexual violence against women and children occurs. This programme will require, and monitor, improvements in safeguarding systems of implementing partners, drawing on learnings from DFID Kenya’s programmes and recent Internal Audit Department (IAD) recommendations.

Sustainability
The programme will prioritise engagement with national government and county government leadership. The programme’s exit strategy is to strengthen government systems for county governments to better manage Kenya’s own revenues. Additionally, we will increase our investment in evidence generation to support the adoption of best practice and sustainability of results.

Appraisal Case

This section includes first a high-level appraisal of intervention options and then defines the programmes scope of proposed interventions. It next appraises delivery options and provides an overarching cost benefit analysis. It concludes with a proposed outline theory of change and VFM statement.

Stage 1 Appraisal: High level intervention options

High level intervention options considered here are:
Option 1: The counter-factual, do not fund the programme, but continue to engage politically
- Option 2: Provide technical assistance (deploying expert advisors) to strengthen government capacity.
- Option 3: Provide direct financial aid. This involves transferring money to the government to manage spending, often with some complementary technical support (e.g. for PFM and Audit)
- Option 4: Strengthening civil society. This involves funding civil society organisations, with additional capacity building support to these organisations.
- Option 5: Support priority service delivery sectors. This would involve aligning closely with a sector programme such as health and sector ministries and staff (rather than focussing on core functions).
- Option 6: A combination of the above

Below we have considered the strengths and weaknesses of the arguments for each approach considering potential for impact, sustainability and efficiency.

Option 1: Do not fund the programme but continue political engagement. It would be possible to have some impact on the priorities identified in the strategic case by ceasing funding and increasing our political engagement. For example, the High Commission could increase its role in analysing and calling for government action to improve the effectiveness of devolution. With sufficient time spent in priority counties it would be possible to deepen the UK’s understanding of the political economy of devolution and to be more vocal in calling for action on corruption, accountable service delivery, and the targeting of poverty reduction efforts. However, this approach would realistically be limited owing to staff time. Without a significant programmatic investment in devolution, our advice carries only so much weight. Without the technical expertise and technical relationships that a programme provides, little impact can be made on the strengthening of core systems. Most importantly, the absence of support to decision makers, and reform processes across the national government, counties and civil society would result in much slower progress in strengthening systems for the effective functioning of devolution and would undermine our wider objectives in Kenya.

Option 2: Provide technical assistance to strengthen government capacity. This option would focus on supply side effectiveness of either or both National and County Government departments and agencies, constitutional commissions and independent offices, by strengthening government core systems. Technical assistance could be provided directly by DFID, through seconding programme funded staff, or to greater scale through an implementing partner (Multilaterals, private sector, or select non-profit organizations) deploying long and short-term technical advisors.

Technical assistance has an important role to play in strengthening government systems and under previous devolution programmes in Kenya technical assistance has effectively strengthened a wide range of national and county government, constitutional commissions and independent offices including: the National Treasury, the Ministry of Devolution and ASALs, the Controller of Budget, the Commission for Revenue Allocation (CRA), the Council of Governors and the County Assemblies Forum, the Inter-Governmental Relations Technical Committee, the Inter-Governmental Budget and Economic Council, the Presidential Advisory and Strategy Unit, four Regional Economic Blocs and 35 County Governments. However, the impact of these investments take time to translate into service delivery improvements on the ground and improved citizen confidence. They also do not, on their own translate into more accountability of government departments and agencies, constitutional commissions and independent offices. Citizen and civil society engagement is also required.

Option 3: Provide direct financial aid through conditional grants to target counties via the Treasury and Ministry of Devolution and ASALs. The main argument for this approach is that government systems are strengthened through the process of managing donor grants and loans in compliance with donor requirements (and supported by technical assistance where needed) and aid effectiveness and efficiency are increased. The WB, EU and Danida are in the processes of providing conditional grants to counties for capacity building, health and specific projects. The argument against financial aid, is that Kenya has sufficient resources, and the priority should be their effective and accountable management. Adding donor funds into government systems potentially reduces the incentives for government to tackle waste and corruption and creates donor dependency. Kenya is a lower-middle income country, and our relationship with Kenya is therefore transitioning towards a development partnership where Kenya needs less aid. The Kenyan government has ample access to finance and is able to borrow from domestic and international markets – finance is not a binding constraint on Kenya’s development.[48] DFID’s partnership principles do not currently permit DFID bilateral funding to government directly in Kenya but we will continue to assess the arguments for and feasibility of doing so. If during the course of implementing this business case we determine there is a strong case for piloting financial aid based on strengthened county financial management systems Ministerial approval would be sought.
[48] A Financial Aid study commissioned by DFID in mid-2018 has mapped the modalities for doing so, and also the risk and remaining weaknesses in government systems: Review of options for providing funding through government systems, Michael Njuguna, 2018

Option 4: Strengthen civil society with a focus on demand side accountability can help build government transparency and accountability. Both the KDSP programme, DDP programme and other donor programmes such as the USAID and GIZ devolution programmes have achieved results through investing in civil society at the national and county level. Civil society has an essential role to play to hold government to account and devolution presents an important opportunity to do this. At the county level citizens can directly engage local officials on government strategies, plans and budgets (county strategies, annual work plans and sector plans), delivery and performance (project selection, procurement, delivery and monitoring), and a wide range of local problem-solving processes (for example on the regulation of natural resources to prevent conflict and protect the environment).

However, there is a large body of evidence that civil society engagement with government without a commensurate investment in government capacity and information sharing will not significantly advance accountability to scale. The 2019 annual and mid-term reviews of the Deepening Democracy Programme found many strong examples of citizens and civil society holding county government to account and effecting changes in local policies and improving the procurement and delivery of local projects. For the most part, these initiatives remained isolated and did not generate a widespread sustained change in systems and behaviours for more accountable and effective service delivery. Additionally, civil society is constrained across the board by limited access to information and decision makers at all levels of government. A review of the AHADI citizen engagement strategy in mid-2019 found that county governments that had been assisted to enact laws, approve policies and establish structures for implementing public participation demonstrated a marked improvement in government and civil society relations. However, poor access to information and inconsistent public participation hampered effective citizen engagement.

A devolution programme that concentrated support solely on civil society would likely face these persistent challenges. However, a programme that combines civil society support with technical assistance to government could facilitate a flow of information and access to decision makers that may unlock a more systemic change in state-civil society engagement for increased accountability and more effective service delivery.

Option 5: Support priority service delivery sectors with a core focus on expanding effective service delivery. There is a strong argument that for DFID to contribute in a measurable way to poverty reduction, devolution programmes should prioritise service delivery in target sectors. The counter argument is that specific sectors, such as health, already receive a large investment from government and donor funded health programmes, and that devolution specific programmes should focus on their comparative advantage of working on core government systems.

Under the previous KDSP programme, DFID has supported specific sector policy development in health, water, agriculture and livestock, and climate change governance. This investment has paid off with concrete results in terms of policy improvements and more coherent and effective county government programmes. However, there is a high demand from across DFID Kenya and indeed from county government line ministries, for more in-depth support to help government systems deliver in specific sectors. While a programme fully focussed on sector impacts would fail to deliver on core government system strengthening, some greater emphasis on specific sectors is justified. These sectors should be identified across HMG to ensure they are prioritised and other programmes capacity can be leveraged for maximum impact (e.g we have a large health programme and health is the largest devolved sector).

Option 6: A combination of some of the above intervention areas (preferred): The options outlined above all offer potential for valuable results, though option 3 is excluded at this stage owing to our partnership principles restricting financial aid at this time. Each of the other options can deliver results, but with a limited contribution to the desired outcomes and impact. A combined set of interventions is required to have a maximum development impact, building government effectiveness and accountability and strengthening core systems to measurably contribute to service delivery in priority sectors. Global experience highlights the need to balance the increased discretion (political, administrative, and fiscal) of sub-national governments with greater accountability (both upwards to national government but also downward to citizens). Demand-side social accountability initiatives face major challenges of sustainability and scale and are typically heavily reliant on donor financing.[49] Integrating demand- and supply-side systems is therefore essential. A focus on priority service delivery sectors is justified by the need to ensure capacity translates into specific development outcomes. This will need to be carefully prioritised. Robust targeting and flexible implementation modalities will be required to ensure responsiveness to key opportunities and value for money.
[49] Horowitz, L. and Palaniswamy, N. (2010), In Pursuit of Votes, The Capture of the Allocation of Local Public Goods by the Central State in Ghana, IFPRI Discussion Paper 01039, Development Strategy and Governance Division.

For all options, political engagement would be essential to have a maximum impact and manage risk.

Stage 1 Conclusion: programme scope and priority areas of intervention

Option 6 is preferred. Maximum impact can be achieved through a combination of technical assistance to national and county government to deliver and civil society capacity to hold government to account for, devolved services. Increased targeting of specific sectors is also justified. This option is most likely to deliver the impact we desire which is improved development results at the county level. The highest performing counties to date, such as Makueni, Elgeyo Marakwet, Kwale and West Pokot have established effective public participation and responsive government. The deployment of a limited number of programme-funded staff could further strengthen the depth of UK partnership with county governments. This programme will not provide financial aid to government. Others are investing in financial aid and this is not in line with DFID’s Partner Principles. We will reassess this periodically.[50]
[50] As we did though the 2018 study commissioned by DFID Kenya: Review of options for providing funding through government systems, Michael Njuguna, 2018

Given the complexity of the programme (working at different levels on supply and demand and with a focus on core government systems and specific sectors), a rigorous approach will be required when selecting implementation and delivery options. This is considered in more depth below under the second and third stages of appraisal. The selection of target counties where we can have most impact is then considered under the VFM section at the end of this chapter.

Scope of proposed intervention

The overall impact this programme will aim for is: Improved development results at county level.

The expected outcomes by 2025 are that:
More effective, open and accountable County Governments
County Governments improve service delivery and reduce poverty

The programme will seek to deliver the following outputs:
Intergovernmental relations support devolution
- County governments effectively manage public finances, staff performance and county planning
- Government and citizens collaborate effectively to address key problems in service delivery and poverty reduction.
- High quality evidence generation, learning and digital approaches improve county government delivery.
- The UK development portfolio is better aligned with county government priorities.

These outputs and illustrative prioritised interventions are described in more detail below

Intergovernmental relations support devolution. Under this output the programme will aim to enhance intergovernmental relations and cooperation through strengthening legal and policy frameworks and capacity building of intergovernmental institutions.[51] Evidence from KDSP strongly supports the need for this investment to complete the transfer of functions from national to county government.[52] We will ensure alignment of devolution support with the PFM Reform Strategy and National Capacity Building Framework. Illustrative interventions include:
[51] It will provide elements of support to the Kenya School of Government, the Inter-Governmental Relations Technical Committee, the Council of Governors, the Controller of Budget, the County Assembly Forum, the Auditor General, the Commission for Revenue Allocation, the Senate Money Committees and the Inter-Governmental Budget and Economic Council. It will also support clusters of counties forming into regional economic blocs.
[52] disputes around the transfer of functions and as poor intergovernmental relations were a major contributor to the weak results of devolution in its early years
  - Providing technical support to strengthen the role of key agencies including potentially, the Council of Governors, Commission on Revenue Allocation, Controller of Budget, the Office of the Auditor General, the Kenya Revenue Authority, the Intergovernmental Budget and Economic Council, and the Intergovernmental Relations Technical Committee.
  - Providing support to Regional Economic Blocks to develop cross county policies and strategies (e.g. for trade and investment, services, natural resources).
  - Supporting increased engagement between devolution institutions and other key agencies in priority devolved sectors (ie. health, agriculture, water and urban development).

County governments effectively manage public finances, staff performance and county planning. Under this output the programme will aim to strengthen county systems to improve service deliver by providing technical support to County Governments (county executives and assemblies). KDSP 1 helped developed assessments we will use to plan and monitor performance. These include Annual Capacity and Performance assessments (ACPAs), Comprehensive Public Expenditure Reviews (CPERs), Gross County Product (GCP) and Own Source Revenue (OSR) Assessments, Public Expenditure Reviews (PERs) Financial, Social and Performance Audits. Illustrative interventions include:
  - Improving County Integrated Development Plans (CIDPs), sectoral and economic plans, programme-based budgets and monitoring and evaluation systems, and the gender responsiveness and conflict sensitivity of county strategies.
  - Strengthening financial management and adherence to the public expenditure management cycle including Integrated Financial Management Information System (IFMIS) systems, enhancing revenue collection,[53] strengthening VfM in procurement and prudent use of resources in service delivery.
    [53] Six years on, county governments are still experiencing challenges in their financial management. This revenue is currently under strain from debt servicing and failure of the Kenya Revenue Authority to reach revenue targets. A scoping mission from Her Majesty’s Revenue Commission (HMRC) in June 2019 identified options for providing technical assistance to the Kenya Revenue Authority.
  - Strengthening human resource functions ensuring performance management, inclusivity, professional development and effective inter-departmental cooperation.

Government and citizens collaborate effectively to address key problems in service delivery and poverty reduction. Under this output the programme will aim to strengthening open government, access to information and public participation to the impact of devolution improve service delivery and poverty reduction. Illustrative interventions include:
  - Supporting a multi-stakeholder problem-driven approach in target counties to address service delivery challenges in key sectors such as health, climate change (energy, water, agriculture, natural resource management) disaster risk reduction.[54]
    [54] This could include collective action where stakeholders from the business community; civil society; and the public sector come together to solve service delivery challenges. We could consider establishing a challenge fund to encourage collective action. In the health sector, this programme could contribute to dealing with issues like absenteeism through improved performance management both at county and service facility level and increasing mechanisms for citizen feedback and redress.
  - Strengthen county government public participation mechanisms such as the County Budget and Economic Forums, County Environment Committees, Open Government Partnerships, Health Facilities Management Committees, Citizen Forums for Urban Planning, and cross-county learning.
  - Supporting local civil society consortia to improve engagement with county government on development policies and programmes, with an emphasis on the inclusion of women, youth and persons with disabilities and where appropriate use of advocacy and public interest litigation.

Evidence generation, learning and digital approaches improve County Government delivery, with a focus government ownership and longer-term resourcing through development of the Council of Governors Maarifa Centre. Illustrative interventions include:
  - Supporting the expansion of innovative approaches to generating and sharing evidence on what has worked and how it has worked across the 47 counties and from other countries.[55] We will also support deep political economy analysis and public perception surveys.
    [55] Political economy analysis (PEA) and a peer review mechanism will jointly be utilised to ensure the programme is adaptive and responsive
  - Supporting use of digital for better targeting of services delivery within the framework of the Government of Kenya’s Digital Economy Strategy[56] and supporting digital solutions to unblock bottlenecks in public service delivery. [57]
    [56] For example, under KDSP in Makueni county, a Geographic Information System (GIS) was established which has informed county spatial plans which in turn are used for planning service delivery.
    [57] For example, we have supported transparency international to work with Elgeyo Marakwet County government to introduce transparent digital systems into health supply chains, which have increased access to commodities in local health facilities.
  - Strengthening monitoring and evaluation of devolution support programmes including an expanded use of (digital) beneficiary feedback systems

The UK development portfolio is better aligned with county government priorities. Programme-funded staff will be recruited in at least 5 regions with the aim of directly supporting county governments in those regions and also increasing the overall impact of UKAID funded programmes by ensuring their coherence and alignment to government of Kenya priorities. Programme funded staff will:
  - Support county governments and regional economic blocks to better coordinate external assistance and development programmes.
  - Work cross-DFID and cross-HMG to strengthen the coherence and alignment of programmes on the ground with government of Kenya priorities. Advise on programme effectiveness, relevance and responsiveness,[58] risk management and opportunities for impact.
    [58] Fritz, V., Kaiser, K., & Levy, B. (2009). Problem-driven governance and political economy analysis: Good practice framework. Washington DC: World Bank.
  - Deepen UK understanding of the local context and relationships with key stakeholders within government; the county assembly; civil society and the private sector.

This will require implementing partners that can
Deploy high quality technical assistance to government ministries, departments, agencies, commissions and independent offices
- Ensure sustained support to county governments and civil society in target counties
- Champion inclusion and innovation

Stage 2 Appraisal: Specific Delivery Options

This section will appraise which delivery modalities work best for different components of the programme by considering the comparative advantage of types of implementing partner:
a) Multilaterals (UN and World Bank)
b) Private sector service providers
c) An NGO consortium.
d) A bespoke/hybrid approach combining a mix of 1,2 and 3.

The potential strengths and weaknesses of delivery options are outlined below in light of eight key criteria:

Criteria 1: Ability to strengthen the planning, public financial management and performance management of targeted county governments. Multilaterals have a high level of legitimacy with government and a mandate to work with host governments. Both UN agencies and the World Bank have existing devolution programmes which have been approved by the government of Kenya. The targeting and quality of delivery by multilaterals requires close monitoring to ensure strong performance, especially UN interventions. Private sector service providers have no formal mandate, but with time are able to establish good working relations based on effective provision of technical assistance. Some NGOs have well-established relationships with government and have proven they can build credibility based on effective provision of technical assistance.

Criteria 2: Ability to strengthen intergovernmental relations to support devolution. Multilaterals have strong existing government relations in Kenya and can provide support to strengthen intergovernmental relations, though they can be slow to adapt to changes in the political context. The targeting and quality of delivery by multilaterals requires close monitoring to ensure strong performance, especially UN interventions. Private sector service providers would require time to establish relationships with various government and intergovernmental agencies. Once established they are often able to adapt quickly. Many NGOs and academia in Kenya have working relationships across government and are able to adapt quickly.

Criteria 3: Ability to strengthen civil society to improve accountable and inclusive service delivery in target sectors. Overall, Multilaterals do not have a strong track record in building the capacity of local organizations. Both private sector service providers and NGOs have stronger profiles in this regard.

Criteria 4: Ability to start early, and DFID Staff time required to manage partners: The management of MOUs with Multilaterals does not take up a lot of staff time but influencing the strategic direction of programming does require time and effort. MoUs can be established quickly with multilaterals, especially where they have existing approvals from government for their programmes. Procurement timelines for contracting private sector service providers are lengthier but can then lead to efficient programme management and strong controls if limited to a single sufficiently large contract. Accountable Grants with NGOs can be more quickly established and this enables flexibility in portfolio management. However, due diligence and compliance requirements can require increased staff time with less experienced NGOs.

Criteria 5: Flexibility, innovation and responsiveness. Multilaterals may be less able to respond flexibly to changing context and needs due to slower processes of planning and procurement. Contract arrangements can support flexible and adaptive programming if well designed. Accountable grant arrangements can offer flexibility and ability to respond quickly to changing context, if carefully designed.

Criteria 6: Longer term sustainability. All potential implementing partners have a degree of dependence on donor funding, the highest dependence being private sector service providers, (specifically contracted for the project). Multilaterals’ formal relationships with government, and multi-donor funding increases the potential sustainability of these programmes. Expert NGOs and local CSOs have credibility in the sector and with communities and often have multiple donors.

Criteria 7: Ability to operate at scale and in programme target counties. Multilaterals have existing legitimacy with government which will facilitate relationships with county executives as well as the county assemblies. However, multilaterals have demonstrated less ability to provide long term sustained technical support at the county level in their devolution programmes in Kenya. The private sector can establish strong relations at the county level based on high quality programmes, but this takes time to establish with new programmes. Depending on the NGO and its consortium, NGOs may already have a history and presence in key counties. Experience from KDSP I proved that NGOs can operate at scale in the targeted counties and in insecure locations and offer long term embedded technical support (e.g the previous AHADI programme)

Criteria 8: Simplicity and aid effectiveness: the most simple and efficient management of this programme could be achieved by solely funding multilateral organizations.[59] DFID funded independent monitoring of KDSP I found that there have been some significant result from DFID support[60] through multilateral partners in terms of strengthening the policy and regulatory framework that underpins devolution including: procurement, public sector remuneration, performance management, planning, public participation, human resource management, climate change and disaster risk mitigation. DFID programming has benefitted from the access, information and lessons emerging from this. However, evaluations found that multilateral programmes have limitations for DFID in terms of (i) control of how resources are spent and the pace/quality of delivery and (ii) ability to flexibly programme and change direction to align with the political context. They suggest that DFID’s ‘arm’s length’ approach by working through multilateral partners led to some missed opportunities to: really understand the political economy at the sub-national level (which underpins whether interventions will succeed); manage risks to HMG (reputational; fiduciary; and political); build direct relationships with key government, private sector and civil society counterparts;[61] and take a more focused, problem driven approach, identifying service delivery challenges (especially for under-represented groups). While some good results have been achieved, we would not recommend solely investing in multilateral programmes.
[59] The WB and UN have new multi-donor devolution programmes beginning in late 2019, with initial funding commitments from other donors.
[60] DFID Annual Monitoring Report commissioned in 2018.
[61] Kenya Devolution Support Programme Annual Review 2018.

We also considered four other criteria and determined that all potential implementers scored equally. These were
Criteria 9: Ability to scale up the use of evidence, learning and digital approaches
- Criteria 10: Ability to deepen the UK’s sub-national strategy, supporting staff secondments
- Criteria 11: Ability to source and deploy high quality technical assistance.
- Criteria 12: Ability to offer VFM if programmes are well designed and managed, and bureaucracy and overheads are kept under control.

Our scoring is provided below. Scores are from 1-5: where 1 is very weak and 5 is very strong. These scores show that each potential partner has a different comparative advantage overall and supports the conclusion that the most effective programme could be implemented through a combination of partners.

	1	2	3	4	5	6	7	8	9	10	11	12	Totals
Multilaterals	5	4	2	5	3	4	3	4	4	4	4	4	47
Private Sector	4	4	4	2	4	2	4	3	4	4	4	4	43
NGO consortium	4	4	4	3	4	3	4	3	4	4	4	4	45

Stage 2 Conclusion: Approach to Delivery

Based on the assessment of criteria above, the preferred option is d): a bespoke/hybrid approach combining a mix implementation modalities.
Multilaterals (MoUs)
- Non-Profit Consortium (Accountable grant)
- Programme funded posts (DFID Managed)
- Independent Monitoring and Evaluation provider (contract)

This will allow the programme, through a limited number of agreements to ensure strong government buy-in and responsive technical assistance, substantial support to county governments through locally deployed technical advisors including DFID programme funded staff and effective support to county based civil society organisations. This would be robustly and independently monitored by a monitoring, evaluation and learning (MEL) provider.

This approach would maximise the UK’s contribution to effective devolution through a combination of partnerships, each with a comparative advantage. It would allow for maximum responsiveness, to both engage politically and technically with senior government officials (primarily through multilateral partners) and also to work in a sustained way at the county level and with county based civil society (through a non-profit consortium). There is also value in this combination of mutually re-enforcing partnerships, which we anticipate will effectively bring a wide range of state and civil society actors together to solve complex service delivery problems. Experience from KDSP I has shown that there is much added value in having multilateral programmes complemented by efforts from non-profit organizations.

DFID will begin detailed discussions with Multilaterals to determine what to support through this business case. The arguments for supporting the World Bank are strong based on its advanced approach to supporting the core technical processes of devolution (ie PFM), results to date and the quality of the draft Multi-Donor Trust Fund proposal (2019-24). The World Bank also has a wide range of grants and loans for Devolution, PFM, Urban Development and the North and North Eastern Development Initiative, that our devolution support can leverage. The argument for supporting the UN at the time of writing is less compelling though the UN programme does propose a robust targeting of poorest counties. The SRO for the business case will consult the DFID Kenya head of office closely on the progression of negotiations with each multilateral partner. No funding is guaranteed. We will continue to focus on results and VFM to make robust decisions for use of UK taxpayer money. The multilaterals will be informed that funding will depend on the quality of their proposals and will continue to be allocated based on strong performance over the life of the programme or redirected in the event of weak performance.

The respective roles of implementing partners are outlined in the table below:

Implementing Partner/modality[62]	Main Project Elements
Multilaterals (UN and WB) / MOU (£11.5m)	Strengthen intergovernmental relations to support devolution / Strengthen the planning, public financial management and performance management of county governments. / Strengthen government and citizens collaboration to address barriers to social and economic development (strengthen public participation to improve accountable and inclusive service delivery in target sectors) / Strengthen high quality evidence generation, learning and digital approaches improve capacity development	Multilateral partners will lead on / Intergovernmental relations. / Creating an enabling environment / Domesticating global frameworks and standards and tools. / Developing and supporting robust county based tools (e.g on revenue, audit, expenditure, effectiveness) / Mainstreaming and wider cross. county learning.
Non-Profit Consortium. / Accountable grants with an NGO Consortium (£20m)		The non-profit consortium will lead on / Ensuring depth of capacity building of county governments. / Strengthening civil society role in accountable service delivery.
Programme funded posts / (DFID Managed) / Direct recruitment and secondment (£2.5m)	Programme funded staff will support: / Technical assistance to county governments and regional economic blocks. / A deepening of the UK’s sub-national strategy to better align and leverage development programmes in support of county government plans.
Independent Monitoring, Evaluation and Learning (MEL) provider / Private sector framework contract (£4.5m)	The MEL provider will lead on / Filling gaps in data collection, monitoring evaluation and programme learning / Strengthening high quality evidence generation, learning and digital approaches improve capacity development / Supporting political economy analysis and public perception surveys
[62] we will not allocate counties to specific partners, but we will ensure collaboration where multiple partners operate in the same priority county. County selection methodology is described below.

Please see the section below on how counties will be selected to ensure maximum impact.

In the first year of implementation DFID will approve initial funding to those workplans of multilateral partners that can be agreed and establish the monitoring and evaluation contract as well as the programme funded posts. Where DFID determines that both the WB and UN should be partnered with, workplans will be robustly challenged to ensure clear results, VfM and complementary roles (avoiding duplication). The monitoring and evaluation contract will be procured with a specific terms of reference that ensures flexibility and responsiveness, with a ringfenced fund for commissioning research and surveys. DFID will complete the process of selecting the not-for-profit consortium selection within 6 months of the approval of this business case. DFID will finalize the scope of work for the consortium to ensure that its interventions will complement the pre-existing multilateral programmes and address priority gaps.

A series of important studies co-funded by DFID will be completed in mid-2020 and DFID will ensure these inform the focus of all implementing partners workplans. For example, the World Bank’s Impact of Devolution on Service Delivery and the AHADI / University of Nairobi County Capacity Assessment Index.

Economic Appraisal

We have assessed that the programme is needed and should invest in government capacity to deliver services, and civil society capacity to hold government to account. The programme will need to deliver high quality and responsive technical assistance to government with a focus both on core systems and also priority sectors, as well as build the capacity of county based civil society. It will be most effective delivered through a combination of multilateral and non-profit implementing partners with and independent MEL provider and supported by programme funded staff deployed locally.

More detailed VFM assessments follow in the sections below. At this point we consider the overall economic argument for proceeding with this preferred option as opposed to ceasing funding and simply working politically. At a cost of £38.5m, we assess that this programme will offer good value for money. Not implementing this programme would save this amount, but would have negative impacts on
  1. The potential for devolution to deliver development results with the estimated $18bn that the Government of Kenya will spend on devolution (the equitable share allocated by the Treasury to county governments) over the coming 5 years
  2. Kenya’s efforts to tackle waste and corruption and mismanagement, which the Auditor General estimates leads to one third of government revenue being unaccounted for.
  3. The evolution of government systems that support our other priorities and programmes, such as in health where we spend significant resources.
  4. Our relationships and influence across the country

If this programme is successful we can leverage our relatively small investment against the much bigger investment Kenya and other donors are making in devolution to development results.

Given Kenya’s huge investment in devolution small changes in effectiveness and efficiency of county governments would yield good returns for our investment through this programme, and more than cover its cost. We expect to see:
Increased absorption against county budgets: though improving, most counties are still unable to fully utilise their annual budgets, especially their development budgets. Absorption data is available by county (though absorption on its own does not guarantee the quality of outcomes and information would need to be triangulated with other data e.g. citizen satisfaction survey data).
- Increased county revenue collection: This programme can help counties better estimate and ensure revenue collection. Data on revenue collection is available by county.
- Savings due to improved procurement and financial management: helping counties improve their public financial management should produce savings due to improved procurement and reduced leakages/corruption. It is possible to use annual county audit reports to see whether individual counties have acted on the recommendations of the previous year. This programme will support county audits and advance the piloting of performance audits to assess VFM

Theory of change

An outline programme theory of change is outlined below. Over a five-year timeframe this will require a regular process of context and political economy analysis, a regular review of programme results, approaches and learning and a staggered commitment of programme resources to ensure they are directed to priority areas where counties and implementing partners are demonstrating results.

This theory of change aims to frame how interventions and outputs are expected to lead to outcomes, with an emphasis on our underlying assumptions. The programme will be managed with an adaptive approach to ensure it remains responsive and has the greatest relevance and impact possible.

The programme will work at higher levels of government to build an enabling environment through multilateral partners, primarily through technical assistance to foster collaboration between different parts of government and to unblock barriers to the effective working of devolution, including legal and policy barriers. County governments will be strengthened through direct technical assistance provided by all delivery partners but most substantially by the non-profit consortium which will have a deeper sustained presence in target counties. Efforts to strengthen civil society engagement will also be led by the non-profit consortium which will provide both technical assistance and grants. A focus on key counties and sectors will be determined through the robust use of selection criteria to identify interventions and programme funding will be used in a flexible and adaptive way to invest where the potential for most impact is identified. The programme, and devolution stakeholders more broadly, will be supported by the independent monitoring, evaluation and learning component which will also provide regular political economy analysis and perception surveys.

Our theory of change aims at development results at the impact level and a significant change in county government approaches and performance at the outcome level (more poverty focussed, capable, open and accountable) with a strong focus on improvements in social and economic development. Essential to achieve this are the five outputs. We have chosen to be ambitious with this theory of change by aiming to measure the results of our investments in capacity and accountability in terms of real social and economic development impacts. This will require a shift from previous devolution programmes towards more partnership with line ministries nationally and at the county level, more analysis of progress in specific sectors (health, agriculture, etc). It will require more focus on transforming county governments from bureaucracies into development agencies focussed on transformative social and economic development and poverty reduction.

Evidence of the effectiveness of programmatic investments in these output areas has been cited in the sections above. Evidence of their sustained impact at the outcome and impact level is more mixed. There is sufficient evidence that county capacity and civil society strength can be developed and that this can deliver improved development results to invest in this programme. However, the generation of more evidence is a key future priority.

There are many assumptions underpinning this theory of change. The higher-level assumptions are outlined in the table above. For the outputs to be achieved, political will and government revenue is required, as well as a willingness to cooperate within government and also with civil society, and a commitment to continued system strengthening and reform at all levels. Realism is essential. This will not be achievable across the board, but we assume there will continue to be sufficient opportunities for the programme to engage and have a significant impact on priority reform processes and in priority counties. These opportunities can only be effectively taken if targeted interventions will be selected based on robust political economy analysis and county capacity and performance assessments. This targeting is described in more detail under the VFM cost effectiveness section below. We also assume that investing where we can have the most impact will incentivise reformers in other counties that we may not have targeted as they witness the progress made. This virtuous cycle is nascent but already evident. Counties are increasingly sharing information, visiting each other and identifying and replicating good practice.

The 2022 election will disrupt county governments significantly, from at least a year before polling day to at least a year after. The programme will need to plan well and the flex and adapt to ensure the support continues where results can be sustained through the election cycle and is withdrawn where the prospects of this are low.

VFM statement

This programme offers good value for money. It will directly contribute to HMG priorities in Kenya and contribute to the sustainability of poverty reduction efforts.

At the highest level of cost effectiveness, VFM will be ensured by allocating funding based on county and implementing partner performance, increasing funding to implementing partners and targeting counties where UKAID can have the most impact. We will also strengthen the linkages of this programme across DFID and HMG. This will be decided by DFID based on assessments of implementing partner achievements.

We will aim to measure cost effectiveness by tracking changes in development results at the county level that can be attributed to programme investments. We will measure these against the costs of achieving sector results through other programme, factoring in an assessment of the sustainability of these results.

Performance of implementing partners will be managed by DFID through a regular review of programme results, approaches and learning and a staggered commitment of programme resources to ensure they are directed to areas where implementing partners are demonstrating a clear ability to deliver results. More specifically we will assess implementing partner performance based on key performance indicators such as the following:
  1. Quality of political and technical analysis
  2. Effective generation and use of evidence
  3. Quality of technical approaches (including ability to deliver responsive bespoke support)
  4. Output and outcome level results achieved
  5. Strength of relationships with government stakeholders
  6. Depth of county presence
  7. Ability to prioritise to ensure responsive adaptive programming and VFM
  8. Ability to coordinate and work with others, including in key sectors (ie health)

To enhance the programme’s effectiveness, DFID staff will work with colleagues across DFID and across HMG (including with centrally managed programmes). The programme team will also work closely with FCO, MoD and DIT in priority counties with high level UK political, security and commercial priorities.

As described above, multilateral partners will work across counties and with limited depth of engagement at the county level. The Non-Profit consortium will complement the work of multilaterals by focussing on in depth county level engagement (while also supporting regional economic blocks). The consortium will target counties where UKAID can have the most impact. This will require a careful initial selection of around 16 potential counties based on need (i.e. depth of poverty) and effectiveness (i.e. level of county government commitment/political will/performance)[63] and relevance to wider UK interests and investments to amplify impact. More specifically, criteria will include:
[63] For example, commitment to progressive policies for service delivery, investment, financial management and system strengthening
  1. Level and depth of poverty
  2. County government commitment to improving systems for service delivery (i.e health and nutrition)
  3. County government commitment to open government, accountability and public participation
  4. Demonstrable progress on capacity and performance assessments (i.e. audit)
  5. County government commitment to addressing equity and drivers of conflict and instability
  6. Strategic importance to UK (e.g. where we already have significant investment) and where the greatest contribution to our country business plan can be realised.

Our experience in Kenya (e.g. from our urban programme and also WB programmes) is that a form of competitive selection based on objective criteria creates a positive dynamic and is likely to maximise impact and value for money. We will therefore require county applications for support and will aim to target around 8 priority counties (at any one time) through the Non-Profit consortium. We test this for the first 2 years of implementation and may adjust this target in discussion with the DFID head of office. We will develop a strategy for each target county recognising the mix of characteristics specific to the county. We will also seek to balance the selection of focus counties across the regions of Kenya and in coordination with country support by other development partners. We recognise there may be a need for targeting within counties to ensure that sub-counties that have markedly higher levels of poverty (such as Tiati in Baringo or the northern region of West Pokot) benefit from the development results the programme is aiming for. We will invest in supporting county governments to plan for equitable development to address historic marginalization.[64]
[64] For Example Elgeyo Marakwet county established a county based local equalisation fund.

As noted above we will support county governments in priority sectors that are wider HMG priorities in Kenya to amplify our impact, including health, urban development and natural resource management.

Quantitative measures of progressiveness (see Annex 2) may include:
  1. Growth of Own Source Revenue (CoB)
  2. Progress with Audit (OAG)
  3. Gross county Product Baseline (KNBS/WB)

Qualitative measures could include
  1. Impact of Devolution study (WB)
  2. County Capacity Assessment Indexes (AHADI/University of Nairobi for 22 counties)
  3. Economic Survey (KNBS/NT)
  4. State of the County reports by governors and details of CIDP
  5. Public participation and citizen engagement measures (ie whether County Budget and Economic Forums have been established)
  6. Progress in key sectors (health, climate change, corruption)

1. The Non-Profit consortium will complement the work of multilaterals. The consortium will focus on in-depth county level engagement based on poverty and progressiveness criteria, which will be mapped against the diagram below to identify where UK resources can have the most impact. This in-depth county focus will be kept under review to respond to changes at the county level. We will initiailly
  1. Concentrate efforts in ideally 4-6 counties with a relatively high level of poverty and progressive county governance (with an intense focus on strengthening county systems and delivering development/poverty outcomes).
  2. Invest in ideally 1-2 counties with a relatively high level of poverty but limited progressiveness of county governance (exploring scope for influencing progressiveness to better tackling poverty).
  3. Also invest in ideally 1-2 counties with relatively low levels of poverty overall but progressive county governance (exploring the scope for institutionalising best practice across Kenya and generating evidence on poverty impacts).
  4. We will not deliver the programme in counties with relatively low levels of poverty and limited progressiveness of county governance.

Efficiency. The programme’s efficiency will be ensured through a regular review of programme results and costs, to establish which investments and output level results are contributing most directly to outcomes and impact. Resources will be allocated based on performance over the life of the programme. Programme efficiency will be ensured by tracking implementing partner performance against a range of indicators and benchmarks to enable us to compare results and the costs of achieving these results, and to direct resources to implementing partners that are having the most impact. We will establish benchmarks to measure the speed, quality and quantity of assistance provided to project beneficiaries and will also compare the overall cost of the results achieved between types of partner, types of intervention and significance of results. External benchmarking against other similar programmes delivered in other countries will also be undertaken where possible.

We will also focus on strong coordination and coherence of implementing partner interventions under this programme and with other donor funded programmes. There will be additional value for money benefits from aligning with National Capacity Building Framework in order to ensure the programmes with the National Governments priorities in supporting devolution in Kenya.

Economy: This programme will benchmark and compare key costs of providing national and international staff and consultants, transport, accommodation, workshops and other costs, throughout the life of the programme.

Equity: this programme will focus on inclusion of historically marginalised regions within the country, and also within counties and also on the inclusion of marginalised sectors of society including women, youth and persons with disabilities.

Commercial Case

This section sets out the commercial arrangements for managing the preferred delivery option for this programme. As set out in the appraisal case above, the programme will be delivered through three delivery mechanisms: memoranda of understanding (MOU) with multilaterals, an accountable grant with an NGO consortium; and a contract with an independent M&E supplier. DFID will also directly recruit and second county-based staff in 5 locations.

As described above, in the first year of implementation DFID will approve initial funding to workplans of multilateral partners and establish the MEL provider contract and finalize programme funded posts. The process of NGO consortium selection will be completed within the year and designed to fit clearly with the pre-existing multilateral programmes.

Multilaterals

The World Bank and the UN have developed devolution programmes through which they aim to establish multi-donor trust funds and a pooled basket fund respectively. We have reviewed their programmes and established the objectives align with those of DFID. We will request the partners to submit concept notes and workplans which should be aligned with the results outlined in this business case.

DFID’s MoU with the UN will be in the form of a contribution arrangement, which draws on the overarching framework agreement agreed between DFID and the UN headquarters. As part of the UN Reforms agenda, DFID centrally has generated agreements that are more demanding of the UN in terms of risk management, fraud prevention, transparency and accountability, as well as new performance agreements which set out the collective reforms that agencies must deliver to receive full UK funding.[65] This programme will use the most recent agreement templates provided centrally. Currently, there is little scope to negotiate on the administrative fees as this is negotiated and agreed at headquarter level – however, there will be no additional overhead fee charged.
[65] In light of the appraisal above, a programme theory of change is outlined below. Over a five-year timeframe this will require a regular process of context and political economy analysis, a regular review of programme results, approaches and learning and a staggered commitment of programme resources to ensure they are directed to priority area where counties and implementing partners are demonstrating results.

DFID has been working with UNDP and UN Women in the implementing of the KDSP programme. The UK Multilateral Aid Review (MAR) 2016 rated UNDP as good organisation with good structures for development. UN Women was rated adequate in terms of organisation structure. In order to increase efficiencies, UNDP, UN Women and UNICEF have developed a joint devolution programme which will help in harmonization of interventions and avoid providing funding to different UN Agencies.

As the largest donor to devolution in Kenya, the World Bank’s country team has been involved in the implementation of devolution programmes in Kenya. This includes management of the DFID funded Kenya Accountable Devolution Programme and Kenya Devolution Support Programme. The World Bank has strong technical expertise and experience in Devolution. DFID Kenya conducted an enhanced due diligence assessment on the World Bank in 2018 to assess their governance, internal controls and systems, delivery capacity, financial management. In order to verify the capacity of the downstream partners to deliver on the programme, it is expected that the World Bank will conduct thorough due diligence assessments on any downstream partners including consultants. Depending on the findings, DFID will decide whether to make provision for a dedicated devolution programme manager procured by the World Bank.

The positive appraisal of World Bank as one of this programme’s implementing partners is in line with the findings from the UK’s Multilateral Aid Review (MAR) 2016 and the DFID Guidance on the use of World Bank Group Trust Funds (June 2017). The MAR assessed that the World Bank Group is one of the most effective multilateral institutions that DFID funds. It is closely aligned to UK development priorities and is an important partner in the UK’s global efforts to reduce poverty. The World Bank performs well in managing risk, controlling fraud and corruption, and promoting transparency. However, the MAR notes that delivery through World Bank Trust Funds can be hindered by relatively limited flexibility and speed due to the World Bank’s operational processes. To address this risk, there will be joint quarterly steering meetings between World bank and all donors contributing to the trust fund.

As this programme is a continuation of effective previous programmes, the degree of adaptability and flexibility required for successful delivery is moderate. For the World Bank, we will use the standard administrative agreement, which has been negotiated with the Bank and DFID centrally. We will earmark funds with the bank to implement targeted interventions in order to achieve maximum value for DFID’s investment.

DFID will commit funds based on performance in sectors and counties. Based on their track record both the WB and the UN are expected to be able to successfully carry out the requirements of this programme. However, as with the accountable grant, DFID will regularly assess performance and adjust funding commitments in response. DFID will carry out a due diligence assessment to further ascertain their ability to deliver and comply with safeguarding guidance. A risk mitigation strategy will be jointly agreed with UNDP and the World Bank following the outcome of the due diligence assessment prior to any disbursement. This will include safeguarding risk assessments.

DFID will only sign annual commitments with the Multilaterals and only renew based on performance and delivery of quality results. The World Bank and the UN will establish steering committees (the UN committee includes also government) which will meet quarterly to assess progress on results and approve any adjustments to the programme. DFID will also carry out independent visit to the counties and discussions with beneficiaries. VFM for Multilaterals will be achieved through close monitoring of their implementation and results. We will negotiate on costs wherever possible.

Contract with the Monitoring and Evaluation Service Provider

The MEL service provider will be procured through an open competition. The terms of reference, design, and evaluation outputs will all be subject to DFID’s independent evaluation quality assurance process. The MEL provider will collect data for the programme and develop analysis of results to continuously inform programme’s adaptability to context.

DFID will develop the Terms of Reference for the procurement of the MEL provider ensuring that all the requirement for staffing, value for money, reporting and payments are well outlined. The contract will be milestone based in-order to ensure high quality and timely deliverables.

Value for Money will be ensured through the following:
Economy-The key cost drivers will be consultancy rates and administrative costs, which will be negotiated and benchmarked against market rates. DFID will monitor the partner budget after delivery of each milestone and insist on cost transparency;
- Efficiency- Drawing on experience with KDSP and the nature of this programme, DFID will insist on a strong team with a high percentage of local staff who have a good understanding of the devolution context in Kenya;
- Effectiveness- We will develop key performance indicators agreed with the partner to ensure performance is monitored regularly. Given this is a long-term programme, we will have break-clauses every 2 years to review performance and also make adjustments to the contract. Extension will only be approved where the partner has demonstrated good performance. In-order to drive quality in deliver, there will be a one-off provision for a Performance Improvement Plan;
- Equity- The MEL provider will carry out a gender and conflict sensitivity analysis to ensure considerations for women, girls and marginalized population and ensure the programme does no harm. The provider will be expected to work with all the implementing partners to mainstream the analysis in their programmes.

Accountable Grant with non-profit consortium

Following approval of this Business Case, DFID Kenya will develop a detailed term of reference for a competitive process of selecting a non-profit consortium to be completed by the end of the first year. At the end of year 1 detailed multilateral partner workplans will be in place and the non-profit consortium ToR will ensure complementarity and avoid duplication. Due to the varied scope of work to be delivered, potential bidders will be encouraged to form a consortium, with each organization bringing their areas of strength into the programme.

The call will specify an initial inception period of 3 months to enable the consortium lead to: finalize their agreements with other partners, prepare and finalize work plans. DFID will set out clear expectations in terms of:
Value for money: bidders will be expected to specify how they propose to drive down the cost of implementation (economy); find innovative ways to support counties implement reforms efficiently and effectively (e.g. in public finance and equitable service delivery). This will include ensuring there is gender, youth and disability inclusion.
Innovation/sustainable exit strategy: bidders will need to propose innovative, sustainable ways to attain the specified outcomes, as well as a well-defined exit strategy. Capacity to deliver local solutions (including local knowledge of the ASALs) past performance and likelihood of delivering results, as well as the strength of the methodology, will be key factors in the selection of proposals.

There are several organizations in Kenya that already have experience, networks and infrastructure in the country and have demonstrated the ability to build capacity, work in partnership with both the national and subnational governments. DFID carried out an Early Market Engagement in March 2019 which attracted 80 organizations. Some of the feedback has been used during the design of this BC. Another EME will be done during the mobilization phase of the programme to clarify the route to market and the programmes expectations.

The selection of a lead implementing partner will follow the UK Cabinet Office’s grant standards.[66] The accountable grant agreement, in addition to the minimum standards specified by the Cabinet Office, will retain the flexibility to scale up or down activities depending on the consortium’s performance, judged against pre-agreed key performance (output) indicators. DFID will, prior to grant award, fully scrutinize and challenge budgets and overhead costs in line with the allowable costs policy, ensuring resourcing and balance of inputs is appropriate to deliver the programme.
[66] Published on 2 December 2016 - https://www.gov.uk/government/publications/grants-standards/grant-standards

During the selection DFID will assess the proposals based on the understanding of the ToRs, VfM, ability to deliver and past performance. Prior to awarding the grant, DFID will carry out a due diligence assessments using the new guidance, to ascertain fiduciary risk and the organization’s ability to deliver the programme. A risk mitigation plan will be developed and monitored in partnership with the grantee based on the outcome of the due diligence assessment. The grantee will be expected to carry out due diligence assessments on any sub-contractors, based on DFID’s due diligence framework. It is expected that the sub-grantees will implement activities directly, without any further sub-contracts or grants, except for specialized short-term technical assistance on a need basis. After 3 years of implementation, we will undertake an independent evaluation and review progress/performance.

DFID will use the revised accountable grant document for this arrangement. Accountable Grant templates were revised in June 2019 following a review of DFID’s programme arrangements. The changes ensure that all grants are, at the minimum, compliant with UK legislation, Cabinet Office grant standards and the Smart Rules. The document specifies DFID’s standards on eligible expenditure, funds disbursement and financial reporting, audits and assurance, assets and inventory management, communication and branding, fraud, corruption, bribery, and other misuse of funds, among others. These standards including safeguarding will be discussed with the implementing partner prior to granting the award.

Implementing partner performance

Key Performance Indicators will be put in place and, as far as will be feasible, DFID will consider a performance-based system on payments for partners or explore and pilot any other system that will incentivize good performance. The lead partner will also be encouraged to apply a performance-based model to their sub-contractors. Lead implementing partner performance will be managed through, regular performance review/discussions, results, and annual reviews. Risk management, value for money, efficiencies and consultants’ costs will be included in performance reviews.

Approaches to achieving results and VFM

We anticipate that the key costs affecting the overall price of the programme will include Administrative fees, Indirect overhead costs, Consultancy fees, travel, workshops and sub-grants to downstream partners. Administrative fees for both the Consortium Partners and the sub-grantees will be benchmarked against rates negotiated in the existing grants arrangements for Governance programmes, which offer good VFM. On indirect overhead cost, the Programme team with support from the Commercial Delivery Manger (CDM) will aim to negotiate the lowest possible management fees and with transparency of overheads.

On the Consultancy fees, the key is to bring in the highest quality people possible at the best price. Clear criteria will be specified for the quality of personal required, and their costs benchmarked against similar organisations. Payment will be directly linked to performance and outputs. The terms of reference will give weight to the sourcing of local expertise that is available at lower cost.

The preferred delivery model is based on experience to date with the DDP and KDSP programme, which generated lessons about how to achieve optimum results and VFM in the Kenyan context.

Drawing on lessons from previous programming, for strong delivery of work DFID will insist on:
A strong field presence by the implementing partners and regular field engagement by senior Nairobi based staff, requiring enough staffing and travel budgets.
- Performance based agreements that are flexible to assess relevance and effectiveness, rather than too rigid sets of outputs/milestones
- Effective risk-based grant management and support to downstream partners, ensuring accountable for results, and efficient management of funds.

Strategies for achieving strong Results and VFM
The accountable grants arrangements will include an annex clearly setting out what the partner is expected to achieve with clearly defined staffing, technical assistance and grant pool budgets, with adequate field travel budgets
- A short inception phase will ensure rapid start up, with ongoing learning and redesign work if necessary
- Economies of scale will be achieved by working with the regional blocks in order to address common problems within counties
- The programme team will maintain long-term relationship with key individuals and institutions, which will be complemented by direct HMG engagement with government counterparts, to enhance prospects for impact on Devolution support.
- DFID will retain responsibility for risk but outsource programme management functions and the sourcing of technical advice to the Lead Partner in the Consortia.
- A clear programme framework and theory of change will ensure that flexible and adaptive programming remains focussed and coherent.
- Risks will be managed by a short delivery chain whereby the Consortium Lead retains direct control of all downstream partner contracts. DFID Kenya will approve all the grants over £15,000
- Inclusion (gender, Youth, persons living with Disability) will be considered throughout with clear milestones in the log frame.

Funding Decisions and driving Quality Performance
Given this is a long-term programme there will be flexibility in funds allocation to ensure that the programme adapts to the changing context. DFID will provide initial funding for two years to all partners and thereafter allocate depending on performance and production of quality results.

Drawn from previous lessons the programme will leave a flexible pot of funding to be allocated to partners depending with performance. This will also provide an incentive for quality performance by partners as they anticipate for more funding.

DFID will ensure all partners have signed the branding and visibility statement for this programme. The consortium provides DFID with a good opportunity for branding and providing visibility in the counties. There is a risk of DFID missing out on branding opportunities with the World Bank and the UN as the organisations have their own programmes and have an advantage of direct engagement with government and both National and Subnational. Drawing from experience with KDSP DFID will ensure the agreements provide recognition for DFID’s contribution on content development and during events.

Financial Case

Costs
The total budget of this programme is £38.5 million. It has been costed at an average of £6-8.5m per year over 5 years. The projections are indicative within the overall budget framework and actual allocations and spend between the budget lines will be adjusted based on performance and the need to keep the programme as effective as possible to respond to changes in the wider political context. Annual project reviews will recommend appropriate adjustments to allocations.

This business case includes a break clause which will be replicated in all partner agreements. Funding from March 2024 will require additional approval in 2023.

Budget (resource) estimated per output

Component	Estimated amount
Output 1: Intergovernmental relations support devolution	£3m
Output 2: County governments effectively manage public finances, staff performance and county planning	£12.5m
Output 3: Government and citizens collaborate effectively to address key problems in service delivery and poverty reduction.	£16m
Output 4: High quality evidence generation, learning and digital approaches improve capacity development	£ 4.5m
Output 5: The UK development portfolio is better aligned with county government priorities	£ 2.5m
Total Budget	£38.5m

A break clause will be inserted in all partner agreements to allow the programme to be discontinued or adjusted annually. A degree of financial flexibility within the overall approved budget will be required to respond to success and failure within the programme and variations within the governance context, particularly based around the risks.

Budget profiles per year

Partner	Incept. / (19/20)	Y1 20/21	Y2 21/22	Y3 22/23	Y4 / 23/24	Y5 / 24/25	Total (£m)
Multilaterals (UN and WB) MOU	0.5	2.5	2.5	2	2	2	11.5
Non-Profit Consortium. / Accountable grant	0	3	4	3	5	5	20
Monitoring and Evaluation Contract	0	0.5	1	1	1	1	4.5
Programme funded posts secondments	0.15	0.45	0.5	0.5	0.5	0.4	2.5
	0.65	6.45	8	6.5	8.5	8.4	38.5

The programme will be funded from DFID Kenya programme resources (RDEL). If this business case is approved, DFID Kenya will inform and seek approval from Management Accounts and Her Majesty’s Treasury for the commitments made beyond the spending review period. The indicative figures set out above are based on learning from the current Devolution programme.

Fund disbursement Mechanism and Management

Funds disbursement will be done based on approved workplans and budgets.

An initial disbursement will made to multilaterals upon signing the agreements, any subsequent disbursement will be done every six months based on performance on the delivery of the workplans and the results delivered. Drawing from the MAR review 2016, the due diligence assessments and recent experience working with both the World Bank and the UN, their systems have proven to be strong to absorb and manage huge funding. A planned light-touch due diligence assessment to both partners will provide additional assurance.

Disbursement to the NGO-consortium will be done quarterly to the lead partner. The consortium lead will be required to submit quarterly narrative and expenditure reports, which DFID will approve before making follow-up disbursements. The Lead partner will be responsible for disbursement and monitoring use of funds by all consortium members/ downstream partners. A funds flow map will be developed showing the movement of funds up-to the beneficiary level. DFID will carry out a thorough due diligence assessment on the consortium to ensure ability to deliver and that policies and procedures are in place for proper financial management. This will include reviewing the finance and project staff qualifications on grant management.

The MEL provider contract will be paid in arears

Financial and fraud risks assessment

At this stage, no direct financial support will be provided to government. The programme will be delivered through a combination of direct technical support to government by the implementing partners supported with ‘in-kind grants’ where required as well as direct grants awarded to (primarily Kenyan) non-profit organizations in order to expand the programme’s reach and local ownership.

While DFID Kenya does not currently provide direct financial aid to government due to concerns around fiduciary risk, as the programme continues (and county financial management systems are strengthened), there may be opportunities to provide direct aid to high performing counties, if our partnership principles are changed. This would have the advantage of delivering better value for money; building county systems and support an eventual exit from aid. This will require a conversation within the office to revise the partnership principles. We will also commission a Fiduciary Risk Assessment if necessary.

DFID Kenya carried out an analysis to explore the option of putting funds through the governments. The review concluded that there are still risks to funding county governments. Given this programme is long-term this option is likely to be reviewed for consideration in future.

After mitigation, the risk of fraud and corruption is considered moderate. The primary risk is poor financial practices by sub-grantees and allegations of unfair allocation of grants. This will be mitigated by rigorous due diligence, capacity building, monitoring, audit and spot checks by the implementing partners, overseen by DFID. DFID will hold regular review of portfolio decision on funding and partnerships.

All agreements will specify DFID’s requirement and timelines for reporting fraud or corruption, or any suspicions of fraud or corruption. Any DFID or partner concerns about fraud and corruption will be reported within the required timeframe to the Head of Internal Audit or the Counter Fraud and Whistleblowing Unit. DFID commits to raise awareness with all partners to ensure there is a mutual understanding of DFID’s expectations on fiduciary risk management especially reporting concerns and enhancing whistleblowing policies.

Monitoring, reporting and accounting for funds.

All partners will provide a justification for any request for advance payments. Any follow-on disbursements will be made after receiving expenditure reports for the previous disbursements. The reports and invoices will be scrutinised for accuracy by a DFID programme officer and quality assured by the programme manager; any inconsistency would be resolved prior to the invoice being paid by DFID. Implementing partners (IPs) will be expected to continuously monitor the progress of the programme and submit quarterly and annual progress reports to DFID. DFID will require detailed financial reporting by implementing partners to ensure that DFID funds are being spent in accordance with agreed work plans.

The non-profit consortium will also ensure that audit reports for funds dispersed to local partners will be made available to DFID, as well as their own annual audits. DFID will carry out ad-hoc risk-based audits of any aspects of IP’s work where we require further assurance. The IPs will also have an obligation to make all records available for audit by DFID. Where applicable due diligence assessments will be conducted on the IP at its HQ offices by the DFID procurement team. DFID has already carried our due diligence assessments for World Bank and UNDP, further light touch assessments will be carried out during the mobilization phase. DFID will carry out a close-out audit for the programme to ascertain all funds were used for the intended purpose of the programme.

All IPs will be expected to conduct due diligence assessments to a DFID standard on all its local partners and any sub-grantees. The DFID Kenya team will conduct spot checks on the IPs, which among others will include, reviewing the quality of some of the due diligence assessments conducted by the IP on sub grantees.

All assets procured under this project, will remain DFID assets and we will make recommendations for their disposal at the end of the programme. The partners will maintain a register of assets and will provide DFID with an updated list of all assets purchased every six months. The DFID programme team will maintain the master assets register and carry out spot-checks every 6 months.

The delivery chain for this programme will be very short. The Consortium Lead will hold a direct contract with all downstream partners, none of which will be permitted to sub-contract, reducing the risk, that DFID is unsighted on any downstream partner.

The SRO will be accountable for the expenditure of funds under this business case, including decisions on which organisations will be funded. DFID’s ARIES system will be used to monitor and account for expenditure. With the approval of the concept note an ARIES “project” has been created for this business case, with separate components for each programme. The SRO will authorise disbursement of funds based on the agreed funding profile set out in the funding agreements and contracts and the assessment of partner performance.

The DFID Kenya Programme Officer will be responsible for producing reports on actual and forecast spend against each of the components on a monthly basis. These reports will be reviewed by the Governance and Security section, including the SRO. Any inaccuracies, risks or issues identified will trigger a discussion with the respective IPs.

Management Case

Staffing
The Senior Responsible Officer (SRO) for the programme will be DFID Kenya’s Senior Governance Adviser. The role of SRO may be delegated to another member of the team in the course implementation if necessary. The SRO will engage with different partners during the mobilisation phase to discuss their detailed funding proposals and ensure spending submissions are drafted for each of them for approval by the Head of Office or delegate. The SRO will be supported by an A2 Devolution Adviser (100%) and an A2 Sub-National Strategy Adviser (20%). In addition, there will be five DFID staff members (County Leads) working in priority HMG counties who will monitor actual implementation on the ground and provide X-Office/HMG support on Political Economy Analysis.

The SRO will have programme management support from the management team of two people (A2L PM and B2 programme Officer). The SRO will ensure that DFID is adequately represented in the governance structures of our implementing partners as well as the overall donor and GoK coordination structures. We have included a provision for programme funded posts which can will support government stakeholders and also implementing partners if required.

Given the cross-cutting nature of the programme, the programme will be engaging with cross-Office/HMG team comprising of the following:

1	Social Development Adviser
2	Urban/Infrastructure Advisor
3	Health Advisor
4	M&E Advisor
5	Humanitarian Advisor
6	X-HMG Policy and Prosperity boards
7	Conflict Advisor
8	Gender Advisor
9	Climate Advisor
10	Sub-National lead

The team will regularly meet as required to discuss linkages, risks and opportunities for more interventions in the counties. DFID will also attend all IP Steering Committee meetings, which happen on a quarterly basis. DFID will constitute a steering committee that will meet every six months to assess progress with partners, learn lessons and agree any programme adjustments. This committee will be supported by the M&E partner, that will act as a secretariat and present findings from PEAs and surveys undertaken in the preceding six months.

The political nature of the devolution programme requires continuous and up to date understanding and appreciation of the political issues in the national and county space. In line with ensuring that the programme is flexible and adaptive, we will have continuous political economy analysis and perception surveys. We will also strengthen the forums for evidence sharing and analysis from the outgoing programme.

Partnerships and coordination

We will apply our partnership principles to ensure consistency in approach with all of UKAID in Kenya. For example we will not put bilateral funds through government systems and if a strong rationale for doing so develops over the life of the programme, we will engage across-DFID in country to consider adjustments to our partnership principles.

We will closely monitor alignment of the programme with government of Kenya’ priorities to ensure strong government ownership. We will also closely monitor all assistance provided to government to ensure it builds capacity rather than substitutes for it, and leads towards an effective exit strategy. We will ensure robust reviews of the programmes delivery to measure results and VfM and reduce funding to inefficient or ineffective workstreams.

The Government of Kenya has a Devolution Sector Working Group (DSWG), chaired by the Ministry of Devolution and Planning and with representation from Kenya’s National Treasury, Council of Governors, donors and other bodies involved in devolution. This body meets monthly at the technical level and is meant to meet twice a year at the level of heads of institutions. The DSWG is still evolving and a lot still needs to be done to improve it and ensure it plays it role effectively.

A second coordination structure is the Devolution Donor Working Group (DDWG.) This brings together donors working on devolution allowing for more in-depth discussions on the respective door funded programmes and agreeing common donor positions for dialogue with national and county governments. This forum also allows for frank dialogue and challenge amongst donors and is proving to be a useful forum for coordination. Helpfully the group is currently co-chaired by DFID and UNDP so this should help with coordination of all devolution programmes.

The World Bank and UN have steering committees for their programmes which meet quarterly, and which the DFID Kenya team will participate in.

DFID will establish a programme steering committee which will bring together the multilateral partners, non-profit consortium, M and E supplier to regularly review the coherence of the programme and to share results reporting and learning identify good VfM.

DFID will actively participate in these two structures and rely on them for coordination of the programmes funded under this BC. This approach allows for coordination with other programmes not funded under this BC and reduces the number or parallel meetings discussing similar issues. DFID will also convene as necessary coordination meetings with the implementing partners especially around developing workplans, annual review and other evaluations. The County Leads will help with mapping and coordination of DFID funding in the counties including Central Managed Programmes (CMPs).

The programme team has a close working relationship with the FCO – Political Team, the Department for International Trade, DFID’s Research and Evidence Division and GOSAC’s Public Finance and Transparency, Accountability and Politics groups. The programme will play a leading role in the roll-out of DFID- Kenya’s Sub-national Strategy including packaging the county assistance offers to improve service delivery and managing the DFID staff hired to oversee clusters of counties. Additionally, CMPs like the tax reform programme and Westminster Foundation for Democracy’s programmes amongst others will liaise with the programme on aligning the tasks and partners.

Monitoring, Evaluation and Learning (MEL)

The programme will be robustly monitored and evaluated by DFID and implementing partners, including through independent assessments. Key information will be shared with government and other donors as a contribution to inform improvements across devolution programmes and learning in the sector.

Experience to date with devolution programming is that there will be some result areas where it is easy to set indicators and targets in advance and others that are less predictable given the political nature of devolution – some entry points will open or close unexpectedly and the programme needs to adapt as necessary. There is also a complex relationship between capacity building and the desired outcomes that is not easily captured in linear results frameworks – one must consider the political environment, institution and cultures. This context is different across counties and is also constantly changing. This reality requires nimble programmes with continuous dialogue, review and reprioritization with partners and government.

We have a clear sense of the broad results at impact, outcome and output level, we also have a good idea of the range of possible interventions that can contribute to meeting each of the output areas. The indicators, milestones and targets will be clearer after the mobilisation phase once we agree specific results and deliverables.

The independent MEL provider will be responsible for supporting DFID’s overall programme monitoring, evaluation and learning. The MEL provider will triangulate data from different kinds of assessment to build a more complete picture of progress e.g. perception surveys, year on year analysis of audit reports, expert panels etc. DFID will also commission case studies/analysis on different topics to ensure there is continuous learning and adaptation in the programme. We will ensure this workstream building government knowledge and capacity for MEL. DFID will provide oversight to ensure the MEL provider delivers on the programme’s results management and evidence generation.

All partners will be encouraged to innovate and use digital approaches to generate learning and evidence and support the government of Kenya’s Digital Economy strategy. The MEL provider will support these efforts across the programme.

We will use the mobilisation phase to firm up the individual results each of our partners will deliver and design this overarching results framework together with the monitoring plan, working with DFID Kenya’s Accountability and Results Team (ART). We expect the following M&E deliverables after the mobilisation phase:
Firm up concrete deliverable for those areas that are easy to measure and set targets and milestones for which may easily lend themselves to a log-frame format
- A framework for how we can better capture the impact of hard to measure inputs such the technical assistance and training as well as contribution for higher level outcomes such as on policy areas or on new laws etc.
- A broader results framework that captures not only the deliverables we can sign up to in advance but those where there are moving targets or those where we have been flexible and taken opportunities of changing circumstances reflecting the demand driven nature of some components.
- A results system that is well coordinated with that of other stakeholders and includes a range of tools for collecting information.
- The climate change results under this programme will be reported against the ICF Key Performance Indicator 13 and any others that may be identified once the programme’s firmed up.

Programme monitoring and independent programme evaluation/review. Ongoing monitoring is integrated into the programme design. The programme will also be evaluated independently at appropriate points – baseline, mid-term and final. The programme will run an in-depth research programme on devolution throughout the core programme, with the aim of building a substantially more robust evidence base on what works in supporting sustainable devolution. We have set aside £4.5m funds for independent M and E (which will also contribute evidence and learning to output 4).

Given the governance context in Kenya is volatile we will continue to monitor regularly the assumptions outlined in the Theory of Change. We will prioritise evidence gaps that we want the programme to fill (e.g. on service delivery impacts, utility of digital approaches, etc)

Monitoring and Evaluation of VFM

We will use the ITAD-DFID Nigeria Governance VFM diagnostic tools and indicators to develop our Governance VFM indicators. Examples of how we will apply them to indicator types under the 4 outputs and against the 4 Es below.

For cost effectiveness we will aim to measure value for money in terms of the overall improvements delivered by the programme at the impact level. We will identify indicators in the top left corner of the matrix below. We will avoid stand-alone process indicators and seek trends and ideally benchmarks that can be measured quantitively (ie nutrition, health and poverty statistics) and in monetary terms (ie gross county product per capita). For example, we will measure changes in poverty statistics in target counties, that can programme interventions aimed to directly contribute to.

Cost-Effectiveness
	Benchmark	Trend	Stand Alone
Monetary
Quantitative
Qualitative
Process

For Efficiency we will aim to measure value for money in terms of how much of the programme contributes to the desired outcomes. Again, we will avoid stand alone process indicators and rather aim for the top left corner of the matrix below. For example, there are quantitative benchmarks for effective open and accountable government (see county targeting above and annex 2)

Efficiency
	Benchmark	Trend	Stand Alone
Monetary
Quantitative
Qualitative
Process

For Economy we will aim to measure value for money in terms of the costs of inputs and activities, we will aim to measure this against benchmarks for DFID programmes in Kenya (ie local consultancy rates, conference costs, downstream partner operating costs, etc) rather than simply against the programme’s own budgets and plans (stand-alone process indicators)

Economy
	Benchmark	Trend	Stand Alone
Monetary
Quantitative
Qualitative
Process

We will develop indicators also for measuring Equity

Partner Monitoring & Evaluation

Implementing Partners will be responsible for providing DFID with quarterly and annual progress reports. In the case of UNDP and WB these reports will be considered at the Project Steering Committee meetings and Quarterly review meetings respectively. Any technical staff working at the county level will maintain regular contact with county interlocutors and continuously evaluate progress, challenges, and opportunities to ramp up assistance.

Different tools supported under this programme will be useful in tracking county performance. Performance management and M&E will be both a programme deliverable contributing to county capacity as well as programme management tool to help us track results. Programming will start by discussing expected results with partners and how they will jointly achieve and measure those results. Participatory M&E will leave improved capacity within the target counties and CSOs, providing partners and communities with more efficient and effective methodologies to collect and share information on program outputs and outcomes, best practices, and effective networking models. Continuous dissemination will support learning, programmatic adaption and partner empowerment.

Risk Management

The risk rating for this programme is moderate, this is within DFID Kenya’s risk appetite. The primary risk for this programme is likely to be political.

Devolution means a transfer of power, functions and resources from the national level of government to county governments. This process has winners and losers which can create resistance to change. As such, the main risks to the success of devolution this programme are political risks. Some of the primary threats to the effective implementation of the system of devolved government identified are: (i) politicization of the process of institutional reforms coupled with inadequate focus on institution building; (ii) poor inter-governmental relations leading to a tendency of both levels of government to discharge (in some cases finance) functions that are not within their purview; (iii) policy, legislative and institutional frameworks that are not cognisant of devolution and; (iv) low levels of capacity and skills.”

This programme will start just after the national population census in August 2019 and within one year (in 2020) there is the possibility of a national referendum on the Constitution. 2022 will be an election year. Intergovernmental tensions may result from disputes over functions and resources as well as inter-county border disputes. Kenya’s macroeconomic situation has the potential to result in reduced disbursements to county governments due to public debt servicing obligations and consistent failure to reach revenue collection targets. There is also a risk of the programme spreading too thin, across issues and counties. The Business Case will help focus down on the areas that will show the greatest impact and value for money.

This programme is within DFID’s risk appetite at the end of 2019. Our risk appetite is reviewed regularly. We have a:
High appetite for external context risk. DFID works in fragile, conflict affected and volatile situations, and in contexts where political stability is low or where political or economic governance compromises the rights of citizens. We have a zero-tolerance approach towards and will work to prevent fraud and corruption, reporting and acting upon all suspicions.
- DFID has a low appetite for operational risk. We strive to ensure the highest possible professional competence, experience and appropriate level of resource in managing our programmes and funds. We have a low risk appetite for management failures but will always seek to learn lessons in order to improve.
- DFID has a low appetite for risk associated with unintended harm to people and to the environment as a result of our programmes. We expect all partners to follow our lead and to apply robust safeguards and reporting measures.
- DFID has a high appetite for delivery risk. We sometimes work in very difficult operating environments and we take an innovative approach to deliver high impact programmes. We will be flexible to accept a higher risk appetite in the contexts where these factors exist but seek to minimise and mitigate risks.
- DFID has a low appetite for reputational risk. DFID must seek to avoid significant reputational damage associated with poor management, the misuse of funds, or inadvertently doing harm through our actions. We are seeking to work more closely with the Government in a maturing development partnership on ambitious programmes of reform, and there is a reputational risk in doing so which will manage through robust cross HMG political economy analysis

The table in annex 1 summarizes the main risks likely to face this programme and the mitigation actions. A more detailed risk register will be maintained for the programme and regularly reviewed.

ANNEX 1: Outline Risk Matrix

Risk Description	Like-lihood	Impact	Gross Risk	Mitigation Strategy	Likely-hood	Impact	Residual Risk
Contextual
Reduced political commitment to devolution and reforms.	Possible	Major	Major	Devolution will continue to feature high in the UK’s political and development dialogue with GoK, building on GoK strategies and commitments. Recruitment of county-based programme funded staff will keep UK informed on the political economy and development effectiveness at the county level.	Unlikely	Major	Major
Vested interests and elite networks undermine accountability and transparency initiatives.	Likely	Moderate	Major	We will work with the political team on high level policy dialogue to keep open government and anti-corrption high of the agenda and will ensure within the programme a balance of support to citizens and civil society.	Possible	Moderate	Moderate
Inertia results from political challenges in inter- and intra- governmental coordination	Possible	Moderate	Moderate	Encourage constant dialogue between national and county governments. Provide support to strengthen inter-governmental dialogue structures e.g. Council of Governors, the IGRTC, and Regional Economic Blocks	Unlikely	Moderate	Moderate
Operational Risk
Breadth and depth of capacity building by partners is insufficient to build a critical mass of county capacity.	Unlikely	Moderate	Moderate	The programme design is intended to ensure sufficient capacity build at the county level, through the combination of multilateral efforts and the non-profit consortium. County based staff and more robust county targeting will support this. DFID will monitor results closely and ensure adaptation if they are ineffective	Rare	Moderate	Minor
Security context deteriorates in target counties limiting the programme’s access	Possible	Major	Major	DFID will work with implementing partners to deepen our shared understanding of the security context in each county and strengthen further our mitigation measures. We will ensure regular analysis and prompt measures to adapt	Possible	Moderate	Moderate
Delivery Risk
Inadequate funding for multilateral programmes as other donor programmes close in Dec 2019	Unlikely	Moderate	Moderate	DFID will support multilateral fundraising efforts, and support multilaterals to plan for maximum impact with available budgets	Rare	Moderate	Minor
Potential duplication of activities by implementing partners	Unlikely	Moderate	Moderate	DFID will ensure that coordination between all devolution implementing partners takes place through the steering committees, donor group and this programme’s committee. meeting. The M&E team will also be required to all IPs together for learning and coordination.	Rare	Moderate	Minor
The 2022 elections will lead to a change of some national and county govt officials and if results are contested this may lead to extended gaps in staffing.	Possible	Moderate	Moderate	Programme interventions are designed to target a sufficient number of senior national and county government staff who do not hold elected positions. Programme timeframes have been proposed with due consideration of the likely reduction of programming around the 2022 election period. DFID and partners will work with the IGRTC to start preparations on key government transition activities that occur after elections.	Possible	Minor	Moderate
Poor Performance by implementing partners	Unlikely	Major	Major	We will review implementing partner performance quarterly and during annual reviews. The Devolution Sector Working Group, donor group, steering committees, and independent MEL contract will be used to track progress. This will be complemented by regular external engagement by the DFID teams, nationally and in counties. The County based programme funded staff will support this.	Rare	Moderate	Minor
Safeguarding risk
4.1 Risk that the staff/consultants employed by implementing partners and their downstream partners use their position to cause harm to vulnerable people	Unlikely	Severe	Major	DFID will carry out enhanced due diligence assessments on all partners. We will also provide additional capacity to first tier partners to manage the risks with downstream partners. Regular DFID-led risk discussions and spot-checks will provide assurances on management of this risk.	Rare	Major	Moderate
Fiduciary Risk
Loss of UKaid from financial mismanagement or fraud	Possible	Moderate	Moderate	We will not provide direct financial aid to GoK. We will monitor risks of fraud within implementing partner programmes closely though due diligence risk assessments, financial reports, audits and spot checks (including beneficiary feedback and check on whilstle-blowing requirements). Major procurement decisions will be discussed at quarterly steering committee meetings.	Unlikely	Moderate	Moderate
Reputational risk
Implementing partner/s perceived to be partisan towards a political party/politician.	Possible	Major	Major	DFID will issue annual letters to partners reminding them of the need to be impartial, and will increase emphasis on this during the election period	Unlikely	Moderate	Moderate
Reputational risk to UK through association with county governments that may face scandals arising from politics or corruption	Possible	Major	Major	DFID will ensure that the programme works primarily with counties where there is a clear path towards reforms and commitment demonstrated to achieving development impact. We will ensure support is rapidly scaled down/suspended to individuals and counties where new significant risks emerge.	Possible	Moderate	Moderate
Sustainability Risk
Risk the programme undermines sustainability of devolution by substituting capacity rather than building it	Possible	Major	Major	DFID will monitor closely all programme approaches to capacity building to ensure that all experts and advisors working with GoK have clear capacity building plans and exit strategies for specific workstreams	Unlikely	Moderate	Moderate

R1.1 Reduced political commitment to devolution and reforms.
R1.2 Vested interests and elite networks undermine accountability and transparency initiatives.
R1.3 Inertia results from political challenges in inter- and intra- governmental coordination
R2.1 Breadth and depth of capacity building by partners is insufficient to build a critical mass of county capacity.
R2.2 Security context deteriorates in target counties limiting the programme’s access
R3.1 Inadequate funding for multilateral programmes as other donor programmes close in Dec 2019
R3.2 Potential duplication of activities by implementing partners
R3.3 The 2022 elections will lead to a change of some national and county govt officials and if results are contested this may lead to extended gaps in staffing.
R3.4 Poor Performance by implementing partners
R4.1 Risk that the staff/consultants employed by implementing partners and their downstream partners use their position to cause harm to vulnerable people
R5.1 Loss of UKaid from financial mismanagement or fraud
R6.1 Implementing partner/s perceived to be partisan towards a political party/politician.
R6.2 Reputational risk to UK through association with county governments that may face scandals arising from politics or corruption
R7.1 Risk the programme undermines sustainability of devolution by substituting capacity rather than building it

Annex 2: Illustrative County data to inform prioritization and targeting
County	Total population in poverty (2016)	Of which extreme poor (2016)	total county population (2016)	% of total population in poverty (2016)	Growth Own Source Revenue % 18-19	Progress Audit / account-ability Index %	Gross County Product pc growth (%) 14-17	Depth of X-DFID/HMG interests investment
Mombasa	321,000	27,000	1,185,000	0.27	56	74.21	2.9	Tbc
Kwale	389,000	48,000	820,000	0.47	12	73.53	2	Tbc
Kilifi	650,000	98,000	1,400,000	0.46	42	72.52	1.3	Tbc
Tana River	189,000	54,000	304,000	0.62	99	24.32	1.8	Tbc
Lamu	36,000	4,000	128,000	0.28	2	21.61	1.5	Tbc
Taita Taveta	116,000	19,000	358,000	0.32	79	48.31	3	Tbc
Garissa	283,000	103,000	432,000	0.66	35	73.53	1.4	Tbc
Wajir	287,000	48,000	459,000	0.63	-17	21.61	1.8	Tbc
Mandera	552,000	277,000	711,000	0.78	42	73.87	2.5	Tbc
Marsebit	201,000	75,000	316,000	0.64	51	73.31	3.7	Tbc
Isiolo	81,000	14,000	156,000	0.52	57	69.47	3.8	Tbc
Meru	285,000	42,000	1,471,000	0.19	20	72.4	4	Tbc
Tharaka Nithi	94,000	7,000	396,000	0.24	85	72.4	7.5	Tbc
Embu	158,000	22,000	560,000	0.28	89	46.39	1.6	Tbc
Kitui	522,000	141,000	1,098,000	0.48	50	72.4	2.4	Tbc
Machakos	278,000	41,000	1,191,000	0.23	-17	71.73	3.85	Tbc
Makueni	334,000	63,000	959,000	0.35	53	99.21	2.8	Tbc
Nyandarua	239,000	23,000	686,000	0.35	16	98.42	7.2	Tbc
Nyeri	154,000	1,000	798,000	0.19	20	73.87	4.5	Tbc
Kirinyaga`	122,000	6,000	608,000	0.20	56	72.74	2.7	Tbc
Muranga	274,000	56,000	1,085,000	0.25	75	46.95	2.5	Tbc
Kiambu	435,000	58,000	1,868,000	0.23	58	73.31	4.5	Tbc
Turkana	860,000	571,000	1,084,000	0.79	17	74.77	0.6	Tbc
West Pokot	373,000	170,000	649,000	0.57	44	73.53	1.4	Tbc
Samburu	215,000	120,000	284,000	0.76	-3	71.61	1.7	Tbc
TransNzoia	353,000	101,000	1,038,000	0.34	47	73.08	0.5	Tbc
Uasin Gishu	465,000	137,000	1,133,000	0.41	15	74.44	1.3	Tbc
ElgeyoMarakwet	204,000	57,000	469,000	0.43	39	72.97	6.2	Tbc
Nandi	343,000	76,000	954,000	0.36	8	73.31	0.1	Tbc
Baringo	278,000	60,000	704,000	0.39	20	72.97	3.6	Tbc
Laikipia	233,000	76,000	507,000	0.46	95	73.31	4.5	Tbc
Nakuru	592,000	75,000	2,031,000	0.29	30	71.5	3.75	Tbc
Narok	243,000	60,000	1,078,000	0.23	64	73.08	1	Tbc
Kajiado	355,000	99,000	871,000	0.41	70	73.42	2.1	Tbc
Kerichio	286,000	69,000	945,000	0.30	35	73.31	1	Tbc
Bomet	447,000	56,000	916,000	0.49	1	73.76	2.3	Tbc
Kakamega	672,000	129,000	1,876,000	0.36	100	73.87	2.7	Tbc
Vihiga	271,000	51,000	627,000	0.43	32	70.82	4.25	Tbc
Bungoma	555,000	137,000	1,553,000	0.36	31	74.55	5.75	Tbc
Busia	583,000	225,000	840,000	0.69	52	73.87	5.25	Tbc
Siaya	333,000	60,000	985,000	0.34	29	72.29	6	Tbc
Kisumu	384,000	68,000	1,132,000	0.34	-5	72.63	1.2	Tbc
Homa Bay	360,000	64,000	1,072,000	0.34	-19	46.05	3	Tbc
Migori	464,000	40,000	1,126,000	0.41	79	23.76	4.5	Tbc
Kisii	562,000	101,000	1,347,000	0.42	48	73.87	2.9	Tbc
Nyamira	229,000	53,000	699,000	0.33	74	73.65	2.5	Tbc
Nairobi	745,000	26,000	4,463,000	0.17	8	18.45	0	Tbc