Programme Completion Review

Title: Kenya Devolution Programme (KDP)
Final Programme Spend £ (full life): £10,400,000	Review Date:	Sept 2025
Programme Code: 300645	Start Date: / 17 December 2019	End Date: 30 June 2025

Summary of Programme Performance
Year	Dec 2020	Dec 2021	Dec 2022	June 2024	Sept 2025
Programme Score	A	B	A	B	B
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300645
DevTracker Links to all logframes used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/60025540.xlsx

A. Summary and Overview (1-2 pages)

Description of the programme
In 2013, Kenya launched a major governance reform with the creation of 47 county governments, as mandated by the 2010 Constitution. Devolution is widely seen as the most significant governance reform since the start of multiparty politics in the 1990s, and a key driver of improved service delivery and poverty reduction beyond the capital, Nairobi.

The UK has supported this journey with over £39.5 million, delivered through 4 successive programmes implemented between 2013 and 2025[1]. The most recent, the Kenya Devolution Programme (KDP), provided £10.4 million over 5.5 years (January 2020 – June 2025). KDP aimed to strengthen the effectiveness of devolution by supporting county governments to be more accountable, responsive and to deliver better services to citizens. Initially approved as a £38.5 million programme, KDP was scaled down to £13.75 million in 2020, prior to implementation in anticipation of potential reductions in UK Overseas Development Assistance (ODA). It ultimately spent £10.4 million by its conclusion, mainly due to in-year ODA allocation reductions between 2022 and 2025.
[1] Kenya Accountable Devolution Programme, July 2012 – Nov 2015, £3.96m Kenya Bridge Devolution Programme, Sept 2013 - June 2014, 1.35m Kenya Devolution Support Programme, May 2015 – Dec 2019, 23.5m

KDP built on the Kenya Devolution Support Programme (KDSP, 2015 - 2019), which focused on helping counties establish foundational systems and processes to manage increased resources. KDP was designed to shift the emphasis to demonstrating how these systems and processes could lead to tangible improvements in service delivery.

The programme aimed to achieve two main outcomes:
1. More responsive, open, and accountable county governments.
2. County governments that are socio-economically stronger and delivering improved services.

These outcomes were pursued through five outputs:
- Improved intergovernmental relations and coordination[2].
  [2] Between County Governments and the National Government and among County Governments themselves
- Strengthened county economic planning, trade, and investment capacity.
- Enhanced social accountability and participatory approaches in devolved sectors.
- Increased use of research and evidence to inform policy and service delivery.
- Better alignment of the UK development portfolio with county priorities.

The intended impact was improved development outcomes and reduced poverty at the county level.

Context and impact on programme design
Shortly after KDP’s approval in early 2020, Kenya reported its first COVID-19 case. Containment measures quickly disrupted programme mobilisation and delivery by BHC Nairobi. Simultaneously, in recognition of potential significant UK ODA reductions, BHC Nairobi made immediate adjustments to the programme scope and funding. As a result, plans for funding were scaled down as follows:
A £2 million Administration Agreement was signed with the World Bank, contributing to the Kenya Accountable Devolution Programme (KADP) Phase III trust fund, co-financed with the Danish International Development Agency (DANIDA) – to support enabling policy environments, public finance and Human Resource management, and cross-county learning. This was down from the £11.5 million intended for multilaterals in the business case.
A £250,000 rapid response grant was issued to Mercy Corps/Shujaaz for a county youth-focused public health campaign.
A £10 million accountable grant was awarded to Act Change Transform! (ACT) (down from the £20 million proposed in the business case) – to focus on intergovernmental relations, county capacity building, and civil society engagement.
The planned £4.5 million independent Monitoring, Evaluation and Learning (MEL) service was cancelled. Instead, bidders for the non-profit component - ultimately awarded to ACT - were required to integrate MEL into their proposals. The implementing partner’s MEL would be complemented by FCDO’s internal MEL, including evaluations and reviews commissioned directly by BHC.

A team of (initially 4) programme-funded regional advisers were recruited to support county governments and regional economic blocs, aligning UK development efforts with county plans. This proceeded as per the business case plan.

Additional contextual challenges included the 2022 general elections, which slowed government operations and required re-engagement with new county leadership. Significant national events in 2023 required schedule adjustments . Delays in national revenue disbursements to counties continued to affect county service delivery.

Performance and programme achievements
Despite operating in a challenging national and global context, KDP delivered or contributed to several important results in Kenya’s devolution sector including:
1. Progress on delineation of devolved functions: KDP provided targeted support to the Inter-Governmental Relations Technical Committee[3] (IGRTC) on the unbundling and transfer of functions, culminating in the gazettement of the Delineation of National and County Government Functions in December 2024[4].
  [3] A state agency tasked with ensuring harmonious intergovernmental relations within Kenya’s devolved system of government. Its core mandate includes administering the Summit (the apex body for intergovernmental relations) and the Council of Governors, including implementing their decisions; promoting intergovernmental dispute resolution mechanisms; coordinating sector working groups or committees to enhance collaboration across different government functions; taking over residual functions of the transition entity that oversaw the shift to devolved governance.
  [4] The Gazette Notice (Vol. CXXVI—No. 219), formalised the transfer of over 500 functions. This was important as it provided the legal and formal confirmation of the shift in responsibilities from the national government to county governments across the 500 functions, in a way that’s transparent, binding and enforceable. It also enables the allocation of resources - both financial and human - aligned with the transferred functions. It creates a reference point for accountability, coordination, and monitoring. The transferred functions span the following sectors: 1. Agriculture, Livestock & Fisheries: Functions related to crop production, animal health, fisheries, and agricultural extension. 2. Health Services: Includes county health facilities, pharmacies, public health, and primary healthcare. 3. Trade, Industry & Cooperatives: Covers trade licensing, market development, support for cooperatives, and local enterprise promotion. 4. Transport & Infrastructure: Encompasses County roads, street lighting, traffic management, and public transport. 5. Education: Focuses on Early Childhood Development (ECD), village polytechnics, and adult education. 6. Environment & Natural Resources: Includes waste management, pollution control, forestry, and climate change adaptation. 7. Public Works & Housing: Covers stormwater drainage, county housing, building approvals, and infrastructure maintenance. 8. Disaster Management: Includes firefighting services, emergency response, and disaster preparedness. 9. Cultural Services & Recreation: Encompasses libraries, museums, sports facilities, and cultural heritage programs. 10. Land, Urban Planning & Survey: Covers spatial planning, land survey, development control, and zoning. 11. Water & Sanitation: Includes water supply, sewerage systems, borehole development, and hygiene promotion. 12. Social Services: Focuses on support for vulnerable groups, gender and youth empowerment, and community development.
2. Strengthening Public Financial Management (PFM) and Human Resource (HR) systems: The programme contributed to major reforms, including enhancements to Kenya’s Integrated Financial Management Information System (IFMIS), the nationwide shift to accrual accounting and elimination of manual payroll in 27 counties.
3. Increased Own Source Revenue (OSR):  Notable growth in locally generated revenues during FY 2024/25[5]. Four of five counties receiving targeted technical assistance from KDP – including Taita Taveta, Homa Bay, Kakamega and West Pokot - recorded revenue growth. Homa Bay’s growth was significant at 44%, also surpassing its revenue target by 17%.
  [5] COUNTY GOVERNMENTS BUDGET IMPLEMENTATION REVIEW REPORT FY 2024/25 – Office of the Controller of Budget
4. Improved participatory governance: County CSO networks applied social accountability tools to improve service delivery in key devolved sectors for example, successful advocacy for health facility infrastructure improvements in Kiambu County, improved access to water in Baringo County and better access to markets in Bungoma County.
5. Support to Regional Economic Blocs (REBs): KDP strengthened REBs institutional capacity, for example by developing an e-Monitoring, Evaluation and Learning (e-MEL) system for the Lake Region Economic Bloc’s (LREB), to build the bloc’s capacity for future evidence-based decision-making[6].
  [6] Work on the system was only completed in June 2025, it is yet to be tested.

While KDP delivered a number of notable outputs, and built strong relationships with government stakeholders, there was limited and inconsistent evidence that these outputs translated to the intended outcomes[7]. The review notes that the logframe measures could have been more robust, and that significant delivery challenges impacted the programme’s Value for Money. Consequently, the programme scores an overall ‘B’.
[7] Outcomes are not scored quantitatively in FCDO Programme Completion Reviews

Globally, devolution is inherently political, involving control over resources and power, often fuelling tendencies toward recentralisation. For example, the initial gazettement - and later revocation - of the delineation of national and county government devolved functions illustrates this. As well, KDP had to pause progress on a County Resource Development Bill - which would have provided a legal basis for the establishment of REBS and therefore allowed for their funding and sustainability - when the Bill was not passed by the Senate. The programme has had to navigate this highly political environment, which required adapting to shifting priorities and pausing or dropping some workstreams, which exacerbated the issue of thin spread. Finally, the level of devolution in Kenya remains relatively nascent, and more time is needed for reforms to take root and translate into measurable development outcomes.

While the programme delivered well on several process indicators, such as the drafting of legislation, it will take time for these to be implemented and to translate into sustainable, and meaningful outcomes. Implementation will depend heavily on political will, and sustainable financing, primarily from the Government of Kenya, and gradual cultural and behavioural shifts. Governance outcomes such as improved public administration, decentralisation, reduced corruption, and rule of law often emerge slowly, beyond typical project cycles, and therefore development partners and governments must take a long-term perspective.

That said, devolution remains central to Kenya’s governance, and an anchor of national development, economic prosperity and political stability in Kenya. In mid-2025, the government has made further steps toward empowering counties both administratively and politically. Following the gazettement of function transfers, the National Government committed to ensuring that resources - funds, personnel, and assets - follow the devolved mandates. In August 2025, the Government of Kenya (GoK) gazetted the transfer of fixed assets from the defunct local authorities and national government entities to respective counties, and at the 2025 Devolution Conference, the President signed two significant bills into law:
1. County Allocation of Revenue Bill, 2025 – governing the distribution of KSh 415 billion[8] to counties, a KSh 30 billion[9] increase from the previous year and
  [8] £2.39B
  [9] £0.17B
2. County Public Finance Laws (Amendment) Bill, 2023 – establishing a dedicated fund for each county assembly to strengthen financial independence and oversight.

Major lessons learned, evidence generated and recommendations
Several recommendations from the predecessor programme were successfully implemented or demonstrated including:
1. Working with a mix of a multilateral and a non-profit consortium proved advantageous. The World Bank was well-positioned to lead analytical work, generate evidence, and provide technical assistance. Participation in the World Bank-managed trust fund also offered a degree of stability and continuity during periods of uncertainty in UK ODA, by leveraging co-donor contributions.
2. Building the capacity of national institutions to effectively engage with and support county governments was essential for scaling and sustaining reforms. By the end of KDP, this approach had contributed to improved capacity within national institutions to provide technical assistance - often preferred by county governments over externally sourced consultants. Holistic methods that combined coaching, mentoring, and technical assistance - delivered by teams working closely with both mid-level and senior county officials - proved to be the most effective.
3. Institutional strengthening was reaffirmed as both a technical and political process. Workstreams that were successful required time to embed change, relationship-building and continuous dialogue.
4. Regional Economic Blocs (REBs) continued to demonstrate their value as platforms for cross-county learning and collaboration, with strong potential to support the scaling of results. While efforts by KDP (and other partners) to develop a legal basis for REBS that would allow their funding by counties were unsuccessful, engagement with REBs should remain a priority for BHC Nairobi. They offer a more viable approach for economic development, growth, trade and investment objectives, which are more feasible across county clusters, than with individual counties. BHC should also continue to leverage REBs’ convening power.
5. A consistent approach across implementing partners on financial support to workshop participants remains necessary. Variation in stakeholder practices on meeting participation affected scheduling in some instances.

Lessons from KDP implementation:
1. This phase of the programme focused on improving sector-specific service delivery through capacity building at county level and policy reform at national level. However, implementation showed that foundational aspects of devolution (systems, processes and frameworks) still need strengthening - an iterative process that will take time. Achieving and measuring sustainable service delivery outcomes, in this sector and political context, requires long-term commitment by both development partners and GoK (national and county).
2. Anticipating potential ODA reductions, BHC Nairobi made early, difficult but prudent decisions to scale down budgetary commitments, as noted in the December 2021 Annual Review. While this helped manage expectations and resources, it was not followed by a thorough revision of the programme’s theory of change or a redefinition of expected results. Although logframe milestones were revised annually, a more robust review of the Theory of Change and logframe outputs and indicators would streamline the programme,guide adaptive management, and better align delivery with intended outcomes. Implementation was fragmented across small-scale initiatives in multiple locations, many of which were not sustained in subsequent years. This broad reach often compromised depth, quality, often did not achieve a critical mass needed to drive broader reforms or ensure lasting results.
3. The programme operated in a highly political environment, which at times required prioritising workstreams with greater political traction while pausing or discontinuing others. KDP also frequently responded to ad hoc requests from GoK, which, while fostering goodwill and collaboration, diverted attention and resources from its core objectives. This high level of responsiveness led to a dispersion of efforts, with the programme engaging in a wide array of activities across multiple areas. In this context, the programme would have benefited from a stronger adaptive management and MEL, to inform strategic changes to workstreams.
4. While KDP invested significantly in data and statistics through KADP - for example, through the development and updates of the Gross County Product (GCP) Report - strengthening county-level statistical functions remains a gap. Future programming should focus on enhancing counties’ ability to generate and analyse data, and to use evidence to inform policy decisions. This may include making difficult trade-offs, as evidence-based policies may not be the most popular or demanded by citizens.
5. KDP’s Output 5 was partly delivered through 2–5 county-based regional advisers who supported aid effectiveness at sub-national level, political analysis, stakeholder engagement, and local representation. In the context of declining ODA budgets and no follow-on devolution programme, this function is increasingly critical to guiding BHC’s programming and Country Business Plan delivery. Evidence from FCDO’s “best buys” highlights that politically informed development is highly cost-effective, often amplifying the impact of other interventions, even those with mixed or low evidence. Experience from Output 5 also shows this work is most effective when delivered internally, given the need for a nuanced understanding of evolving BHC priorities.

Recommendation
BHC Nairobi should (as part of its annual/multi-year planning cycles) agree on a strategy and scope for sub-national engagement, within the limits of available resources, to help maintain influence in key devolution processes and sectors, that are essential to achieving the objectives of the Country Business Plan and the UK - Kenya Strategic Partnership (2025 - 2030), and to maintain momentum on priority outputs from KDP. Action by: Democracy, Governance and Political Team – BHC Nairobi.

How this review was conducted
This review was carried out by the FCDO KDP team, comprising the Programme Responsible Officer (PRO), Regional Advisers, and Programme Managers. It draws primarily on partner reporting, beneficiary feedback gathered during field visits, and insights from stakeholder engagements.

Actions following approval of this report
Upon approval, the programme team will proceed to:
- Finalise the ongoing audit of the ACT-led component and settle any outstanding liabilities. Recover any funds owed to FCDO, where applicable, as recommended by the audit.
- Complete the disposal of any remaining programme assets, in line with FCDO asset disposal procedures (an asset disposal submission, with recommendations on how to dispose of programme assets has been agreed)
- Share the delivery and technical lessons internally [for example with the BHC Nairobi Programme Board] to support their application in new FCDO programmes and Country Business Plan delivery.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£38,500,000	£10,400,000
Timeframe	5 years, 3 months	5 years, 6 months
Outcomes	Original outcome statement: / More effective, open and accountable county governments for improved service delivery / Target was open-ended, to be defined iteratively during implementation.	Final outcome statements: / More effective, open and accountable County Governments / County Governments improve service delivery and reduce poverty / Indicators changed during the programme to enhance measurability but maintained a focus on demonstrating greater citizen participation and strengthened county capacity.

Overall assessment of programme outcomes, sustainability and VfM [1/2 – 1 page]

Outcome 1: More effective, open and accountable County Governments
Indicator	Target	Performance
1.1 Number of new County Government initiatives in response to CSO accountability actions by sector	4 new initiatives across the sectors	Exceeded expectation – numerous initiatives delivered in 4 sectors / Health[10] (health facility infrastructure improvements and longer operating hours, medical staff deployments, availability of essential drugs) / Agriculture & Livestock[11] (provision of agricultural feeds and inputs, and improved extension services) / Water & Climate change[12] (improved access to water, rehabilitation & upgrading of water sources) / Trade & Markets[13] (improved access to, and expansion of local markets)
1.2 Number of instances of strengthened policies, systems and processes for national and county governments which address bottlenecks to service delivery.	a) At least 4 significant results (from list agreed in logframe) that evidence improvement in processes at county and national level from KDP interventions	Partially met expectation / Improvements in process by county technical committees & members of county assembly in 6 counties / Implementation of reform initiatives in at least 2 counties to increase own source revenue (adoption and use of county revenue administration manuals, and other recommendations from county revenue potential assessments). / Significant improvements in critical public financial management and human resource systems.
	b) At least 4 significant instances of progress on policy & legislation (list agreed in logframe) from KDP’s knowledge and analytical products.	Met expectation / Delineation of county and national government functions gazetted / National policy on devolution revised / Gross County Product report informing the fourth revenue allocation formula / County Public Participation Guidelines reviewed to institutionalise citizen engagement
Outcome 2: County Governments improve service delivery and reduce poverty
2.1 Instances of new socio-economic opportunities linked to KDP provided by the County Government for the community.	5 instances of new socio-economic opportunities	Could not be measured due to data limitations – there was no clear definition of ‘socio-economic’ opportunities in the results framework.
2.2 Instances of positive change in service delivery by counties across various sectors as a result of KDP interventions	5 stories of positive change	Could not be measured due to data limitations – it was not possible to verify reported change stories.
[10] Numerous small-scale initiatives in Kiambu, Kisumu, Kilifi, Baringo, Mombasa, Siaya, Kakamega and Isiolo Counties
[11] Numerous small-scale initiatives in Kisumu, Nyamira and West Pokot Counties
[12] Numerous small-scale initiatives in Kiambu, Kisumu, Baringo and Bungoma Counties
[13] 2 initiatives in Bungoma

Outcome 1 aimed to demonstrate improved openness, accountability, and effectiveness in target county governments. The initiatives reported under outcome 1.1 show increased capacity among county-based civil society networks, including effective use of citizen engagement tools such as community scorecards, community contracting, and Project Management Committees. These, combined with more evidence-based engagement with county governments by CSO networks, led to the delivery of several projects and created opportunities for citizens to express their needs and priorities and influence key county and national level policies.

At the time of the PCR, there was limited data showing that this increased capacity would be sustained. Nonetheless, valuable insights have emerged from a Kenya demand-side study on what works[14] or not[15] to improve citizen-focused service delivery, which can inform future governance and sectoral programmes. Additionally, the growing use of social media and mobile platforms is creating new opportunities for citizens to engage county governments on service delivery issues.
[14] Synthesis and dissemination of simplified information, capacity building of communities, community dialogues, use of social media, demonstrations, roundtables with county governments, collective bargaining agreements, presence of strong and active CSOs in a county
[15] One-off mobilisation campaigns, lack of follow-up mechanisms, heavily technical communication, use of petitions

Under indicator 1.2(a), KDP contributed to several improvements in county government processes:
1. Multiple manuals were developed to guide county operations, including county assemblies procedures and processes manuals, an induction guide for Governors and Deputy Governors (used post-2022 elections), and a manual on impeachment procedure). Other key resources included guidance on establishing and operationalising Intergovernmental Sector Working Groups and a County Revenue Administration Operations Manual. While several of these tools have been used, there was limited data at the time of the PCR to confirm a causal link to improved county-level performance.
2. County Own Source Revenue (OSR) processes improved, informed by recommendations from the World Bank’s KADP OSR Potential Report. Four of the five counties receiving KDP technical assistance recorded revenue growth.
3. Significant reforms were made in Human Resource and Public Financial Management. From July 2024, all MDAs began transitioning to accrual accounting and rolling out Electronic Government Procurement (E-GP), improving transparency and efficiency. Additionally, 27 counties eliminated manual payroll systems, likely improving wage bill management. Progress was also made toward implementing a Treasury Single Account, with the National Treasury aiming to onboard counties by 2026.

The milestones not met include (i) the adoption and use of the KDP-supported communications strategy by the State Department for Devolution (ii) evidence of adoption and use of KDP-supported manual for establishment and operationalisation of at least 3 inter-governmental relations sector forums (platforms where the two levels of government consult and make decisions to harmonise their approaches to mutually important sectoral issues).

Under indicator 1.2(b), KDP contributed to progress on several key policy and regulatory frameworks supporting devolution. Notably, the delineation of county and national government functions was gazetted - a major milestone in the unbundling and transfer of devolved functions. This provides the legal and formal confirmation of the shift in responsibilities from the national government to county governments across 500 functions, in a way that’s transparent, binding and enforceable. It has provided clarity and the legal authority for counties to fully take charge of the transferred functions. The gazettement has triggered:

- Stakeholder sensitisation on the gazetted functions, led by the Intergovernmental Relations Technical Committee (IGRTC)
- Budget rationalisation to ensure resources follow functions continues. For example, counties are now set to receive KES 415 billion in the 2025/26 fiscal year, up from KES 387 billion the previous year. However, the Government of Kenya’s ability to further increase funding will depend on macroeconomic performance, debt levels, and improvements in transparency and accountability, which influence the availability of public resources.
- Policy and legislative review, with 94 pieces of legislation identified for repeal or amendment to remove barriers to effective devolution and harmonise the legal framework. Some of this was started by KDP (output 1)
- Restructuring of government institutions is anticipated to align with devolved functions. This will involve reorganising both national and county-level structures, potentially including the merging of departments and creation of new entities, and some national government agencies may become redundant.
The National Policy on Devolution was also revised with KDP support, to update the 2016 policy, incorporating lessons from the past decade and setting a roadmap for the next 5-10 years. While the policy is not yet in force pending Cabinet approval and gazettement, preparations for its rollout are underway. The State Department for Devolution has prioritised it in its 2023-2027 Strategic Plan, and the Government has taken several actions aligning with the policy’s objectives, which suggest growing political support - increasing the likelihood of its adoption and sustained use once formally approved.

The County Public Participation Guidelines were reviewed, updating the 2016 version, to broaden their scope and strengthen implementation. The updated framework now applies to all responsible authorities, including national government, commissions and independent offices, in addition to county governments and covers policy formulation, legislation, audits and other areas. Implementation mechanisms have been formalised, requiring each authority to develop specific guidelines and establishing oversight roles. Inclusivity has been expanded to mandate effective engagement of marginalised groups, and robust monitoring systems now include participation plans, feedback mechanisms and enforcement provisions.

Outcome 2 aimed to demonstrate that integrating supply-side interventions - such as improved county planning, budgeting, and human resource management - with demand-side approaches like citizen participation and accountability mechanisms could enhance service delivery in specific sectors, in selected counties. However, due to limitations in monitoring & evaluation, it was not possible to comprehensively measure or verify these results. Despite this, partner reports indicate that several county governments responded to citizen demands by initiating or improving services across various sectors, albeit on a limited scale.

Consistent with assumptions at the business case stage, implementation experience showed that demand-side social accountability initiatives faced challenges related to scalability and potentially sustainability – though it is too early to determine whether the observed changes will be sustained.

To note - KDP contributed 30% of the basket funding to the KADP trust fund and will therefore claim 30% of KADP’s outcome-level results in this PCR. All output-level results reported in this PCR relate to activities implemented by ACT and the Regional Advisers. The KADP outcome-level results are:
  1. Increase in county own source revenue
    1. Target – +10%. Achievement: As of June 2025, counties recorded a 62.6% increase nationwide compared to Kes 41.4 billion collected in the previous year . Four of five counties receiving targeted technical assistance from KDP – including Taita Taveta, Homa Bay, Kakamega and West Pokot - recorded revenue growth.
  2. Significant improvement in critical PFM and HR systems.
    1. Target – Met. Metric is ‘exceeded, met, partially met’ based on the work plan for IFIMS and HRIS improvements. Achievement: Met.
  3. The extent of county uptake of enhanced participatory approaches (participatory budgeting, citizen project management committees, Social Risk Management, and Grievance Redress Mechanisms).
    1. Target – 40 counties. Achievement: 45 counties using them at varying levels.
  4. Number of KADP initiatives/interventions that have gone to scale (e.g., adopted at both levels of government).
    1. Target – 7. Achieved: 8[16]
      [16] enhancements to the Kenya Integrated Financial Management Information System (IFMIS), Human Resource Information System (HRIS), Gross County Product Report (GCP), Own Source Revenue enhancements, Social Risk Management tools, roll-out of Project Management Committees (PMCs), Treasury Single Account, Accrual Accounting

The scale of expected results was adjusted annually based on available resources and shifting political contexts in Kenya and the UK. There is limited evidence that the intended outcomes were achieved, primarily due to a shorter-than-ideal implementation period and gaps in technical and MEL capacity. Numerous attempts to evidence outcome-level results beyond partner reporting have been unsuccessful. Progress was made in improving the policy and legislative environment for devolution, but experience confirmed a key assumption: that building systems, embedding reforms, and enabling counties to sustainably deliver services requires long-term, patient engagement.

Value for Money and sustainability
The combination of outputs proposed during KDP’s design had strong potential to contribute to meaningful outcomes. However, by the end of the programme, there was limited evidence that these outcomes (and therefore Value for Money) were achieved or would be sustained. There is mixed evidence across the outputs, for example:
- Policy and legislative support for inter-governmental relations: KDP helped draft bills, regulations, strategies, and manuals - many of which were initiated by the State Department for Devolution (SDD). While these requests reflected SDD’s intent and policy direction, meaningful change depends on legislative approval, implementation, and institutional uptake. Drafting is a critical first step, but by programme close, it was too early to verify whether these documents were being used in practice.
- County revenue improvement: Support to counties such as Homa Bay and Uasin Gishu showed early signs of sustainability. Anecdotal evidence suggested that revenue administration manuals, combined with tailored mentoring and coaching, contributed to improved practices in revenue collection.
- Blue economy MEL system: KDP’s support to the Lake Region Economic Bloc Multi-Agency Taskforce led to the development and implementation of an e-MEL system. Early signs of use and sustainability were evident - projects were being tracked on the system, host institutions had deployed staff to operate the system, and the Kenya Maritime Authority had allocated annual budgets for its maintenance.
- Citizen engagement and service delivery: Under Output 3, KDP supported county civil society organisations to mobilise citizens in demanding better services. While the physical projects (e.g. rehabilitated water pans, improved markets) are likely to be sustained, it was unclear whether civil society and citizen capacity had strengthened enough to continue advocacy efforts independently beyond KDP funding.
Some implementation approaches improved the likelihood of sustaining outcomes, for example, support tailored to different counties’ needs (for example on Own Source Revenue), and locally led initiatives fostered relevance and ownership. However, the implementation of the policy and legislative reforms started by KDP, by county governments will depend heavily on political will and Kenya’s fiscal capacity. Continued engagement and influencing by BHC and other stakeholders in the devolution sector will be essential to maintain momentum and ensure reforms are institutionalised and translated into measurable development outcomes.

Overall, KDP faced significant delivery challenges that affected its Value for Money. Activities were spread too thinly across geographic and thematic areas and were implemented discontinuously in response to short-term requests (by Government and other stakeholders). This limited KDP’s ability to achieve a critical mass of outputs necessary for systemic change. Additionally, gaps in technical and strategic leadership - which could have been mitigated through a stronger Monitoring, Evaluation, and Learning (MEL) function and genuinely adaptive management - further affected delivery. For instance, annual work planning and choice of interventions, revisions of logframe milestones and indicators, and development of Value for Money metrics could have been better aligned with testing the theory of change.

While there was an effort to revise the Theory of change in 2022, the process could have been more robust and evidence driven. These issues, compounded by fluctuations in the availability and timing of UK Overseas Development Assistance (ODA), meant that KDP delivered less Value for Money than it had potential to. Over the life of the programme, FCDO experienced periods of reduced technical and programme management capacity. Maintaining and strengthening this capacity consistently could have provided greater scope to anticipate and mitigate these risks.

An end-line political economy analysis completed in March 2025 by KDP found that the core challenge facing devolution in Kenya is not primarily funding, but poor accountability, corruption, and resource wastage. Despite investments, service delivery is constrained by weak oversight, limited transparency, and resistance to reforms by elites.

Taken together, these factors, BHC Nairobi decided that future engagement will be channelled through sectoral programming and sub‑national approaches, the network of regional advisers, and targeted engagement. BHC Nairobi’s governance programming will, instead, focus on strengthening accountability institutions by:
- Strengthening legal & policy frameworks and processes to tackle corruption & illicit finance
- Improving governance & integrity of electoral processes & practices (at national and county level)
- Enhancing citizens’ capacity for issue-based engagement and holding power to account

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]

KDP was designed to address key challenges facing devolution in Kenya, including weak intergovernmental coordination, limited county capacity for revenue generation and economic development, inadequate citizen engagement in service delivery, and underutilisation of evidence, digital tools, and learning in public sector reform.

The original theory of change envisioned improved service delivery through empowered citizens, working with capable county governments - those with sound plans, skilled personnel, adequate financing, and clear national policy direction. Strengthening regional economic blocs was intended to help counties with shared characteristics collaborate under harmonised systems, especially in key sectors, to deliver services at scale and create socio-economic opportunities that reduce poverty.

From mid-2021, as Kenya entered the year leading up to the 2022 general election, KDP adopted a phased approach - pre- and post-election. In the pre-election phase, the programme focused on consolidating gains with outgoing county governments. This included finalising policies, delivering against county strategies, supporting effective transitions led by national and county civil servants, and preparing for the induction of new county administrations.

Post-election, while the theory of change remained broadly aligned with the original business case, the programme’s ambition was revised down in 2022 due to reduced budgets (which also led to a change in the delivery model, from a consortium of over 7 partners led by ACT, to one downstream partner – PWC), shifting UK priorities, and the evolving political context under the new Kenya Kwanza administration. The five original outputs were retained, but with scaled-down contributions under each, resulting in a reduced pathway to outcomes.

The original theory of change was amended in 2022/2023, with the second outcome revised from “improved effectiveness and efficiency of service delivery” to “county governments grow socio-economically and improve service delivery.” This adjustment led to changes in Output 2 and its sub-outputs, shifting the focus from policy, planning, budget execution, and staff performance to more targeted support for economic development and public expenditure management. Key areas included the blue economy, county revenue enhancement, trade and investment, and strengthening county data and statistics. These changes aligned with evolving UK and Kenyan priorities around economic growth and mutual prosperity.
C: Detailed Output Assessment

Output Number and Title	Output 1 - Improved inter-governmental relations and coordination at national and sub-national level to support the devolution sector
Output Score	A
Impact weighting (%)	10%	Impact weighting revised since last AR?	Yes, reduced by 20%

Output Indicator	Final Logframe Target[17]	Final Result Achieved [18]
1. No and type of initiatives implemented to strengthen mechanisms for coordination, cooperation and consultation between the national and county government	A) Three[19] policy and legislative reform initiatives completed to progress the process of unbundling and transfer of devolved functions: / B) Five[20] policy and legislative reform initiatives completed to improve legislative systems and processes for devolution: / C) Revised policy on devolved system of government finalised	A) Met expectation: / A draft Bill on the Performance of Concurrent Functions developed / Draft Intergovernmental Relations [Transfer of Functions, Powers and Competencies] Regulations developed / Manual for establishment and operationalisation of Inter-Governmental Relations (IGR) sector forums developed, published & disseminated. / B) Met expectation: / Model County Assemblies Committee Manual, 2nd Edition developed, published and disseminated / Model County Assemblies Procedure and Processes Manual, 2nd Edition developed and adopted / 2nd Edition of the Guide to the Legislative Process developed and adopted / Impeachment of County Governors and Deputy Governors: A Digest of the Law and Practice developed and adopted by the Senate / Impeachment of County Governors and Deputy Governors: An Easy-to-Use Manual on the Procedures and Rules developed Committee manual developed and adopted by the Senate / C) Met expectation / Revised policy completed but not yet approved by cabinet for implementation.
2. No of initiatives to establish/strengthen mechanisms for coordination, cooperation and consultation between county governments	A) One initiative - SEKEB Blueprint and Investment Plan developed, finalised and launched.	A) Met expectation / Plan developed and published, with anecdotal evidence of its use.
[17] No end of programme targets are provided since milestones and targets were set annually.
[18] Scoring: - Moderately not met - drafted/completed - Met - handed over to GoK - Moderately exceeded - adopted - Substantially exceeded – implemented/in use
[19] Initiatives described in logframe
[20] Initiatives described in logframe

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

  - Through Output 1, KDP sought to advance devolution by facilitating the development of legislative and policy frameworks to improve intergovernmental relations, and coordination between the national and county governments. It also worked with Regional Economic Blocs to develop joint strategies on trade, investment, services, and natural resources. This work aimed to address key challenges: underfunding of devolved functions, continued national control over county-level responsibilities, and ineffective intergovernmental institutions with overlapping mandates. Completing the unbundling, costing, and transfer of functions was critical to improving service delivery at the county level.
Indicator 1.1 - A) Policy and legislative reform initiatives to progress the unbundling and transfer of devolved functions (Met expectation)
The State Department for Devolution (SDD) requested support to draft a Bill on the Performance of Concurrent Functions. This is a proposed law to clarify and regulate how national and county governments jointly perform functions that are assigned to both levels of government. Positively, while requesting support signals SDD’s intent and gives overall policy direction, real change will happen when the bill is passed in to law, regulations are developed to implement the law and institutions operationalised, to translate into tangible improvements in service delivery.

KDP also funded the development of Intergovernmental Relations [Transfer of Functions, Powers and Competencies] Regulations. These are designed to operationalise the legal provisions on the transfer of functions. While the regulations do not require parliamentary debate, they must be approved by the Cabinet Secretary and Gazetted as subsidiary legislation to become legally binding and enforceable – which had not happened by the end of KDP.

Finally, a manual for establishing Intergovernmental Relations (IGR) sector forums was published and disseminated. It offers a structured approach to sector-specific collaboration. Although the manual formalises existing practices, its uptake could not be verified by the end of KDP. Some key indicators of its uptake, e.g. submission of annual sector reports to the National and County Governments Coordinating Summit are due beyond the timing of this PCR.

Nonetheless, that the State Department for Devolution (SDD) proactively requested support for these initiatives, and participated in their development, is a positive signal. It reflects growing ownership and commitment to institutional reform, which is essential for long-term sustainability. However, until they are implemented and operationalised, their impact remains unrealised.

Indicator 1.1 B) Policy and legislative reform initiatives to improve legislative systems and processes. (Met expectation):

KDP supported the development of several legislative and procedural tools aimed at strengthening county assemblies and national legislative processes. The Model County Assemblies Committee Manual (2nd Edition) provides a standard framework for establishing and managing committees within county assemblies. The Model County Assemblies Procedure and Processes Manual (2nd Edition) standardises key operations such as member swearing-in, Speaker elections, plenary conduct, voting, and petition handling. While there is limited formal evidence of uptake, both manuals were developed and published by the Society of Clerks at the Table in Kenyan County Legislatures (SOCATT Kenya) with KDP’s support and are publicly available. Some counties appear to follow practices aligned with the manuals, suggesting possible influence. Importantly, SOCATT and the County Assemblies Forum (CAF) have taken ownership, increasing the likelihood of sustained use through their ongoing role in training and coordination of county assemblies.

The Guide to the Legislative Process (2nd Edition) was also developed to help ministries follow correct procedures when drafting laws and policies. Its success depends on whether ministries adopt it, train staff, and apply it in their daily work. However, by the end of the programme, it was too early to confirm adoption.

Two impeachment resources were also finalised: a Digest of the Law and Practice and an Easy-to-Use Manual for county governors and deputy governors. These were developed to address long-standing gaps in how impeachment proceedings are conducted in Kenya. These resources aim to improve fairness, transparency, and consistency by providing clear legal guidance and step-by-step procedures for county assemblies and the Senate. They were finalised, launched, and disseminated in March 2025, with input from legal practitioners and key institutions including the Senate, CAF, CoG, SOCATT, and the Office of the Attorney General. It is likely they have informed recent impeachment proceedings.

Overall, all products were successfully developed and disseminated, and there is some likelihood of their implementation. Strong institutional ownership suggests a high potential for sustainability and gradual uptake.

Indicator 1.1 (C) Revised policy on devolved system of government finalised. [Moderately did not meet expectations]
The Revised Draft Policy on the Devolved System of Government was developed to update Kenya’s 2016 Devolution Policy, drawing on lessons from the past decade and setting a roadmap for the next 5-10 years. Though the review is complete, the policy is not yet in force, pending Cabinet approval and gazettement. However, preparations for its rollout are underway. The State Department for Devolution (SDD) has prioritised the policy in its Strategic Plan (2023 - 2027). President Ruto’s support for the process of transfer of functions aligns with the policy’s goals, signalling strong political and institutional support and increasing the likelihood of sustained implementation.

Indicator 1.2 - SEKEB Blueprint and Investment Plan developed, finalised and launched.
The South Eastern Kenya Economic Bloc (SEKEB) Blueprint and Investment Plan 2025–2035 has been finalised, launched, and officially adopted by the counties of Machakos, Makueni, and Kitui. The 3 governors committed to begin implementing the first phase of the plan within the next three years. There is some evidence that the Blueprint is influencing county-level decisions. For example, the counties have agreed to jointly invest in specialised health services - Kitui will establish a renal centre, Machakos a cancer centre, and Makueni a trauma centre. They also plan to harmonise tariffs and business licences to improve the ease of doing business across the region. These actions show early signs of political commitment and early practical steps toward implementation

In its earlier years, KDP supported the development of frameworks to strengthen the role of Regional Economic Blocs (REBs) in coordinating development. Although a draft national policy was formulated, it remains unapproved and ungazetted due to political and national security concerns. The absence of formal policy and legislation has left REBs in an informal state, limiting their legitimacy and operational clarity. Without legal recognition, REBs cannot access public funding, and their financial operations remain unaudited, raising concerns about transparency and sustainability. Their continued existence currently depends on the goodwill of governors, pending Cabinet approval and legislation to formalise their funding and structure.

Overall, the programme made commendable progress in supporting the development of several important policy and legislative reform products which if implemented, could significantly improve intergovernmental coordination, legislative processes, and regional economic planning. However, the programme spread its efforts across too many reform areas, which limited its ability to follow through on each initiative in depth. While there is early evidence of political commitment - such as the adoption of the SEKEB Blueprint by county governors and the inclusion of the revised Devolution Policy in national planning documents - most reforms were still at the early stages of the policy cycle by the end of the programme. In many cases, it was too soon to determine whether these products would be formally adopted, implemented, or lead to tangible improvements in governance or service delivery.

Lessons learned through this output, and recommendations for future programming
Political dynamics have been and will likely continue to be the main determinants of progress in successfully implementing devolution. While the programme consistently delivered technical outputs on schedule, political decision-making was delayed. For example, although the 12 sector reports to inform the delineation, unbundling, costing, and transfer of functions were completed early, finalisation through the Summit, Cabinet approval, and gazettement was prolonged and dependent on political goodwill. Recentralisation tendencies in key devolved sectors such as agriculture, health, and housing will likely undermine devolved governance. As well, the Devolution Policy and the Policy on Regional Economic Blocs - were not approved at the political level by KDP’s end date (June 2025). Future interventions should embed Political Economy Analysis (PEA) during design, and think and work politically, to determine potential blockages, enhance traction, ensure timely policy adoption, or determine what should not be pursued altogether.

Balancing responsiveness with strategic focus: The programme frequently responded to ad hoc requests from government departments, which, while fostering goodwill and collaboration, diverted attention and resources from its core objectives. This high level of responsiveness led to a dispersion of efforts, with the programme engaging in a wide array of activities across multiple areas, often at the expense of depth and strategic focus. A more concentrated approach - focusing on fewer, high-impact areas - would have significantly enhanced programme effectiveness.

That said, the programme’s flexibility also yielded important benefits, such as increased access to and influence with key government stakeholders, both for the Kenya Devolution Programme (KDP) and the British High Commission (BHC). Future programmes should aim to strike a balance between responsiveness and strategic focus, ensuring that depth is not compromised by breadth.

Evolving capacity and shifting demand by GoK: Over time – and with input from development partners, state institutions have significantly strengthened their capacity in devolution, reducing the need for external technical assistance. National agencies are now better positioned to support counties directly. Consequently, demand for support from national agencies shifted to funding for travel and convening meetings, rather than technical assistance. While the programme adhered to the “Harmonised Donor Principles on GoK Allowances[21]”, this mismatch between government needs/expectations and programme resources posed delivery challenges. Future programmes should anticipate changes in what support is needed - e.g., less technical assistance, more facilitation or coordination, adapt their approach to match the new realities - supporting areas where they can make the most meaningful impact, and stay focused on value-added contributions - offering expertise, innovation, or strategic support that government institutions may not be able to provide on their own.
[21] These are a set of principles endorsed by the Kenya Development Partners’ Group – Heads of Cooperation in June 2024, aimed at guiding the use of development partner resources – they cover appropriate meeting venues, the application of per diem and daily subsistence allowances for GoK officials, salary top-ups, and the use of donor-funded vehicles. Their purpose is to promote accountability and transparency in public financial management, and to ensure the effective and efficient use of development assistance.

Recommendations
1. The programme provided valuable access to county and national officials, which supported broader British High Commission (BHC) engagements. These relationships should be sustained through a broader BHC Nairobi sub-national engagement strategy, which could be supported by county-based staff (Regional Advisers). BHC should agree a sub-national stakeholder engagement strategy, within an appropriate timeline, in line with available resources. Action: relevant internal teams.
2. While there are no current plans for a follow-on devolution programme, it would be beneficial for BHC Nairobi to maintain engagement with key processes and sectors within the devolution space that support the delivery of its sectoral and geographic priorities. The following areas present opportunities and should be further explored, and relevant options agreed upon, in line with the BHC Nairobi Country Business Plan (CBP), the UK - Kenya Strategic Partnership (SP, 2025 - 2030), and available resources:
- Advocating for a stronger and more empowered IGRTC that can effectively deliver its mandate.
- Influencing resource allocation to counties to ensure resources accompany the transfer of functions.
- Supporting legislative reforms to operationalise function transfers in sectors relevant to the CBP and SP.
- Promoting approval of the Regional Economic Blocs (REBs) Policy to enable county-level financing and enhance the sustainability of REBs, given their convening power to drive economies of scale in sub-national initiatives.
- Continuing BHC Nairobi’s membership in the steering committee of the World Bank’s Kenya Accountable Devolution Programme, which remains active until June 2027.
Action: Democracy, Governance and Political Team – BHC Nairobi

Output Number and Title	Output 2 - County governments effectively manage public finances, staff performance and county planning
Output Score	A
Impact weighting (%)	30%		Impact weighting revised since last AR?		No

Output Indicator		Final Logframe Target[22]		Final Result Achieved
1. No of initiatives to enhance county governments' generation and use of evidence in planning in the blue economy sector.		1) Baseline assessments of: / (a) the blue economy potential of 5 counties / (b) blue economy development potential of 6 inland basin areas / completed and disseminated. / 2. e-MERL system hosted in an institution, in use with operational support		1A) – Moderately exceeded expectations. Assessment and dissemination of findings complete with some evidence of uptake of recommendations. / 1B) Met expectations. / Survey undertaken and disseminated. / 2. Met expectations / System currently in use, hosted in an institutions with operational support in place.
2. No of initiatives to sustainably enhance county own source revenue.		2) / a) Evidence of implementation of Own Source Revenue (OSR) assessment findings in 3 counties / b) Operations manual for county revenue administration finalised.		2A) Moderately did not meet expectations / Evidence of implementation of OSR assessment findings in two out of three counties. / B) Moderately exceeded expectations / Operations manuals finalised and in use in Homabay and Uasin Gishu Counties.
3. Initiatives to strengthen the capacity of county investment authorities for trade and investment.		3) Development of County Investment Authority 5-year strategic plans for Kajiado & Kirinyaga counties.		3) Met Expectations / Strategic plans developed.
[22] No end of programme targets are provided since milestones and targets were set annually.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]

This output supported county governments in enhancing service delivery through strengthened long-term, medium-term, and annual development planning, improved budget execution, and human resource management. The support followed a two-pronged approach: strengthening planning units, and providing targeted sectoral support, implemented in two phases.
Phase One focused on technical assistance for developing 10-year sector plans, which informed 5-year County Integrated Development Plans (CIDPs) and Annual Development Plans (ADPs), as well as support to strengthen county functions in procurement, audit, and human resource performance management.
Phase Two aligned with the UK’s mutual prosperity agenda, pivoting to PFM, enhancing counties’ trade and investment capacity, as well as developing the blue economy and boosting OSR.

Indicator 2.11a/b: The Government of Kenya’s strategic development plans prioritise the blue economy as a growth area. However, more focus had been placed on the coastal blue economy rather than inland waters. Lake Region Counties and national government agencies with a blue economy mandate, formed the Lake Region Multi-Agency Technical Committee (MATC) to coordinate efforts around harnessing the economic potential of inland waters. KDP re-focussed towards this area during the post-election phase and primarily supported the MATC to generate the initial evidence and data, on Kenya’s inland blue economy potential. This would support counties to increase their revenues through better governance of the blue economy resources within their jurisdictions.

KDP commissioned a baseline survey (on the blue economy potential of 5 counties and 6 inland water basins) through the Africa Centre for Health Environment and Water Services (ACHEWS), supported by FCDO’s East Africa Research and Innovation Hub. The surveys found that: counties face several challenges that hinder broader blue economy development: inadequate infrastructure and technology, weak policy and regulatory frameworks, limited financial resources, and low awareness among officials and communities. These gaps result in unsustainable resource use, poor investment confidence, and limited stakeholder participation. While the blue economy includes diverse sectors beyond fisheries - such as marine transport, biotechnology, and renewable energy - these remain underexplored due to lack of knowledge and strategic planning. Addressing these challenges is essential to unlock the full potential of the Blue Economy, promote inclusive growth, and build resilience across the counties.

Findings were disseminated through peer learning, county-level engagements, and regional summits, including the Mombasa Blue Economy Innovation Summit and the LREB Summit. Two policy briefs were produced: one on institutionalising blue economy governance in counties, and another on collaborative frameworks for the Lake Victoria region. From its findings:
Budget and revenue projections were discussed with counties. To note, these are commitments made by county governments. It was too soon by the end of the programme, to know whether these will be implemented to realise results.

Two knowledge products were produced and disseminated, a policy brief on "Institutionalising Blue Economy Governance in Counties" and another on "Collaborative Framework for Blue Economy in the Lake Victoria Region."

Indicator 2.1.2: KDP also developed an electronic monitoring, evaluation and learning system (e-MEL) to support the Lake Region Economic Bloc (LREB) harness the blue economy potential in the region. It will provide data for better planning, budgeting, and enhancing blue economy revenue sources besides providing valuable insights to potential investors. Already, 258 projects worth Kes 8.6 billion (approx. £53m) are uploaded and being tracked on the system. Implemented by a downstream technical partner commissioned in late 2024 hosted by a relevant government institution. . KMA has committed budget and personnel to maintain the system and ensure accessibility. It will provide M&E data on blue economy projects and programmes within the region, the progress in their implementation, and on results.

While there is little evidence yet of the above initiatives enhancing county governments' generation and use of evidence in planning in the blue economy sector, there are early signs of political commitment (e.g. above commitments by Busia, Migori and Homa Bat Counties to implement blue economy projects, and setting aside of budgets by the KMA to resource the functioning of the e-MEL system).

Indicator 2.2: County governments in Kenya continue to rely heavily on national transfers, generating only 8%-12% of their income locally - well below the expected 50%. A World Bank-led OSR Potential and Tax Gap Analysis, co-funded by FCDO, estimated that counties could raise up to KES 260.6 billion if they fully leveraged their revenue streams.

In its first year, the programme supported Elgeyo Marakwet, Isiolo, Mandera, and Marsabit counties with technical assistance on OSR.

Indicator 2.2(a) indicator met expectations as there was evidence of implementation of Own Source Revenue (OSR) assessment findings in 2 out of 3 counties in the last review year. Mombasa County Government got alternative funding to implement assessment findings outside of KDP. The logframe should have been amended to reflect this change. On indicator 2.2 (b) the county operations manual for county revenue administration was finalised, and there is early evidence of its use in Homa Bay and Uasin Gishu counties .

Between 2023 to 2025, an OSR advisor provided technical advice and mentorship to Uasin Gishu, Homabay, and Mombasa counties. This addressed gap identified in the OSR assessments and provided support to implement policy reforms and recommendations. This TA contributed to some achievements including:
Uasin Gishu and Homa Bay recorded significant OSR improvements during the period. During a field monitoring visit to Homabay revenue administrators shared examples of how they had used the manuals developed.
The results above demonstrate well the impact of continuous work with a county over a longer duration.

Indicator 2.3: Counties have faced challenges in attracting private investment. To address this, many have established County Investment Corporations (CICs) to act as corporate entities for trade facilitation and investment promotion.
They are primed as leads in investment projects and as investment promotion agencies. Through this output, institutional strengthening assessments were conducted in CICs of three counties’ (Kisumu, Kirinyaga and Kajiado) to inform follow-on activities and develop strategic plans for Kajiado County Investment Authority and Kirinyaga County Development Authority. The assessment of Kisumu Lake Front Development Corporation (KLDC) and Kirinyaga County Investment Authority (KCIA) focussed on their Policy and legal frameworks standpoint, their performance in line with their mandate and challenges hindering their performance and ability to attract investments. A deep dive desk analysis of six County Investment Corporations, one from each County Economic Bloc was undertaken on their organisational capacities and performance.

By the end of the programme, it was too early to demonstrate evidence of implementation of the recommendations of the strategies as they had just been completed. Besides Kirinyaga County acquiring the mandate to run the County Aggregation Industrial Park, there was no evidence provided on investment attraction by any of the County Investments Corporations.

Lessons learned through this output, and recommendations for future programming
Navigating political transitions and leadership changes: The 2022 county leadership transition disrupted programme momentum, as incoming officials required time to understand ongoing activities and reassess priorities. This led to delays in decision-making and implementation. To mitigate this, the programme conducted structured onboarding sessions and aligned activities with new leadership priorities. Anticipating election-related disruptions, the workplan was adjusted to focus on quick wins during the pre-election and transition phases. Implementing partners prioritised counties demonstrating good practice, supporting them to finalize policies and document lessons for wider uptake across the 47 counties.

Tailored engagement and county ownership are critical: Understanding each county’s unique context, capacity, and priorities was key to programme success. Early engagement and co-creation of activities fostered relevance, ownership, and sustainability. Counties like Migori and Uasin Gishu, which actively participated and contributed resources, demonstrated stronger commitment. This experience also validated the intended “poverty vs progressiveness” targeting approach in the business case (though not formally applied), showing that strategic resource allocation can enhance impact where counties are both in need and ready to engage.

Coordination between implementing partners: Improved alignment between ACT! and the World Bank-led KADP could have enhanced efficiency and reduced duplication, particularly in counties like Uasin Gishu and Homa Bay where both delivered seemingly similar Own Source Revenue activities. Although all results contributed to KDP’s overall objectives, the lack of clear coordination made it difficult to assess the distinct value of each partner’s contribution. However, this overlap may have been exacerbated during 2022–2023, when BHC reduced its financial engagement with the World Bank Trust Fund. Future programmes should establish robust collaboration frameworks, even in periods of reduced donor engagement.

Deepen county-level engagement through contextual understanding: Future programmes should allocate sufficient resources to understand the unique characteristics, capacities, and priorities of each county. In KDP, this was achieved through detailed pre-implementation assessments, which enabled tailored interventions and fostered stronger county ownership. Early and context-specific engagement ensures relevance, builds trust, and enhances the sustainability of programme outcomes. The role of the programme-funded regional advisers strongly came to bear in understanding county contexts and implementing relevant, tractable interventions under this output.

Ensure continuity and following electoral cycles: Starting KDP implementation just a year before the 2022 elections required a strategic shift toward short-term engagements with select counties, focusing on quick wins. However, many of these counties - such as Laikipia, Isiolo, and Kakamega - were not retained post-election, resulting in lost momentum. To maximise impact, future programmes should adopt an election cycle approach, launching soon after elections to allow sustained engagement with one set of county leadership. If not possible, even minimal continued support can preserve progress, build trust, and ensure long-term benefits.

Output Number and Title		Output 3 - Government and citizens collaborate effectively to address key problems in service delivery
Output Score		A
Impact weighting (%)		40%	Impact weighting revised since last AR?		Yes, up by 15%

Output Indicator	Final Logframe Target[23]			Final Result Achieved
Instances of effective application, by county CSOs networks, of social accountability and advocacy tools in planning, budgeting and for enhanced service delivery.	9 instances of effective application, by county CSOs networks, of social accountability and advocacy tools in planning, budgeting and for enhanced service delivery			Substantially exceeded expectations – over 15 instances in FY 24/25 / 3 instances where effective application of knowledge on county budget processes, and advocacy, contributed to allocation of budgets of over Kes 114,000,000[24] for priority projects and services by 4 county governments in FY 24/25. (Bungoma – Kes 50m, Kisumu – Kes 14m, Mombasa – Kes 50m); and better access to information on these projects. / A substantial number of instances across multiple counties leading to resource prioritisation and implementation acceleration 2 instances of effective community contracting contributed to timely completion of 6 water projects, and construction/enhancement of 2 dispensaries in Baringo County. / 3 instances where effective use of various forms of social accountability (including community score card, social audits and public expenditure tracking surveys) contributed to improvements in access to services in Isiolo, Kisumu and Mombasa (community scorecards & social audits led to health facility improvements) / 3 instances where effective advocacy contributed to improved transparency & management of own source revenue by county governments in Bungoma, Mombasa and Kisumu counties.
Level of enhanced institutional capacity, at county level for public participation.	Each of the 6 CSOs networks has developed/put in place at least 2 components of the recommendations of the organisational institutional capacity assessment.			Moderately did not meet expectations / All 6 CSOs networks have in place at least 2 components recommended by the organizational institutional capacity assessment. / Isiolo: Monitoring, evaluation, research and learning plan, Advocacy Plan[25] and Resource Mobilisation Plan[26] / Kisumu: Constitution reviewed, Advocacy and Resource Mobilisation Plans developed / Mombasa: Advocacy Plan, Resource Mobilisation Plan, and Website developed. Finance policy and Network Guidelines reviewed. / Baringo: Advocacy Plan, Resource Mobilisation Plan and Website developed / Bungoma: Advocacy Plan and Resource Mobilisation Plan developed. Constitution reviewed and MERL Plan advanced. / Kiambu: Advocacy Plan and Resource Mobilisation plan developed. Constitution finalised, Finance policy, procurement policy and Strategic Plan developed.
Effective CSO engagement in national devolution issues	Effective engagement in 5 national level devolution issues (effectiveness measured by level of traction). / (1) Transfer of pending constitutional functions to county governments / (2) Transfer of equitable share of revenue collected nationally to county government / (3) Expenditure on bursary for secondary and higher education by county government / (4) Division of revenue between the two levels of government / (5) Data driven advocacy for devolution			Met expectations (although evidence of 3 of 5 agreed issues engaged in effectively as a direct output of KDP interventions level of traction deemed to be an overachievement, so overall score is met –) / Advocacy for transfer of functions: Played a key role in promoting the transfer of functions to county governments through national media coverage, engagement with IGRTC, and initiating plans for public interest litigation. / Contributed to preventing reduced budgetary allocation to county governments through a Senate memorandum endorsed by over 3,000 citizens / Promoted Constitutional Compliance in Education: Advocated for counties to uphold education mandates through litigation plans, media outreach, and collaboration with the Controller of Budget.
[23] No end of programme targets are provided since milestones and targets were set annually.
[24] Approx £712,500
[25] outlines the strategic focus areas for the network in strengthening county policies, influencing county development plans and budgets for the benefits of the local communities and enhancing accountability in the county governance and service delivery processes
[26] identifies the resources required by the network to undertake its objects, the potential source of the resources, both internal and externa and the approaches the network will apply in sourcing for these resources

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]
This output aimed to enhance citizen engagement and public participation across policymaking, planning, budgeting, and service delivery. It supported counties in operationalizing public participation mechanisms, citizen engagement policies, and access to information frameworks. This included helping counties develop or implement enabling legislation and structures such as County Budget and Economic Forums, Access to Information Offices, and Sector Working Groups. The later phase of the programme involved partnerships with county CSO networks in 6 counties and establishment of national-level advocacy through the Kenya Devolution CSOs’ Working Group.

Output Indicator 3.1 - Through the application of social accountability approaches, over 13 projects across six counties were successfully influenced for budgetary allocation, while 11 of these were fast-tracked for implementation within approved budgets. In Baringo County, lessons from piloting community contracting contributed to the timely and high-quality completion of 4 additional water projects. The use of advocacy tools such as the Community Score Card led to notable improvements in health service delivery at 2 health centres in Kisumu, 4 in Mombasa, and 1 in Isiolo. Additionally, 15 projects were influenced to enhance access to budgetary information. Advocacy efforts on OSR transparency in Bungoma and Mombasa counties also contributed to increased OSR.

Output Indicator 3.2 - In its early phase, the program strengthened county-level public participation by supporting CSO inclusion in planning processes. Counties like Isiolo, Kisumu, Mandera, Mombasa, and Tharaka Nithi established inclusive Sector Working Groups, while CSO networks in Baringo, Bungoma, Kisumu, and Mombasa advocated for participation in Governor’s roundtables - some created through KDP support.

In the final year, the program shifted focus to strengthening the internal capacity of six partner CSO networks in Baringo, Bungoma, Isiolo, Kiambu, Kisumu, and Mombasa. Each underwent a comprehensive organisational assessment to identify strengths and capacity gaps. With technical support, they developed tailored capacity improvement plans and prioritized actions based on available resources.
Several counties achieved similar milestones:
- Isiolo, Bungoma, and Kiambu developed Monitoring, Evaluation, Research, and Learning (MERL) plans, advocacy, and resource mobilization strategies. Bungoma and Kiambu also had their constitutions reviewed, with Kiambu additionally developing a strategic plan.
- Kisumu and Mombasa focused on advocacy and resource mobilization plans, with Kisumu reviewing its constitution and Mombasa enhancing its finance policy, network guidelines, and launching a website.
- Baringo also developed a website and created advocacy and resource mobilization plans.

Notably KDP trained CSO networks on collecting, analysing and using data and evidence for advocacy with Governments – which improved the quality and success of engagements with Governments. If put in to use, the products above will create stronger, more structured, and better-equipped CSO networks across the six counties. By the end of the programme, it was too early to tell if this was the case.
.
Output Indicator 3.3: In July 2023, KDP supported the formation and capacity building of the Kenya Devolution CSOs Working Group (KDCWG), a national umbrella for civil society networks focused on devolution. Within 18 months, KDCWG gained national recognition, joining the State Department for Devolution’s Sector Working Group as its sole non-state member. It published the widely covered Devolution@10 report, advocated for full transfer of functions to counties, and pushed for timely fund disbursement.

KDCWG supported evidence‑based advocacy and policy engagement., aligned with the Controller of Budget’s findings, and submitted key legislative memorandums. It influenced anti-corruption discourse, built CSO capacity, and partnered with County Economic Blocs on inclusive development. KDCWG, being a nascent formation, while it did not engage in 5 issues as per the logframe in the review period, engaged and influenced the 3 issues significantly and has elevated civil society’s role in Kenya’s devolution. Performance on this indicator is assessed as having met expectations.
Overall, the results from Output 3 demonstrated that empowering citizens to advocate for their own issues has the potential to be both impactful and cost-effective. While citizens are central to advocacy, CSOs play a vital role in linking them to decision-making spaces and mentoring them to influence governance processes. A key achievement of KDP was strengthening connections between CSOs and government actors at both county and national levels. These linkages enabled CSOs to access timely information and contribute meaningfully to planning and budgeting processes. In counties like Mombasa, Isiolo, and Kisumu, CSOs were integrated into Sector Working Groups and County Budget Forums, influencing the Third Generation CIDPs. Nationally, the Kenya Devolution CSOs Working Group was included in the Devolution Sector Working Group - marking a shift in government-CSO relations. These collaborations helped reposition CSOs as credible development partners, moving away from perceptions of them as underqualified or adversarial.
While projects under Output 3.1 show potential for sustainability, there was limited evidence of CSOs independently continuing work without KDP support - activities often paused during funding gaps. The long-term impact of community-based approaches on service delivery remains mixed (FCDO Best Buys). More effective models combine citizen empowerment with service delivery data and engage both government (supply) and citizens (demand). However, KDP did not strategically align Outputs 2 and 3 to test this approach in the same locations or sectors. Additionally, CSO networks were engaged for short cycles, limiting institutional strengthening and continuity. Future programmes should adopt longer engagement periods - ideally two years or more - to better test the theory of change.
Lessons learned through this output, and recommendations for future programming
KDP promoted continuous learning among CSOs through exchange visits, webinars, and learning events. These platforms enabled replication of successful tools like Governors’ roundtables and social media mobilization. A key achievement of KDP was strengthening linkages between CSOs and government actors at both county and national levels. These connections allowed CSOs to access timely information on development plans and influence decision-making processes directly. These collaborations allowed CSOs to maintain their independence while demonstrating professionalism and objectivity in governance processes. In addition to this, the use of data, evidence and improved analysis improved the quality of advocacy and engagement between CSOs and government actors, shifting perceptions of CSOs from adversaries or foreign-funded disruptors to legitimate development partners.

A major obstacle was the widespread demand for allowances by government officials, CSOs, and community members. Since KDP activities required collaboration with government agencies, their participation was often contingent on receiving per diems or other incentives. This expectation extended to some CSOs and citizens, complicating engagement efforts. The situation was exacerbated by other development programmes, which provided such allowances, making it difficult for KDP to maintain consistent participation. In some cases, planned activities had to be cancelled at the last minute due to scheduling conflicts with better-funded programmes. Full implementation of the harmonised donor principles for GoK allowances will help, in future programmes.

FCDO’s best buys show mixed evidence on the long-term impact of community-based approaches on service delivery. More holistic social accountability models - combining citizen empowerment with practical service delivery data and engaging both supply and demand sides - are more effective. KDP did not appear to strategically align Output 2 (supply) and Output 3 (demand) interventions to test this approach. Additionally, CSO networks were engaged for short cycles, limiting the institutional strengthening needed for sustained impact. Future programmes should adopt longer cycles (at least two years where possible) to allow meaningful citizen engagement in planning and oversight, and to test the theory of change more effectively.

Through this output, KDP enhanced equity, through improving the participation of citizens in governance. Future programmes should go further by intentionally targeting marginalised populations from the outset.

Output Number and Title		Output 4 - Research and evidence generation to inform public policy, facilitate peer learning and improved county service delivery
Output Score		B
Impact weighting (%)		10%	Impact weighting revised since last AR?		No

Output Indicator	Final Logframe Target[27]			Final Result Achieved
Evidence of utilisation of developed knowledge products for policy, strategy and programme development.	At least 10 knowledge products developed and disseminated from the four output areas (plus endline PEA and endline public perceptions survey).			Score B - Moderately not met[28] / A Political Economy Analysis (PEA) and an endline perception survey were completed, though full dissemination was not achieved. / Another 106 products - including videos, infographics, blogs, etc - were developed and shared. Some were submitted to the Maarifa Centre for publication.
[27] No end of programme targets are provided since milestones and targets were set annually.
[28] Scoring: Moderately not met - drafted/completed Met - disseminated Moderately exceeded - used Substantially exceeded - used significantly

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

This output delivered the programme’s monitoring, evaluation, results, and learning component, aimed at generating evidence to inform public policy, support peer learning, and improve county service delivery. In the final year, an endline perception survey was conducted, alongside a Political Economy Analysis (PEA) that explored why devolution has not achieved its full potential as envisioned in the 2010 Constitution, despite years of investment and reform efforts.

The Political Economy Analysis (PEA) concluded that while funding remains important, the deeper challenge facing devolution in Kenya lies in poor accountability, corruption, and inefficient use of public resources. Both national and county governments struggle with transparency in budget formulation and execution, which continues to constrain service delivery. Citizens often lack the tools and knowledge to hold duty bearers accountable. Limited civic education means many do not view the proper use of public resources and good service delivery as a right. Strengthening this connection can foster a sense of responsibility and encourage citizens to actively engage in governance processes. However, counties rarely allocate resources for civic education, leaving this critical function to donors.

In addition to internal governance challenges, stakeholder roles and mandates have continued to evolve creating implementation complexities for devolved functions Timing of inter‑governmental transfers has at times impacted service delivery planning, and there is growing involvement of the national government in devolved sectors such as health, agriculture, and housing. These trends suggest a heightened central coordination in selected sectors, which risks reversing gains made under the 2010 Constitution.

County assemblies, which are constitutionally mandated to oversee county executives, are also weakened by patronage politics, limiting their effectiveness. Strengthening the capacity of Members of County Assemblies (MCAs) and their committees is critical to restoring oversight and accountability. Overall, addressing the governance and institutional weaknesses - rather than focusing solely on funding - is key to unlocking the full potential of devolution and ensuring it delivers on its promise of improved service delivery and citizen participation.

From the end-line public perceptions survey - The end‑line survey indicated declining satisfaction with devolution and concerns about transparency and service delivery.

Perceptions of county government transparency also worsened. Only 15.9% of respondents believed county budgeting processes were transparent, down from 20% in 2022. While understanding of the budget-making process rose slightly (from 24% to 30.8%), it remains low. Just 18.8% agreed that counties publicize planning and budget documents, down from 22%, and only 29.8% felt services were delivered without favouritism.

Disillusionment with elected county officials is growing. 64.1% of respondents believed Governors and MCAs serve personal interests over the public good, and 60.2% disagreed that county governments genuinely care about citizens’ development needs. Reflecting this sentiment, 64% said they would not re-elect their current Governors or MCAs.

However, because both products were completed very close to the end of the programme, their dissemination and use were limited.

During the lifetime of the programme, a highlight for the output was the Devolution @10 Survey: A Citizens' Perspective   - The study reached over 2,200 respondents across the country through individual responses, KIIs, and FGDs. The survey examined the citizens’ perspectives on the relationships between the national government and county governments, the operationalization of devolution objectives, and the quality of delivery of devolved functions at the county level such as health, water, agriculture, and trade, among others. The survey also identified the gaps and challenges in each of the focus areas and provided recommendations which the CSO networks took up. The survey findings were disseminated to a wider audience compared to other knowledge products.

Learning and lessons sharing happened through peer reviews, accountability webinar series, devolution study groups and REBS peer-peer exchanges. This output also made a considerable contribution to organising validation workshops, side events for national conferences such as Afri-cities and the Devolution conference and support to development of knowledge products for other outputs. The review notes that most of these products were completed through outsourced TA. In the last year, KDP introduced social media segments dubbed devolution Wednesdays, where videos, blogs and newspaper articles were published to offer the public insights of devolved system of governance.

Output 4 was designed to be outward facing, aiming to generate research, evidence, and knowledge to inform the broader devolution sector. However, during implementation, this external focus appeared to come at the expense of internal Monitoring, Evaluation, and Learning (MEL). Internal MEL systems remained relatively weak and did not effectively guide programming decisions, or the prioritisation of workstreams based on their potential to achieve outcomes. Ideally, MEL should have played a central role in shaping implementation strategies. Measuring results remained a persistent challenge.

Lessons learned through this output, and recommendations for future programming
1. KDP produced a wide range of knowledge products, many with actionable recommendations to improve devolution and county service delivery. However, the emphasis on quantity may have compromised quality and relevance, with some findings duplicating known issues. Future programmes should focus on producing fewer, high-quality products with targeted dissemination to better influence stakeholder action. Evidence from PEAs could also have been used better, to directly support programme implementation and decision-making.
2. Although digital solutions became less prominent in later years, they remain a high-potential tool for citizen engagement and service delivery. Virtual CSO learning forums proved cost-effective and sustainable, and should be prioritised in future programming, especially given the growing role of digital platforms in shaping public discourse and increasing digital access.
3. Limited and delayed dissemination reduced the impact of some products – as some products were developed too close to the programme’s end. PEAs, for instance, could have informed broader BHC programming (in addition to KDP) but were either outdated or not widely shared. Future efforts should ensure timely dissemination. In its future sub-national engagement approach, BHC should also consider whether and how to disseminate relevant quality knowledge products and findings both externally and internally, through the network of regional advisers and other sector programmes.
4. While no follow-on devolution programme is planned, BHC Nairobi should continue using existing knowledge products for policy influence. Strengthening county statistics offices remains a gap. BHC could support finalisation of the County Statistics Bill 2024 and collaborate with KNBS to establish standards for county-level data management.

Output Number and Title	Output 5 - The UK development portfolio is better aligned with county government priorities
Output Score	B
Impact weighting (%)	10%	Impact weighting revised since last AR?		Yes, up by 5%

Output Indicator			Final Logframe Target	Final Result Achieved
Availability and use of tools to track the alignment of UK government development portfolio in Kenya with County priorities			Evidence of county profile use in supporting timely assessment of common objectives and adequate adaptation of FCDO activity in at least 10 counties.	B – Moderately not met expectation / 10 reports produced documenting UK aid investments in 10 counties and alignment with county priorities but produced too late (at end of programme) to be of use.
Effectiveness of coordination (a) internally and (b) externally to align UK support with country/county priorities.			Evidence of enhanced coordination of devolution initiatives (a) within FCDO and (b) in 5 counties	B – There is anecdotal evidence from BHC teams that the presence of regional advisers has enhanced internal coordination of county-implemented BHC initiatives and improved BHCs understanding, and response to, county priorities

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

In line with the KDP business case, programme-funded staff were to be recruited across at least five regions to directly support county governments and enhance the impact of UKAID-funded programmes. This approach aimed to ensure coherence and alignment with the Government of Kenya’s priorities. BHC successfully recruited four regional advisers, deployed regionally . By the final year of the programme, all but 2 (Kisumu and Uasin Gishu) regional adviser positions were vacant.

Over time, the role of regional advisers significantly strengthened the British High Commission’s (BHC) understanding of sub-national political dynamics, improved political access and influence at both county and national levels, and promoted coherence across HMG investments at the county level. Initially focused on overseeing ODA programmes within their respective counties, the advisers’ roles evolved to encompass broader responsibilities, including supporting cross-departmental HMG programme and political engagements across regional economic blocs (rather than just counties).

Indicator 5.1 - aimed to assess the extent to which tools - such as county profiles - could be developed and institutionalised to support KDP, the BHC, and implementing partners in understanding county contexts, mapping HMG investments in key locations, and identifying local priorities. To this end, ACT procured technical assistance to produce county reports for 10 counties. However, it is arguable that this task would have been more effectively undertaken in-house, where there is better access to and understanding of evolving cross-HMG geographic priorities. While the reports were completed, their utility could be limited.

Indicator 5.2 Regional advisers through various mechanisms increased BHC’s contextual understanding of and response to county development and political contexts. They:
- Produced timely and relevant political analysis, including situational reports along with BHC programming and sector priorities (e.g. trade and land issues in the North Rift), weekly political updates, and a teach-in on emerging regional trends – which enhanced the BHC’s contextual understanding and influenced engagements.
- Provided regional expertise to inform UK programming and delivery, contributing to programme design (e.g. SUED 2), producing bespoke analysis, monitoring implementation of UK-supported initiatives (e.g. SUED, KDP, Tech Hub, DIT), and provided contextual analysis and supported official engagements. Supported the Digital Access Program progress on their way of working with Busia County to support the implementation of the Busia County Ward based Agricultural Strategy on Social and Economic Revitalization Program.
- Represented the UK in the regions, by facilitating meetings with influential stakeholders, advising on county and regional dynamics, supporting senior visits, and maintaining strong relationships across government, civil society, and the private sector.
- Contributed to the technical delivery of KDP in its final year by providing strategic direction across Outputs 1, 2, and 3.
While assessing the success of this output (through a logframe), was challenging (mainly due to the dynamic nature of inputs and requirements), overall, there is anecdotal evidence that regional advisers’ inputs were valued by teams internally and overall have enhanced BHC’s engagement in various counties, and helped manage risk.

Externally, the British High Commission (BHC) remained an active member of the Devolution Donor Working Group, while ACT participated in the Devolution Sector Working Group (DSWG). A notable achievement was the incorporation of the Devolution Sector Working Group, which has now been institutionalised by SDD. Through the programme, technical experts were embedded within the State Department for Devolution (SDD), where they contributed to key policy processes via the DSWG. Notably, these experts supported the review and development of the Devolution Policy and the Devolution Sector Plan for the Fourth Medium-Term Plan (MTP IV) 2022–2027. These transitional documents are expected to guide the implementation of devolution over the next 5 - 10 years, shaping strategic priorities and informing future investments.

Lessons learned through this output, and recommendations for future programming
KDP has clearly demonstrated the benefits of politically aware delivery, through the contributions of regional advisers. Their role significantly enhanced the BHC’s understanding of sub-national political dynamics, improved political access and influence, and strengthened coherence across HMG investments at the county level.

In the context of declining ODA budgets and the absence of a follow-on devolution programme, gaining local political insights becomes even more critical. These insights can guide programme delivery, foster strong and mutually beneficial local partnerships, and support a portfolio approach to HMG engagement at the county level. They also play a key role in managing risks and ensuring strategic alignment with GoK priorities. Evidence from FCDO’s “best buys” highlights that politically informed approaches are highly cost-effective, often amplifying the impact of development interventions - even those with mixed or limited evidence bases.

The implementation of Output 5 has shown that this work is most effective when delivered internally. Outsourcing this function limits its effectiveness due to the need for nuanced understanding and real-time access to evolving cross-HMG priorities. It is recommended that BHC Nairobi develop and agree on a revised sub-national engagement strategy. This strategy should align with new organisational priorities and include appropriate resourcing to sustain and build on the gains made through KDP.

D: Value for Money

VfM performance compared to the original proposition in the business case (As per the Aug 2025 FCDO template on programme completion reviews, Equity and Effectiveness are covered in Section 1 with this section focusing on economy and efficiency).

Key Cost Drivers and Performance
KDP’s key costs included technical assistance (especially under Output 1 & 2), staff costs, grants to civil society organisations, and administrative expenses. Costs were affected by rising living expenses, changes in Kenyan tax policy, and foreign exchange fluctuations. With FCDO approval, exchange rate gains of approximately £250,000 were reinvested into programme activities. Costs were managed within agreed parameters; savings and gains were applied to delivery in line with policy
Economy
The business case proposed benchmarking key costs such as staff, consultants, transport, and workshop costs. Broadly, KDP performed well on economy indicators. For example:
- ACT competitively procured experts and negotiated reasonable consultancy rates. However, Value for Money could have been improved by more precisely defining the optimal level of inputs required for specific outputs, as well as setting clearer expectations for output quality. An end-of-programme audit noted that input levels varied across assignments without a guiding framework for allocating technical assistance or assessing the quality of consultancy deliverables.
- The World Bank adhered to its procurement policies, and most technical assistance was delivered by national experts. Medium-term, locally sourced TA proved more effective and economical than short-term or international support. Some downstream partner rates were higher though these were limited in scope.
- Workshops were held in cost-efficient county venues, and competitive procurement ensured value for money.
- The programme embraced digital tools - webinars, virtual meetings, and online engagement - reducing travel costs and expanding reach. For example:
  - Shifting Shujaaz meet-ups online during COVID-19 saved costs and enabled weekly Barometer reports.
  - Shifting to virtual forums with the Kenya Devolution CSOs Forum (1,100+ members) reduced costs but also made the forums self-sustaining beyond KDP funding.

Efficiency
Efficiency was to be achieved through regular reviews of results and costs, ensuring resources were directed toward high-impact outputs. Coordination among implementing partners and alignment with the National Capacity Building Framework were central to this approach.

With ODA reductions, there is a question whether budgets were allocated optimally with higher budgets to outputs with the highest potential to achieve intended outcomes. Total expenditure remained within the approved envelope, aligned to outputs.

The programme’s delivery mechanisms could also have been used better to enhance efficiency. While funds were allocated between delivery partners in line with their strengths in delivering specific outputs, this could have been even more robust. However, funding to the World Bank leveraged synergies with other Bank operations, such as the Kenya Urban Support Programme, allowing more resources to be directed toward delivery. Alignment with national frameworks and regular engagement through the Devolution Donor Working Group helped minimise duplication.

The sub-national team, accounting for 8% of the budget, played a vital role in facilitating UK engagement with counties and Regional Economic Blocs (REBs), especially during COVID-19. Their support enabled high-level visits, joint commitments, and analytical products like county profiles, improving programme alignment and delivery.

Working with REBs proved valuable, leveraging their convening power to drive coordination and scale. For example, the MEL system developed for the LREB will be used by all 14 Lake Region Counties. However, the lack of a legislative framework for the financing and sustainability of REBs remains a challenge.

Effectiveness
KDP’s business case ambition was to measure effectiveness by linking programme investments to development results at the county level, comparing these with sector benchmarks, and assessing sustainability. Funding was to be allocated based on implementing partner performance and counties targeted based on potential impact, where UKAID could deliver the greatest value, guided by criteria such as poverty levels, government county commitment to reform, and alignment with UK priorities. ACT would complement multilateral partners by engaging more deeply at the county level.

Notable achievements include:
- Cost-effective and impactful CSO partnerships under Output 3, which delivered strong results in social accountability with just £598,000 - 6% of the programme spend.
- Improved intergovernmental coordination and service delivery in some cases, including the December 2024 gazettement of delineated national and county functions.
- Locally driven, context-aware approaches that increased sustainability, such as building national institutions’ capacity to support counties and delivering technical assistance through coaching and mentoring – and placement of regional advisers to support implementation and political engagement.
- Co-creation and government-led development of systems like PFM and HRIS ensured alignment with national priorities and long-term viability.
- While the formal county selection criteria were not consistently applied, counties were generally chosen based on potential impact, government county commitment to reform, and alignment with UK priorities.

KDP’s design and delivery approaches improved the likelihood of sustaining outcomes. However, due to various challenges outlined earlier in the report, there was little evidence that KDP’s outputs translated to the intended outcomes. Tailored support, deep engagement, and locally led initiatives fostered ownership and relevance in some cases. However, the implementation of policy and legislative reforms by county governments will depend heavily on political will and Kenya’s fiscal capacity. Continued engagement and influencing by BHC and other stakeholders will be essential to maintain momentum and ensure reforms are institutionalised and translated into measurable development outcomes.

Equity
KDP performed well on equity, promoting inclusion of citizens in governance processes through improving capacity for participatory approaches. Inclusive county-level processes for planning, procurement, and M&E were embedded, particularly under Outcome 1.1 and Output 3 led by ACT. It is, however, not clear that a targeted, differentiated approach to promoting equity was applied consistently through all the outputs.

KADP piloted digital tools such as a grievance redress mechanism (e-GRM) and a participatory budgeting platform. Technical assistance supported the development of a Social Risks and Impacts Management Policy and tools like Social Audit and Project Management Committee (PMC) guidelines – which mandate for PMCs to include representatives of youth, women, persons with disabilities, and other interest groups - have been widely adopted by counties. Disaggregated data collection was prioritised, with records showing women made up over 40% of PMC membership. County selection also reflected geographic and income diversity.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

Throughout its lifespan, the programme maintained a moderate overall risk rating, as assessed during each annual review, and operated comfortably within the programme’s set risk appetites across all categories. While the original business case identified contextual and reputational risks, additional unforeseen challenges emerged during implementation - most notably the COVID-19 pandemic and ODA budget reductions, which partially affected delivery.

FCDO applied standard risk management and assurance processes. These reviews also ensured that partners had clear approaches to managing risks related to SEAH (Sexual Exploitation Abuse and Harassment) and safeguarding. No safeguarding cases were reported during the life of the programme.

Annual spot checks were conducted across programme locations to assess implementation and financial management. The findings were documented, and follow-up recommendations were implemented accordingly.

During the programme period, several strategic and contextual risks emerged that influenced delivery and sustainability.

Political transitions and the 2022 elections
The 2022 general elections brought significant leadership changes at both national and county levels, including 22 new governors and widespread turnover in county assemblies. This led to temporary disruptions, as newly elected officials needed time to familiarise themselves with ongoing initiatives and reassess priorities. While the programme partially mitigated this by developing a clear pre- and post-election workplan and pivoting to support transition management, the scale of leadership change required extensive re-engagement. Additionally, the timing limited the programme’s ability to apply its county selection criteria - poverty levels and progressiveness - and to implement long enough in new counties to embed meaningful change.

Economic constraints and counterpart funding
The broader economic context also posed challenges. Austerity measures introduced by GoK, while fiscally prudent, significantly reduced the availability of counterpart funding for co-financed activities. This affected the programme’s ability to share costs with county governments, particularly for logistics such as accommodation, per diems, and conferencing. Although the programme continued to operate in line with donor principles on allowances, these constraints remained a persistent challenge. In response, the programme prioritised essential activities and limited full funding to those deemed critical for achieving outcomes.

Fiscal space and service delivery risks
Delays in the disbursement of national revenue to counties, coupled with Kenya’s constrained fiscal space, continue to pose a risk to service delivery. Even where capacity, systems, and frameworks had been successfully built, counties often lack the resources to implement and sustain reforms. As the programme concludes, this remains a key concern. Continued advocacy and influencing - particularly by BHC and other stakeholders - will be essential to ensure that county governments receive adequate and timely allocations of financial and human resources, in line with their delineated and concurrent functions under the devolved system.
The programme had a low environmental and climate risk profile, given its primary focus on policy, technical assistance, and capacity building. Most activities involved meetings, workshops, and virtual engagements, which had minimal environmental impact. However, KDP did contribute positively to environmental outcomes through Output 2, which developed monitoring tools for the blue economy - specifically focused on inland waters.
F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

KDP was implemented through:
1. KADP III (World Bank Trust Fund): A million multi-donor trust fund managed by the World Bank.
2. Mercy Corps: A COVID-19 rapid response grant, with a sub-grant to Shujaaz Inc.
3. Act Change Transform (ACT): An accountable grant. From 2021–2022, ACT sub-granted to 8 downstream partners and 7 CSO networks. In 2023, this was streamlined to 1 partner (PwC) and 6 CSO networks to align with reduced budgets.
4. Programme-Funded Regional Advisers: Initially 4, reduced to 2 by programme close.

Both ACT and Mercy Corps submitted quarterly narrative and financial reports in line with their grant agreements. Reporting was timely, and quality improved over time. Financial reports were reviewed alongside narratives, allowing FCDO to query unclear expenditures and forecasts before approving disbursements. Forecasting accuracy was generally good, however, unclear forecasts in the final quarter delayed ACT’s payment of final liabilities.

ACT commissioned annual audits for itself and its downstream partners. All audit reports were unqualified, with no major issues identified. FCDO conducted annual spot checks to verify financial management and reporting and commissioned an independent end-of-programme audit. Lessons on partner and contract oversight have been captured for future programmes.

In line with the FCDO Programme Operating Framework Rules and good practice, it is encouraged and commendable to report any suspicions or allegations of fraud, terrorist financing, sanctions violations, money laundering, bribery, corruption, sexual exploitation and abuse (SEAH), and sexual harassment. During the reporting period, there was no substantiated safeguarding or fraud cases.

In the first two years, programme spending fell short of projections due to delays in mobilisation and work planning. In the final two years, ACT’s annual allocation was reduced to £1.5 - £2 million due to ODA reductions, below the original ceiling of up to £2.5 million a year. In the final year, FCDO approved an additional approximately £250,000 from foreign exchange gains for specific activities to be implemented by ACT. A persistent challenge was the misalignment between FCDO’s financial year (April–March) and ACT’s programme year (October–September), which complicated partner contracting and budget planning. Future programmes should aim to align financial and results cycles to avoid similar issues.

Asset management followed FCDO Programme Operating Framework rules. All partners-maintained asset registers, shared annually with FCDO. Key assets included vehicles, IT equipment, and office furniture. Regular spot checks were conducted, and disposal is currently underway. Assets were managed and disposed in line with the FCDO PrOF guide. As a precondition of donation, all recipients gave written confirmation on their ability to maintain and operate the assets.
The World Bank submitted six-monthly narrative reports, and expenditure data was accessed via the Development Partner Centre portal. FCDO contributed £2,000,000 in March 2020 and £800,000 in December 2024. Audits were covered within the World Bank’s Single Audit reports, though a limitation remains: trust funds are not audited individually, and oversight of trust fund audits is managed by FCDO centrally. Despite not contributing to the fund for two years, FCDO remained an active member of the Trust Fund Steering Committee and continued to influence investment decisions in Kenya’s devolution sector.

Table 1: Total Programme Spend
Implementing Partner	Agreement value (£)	Spend (£)
Contribution to World Bank Trust Fund	2,800,000	2,800,000
ACT![29]	10,000,000	6,461,606
Mercy Corps	250,000	247,912
Programme Funded Regional Advisors	869,821	869,821
Independent MEL & audits	96,238.10	64,051.70
Total	14,016,059	10,443,390.70
[29] As a result of a lower ODA allocation for FCDO globally, country budget allocations were lower than in preceding years and consequently, allocations to individual programmes, including KDP were lower than optimal. The variance between ACT’s agreement value and actual expenditure is therefore attributable to these reduced annual allocations throughout the programme period, rather than to underspending.

Programme-level approach to monitoring and evaluation.
KDP conducted monitoring through partner reporting, field visits, and dissemination of learning. The programme logframe was reviewed annually, with ACT’s reporting linked to output indicators. In Years 1 and 2, the World Bank’s indicators were included at both output and outcome levels. In the final year, 30% of the World Bank’s reported outcome results were attributed to KDP, proportionate to FCDO’s financial contribution. While output statements were broadly aligned across implementers, incorporating output-level results from the World Bank into the logframe proved challenging due to varied levels of funding by FCDO into the fund over the years.

ACT’s deliverables were monitored through monthly programme management meetings, quarterly progress reports, and periodic field visits and spot checks. These included beneficiary engagement at both national and county levels. ACT also held monthly meetings with PwC to review progress and make changes to workplans and conducted routine monitoring visits to CSO partners to provide mentorship on reporting. CSO partners used digital tools for monitoring.

KDP remained an active member of the KADP Steering Committee, participating in bi-annual meetings to guide investments in Kenya’s devolution sector. The regional advisers played a key role in monitoring progress, particularly for Outputs 1, 2, and 3, and provided valuable insights from the counties.

While ACT conducted a series of Political Economy Analyses of the devolution sector, it was not evident that the findings informed programme delivery. Nonetheless, both implementers produced and disseminated a range of knowledge products, including a Baseline Public Perception Survey, Endline Study, Digital Technology Assessment, and the Devolution@10 Report. These resources were shared widely and are in the process of being added to the Council of Governors’ Maarifa Portal, ensuring continued access and learning beyond the programme’s lifespan.

Lessons were shared through webinars, in-person workshops, and virtual forums. CSO partners also conducted exchange visits to other counties to learn from successful practices and adapt them to their local contexts. These peer-to-peer engagements helped foster cross-county learning and contributed to the sustainability of programme results. Half of the programme’s annual reviews were conducted independently by FCDO staff outside the core programme team, adding objectivity to performance assessments.

While the programme implemented some good monitoring practices, there is limited evidence that learning and insights were consistently applied to inform its strategic direction. The BHC – commissioned end-of-programme evaluation (July 2025) was also inconclusive. Quality assurance[30] of the evaluation report highlighted gaps in data and insufficient evidence to fully address some of the evaluation questions. It also noted that the sources supporting key findings and the methodology used, lacked clarity. As a result, the findings and recommendations could not be reliably drawn on.
[30] By FCDO’s Evaluation Quality Assurance and Learning Service (EQUALS)

Date of last narrative and financial report	ACT! – April 2025 (for Jan – March 2025) / World Bank - June 2025	Date of last audited annual statement	ACT - June 2025