## Annual Review Template

Title: Supporting Pastoralism and Agriculture in Recurrent and Protracted Crises (SPARC)
Programme Value £ (full life): £17.6m		Review date:
Programme Code: [AMP ID#] 300655	AMP start date: / 22/03/2019 / Actual: 6/01/2020	AMP end date: / 31/01/2026

Summary of Programme Performance

Year	2020	2021	2022	2023
Overall Output Score	A	A	A+	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300655/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300655/documents

A. SUMMARY AND OVERVIEW

Description of programme

SPARC is a six-year (2020-2025) £17.6 million research initiative funded by the Foreign Commonwealth and Development Office (FCDO) focused on supporting livelihoods in the world’s most vulnerable and conflict affected countries. It aims to develop, broker and manage knowledge, in order to enhance the ability of the FCDO and the broader development community to assist pastoralists, agro-pastoralists and farmers living in the context of climate change, protracted crises and ongoing conflicts. SPARC’s ultimate objective is to help communities in the drylands of East, North and West Africa and the Middle East to increase their resilience to recurring shocks and protracted crises.

SPARC does this by supporting more effective interventions and a better understanding of the challenges in these communities. By partnering with local researchers and organisations and drawing on our own research and field programme experience, SPARC’s activities include the following:
1. Research activities designed to strengthen the evidence base on how to effectively deliver programmes and adapt policies.
2. Innovation and technology which supports the development and scale up of innovative approaches across a range of contexts in fragile and conflict-affected countries.
3. Targeted technical support to FCDO country offices and programmes, which will inform the design, delivery and review of existing programmes and policies.
4. Knowledge management lessons that will inform both the development of future policies and programmes, and technical support, ensuring that the research remains operationally relevant.
5. Research uptake and dissemination to ensure that findings, lessons-learned and other outputs are widely disseminated and targeted to relevant policy and programme decision-makers to ensure impact.

Summary supporting narrative for the overall score in this review

The SPARC programme has generated new evidence and produced high-quality, rigorous and accessible research products. It has worked to position itself as a centre for knowledge and expertise on resilience to climate change, recurrent shocks and protracted crises impacting agricultural and pastoral livelihood groups living in fragile and conflict-affected contexts. SPARC is a research-into-action programme that directly informs policies, practices and programming, and has contributed to the ambitions of the International Development Strategy, Integrated Review Refresh, and FCDO’s Humanitarian Prevent pillar and Women and Girls strategies.

The programme excelled in its demand-responsive research, pivoting rapidly as required and drawing in world-class expertise to produce highly relevant and impactful analysis to directly inform critical FCDO policy areas and programmatic decision-making. During 2022/23, SPARC responded to eleven responsive research requests from FCDO and began planning for four additional requests with FCDO posts and policy teams for implementation in 2023/24. Examples of demand-responsive research include support for: FCDO Economy, Basic Services, Inclusion and Governance Team at the Afghanistan and Pakistan Directorate in understanding livelihood opportunities and coping mechanism of priority groups; FCDO Humanitarian and Migration Directorate (HMD) on advancing climate action in fragile and conflict affected settings; FCDO Somalia on the barriers and opportunities to designing and implementing climate finance in Somalia; and HMD on the role of the private sector in promoting food security in fragile contexts.

SPARC has successfully leveraged an additional £350,000 from IDRC this financial year, in addition to the existing £1.2m agreed by IDRC covering the period May 2022 – May 2024. This collaboration has enabled the programme to increase its focus on women and girls, and localisation - two areas of significance to FCDO. These projects involve deep analysis of the local context by Southern researchers, focused on: women and girls, looking at gender equality, increasing social inclusion and empowering women and girls living in the context of climate change and conflict, using community-based participatory action research; and on the implications of food and commodity price rises for dryland households in the wake of Russia’s invasion of Ukraine.

It is FCDO’s assessment that the programme demonstrated value for money and has performed well or exceptionally in most areas, and has therefore been awarded an overall score of A.
Major lessons and recommendations for the year ahead

1	Review of programme log frame and monitoring, evaluation and learning (MEAL) systems, to ensure that targets and means of verification are robust and appropriate. This is particularly relevant for Outputs 1 and 2. The programme should look at options to collect data on reach, uptake, use and impact of research products. The current system of measuring Outputs 1.2 and 2 does not appear to be sufficiently robust and could be strengthened. / SPARC leadership and MEAL team to review logframe and MEAL system. Report back to PRO by November 2023.
2	Ensure there is a clear policy engagement and influencing strategy in place. This was a recommendation in the last Annual Review, but while some progress has been made there is no clear strategy in place and being utilised. Be strategic in identifying opportunities for policy impact and influence ahead of developing and undertaking research. Develop a plan which will outline how this will be achieved. / SPARC leadership. Status report to be sent to PRO by November 2023
3	Reinstate the role of Learning Expert, as per the SPARC contract and Inception Report. Ensure that programmatic level learning is taking place, led and supported by a Learning Expert. The Learning Expert should report to the Programme Steering Committee. Ensure adaptive management systems being upheld; foster a culture of openness and transparency where programme staff and in particular technical leads and consortium leads are able to feed into decision-making, and provide opportunities for reflection, learning and action where possible. / SPARC leadership. Progress report to PRO by 1 November 2023
4	Ensure that the programme is sharing and disseminating findings widely, being innovative and proactive in sharing research products and analysis with FCDO and externally. A Communications Strategy was developed at the end of the reporting period, and should be a key tool for driving up engagement, reach and uptake over the next year. The programme should look for opportunities to share research and analysis with FCDO over the next 12 months through a number of learning events with Heads of Profession, advisers and relevant Posts and policy teams. / SPARC leadership and communications team. Progress report to PRO by November 2023
5	Research teams and PRO should continue to build links between the programme and FCDO Posts, as well as other relevant UK-based geographic and policy teams. While these connections exist where technical assistance has taken place, these are currently quite individually driven by members of SPARC, and there doesn’t appear to be a clear strategy for how the wider programme engages and communicates with relevant teams at Post to share and get feedback on research projects. PRO can provide contacts and support in initiating introductions, however SPARC needs a clear engagement strategy in relation to research, in order to maximise policy and programmatic relevance, and broader impact. / SPARC leadership and communications team to develop strategy, and PRO to support FCDO engagement. To be sent to PRO by November 2023
6	Review the programme’s innovation component and output 4, to strengthen links between SPARC’s findings and FCDO’s programming and approach to innovation in drylands. If this is no longer considered to be the most appropriate focus of the innovation component, the output will need to be reviewed and reframed. / SPARC leadership and innovation team to undertake review, with PRO to support FCDO engagement. To be sent to PRO by November 2023.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

SPARC’s ultimate objective is to help communities in the drylands of East, North and West Africa and the Middle East to increase their resilience to climate change, recurring shocks and protracted crises. SPARC does this by supporting more effective interventions and a better understanding of the challenges in these communities. Specifically, SPARC: informs the decision-making process for policies, programmes, or practices affecting these dryland communities (instrumental changes); influences how stakeholders involved in and affected by the decision-making processes think about social, economic, climate and environmental issues in the drylands and how these interact (conceptual changes); and enhances the collective ability and competencies of actors who have a stake in decision-making processes (capacity changes).

SPARC uses a knowledge-to-action approach, focused on addressing gaps by generating and sharing practical knowledge on what works, what does not, and how, why, for whom and under what circumstances. The programme's added value is that it offers an agile mechanism for research, advice and convening to enhance decision-makers' choices, by generating practical knowledge that improves the effectiveness of programmes and policies. SPARC does this by:

1. Generating timely and accessible evidence through research;
2. Providing advice to the UK Government and development partners through TA
3. Engaging effectively with knowledge networks and building relationships, and
4. Providing and testing innovative approaches and solutions – including through an innovation facility
There have been no changes to outcome and impact indicators since the last annual review.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

SPARC is on track to contribute to expected outcomes and impact, despite having faced considerable challenges of prolonged uncertainty in confirming budgets for the year, as a result of ODA reductions and reallocations. The programme has substantially exceeded expectations in its demand-responsive research and technical assistance to FCDO. It has been able to rapidly pivot resources and capability to meet urgent and emerging HMG priorities, providing the specific analysis required to make evidence-based programming and policy decisions. This has resulted in significant positive impact on FCDO’s effectiveness in priority areas. It has consistently delivered high quality, rigorous and accessible research products. It has successfully leveraged an additional £350,000 from IDRC this financial year, in addition to the existing £1.2m agreed by IDRC covering the period May 2022 – May 2024.

SPARC has had part of it’s budget realigned from 2023/2024 to future years, although continuing under the same overall total budget. An external mid-term evaluation was originally planned for 23/24, however this has now been postponed due to capacity constraints in FCDO and within the programme, and will instead will be commissioned as an end-of-programme evaluation.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

It is the assessment of the of the FCDO programme leadership and management that SPARC should continue. It has met or exceeded expectations, despite budget cuts, reallocations and uncertainty, and demonstrating agility when required by pivoting to meet FCDO priorities. It provides a valuable role in the overall Food and Agriculture Research Team’s portfolio with its responsive research offer, supporting teams with policy-relevant analysis for decision-making. It directly supports teams in working towards achieving the objectives of the International Development Strategy and the Integrated Review Refresh, including through contributing to the FCDO Humanitarian Strategy’s ‘Prevent’ Pillar, the ‘Empowerment’ pillar of the Women and Girls Strategy, and focusing on building resilience in fragile contexts. This programme is particularly relevant to FCDO’s wider research portfolio given the UK’s Development campaign on food security and nutrition and on open science for global resilience. Tackling global challenges of resilient food systems in the face of growing climate change, recurrent shocks and protracted crises requires robust evidence to support decision-making. SPARC directly contributes not only to the wider body of evidence on resilience to climate change and compound risks, as well as innovations in drylands, but also informs FCDO policies and investments through its demand-responsive component. SPARC also contributes to the International Climate Fund results, particularly KPIs on TA and Transformational Change. The collaboration with IDRC has strengthened the programme and signals its broader reputation, relevance and impact.

## C. DETAILED OUTPUT SCORING

Output Title	Timely and accessible body of evidence representing regional, cross country and country-specific perspectives made available to decision-makers.
Output number:		1	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number and range of SPARC research products (by type and including those delivered through technical assistance (TA)	A total of 14 publications (Policy Briefs, Discussion Papers, Research Reports), including 4 articles submitted to peer-reviewed academic journals.	Milestone partially met: Exceeded milestone for number of publications (16), however only 3 submissions to peer reviewed journal articles. Please refer to the full list of publications below.
1.2 The level at which SPARC interventions are assessed to be relevant, accessible and well-positioned for ease of use	20% Adequate / 75 % Good / 5 % Very Good	Milestone exceeded: 100% (this represents the score of the QA assessment for all the Issue Briefs and Research Papers that were reviewed, these being the type of SPARC publications which include this category of assessment). The evaluation rubric was adapted from the SPARC RQ+ Framework to assess this indicator. A sample of 6 outputs from a variety of types of SPARC publications were reviewed by the internal evaluator (not involved in any of the publications).
1.3 Co-authorship of knowledge products that can be attributed to researchers from the region in which the evidence is relevant	60%	Milestone essentially met: 57% of publications produced by SPARC this year were co-authored with researchers from relevant regions. This indicator was elaborated by calculating the percentage of outputs produced in this reporting period that are co-authored with southern authors in which the evidence is relevant.

Over the April 2022 to March 2023 period, SPARC has produced 19 outputs. These range from peer reviewed journal articles either submitted or accepted for publication (3), scoping papers (1), technical reports (1), research reports (3), policy briefs (3), issue briefs (7), and working papers (1). These were complemented by 28 other communications outputs such as blogs and news articles.

### FY21/22 Outputs (April 2022 – March 2023):
1. Issue Brief: Wiggins, S. (2022). Impacts of war on food prices and food security in potentially vulnerable countries.
2. Working Paper: Quevedo, A., Cao, Y., Alcayna, T., & Jarvie, J. (2022). Exploring the conflict blind spots in climate adaptation finance in the Sahel and Horn of Africa.
3. Issue Brief: Levine, S. (2022). Making the concept of resilience in the Sahel more useful.
4. Issue Brief: Weingartner, L., Humphrey, A., Sheikh, A. M., & Levine, S. (2022). Obstacles to and opportunities for anticipatory action in Somalia.
5. Scoping Paper: Vincent, K. (2022). Gender in agricultural and pastoral livelihoods in SPARC countries in sub-Saharan Africa and the Middle East: A review.
6. Policy Brief: Quevedo, A, & Cao, Y. (2022). Climate Adaptation Investments in Conflict-Affected States.
7. Issue Brief: Mayhew, L., Alasia, J. I., Opitz-Stapleton, S., Dagane, A. I., Mbeche, I., Sheikh A. M., Nor, Y. S., Harir, M. A., Hassan, S. A., & Egemonye, O. (2023). Somalia: drought and rising costs take hold.
8. Research Brief: Opitz-Stapleton, S., Alasia, J. I., Adamu, Z., Hassan, U., Jibo, A. A., Bayero, Y. M., Mallumre, B., Kuba, A., Mayhew, L., Egemonye, O. & Nana, S. (2022). Livelihoods, conflict and meditation: Nigeria.
9. Research Brief : Opitz-Stapleton, S., Mayhew, L., Alasia, J. I., S., Dagane, A. I., Mbeche, I., Sheikh A. M., Nor, Y. S., Harir, M. A., Hassan, S. A., & Egemonye, O. (2022). Livelihoods, conflict and mediation: Somalia.
10. Technical Report: Humphrey, A., Levine, S., Gai, J. T., & Lony, N. (2023). Dynamism in the drylands of South Sudan.
11. Issue Brief: Opitz-Stapleton, S. (2023). Transboundary climate risks to African dryland livestock economies.
12. Research Brief : Lepariyo, W., Banerjee, R., Alulu, V., & Shikuku, K. (2022). Digital innovations for high-frequency ground truthing and monitoring of household welfare in pastoral communities.
13. Policy Brief: Cao, Y., Quevedo, A., Khatri, N., & Khouzam, A. (2022). Embracing discomfort: a call to enable finance for climate-change adaptation in conflict settings.
14. Policy Brief: Hakiman, K. L, & Stull-Lane, C. (2022). Innovation in governance: Integrating technical and contextual perspectives to address fragility.
15. Issue Brief: Opitz-Stapleton, S., Alasia, J. I., Adamu, Z., Hassan, U., Jibo, A. A., Bayero, Y. M., Mallumre, B., Kuba, A., Mayhew, L., Egemonye, O. & Nana, S. (2023). Nigeria: Some land tenure insecurity issues in Hayin Ade and Wuro Bappate
16. Issue Brief: Hakiman, K. L, & Stull-Lane, C. (2023). Unravelling the knot: Addressing wicked problems through stakeholder engagement

Journal articles:
1.	Sisodia, R., & Jobbins, G. (2022). Climate change and psychosocial resilience in drylands: the need for more evidence. Published in ‘International Review of Psychiatry’s special issue on mental health and the climate crisis.’
2.	Chelanga P., Fava F., Alulu V., Banerjee R., Naibei O., Taye M., Berg M., Galgallo D., Gobu W., Lepariyo W., Muendo K. and Jensen N. (2022). KAZNET: An Open-Source, Micro-Tasking Platform for Remote Locations. Published in ‘Frontiers in Sustainable Food Systems.’
3. Hakiman, K. L. (2023). Unlocking the Potential of Participatory Planning: How Flexible and Adaptive Governance Interventions Can Work in Practice. Academic journal article (submitted to 'Studies in Comparative International Development' in 2023, awaiting publication).

Briefly describe the output’s activities and provide supporting narrative for the score.
In 2022-23, SPARC updated their research framework, in order to make it clearer, more accessible and to strengthen synergies. The research has three main areas of focus: Aid and Resilience; Livelihoods and Markets; Land and Conflict. Cutting across these areas are key themes: gender and social inclusion, climate change and innovation. The programme has produced a number of different types of knowledge products for a variety of audiences, and draws on a diverse range of research interventions, from longitudinal panel studies to rapid reviews.
SPARC was awarded a score of A for this output. The programme exceeded its target of 14 publications, however it did not meet the incorporated target of 4 products being submitted to peer reviewed academic journals. Acceptance of papers to peer reviewed journals provides confirmation of high-quality products and academic rigour, and so for a research programme of this size, FCDO would expect this target for submission to be met. SPARC exceeded the indicator for the number of products assessed to be relevant, accessible and well-positioned for ease of use, although missed the target for co-authorship by Southern-based researchers by a small amount. The latter is not considered a concern and is not being taken into consideration for the scoring. This is partly due to FCDO budget cuts and uncertainty, which impacted the programme’s ability to engage Southern-based partners through a call for proposals to undertake specific pieces of research, as had originally been planned in the Inception Report. This target should be reduced slightly for future years, reflecting the impact of earlier budget cuts.
While it appears from internal FCDO review that SPARC’s research products are high quality, relevant and accessible, there are concerns that there is currently insufficient data available on impact, reach and uptake. Research products are shared on the website and social media, and to relevant partners, stakeholders and those signed up for updates, however there is no evidence available of how widely they are being accessed and used, and how they are impacting broader knowledge or decision-making. Additionally, it is recommended that the indicator for 1.2 be reviewed, to ensure that it is robust and rigorous, and that the indicator does not rely only on the perspective of one SPARC internal reviewer. Last year this score was corroborated by the engagement of an external reviewer by FCDO, however this year that was not possible, which has confirmed the need for a more robust means of measurement for future years. It is important that the programme considers the broader impact of its research work, and demonstrates strong policy and programme linkages and evidence of change.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year it was agreed that the log frame would be reviewed by Q3 to ensure targets were robust, appropriate and stretching. However, due to continued uncertainty and delays in communicating budgets by FCDO, this was not undertaken. It is recommended that the SPARC team undertakes a review of logframe indicators, targets and means of verification by end of Q2 2023 and reports back to FCDO, to ensure that they are appropriately robust. In particular, the programme should look to find ways to record data on uptake, reach and use of research products, and increase means of verifying that products are relevant, accessible and well-positioned for ease of use. Additionally, it is recommended that output 1.3 on Southern led partners be reduced slightly to reflect the impact of budget cuts on programme design, to ensure that future overall scores for output 1 are not skewed. It was also recommended last year that there is a clear policy engagement and influencing strategy in place, and that the programme is strategic in identifying opportunities for policy impact and influence ahead of developing and undertaking research. While a consultant has been hired to support this work, the plan is not yet complete or operational. The programme should ensure that there is a clear policy engagement and influencing strategy in place, being strategic in identifying opportunities for policy impact and influence ahead of developing and undertaking research.

Output Title	Timely advice provided through technical assistance to HMG
Output number:		2	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 The level that TA requests satisfactorily addressed the scope of work	70%	Milestone Exceeded: 94% (Very satisfied) that TA requests addressed scope of work. A satisfaction survey was sent to six TA recipients from FCDO; two responses were received. This indicator is calculated by the average of 100% and 87.5%, which are the percentage satisfaction indicated by respondents for Question 2 and Question 4 of the survey.
2.2 The level of satisfaction of timeliness regarding SPARC support to HMG	70% Good	Milestone Exceeded: 87.5% (Very satisfied) with timeliness of production of research. Responses to Question 1 of the TA survey were used to enumerate this indicator.
2.3 HMG and other partners find that SPARC evidence is relevant and well-positioned for use	30 % Adequate / 70 % Good	Milestone Exceeded: 87.5% (Very satisfied) with the way SPARC evidence is positioned for use and its relevance. Responses to Question 3 (87.5%) and 4 (87.5%) of the TA survey were used to enumerate this indicator.

Briefly describe the output’s activities and provide supporting narrative for the score.

SPARC offers a flexible demand-responsive research component, which FCDO Posts and policy teams are able to draw on, providing high quality evidence and analysis to support decision making on positions, policies and programming. The design of this part of SPARC facilitates efficient collaboration with emerging initiatives and support for fast-evolving policy needs, using co-creation and a lean management approach, allowing support to adapt rapidly and respond to new opportunities or requirements.

During 2022/23, SPARC responded to eleven responsive research requests from FCDO and began planning for four additional requests with FCDO posts and policy teams for implementation in 2023/24. The FCDO requests for which TA was initiated in FY 22/23 were from the Humanitarian and Migration Directorate; FCDO Somalia; FCDO and DIT Ethiopia, FCDO Yemen, FCDO Afghanistan, FCDO Sudan and the Research and Evidence Directorate on the policy impacts of rising food prices in Mali and Sudan. Examples of responsive research undertaken include: Accessing climate finance in FCAS contexts (FCDO HMD); Livelihoods and markets in Afghanistan (FCDO Afghanistan Economy, Basic Services, Inclusion and Governance Team); Food price analysis in Sudan and Mali (FCDO RED); The role of the private sector in supporting food security (HMD); Trade and customs barriers for food security (FCDO Ethiopia)

This component was awarded a score of A+. The programme undertook high quality, wide-ranging and impactful demand responsive research for FCDO, at times pivoting resources and capacity rapidly with little notice and tight deadlines, to provide evidence and analysis to support FCDO decision-making. This component has been a valuable asset to the programme. The PRO has verified that FCDO clients have been satisfied with the scope of work, its relevance and its timeliness. However, it is clear that the current logframe means of verification are not an appropriate way to assess this output. For the last two years, only two responses have been received by SPARC to their satisfaction surveys, and this limited data has been the only formal means of assessing success and impact. Additionally, the programme should improve how it communicates and disseminates findings from responsive research, working with commissioning teams to proactively look for opportunities to share widely, both internally and externally (where appropriate).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

It was recommended last year that the programme review the logframe and MEAL systems, to ensure that a robust means of verifying the indicators was in place. However, due to ongoing budget discussions that did not take place. It is therefore recommended that this review is undertaken by the programme MEAL team in Q2 2023 and reported back to the programme PRO. Additionally, SPARC should review its approach to disseminating and sharing findings of responsive research requests, including to broader FCDO colleagues beyond immediate commissioning teams.

Output Title	Knowledge networks and relationships with, among and between implementing partners and stakeholders involved in relevant decision-making processes which are improved/strengthened by SPARC providing linkages and brokering.
Output number:		3	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of stakeholders collaborating through SPARC networks and interventions	70	Milestone Exceeded: SPARC has co-published with 50 stakeholders but engaged an additional (cumulative) 204 stakeholders throughout the year in a substantive way. Target for this FY was 130 cumulative.
3.2 SPARC knowledge sharing mechanisms are perceived to improve successful knowledge into use	20% Adequate / 75 % Good / 5 % Very Good	Milestone Exceeded: Reviewers provided rating of 87.5% or very satisfied that knowledge sharing mechanisms improve knowledge into use successfully. The results of Question 4 of the TA survey were used to enumerate this indicator.
3.3 The extent that SPARC is engaging effectively with relevant stakeholders	30 % Adequate / 70 % Good	Milestone Exceeded: rated as 94% very satisfied with the way SPARC researchers engaged with stakeholders in design, development and delivery of research product. Responses to Question 2 and 3 of the TA survey were used to enumerate this indicator. The results of the survey are outlined in Annex 14.

Briefly describe the output’s activities and provide supporting narrative for the score.

SPARC has collaborated with 204 stakeholders to date, including co-publishing with 49 individual stakeholders in key areas including education, transboundary climate risk, climate finance, and pastoralist resilience in fragile and conflict-affected states. The programme researchers took a leading role in a number of high-profile events, including sessions at COP 27 with ministerial attendance, the Intergovernmental Authority on Development (IGAD) High Level Regional Conference on Land and Conflict; the Riyadh International Humanitarian Forum, and the European Humanitarian Forum. In addition, they contributed to other events and organised webinars and seminars, including for FCDO (ie. cross-cadre HoPs discussion on supporting livelihoods in protracted crises; FCDO’s 2023 Economics Conference Navigating Storms: Economics for a Better World; FCDO Briefing on High Commodity Prices). The programme has continued to work on building the SPARC brand as a credible and internationally-recognised research group and partner that can respond effectively to the priorities of organisations and governments working to build resilience for agricultural and pastoral livelihoods in drylands. Within FCDO, the programme has built a reputation as a programme which offers high quality evidence and analysis on areas of strategic priority.

This output has been awarded a score of A+. It has exceeded expectations and showed good results in engaging, convening and collaborating with stakeholders. The programme is proactive and energetic, reaching out to build connections with relevant stakeholders and looking for opportunities to fill gaps, offer SPARC’s knowledge, expertise or products, and promote the programme’s brand. In particular, in building the relationship with IDRC and leveraging substantial additional funding, it has excelled. This collaboration has led to expanded pieces of work highly relavant to FCDO, in addition to an enhanced focus both on women and girls and on working with Southern-based partners.

There are, however, areas within this output which could be improved, particularly in terms of raising visibility of the programme, and increasing the type and number of events to disseminate and share SPARC’s products and analysis. Over this year, there were 26,452 visits to the SPARC website, the Twitter account grew from 257 followers to 387, and the e-news letter was sent to 198 subscribers, and 16 blogs were published on the website. There is scope to continue to build on these numbers, and to be more proactive and innovative in findings ways to share SPARC’s findings, both externally and within FCDO. As mentioned under Output 1, there would be value in identifying ways of recording data on numbers of people accessing blogs, how the information is being used and what the wider impact is. Additionally, a key stakeholder for SPARC is FCDO teams located at Posts, within the programme’s target countries. It is recommended that in the next year, the programme works to build connections and regular communications with FCDO teams in all countries within which it is undertaking research, and is using those networks to ensure the policy relevance and strengthen impact of its research findings.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s recommendations were that the programme develop and implement a communications strategy, and that it continue to find innovative ways to build the profile of the programme and share findings widely. The communications strategy was submitted to FCDO in the last month of this reporting period. Therefore, it has not yet been implemented. Communication, disseminating and engagement with stakeholders should be a priority for the programme for the next reporting period, particularly now that the strategy is in place.

Output Title	Innovative approaches and solutions, including technological innovation, made available to FCDO partner programs in a timely manner
Output number:		4	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of SPARC-led evaluations commissioned and published focused on what works and in which context	2 initiated	Milestone Exceeded: Initiated 4 new evaluations this year in addition to the two reported last year. Continued the studies with Wowzi on campaigns and jobs, and with SHARED. Published an evaluation of two different versions of SHARED in Ethiopia and Kenya. In addition, initiated impact evaluations of Afriscout 1.0 in Kenya, Afriscout 2.0 in Ethiopia, and the WDP in Kenya. Continued scoping additional examples of innovation and integrating them into the innovation dashboard.
4.2 Number of innovations identified as having potential to iterate to scale.	1	Milestone Met: This year recommended one innovation area for investment to iterate and scale: social technology. In addition, conducted studies related to two additional areas to consider as recommendations in upcoming years.

Briefly describe the output’s activities and provide supporting narrative for the score.

SPARC continued to make good progress against this output over the reporting period and has been awarded a score of A+. Building on the Innovation Landscape paper, they continued scoping and sharing evidence with Agrifin Accelerate, AfriLabs and Sankalp Africa and added to the live online innovation dashboard. SPARC continued the three studies on selected examples of innovation: SHARED, an innovative approach to supporting governance and evidence-based decisions; Wowzi, a social media platform that engages influencers in campaigns; Afriscout, an app that provides geo-satellite and crowd-sourced information to pastoralists making grazing decisions; and added a fourth on the Ward Development Planning (WDP) model, an approach to strengthening local governance and planning in Kenya. These studies contribute to generating evidence in three innovation areas: social technology, digital services, and innovative approaches in governance. They hosted a webinar on social technology highlighting social media in the drylands with Wowzi and Nendo, and published a long form article on Kenya and two blogs on Uganda and Tanzania. In digital services, they started data analytics and scoping studies on available services; and initiated impact evaluations on Afriscout 1.0 which provides climate information in Kenya and Afriscout 2.0 which provides climate information and grazing advice in Ethiopia. In governance they published a descriptive brief on SHARED, a comparative evaluation of SHARED in Kenya and Ethiopia and submitted an academic article on WDP with the draft title Unlocking the Potential of Participatory Planning: How Flexible and Adaptive Governance Interventions Can Work in Practice to the journal Studies in Comparative International Development.
SPARC initiated two scoping studies this year in partnership with other innovation enabling initiatives: Mercy Corps’ Agrifin Accelerate, funded by Gates Foundation, to conduct a scoping study led by the Dalberg Research Agriculture and Food Security team on pastoralist, agro-pastoralist, and farmer use of digital financial and digital information services in Kenya, Nigeria and Ethiopia; and Mercy Corps ASAL Adapts, funded by Google.org and Cisco, on a scoping study on climate information services in pastoralist areas. In addition, SPARC is collaborating with Agrifin Accelerate, ISF Advisors and BriterBridges to establish AgBase (formerly Digital AgriHub) as an investment platform including databases of innovators, investors and enablers. With SPARC support, AgBase will integrate opportunities to invest in innovation in the drylands of East and West Africa alongside other agricultural markets in Africa, Asia and South America.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations in the last annual review centred on better integrating innovation into the rest of the programme, and SPARC has made progress with this by innovation both cross-cutting the other thematic research areas, and also being a theme in its own right. While this component of the programme is performing strongly and proactively, the wording of the output specifically states that it should make innovative approaches and solutions “available to FCDO partner programs in a timely manner”. Additionally, the inception report states that SPARC will seek to contribute to FCDO’s priorities by feeding into programme and grant design and programme implementation, generating evidence and best practices for country and/or programme-specific knowledge to improve project delivery, and generating learnings that inform FCDO’s approach to innovation and design for grants and development planning.

It is recommended that SPARC undertakes a review to identify the direction of the innovation work for the remainder of the programme, in order to understand where stronger connections can be made to directly link to and influence FCDO’s work in dryland innovation programming and approaches. If this is no longer considered to be the main focus of this component, the Output will need to be reviewed and reframed.

Output Title	SPARC is managed in accordance with management good practices and in line with adaptive programming principles to amplify and accelerate results
Output number:		5	Output Score:	B
Impact weighting (%):		5%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 The extent to which learning emerging from the Monitoring, Evaluation and Learning Activity (MELA) system leads to documented insights that help inform decisions to adapt the programme to changes in context, circumstances, and new knowledge	Adequate	Milestone Partially Met: Annual Learning Forum (AFL) and Portfolio Sense Making workshops organised with key recommendations under consideration by the Consortium Management Committee (CMC) for action in FY22/23. MEAL system captures some data and insights required for reporting on progress and learning.
5.2 Governance and management systems established and functioning	Programme managed according to SMART rules and programming principles	Milestone Met: Internal processes and key elements of governance and management in place and being operated in line with SMART rules and programming principles. Supporting programmatic documents include PSC minutes, the updated Risk Register, the revised Log Frame, Financial Report, and VfM analysis, updated supply chain.

Briefly describe the output’s activities and provide supporting narrative for the score.

All governance structures within the SPARC programme are in place and functioning; all Boards and steering committees have taken place regularly as scheduled; all core management standards have been met and there are no concerns regarding compliance or the long-term viability of the programme. As outlined above, the leadership of the programme has always had open communication with FCDO, been very responsive to requests for information or for a rapid pivot of resources, and have proved to be a very reliable, responsive and effective programme partners, particularly considering the uncertainty and instability caused by FCO budget cuts. Regular Consortium Management Committee meetings and Programme Steering Committee meetings have taken place as scheduled, in addition to the Annual Learning Forum which took place in September 2022 and was a positive and productive internal event.

However, it is felt by FCDO programme leadership that Output 5 milestones were only partially met during this period. As a result, this output was awarded a score of B. Adaptive management and learning within the programme need to be strengthened and better evidenced, including by demonstrating commitment to the internal role of Learning Expert, which was cut during this reporting period without consultation with FCDO, and despite the role holder being a named person on the contract. It was felt that the process of cutting the role of Learning Expert was not handled with appropriate transparency, The Learning Expert and the associated Learning Framework contributed to the adaptive management principles covered by Output 5, and therefore the evidence required to assess and verify Output 5.1. It is important to ensure that the programme – which has adaptive management and programmatic learning at its centre and embedded into its design – fosters a culture of trust and openness within the consortium. SPARC should ensure that learning processes and structures are embedded into the programme, and that there is a willingness and openness to reflect, discuss, learn and where possible act and improve.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s Annual Review recommended that: all governance structures and processes originally proposed in the Inception Report are in place and functioning, including the Learning Framework and associated mechanisms and processes; there should be a rigorous way to ensure that targets for this output are being met, particularly around adaptive management, including using the inputs of an embedded learning expert throughout the next year. FCDO does not feel that these recommendations were adequately met.

For this review period, it is recommended that SPARC re-establishes the role of Learning Expert within the programme, and re-focuses on programmatic learning as per the Inception Report. At this stage of the programme it is acknowledged that all original plans are unlikely to be achievable, however engaging a Learning Expert and developing a plan for the remainder of the contract would be advisable. It is also recommended that this role reports to the Programme Steering Committee or to another governance structure where all consortium members are represented. It is also recommended that future PSCs are structured in such a way as to ensure maximum possible space for discussion and direction-setting by members, with papers circulated in advance.

## D: VALUE FOR MONEY

Key cost drivers and performance

The programme team strengthened the VfM aspect of the programme by taking advantage of the break point (2.5 months unpaid pause) at the end of the nine-month inception phase to shape the implementation plan in such a way that it fully aligns with the vision of the FCDO programme team and Business Case. This ensured that the implementation plan is as detailed as it can be so that delivery was effective and efficient from day one of the implementation phase.

Secondly, renegotiation of the PbR value during the break point, gave a greater control to FCDO over the supplier’s quality of delivery. This gave a clear message to the supplier about the high level of expectations of the FCDO programme team while managing to maintain a continuous good working relationship with the supplier.

SPARC’s effectiveness is also demonstrated and validated through the leveraging of funds from other donors. SPARC has been successful in leveraging £1.7 in additional funding (cash or in-kind) from other donors and programmes to support SPARC research. Notably, a IDRC funding partnership has been secured for investment in the programme. This resources for knowledge management and research design and quality assurance activities as well as £88k in funding exclusively oriented to engaging southern organisations in carrying out gender-responsive research in SPARC countries over the next three years.

VfM performance compared to the original VfM proposition in the business case

Economy
Indicator	Performance Review
Cost saving measures	Given the impact of Covid-19 the programme has made savings on travel and events costs, with the programme organising online dissemination and virtual meetings. Although travel is now taking place these cost saving measures are still in place.
Best practices in procurement	Maximising VfM during contact amendments
Financial oversight	Robust financial systems in place, with internal and external auditing put in place for the Supplier
Financial risk management	Financial risk management strategy adhering to FCDO policies in place.
Efficiency
Indicator	Performance Review
Project management strategies	Digital technologies used to enable continuous communication between consortium members. / Outputs are delivered on time, where specified, and tracking this. / Project outputs/partner commitments across the programme are assessed at quarterly meetings and the Annual Review process to ensure the outputs are fairly balanced given the resources available and priorities of the programme.
Quality/quantity of output	Internal peer review process in place for each project output. / Internal peer review and FCDO consultation on innovation component and sourcing the highest quality specialist expertise in key areas as required. / Tracking number of research outputs produced, including peer reviewed and non-peer reviewed.
Effectiveness
Indicator	Performance Review
Promote operationally relevant research	Prior engagement took place with key stakeholders during Inception Phase. / FCDO country offices were involved in programme design and implementation to ensure that the outputs are operationally relevant. / Relationship building with governments, coordination bodies, the private sector and local communities is continuing to provide pathways to impact and improve policy uptake and drive innovation.
Ensure outputs are accessible to intended audiences	Publication channel and form specific to intended audience e.g. academic journals, toolkits, reports, workshops. SPARC published 49 knowledge and communication products in FY22/23, in key areas of food security, innovation, social protection, anticipatory action, and climate change. SPARC publications include four peer-reviewed journal articles on gender, pastoral land tenure, participatory planning and psychosocial resilience in the drylands, submitted to journals including Frontiers in Sustainable Food Systems and the International Review of Psychiatry. / SPARC has collaborated in publishing with nearly 50 individual stakeholders in key areas including education, transboundary climate risk, climate finance, and pastoralist resilience in fragile and conflict-affected states. In FY22/23 SPARC published 26 technical, policy and issue briefs, in addition to 23 blogs and news items
Establish high quality research partnerships	SPARC this year has built upon previous success in leveraging additional funding (a total of approximately £1.71m to date, including around £540,000 this FY) and forging strong operational partnerships with co-funders to contribute to key SPARC work. / IDRC also provided extended funding for the project “Commodity Price Impacts in Fragile African States”, under the umbrella of the SPARC programme. IDRC is providing CAD $599,939 to fund a series of studies to be implemented over an 18-month period by southern research organisations
Reach of research outputs	SPARC has continued to use its website as a key digital resource to disseminate all publications, news and feature articles and engage with relevant stakeholders. In the FY 2022–23, there were 26,452 visits to the SPARC website, and the programme's Twitter account grew from 257 followers to 387 over the year. / A quarterly subscription-based newsletter “SPARC e-news”, published in both English and French, shares news, events updates, and recently published research with a range of stakeholders. Currently the SPARC e-news is sent to 198 subscribers. / The programme also recently established a YouTube channel, which provides a platform to collate and disseminate relevant digital content, including recordings of SPARC webinars, an introductory SPARC animated video and a series of SPARC introductory videos, with researchers explaining key highlights from their work
Equity
Indicator	Performance Review
Participation of beneficiaries in research design & implementation	Not applicable to current period
Disaggregation of data	The Gender, Equality and Social Inclusion (GESI) Thematic Working Group is helping with the integration of GESI issues and scoping the baseline of knowledge of GESI issues in pastoral livelihoods in fragile and conflict-affected settings (FCAS) in SPARC countries. In the last review period, the programme undertook a peer-reviewed landscape study on gender in agricultural and pastoral livelihoods in drylands, which has helped to guide follow-on research in this reporting period. As well as mainstreaming GESI through the GESI adviser’s involvement and early review of each research proposal, the programme has also developed a number of specific research projects focused on women and girls. The collaboration with IDRC has also led to an enhanced focus both on women and girls and on working with Southern-based partners.
Promote careers of project staff	57% of knowledge products being co–authored by Southern researchers. Over the course of FY22/23 13 third-party suppliers have been actively engaged in the implementation of SPARC’s research activities, of which 9 can be considered southern research organisations based in the regions of research.
Overall cost-effectiveness	Assessment of whether the programme continues to represent value for money
Based on the above analysis of progress towards outcomes and outputs, theory of change and overall value for money, the FCDO programme management team’s assessment is that SPARC should continue. It has delivered a substantial contribution towards FCDO priority areas and demonstrated good value for money, particularly considering the challenges of the reporting period. The proactive leveraging of additional external funds through collaborations with other organisations to further advance their work in these strategically relevant areas has also been a significant achievement of the programme.

E: RISK

Overview of risk management

The overall risk rating for the programme remains moderate. Risk registers are held at the programme level and are updated by partners. Risk ratings range from minor to high. Risk is monitored by SPARC through regular check ins with partners, and the portfolio risk register is reviewed periodically by the Consortium Management Committee. FCDO receives an updated risk matrix quarterly. SPARC have also proactively audited themselves with independent audits of the inception phase and the first 18 months of implementation conducted in June 2022, with no issues. The next audit is scheduled to be conducted in Q2 2023/24.

Description of gross risk	Mitigation strategy	Residual risk rating	Risk rating changed from business case?	Expected trajectory of risk severity
Strategy and Context
Risks arising in the operating context: political developments, economic situation and operating environment. / 1. Political Instability: Safety and security issues in operating context. Diminished access to project areas	Continued monitoring of any changes that may affect delivery, with adaption to research plans and activities as required. associated risks monitored, managing operational challenges to data collection and field level engagement. (All partners are subject to due diligence assessments in line with FCDO enhanced due diligence requirements) / Progress is monitored monthly and flags any areas where new risks are emerging. Security is monitored using Cowater Security assessment tools (Drum Cussac and Max-Security) which help to proactively signal any problems. Access to real-time alerts, ensures staff and partners Duty of Care to pre-empt and avoid civil unrest associated with political developments and social issues. / Security Risk Assessment incorporated during the design of research ToRs, to ensure detailed understanding of local context, followed by continuous security risk assessment throughout implementation to identify and mitigate emerging or changing threats. / Northern regions of Ethiopia and Sudan continue to be affected by armed conflict. The SPARC team has adapted accordingly by reorienting the interventions.	Moderate	No
Policy and Programme Delivery
Non-delivery of high quality & timely evidence. (Notably related to the strategy and context challenges).	Robust planning and reporting systems and close monitoring of data and analysis. Clear terms of reference for all partners, with payments linked to specific milestones/outputs. / Regular meetings between programme & FCDO colleagues help to transparently address needs, gaps, and inform planning going forward. SPARC team maintaining core activities and manage consortium workflow.	Moderate	No
Conflicts arise between partners on allocation of resources (research fund).	There is a transparent process for allocating resources within the consortium. Quarterly meetings ensure any conflicts are effectively managed.	Minor	No
Programme duplicates other FCDO programmes.	Scoping work identified evidence gaps in existing FCDO programmes that are targeted by the programme. Opportunities for alignment identified. Scoping & alignment process continues during the life of the programme.	Minor	No
COVID-19 poses additional risks in delivery of programme. Limited movements have an impact on data collection, verification and roll out of activities and communication of results	COVID-19 has significantly decreased as an operational challenge. However their remains a residual risk in delivery of programme. Although International travel returned globally SPARC have maintained a top-quality website and digital approach to convey lessons; and has a well-resourced communications team in place to maintain a strong online profile through social media and digital marketing.	Minor
Public Service Delivery and Operations
Research outputs are of poor quality. / Lack of adequate resources to manage the programme.	Established peer review mechanisms provide researchers with strong incentives to produce quality research outputs. Quarterly meetings and the AR process provide opportunities for oversight of the research process and outputs. / The reporting timetable, agreement of Payment by Results framework and VfM matrix ensures FCDO minimise the Risk.	Minor	No
People
Risk arising from weaknesses in leadership and engagement, culture and behaviours and/or workforce capacity and capability, impacting on performance	As mentioned in Output 5, some issues have been identified with adaptive management and MEAL within the programme. However, there are no concerns regarding overall viability or compliance of the programme. Policy and process issues raised in the previous annual report were taken on board and have improved over this reporting period. The consortium partners have strong research expertise and are leading their respective areas well, while also continuing to build synergies between workstreams. Challenges arising from uncertainty associated with the Spending Review were pro-actively managed. Logframe performance outputs ensure maintenance of focus on team coherence and performance.	Minor
Safeguarding
Issues related to safeguarding mechanisms due to multiple partners in the consortium. Risk arising from failure to establish and maintain strong safeguards to prevent harm to beneficiaries of our programmes, staff and those implementing our programmes, the communities where we work, or the environment, resulting in ethical violations and reputational damage	Programme follows a strict ‘do no harm approach’. Cowater Safeguarding and Whistle-Blowing policies & safeguarding Code of Conduct signed by all partners, and assistance provided to partners to update safe-guarding policies. Due Diligence assessments aligned to FCDO enhanced safeguarding requirements undertaken for all partners in the supply chain. / Research quality assessment: gender equality & social inclusion assessed in depth for all research interventions. Follow up proactively addressed by the SPARC management unit, / SPARC will conduct due diligence to ensure partners have adequate policies and mechanisms for safeguarding risk mapping, reporting and remedial action. All partners sign on to Cowater’s FCDO-compliant Supply Chain Code of Conduct. / Since March 2022 SPARC’s security risk management has been further enhanced by continued development in the Cowater Security Risk Management Framework in the SPARC country of Mali and a dedicated Cowater Security Risk Manager (SRM) based in Burkina Faso, also covering Niger, / SPARC further developed its capacity for real time alerts and contextual analysis in seven countries - Nigeria, South Sudan, Kenya, Ethiopia, Somalia, Sudan, and Mali, with a subscription to The Signal Room- a commercial Africa analysis provider, Signal Risk, flagship reporting and analysis platform.	Minor	No
Financial and Fiduciary
Risk arising from our funds being used for unintended purposes or not managed in accordance with requirements and constraints, or poor management of assets/liabilities, resulting in weak value for money, compliance and delivery failures and reputational damage.	Systems used for setting budgets, monitoring expenditure & design, and strict oversight of partner contracts to ensure payment on delivery of milestones mitigate this risk. Programme follows Cowater financial rules and procedures. In 2020 policies and procedures were reviewed to ensure 100% compliance with FCDO rules. Due Diligence of downstream partners are compliant with Cowater/SPARC policies.	Minor	No

Reputational
The programme doesn’t deliver and achieve any of its objectives. / Risk arising from political or adverse events, including delivery failures and ethical violations, damaging FCDO’s and/or the UK’s reputation.	Management unit in discussion with PRO on average twice per month. Minutes and action items are shared. Specific discussions are held around research plans and allocations associated with the research fund. Programme Managers (for both SPARC and FCDO) are in regular contact around compliance, financial management and reporting.	Minor	New risk May 2021

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The Annual Review period covers a 12 month period from 1st April 2022 to 30th March 2023. The Supplier has submitted all its reports, invoices and management related documents within the agreed timeline. Throughout the reporting period they have continued to adopt a proactive approach and responded to all requests quickly, often at short notice and under changing circumstances. Key members of the Programme Management Unit (PMU) were replaced during this period; however the transition was seamless. All issues were still dealt with promptly and with a high degree of cooperation.

The programme is up to date on all required management systems, such as delivery chain maps, risk matrix and compliance with the Supply Partner Code of Conduct. The variance between planned and actual spend as per Contract Amendment 4 was 0.79%, and all invoices were raised in line with the contractual proforma and agreed milestones. In 2021 programme’s breakpoint was used to renegotiate the contract and move from an input-based contract to an output-based. Milestones are derived from the logframe and lump sums are attached to each milestone.

The Payment by Results (PbR) model additionally ensures greater value for money. The total PbR value is withheld until Q4 and supplier performance is scored against the logframe for the entire year. The scoring system is agreed, and payment is withheld until full score is achieved against an indicator. The programme team is confident that an effective system has been set up to monitor and encourage good supplier performance. Full scores were achieved within this reporting period and all payments made.

Meetings are held on a regular basis between FCDO and Cowater. Regular dialogue also takes place with the PRO and consortium leads to discuss any key research issues. The SPARC Programme Steering Committee (PSC ) takes place twice yearly with representatives from FCDO and all the SPARC consortium leads. Key issues covered are FCDO priorities, SPARC progress to date, and future plans.

Financial Position:
The total budget spent at 22/23 stands at £3,608,099 across PMU fees, research fund fees, communications, and other programme expenses. Total fund expenditure for 22/23 is £3,017,021. However due to FCDO budget constraints the 23/24 budget will remain as 22/23. This means a reduction of £1.3 m (27%) and will require realignment of the remaining budget into future years with a revised workplan and milestone payments. There will however be no overall change to the budget or the outputs.

Through the budget review process permanent savings have been identified in PMU costs, including savings from the variance in spending associated with the resourcing of Key staff and travel. All of these savings, totalling £111,050, will be reallocated to the Research Fund which will result in greater impact and VFM for the programme. Total Direct Programme Costs, as a percent of the Total Programme Cost, have therefore decreased by 0.6%. Fund value, as a percent of the Total Programme Cost, will increase by 0.6%.

Future Years:
The current end date shown on the contract is March 2024. There is a break point at the end of financial year 2023/24. Progression to the final 2 years of the programme is dependent on the effective performance and the quality of research conduct and outputs. SPARC will provide FCDO with a Research Report that summarises the research, preliminary findings, the activities of the research and innovation facilities, and a detailed workplan for research synthesis. Subject to FCDO agreeing the final period research plans a contract amendment will issue formally extending the contract end date to December 2025

Compliance:

- Gender- the programme is fully compliant with Equality Act
- Delivery partner mapping is complete and the programme is International Aid Transparency Initiative (IATI) compliant .
- Asset register fully updated.
- Risk register is fully updated.
- Delivery against Key Performance Indicators (KPI) are reported on a quarterly basis and have been fully met during this period.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
This Annual Review was led by an internal FCDO team and drew on feedback provided by a number of FCDO colleagues, and discussions with HQ and country office colleagues who have utilised the programme TA facility and research outputs. The review was completed by the programme’s Programme Responsible Owner and Deputy Programme Manager in the Food and Agriculture Research and Development Team. The annual review team drew upon the SPARC annual report and finances report, logframe, and research outputs, and on meetings with the programme leadership team on the programme annual report. FCDO has regular meetings with Executive Director and Programme Manager from Cowater to discuss programme progress and any issues, as well as research and technical assistance update meetings with the Research Lead. An external review of the programme was originally planned for this reporting period, however due to capacity constraints it was agreed that it would be postponed to later in the programme.

Evidence
The generation of new reach and impact evidence on building resilience for pastoralists and dryland farmers is an explicit element of the programme and is reported above. SPARC has been performing well at generating new evidence and working with national, regional and international actors to further knowledge and collaboration in this area.

Learning
Learning and adaptive management are explicit in the programme’s design. SPARC has a specific Learning Expert role identified in the inception report and contract. See Output 5 above for more detail.

Date of last narrative financial report	June 2023	Date of last audited annual statement	13th July 2023.