## Annual Review

Title: Structural Transformation & Economic Growth (STEG)
Programme Value £ (full life): £12m		Review date: Sept 2024
Programme Code: 300656	AMP start date: 25/10/18	AMP end date: 31/03/2025

Summary of Programme Performance
Year	18/19	19/20	20/21	21/22	22/23	23/24
Overall Output Score	B	A	A	A	A+	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Minor

DevTracker Link to Business Case:	https://ec.vault.dfid.gov.uk/otcs/cs.exe/properties/35715594
DevTracker Link to results framework:	https://ec.vault.dfid.gov.uk/otcs/cs.exe/properties/57752368

A. SUMMARY AND OVERVIEW

Description of programme
The Structural Transformation and Economic Growth (STEG) programme, established in March 2020, aims to provide a better understanding of structural change, productivity, and growth in low- and middle-income countries. STEG seeks to develop a strong body of evidence that will help country governments, international development organisations, NGOs, and the private sector to design and implement strategies, policies, and programmes that better facilitate structural change, productivity gains, and sustained, sustainable, and inclusive growth.
To achieve this goal, STEG aims to increase the quantity, quality, and policy relevance of research in the field and engage a greater number and more diverse group of scholars in the research community. STEG delivers policy insights and distils lessons that can be put into practice by policymakers and other key development actors in low-income countries. The programme also collects new data and improves the accessibility of existing data. STEG uses a wide range of evidence products and other communications channels to take stock of existing knowledge and to communicate the new knowledge created by STEG to stakeholders.

This first phase of STEG is a five-year programme of academic research budgeted at £12 million. In April 2024 new STEG activities will be incorporated into the broader Growth Research Platform (GRP) and receive an additional funding budgeted at £10 million. This existing STEG contract will then draw to a close in March 2026. The first phase of STEG is implemented by a consortium led by the Centre for Economic Policy Research (CEPR), and including the University of Oxford, the University of Notre Dame, the African Center for Economic Transformation (ACET), the Yale Research Initiative on Innovation and Scale (Y-RISE), and the Groningen Growth and Development Centre. Doug Gollin (Tufts University, University of Oxford, and CEPR) and Joe Kaboski (University of Notre Dame and CEPR) are responsible for the scientific direction of the programme.

The progress outlined in this report is for the 12-month period from 1 March 2023 until 29 February 2024 (henceforth termed “the review period”).

Summary supporting narrative for the overall score in this review

STEG has continued to perform well over the last year scoring an overall A in this review.

STEG held a total of five funding calls between March 2023 and February 2024 and received 709 Small research Grant (SRG) applications, 279 PhD applications, and 156 Large Research Grant (LRG) applications. STEG subsequently funded 23 Small Research Grants (SRGs), 28 PhD Research Grants (RGs), and 9 Large Research Grants (LRGs), and selected an additional 9 Ideas for Transformation (I4Ts) for funding. This additional 69 projects has taken the overall number of projects to 207. This has exceeded initial expectations and should lead to a significant volume of research output in subsequent years.

STEG is beginning to deliver a significant body of research some of which is reaching the publication stage and significantly increase the number of STEG-funded outputs.
- STEG has published two new synthesis papers focused on insights from recent literature on structural transformation and on self-employment, micro-entrepreneurship, and development.
- STEG grants or partners have produced 18 new journal articles, exceeding expectations at this stage in the programme.
- STEG Pathfinding Papers and one of the synthesis papers were published following a full peer review process as a special Issue of the journal Oxford Development Studies.
- The number of working papers from STEG grants or partners has increased to 75. Most papers are still in development with their expected publishing of preliminary versions in the next reporting period.
- There are now 10 STEG Project Policy Briefs from grantees published on the STEG website.
- Two Ideas for Transformation Essays from LIC researchers have been published as letters or perspective pieces in respectable journals (Science and Outlook on Agriculture).
- VoxDev has published six columns based on STEG projects, and another two columns based on papers from the STEG Working Paper Series.
The increase in publications and expanding reach of STEG research is reflected in the 1,962 citations of STEG research that have been already achieved at a relatively early stage in the programme’s lifetime.

In addition to the working papers and policy briefs, STEG-funded projects are beginning to produce and share useful data sets. Three data sets published in the review period can be found here. To expand this public good, STEG has put in place plans to build a data repository that will bring together all STEG-funded publicly available data, as well as other data sources that are relevant to the field. We are discussing where best to hold these data sets long term.

STEG engagement with policymakers is also increasing. 56% of grants have direct links with policy makers and 36% of projects have already presented findings to policymakers at conferences. STEG continues to push researchers to think about policy engagement and build direct links with policy makers. The evaluation and selection of grant applications strongly considers the policy relevance and engagement aspects. It is anticipated that the reported policy engagement and influence of STEG funded projects will increase as more projects are finalised and research findings are validated. Often researchers delay engaging with policymakers until the results from their research are either published in journals or are considered robust. See section B below for research output examples.

During the year under review Doug Gollin presented on a panel about “Structural Transformation and Pathways to Growth” at the FCDO Economics Conference: Charting Pathways to Growth. Engagement activities with other organisations and institutions, such as the World Bank and IMF, have also been undertaken this year. Doug Gollin has also advised the Gates Foundation on incorporating macro-level research into their analysis on gender and growth. STEG expects that this relationship will develop into further collaboration in the coming year, whereby GATES fund calls using the STEG research process and network.

The programme is also looking to increase the number of researchers working on structural transformation issues. Funding calls reserved for PhD students have led to 32% of total grantees and 44% of principal investigators (see Annex B) being PhD students. From previous experience with PEDL, funding researchers at this early stage encourages them to continue pursuing a career in fields related to the programme. The majority (81%) of grantees continue to originate from North American and European institutions (see Annex B). However, the number of grantees based in Sub-Saharan Africa has increased slightly since the end of Year 3 from 9.2% to 9.5% while the number of principal investigators based in Sub-Saharan Africa has also increased slightly from 10.1% to 10.3%. Considering the tensions that exist between a push for localisation and the quality requirements in research this is a reasonable achievement. However, it is recognised that more needs to be done going forward. CEPR through GRP are in the process of bringing together their experience with capacity building and will be developing an overarching strategy as a means to push this agenda.

Major lessons and recommendations for the year ahead

STEG has not reviewed or commissioned new Ideas 4 Transformation (I4Ts) as quickly as originally planned. STEG should review the value of continuing the I4Ts under the GRP in the context of the capacities of the team and contribution of the outputs from past I4Ts.

STEG should seek to build on its capacity building activities that feed into grant giving. The success of the matchmaking efforts under the PEDL programme offers some guidance and the increased emphasis on expanding and enriching the programme’s networks in Africa under the GRP presents further opportunities for the programme to develop some of the relationships established this year.

STEG should pursue the policymaker engagement, research and dissemination opportunities that have been identified this year. In particular, the relationships with networks either based in or focused on Africa should be further developed.

STEG should continue with in-person events where feasible and appropriate, recognising that online events are best suited to particular engagement and capacity building activities.

As STEG is incorporated within the GRP, the GRP should undertake a detailed examination of its localisation and capacity building approach developing more strategic approach to this important agenda. The GRP should report on this in the new year. In line with previous recommendations, STEG should also explore scope for its partners and wider network to help organise in-country events with the aim of connecting grantees and policymakers. As new research is being produced and formalised in academic papers, policy briefs, and other formats, accessing these networks is a high priority.

As the STEG programme matures and research funded under the programme expands, STEG should seek to more strongly emphasise dissemination of policy relevant research. This dissemination should be considered in the broader integration of the programme into the GRP and the potential leveraging opportunities that arise from this integration and the relationships with the other programmes under the GRP.

With the increased volume of and emphasis on research outputs from the grants awarded in the programme’s first phase, STEG should continue to proactively seek opportunities for the production of synthesis papers (including VoxDevLits) targeting key STEG themes and cross-cutting themes.

STEG, along with the other programmes under the GRP, should seek to integrate additional indicators relating to the gender focus of projects into the new GRP logframe. Of note here are the ongoing discussions with the Gates Foundation for STEG to take on a Gates project on Women’s Work in Markets of the 21st Century.

Finally, the increased volume of STEG activities means that the Research Directors should seek to continue their moves towards assigning new leadership roles in order to delegate some of their tasks. This gives opportunities to get more people involved and expand leadership in the community of scholars that STEG is contributing to the growth of. For Phase 2 of STEG there should be a move to reorganise and bring new leadership into the themes and Academic Steering Committee.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The current theory of change for STEG was updated at the end of the inception phase in February 2021 and remains valid. A summary is provided here.

Low-income countries follow a wide range of strategies to achieve structural transformation, but knowledge of the effectiveness of these strategies is limited. These constraints arise from several factors:
1. While there has been a rapid growth in the literature on structural transformation, at least until recently it has not been as active an area of research in developing countries: we need to encourage more researchers working on the theory and empirics of transformation to extend their work to low-income countries.
2. While there has been progress in collecting new information, evidence on patterns of transformation and on the effectiveness of transformation policies is still limited: we need to gather more evidence on these issues and make it more widely accessible to researchers and policymakers.
3. While there is much more to be learned about both structural transformation and transformation policies, existing research remains relatively inaccessible, and so key development actors are not aware of what we do know about transformation. We need to make the existing stock of knowledge more accessible to policymakers in low-income countries (as well as other development actors). We also need to focus researchers’ attention on what we should – but do not – know.

STEG’s assumption is that if each of these constraints are successfully addressed, STEG’s Outcome will be realised: a new understanding of: (i) the process of, and (ii) options for enhancing structural change, productivity, and growth in low- and middle-income countries.

In the longer term, achieving this Outcome will help achieve STEG’s desired Impact: that developing country governments, NGOs and the private sector design and implement strategies, policies and programmes that better facilitate productivity gains, structural change, and sustained growth.

STEG identifies four pathways in its theory of change:
Assess and synthesise existing knowledge:
STEG will deliver syntheses of existing knowledge via three outputs:
- Pathfinding Papers: full-length reviews on selected topics identified as important by stakeholders (researchers and policymakers), and where a sufficient body of research exists;
- Pathfinding Paper Policy Briefs: summaries of the full-length reviews that focus on the policy lessons from the body of research and are more accessible to policymakers and non-specialists;
- Virtual Course on "Key Concepts in Macro Development": aimed at doctoral and post-doctoral students, the course is in effect a synthesis of existing knowledge about structural transformation.
Create new and relevant knowledge via open calls for research:
A series of open research calls focused around, but not exclusively, on the STEG research themes will increase the quantity and quality of new research on structural transformation and its relevance to low-income countries. STEG funding will also help build a research community by increasing the number of existing and rising scholars across a range of countries engaged in work on structural transformation in low-income countries and enabling them to interact and exchange ideas.
Create new and relevant knowledge via research by consortium members:
The partners in the STEG consortium have (modest) budgets to fund new research by their own research staff. This offers the opportunity to STEG to fund the work of other organisations specialised in certain areas and methods of structural transformation.
Ensure effective research uptake:
Synthesis outputs produced by STEG, and the new knowledge generated through the open calls for research and the research by consortium partners must reach relevant policymakers if policy is to be affected. Several steps will be taken:
- Dissemination: publication and presentation of STEG output (new research and synthesis pieces) in academic journals, on the programme’s website, on research-to-policy portals such as VoxDev, and in direct meetings between researchers and policymakers.
- Partnerships: introduce STEG to related organisations and ensure awareness of the programme’s goals and work plans while expanding the pathways of impact for STEG research and avoiding duplication of work that may be well supported elsewhere;
- Project policy engagement: support links between researchers and policymakers using the decentralised model pioneered by PEDL, in which both incentives and support for policy engagement are provided.
- Existing evidence-informed discussions: utilise established fora for dialogue set up by organisations such as ACET’s African Transformation Forum and Pan Africa Coalition for Transformation.

The pathways to achieving outcome and impact laid out in the theory of change are still valid. The programme’s experience over the last four years suggests that these pathways are effective and remain relevant. Although no new evidence has arisen that would prompt a change to the existing pathways or the development of new pathways, it should be noted that in the context of the STEG being incorporated into the GRP in the next year the programme will sit within the new GRP Theory of Change and it will derive its intended outcome and impact indicators from the new GRP business case.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The logframe outcome statement is “developing country governments, NGOs and the private sector design and implement strategies, policies and programmes which better facilitate productivity gains, structural change and sustained growth” indicated by “number of strategies, programmes and policies in target countries influenced by research funded under STEG.” This is a longer-term objective for the programme to achieve as projects translate their output and research activities into policy impact.

However, STEG projects are already strengthening relationships with policymakers and beginning to influence policymaking. First, during Nicola Limodio’s Large Research Grant project in Rwanda, Financial Technologies and Credit Markets in Africa, connections were established with the Rwandan central bank which helped guide discussions on how leveraging mobile internet technology can drive financial inclusion and land reform. Research from the LRG demonstrates that mobile internet facilitates easier and more widespread access to banking services, enabling a transition away from microfinance institutions. The research further highlighted the crucial role of mobile internet in driving land title reforms. The improved communication and data access provided by mobile internet allowed for more efficient and transparent land registration processes. These reforms, stimulated by mobile internet access, strengthened property rights, making it easier for individuals to use land titles as collateral for mortgages and collateralized loans through the creation of a digital mortgage registry, thereby enhancing credit availability. Preliminary results suggest that this has fostered the development of a real estate market.

Second, Verena Wiedemann’s PhD Research Grant, The Effect of Internet Upgrades on Domestic Market Integration in Kenya, examines how improvements in internet infrastructure affect domestic firm-to-firm trade and firm dynamics in Kenya. Research findings funded by STEG and PEDL were used as performance indicators for direct budget support by the World Bank to the Government of Kenya. To measure performance on trade improvements, two indicators were included. The first measures integration with international markets, based on a figure from a World Development paper funded by PEDL. The second focuses on domestic market integration, specifically the extent to which counties within Kenya are trading with each other and is derived from the paper supported by STEG. The idea is that future policies will aim to reduce trade barriers within the country, with the ultimate goal of improving the proposed measure on trade integration beyond current trends.

Third, Bruno Conte’s Small Research Grant, Climate Change and the Regional Lake Economies of Sub-Saharan Africa: Analytical Framework, Predicted Economic Effects, and Policy Implications, impacted the policy world through discussions and debates following Conte’s presentations in policymaking institutions. These conversations emphasized the importance of relaxing land conversion frictions in rural settings (e.g., fostering competitive land markets, overcoming social norms associated with land (mis)allocation in rural villages) to enable smoother adaptation to climate change. This new dimension adds to the project's current focus, which was initially more centred on relaxing trade and migration frictions. By combining these three sets of policy tools, the adaptive capacity of these economies in the face of climate change can be significantly enhanced.

A second outcome for STEG is the number of citations of papers funded by STEG. This provides a good indication of the awareness of STEG-funded research in the academic field but also in the policy sphere. Research output that is more widely discussed and distributed is more likely to be known to policymakers. STEG has significantly surpassed the high milestone for citations with 1,978 citations across 130 papers that cover STEG-funded research carried out by grantees and researchers at our partner institutions, as well as the ten initial 2021 pathfinding papers.

As the STEG programme continues to mature, with even more projects moving from research to outputs, there are likely to be significantly more examples of STEG-funded research influencing and impacting strategies, policies, and programmes. Furthermore, the production of working papers and the transition to journal articles is likely to accelerate in the coming year as more projects complete.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The programme has matured and is starting to produce outputs. Economic issues and questions around structural transformation continue to remain relevant to FCDO’s policy engagement and interest across the breadth of low-income and lower middle-income countries. The UK Government has committed to a mission to drive economic growth, with a focus on accelerating economic development that is climate and nature compatible, sustained and delivers opportunity by unlocking human potential. STEG is well placed to deliver the evidence that will help to guide this. Recent events including the COVID-19 pandemic and emergence of AI have heightened the interest in and need for new evidence on structural transformation.

STEG has made good progress and is delivering the expected outputs according to the contract. The programme remains relevant and good value for money. The incorporation of the programme into the wider GRP will allow for the leveraging of more opportunities and synergies across the different programmes that make up the GRP.

## C. DETAILED OUTPUT SCORING

Output Title	High-quality, policy-relevant research on productivity, structural change and economic growth
Output number:		1	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress
1.1 Number of Small Research Grants (SRGs) awarded in open calls that meet the quality standards set by the Initiative.	L=95, M=100, H=105	92 (up from 69 last year)
1.2 Number of PhD Research Grants (PhD RGs) awarded in open calls that meet the quality standards set by the Initiative.	L=60, M=65, H=70	70 (up from 42 last year)
1.3 Number of Larger Research Grants (LRGs) awarded in open calls that meet the quality standards set by the Initiative.	L=22, M=25, H=27	27 (up from 18 last year)

Briefly describe the output’s activities and provide supporting narrative for the score.

STEG has scored an A for this output. STEG held a total of five funding calls between March 2023 and February 2024 including two Small Research Grants (SRGs) Calls, two PhD Research Grants (PhD-RG) Calls, and one Larger Research Grants (LRG) Call.

This year STEG received and reviewed 709 SRG applications, 279 PhD applications, and 156 LRG applications, subsequently funding 23 SRGs, 28 PhD RGs, and 9 LRGs. This exceeds the high milestone for each of LRGs and PhD RGs but scores low for SRG. At the PMG meetings during the year, it was decided to prioritise funding PhD calls over SRGs as overall numbers were limited by the budget available.

STEG continues to generate a significant interest among researchers, attracting both new and established academics.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The logframe was updated according to last year’s review, as well as feeding into the new GRP logframe.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from last year’s AR were:

- STEG has recognised the high fixed time costs of holding so many funding calls during the year. This is largely related to the coordination of the evaluation process. STEG should explore holding fewer larger calls during the year ahead, with the expectation that the same number of high-quality applications will be submitted given demand for grant funding is still high.
- It has become evident during the year that the projects funded through SRGs, and PhD RGs are taking longer to complete than the 12-month timeline than had originally been assumed. STEG should look to extend the contract length for these programmes going forward and monitor progress. STEG should review how this will impact the generation of research outputs and how it will impact the logframe indicators and amend accordingly.

In response to last year's recommendation STEG reduced the number of calls it ran this year. However, the high volume of applications received has stretched the capacity of the STEG Research Officer to process them. To deal with this STEG engaged a Research Assistants at its partner Notre Dame to assist in the early stages of the evaluation process. STEG is in the process of reviewing its evaluation process in order to identify areas of improved efficiency.

In line with last year’s recommendation STEG looked at extending the standard duration of SRGs and PhD grants to more than 12 months. However, it is not clear that extending the timeline will reduce the number of extension requests as there is a risk that it may reduce the impetus on researchers to commence and complete their research in a timely manner. Moreover, this modification to the management cycle of the grants will increase the administrative workload on CEPR. A final decision on the approach will be made in the coming months.

In the selection of projects, STEG continues to try and fund researchers either based in lower-income countries or those studying and starting their careers abroad but from lower-income countries. Quality thresholds, however, mean that there are often tensions. STEG similarly considers the gender composition of research teams selected for funding. Going forward metrics associated with this will be added to the GRP logframe for monitoring purposes.

STEG remains committed to building local capacity in the global South for research on growth and transformation, but to this point it has resisted holding special funding rounds that target LIC researchers. The STEG team feel that there are some high-quality proposals from LIC-based researchers that can be funded through the regular call process, and that this is a preferable mode of operation. STEG continue to track and monitor the proportion of LIC researchers in the pool of STEG grant recipients, and it remains a criterion that the funding panels to carefully consider.

Lessons learned and recommendations:

STEG should seek to expand its capacity building activities that feed into grant giving. The success of the matchmaking efforts under the PEDL programme offers some guidance and the increased emphasis on expanding and enriching the programme’s networks in Africa under the GRP presents further opportunities.

Output Title	Activities which build and maintain attention and momentum for the STEG programme's research findings
Output number:		2	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress
2.3 Conferences with participation by policymakers in which STEG-funded research is presented	L=70, M=100, H=120	133 (up from 56 last year)
2.4 Number of projects engaging with policymakers	L=70, M=80, H=90	87 (up from 67 last year)
2.5 STEG Research Notes/Policy Briefs	L=36, M=40, H=44	10 (up from 0 last year)
2.6 VoxDev/VoxEU columns	L=8, M=11, H=14	8 (up from 2 last year)
2.7 Policy papers/briefs	L=5, M=6, H=7	5 (up from 3 last year)
2.8 STEG-funded events and workshops	L=40, M=45, H=50	46 (up from 35 last year)
2.9 STEG stakeholder engagement/events (annual target)	L=5, M=6, H=7	7 (achieved 6 last year)

Briefly describe the output’s activities and provide supporting narrative for the score.

STEG has achieved an A for this output. STEG has met or exceeded the high target in two of the seven indicators, exceeded the medium target in two indicators, and met the low target in two others and not met the low target on one indicator.

STEG projects have exceeded expectations in relation to building and garnering attention for STEG-funded research. STEG-funded research from 56 projects has been presented at a total of 133 conferences and/or workshops attended by policymakers. Most of these projects are those funded in the initial calls in late 2021, where results and findings are more developed. In addition to these presentations, a further 87 projects are engaging with policymakers, with 270 individual policymaker engagements noted. Several researcher projects anticipate that these engagements will lead to policy impact in the next year. This significantly exceed the high milestones for both presenting at policy-relevant conferences and engagement with policymakers.

The number of published STEG Research Notes (also known as STEG Policy Briefs resulting from STEG-funded projects) is below the lower target of the logframe. There are two reasons for this. First, a number of grants have been contractually extended, resulting in a delay in receiving their outputs. Second, engaging with policymakers and writing outputs for a broad audience typically occurs later in the research timeline. Feedback from grantees indicates that they prefer writing policy briefs or research notes only once their results are considered robust and their working papers are close to publication. It is expected that the number of published research notes will increase in the next year. Under the GRP, there will be focus on the dissemination of policy-relevant outputs from STEG, PEDL, and ReCIPE to broader audiences.

Eight VoxDev columns have been published in relation to STEG-funded research carried out by STEG’s partners at the University of Notre Dame and the University of Oxford. This meets the lower target of the logframe. We expect this number to increase in the coming year, given the introduction of the GRP and the synergies across the research programmes. One example can be found below.

How lumpy investments determine the effect of expanding financial services: Evidence from Uganda | VoxDev
(Joseph P. Kaboski, Molly Lipscomb, Virgiliu Midrigan, and Carolyn Pelnik)

The aggregate and individual impacts of expanding financial services, such as credit and savings, to the poor can depend greatly on the importance of high-yield, indivisible investments for these populations. When small investments pay low returns but large investments pay substantially higher returns due to the need to make lumpy or indivisible investments (e.g. a tractor as opposed to seeds or fertiliser), access to credit and savings can help poor households overcome barriers to making investments at a larger, more profitable scale. How important are these lumpy investments for the peri-urban poor, and what are the implications for the potential gains from expanding financial services? We explore these questions theoretically, experimentally, and quantitatively in our recent working paper (Kaboski et al. 2022).

The published VoxDev article can be found here.
This article is based on an external STEG Working Paper (written by STEG Head of Commissioning and Chair of the Academic Steering Committee, Joseph Kaboski).

STEG’s partner, the African Center for Economic Transformation (ACET), published a policy brief titled Does the Origin of Multinational Enterprises Matter? Findings from Ethiopia, Kenya, and Ghana. This brief benefited from valuable feedback received from seminar participants at the STEG-IGC Annual Conference in 2023. Another STEG partner, Y-RISE, also produced a policy brief aimed at explaining different theories of the role of microentrepreneurs in growth, and summarising research into different policies intended to help entrepreneurs.

STEG has funded a further eleven events over the past year, bringing the total to 46 since the start of the programme. This exceeds the high milestone set out for the year and highlights two key related points. The events for the year include:
- STEG/Tufts Workshop on Gender and Structural Transformation, November 2023.
- STEG Panel on The Emerging Agenda for Macro Development hosted by CEPR at the CEPR Paris Symposium 2023.
- ACET Brown Bag Session, February 2024. Virtual stakeholder engagement with a focus on Ethiopia, Ghana, and Kenya.
- Y-RISE along with the UNESCO Chair on Climate Change Resilience and Sustainability at Strathmore University and Kenya’s Energy and Petroleum Regulatory Authority (EPRA) held two policy conferences in Nairobi in the summer of 2023.

This year STEG’s Annual Conference was held jointly with NYU Abu Dhabi in January. The conference was well received and attended. Holding the conference in-person has significant positive benefits, and scheduling the theme workshops in conjunction with the annual conference maximized the spillovers. The conference was also streamed to an external audience to ensure accessibility. The two plenary days featured eight full-length presentations and six speed-round presentations on research at the forefront of the knowledge frontier. In addition, STEG organised an academic keynote from Yongseok Shin (Professor of Economics, Washington University in St. Louis) on Industrial Policy: Some Theory and Evidence and a policy keynote from Yaw Nyarko (Professor of Economics, NYU) on Technology and Development.

In conjunction with the STEG Annual Conference, STEG also held three theme workshops in Abu Dhabi and three theme workshops in Barcelona at Universitat Pompeu Fabra, each showcasing some of the recent work in the respective themes. Aligning the theme workshops with the conference in Abu Dhabi allowed for greater academic and policy attendance at the workshops. The additional three workshops were held immediately following the conference in Barcelona and were co-sponsored by a European Research Council grant held by the Institute of Political Economy and Governance.

STEG has continued to seek opportunities to engage with policy stakeholders and key academic stakeholders beyond the work of individual grants helping to ensure the programme’s Research Strategy remains relevant and responsive to research demands, increasing the awareness of the programme and disseminating its output, and contributing to capacity building activities. Stakeholder engagement has been significant over the past year with STEG meeting the high milestone. Several engagements are particularly worth noting:
- In June 2023, Doug Gollin presented the keynote address (titled “Sectoral, Structural, and Spatial Transformations: New Directions in Development Economics”) at the World Bank’s Annual Bank Conference on Development Economics.
- In autumn 2023 and early 2024, Joe Kaboski conducted discussions with the World Bank and IMF on developing a multi-sector growth model for use in the institutions. These discussions followed early conversations with the IMF in 2022. From these discussions, STEG, Big Lab, the World Bank, and the IMF are launching a joint project to develop this model in the next reporting period.
- In autumn 2023, Joe Kaboski had discussions with the World Bank regarding the development and use of a repository of data sets from STEG projects and other projects focused on structural transformation. These discussions have contributed to the development of STEG’s new data hub project, which will commence in the next reporting period.
- In November 2023, Doug Gollin and Joe Kaboski led a short course on Structural Transformation and Economic Growth for African scholars, doctoral, and master’s students at Makerere University in Kampala, Uganda. This course was also organised in conjunction with the Centre for the Study of African Economies. While at Makerere, Doug and Joe also held meetings with the Director of the Economics Department regarding potential collaborations around capacity building activities.
- In November 2023, Doug Gollin presented the keynote address (titled “Understanding Rural Economies in Africa: Fifteen Years of the LSMS-ISA”) at the 15th World Bank Living Standards Measurement Studies Conference. Alongside this event, Doug also met with the heads of the national statistical offices for Tanzania, Nigeria, and several other countries. Doug also met with Andrew Dabalen, Chief Economist for Africa at the World Bank, to discuss possible synergies with STEG.
- In December 2023, Doug Gollin also convened and chaired a STEG panel at the CEPR Paris Symposium on the future of development economics.
- During 2023 and early 2024, Doug Gollin was also engaged in conversations with the Gates Foundation on gender, structural transformation, and macro-level research.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During this year, the new logframe for the GRP was developed, which will include the indicators for STEG going forward.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from last year’s AR were:

- Following the end of Covid restrictions STEG should explore finding the right balance between in-person and virtual events. While events such as the STEG Special Lecture are well suited to an online medium, attendance at the STEG Theme Workshops was a little lower this year. These events may benefit from being held in-person in future years. STEG should explore the possibility of holding these workshops alongside the annual conference at NYU Abu Dhabi in early 2024. As research outputs increase STEG should also put and increased focus on developing policy papers and briefs.
- STEG should also explore scope for its partners and wider network (institutions such as ACET, IGC, and Y-RISE) to help organise in-country events with the aim of connecting grantees and policymakers. As new research is being produced and formalised in academic papers, policy briefs, and other formats, accessing these networks is a high priority.
- STEG has made efforts to improve the website and increased dissemination of new outputs via social media and its newsletters. STEG should consider whether, with increased output from projects, it may be suitable for the programme to have its own social media accounts, rather than posting through the CEPR account. This would reduce the size of the audience, although, the audience would be directly aligned to and interested in STEG. STEG should also review and update the website improving its functionality and searchability particularly with regard the research outputs.

This year, following the lessons and recommendation in the previous Annual Review, STEG has sought to balance between in-person and online events. Workshops for all the themes were held in-person in conjunction with the Annual Conference, and this improved attendance and engagement beyond previous online iterations. The events were also livestreamed on Zoom to allow for remote attendees to access the event). Where there is a significant benefit in reaching a wider audience, such as for the courses targeting graduates, STEG will continue to hold some events online.

STEG has sought to develop strategic relationships with organisations that may allow for the expansion of research, dissemination, and policy engagement activities beyond what has previously been achieved. In particular, discussions have been undertaken with the Centre for the Study of African Economies (CSAE) and the African Research Universities Alliance (ARUA) network to explore options for collaboration targeting African policymakers and scholars.

Based on feedback from STEG Advisory Group member Sarah Ssewanyana (Executive Director, Economic Policy Research Centre at Makerere University, Uganda), STEG is also exploring opportunities for directly organising an event with the Ugandan Ministry of Finance or a senior policy event in collaboration with the African Economic Research Consortium (AERC). Regarding possible capacity building activities, STEG is also investigating the possibility of organising a short graduate training programme with STEG researchers teaching students and faculty at Makerere University. All of these activities will be taken forward in the context of the wider GRP review and development of its new localisation and capacity building strategy.

Additionally, discussions remain ongoing with the World Bank and IMF relating to a possible STEG project on producing a multi-sector growth model toolkit that can be disseminated for use through both institutions and their clients. It is expected that this project and the discussions with the Gates Foundation relating to gender and macro-level research will further develop in the next period.

This year there has been a significant increase in the outputs produced with STEG support (see section below). However, in anticipation of STEG incorporation into the GRP, the plans for improving the STEG website and consideration of the use of social media has been postponed. This decision was taken to ensure that any modifications to the STEG website and social media are in line with the planning for the GRP as whole, and thus not made redundant soon after implementation.

Lessons learned and recommendations:

STEG should continue to pursue in-person events where feasible and appropriate, recognising that online events are best suited to particular engagement and capacity building activities.

In the context of the incorporation of STEG into the GRP, the GRP should review the structure of its programme Partners to build on learnings from STEG and PEDL and ensure any future partnerships align with the programme’s goals and thematic focuses under the GRP. In line with previous recommendations, STEG should also explore scope for its partners and wider network to help organise in-country events with the aim of connecting grantees and policymakers. As new research is being produced and formalised in academic papers, policy briefs, and other formats, accessing these networks is a high priority.

STEG should pursue the policymaker engagement, research and dissemination opportunities that have been identified this year. In particular, the relationships with networks either based in or focused on Africa should be further developed in order to better reach policymakers and to facilitate capacity building activities.

Output Title	Peer-reviewed and published outputs
Output number:		3	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress
3.1 Number of podcasts (annual target)	L=2, M=3, H=5	2 (achieved 5 last year)
3.2 Number of videos (annual target)	L=1, M=2, H=3	3 (achieved 3 last year)
3.3 Number of peer-reviewed articles (only) produced by projects funded under the Initiative	L=5, M=6, H=7	18 / (up from 2 last year)
3.4 Number of working papers produced by projects funded under the Initiative	L=20, M=26, H=32	75 (up from 14 last year)
3.5 Number of synthesis and evidence papers	L=4, M=5, H=6	4 (up from 2 last year)
3.6 Number of Ideas 4 Transformation papers	L=10, M=12, H=14	4 (up from 3 last year)
3.7 Proportion of written outputs that address each of STEG's research themes	L=>5%, M=>10%, H=15% for each research theme	Greater than 15% for 5 themes; 9% for Political economy and public investment
3.8 Proportion of written outputs that address at least one of STEG's cross-cutting issues	L=20%, M=25%, H=30%	39% (up from 33%) / Gender = 18% | Climate Change and the Environment = 5% | Inequality and Inclusion = 16%
3.9 Percentage of projects involving LIC researchers as PIs/Co-PIs	L=5%, M=8%, H=10%	11%

Briefly describe the output’s activities and provide supporting narrative for the score.

STEG has scored an A for this output. STEG has exceeded or met the high expectations of the logframe on six out of nine indicators, met the low expectations on two indicators, and has not met the target for one indicator.

As a part of the STEG Annual Conference 2024, CEPR’s podcast producer for VoxTalks, Tim Philips, recorded a series of seven podcasts under the title Conversations for Transformation that investigated some of the most important new research in economic development related to structural transformation, with particular emphasis on Sub Saharan Africa and South Asia. While these podcasts were recorded in January 2024, at the STEG Annual Conference, they were released after the end of the reporting period in March 2024 so are not counted against the logframe targets. This year VoxDev released two podcasts (low target) on STEG topics which have been included: Micro and macro research: Bridging the divide with Joe Kaboski and Francisco Buera, and Macroeconomic development: An emerging agenda with Doug Gollin and Paula Bustos, with STEG releasing three podcasts in the current reporting period. This year, STEG published three groups of videos representing recordings of the STEG Annual Conference and the two groups of Theme Workshops. This meets the high target for videos.

During the year there has been a significant increase in the number of journal articles produced with STEG support significantly exceeding the high target. In particular, this year marks the first journal article accepted for publishing from a STEG grant with an LRG from the first round expected to be published in mid-2024.

In addition to the above journal articles, this year STEG Pathfinding Papers were published as a Special Issue of the journal Oxford Development Studies. The Special Issue included an introduction on New Views of Structural Transformation by STEG leaders Doug Gollin and Joe Kaboski (noted below as a Synthesis Paper), and the below articles. As these articles were originally Pathfinding Papers, they are excluded from the logframe indicator on peer-reviewed published articles.
- The role of labor market frictions in structural transformation by Kevin Donovan and Tood Schoellman. Link.
- Agricultural productivity and structural transformation: evidence and questions for African development by Doug Gollin. Link.
- Financial frictions, financial market development, and macroeconomic development by Joe Kaboski. Link.
- Political economy and structural transformation: democracy, regulation and public investment by Monica Martinez-Bravo and Leonard Wantchekon. Link.
- The role of micro data in understanding structural transformation by David Lagakos and Martin Shu. Link.
- Perspectives on trade and structural transformation by George Alessandria, Robert C. Johnson, and Kei-Mu Yi. Link.
This year there have been 75 working papers that have been produced with STEG support, significantly higher than the high milestone of 32 for working papers. Part of the reason for this is that the STEG research is often able to use existing data as opposed to undertaking its own data f=gather as is the case with PEDL. This means that projects are able to more quickly move from approval to working paper to publication. Going forward logframe indicators will be amended to reflect this. Below are two examples of working papers produced during the year.

Paternalistic Discrimination (Nina Buchmann, Carl Meyer, Colin D. Sullivan)

This study combines two field experiments in Bangladesh with a structural labour model to define and test for paternalistic discrimination, the differential treatment of two groups to protect one group—even against its will—from harmful or unpleasant situations. The researchers observe real hiring and application decisions for a night-shift job that provides safe worker transport home at the end of the shift. In the first experiment, they vary employers’ perceptions of job costs to female workers by experimentally varying information about the transport but holding taste-based and statistical discrimination constant. Not informing employers about the transport decreases demand for female labour by 22%. However, employers respond significantly less to a cash payment to female workers that would allow them to purchase safe transport themselves. This suggests that employers paternalistically prevent women from making their own choices. In the second experiment, not informing applicants about the transport reduces female labour supply by 15%. In structural simulations that combine the results of both experiments, eliminating paternalistic discrimination reduces the gender employment gap by 24% and increases female wages by 21%.

A Policy Brief from the STEG grant can be found here.
Nina Buchmann won the Daniel Cohen Award for her work on this project at the PSE-CEPR Policy Forum in 2024. The press brief can be found here.

Bringing Work Home: Flexible Arrangements as Gateway Jobs for Women in West Bengal (Lisa Ho, Suhani Jalota, Anahita Karandikar)

Several hundred million women want a job but are out of the labour force, often because available opportunities are incompatible with traditional norms about their household roles. In a field experiment with 1,670 households in West Bengal, this study offers flexible, short-term data entry jobs which meet households where they are in terms of expectations on women’s domestic responsibilities. The paper finds three sets of results. First, job flexibility more than triples take up, from 15% for an office job to 48% for a job that women can do from home while multitasking with childcare and at the hours they choose. Second, working from home reduces worker efficiency. Third, flexible jobs act as a gateway to outside-the-home jobs for women initially out of the labour force: experience with flexible jobs makes women more likely to accept inflexible work several months after the initial intervention. This gateway effect may be explained by changes in attitudes about appropriate behaviour for men and women: flexibility makes a larger difference to the labour supply of women who hold more traditional pre-intervention attitudes, and work experience in turn shifts the gender attitudes of these women and their children to become less traditional. Thus, flexible work arrangements can both attract women to the labour force and provide a gateway to less flexible jobs.

A Policy Brief from the STEG grant can be found here.
Lisa Ho presented her work on this project at the CEPR Development Economics Annual Symposium in 2024.

In addition to working papers directly funded by STEG, the programme also introduced the STEG working paper series in June 2022. This series was created to exclusively feature leading research in the fields of structural transformation, productivity, and growth. Working papers that have been produced through STEG-funded projects are included in the series and the programme also welcomes papers from researchers directly affiliated with STEG as well as papers that have been presented at STEG-funded events including our Annual Conference and Theme Workshops. Since its inception, there has been great interest from researchers and, to February 2024, 74 papers have been released in the series. The series also provides an opportunity for less established researchers to disseminate their work.

Synthesis papers. Two papers have been written this past year, bringing the total to four and meeting the low milestone:

Synthesis paper – New Views of Structural Transformation: Insights from Recent Literature – Douglas Gollin, Joseph Kaboski

This paper describes an emerging literature in economics that aims to merge macro issues of structural change and growth with micro data and analysis. This literature focuses on a set of related patterns of change that accompany the processes of growth and development. Traditionally, the focus has been on industrialization – and more broadly the reallocation of employment and economic activity from agriculture to manufacturing and services. The new literature considers a broader set of transformations: from rural to urban, from home to market (and from market to home), from informal to formal, and from self-employment to wage work. Drawing on new data sources, including micro data and administrative records, the literature tries to understand the complex interactions of a broad set of market failures, policy distortions, and impediments to the growth process. In broadening the understanding of structural transformation – to encompass processes beyond industrialization – this literature opens the door to a richer understanding of the processes of growth and a wider set of potential levers for policy.

NOTE: This synthesis papers was included as the Introduction to the Special STEG Issue of the journal Oxford Development Studies.

Synthesis paper – Self Employment, Micro-Entrepreneurship, and Development – Austin Dvisa, Eric Hsu, Mitchell VanVuren

Firms in low- and middle-income countries tend to be disproportionately small in size compared to firms in high income countries, driven by high rates of self-employment. What explains this empirical fact? The paper discusses existing evidence and promising paths for future research. They begin by summarising existing work investigating the role of capital constraints as a primary explanation. They then discuss theories beyond credit constraints, such as monitoring costs and demand structure, that could lead to small firm sizes. Finally, the researchers suggest directions for future work that expands on the rich literature studying the effects of interventions that aim to reduce barriers to firm growth. They identify frictions in managerial labour markets as another interesting direction for research focused on barriers to growth among SMEs. However, they also suggest research directions that examine the possibility that micro-entrepreneurship may be an optimal response to frictions that may not directly affect SMEs but make finding wage labour more difficult.

Further synthesis and evidence papers are planned for Year 5 including potential VoxDevLits. One VoxDevLit on multinational corporations and foreign direct investments is currently being produced by Nina Pavcnik (as the Senior Editor) and is expected to be published in the next reporting period.

The Ideas for Transformation (I4T) initiative, however, has not met with expectations. I4T was an experimental initiative under STEG which has also been trialled by the IGC. However, this year STEG has only produced one I4T, bringing the total to four, which is below the lower target of the logframe. Of the four published Ideas for Transformation essays, two have been published in respectable journals:
- From I4T 115: Mkondiwa, M., Kabambe, V., & Ngwira, A. (2024). “Good fences make good neighbors? Exploring potential transformative impacts of local governance towards livestock fence-in rights in Malawi” Outlook on Agriculture. Volume 53, Issue 2, pp 106-112. Link.
- From I4T 211: Gupta, I. (2024) “India's services-driven growth excludes women” Science. Volume 383, Issue 6683, pp. 598-599. Link.
During the current review period, STEG has contracted nine additional I4T grants - three under I4T 3 and six under I4T 4. These essays have not yet been published on the STEG website, as they are still under review to determine if they meet the required quality and relevance standards. As noted in the previous Annual Review, STEG has not reviewed or commissioned new Ideas for Transformation (I4Ts) as quickly as originally planned. It was recommended that STEG evaluate the value of continuing the I4Ts under the GRP, considering the team's capacities and the contributions of past I4Ts.

STEG has exceeded the high target of 15% for the proportion of written outputs addressing five of the six STEG research themes. The remaining theme (Theme 5: Political Economy and Investment) is addressed by 9% of the outputs, which is slightly below the median target. STEG has revised Theme 5 to emphasise the macroeconomic aspects of public finance and investment, in conjunction with the introduction of the GRP and the new ReCIPE initiative, which has a stronger focus on political economy. With a growing output population and Theme 5's revision, we expect thematic representation to balance in the coming years. Annex B shows a reasonably even thematic distribution of projects, which we expect to continue in future outputs. STEG has exceeded the high target of 30% for outputs addressing cross-cutting issues, with 18% of projects focusing on gender, 5% addressing climate change and the environment, and 16% tackling inequality. This demonstrates active engagement with these pressing global challenges.

The programme is also looking towards the future of the field. Funding calls reserved for PhD students have led to 32% of grantees and 44% of principal investigators (see Annex B) being PhD students. From previous experience with PEDL, funding researchers at this early stage encourages them to continue pursuing a career in fields related to the programme. The majority (81%) of grantees continue to originate from North American and European institutions (see Annex B), and 11% of grantees (PIs and Co-Is) originate from institutions based in low-income countries.

Currently, we do not have data on the percentage of projects involving female PIs and Co-Is. In the Annual Survey for the current reporting period, STEG did not ask researchers to provide information on their gender. However, in future Annual Surveys, STEG will include this question to gather further data on gender and will include an additional indicator in the GRP logframe.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following the recommendations from last year’s report, STEG has introduced two new logframe indicators, on the percentage of projects involving female PIs/Co PIs, and the percentage of projects for which the PI/Co-PI is based at an institution in an LIC country. These indicators will be taken forward in the GRP logframe which is currently being refined.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from last year’s AR were:

- STEG should be more proactive and quicker to seek opportunities for and commissioning synthesis and evidence papers. One VoxDevLit currently being produced s a paper on foreign direct investment by Nina Pavcnik.
- STEG has not reviewed or commissioned new I4Ts as quickly as originally planned. This has partially been a result of a lack of capacity for the STEG Research Officer. With STEG having recently hired a Research Intern, this should help to speed the progress on the review of existing I4Ts and the evaluation of closed I4T funding calls.
- STEG should develop indicators that pick up the good work they are doing on gender (both research areas and researchers) and with LIC researchers.
- The logframe milestones should be reviewed and updated.

The publication of the STEG Pathfinding Papers in the Oxford Development Studies journal provided an opportunity for the STEG leadership to review recent literature on structural transformation, with the papers available on both the STEG website and through the journal. The VoxDevLit on multinational corporations and foreign direct investment led by Nina Pavcnik is still being produced and the publication is expected in late 2024.

While the publication of two I4Ts is a positive step for this type of project, there are a number of issues with the I4Ts that remain. On the research side, the quality of the I4T essays remains inconsistent and developing some of the essays requires multiple rounds of editing by the STEG Research Officers. On the management side, the I4Ts are very time consuming for the small size and impact of the expected output and the capacity of the STEG Research Officer is better focused on STEG’s other more productive aspects. STEG will review the value of continuing the I4Ts under the GRP.

In the context of the programme’s incorporation into the GRP, the logframe was reviewed, updated, and merged with the logframes for the other GRP programmes. The update to the programme was based around the programme’s progress and expected shift to focus more on finalising and disseminating research from the grants over the first phase and on policy engagement. As such, the new logframe for the GRP is based around the structure of the PEDL and STEG logframes. This refined GRP logframe will include indicators relating to Southern-led projects, female researchers, and capacity building activities.

Lessons learned and recommendations:

As noted in the previous Annual Review, STEG has not reviewed or commissioned new Ideas 4 Transformation (I4Ts) as quickly as originally planned. STEG should review the value of continuing the I4Ts under the GRP in the context of the capacities of the team and contribution of the outputs from past I4Ts.

As the STEG programme matures and research funded under the programme expands, STEG should seek to more strongly emphasise dissemination of policy relevant research. This dissemination should be considered in the broader integration of the programme into the GRP and the potential leveraging opportunities that arise from this integration, as well as the relationships with the other programmes under the GRP.

With the increased volume of and emphasis on research outputs from the grants awarded in the programme’s first phase, STEG should continue to proactively seek opportunities for the production of synthesis papers targeting key STEG themes and cross-cutting themes.

STEG, along with the other programmes under the GRP, should seek to integrate additional indicators relating to gender and capacity building into the new GRP logframe.

## D: VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case
Value for money (VfM) is as outlined in the business case and CEPR programme proposal. VfM was a key factor in determining the contract award in line with the business case. Performance and costs are in line with expectations as set out in the contract. While it has been necessary to reduce budget allocation in the early stages of the programme, this will not affect the VfM over the programme’s lifetime. AS GRP is developed guidelines and metrics will be developed across the GRP research areas of PEDL STEG and ReCIPE.

Economy

STEG is assessed as good.

CEPR has built on recommendations from previous reviews for the use of “country coefficient rates” as a fair and reasonable way of calculating the appropriate rates for researcher remuneration. The purpose of the country coefficient is to ensure that during the negotiation process of both ERGs and MRGs, salary costs deemed to be too high are recalculated at an appropriate rate (based on actual average salaries). For many of STEG’s projects this is not an issue as researcher salaries are paid at the rate at which the researcher is paid by their institutions (and thus are effectively a buy-out of time) and are capped at £20,000 per researcher per year.
CEPR has developed maximum rates for the remuneration of Principle Investigators (PIs) and their research team members (typically Co-Investigators, Post-Doc Research Assistants, PhD Students, Field Managers, Field Assistants and Enumerators) or stipends for PhD students. These rates have been calculated in line with those typically allowed under UK Research Council rules and by using both EUROSTAT country indices to adjust fees to the corresponding country and applying budget data from past grants, which in turn helps to determine equivalent salary rates that can be supported by the grants in those countries in which the projects are being conducted.
STEG has tight guidelines for the eligibility of costs and how grantees report financially
Staff salaries and research stipends for Principal Investigators and research team members are subject to regular review. These rates are evaluated on the level of the researcher as well as the country they are working in. Research personnel are eligible costs under STEG to the extent that the research staff are directly involved in providing services to the project. STEG monitors travel and subsistence costs and ensures that items that relate to travel, accommodation and subsistence are in line with UK Gov subsistence rates. In line with VfM, it is expected that researchers and institutions provide their own IT equipment for the duration of the project.

Efficiency

Efficiency is assessed against two criteria: balanced portfolio and efficiency in delivery. STEG is assessed to be good.

Balanced portfolio: As detailed in the logframe output 3.7 STEG is able to maintain a good allocation of research across all of its main areas as well as addressing key cross cutting issues (indicator 3.8).

Efficiency in delivery: This element is assessed against, the delivery of the intended outputs within budget and with the anticipated timeframe. STEG is assessed to be good.
STEG is performing well on key metrics such as journal articles and working papers through effective funding of its partners. STEG is exceeding the logframe targets for the number of research outputs and doing this in a manner that engages with policy makers (see output 3.3, 3.4 and 2.4). Furthermore, STEG funding has been leveraged by the University of Notre Dame to raise donor funds for the BIG Lab at Notre Dame (https://al.nd.edu/news/latest-news/notre-dame-launches-big-lab-to-address-global-poverty-and-economic-inequality/).

Effectiveness

Effectiveness is assessed against three criteria: Good practice in research and programme design; Progress against the LogFrame indicators, based on an overall assessment of whether these are mostly being achieved at the high/ medium /or low levels, and; Early evidence of the emergence of impacts. STEG is assessed as good.

Best practice: STEG is assessed as having performed well against this criteria.
STEG-funded projects are engaging with many policymakers, both directly and through conferences and workshops. The STEG application process puts a strong weight on policymaker engagement with grantees who are reminded and surveyed regularly to undertake these engagements. This has helped to spread awareness of STEG-funded projects at a low cost, leading to greater policy impact and effectiveness.

Progress against the logframe: STEG has scored an A across each of the 3 output indicators exceeding the high level for a significant number of the indicators.

Impact: It is too early to assess STEG’s impact, but the necessary ingredients are in place to ensure that this is delivered.

Equity

STEG is assessed as adequate.

The focus of the STEG research is to reduce poverty through supporting the process of structural transformation facilitating LICs to grow and generate jobs. In this respect the programme has equity considerations at its core.

Second STEG also gives significant consideration of gender implications throughout the research with over 39% of the research projects looking at gender dimensions (above indicator 3.8 high target).
STEG also looks to identify and support LIC and female researchers. To date 11% of the projects involve LIC researchers as PIs/Co-PIs. STEG is looking to develop metrics for female researcher in the new GRP.

Assessment of whether the programme continues to represent value for money
STEG is performing well, exceeding the original logframe indicators set out in the original business case. STEG is developing a network of researchers working on structural transformation and has developed outputs (such as the STEG working paper series) that were not envisaged at inception. STEG is beginning to establish good relationships with policy makers. STEG continues to represent good value for money.

E: RISK

Overview of risk management

The overall risk rating of the programme is currently Minor. STEG formally reports risks annually to FCDO. During the year, risks are reviewed, discussed and ratings adjusted appropriately at the quarterly programme management group meetings between STEG and FCDO.

Strategy & Context - risk rating is minor. The main risk of the programme is if the research outputs proved to not be policy relevant and thereby failed to make any significant impact on policy. However, the end of COVID has meant that direct engagement with policymakers in LICs is possible and policymakers have been prevalent at both the STEG annual conference and in engagements with the STEG partners. Discussions regarding a greater emphasis under the GRP on in-person engagement with policymakers in Sub-Saharan Africa and South Asia either directly or via partner networks remain ongoing.

Although the impact of COVID has decreased significantly, the programme continues to feel some ripple effects of the pandemic, e.g. previous delays to projects have pushed back the production of working papers. However, these effects continue to reduce with time.

Financial and Fiduciary – risk rating is minor. As a result of FCDO funding cuts in previous years STEG funded fewer research proposals than originally anticipated. However, the incorporation of the programme into the GRP will allow STEG to deliver fully against its original objectives and extend beyond them to meet the new objectives under the GRP.

Policy & Programme Delivery – risk rating is minor. STEG is now a well-established programme with strong governance and research commissioning processes in place.

Safeguarding – risk rating is minor. CEPR promotes an organisational culture that prioritises safeguarding to ensure it is safe for those affected to come forward. Appropriate policy and processes are in place.

Reputational – risk rating is minor. Research activities and topics pose little or no reputational risk.

People – risk rating is minor. Experienced management teams are in place at both FCDO and CEPR.

The programme continues to operate with FCDO’s risk appetite. The full risk matrix can be seen at Annex G.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

This review focuses on the 12 months of the fourth year, March 2023 to February 2024.

STEG is governed by a Programme Management Group (PMG) including FCDO (SRO and programme manager), CEPR, and the scientific leads. The PMG meetings take place on (at least) a quarterly basis and are chaired by the CEO of the Centre for Economic Policy Research (CEPR). PMG meetings review progress, assess risks, and address any emerging issues. Aside from the more formal PMG meetings, FCDO, CEPR, and the scientific leads are in regular contact. Moreover, CEPR and the scientific leads have fortnightly videocalls. This management structure will remain in effect as STEG is incorporated into the GRP in the next year.

CEPR is responsible for the operational delivery of the programme, as a whole, in collaboration with five sub-contractors: University of Oxford, University of Notre Dame, the African Center for Economic Transformation (ACET), the Yale Research Initiative on Innovation and Scale (Y-RISE), and the Groningen Growth and Development Centre of the University of Groningen. CEPR has annual contracts with each sub-contractor who in turn supply a team of researchers, with some also providing data and event support. The sub-contractors report formally to CEPR on an annual basis, although the elements of the consortium are in continual contact on progress.

So far, the programme has been performing in line with expectations with all the project partners delivering as expected. CEPR’s oversight and management are good. While online events were popular and well attended during the COVID period, interest has now shifted back to in-person events. The STEG Annual Conference 2023 was successful with a strong level of interaction and attendance. The programme has been successful in launching new calls for proposals and awarding a large number of projects.

The programme is funded by FCDO through a contract with CEPR which includes a formal set of deliverables and payment schedule. CEPR invoices FCDO according to the contract schedule. To date, reporting and invoicing has been timely and according to the contract.

Towards the end of the Inception period, STEG was informed that it would face an invoicing cap for the financial years 2021-22 and 2022-23. Following this news, STEG submitted a revised budget based on the invoicing caps and lessons learnt from the inception period to FCDO in June 2021. In the context of the STEG programme being incorporated into the broader GRP, the budget for the STEG programme will be split. A proportion of the funds from the original STEG budget will remain in this budget for the expected expenditure covering the financial year 2024 – 2025. The remaining amount from the original STEG budget will be incorporated into the STEG window of the GRP budget. This specific value has been agreed between CEPR and FCDO as part of the GRP proposal process and an amended contract is being finalised with PCD.

The programme was audited in May 2024. See Annex E for Audit report.

Date of last narrative financial report	May 2024	Date of last audited annual statement	May 2024