## Annual Review Template
Title: Kenya Elections Support Programme (KESP)
Programme Value £ (full life): 7,500,000		Review date: 28/02/2024
Programme Code : 300657	AMP start date: / 31/01/2020	AMP end date: 31/12/2024

Summary of Programme Performance
Year	2021	2022	2023	2024
Overall Output Score	A	A	A	A
Risk Rating	Major	Major	Major	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300657/documents
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

Kenya Elections Support Programme (KESP) is a 5-year, £7.5m programme from Jan 2020 to Dec 2024 (a time extension approval to the business case changed end date from Dec 2023 to Dec 2024). KESP aims to contribute to a more credible, peaceful, and inclusive electoral process in Kenya. At outcome level, the programme supports meaningful electoral and democratic reforms to be enacted promptly.

During this reporting period (March 2023 – Feb 2024), the programme’s theory of change was refreshed following successful support to the 2022 general elections in Kenya. The programme in this phase focused on strengthening the Kenyan electoral reform process in the new election cycle (2022-2027), for a more credible general election in 2027 and beyond.

KESP was delivered through Electoral Law and Governance Institute for Africa (ELGIA) with a budget of £300,000, mainly through provision of technical assistance, trainings, multi-stakeholder coordination and capacity building of Independent Electoral and Boundaries Commission (IEBC), Parliament, the National Dialogue Committee (NADCO) and other key elections stakeholders.
[note] NADCO is a committee that was convened by the President and the Opposition leader to facilitate dialogue and consensus building and to recommend appropriate constitutional, legal and policy reforms on issues of concern to the people of Kenya. This was after the opposition led disruptive anti-government protests arising from disagreements with the outcome of the 2022 elections.

The political context has improved compared to the immediate post-election period in 2022/23 that was characterised by disruptive anti-government protests. The opposition leaders were not only protesting outcome of 2022 elections upheld by the Supreme Court of Kenya but also high cost of living for citizens. The improvement can be attributed to the National Dialogue Process that reduced the political tensions. However, Kenya’s inability to effectively tackle its systemic governance and accountability challenges, high debt burden and increased cost of living, remains an open concern to many citizens and might frustrate constructive debate on electoral reforms a head of 2027 elections.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The overall score for this Annual Review is A with the risk level assessed as Moderate.
During the reporting period, KESP refocused to kickstart electoral reforms in the new electoral cycle as per requirements of the electoral cycle approach.
[note] Electoral cycle approach is a tool that appreciates elections as continuous processes rather than isolated events. At the most general level, the electoral cycle is divided in three main periods: the pre-electoral period, the electoral period and the post-electoral period, each period with specific activities aimed at contributing to credible elections.

Key achievements include the following:
KESP successfully mobilized elections stakeholders to identify gaps and recommend legal amendments and changes to election laws and election related policies. As a result, draft bills developed include IEBC Act Amendment bill 2023 (on boundaries delimitation), IEBC referendum bill 2023, IEBC Act Amendment bill (on Election Regulations-2023), and Office of Registrar of Political Parties (ORPP) Political Parties Act Amendment bill 2023. These bills have been adopted by the respective institutions IEBC/ORPP and have been submitted to parliament through the Justice and Legal Affairs Committee (JLAC) of Parliament for consideration.
[note] ELGIA convened stakeholders on electoral reforms comprising Election sector CSOs, IEBC, ORPP, Kenya Law Reform Commission, Officials from the Attorney General’s Office, Elected Officials, Political Part representatives and Parliament’s Justice and Legal Affairs Committee.

KESP provided technical assistance to the National Dialogue Committee (NADCO) mediation process which contributed to unlocking the stalemate and deescalating the political tensions associated with the conduct and outcome of the 2022 elections, thereby contributing to stability in the country. However, the NADCO process itself was possible due to agreement between the Government and Opposition to find a solution to the political crisis.  This opened space within which the programme could operate, enabling it to meet expectation for output indicator 1.2 on consultation which envisioned a diffusely permissive environment. KESP through ELGIA provided technical assistance which entailed advisory and expert support that assisted members of the NADCO committee to deepen learning of the Kenyan election legal framework and the wider democratic governance principles. Programme support therefore resulted in adoption of the harmonized issues for negotiation, signing of the Dialogue Framework Agreement and the passage of the Notice of Motion in parliament anchoring the Dialogue Process in law, and a successful public feedback exercise. These constituted key milestones for the talks given the contentions that characterized the initial negotiations.

KESP technical assistance also shaped content of the final NADCO report, in particular, recommendations touching on electoral reforms. These recommendations will be key for electoral reforms moving forward within the current electoral cycle. Key issues prioritised include women and minority representation; campaign finance regulations; boundaries review; leadership and integrity; political party regulation and other policy/administrative proposals such as the resolution on how to appoint new IEBC commissioners. Both the Government and opposition side have endorsed the recommendations of the NADCO report and have signalled their commitment to ensure implementation of reforms that specifically touch on elections to be passed not later than 18 months before the next election.

KESP provided FCDO with the knowledge and access to influence key actors in and outside government. This contributed to the NADCO process holding together till the end. BHC leadership coordinated the diplomatic influencing process with other Heads of Missions in the country.
Major lessons and recommendations for the year ahead [1/2 page]
Lessons
- Development partners have to assess when there’s political good will on certain reforms, to know when to act. Political goodwill was essential to the success of NADCO, which was the second mediation attempt. The initial Parliamentary Bipartisan Dialogue Committee process failed, in large part due to a lack of elite consensus.
- Supporting enhanced collaboration and consultation between key election institutions and stakeholders was critical in deriving consensus on reforms roadmap and specific reform proposals. The programme facilitated collaboration with stakeholders such as IEBC, ORPP, Political Parties Liaison Committee (PPLC), Kenya law reform commission, Parliament, and Political party officials and election sector Civil Society Organisations (CSOs). This level of coordination helped the project not only build consensus but also synergies to avoid duplications, especially during delivery of activities.
- Evidence based programming - By prioritising generation of evidence through studies/research eg. the legal reforms audit of the 2022 elections, the project was able to establish a baseline of the gaps in the legal framework for elections. In 2024, the project will continue generating and relying on evidence from expert recommendations, citizens, and professional insights / Political Economy Analysis (PEA) to help highlight issues in the political context and how these influence election law and democratic reform priorities.

Recommendations:

Recommendation	When	Who
FCDO in collaboration with Government of Kenya (GoK) and other donors, should consider an expanded programme that extends assistance to an “implementation phase of the election reform process”. There is a risk that implementation of ongoing reforms, including NADCO recommendations, could be deferred in case the momentum or political goodwill which has been created by this programme is lost due to a funding gap.	Ensuring that new programming is in place to make the most of post-election reform window.	FCDO in coordination with Government of Kenya, and Donor Working Group on Elections to map out upcoming programmes by other development partners to complement each other’s efforts.
The indicators relating to influencing could be made clearer to directly link quantity of engagements with impact. There also needed to be clearer milestones identified to enable accurate monitoring and evaluation of the intervention.	When designing KESP successor programme	Action to be taken by the FCDO programme team.
International community engagement should be encouraged, to ensure push for timely reforms ahead of 2027 elections.	Continuous engagement	FCDO in collaboration with other Development Partners, Private Sector and Civil Society.
More public participation will be required moving forward to ensure the electoral reforms have widespread buy in from the public.	Continuous	Action to be taken by GoK while supported by CSOs.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The last annual review recommended a refresh of the original theory of change in the business case to reflect the 2022 post-election reform environment in Kenya. Decision was taken to reword the outcome statement and output one, and to close three output areas in the original business case following their successful implementation up to August 2022 Kenyan elections. The prevailing political context which was characterised by anti-government protests led by the opposition actors necessitated formation of the Bipartisan Parliamentary Dialogue process to resolve the prevailing stalemate. Unfortunately, this process failed due to stand off by the protagonists. It was later succeeded by the National Dialogue Committee (NADCO) which then presented a good opportunity to premise electoral reforms agenda in the dialogue and mediation process. This programme engaged with the political actors through diplomatic influencing to reduce the political tensions, and parliament and the NADCO committee to provide technical assistance to ensure an efficient and effective process that contributed to stability in the country. At the same time, electoral agencies were facilitated to develop reforms roadmap that will guide implementation up to 2027 elections.

The programme theory of change states that: IF IEBC, Parliament, and other law reform stakeholders can overcome technical and coordination issues which impede delivery of timely and meaningful electoral and democratic reforms; and IF key stakeholders can ensure that mediation process is conducted in line with the Kenyan constitution, legislative framework, and best practices governing political dialogue and mediation; THEN, IEBC, Parliament, and other electoral and governance institutions will deliver meaningful and timely electoral and democratic reforms, the political dialogue and mediation process will also be conducted effectively, efficiently, and free from violence and insecurity. In turn Kenya will be more peaceful and stable democracy. The key assumption around the new theory of change included – need for good political will to enable the mediation process to succeed to allow for the reform process to start early in the new electoral cycle. This assumption is still valid even though a lot of influencing still needs to be done to sustain political good will.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Progress against the programme impact and outcome indicators

	Indicator	Progress	Plans for the year ahead
Impact: Contribute to a more credible, peaceful, and inclusive electoral process in Kenya.	Global State of Democracy Index (GSoD) indicator 1: Representative Government. / Measures free and equal access to political power, against 4 indices: Clean elections; Inclusive suffrage; Free political parties and Elected government.	The last GSoD representation index for Kenya was at 0.53 in 2022 as compared to 0.50 in 2017 elections, indicating some improvement. / We judge that the programme has laid good foundation for reforms in the 2022 – 2027 electoral cycle through the NADCO reform recommendations and the bills already submitted to Parliament. Kenya is therefore on the right course towards putting in place effective electoral reforms and FCDO will continue to track the contribution made by these early reforms on the 2027 general elections.	The scope for this programme during the reporting year was limited and hence could not address all the recommendations from the IEBC Post Election Evaluation (PEE) report, External and Domestic observer groups and recommendations from KESP last annual review. / KESP successor programme should have a bigger scope for comprehensive reforms in the electoral sector including addressing the political and campaign financing challenges.
Outcome: Electoral and democratic reforms are meaningful and enacted promptly.	At least 4 reforms submitted to parliament by Dec 2023	The programme is on course to meet its outcome indicators. 4 bills submitted to parliament during the reporting period as elaborated in section C of this report. / National Dialogue Committee Report (NADCO) has also been adopted by the committee and submitted to parliament and it has several recommendations touching on electoral reforms.	KESP successor programme should have a bigger scope for comprehensive reforms in the electoral sector.
[note] Global State of Democracy Indices | The Global State of Democracy (idea.int)

# Planned changes to the project’s log frame
# This is the programme’s last year of implementation. If a new programme is approved, we will develop a new logframe to measure our support to implementation and impact of electoral reforms within this electoral cycle.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The electoral reform process has just begun in this electoral cycle. The NADCO report has a set of recommendations that will require amendments to the existing elections legal framework. The reform process will need the UK and other donors to contribute to the government of Kenya’s efforts to deliver and implement quality and effective laws and policies that will enable credible elections in 2027, thereby contributing to the country’s stability. Stability will not only enable safety and business continuity for the local citizens, but also for the UK to meet the strategic partnership objectives in Kenya.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]
Output Title	Electoral and democratic reform process for the 2022 - 2027 electoral cycle is strengthened
Output number:		1	Output Score:	A
Impact weighting (%):		100	Weighting revised since last AR?	Yes, Up

Indicator(s)	Milestone(s) for this review	Progress
1.1: Key electoral and democratic reforms are prioritised and addressed by the IEBC and parliament for the 2022 - 2027 electoral cycle.	IEBC, JLAC and other key reform stakeholders agree on a common road map for developing key electoral reforms, policies and regulations. (Priority roadmap which includes timeline for addressing key electoral reforms). / List of drafted electoral reforms, draft bills, policy solutions, regulations etc handed to IEBC for onward submission to parliament	A - output met expectation. / ELGIA completed legal audit research report highlighting the final list of electoral and democratic reform issues to be prioritised and addressed in the 2022-2027 cycle. / ELGIA consultatively developed harmonized roadmap on electoral legal reforms, agreed by election sector CSOs, IEBC and ORPP from August 2023 to May 2025. / Harmonized JLAC sessional paper on election law reforms developed. / Drafting of 4 bills supported by ELGIA: / IEBC Act Amendment bill 2023 (on boundaries delimitation) / IEBC referendum bill 2023 / IEBC Act Amendment bill (on Election Regulations-2023) / ORPP Political Parties Act Amendment bill 2023) / Bills then submitted to parliament for adoption and debate.
1.2: Number of Consultations supported and Number of Constitutional, Governance and Democratic reform issues prioritised and addressed through the dialogue and mediation process.	At least 6 Consultation sessions to build consensus supported through the programme. Technical assistance provided. Dialogue framework finalised outlining priority issues for dialogue. Report with recommendations on key electoral reforms including timelines, submitted to parliament by the dialogue committee.	A - output met expectations. / In total, 51 NADCO dialogue meetings supported (20 technical meetings and 30 committee meetings). Support included facilitation of venue and technical / expert support (including presentation on key issues/reforms to be discussed and implications for the legal framework). / Supported drafting of the dialogue framework agreed on 30 August by NADCO outlining priority issues for dialogue. / Provided technical advice to NADCO: to agree proposed timeline of reforms, presenting on electoral and legal issues, drafting of recommendations on electoral reforms, and providing best practice in line with the Kenyan Constitution. / Supported drafting of report with recommendations on key electoral reforms (including timeframe, by 18 months before next general election), submitted to parliament by dialogue committee on 26 November 2023. Report endorsed by Government and Opposition, awaiting debate in parliament.
1.3: Number of high-level engagements by BHC staff on KESP	At least 6 engagement sessions.	A - output met expectations Meetings held where the NADCO process and electoral reforms were discussed: / British High Commission (BHC) briefing for Head of Missions (HoMs) through Governance Group to discuss and understand implications of NADCO report and recommendations - 18 January 2024 / High Commissioner (HC) engagement with the immediate former President of Kenya – 6 December 2023 to discuss electoral stability related issues. / HC engagement with the Opposition Leader – 11 October and 25 November 2023 to discuss dynamics around the NADCO process. / Minister Counsellor meeting with Leader of Majority in the National Assembly - 3 October / HC hosted Governance Group meeting – 22 September to discuss progress of the NADCO process. / BHC meeting with Leader of Minority – 2 August, to discuss progress of the NADCO process.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Summary: The programme performed well against all indicators. Strong relationships and high-quality technical support allowed ELGIA to play a crucial role throughout the NADCO process. However, the NADCO process itself was possible due to agreement between the Government and Opposition to find a solution to the political crisis. This opened space within which the programme could operate, given the diffusely permissive environment. Important to note that success of the NADCO process will be fully realised only when the electoral reform recommendations contained in the current report are implemented. This will happen outside this programme review period. We have therefore scored the programme at A to only reflect success of the process indicators.

Indicator 1.1: The programme's strategic approach for electoral reform involved supporting both the NADCO dialogue and concurrently advancing priority election reforms. This dual approach served as a contingency plan, allowing the IEBC to progress their reforms independently if necessary. The programme developed a baseline report identifying issues that prevented reforms for the 2022 elections cycle. The findings informed the subsequent work with IEBC representatives and legislators to devise a strategy for legal drafting, public participation, consensus building, to allow for timely law reforms before the 2027 general election. The programme further supported the drafting of 4 key bills including IEBC Act Amendment bill 2023 (on boundaries delimitation), IEBC referendum bill 2023, IEBC Act Amendment bill (on Election Regulations-2023) and the Political Parties Act Amendment bill 2023), all submitted to parliamentary Justice and Legal Affair Committee.

Indicator 1.2: Despite initial setbacks including threats by the opposition politicians to return to street protests, the programme successfully provided technical assistance to the second round of mediation through NADCO, leading to a consensus. This involved continuous dialogue, expert advice on legal and electoral reform issues, and engagements with the IEBC. The result was agreement on crucial electoral reform recommendations that includes affirmative action on women and minority representation, campaign finance regulations, electoral boundaries review, reconstitution of IEBC leadership and timelines for electoral reforms, amongst others. This NADCO report, endorsed by both Government and Opposition, signals their commitment to implement the crucial reforms recommendations.

Indicator 1.3: Diplomatic influencing through high-level engagements with important interlocutors enabled the momentum around the NADCO talks to be maintained. The BHC was also able to coordinate across the international community through the Governance Group, using the regular meetings to update HoMs and align messaging. High level engagement was sustained, despite staffing changes and competing priorities.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The output statement was changed to focus on the new 2022 – 2027 electoral cycle, and suitable indicators and milestones agreed.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Key recommendations from the last Annual Review and status of implementation
Recommendation		Implementation status
	A focus on corporate governance and leadership within IEBC is critical to maintain confidence in the electoral process and mitigate the risk against violent escalation of subsequent elections.	Action for GoK with support from donors. NADCO report include a recommendation on how to reconstitute and reform the IEBC leadership and governance.
	Legal reforms should take place promptly after the election and should be concluded at least one year prior to elections to allow sufficient time for parliamentary engagement and operationalisation.	Action for GoK with support from donors. FCDO has begun through this KESP programme. NADCO report has recommended that legal reforms should be completed at least 18 months to the next general elections.
	Adoption and implementation of campaign finance law is necessary to promote more competitive and inclusive elections and mitigate against the use of bribery during the campaign period.	Action for GoK with support from donors. The NADCO report has a recommendation to implement the election campaign finance regulation.
	IEBC should undertake a comprehensive review of the use of technology, consulting with a full range of stakeholders	Action for GoK. This will be one of the priority issues for diplomatic influencing by development actors.
	A deep dive into IEBC procedures, arrangements and strategic communications is recommended to enhance the institution’s transparency.	Action for GoK with support from donors – Pending.
	Promoting inclusion in the election process is a priority. A more comprehensive approach to inclusion is essential going forward and must start early. This includes the role of Special Interest Groups (SIGs) as voters, political contestants and mobilisers, and election officers.	Action for GoK with support from donors. NADCO report include a recommendation on how to achieve inclusion for women.
	Voter education and information activities should be enhanced. Increasing voter apathy, especially among youth, is a concerning trend. IEBC, together with the international community, should consider how voter education can be improved.	Action for GoK with support from donors – Pending.
	A business case addendum is required to focus on post-election activities with remaining funds available under KESP.	Action for FCDO - Done
	A ‘whole of election cycle’ approach is essential to consolidate gains and deliver Value for Money (VfM).	Action for both GoK and FCDO plus other donors – Started.
	Refresh the KESP Theory of Change to reflect the context of the 2022-27 electoral cycle.	Action for FCDO - Done

Most of the above recommendations from the last annual review were outside the scope / timeframe for this programme. They will be addressed through the new business case to be designed (if approved) and implemented in coordination with GoK and interventions from other donors. Important to note that the NADCO process has significantly unlocked the reform space for these 2022/23 annual review recommendations to be progressed and implemented.

Lessons learnt this year

- Using an implementing partner with access to both sides of the political divide was essential to the dialogue and consensus building process. As well as a partner with existing expertise and a positive reputation working in the electoral reform sector enhanced the credibility of this intervention.
- Embedding the dialogue on a legal framework was crucial in ensuring meaningful reform recommendations. Talks and the subsequent recommendations were guided by existing laws and regulations, as well as the Kenyan constitution.

D: VALUE FOR MONEY (1 page)

Key cost drivers and performance
The programme considered value for money (VfM) across the 4E’s framework and as set out in the business case. From programme team efforts and partner reports, below is a review of instances demonstrating VfM.

Economy: The key costs during the period were staff costs, consultancy, and workshop related costs. Daily rates for consultants ranged from £60 - £180 compared to other FCDO programmes and other donor programmes in Kenya that have higher costs that range from £ 450- £900. ELGIA also negotiated with vendors to secure the most competitive unit prices, example, they opted to use affordable workshop venues like the Bomas of Kenya, which is a Government of Kenya owned facility, for NADCO dialogue meetings instead of hotels. Economy has also been enhanced by working with partners to cost share the financial burden of activities - ORPP, IEBC and Parliament have routinely paid for the cost of travel for participants travelling from out-of-town locations to attend project funded trainings and meetings.
[note] Example include the current Elections thematic evaluation assignment by FCDO EQUALS department

Over the reporting period, ELGIA spent 38.35% of the budget on project staff pay and benefits, 47.78% on direct programme activities, 2.45% on monitoring, evaluation and learning and 9.1% on Non-Project Attributable Costs (NPAC). Travel & Subsistence took up 1.39% and Capital Expenditure took 0.93%. While expertise was sourced from short term technical assistance, some of it was also directly provided by ELGIA staff, which explains the high spend on staff pay.

Efficiency: All the three indicators for this programme were achieved. There has been no variation between the planned and actual number of output indicators met. The project has been able to design, consolidate and correctly adapt activities to deliver the process results efficiently and at fair cost to the project. This has been possible in part due to routine consultations/co-creation meetings with stakeholders and beneficiaries. Case examples include technical multisectoral workshops to develop electoral reform roadmaps, which were originally planned as being conducted separately but were consolidated. As a result 4 bills were submitted to parliament and the NADCO report achieved recommendations that are key to enable electoral reforms ahead of 2027 elections.

Effectiveness: Beyond the goal of achieving consensus early on the areas of electoral and governance reforms ahead of the 2027 elections, technical support given to the NADCO process enabled politicians from both sides of the political divide to stay committed to the dialogue process. This gave hope to the country and calmed down political tensions that were quite high at the beginning of the programme review period. Before the talks, as a direct impact, the Kenyan economy was reported to be losing an estimated KES 1.2B per day due to disruption of businesses. The talks also prevented further loss of lives, livelihoods and stopped human rights violations.

Equity: The programme proactively ensured that at least 30% of programme participants had representation from the marginalized groups (youth, women and PLWD). Stakeholders such as IEBC, ORPP and CSOs have been required to develop a diverse list of participants at the design stage of project funded workshops and trainings. Beyond providing disaggregated data to monitor the success of inclusion, ELGIA technical personnel have routinely provided advisory support to stakeholders such as IEBC and ORPP to help advance the project’s equity objectives. For example, consultations with women ensured the NADCO report included recommendations on how to achieve affirmative action for women representation in political leadership. In addition, representatives of marginalised groups were facilitated to present their views on reforms before the NADCO committee as indicated on page 17 and 35 of the NADCO report.

Assessment of whether the programme continues to represent value for money
  This programme has unlocked space for reforms and laid foundation to enable start of meaningful electoral reforms aimed at increasing accountability and enhancing electoral integrity ahead of 2027 elections. It therefore represents good value for money. More work will need to be done to complete delivery of the recommended reforms.

It is important to ensure that the opportunity, momentum, and multi-stakeholder goodwill that has been generated through this programme is not lost. Based on the above analysis of outcome and output attainment, Theory of Change, VfM and evidence analysis, there is sufficient evidence for the programme to continue, and it is recommended that FCDO considers allocating additional funds to facilitate continuation of the reform programme.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The overall risk rating for this programme is moderate considering improvements in the political context. In the immediate post-election period, the new Government agreed to talks with the opposition to discuss calls for electoral reforms and address the opposition’s lingering dissatisfaction with the conduct of the 2022 election. However, the initial dialogue collapsed and was followed by anti-government protests that turned violent, leading to loss of livelihoods and deaths. The second round of talks (NADCO) has reached consensus on proposals for key electoral reforms and has dissipated the tensions. However, we’ll have to keep monitoring impact of current political class jostling, systemic governance and accountability problems, and a worsening economy. All of which may combine to increase the levels of apathy and dissatisfaction among citizens in Kenya.

A record of risks and mitigation measures is in the FCDO risk log. This is discussed with the implementing partner monthly and reviewed every 3 months with escalation procedures should risks evolve outside of the programme’s risk appetite or threaten wider objectives.

Over this review year, strategy and context risks heightened, especially in early 2023 when the political context became volatile due to anti-government protests. The political risks could have affected delivery of the programme but were mitigated by the FCDO through ongoing and regular political monitoring and messaging. We remained vigilant on reputational risks associated with supporting a delicate mediation process. Critically, the risks of development partners not supporting the electoral reform process early within the electoral cycle, are much greater, with worse implications for the credibility of the elections in 2027.

Below are the risk appetites for the programme per category:

Risk Category	Risk Appetite
Strategy & Context	Receptive: Although the context was volatile at the beginning of the year following violent street demonstrations, this has since changed after stakeholders agreed to engage in dialogue to pursue electoral reforms. Under the current context, the risk appetite remains receptive.
Policy & Programme Delivery	Cautious: Having delivered the key elements of the programme in 2022, and with limited funding in FY23/24, it was deemed appropriate to prioritise support for electoral reforms. Value for money considerations were key in deciding on targeted support and identifying a suitable implementing partner to deliver on electoral reforms. As this happened after the elections, the level of delivery risk is lower than that before the elections. The risk appetite remains cautious.
Reputational	Cautious: Unlike the previous year when the British High Commission was perceived, by a section of the political class, as partisan during the elections, the year under review benefitted from communication efforts that clarified the roles of the UK and the international community as supporters of democracy and strong independent institutions. FCDO has continued to engage objectively, and transparently to counter any negative perceptions. The reputational risk appetite remains cautious.

All current risks are within the programme’s risk appetite.

The programme’s climate risk remains low, both in terms of direct contribution to and suffering the impacts of climate change, due to the nature of activities.

Update on Partnership Principles
The most recent assessment of partnership principles informed decision making that funds should be channelled through implementing partners.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]
Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

Performance of FCDO
Reports from the partner indicates that FCDO programme team has effectively engaged with them to deliver the programme successfully. The team has collaborated and maintained strong relationships with the partner and across BHC. Close monitoring of the programme has been maintained through pre-programmed monthly meetings that focus on programme progress, financial management, and risks.

Performance of partners
The implementing partner, ELGIA, been responsive and has demonstrated competence. Project implementation is of high standard and has met expectations. ELGIA has prepared and submitted good quality progress and financial reports and the financial projections have been updated and submitted in a timely manner.
Financial Performance
Financial management and reporting is a collaborative effort where FCDO provides detailed requirements, and the partner adheres to these requirements. Financial performance is monitored through the quarterly reports as well as the monthly Programme Management meetings. ELGIA prepares and submits monthly forecast updates which facilitate accurate reporting for the monthly forecasting requirements, as well as declaring prepayments and accruals.

Out of the total budget of £7,500,000, the programme has so far spent £7,499,627 (99.99%) as shown below:
Component	2020/21	2021/22	2022/23	2023/24	Total Spend
101 UNDP		100,000			100,000
102 IFES-led Consortium	661,016	3,433,508	2,262,767		6,357,291
103 (Kenya Editors Guild			219,384		219,383.51
104 Westminster Foundation			247,395		247,395
105 Programme funded position	8,251	65,835	38,612		112,697.7
106 (Usiku Games)	24,962		0		24,962
107 (Wilton Park)	36,256		0		36,256
108 (Baraza Media Labs)			50,886		50,886
401 (ELGIA)				300,000	300,000
402 (IFES Audit)				50,756.64	50,756.64
Total	730,485	3,599,343	2,819,043.21	350,756.64	7,499,627

 The year under review focused on only one output - Electoral and democratic reform process for the new electoral cycle is strengthened - and the entire budget of £300,000 went into the delivery of this output. The project maintains a detailed asset register, which is updated regularly and shared with FCDO as part of the quarterly reports.
 The annual external audit has been commissioned and is planned to begin on January 26, 2024. It is expected that the audit exercise will be completed, and an audit report shared with FCDO by February 19, 2024.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
The programme has been monitored through quarterly reporting as well the pre-programmed monthly meetings between FCDO and ELGIA. Additionally, ELGIA conducts continuous monitoring of project implementation, including monthly and quarterly assessments/meetings to develop strategies effectively assess and improve performance and successful implementation of programme objectives. FCDO received beneficiary feedback through engagements with IEBC and the NADCO secretariat. This was a small-scale programme hence did not merit a big independent evaluation process.

Evidence and learning
During the reporting period, the programme through ELGIA generated legal audit of the 2022 elections that helped in establishing a baseline of the gaps in the legal framework for elections. They also developed the Election law reforms Sessional Paper (Harmonized Technical Presentation Report on election law reforms to JLAC) that is intended to contribute both to the election law reform and consolidation agenda and provide a comprehensive, principle-based approach to election law reform in line with the constitutional transformation framework. ELGIA also convened the quarterly CSO learning network where they shared lessons learnt and disseminated reports from new studies.

Date of last narrative and financial report	29 January 2024	Date of last audited annual statement	19 February 2024