Programme Completion Review

Title: Kenya Elections Support Program (KESP)
Final Programme Spend £ (full life): £ 8,500,000	Review Date:	30 June 2025
Programme Code: 300657	Start Date: 31/01/2020	End Date: 31/03/2025

Summary of Programme Performance

Year	2021	2022	2023	2024	2025
Programme Score	A	A	A	A	A
Residual Risk Exposure Rating	Major	Major	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300657/documents
DevTracker Links to all logframes used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/58849091.xlsx

A. Summary and Overview (1-2 pages)

Description of the programme and what it has achieved [1/2 page]

Kenya Elections Support Programme (KESP) was a £8.5m programme implemented from January 2020 to March 2025. The programme was designed to build on achievements and lessons learnt from previous UK elections support programmes with the main aim of contributing to a more credible, peaceful and inclusive electoral process in Kenya, at impact level. The business case was mainly intended to support effective delivery of 2022 Kenyan elections but was later amended in 2023 to address post-election reforms.
[note] Previous UK programmes that supported elections include the Elections Management and Security Programme (EMAS) (2012-13), the Drivers of Accountability Programme (DAP) (2010-15), the Deepening Democracy Programme (DDP) (2016-19).

The first phase of KESP (Jan 2020 – March 2023, total budget £ 7.2m) was implemented by International Foundation for Electoral Systems (IFES) together with downstream consortium partners. The programme outputs included: i) Meaningful electoral reforms and effective coordination between the Independent Elections and Boundaries Commission (IEBC), Judiciary, Office of the Registrar of Political Parties (ORPP) and Political Parties Liaison Committee (PPLC); ii) Kenyan institutions to improve on standards achieved in the 2017 election, and incorporate lessons learned for more effective planning, management, strategic communication, and stakeholder engagement to build public trust; iii) An enabling environment that leads to more women, youth, and persons with disabilities (PWDs) turning out to vote and elected to representative posts; and iv) Strengthened domestic election observation and monitoring.
[note] Including National Democratic Institute (NDI), South Consulting and Elections Observation Group (ELOG) to provide technical assistance, training and other forms of capacity building support to key electoral institutions(£6.6m). Westminster Foundation for Democracy (WFD) provided expert elections monitoring (£284,721); Kenya Editors Guild (KEG) promoted responsible media reporting on elections (£250,000); United Nations Development Programme (UNDP) as part of a multi donor basket fund provided technical assistance and support to election institutions(£100,000); and Baraza Media Lab (BML) raised awareness and prevent the spread of misinformation and other forms of fake news (£55,000).

The second phase of KESP beginning June 2023 - March 2025 was implemented by Electoral and Governance Institute for Africa (ELGIA) with a total budget of £1.3m. The business case extension was aimed at kickstarting electoral reforms to address lessons learnt and recommendations from the 2022 post-election evaluation reports. Our programme placed the UK as one of the donors that adhered to the electoral cycle approach. Outputs included: i) Increased organisational effectiveness of electoral institutions (IEBC and ORPP); ii) Legal reforms that will improve elections integrity are developed and submitted to parliament promptly ahead of 2027 elections; and iii) Evidence is generated and used to inform electoral reforms and their implementation.
[note] A key aspect of successful election assistance programs which recognizes that elections should not be viewed as one-off-events that occur on voting day, but rather as continuous processes of policymaking, preparation, implementation and evaluation.

Score against final output targets: Output 1 - B, Output 2 - A, Output 3 - A

Overall, KESP has been a successful programme having scored As in all the annual reviews and contributed to improved elections management, better election dispute resolution process and reduced election related violence in Kenya. An independent evaluation undertaken in early 2024 to assess how the British High Commission contributed to the 2022 Kenyan elections found that KESP, in addition to BHC diplomatic influencing and complimented by other programmes, were relevant to the context and programme priorities were well-delivered.
[note] Both domestic and international observation missions highlighted significant improvements in the electoral process that resulted in better administered elections in 2022 in Kenya. This included the use and application of technology in the transmission of results, more effective coordination between key electoral institutions, more professionalised and restrained policing and a significant fall in incidences of sexual and gender based violence (SGBV) during this election, and a more empowered, efficient and trusted judiciary that was able to complete petitions with the 6 months post-election as stipulated in the law.

The programme addressed key constraints and potential areas of risk in the elections period. Improvements in Independent Electoral and Boundaries Commission (IEBC) capacity contributed to the transparency and quality of elections operations and management processes, noted by observers. Technical assistance to the judiciary led to advancements in elections dispute resolution processes, credited as mitigating potential de-stabilising forces. The evaluation concluded that the UK’s support to the 2022 Kenya elections was effective, aligned with UK strategic intent, and can be seen as a good example of cross-mission working in a risky context. Though many actors supported the 2022 elections, the evaluation identified that the UK can credibly claim to have contributed to improvements that enhanced the likelihood of a peaceful result. These changes were possible thanks to the UK’s investment, combined with its ability to convene and cohere international action. A commitment to generating and using insight and evidence contributed to this success, enabled by a conceptual and operational synergy between British diplomacy and well-targeted, complementary, UK-funded technical programmes. As a result, the BHC could better understand and anticipate challenges and provide a response that often blended diplomatic and technical solutions in a timely and appropriate manner.

The context of 2022 elections were marked by a highly contested and transitional presidential election that took place amid a politically polarised environment. Kenya’s Deputy President William Ruto narrowly defeated veteran opposition leader and former Prime Minister Raila Odinga with 50.4% of the vote. In a unanimous verdict, the Supreme Court upheld the election result after challenges by the opposition and electoral commissioners.
[note] Full judgement can be found here: supreme-court-judgment-data.pdf (Nation. Africa)

The second phase of KESP from June 2023 – March 2025 has delivered strongly against outputs and has laid a strong foundation for reforms based on lessons learnt and recommendations from 2022 elections, despite a difficult political environment. Main aim of the second phase was to contribute to electoral and democratic reforms that are meaningful and enacted promptly ahead of 2027 elections. Even though most of the planned electoral reforms under the programme were completed, and the ones that required to be enacted through parliament have been submitted to the relevant Parliamentary Justice and Legal Affairs Committee, public trust in the electoral institutions remain low albeit due to factors beyond this programme, such as delays in the appointment of the IEBC Commissioners and high cost of living and perceived high corruption in government.
[note] Policy documents and guides developed to improve election operations, management and organisational effectiveness of IEBC.
[note] Political Parties Amendment bill 2024; Election Offences Amendment bill 2024; Referendum bill; ECF regulations
[note] Low trust in key electoral institutions – IEBC at 34% no trust at all and 35% little trust; police – no trust all 28% and 35% little trust; judiciary – 26% no trust at ll, 39% little trust and the executive 35% no trust at all and 38% little trust – Infotrak opinion poll done in April 2025.

During this second phase, KESP was delivered in a politically complex context. It was marked by a prolonged period of political opposition led protests over the conduct and outcome of the 2022 election, removal of IEBC commissioners, political class fallouts and realignments, a nationwide youth-led protest in June 2024 over the unpopular finance bill of 2024, dissolution of the cabinet, and legal disputes over election process issues. Notwithstanding the complex challenges, KESP has managed to deliver several tangible results including facilitating the National Dialogue Committee (NADCO) that contributed to stability in the country after the 2022 elections disputes; accelerating election law reforms – for example, IEBC Amendment Act passed by parliament and 5 other amendment bills submitted to parliament for debate. KESP also established institutional strengthening processes that will address coordination and technical capacity gaps within institutions like the Independent Electoral and Boundaries Commission (IEBC), and Office of the Registrar of Political Parties (ORPP) – for example, IEBC has developed crucial policy documents and guides awaiting adoption by new commissioners once appointed. All these results have been delivered while working collaboratively with IEBC, ORPP, Parliament, Political Parties, and Civil Society counterparts.

Major lessons learned, evidence generated and recommendations [1/2 page]
These lessons learnt and recommendations will be shared within FDCO internal networks including the governance cadre, and externally with the Kenya Elections Donor Group, relevant government institutions e.g. IEBC, ORPP, judiciary and elections CSOs. Some of the lessons learnt have informed design of the KESP successor programme, Kenya Institutional Strengthening Programme (KISP) and the British High Commission (BHC) Kenya 2027 elections strategy.

Lessons Learnt
Elections as a process: Elections in Kenya and elsewhere are a process, not an event. Early programmatic and diplomatic support is most effective and builds relationships and credibility, meaning the UK engages as a strategic partner, not as tactical support. It is critical that the UK can think and work politically, using its combined expertise, and adapt to changing processes.

Integrated strategic approach: Addressing the complexity of electoral support and changing environmental factors requires an integrated, strategic approach which draws on a range of programmatic and diplomatic influencing tools. An underpinning theory of change or integrated strategy enhances the value of these tools and better enables them to contribute to change. UK-led coordination processes can contribute best when designed into the support from the outset.

Political access and influence: Strategic deployment of political access and influence can reinforce the package of support and build UK credibility. Value is added by adopting a structured approach, understanding how to turn access into influence, and involving programmes in those conversations.

Elections support requires ongoing rigorous analysis: Support needs to be informed by continuous political economy analysis rather than just fed with information. A high volume of unassessed detail can easily overwhelm, leading to tactical rather than strategic engagement.

Changing elections environments: The election environment is changing. Drivers of both positive and malign influence are increasingly online and less susceptible to formal, institutional mechanisms. As intelligence is gathered, clear processes are needed to identify risks and develop mitigation plans.

The highly polarised and contested nature of elections in Kenya, together with a history of electoral related violence, puts greater emphasis on a robust, transparent and well administered electoral process given the high probability of challenge. Similarly, having a trusted election board that is perceived as neutral and independent is crucial to maintaining public trust. These are both longstanding issues, well understood by Kenyans, though solutions are elusive.

Election support programmes have not tackled the systemic drivers of corruption in the political system – manifest especially in the prohibitive costs of election campaigns and post-election patronage, including tackling the social norms like gifting. It requires having an understanding and addressing issues of social norms and behaviour change to address such systemic drivers. To tackle the complexity of anti-corruption and electoral support in a changing environment requires a coordinated, flexible and adaptable approach that uses a range of strategies and diplomatic tools.

Recommendations
Use UK political capital strategically. Plan for how UK political capital is used to extend diplomatic and programmatic support, given that it is valuable and finite and can be maximised when used strategically. This should be linked to learning and coordination processes within BHC. This recommendation is already being applied by the BHC Democracy Governance and Political (DGP) team to influence certain policy positions, example, urging GoK to urgently reconstitute leadership of IEBC to enable early preparation for the next elections in 2027.

The UK should continue to participate in donor/ambassadorial forums to promote information sharing and cohesion among the international community. As part of a “whole of election cycle approach”, there should be continued international community engagement on political and operational aspects of electoral reform and the impact of the political transition. The UK’s communications and engagement approach should be carefully balanced with reputational risk considerations. In line with this recommendation, the UK continues to convene and regularly engage in various coordination forums like Elections Donor Group and Head of Missions Governance Group, among others.

Adoption and implementation of campaign finance law is necessary to promote more competitive and inclusive elections and mitigate against the use of bribery during the campaign period. EOMs highlight the challenges around the lack of a proper campaign finance framework, significantly undermining democratic principles and practices. Finding ways to support the implementation of the campaign finance law is a priority to promote a level playing field and mitigate against risks of bribery. This will require coordination among all electoral stakeholders, effective oversight and advocacy efforts and political will. Regulating Election Campaign Financing is one of the key intervention areas for the KESP successor programme.

IEBC should undertake a comprehensive review of the use of technology, consulting with a full range of stakeholders. Kenya’s elections are among the largest and the most expensive to run in the world – technology plays a key role but also presents a key risk. Alongside the significant costs of procuring technological solutions, there are also many longer-term costs e.g. storage and security of equipment, many of which becomes redundant or unusable for subsequent elections. In addition to this, the paper record is the legal record. Going forward, it might be beneficial for IEBC to facilitate an open and inclusive discussion to ensure that elections administration continues to represent good VfM and technology (e.g. KIEMS kits) are used to their full potential and according to international best practice. DGP team will engage other stakeholders including electoral institutions, political parties, media and CSOs to help find sustainable solution.

Future election programmes should consider the latest issues regarding the role of technology, social media, influencers, cyber, and mis/disinformation in the elections, and clarify where BHC assets can together add value, informed by 2022 elections experiences and gaps.

GESI should be better embedded into programme design and MEL. Despite the intended logframe outcomes to promote more inclusive election, programme design and MEL could have better captured GESI considerations – e.g. disaggregated data detailing the beneficiaries of technical assistance and training, and evaluation of GESI of legal reforms supported. In future, this should be based on evidence generated thus far on the barriers to inclusion and opportunities and constraints.

How this report was conducted [1 paragraph]
This reported was conducted by doing literature review and analysis of the previous annual reports, the thematic evaluation report on how the UK delivered the 2022 Kenyan elections, quarterly reports from implementing partners including IFES and ELGIA and a light feedback session with electoral institutions (IEBC and ORPP) conducted by the BHC programme team.

Actions following approval of this report [1-2 paragraphs]

Following approval of this report BHC team will conduct a responsible programme closure process. This will include recovery of unspent funds from implementing partners, receipt of audited statement from ELGIA, and final disposal of assets. Lessons learnt and recommendations have been used to inform development of the BHC Kenya 2027 elections strategy and design of the successor programme, KISP and will inform implementation of future activities.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result
Budget	£7,500,000	£8,500,000
Timeframe	3 Years	5.3 years
Outcomes	Initial Outcome statement: Enhanced Management of the 2022 elections, with increased citizen participation and strong domestic monitoring delivers a peaceful and credible election. / Outcome Indicator 1: Improvement on standards and management of the 2022 elections as evidenced by domestic and international election observer reports / Outcome Indicator 2: Percentage increase of women, youth and PWDs participating as candidates in 2022 elections	Final outcome statement: Electoral and democratic reforms are meaningful and enacted promptly. / Outcome Indicator 1: Improved levels of public trust in electoral institutions

Overall assessment of programme outcomes, sustainability and VfM [1/2 – 1 page]

At outcome level, KESP has contributed to a stronger elections management framework in Kenya. This was evidenced by our UK commissioned evaluation report and by both domestic and international observation missions which highlighted significant improvements in the electoral process that resulted in better administered elections compared to 2013 and 2017 elections. The thematic evaluation findings that speak to strong impact include the following:
[note] Thematic evaluation of UK support to Kenya’s 2022 elections (June 2024)
UK 2022 elections support was highly relevant to the Kenyan context, conflict drivers, and beneficiary priorities, including the combination of programmatic and non-programmatic support. This was informed by the consideration of lessons from 2017 and the understanding of the political context that provided insight into what was both needed and possible. KESP while working in collaboration with Reducing Insecurity and Violent Extremism in Northern and Coastal Regions of Kenya (REINVENT) programme to focus on inclusive political participation and election-related SGBV addressed key issues relevant to marginalised groups. The BHC aligned evidence gathering and analysis to programming and influencing to maintain the relevance of this support as the context shifted ahead of the elections.

Effectiveness - the UK made important contributions to the peacefulness and credibility of the Kenyan elections, underpinned by a combination of high-quality programming and strategic diplomatic influencing. These changes built on previous UK investments and included important technical and capacity improvements in electoral institutions, violence prevention, and donor alignment and messaging, all reflected value for money.

More inclusive elections - UK goals were not fully achieved regarding the implementation of affirmative action processes for women and PWD candidates, and youth voter registration and turnout was lower than expected. However, overall, the 2022 elections were more inclusive than in previous years, with KESP making important contributions to the number of female candidates vying for various positions increasing by 12% compared to 2017 elections.
[note] Number of female candidates increased from 1300 in 2017 to 16,100 in 2022 elections.

Value for Money (VfM) - KESP provided good VfM and addressed needs unlikely to be supported by others. The BHC’s investment in the 2022 elections reflected the importance of the event and high stakes for Kenyan stability and UK interests.

Sustainability - Certain features of UK elections support are likely to have enabled sustainable change, largely related to institutional coordination, processes, and training. However, sustainability may not have been maximised due to short implementation period. It is not clear how sustainable diplomatic influencing gains have been or were meant to be, or to what extent diplomatic influencing was considered as a tool to promote sustainability.

The second phase of KESP has contributed to putting a strong foundation for reforms a head of 2027 elections. The following achievements have contributed to success of this outcome:
The National Dialogue Committee (NADCO) reform recommendations – Technical assistance through KESP shaped content of NADCO recommendations that not only helped to stabilize the country but also prioritized electoral reform issues to be implemented within the 2022/2027 election cycle. The NADCO process created an enabling environment and set pace for electoral reform discussions.
[note] NADCO is a committee that was convened by the President and the Opposition leader to facilitate dialogue and consensus building and to recommend appropriate constitutional, legal and policy reforms on issues of concern to the people of Kenya. This was after the opposition led disruptive anti-government protests arising from disagreements with the outcome of the 2022 elections.
[note] Election laws targeted under NADCO included enhancing participation of women and minority representation, campaign finance, boundaries review, leadership and integrity, political party regulation and other policy / administrative proposals, such as the resolution on how to appoint new IEBC commissioners.

Enactment of the IEBC Amendment Act 2024 - KESP supported stakeholder coordination and provided legal drafting assistance to help develop the law which was successfully passed in parliament. The IEBC Act 2024 made it possible for the president to appoint a selection panel to appoint IEBC Commissioners, a process that stalled since 2022 elections, causing delays in IEBC preparations towards 2027 elections, including the boundary delimitation review constitutional deadline that passed in March 2024. It’s expected that new commissioners will be appointed to assume office by end of June 2025.

Policy documents and operational guides that have been developed for IEBC. The IEBC secretariat have expressed satisfaction and confidence in the policy documents and operational guides that have been developed through KESP support. The documents comprise IEBC’s new five (5) year strategic plan, by-elections operations plan, statutory timelines for the 2027 general elections, comprehensive induction/training programme for incoming IEBC commissioners, 2027 general elections ICT plan, boundaries delimitation and voter registration operational plans alongside other guides that IEBC will use to conduct the 2027 general elections. IEBC’s secretariat staff were extensively involved in developing and duly validating all these KESP supported policy documents awaiting adoption by new Commissioners. The successful validation and anticipated adoption of these policy and operational documents will enable IEBC to conduct all delayed electoral activities within a short time, once new commissioners are appointed.

Data from opinion surveys and PEA has been disseminated to key electoral institutions and are already being used to inform policy decisions. The new IEBC strategic plan, for example, has strategies to improve public trust in the commission’s preparations ahead of the 2027 Elections. The EU-Elections Observation Mission used the same survey data in February 2025 to review progress of recommendations from the EU Election Observation report from the 2022 election process. They have since made recommendations on areas of improvement by elections institutions as they prepare for 2027 elections.

As much as output level results were met, the outcome level result which was - Electoral and democratic reforms are meaningful and enacted promptly – with indicator being - improved public trust in electoral institutions, were not fully met during second phase of KESP. According to the KESP survey published on 16 December 2024, 54% of Kenyans believed IEBC will not conduct free, fair elections in 2027. KESP 2nd round survey conducted in March 2025 shows a marginal improvement, with 46 pc indicating that IEBC will not conduct free and fair elections in 2027. In the 2nd round survey, respondents highlighted several key actions required to strengthen trust in the electoral process, including increasing transparency and inclusivity in the appointment of commissioners (38%), ensuring full independence from political parties (24%), and enhancing transparency in electoral processes (19%), among other suggestions. Public trust in IEBC, for example, will depend on how well the new commissioners will be onboarded to begin working effectively, how well they communicate their work, how they organise and manage upcoming electoral processes such as the anticipated by-elections for up to 20 civic seats, continuous voter registration and a possible boundaries delimitation. IEBC performance in these mid electoral cycle activities will help set up the commission for success in 2027.
That FCDO adhered to electoral cycle approach to initiate reforms post 2022 elections will contribute to sustainability. KESP successor programme, Kenya Institutional Strengthening Programme (KISP), will not only help sustain gains made by the UK and other donors from various investments in strengthening elections administration over the last decade, but will also contribute to sustainability by addressing shortcomings of KESP, eg. failure to address excessive use of money in Kenyan politics and the link to corruption and illicit finance flows.
[note] Evidence suggests that a “whole of election cycle” approach represents best VfM. For example, FCDO’s “Governance Best Buys” states that ‘holding elections’ and ‘voter education and information dissemination’ are ‘great buys’ (i.e. good evidence and strong cost-effectiveness data) and that increasing women’s political participation was ‘high potential’.

Important to note that USAID funding cuts and UK ODA cuts will negatively impact sustainability. We have already started discussions to reflect how donors, CSOs and government can work together to sustain reforms in the context of reduced funding.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]

The original Theory of Change (ToC) in the business case was refreshed in June 2023 to reflect the 2022 post-election reform environment and new challenges in Kenya’s election governance context. KESP was assessed as having already contributed to the effective delivery of many of the expected outcomes and impact of the programme.This was based on the findings of domestic and international election observation missions as well as the wide range of stakeholder interviews conducted during the 2023 Annual Review process, including beneficiaries of programme support. Decision was taken to reword the outcome statement and output one, and to close three output areas in the original business case following their successful implementation up to August 2022 Kenyan elections.
[note] Which was to attain enhanced management of the 2022 elections with increased citizen participation and strong domestic monitoring and observation.

The ToC revised in 2023 - states that IF key electoral institutions (IEBC and ORPP) are strengthened to enhance their efficiency, leadership and election management capacity, and IF The integrity of elections is strengthened through legal reforms (IEBC/ORPP sponsored law reforms, NADCO election justice law reforms and IF Election reforms and their implementation is informed by credible evidence/data. Then IEBC and ORPP will have sustained capacity to deliver credible elections in 2027 and beyond, and public trust in the electoral process will increase. In turn the general elections in 2027 and beyond will be more credible thereby leading to stability in the country.
The key assumptions on the new theory of change were that there would be sufficient political goodwill, broad stakeholder support and prompt budget allocation by government and donors to enable election reforms to happen promptly. These assumptions did not prove to be true during the period under review. Limited political will proved to be a barrier in promptly reconstituting IEBC leadership and led to delays in subsequent reforms preparations towards 2027 elections.

## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Output Number and Title		Increased organisational effectiveness of electoral institutions (IEBC and ORPP)
Output Score		B
Impact weighting (%)		35%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
1.1 Levels of understanding of new IEBC commissioners in election leadership and corporate governance.	2022 International and domestic election observer reports and Supreme court recommendations on steps to strengthen the capacity of electoral institutions such as IEBC and ORPP.		Induction curriculum in place by Jan 2025 / IEBC commissioners inducted by March 2025	Met expectation - A comprehensive induction curriculum in place by Jan 2025? / Did not meet expectation - Commissioners interview guide developed but commissioners not inducted as of March 2025 due to Government and procedural delays
1.2 Development, review and adoption of key election administration and policy frameworks	2022 International and domestic election observer reports and Supreme court recommendations on steps to strengthen the capacity of electoral institutions such as IEBC and ORPP (leadership, efficiency, and coorporate governance).		At least 5 policy and administrative guides developed / and adopted by respective institutions including IEBC and ORPP	Did not meet expectation - / The following have been developed but awaiting adoption when new commissioners assume office: / New five-year IEBC strategic plan / IEBC 2027 general election ICT plan / IEBC 2027 general election statutory timelines / By-Elections operations plan and timelines / IEBC procurement reforms / Development of IPPMS manuals and guides for ORPP

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]

This output has developed vital policy documents and administrative guides for both the secretariat and incoming IEBC commissioners. The secretariat is already familiar with these guides, having participated in their development. This will facilitate a smooth adoption and utilization process once the new commissioners take office in July 2025. KESP was however, unable to facilitate the induction of the new IEBC commissioners due to delays stemming from government bureaucracy and political factors which are beyond the programme's control.

The following administrative guides and frameworks have been developed by IEBC through KESP programme:

Comprehensive training curriculum for new IEBC commissioners: The KESP supported curriculum offers a comprehensive, context-responsive training tool for IEBC leadership, covering election operations, law, boundary delimitation review, corporate governance, procurement, technology, performance management, and lessons from past elections. This curriculum will facilitate swift induction of new commissioners once they assume office in July.

Support for IEBC commissioners' recruitment process: KESP has aided the IEBC recruitment process by providing an advisory / resource document for the selection panel to guide the interviews - covering election legal framework, management, boundary delimitation, dispute resolution, and technology. The advisory emphasises a transparent and efficient interview process.

New five-year IEBC strategic plan: The strategic plan for 2024-2029 outlines IEBC's major operations, including the 2027 Election Operations Plan (EOP), which details voter registration, education, and procurement protocols. This plan will allow new commissioners to focus on urgent activities like by-elections and mass voter registration without delay.

IEBC 2027 general election ICT plan: This plan outlines strategic objectives for integrating ICT in election operations, reviewing past elections and assessing AI and digital technology risks and opportunities. It will guide ICT procurement, staff training, and technology use in voter education and results management.

IEBC 2027 general election statutory timelines: Linked to the 2027 Operations Plan, these timelines establish deadlines for key election activities, including political party spending limits, party primaries, voter registration, and polling station gazettement.

By-Elections operations plan and timelines: New IEBC Commissioners will manage by-elections for up to 20 civic seats, with a plan detailing timeline for voter registration, education, and procurement to facilitate swift execution of pending by-elections.

IEBC procurement reforms: Training and advisory support have initiated procurement reforms, enhancing IEBC officials' capabilities to uphold procurement rules, in line with 2022 observer recommendations and a new policy framework launched in August 2024. ELGIA partnered with National Treasury experts for training on procurement processes, covering planning, supplier management, and invoicing. Improved procurement efficiency is expected to enhance public trust in IEBC's election integrity.

Development of IPPMS manuals and guides: The Integrated Political Party Management System (IPPMS) streamlines political party record management and reduces paperwork. Manuals developed through KESP will assist in maintaining accurate membership data and enable public opt-out from parties without consent, addressing past election challenges. AI technologies in the IPPMS aim to engage youth voters ahead of the 2027 elections.

These policy documents ad guides will contribute to enhancing the efficiency, leadership, and management capacity of the IEBC and ORPP.

 Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

- Lessons - Protracted political disputes, legal disputes, and changes in context during implementation can impact or delay the ability to undertake election reform activities. Protracted legal disputes over the reconstitution of IEBC delayed the process of recruiting new IEBC commissioners. It helps to deliberately convene multistakeholder consultative sessions to achieve consensus on appropriate reforms.
- Recommendations - It’s important to design adaptable activities and routinely review context changes/risks and use PEA evidence to adapt interventions.
- The BHC programme team should continue to engage IEBC leadership (once appointed) to adopt all the policy documents and administrative guidelines that have been developed through KESP support.

Output Number and Title		Legal reforms that will improve elections integrity are developed and submitted to parliament
Output Score		A
Impact weighting (%)		35%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Comprehensive legal reforms that promote and safeguard election integrity are developed for adoption and onward transmission to Parliament.	2022 international and local observer’s proposals on priority election law reforms. NADCO & MSWG law reform proposals and IEBC and ORPP sponsored legal reforms during the 2022-2027 election cycle.		All the election law reform proposals under NADCO, IEBC and ORPP proposals have been developed and submitted to Parliament.	Met expectation / All the 5 NADCO bills developed and submitted to parliament: The Constitution of Kenya (Amendment), Bill, 2023; IEBC (Amendment) Bill, 2023; Elections (Amendment) Bill, 2023; Elections Offences (Amendment), Bill, 2023; and the Political Parties (Amendment), Bill, 2023. / IEBC Act 2024 passed. / AI in Elections Regulations proposed from the KESP convened regional Conference on Artificial Intelligence (AI) and Digital Technologies in Election

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]
KESP through implementing partner ELGIA provided critical legislative drafting and research support to Parliament, particularly the Justice and Legal Affairs Committee (JLAC). This included development of a model law on Electoral Campaign Finance and contributions to various Bills such as the IEBC Amendment Act, Referendum Bill, and amendments relating to public participation, gender equity, and political party regulation. These efforts aim to ensure robust, inclusive, and enforceable legal frameworks ahead of the 2027 elections. Details of specific bills submitted to parliament described below:

NADCO Election Law Reforms: The National Dialogue Committee (NADCO) led the development of nine draft Bills aimed at reforming Kenya’s electoral system for the 2022/2027 cycle. Five of these Bills focus on electoral justice and are currently before Parliament. They include amendments to the Constitution, IEBC Amendment Bill (already enacted), Elections Amendment Bill, Elections Offences Amendment Bill, and Political Parties Amendment Bill. These reforms target increased inclusion of women and minorities, campaign finance, boundaries review, leadership integrity, and IEBC commissioner appointments. In February 2024, Parliament unanimously endorsed the NADCO report, and a March 2025 cooperation agreement reaffirmed the commitment to fully implement the reforms ahead of the 2027 General Elections.

Independent Electoral and Boundaries Commission (IEBC) Act 2024: Passed in August 2024, the IEBC Act re-established the selection panel necessary to appoint new IEBC commissioners, filling a leadership gap since early 2023. This reconstitution allows IEBC to resume essential functions like by-elections, voter registration, and boundaries review, which had stalled. The Act also introduces a requirement for IEBC to submit a comprehensive post-election review report within 18 months after each general election to Parliament, promoting transparency and continuous improvement.

Multisectoral Law Reforms on Two-Thirds Gender Rule: A Gender Principle Task Force was established by President Ruto and later supported by KESP to propose a framework for implementing the two-thirds gender rule. Through ELGIA’s legal support, they proposed a formula for special seats for women, transitional clauses for current parliamentary compliance, and use of proportional representation. Additionally, amendments to the Political Parties Act aim will support women through funding for education, mentorship, and capacity building within parties.

Regional Conference on AI and Digital Technologies in Elections: This regional conference explored the benefits and risks of AI and digital technologies in electoral governance. It highlighted issues like disinformation through bots, hate speech, and microtargeting of voters. Participants discussed regulatory gaps and shared strategies for real-time fact-checking and cybersecurity. The conference established regional principles for responsible AI use in elections and emphasized the role of tech. The recommendations have been included for consideration in the AI regulatory framework.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

Lesson - The political class and particular members of the executive, have significant influence on electoral reforms politics. They use their control of political power to advance or withdraw political goodwill for law reforms. The success of KESP inputs for law reforms under the NADCO-led process can be attributed in part to the political goodwill and close working relationship between the political class and government.

Recommendations
Make use of PEA to understand enablers and blockers of change in a complex political context like Kenya.

Future election reforms programs and activities should consider starting with reforms that have more government and political class support and build on government relationships and processes before focusing on more contested reforms.

Output Number and Title		Evidence is generated and used to inform electoral reforms and their implementation.
Output Score		A
Impact weighting (%)		30%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
1. Incidences where PEA is used to inform reforms / 2. Dissemination and uptake of perception survey results with relevant institutions	PEA done by October 2025 / KESP Nationwide Public Opinion Survey Conducted by Sept-Oct 2024, focusing on election reforms, public trust, democratic participation, and public governance processes.		1. Documented incidence/s where reforms are informed by Political Economy Analyses (PEA) reports. (case studies generated by partner). / 2. Citizen perception surveys complete, results shared with the public and dissemination events held with electoral institutions including IEBC and ORPP.	i) Met expectation / The following policy and administrative guides have been informed by findings from the PEA and perception survey: Five (5) year, strategic plan, a Comprehensive Curricular and training programme to guide the induction IEBC’s new leadership, 2027 General Elections ICT plan, Legal timelines for the 2027 General Elections, Harmonised Boundaries Delimitation law, Boundaries Delimitation Operations plan / ii) Met expectation / -PEA done and results disseminated. / -Opinion poll done and results disseminated (included results on public trust levels of key electoral institutions including IEBC, judiciary, police, ORPP, Parliament, Executive).

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]

KESP undertook a Political Economy Analysis (PEA) study to examine context-specific factors and lessons that are affecting electoral reform work in Kenya. The findings confirmed that key electoral stakeholders, and in particular members of the Executive, have significant influence on electoral reforms and political attitudes. Specifically, they use their control of political power to advance or withdraw political goodwill for law reforms and to dominate and demobilise their opponents. Consequently, KESP considered starting with reforms that had more government support like the IEBC Amendment bill, but de-prioritized the Elections Campaign Finance regulations since there’s luck of political will amongst legislatures. The PEA recommendation to use multi-stakeholder / coalition of change makers approach to push for reforms worked well. KESP mobilised and facilitated electoral reform working groups, inter-party dialogues, and the legislature. These pressure groups successfully pushed to parliament other pending legal reforms including the Political Parties Amendment Bill 2024, the Elections Offences Amendment Bill 2024, Election Amendment bill 2023 and IEBC Boundaries Delimitation Bill 2023. These bills are at different stages in both Senate and National Assembly.

The PEA and perception survey findings have been disseminated to the Kenyan public, institutions and key electoral stakeholder groups including IEBC, Parliament, ORPP, CSO elections coalition / uchaguzi platform and media. The following are examples of how findings of PEA and perception survey are being used by various institutions and CSOs:

1. IEBC - The new IEBC strategic plan covering five years 2024-2029 now includes strategies to tackle the problem of public disaffection towards the commission alongside measures to improve public trust in the commission’s activities ahead of the 2027 General Elections. The opinion poll showed that only 26% of the surveyed respondents expressed confidence in the IEBC to conduct free and fair elections in 2027. Lack of transparency (60%), corruption (47%), past election irregularities (47%), and lack of independence (19%) were cited as the major causes of lack of confidence in the IEBC. Interventions proposed by respondents to increase Kenyans’ trust in the electoral processes include, ensuring independence and impartiality of the IEBC (40%), ensuring elections are free, fair and transparent (39%), provision of civic / voter education (29%), and prevention of vote rigging at 29%, among others. Consequently, all the policy documents and administrative guides that KESP supported IEBC to develop have been informed by the research findings and if well implemented will help boost confidence and trust in IEBC.
  [note] Five (5) year, strategic plan, a Comprehensive Curricular and training programme to guide the induction IEBC’s new leadership, 2027 General Elections ICT plan, Legal timelines for the 2027 General Elections, Harmonised Boundaries Delimitation law, Boundaries Delimitation Operations plan, among other outputs.
2. Civil Society Organizations - The first round KESP survey findings were disseminated to the public on 16 December 2024. Mainstream media coverage and reporting of the survey ensured nationwide reach.
  [note] . Infotrak survey media report Citizen TV and https://www.infotrakresearch.com/nationwide-perception-study-dec-16-2024/
Under ELGIA’s co-convened umbrella CSOs Platform, “Uchaguzi” CSO Platform, information from the survey is assisting CSO organizations to adapt their programs and focus attention on activities which can address public trust concerns.
During the Peoples Dialogue Festival, a CSO-led initiative jointly supported through the EU, Danish and Netherlands missions in Kenya, held in March 2025, data from the KESP perception survey was used to highlight areas of action for government agencies and CSO groups to address the low levels of public trust and issues affecting democratic participation.
1. Data from the KESP perception survey was used on 20 March 2025 to guide discussions during the EU- Election Observation Mission (EOM) 2022 follow-up mission. Follow Up Recommendation Implementation Conference (FURIC) was held to undertake a mid-term review of the progress of election reform recommendations from the EU Election Observation made in 2022.
  [note] CSOs FURIC Conference
2. Parliament – 75% of respondents indicated that they have not been involved in any public participation forum. Only 21% have participated in public participation forums to give their views on governance processes such as legislation and budget making. A majority (55%) don’t feel that their voices can influence the government’s decision-making. Only 36% believe that Kenyans’ voices can influence the government’s decision making. Various parliamentary committees are rethinking how best to make public participation more meaningful.
3. Political party coalitions - the perception survey found that 56% of respondents do not believe that the broad-based government will lead to improved governance and unity.  Only 33% believe the broad-based government will realize improved governance.

State of the nation. Overall, a majority (68%) of Kenyans feel that the country is headed in the wrong direction, with only 9% expressing that the nation is headed in the right direction. Surveyed respondents identified the high cost of living, poor governance/bad politics, and unemployment as the main reasons they believe the country is headed in the wrong direction. This suggests widespread dissatisfaction with these issues, indicating public concern over the country's trajectory. CSOs and media have used these statistics to engage government officials both at national and county levels to reconsider various policies eg. lobbying around the new finance bill 2025 to drop taxes that continue to worsen cost of living for citizens.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
Investment in research and analysis ensured KESP was able to make evidence-based decisions and reform contributions. Future programmes should integrate research and analysis.

D: Value for Money [½ - 1 page]

 VfM performance compared to the original VfM proposition in the business case

The programme considered value for money (VfM) across the 4E’s framework and as set out in the business case. From programme team efforts and partner reports, below is a review of instances demonstrating VfM.

Economy: The key costs during the period were staff costs, consultancy, and workshop related costs. Daily rates for consultants ranged from £60 - £180 compared to other FCDO programmes and other donor programmes in Kenya that have higher costs that range from £ 450- £900. The programme opted to use affordable workshop venues like the Bomas of Kenya, County Hall and Parliament Office Building “Bunge Towers” which are all Government of Kenya owned facilities, for NADCO dialogue meetings, legal advisory presentation meetings and law memorandum presentation meetings, instead of hotels or out of town venues. Economy has also been enhanced by working with partners to cost share the financial burden of activities - ORPP, IEBC and Parliament have routinely paid for the cost of travel for participants travelling from out-of-town locations to attend project funded trainings and meetings.

Over the implementation period, ELGIA spent 31.65% of the budget on project staff pay and benefits, which includes direct short-term technical assistance for consultancies and expert support, 53.32% on direct programme activities, 3.56% on monitoring, evaluation and learning and 9.88% on Non-Project Attributable Costs (NPAC). Travel & Subsistence took up 2.59%. There was no Capital Expenditure. While expertise was sourced from short-term technical assistance, some of it was also directly provided by ELGIA staff, which explains the high spend on staff pay.

Efficiency: Throughout implementation period, the primary driver of efficiency for KESP was its ability to leverage small investments to unblock the provision of technical assistance, promote diplomatic engagement and international community coordination, and also to address challenging issues in innovative ways. This has also been possible in part due to routine consultations/co-creation meetings with stakeholders and beneficiaries. Case examples include technical multisectoral workshops to develop electoral reform roadmaps, which were originally planned as being conducted separately but were consolidated and held during the National Conference on Election Law Reforms and Regional Conference on use of AI and Digital Technologies in Elections. As a result, bills including the Election Amendment bill 2023, IEBC Boundaries Delimitation Bill 2023, IEBC Amendment Bill 2024 among other legislative instruments were submitted to parliament alongside the NADCO report achieved recommendations that are key to enable electoral reforms ahead of 2027 elections.

Effectiveness: KESP has contributed to ownership and sustainable change through relatively small amount of TA funding. Capacity of core institutions has been enhanced and there has been effective delivery of many core functions throughout the 2022 electoral cycle, e.g. efficient results transmission through a portal accessible to the public. KESP has started multistakeholder reform conversations early and impact will enable early preparations for 2027 elections. Technical support given to the NADCO process enabled politicians from both sides of the political divide to stay committed to the dialogue process. This gave hope to the country and calmed down political tensions that were quite high at the beginning of the programme review period. Before the NADCO talks, as a direct impact, the Kenyan economy was reported to be losing an estimated KES 1.2B per day due to disruption of businesses. The talks also prevented further loss of lives, livelihoods and stopped human rights violations.

Equity: The programme proactively ensured that at least 30% of programme participants had representation from the marginalized groups (youth, women and People Living with Disability (PLWD)). Consultations with women ensured the NADCO report included recommendations on how to achieve affirmative action for women representation in political leadership. In addition, representatives of marginalized groups were facilitated to present their views on reforms before the NADCO committee as indicated on page 17 and 35 of the NADCO report. Through KESP assistance, the Multi-Sectoral Working Group (MSWG) has proposed wide-ranging legal, policy and administrative measures designed to promote implementation of the two-thirds gender principle that is currently with legislators undergoing debate with strong indications of potential enactment before the 2027 General elections.

VfM assessment compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme
Evidence suggests that a “whole of election cycle” approach represents best VfM. For example, FCDO’s “Governance Best Buys” states that ‘holding elections’ and ‘voter education and information dissemination’ are ‘great buys’ (i.e. good evidence and strong cost-effectiveness data) and that increasing women’s political participation was ‘high potential’.

Now is a critical time to consolidate gains made and act upon all recommendations identified by 2022 EOMs and IEBC’s own post-election evaluation, ahead of 2027 elections. This will help promote sustainability of reforms.

Lessons learned from the KESP programme, alongside the wider BHC Nairobi approach to the 2022 elections, were also documented and shared with the relevant wider FCDO staff (in the form of a presentation and short briefing note to governance cadre and research and evaluation cadre) demonstrating value beyond the programme and providing a useful basis to inform wider FCDO programming and policy on elections.

E: Risk [½ - 2 pages]

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]

Overall risk rating for KESP programme was major throughout the implementation period but remained within FCDO’s risk appetite. Over the past year, while the risks were substantial, delivery under these conditions were possible and KESP delivered well against key objectives. Critically, the risks of not supporting the elections process – and in particular key electoral institutions and early legal reforms – are much greater, with worse implications for the credibility of elections in 2027. Well administered elections are important for contributing to peace and stability of the country. A record of risks and mitigation measures were maintained in the FCDO risk log. This was reviewed every 3 months with escalation procedures should risks evolve outside of FCDO’s risk appetite or threaten wider objectives. In the year prior to 2022 elections, a x-BHC Nairobi Elections Working Group was established, which conducted monthly risk assessment, primarily assessing operational, political and security risks – this review occurred on a weekly basis as elections drew closer. IEBC’s own internal risk register was also reviewed and discussed with relevant staff. Programme implementing partners also conducted monthly risk monitoring and prepared additional documentation and participated in meetings on scenarios, triggers and red lines, closer to 2022 elections.

Risks to the external context (including political and security risks) increased during the review period. Key risks identified included conflict and political risks, constitutional and legislative challenges, security and police accountability and effectiveness - especially during the GenZ anti-government protests in June 2024 which were marked by excessive use of police force, disappearances and extra judicial killings. Risks were mitigated by the FCDO through scenario planning e.g. possibility of protracted countrywide protests due to increased cost of living, and ongoing and regular political monitoring and messaging by BHC leadership. The UK’s participation in various forums e.g. Head of Missions Governance Group, Elections Donor Group - also facilitated knowledge sharing and promoted more cohesive international community and implementing partner actions. However, the political risks were mostly beyond the control of the programme or embassy.

Strategy and context – GoK attacked the media and select civil society organisations for alleged incitement and funding support to anti-government protests, led to reduced civic space. There were risks that protracted anti-government protests in mid-2024 would delay early electoral reforms in the 2022/27 electoral cycle thereby fuelling political crisis up to 2027. This would be because of disagreement between the political class & citizens, lack of clarity on the trajectory of reforms, timelines missed due to political realignments (risk and opportunity). Mitigation strategies applied by BHC leadership included engagement with the president, opposition leaders, parliamentarians, religious leaders, and youths to ensure reforms continue. Both GoK and Civil Society Organisation were urged to adhere to Public Benefits Organisations (PBO) Act through Heads of Mission engagements. We also used the Kenya 2022 Post Election Evaluation Report and the NADCO report recommendations as reference point to steer electoral reforms.
There was also risk that the political class would interfere with IEBC leadership reconstitution process, leading to appointment of persons with questionable integrity and consequently resulting in lower public trust in IEBC. CSOs and other political actors engaged at various levels to encourage the IEBC commissioner selection panel to maintain high levels of professionalism.

Policy and programme delivery – the rising public debt, GoK resourcing cuts and USAID funding cuts will impact negatively the sustainability plans. Delayed appointment of IEBC commissioners contributed to delayed adoption and implementation of key policy documents and guidelines developed by IEBC through KESP support. The BHC leadership in collaboration with other Development Partners consistently engaging Kenyan leaders and politicians to fast-track appointment of IEBC Commissioners and to prioritize government funding to IEBC to enable early preparations for 2027 elections.

Safeguarding risks including of elections triggering human rights abuses by security forces during political opposition protests and GenZ protests were recorded. The parallel FCDO programme REINVENT that trained police officers on crowd control was a critical part of risk mitigation. The BHC leadership together with other Development Partners consistently engaged Kenyan leaders and relevant ministries to stop excessive use of police force, forced disappearance and extra judicial killings during peaceful protests.

Financial and fiduciary risks – All the implementing partners were sensitized on the FCDO guidelines on fraud (zero-tolerance) and fraud reporting procedure to FCDO. There were no financial and fiduciary risks reported during the entire implementation period of KESP. FCDO team worked closely with IFES and ELGIA to ensure the budget was linked to workplan, performed quarterly spot checks to understand flow of funds and reporting, as part of mitigation strategy.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]

Performance of FCDO
Reports from the implementing partners (both IFES-led consortium in first phase and ELGIA in the second phase) indicates that FCDO programme team effectively engaged with them to deliver the programme successfully. The team collaborated and maintained strong relationships with the partners and across BHC. Close monitoring of the programme has been maintained through pre-programmed monthly meetings that focus on programme progress, financial management, and risks.

Performance of partners
The implementing partners – IFES and ELGIA, were responsive and demonstrated competence. Project implementation was of high standard and met expectations. They prepared and submitted good quality quarterly progress and financial reports and the financial projections have been updated and submitted in a timely manner. A key lesson learnt was that the monthly FCDO programme team catch-up meetings with partners enabled effective monitoring of programme implementation progress, free flow of information and effective management of each other’s expectations.
Financial Performance
Financial management and reporting were a collaborative effort where FCDO begun by providing detailed policy requirements and sensitizing partners on the same to facilitate compliance. Financial performance was monitored through the quarterly reports as well as the monthly Programme Management meetings. The partners prepared and submitted monthly forecast updates which facilitated accurate reporting for the monthly forecasting requirements, as well as declaring prepayments and accruals. The FCDO programme team ensured that the monthly variances were no more than 5% by monitoring, discussing and challenging partners’ financial information and financial status. This enabled partners to provide accurate and detailed financial data thereby promoting accountability.

Out of the total budget of £8,500,000, the programme spent £8,430,614 as shown below:

Component	2020/21	2021/22	2022/23	2023/24	2024/25	Total Actual Spend
101 UNDP		100,000				100,000
102 IFES-led Consortium	661,016	3,433,508	2,262,767			6,357,291
103 (Kenya Editors Guild			219,384			219,383.51
104 Westminster Foundation			247,395			247,395
105 Programme funded position	8,251	65,835	38,612			112,697.70
106 (Usiku Games)	24,962		0			24,962
107 (Wilton Park)	36,256		0			36,256
108 (Baraza Media Labs)			50,886			50,886
401 (ELGIA)				300,000	930,987	1,230,986.30
402 (IFES Audit)				50,756.64		50,756.64
Total	730,485	3,599,343	2,819,044	350,756.64	930,987	8,430,614

The year under review focused on three outputs with a budget allocation of £1,000,000, out of which £930,987 was spent. The project maintained a detailed asset register, which was updated regularly and shared with FCDO as part of the quarterly reports. ELGIA’s annual external audit report has been submitted to FCDO for scrutiny. The Auditors’ unmodified opinion indicates that the financial statements give a true and fair representation of ELGIA’s financial position and raises no issues of concern. Asset disposal is under consideration, with the programme team exploring the transfer of assets to new or ongoing FCDO programmes, which would represent the best value for money.

Programme-level approach to monitoring and evaluation [1/2 page]

Monitoring and Evaluation
The programme has been monitored through quarterly reporting as well the pre-programmed monthly meetings between FCDO and ELGIA (and previously IFES). Additionally, partners conducted continuous monitoring of project implementation, including monthly and quarterly assessments/meetings to develop strategies effectively assess and improve performance and successful implementation of programme objectives. FCDO received beneficiary feedback through engagements with IEBC, ORPP secretariat and other related institutions.

An independent thematic evaluation of the UK support to Kenya’s 2022 elections was commissioned by the British High Commission (BHC) Nairobi in early 2024. It was intended to support learning by understanding how the UK supported Kenya’s 2022 elections and by identifying lessons for future support in Kenya and for other posts. It found that the UK’s support to the 2022 Kenya elections was effective, aligned with UK strategic intent, and can be seen as a good example of cross-mission working in a risky context. Though many actors supported the 2022 elections, based on contribution stories developed for this evaluation, the UK can credibly claim to have contributed to improvements that enhanced the likelihood of a peaceful result, including: improved elections management, improved electoral dispute resolution and reduced election related violence. Recommendations from this evaluation have been used to inform design of KESP successor programme and drafting of BHC strategy and approach to Kenyan 2027 elections. The evaluation report was also disseminated to FCDO governance cadre and evaluation network. The evaluation management response and recommendations action plan have been published.

During the year, ELGIA disseminated PEA and public perception surveys results to electoral institutions including IEBC, ORPP, Judiciary, Civil Society including media and International Community to inform their interventions and future programmes.

Date of last narrative financial report	9 May 2025	Date of last audited annual statement	9 May 2025