Business Case
Summary Sheet

Business Plan Summary / The United Kingdom’s Business Plan for Kenya has the following vision, aligned with the UK’s new Strategic Approach to Africa: A prosperous, safer, healthier Kenya which sees the UK as a partner of choice for peace, trade and economic development, is less reliant on aid and more resilient to shocks and stresses. This programme will contribute to sustainable development goal 16: Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective accountable and inclusive institutions at all levels.

Title: DFID Kenya Governance – Kenya Elections Support Programme (KESP)
Programme summary / The proposed programme builds upon electoral reforms previously supported by DFID to contribute to a credible, peaceful and inclusive 2022 general election in Kenya. This will indirectly benefit all Kenyans and contribute to peace, stability and economic development. The programme will also provide support to election institutions to manage a constitutional referendum and electoral boundary review if required. Specifically, it will support: / Meaningful electoral reforms early in the electoral cycle and effective coordination between the Independent Elections and Boundaries Commission (IEBC) Judiciary, Office of the Registrar of Political Parties (ORPP) and Parliament. / Kenyan institutions to improve on standards achieved in the 2017 election, and incorporate lessons learned for more effective planning, management, strategic communication and stakeholder engagement to build public trust. / An enabling environment that leads to more women, youth and persons with disabilities (PWDs) turning out to vote and elected to representative posts / Strengthened domestic election observation and monitoring.
Rationale for UK Aid spending / The UK can contribute to increasing the chances of a credible, peaceful and inclusive 2022 general election in Kenya, based on our long-term experience. Kenyan elections are often highly contested and divisive and can generate significant instability and economic uncertainty. In 2007 they led to a widespread violence and displacement. The management of Kenyan elections has steadily improved since 2007 and the UK has played a lead role within the international community. Our role is valued by the Government of Kenya. This programme will support the enabling environment for economic growth and poverty reduction and is central to the UK business plan for Kenya.
Programme Value: £7.5m		Country and Sector: Kenya, Governance
Department/Country Office/ Contact name		DFID Kenya
Threshold for Approval of Business Case:		Deputy Director <£40m
Date of Approval of Concept Note:	22 May 19
Date of Approval of Business Case
Programme Code: 300657	Start Date: / 01/01/2020	End Date: / 31/10/2023
Overall programme risk rating:	Major
Vault Number:	48490566

## A. Strategic Case

Context and strategic fit with UK objectives

This programme is an important part of the UK Government’s efforts to promote democracy, stability and poverty reduction in Kenya. It will support the enabling environment for economic growth and poverty reduction in Kenya. UK interests in Kenya are directly affected by the political and economic instability caused when elections are not well managed. This programme is, therefore, an enabling programme for our wider portfolio.

The UK will work across government to support a peaceful and credible 2022 election, using a wide range of diplomatic and development levers. This programme will build on the extensive lessons learned from the 2017 election to respond to priority needs and effectively manage risk. It will also build on UK experience to date with supporting Kenya elections. We will closely coordinate with across the British High Commission Political Governance team and with other key development partners.

A number of other donors have expressed an interest in supporting Kenyan elections, but at the time of writing no other election support programmes have been finalised. Recent discussion at the Election Donor Group, suggest that there is likely to be less support available for the 2022 election than there was for the 2017 election and robust prioritization will be required. Through this programme the UK will be the first donor to start up an election support programme for the 2022 election. All evidence points to the importance of beginning early in the election cycle, within a longer-term election cycle approach, learning lessons and building good practice over a series of election cycles.

We have a comparative advantage through our established role as a lead member of the international community working on credible and peaceful elections in Kenya. The Kenyan Foreign Minister requested continuing UK support in her May 2019 meeting with the UK Foreign Secretary. UK support has been directly requested by Kenya institutions including the IEBC, Judiciary, Parliament, ORPP, and civil society.

Elections in Kenya have witnessed electoral malpractice, political attacks on independent institutions and at worst widespread violence. However, there have been significant improvements through each cycle since 2007, with more incremental increases in issue-based politics, better technical preparations, more scrutiny, decreasing levels of intercommunal violence[1] and an improved public awareness of the roles of institutions such as the IEBC and Judiciary.
[1] See the February 2018 Political Economy Analysis produced under the previous Deepening Democracy programme.

Multi-party politics were reintroduced in Kenya in the early 1990s.[2] In a context of weak institutions, a compromised electoral commission, pronounced inequality, inter-ethnic tensions and high levels of political corruption, multiparty elections were high stakes and divisive contests from the start.[3] Kenyan elections have come to be associated with extremely high political tension, inter-ethnic clashes, and disputed results.[4] Since the fall of the Moi government in 2002, the main risk has been post-election violence as a result of close elections, flawed processes and disputed outcomes.[5] This risk has often been exacerbated by changes to the election management body late in the election cycle.
[2] Following a short period of multi-party elections immediately before independence in 1964, the country became a one-party state. For the most part, elections held during this period did not allow voters to choose the party of government but did offer them a choice on their Member of Parliament from a set of candidates approved by the ruling party. The localised nature of these elections typically focussed the minds of voters and candidates on constituency-based issues, and away from national level political concerns. As a result, elections rapidly became “referenda” on the performance of the incumbent MP.
[3] Lacking other forms of political structure – such as trade unions or pre-existing opposition parties – through which to mobilise, most leaders fell back on personalised and ethnic networks to rally support. In turn, this exacerbated the political importance of ethnic identity, as the party system fragmented into a series of parties that predominantly represented the interests of one or two communities. Campaigning by these parties covered a divisive range of issues, e.g. land and government spending. This difficult context was exacerbated by vote-buying, intimidation, and political violence to hold on to power.
[4] Klopp and Kamungi, 2007
[5] Branch and Cheeseman, 2010

In 1992 and 1997, the worst of the violence occurred before the elections, as a result of ethnic clashes.

The 2007/8 election revealed how quickly post-election violence can spread in Kenya and the danger of having weak institutions to manage elections and conflict. Over 1,000 people died and 300,000 were internally displaced. Economic growth plummeted from 7.1% to 1.7% and regional trade was disrupted.[6] Following a government of national unity, an agreement on devolution, the intervention of the International Criminal Court and extensive investments in peacebuilding and police reform, the 2010 constitutional referendum and 2013 elections were generally peaceful at the national level.
[6] Much of this violence, especially in the Rift Valley had historical roots in competition for land and had antecedents in the ‘ethnic clashes’ of the 1992 and 1997 elections.

In 2013, devolution and the upholding of the national result by the new Supreme Court (which noted irregularities but that these were not substantial enough to have affected the overall result) contributed to a peaceful election overall, though controversy followed from another close election and the failure of new election technology to build public confidence. County level conflict in Tana River and Mandera was severe.[7]
[7] there were major spikes in conflict in some of the 47 newly formed counties, driven by ethnic competition for control of new county government. Over 400 people were killed in pre and post-election violence in Mandera and Tana River counties. Violence was also witnessed at lower levels across approximately a third of all counties.

The 2017 election[8] was highly contested and Kenya’s independent institutions, the IEBC and Judiciary, came under sustained attack from all sides of the political spectrum. 2016-18 witnessed high tension, frequent protests, violence and loss of up to 100 lives as a result of the actions and rhetoric of politicians on all sides, with some political actors using violence and intimidation as part of their strategies. It left Kenya deeply divided along ethnic and political lines with the tension continuing into 2018.[9]
[8] As in 2013, in the Kenyan election of 2017, voters simultaneously cast their ballots in six elections: Member of the National Assembly, Governor, Senator, Member of County Assembly, Women’s Representatives, and President.
[9] In line with previous elections, voting was conducted in an orderly and peaceful manner. However, the process descended into controversy during the tallying of ballots and the transmitting of results. As President Kenyatta moved into a strong lead, according to the digital votes electronically transmitted to an online count, the opposition alleged that the results processing server had been “hacked”. Although the domestic observers conducted a Parallel Vote Tabulation that confirmed the official result. Elections for the other five positions, including county governors and senators were significantly less controversial than the presidential vote. 2017 nonetheless saw a remarkably high number of election petitions in response both to the party primaries and to the final results for these positions.

A new team of IEBC Commissioners took office with just seven months to plan the August 2017 poll.[10] Procurement of equipment and ballot papers faced a number of legal challenges leading to delays. The final week before the August 2017 poll was marred by the torture and death of the IEBC ICT Director, Chris Msando.[11] On 11 August (while international observers did not find evidence to support the opposition’s claims) the Supreme Court ruled that the presidential election was null, void and invalid. This judgement, which was largely based on procedural flaws and the refusal of the IEBC to fully assist the investigation (to give access to the electronic servers), necessitated a re-run of the presidential election on 26 October 2017 and a review of some IEBC procedures. The opposition boycotted the October re-run.
[10] Lynch et al, 2017.
[11] Political disagreements persisted throughout the extended election period over a number of important features of the elections, including the printing of ballot papers, the use of technology, and the level at which results should be announced and become “official.” Relations between the security forces and local communities were strengthened in the run up to the election but deteriorated severely in conflict hotspots following the August poll.

On 9 March 2018 the President and leader of the opposition ‘shook hands,’ reconciled, and announced a ‘Building Bridges to Unity’ initiative (BBI) to identify reforms needed across 9 areas including ‘electoral justice’. A Task Force was established which undertook consultations and issued its report in November 2019.[12] Its main recommendation for electoral justice was to reconstitute the IEBC with Commissioners appointed on the basis on political party consultations (a return to the pre-2007 system). It also proposed a new Prime Minister position, to be appointed by the President from an elected member of parliament from the majority party. It also proposed a formal role for the loser of the presidential race leader who would become an ex-officio member of parliament and Leader of the Opposition. At the time of writing it is not yet clear how significantly the Building Bridges report will affect preparations for the 2022 election. A further process of consultation is underway. Some recommendations may be translated into bills and submitted to Parliament. There is also a possibility of a constitutional referendum if there is sufficient political consensus that one is required and on the proposed constitutional changes to be voted on.[13]
[12] Building bridges to a United Kenya: From a Nation of Blood ties to a Nation of Ideals. A report by the Presidential Taskforce on Building Bridges to Unity Advisory, October 2019.
[13] A referendum is required to amend the constitution in the following areas: supremacy of the constitution; territory of Kenya; sovereignty of the people; national values and principles of governance; the Bill of Rights; the term of office of the President; the independence of the Judiciary and other commissions and independent offices; the functions of the parliament; the objects, principles and structure of devolved government. Otherwise amendments can be made by parliament by a two -thirds vote in both Houses, or a popular initiative with the approval of a majority of county assemblies and a majority in each house or by national referendum.

The IEBC now finds itself, under-resourced, without a number of commissioners and without a CEO of the Secretariat and facing a potential overhaul if certain BBI recommendations are supported. It is also responsible for undertaking a constituency boundary review between 2020 and 2024, but not within a year of the 2022 election. While the Kenya National Bureau of Statistics (KNBS) released initial census data for county and constituency levels in October 2019, ward level data required for the boundary review has not yet been released. The IEBC plans to begin the review in 2020 but conclude it after the 2022 election. The IEBC commissioners have also stated their readiness to conduct a referendum if one is required.

The 2022 election is likely to be close, divisive and highly contested. In the absence of sufficient preparation and consensus among political elites, Kenya institutions and also domestic and international observers are likely to be attacked politically, as they were in 2017. The losing side will likely contest the result without sufficient evidence to fully substantiate their claim in court. As with elsewhere on the continent, a lack of a complete set of parallel results make it difficult to evidence claims of malpractice. The risks of violence are high.

The August 2017 elections were probably the best election technically that Kenya has held, but failures in the transparency of results transmission ultimately undermined the credibility of the election and confidence among the Kenyan public. Despite the continued uncertainty, there remains a strong argument for a DFID elections programme that will help ensure that the standards achieved and the lessons learned in 2017 are built on in 2022, in line with an election cycle approach, and that every effort is made to build consensus and avoid violence.

UK experience in supporting Kenyan elections to date

DFID’s support to the 2013 elections[14] was successful in contributing to establishing an improved electoral legal framework. It also contributed to strengthen a culture of peaceful voting, dispute resolution through the courts and an accepted transfer of power. Over 14.3 million voters registered, of which 86% turned out to vote. DFID programmes contributed[15] to more inclusive voter registration and better public order management.[16] 50% of voters registered were women.
[14] DFID has a strong track record of providing support in Kenya in this area through the Elections Management and Security Programme (EMAS) (2012-2013) and the Drivers of Accountability Programme (DAP) (2010-15) and Deepening Democracy Programme (DDP) (2015 – 2020 with elections component ending in 2018).
[15] Scored A in the DFID Project Completion Report.
[16] The police service’s collaboration with the IEBC in the run up and during election day was widely seen as excellent (EU observer report). The NDI August 2013 survey found that 65% of Kenyans assessed the contribution of the Kenyan Police as positive - a significant improvement from the 38% confidence level that existed in 2012.

An independent review of DFID’s Deepening Democracy Programme (DDP) undertaken in 2017 found that there were significant improvements in the administration and planning of the 2017 general elections.[17] These related to the procurement and deployment of technology, the number of women candidates, the provision of training and the running of polling stations, the process of voter registration and the resolution of electoral disputes. 90% of electronic kits worked during the August election and 98% during the re-run. Between the first and second polls in 2017, the IEBC also made a series of improvements to their procedures and protocols. Electoral disputes were all resolved by the Judiciary within 6 months (a total of 391 cases).
[17] DDP. Mid-Term-Review: Final Report, Sayara International for DFID Kenya, 30 September 2019

During 2017/18, the International Community remained united and was able to play a coordinated and effective role which contributed to: a peaceful end to the 2016 IEBC protests resulting in a new Commission taking office; ensuring the opposition participated in the August 2017 election; ensuring the opposition sought redress through the courts (rather than the streets) after its loss at that election; ensuring the government accepted the court’s decision; and, creating the conditions for the political agreement, the ‘handshake’, that followed.[18] The UK played a key role and has a clear comparative advantage in this sector.
[18] Kenyans on all sides, including the President and opposition leader, have since the handshake acknowledged the key role the international community played in supporting democracy and peace in Kenya.

Priorities

UK support will need to be strategic, targeted and begin early, building on lessons from 2017 and previous elections cycles. Robust prioritisation will be required.[19] We will need to closely coordinate with others and deliver through partners who can adapt to a fluid context as required.
[19] Work on improving public order policing and police accountability will be supported through another DFID Kenya programme

The UK will work with other diplomatic missions to emphasise the importance of broader factors in the consolidating democracy in Kenya, such as maintaining democratic competition, incentivising issues-based politics, strengthening independent institutions (including independent election monitoring) and promoting inclusion of women/people with disabilities.

This programme should focus at the national level, and for some activities have nationwide coverage.[20] It will aim to maintain high levels of Kenyan ownership and contribute to sustainable results. It will focus on how key institutions in Kenya work together to manage the 2022 elections and resolve disputes. We have agreed with other members of the international community that diplomatic and development efforts should support the process efficiently, with a focus on technical support for the application of lessons from 2017 and avoiding substitution of Government of Kenya responsibilities (such as funding core costs, staffing or procurement of equipment and supplies).
[20] Such as training IEBC staff at the local level or election monitoring

The lack of transparency with results transmission led to the court annulling the presidential poll and requiring a re-run. Transparency will be a key priority for the 2022 election.

This programme fits clearly with the UK Aid strategy and will support stability and prosperity objectives in Kenya. It will make a central contribution to the cross-government Business Plan for Kenya. It also aims to support the democratic process to deliver accountable government at all levels, and by extension poverty reduction.

At the Impact level this programme will contribute to increasing the chances of a credible, peaceful and inclusive constitutional referendum and 2022 general election (and boundary review and constitutional referendum if required).

At the Outcome level, the programme will aim to contribute to further improvements in the conduct of Kenyan elections, building on standards achieved to date and lessons learned. By the end of this programme we would expect to see evidence:
  1. Of an improved legal and policy framework and improved institutional coordination in management of the elections and disputes.
  2. That the 2022 elections are well-administered, and this is perceived by the population; and electoral disputes are effectively managed in a timely manner.
  3. That an enabling environment leads to more women and PWDs participating and elected in representative posts.
  4. That the electoral process is effectively monitored by international and domestic observers.

Strength of supporting evidence – global

There is a growing body of evidence globally on what works in election support programmes. We have drawn on this in the design of this business case and hope to make a further contribution to it.

There is evidence that donor support has helped to run more credible elections and prevented electoral violence.[21] There is evidence that efforts to build the capacity of electoral management bodies is rarely effective if short term[22] and that building capacity rather than replacing it is essential for ownership and sustainability.[23] The technical administration of elections can be measurably improved over time, though it requires long term targeted support over a number of election cycles.[24]
[21] The Evidence & Evaluation Base on the Impact of Election Assistance, part of internal DFID Guidance on elections, http://epe-insight/_layouts/QuestLinking/QuestLink.aspx?docid=4087509
[22] Chiroro, 2010
[23] UNDP (2012). Evaluation of UNDP Contribution to Strengthening Electoral Systems and Processes. UNDP
[24] An, 2006; De Tollenaere, 2006; De Zeeue, 2004

There is generally strong evidence of the positive impacts of election support programmes on the quality and credibility of individual elections. There are many cases worldwide where international electoral support was crucial to prevent undemocratic forces from performing mass manipulation of the results.[25] There is further evidence that election support programmes can reduce corruption and malpractice, that the presence of observers can positively influence election quality and that civil society can reduce clientelism.[26] Women’s political empowerment requires a long-term holistic approach to tackling multiple barriers and levels of gendered inequalities.[27]
[25] Tuccinardi et al. 2008, Peou, 2004, Wantchekon et al, 2006
[26] Tuccinardi et al. 2008, Peou, 2004, Wantchekon et al, 2006
[27] Newbury and Wallace 2015, Combaz 2016, O’Neil and Domingo 2016

However, ICAI have found that sustained national capacity to manage electoral processes has been slow to emerge and the impact on overall political development has been limited.[28] This evidence points to the need for election support to be part of a wider effort to strengthen governance and promote political maturity and accountability.
[28] Evaluation of DFID’s Electoral Support through UNDP, Independent Commission for Aid Impact (ICAI), 2012

Strength of supporting evidence - Kenya

There is a wealth of evidence from the 2017 elections in Kenya. We have drawn on this evidence extensively in the design of this business case.

We have commissioned advice on priorities for this programme in late 2019[29] building on more in-depth research by UK and Kenyan universities through the Rift Valley Institute[30] in 2017-18.[31]
[29] DDP programme: Kenya’s Continuing Quest for Credible Elections, November 2019
[30] funded by the DFID East African Research Hub (EARH)
[31] 14 articles published in the Journal of Eastern African Studies in 2019 in the Bibliography

The DDP Programme 2019 mid-term and annual reviews found evidence of the relevance and effectiveness of DFID support to the 2017 election. Overall, findings point to the UK making an effective contribution and focussing on the right areas. Further sources include evaluations by USAID, UNDP, IFES, IDLO, ELOG, the IEBC and the Carter Centre and EU election observation mission.[32]
[32] For a full list see the bibliography in Annex 1.

All sources show that donor interventions can help in maintaining the drive to reform that exists in Kenya and contain the risk of violent spill-overs. Starting early in the election cycle helps to build confidence with partners and manage risk.[33]
[33] DFID EARH: RVI 2017 Kenya Election Monitoring Report

The Rift Valley Institute research[34] confirmed that significant improvements were realised in the administration and planning of the 2017 general elections compared to 2013 elections. These related to the procurement and deployment of technology, the provision of training and the running of polling stations, dispute resolution and the process of voter registration. There is also evidence of improved IEBC effectiveness through early investments in its operational plan.[35] It identified that investment is still needed to build public confidence in the register of voters, further amend election laws, and to harmonise political party dispute resolution mechanisms and appeals process. It recommended promoting the development of a Code of Conduct for Political Parties with practical guidelines on how to fast-track women into office such as through use of female only lists for some seats and dedicated funds for female candidates.[36] These recommendations are reflected in the outputs 1-3 of the new programme.
[34] DFID EARH: RVI 2017 Kenya Election Monitoring Report
[35] For example improving warehousing. DDP: Post Elections Deep Dive: A review of UK contribution to 2017 Kenyan Elections, March 2018
[36] Some of the fiercest competition takes place at the stage of political party primaries and this is where opportunities to secure female candidates are missed.

Technology can help to improve an election and can make some forms of electoral malpractice more difficult but it cannot, in and of itself, ensure a credible and peaceful election. Efforts to build public confidence, strong IEBC management, transparent results transmission and well-trained impartial staff are essential.[37] The use of technology builds efficiency but not necessarily transparency. The transparency of results transmission and building skills in results transmission technologies[38] remain high priorities for 2022.[39] These recommendations are reflected in proposed outputs 1 and 3 of the new programme.
[37] The public face and statements of IEBC are critical. Poor communications and public relations once again undermined the IEBC’s reputation—in addition to a number of substantive mistakes. It is critical that in addition to strengthening internal procedures and cohesion—including communication between the commissioners, secretariat, permanent staff and temporary employees—the body works on its public engagement and further develops internal public relations capacity and expertise. DFID RVI 2017 Kenya election monitoring report
[38] The Judiciary would likely have be unprepared to examine computer servers had they been opened.
[39] DDP: Post Elections Deep Dive: A review of UK contribution to 2017 Kenyan Elections, March 2018

The IEBC post-election evaluation recommended: participatory cross-party consultations on electoral reforms early in the election cycle; an independent review of electoral technology considering security, sustainability, institutional ownership and effectiveness; ensuring that civic and voter education is a continuous exercise involving specialised state and non-state actors; beginning capacity building with key staff early in order to develop a shared set of professional ethics in advance of the politicised election period. These recommendations are reflected in the outputs 1-3 of the new programme.

The evaluation of USAID support to the 2017 elections found that the IEBC structure remains a significant impediment to effectiveness and transparency in particular the roles of Commissioners vis a vis the secretariat and nine departments with overlapping mandate. It recommended continuing to invest in strengthening parties’ internal tribunal mechanisms, and the appeals process through the IEBC, ORPP and Judiciary.[40] These recommendations are reflected in the outputs 1-2 of the new programme.
[40] If candidates find that primary victories achieved through cheating are subsequently overturned, it may help to deter this kind of behaviour in future: IFES Elections on Trial: The Effective Management of Election Disputes and Violations

The domestic Election Observation Group (ELOG) evaluation recommended better planning and timely roll-out of civic and voter education programmes is needed with better leadership and coordination by the IEBC.[41] The voter register also needs in-depth up-dating. IEBC and Parliament move quickly to ensure the operationalization and implementation of the Election Campaign Financing Act (2013) that Parliament should ensure that laws that guarantee the 2/3 gender threshold are in place. The Carter Centre evaluation of international election observation in 2017 recommended, reviewing training materials and building capacity in ICT use in election observation[42] such as for parallel voter tabulation. These recommendations are reflected in the outputs 3-4 of the new programme.
[41] ELOG Observation Report, 2017: One country, Two elections, Many voices. The Kenyan 2017 General Elections and the historic fresh presidential election
[42] Carter Centre 2018 report recommended the strengthening of CSO observation efforts.

Three DFID funded studies on women’s political participation in Kenya have generated valuable lessons. [43] There are signs that women are beginning to be regarded as serious contenders for more senior positions in the political hierarchy such as governors and senators.[44] However, increasing women’s representation in political leadership remains a major challenge. The overall proportion of elected seats going to women has only increased marginally.[45] It is important that women interested in politics begin early by building their visibility in their communities.[46] Increasing incentives for political parties to nominate women is also critical. It is important to invest early in supporting women as candidates, potential leaders and voters. [47] A code of conduct for political parties is needed with practical guidelines on how to fast-track women into office and within parties, such as through the use of female only lists for some seats and dedicated funds for female candidates.[48] Progress on campaign finance regulations would reduce the cost and therefore increase accessibility to less economically advantaged female (and male) candidates.[49] The media should be mobilised to counter public bias against women in leadership and to champion the achievements of women in politics and public service.[50] These recommendations are reflected in the outputs 1-3 of the programme.
[43] DDP: Post Elections Deep Dive: A review of UK contribution to 2017 Kenyan Elections, March 2018; DFID RVI 2017 Study of Women Political participation in Kenya, 2017; NDI A Gender Analysis of the 2017 Kenya General Elections. See also ‘50 Journeys: Stories of courage and transformation from women political leaders in Kenya’, Journey to Gender Parity in Political Representation: Search of a framework for the realization of the not more than two-thirds gender principle in Kenya’; ‘The Milestones: Equality and Inclusion in the 2017 Kenyan General Elections’; and ‘Promoting Participation of Special Interest Groups in the Electoral Cycle; Kenya’s 2017 General Election’. see bibliography for links.
[44] For the first time (in 2017 elections) women became Governors (3) and senators (3) compared to 2013 which had none. Cumulatively women comprised just 9.2% of the 1,835 elected individuals in 2017 a marginal increase from 7.7% in 2013.
[45] DFID EARH: RVI 2017 Kenya Election Monitoring Report
[46] According to RVI Study they recommend – ‘Champion the achievements of women in politics and public service through the media and annual wards to challenge the perception that men are more effective than women within political arena.’
[47] Often programmes targeting women begin late in the electoral cycle when their male counterparts are already campaigning in the communities. While training is useful and needed, it does not necessarily secure more numbers: NDI A Gender Analysis of the 2017 Kenya General Elections;
[48] The regional pattern of political party support in Kenya means that in many cases the fiercest competition takes place at the stage of primary elections. Political party structures are patriarchal and few have actively sought to increase the number and profile of women within their membership. Parties circumvent the spirit of the law through prioritizing male candidates for elective seats and women for nominated seats.
[49] DFID RVI 2017 Study of Women Political participation in Kenya, August 2017
[50] Women who have previously contested for political office are more likely to win office than newcomers to campaigns (owing to experience of campaign planning and outreach). Women who are nominated by political parties have a high chance of being elected at the end of their term. Hence the need to mobilise political parties to nominate more women. The programme should work with nominated, elected and the unsuccessful women from the 2017 elections period, as well as with men as allies to supporting women political representation.

Further sources of Kenya specific learning and evidence are annexed in the bibliography. DFID will continue to undertake robust political economy analysis and to use and generate evidence. If there is scope for additional research and knowledge generation beyond this programme, we will engage with the East African Research Hub to explore options for commissioning it.

Gender equality impact statement[51]
[51] Kenya’s new constitution and the Government’s Vision 2030 both address gender equality. For example, the Bill of Rights in the constitution affirms equal rights and non-discrimination, and the constitution embeds affirmative action aimed at improving equal participation in decision making. Women now constitute at least one third of all county assemblies. However, there are still considerable differences in the country between men and women’s possibilities to control and benefit from economic, social and political resources and structures. This is particularly an issue in the northern arid lands where women and girls and severely disadvantaged compared to the rest of Kenya.
To address the gender gaps in the political leadership, the programme will also focus on strengthening implementation of the constitutional gains, including the legal and electoral frameworks; addressing challenges to women’s political participation in elections, both as voters and candidates; and advocacy to reduce the discriminatory perception of women’s political participation in the media/ public domain; and to enhance safety and security of women during the election period. Gender equality initiatives under the programme will focus on enhancing the capacity of the electoral bodies and CSOs to achieve inclusivity for all citizens. A gender analysis will be conducted during the inception phase to inform a gendered approach to the programme using the following principles:
  1. Use a participatory approach that involves both female and male designed interventions, to ensure activities take into account differences in need, shape interventions and give due regard to the dimensions of equality and diversity.
  2. Integrate gender into the results framework. Outcomes and outputs will be measured using sex disaggregated data.
  3. Challenge and change negative ideas, beliefs and practices that promote gender discrimination.

Disability[52]
[52] 3.5% of the population (approximately 1.3 m people) have a disability. Kenya has taken steps to address disability inclusion, for example, in 2003, the Persons with Disabilities Act was enacted, providing a comprehensive law on rights, rehabilitation and equal opportunities for people with disabilities. Kenya also ratified the UN protocol on the Convention on Persons with Disabilities in 2008. Since then, Kenya has taken steps to introduce legislative, policy and administrative measures including: a review to mainstream disability in all laws and policies; annual targets so that 5% of employment opportunities go to people with disabilities; 30% of public contracts to people with disabilities. However, the situation of disabled and vulnerable people is still fragile and many services need to be provided, such as education, preventative care, and protection against sexual violence.
The programme will undertake a disability audit to ensure that the issues disabled citizens face are incorporated into programme design, e.g. to eliminate barriers to voting; increase registration for disabled voters; provide support to candidates with disabilities to stand for election. The results framework will take into account disability as well as indicators to measure PWDs leadership across key areas of governance (executive and county assemblies). This programme will be fully compliant with Kenyan disability legislation.

Youth
65% of Kenya’s population are under 35 and 40% under 15 years old. The programme will have a focus on youth participation in the democratic process and seek to involve youth in leadership roles and to engage young people in issues which affect them. The programme will coordinate closely with the evolving DFID Kenya youth strategy and will offer analysis on patterns of youth participation in the elections process.

Terrorism and financing
The risks of terrorist financing in this programme are low and within the DFID risk appetite. A thorough risk management framework will be applied to all partner staff recruitment and downstream partner selection. In addition, DFID Kenya will ensure:
  1. Due diligence and audit of all downstream partners
  2. Inclusion in all down-stream partner agreements and contracts, details of their obligations of all relevant terrorism legislation (and a recorded audit trail).
  3. Collaboration across government and reporting of any suspicions to the Counter Fraud and Whistleblowing Unit (CFWU) and National Crime Agency.

Public Sector Equality Duty.
The programme will support this through investments in government human resource systems. There are likely to be some positive impacts from this project in terms of ‘advancing equality of opportunity’ and eliminating prohibited conduct’ and against the protected characteristics (notably, age, disability, sex/gender, and race and ethnicity).,

Climate and Environment.
Kenya is highly vulnerable to drought, which currently costs 2.4%[53] of GDP per annum and may rise with the effects of climate change. If not addressed, climate change will hamper progress towards the sustainable development goals and disproportionately impact vulnerable groups, especially women and those living in the arid and semi-arid lands and coastal regions. The programme will contribute modestly to addressing this challenge by exploring opportunities to support cross party consensus on the climate and environment agenda.
[53] The World Bank calculates that on average, every seven years Kenya experiences a flood that costs about 5.5 percent of GDP), and every five years experiences a drought that costs about 8 percent of GDP. This translates to a direct long-term fiscal liability of about 2.4 percent GDP.

Partnership Principles.
We will use partnership principles throughout the programme to guide our partnership with government. Being closely associated with the Kenyan election poses many risks including reputational risks for Her Majesty’s Government (HMG) that we will monitor closely. We will ensure implementing partners deliver UK aid funded components of their programmes in line with our partnership principles. This programme will not put money through government systems.

Safeguarding.
The programme will comply with DFID’s Smart Rules on safeguarding and adopt a do no harm approach. It will deliberately seek to address harmful norms and practices, and amplify key messages and communications, drawing on learnings from DFID Kenya’s programmes and the recent IAD report recommendations. It will specifically focus on preventing violence against female voters and candidates.

Funding and Sustainability
This is a four year £7.5m programme. The proposed budget fits well with the spending profile of DFID Kenya at just under 2% of our annual bilateral spend (based on recent annual budgets ) and has been included in our spending commitments. Our decisions on programmatic support during implementation will be guided by the following considerations:
  1. Ensuring we do not pay for costs that the Government of Kenya should pay for, but rather add value though strengthening the technical capacity of Kenyan institutions
  2. Only paying for interventions where the UK is uniquely positioned to do so (not funding interventions that can be routinely funded by other donors)
  3. Maintaining an up to date political economy analysis of the Kenyan political context and election institutions

The Government of Kenya is committed to funding the entire costs of Kenyan elections. The UK in coordination with other donors in country will only provide strategic technical support to enhance the capacity of Kenyan institutions to carry out their mandates and use Kenyan taxpayers money effectively. This programme will support our long term and ever closer relationships with the Government of Kenya, key institutions and civil society which will help sustain results.

Through previous elections programmes, UK support has contributed to steadily improving the legal framework, effectiveness of institutions and credibility and peacefulness of Kenyan elections. We have seen a steady improvement in election management and sustainability of results. However, even after the 2022 election there may be a need to continue strategic programmes to assist Kenya to further improve on some, or all, of these areas. As improvements are made, citizen expectations are also raised, and ever more transparent and effective systems are needed. Given how destabilising Kenyan elections can be and given Kenya’s role as the most democratic and open government in the region, further assistance may be justified in the medium term.

This programme supports our wider cross-HMG work on peace and security and will support DFID’s new investment in community security, and specifically elections security and preventing election related violence, through the reducing Insecurity and Violent Extremism in Kenya (REINVENT) programme.

## B. Appraisal Case

This section first apprises the main intervention options for the programme and then defines 4 outputs with illustrative activities. A second stage of appraisal then considers how the programme can be best delivered. This is followed an economic appraisal, VFM statement and a proposed theory of change.

Stage 1 Appraisal - Intervention options

The strategic case above has identified that this programme should focus on how key institutions in Kenya work together to manage the 2022 election and resolve disputes. It should also contribute to building public confidence and promoting inclusion.[54] The programme should focus on applying lessons learned from 2017 (and elsewhere in the world) to help Kenyan institutions to build and improve on standards achieved to date.
[54] The UK has agreed with other members of the international community that international assistance should not substitute for the core responsibilities of the Government of Kenya such as buying equipment and supplies for the election (as Kenyan elections are already among the most expensive per capita in the world) though technical support is still important.

Aiming to have the most impact possible with limited resources, it is important to consider at the outset realistic options for intervention. We have determined that Kenyan elections are complex and will require a range of support to government and civil society. Owing to limited other donor funded programmes,[55] DFID cannot solely provide support to either state institutions to deliver or civil society to hold government to account. The programme will need to do both. The intervention options outlined below therefore consider where the primary investments should be:
[55] at the time of writing it appears that less funding will be available than in 2017, based on current estimated commitments from the EU, USAID, Canada and Finland at the Elections Donor Group
- Option 1- Cease funding to elections but continue political engagement
- Option 2: Invest primarily in technical assistance to independent institutions to help them plan and deliver a well-managed election and resolve disputes, on the assumption that improvements in their performance can have the most direct impact on public confidence.
- Option 3: Invest primarily in civil society and media efforts to inform and educate the public, on the assumption that more effective citizen participation and strengthened election monitoring will build accountability and thereby improve public confidence.
- Option 4: Invest primarily in strengthening political parties to improve inclusion (and election monitoring) on the assumption that behaviour change by political leaders, aspirants and parties can have the most impact on political culture and the conduct of elections (including respect for independent institutions), and through this improve public confidence.

These options have been considered in light of the available evidence of where we can have the most impact in contributing to a credible, peaceful and inclusive 2022 general election in Kenya.

Option 1- Cease funding to elections but continue political engagement
The UK could decide not to provide funding to support elections in Kenya and would still have a significant contribution to make through diplomatic efforts. The UK has previously played a lead role in the international community, calling for politicians and political parties to respect Kenya’s constitution and independent institutions, while also engaging more privately with political leaders to keep channels of communication open at times of heightened tensions and political divisions. The UK will need to continue to play this role, both because of the opportunity to positively influence peace and democracy in Kenya, but also because the UK will likely be targeted at some point during election campaigns and will need to respond, ideally in concert with other members of the international community.

This option is feasible but not recommended. The 2022 election presents a huge opportunity and risk for Kenya’s development prospects and a targeted elections programme could greatly increase the UK’s positive impact. There is also substantial evidence that previous UK investments have delivered results.

Option 2: Invest primarily in technical assistance to independent institutions to help them plan and deliver a well-managed election (and resolve disputes), on the assumption that improvements in their performance can have the most impact on public confidence.

There is a strong argument that the UK should prioritise support to independent institutions to help them plan and deliver a well-managed election. This is based on the premise that this will have the most impact on public confidence overall. Given the high level of public attention on the workings of these institutions and the political pressures they have faced in the past, there is a high risk that even relatively minor areas of weakness in the management of the election will have a disproportionately large effect on public confidence, the scale of political attacks on the institutions and the credibility of the election. Even relatively small targeted support can assist independent institutions to plan well and address technical weaknesses in advance of the election. Conversely, each weakness left insufficiently addressed will undermine the wider election process including reducing public confidence and leaving the institutions open to attack by dissatisfied politicians. It is important to be realistic, however. There are many factors that can undermine the performance of independent institutions, irrespective of UK support. For example, if they are underfunded, understaffed, or face political pressures and gaps in leadership at critical times, their performance will be significantly affected. To some extent they are likely to face all of these challenges.

This option is recommended. Evaluations of the 2017 election identified the clear contribution of donor programmes to strengthening the functioning of election institutions in Kenya, including the planning and management of elections and resolutions of disputes pre- and post-election. the primary focus on technical support to independent institutions to help them plan and deliver a well-managed election, should be complemented by support to civil society to mobilise effective participation and support effective independent monitoring.

Option 3: Invest primarily in civil society and media efforts to inform and educate the public, on the assumption that more effective citizen participation and strengthened election monitoring will build accountability build accountability and thereby improve public confidence.

There is a strong argument that civil society and media play an important role in elections. The public are often poorly informed and media reporting sometimes unprofessional which in turn exacerbates low public confidence. Both have a critical role in strengthening accountability for the election process itself providing independent monitoring and reporting which in turn strengthens the systems themselves and holds institutions and duty bearers to account.

However, the argument for UKAID to primarily support civil society and the media is weaker. There are a wider range of existing sources of potential support for the media and civil society to access in Kenya (though the sector remains under-funded) while in contrast there are very few programmes for supporting election institutions. Without effective core institutions, weaknesses in the process will undermine public confidence irrespective of outreach efforts. Also, there are insufficient UKAID resources available to conduct large scale civil society programmes to educate and mobilise the population to vote, and mixed, limited evidence that this builds confidence when election institutions remain weak. Nonetheless this programme should support civil society as a secondary objective, to mobilise effective participation and support effective independent monitoring, as recommended under option 2 above.

Option 4: Invest primarily in strengthening political parties to improve inclusion and dispute resolution (and election monitoring) on the assumption that behaviour change by political leaders, aspirants and parties can have the most impact on political culture and the conduct of elections (including respect for independent institutions), and through this improve public confidence.

In theory political parties could transform the political culture in Kenya. Some improvements in pre-election dispute resolution and the inclusion of women are evidenced from 2017. However, political parties in Kenya are still nascent with rapidly changing membership, coalitions and party candidates with each election cycle. Many have a strong regional (ethnic) base, though this is starting to change. The BBI report has recommended a stronger role for the Office of the Registrar of Political Parties (ORPP), and its decentralization to the local level (as well as a stronger role for parties in nominating IEBC commissioners). This programme could therefore make a timely contribution to strengthening the ORPP to further enhance inclusion and dispute resolution.

Support to the ORPP is justified but should not be the primary investment made by this programme.

Stage 1 Conclusion: Preferred option.

In light of the appraisal above and based on the strength of supporting evidence, the core objective of better managed elections and public confidence and trust requires first and foremost support to core institutions that risk being overwhelmed by the tasks ahead of them. A secondary investment in civil society and media is also justified to strengthen participation and accountability and will need to be carefully targeted, given limited resources. Finally, some support to political parties to strengthen inclusion is justified on a limited basis as this remains an experiment. The evidence base for supporting key institutions globally but also in Kenya is the strongest, with media and civil society roles also important but secondary and pilot support with political parties justified but on an experimental basis.

In light of the considerations above, the preferred option is option 2, to primarily invest in primarily in technical assistance to independent institutions to help them plan and deliver a well-managed election (and resolve disputes), on the assumption that improvements in their performance can have the most impact on public confidence. As a secondary investment, it will be important to support civil society and the media to undertake targeted voter education and domestic monitoring, as well as political parties to broaden inclusion (women and PWDs).

A substantial investment in real time risk monitoring and mitigation will be required. The programme will need to be able to flex and adapt to changing circumstance. The UK is aligned with other donors in prioritising external support. As noted above the Elections Donor Group has identified that there is likely to be less financial support available for the 2022 elections than there was for 2017 and prioritization will need to be robust.[56]
[56] It is likely that the EU and the UN will concentrate support on electoral institutions with the UK, and that USAID will remain involved across the board but increase emphasis on civil society support.

Programme scope

At the Impact level this programme will contribute to increasing the chances of a credible, peaceful and inclusive 2022 general election (and boundary review and constitutional referendum if required).

At the Outcome level, the programme will aim to contribute to further improvements in the conduct of Kenyan elections, building on standards achieved to date and lessons learned: By the end of this programme we would expect to see evidence:
  1. Of an improved legal and policy framework and improved institutional coordination in management of the elections and disputes.
  2. That the 2022 elections are well-administered, and this is perceived by the population; and electoral disputes are effectively managed in a timely manner.
  3. That an enabling environment leads to more women and persons with disabilities (PWDs) participating and elected in representative posts.
  4. That the electoral process is effectively monitored by international and domestic observers.

At the Output level, Previous work in Kenya and global experience, combined with inputs from Kenyan institutions and independent experts have led us to identify the following four high level results/outputs:
Meaningful electoral reforms early in the electoral cycle and effective coordination between the IEBC, Judiciary, ORPP and Parliament.
- Kenyan institutions improve on standards achieved in the 2017 election, and incorporate lessons learned for more effective planning, management, strategic communication and stakeholder engagement to build public trust. [57]
  [57] The IEBC will be supported to plan and manage the election process. The Judiciary will be supported to prepare for high quality and timely election dispute resolution. The Registrar of Political Parties will be supported to ensure political party compliance with the law.
- Increased participation of women, PWDs and young people as voters and standing for election.
- Strengthened domestic election observation and monitoring.

The programme will employ an electoral cycle approach, supporting the various stages of planning, execution and monitoring of the election and dispute resolution and evaluation in the post-election period. It will build on UK investments to date in strengthening Kenyan election processes and institutions, within previous election cycles and over the longer term. Specifically, the programme will support
- Legal and policy actions on systemic issues of the electoral system, boundary delimitation, the role of institutions, promotion of inclusiveness (outputs 1 and 2)
- Specific election planning and preparation related to strategic planning and communications, voter registers and registration, government procurement, training for IEBC judiciary and ORPP staff, and election monitors (outputs 2, 3 and 4)
- The execution of the election, including implementation by IEBC and specifically results transmission and observation by domestic observers (outputs 2, 3 and 4)
- The post-election period, judicial action on petitions, mediation if required, post-election evaluation, audit and lesson learning (all outputs).

Illustrative interventions[58]
[58] The illustrative interventions below are not exhaustive. The have been validated with key stakeholders and draw on evidence and research cited above. See Kenya’s Continuing Quest for Credible Elections, Elections Report and Policy Brief, November 2019, hereafter ‘the 2019 Policy Brief’

Output 1: Meaningful electoral reforms early in the electoral cycle and effective coordination between the IEBC, Judiciary, ORPP and Parliament.
- Provide technical support to IEBC, or its successor, to respond to reform priorities, working with Parliament[59] to ensure enabling legislation is in place to support a boundary review and referendum if required before 2022, and a more effective 2022 election.[60]
  [59] The Justice and Legal Affairs Committee (JLAC)
  [60] E.g to prioritize legal reforms and improve on the regulations for political party nomination processes (esp. Campaign Financing Law) as well as on the compliance with integrity criteria according to Chapter 6 of the Kenyan Constitution
- Support joint planning between IEBC, Judiciary and ORPP[61] to ensure effective coordination.
  [61] The 2019 Policy Brief recommended convening structured meetings of the Judiciary, relevant parliamentary committees, and political parties early in the electoral process in order to identify the challenges for ‘collective action’

Output 2: Kenyan institutions improve on standards achieved in the 2017 election, and incorporate lessons learned for more effective planning, management, strategic communication and stakeholder engagement to build public trust.[62]
[62] The IEBC will be supported to plan and manage the election process. The Judiciary will be supported to prepare for high quality and timely election dispute resolution. The Registrar of Political Parties will be supported to ensure political party compliance with the law.
- Support IEBC, or its successor, to restructure and more clearly define roles and relationships between the Commission and the Secretariat, and between departments within the secretariat, to improve procurement processes,[63] strengthen administrative structures and re-train staff.[64]
  [63] Increase transparency in addition to ensuring their process adhere to VFM policy
  [64] The 2019 Policy Brief recommended this so that the IEBC does not lose focus and institutional memory during this transition, especially to strengthen results counting, collation and transmission process to reduce the risk of future disputes. It noted that many of the improvements in 2017 came as a result of the building of more effective institutional systems.
- Support IEBC, or its successor, to deliver an improved strategic communications strategy, [65] an updated voter register,[66] better voter education, improved staff training, more transparent results transmission and better procurement.
  [65] IFES evaluation that the IEBC challenge with strategic communications was not only a capacity issue but also that the legal department is part of the communication and PR team. These functions need to be separated to give the coms department more room for responsive communications. The 2019 Policy Brief recommended investing in a robust communication strategy to increase public confidence.
  [66] KPMG reports made short-term, mid-term and long-term recommendations which IEBC will need to take forward working together with other government departments to ensure their data is valid. A credible register will boost confidence in the process and make IEBC’s works easier with less challenge. See KPMG Independent Audit of the Voter Register
- Support the ORPP and Judiciary to prepare for high quality and timely pre- and post- election dispute resolution,[67] and compliance with the law.
  [67] The 2010 Constitution imposed a two-way electoral dispute resolution mechanism at the pre-election and the post-election stage. Dispute Resolution: In the pre-election phase, the jurisdiction for electoral dispute resolution is vested on the Political Parties Dispute Committees and the Political Parties Dispute Tribunal (PPDT). In the election and post-election phase, IEBC is vested with the jurisdiction of resolving disputes arising from party nominations while the judiciary exercises the appellate jurisdiction over decisions of the Tribunals and post-election dispute resolution. looked at within the context of 2013 and 2017 elections.

Output 3: Increased participation of women, PWDs and young people as voters and standing for election.
- Support IEBC, civil society and the media to plan and implement civic and voter education early in the election cycle,[68] with a focus on improving access to accurate information (and countering disinformation) with a focus on women, PWDs and youth.[69]
  [68] IEBC curriculum needs to consider PWDs and ICT
  [69] The 2019 Policy Brief recommended that voter registration among young people is most effectively done by working through civil society and media organisations that already have strong networks among younger Kenyans.
- Support the ORPP[70] to support political parties to create a favourable environment for women candidates.[71]
  [70] assistance to strengthen its own structure, systems and operations.
  [71] Political parties also hold the key to youth, PWD, youth and women’s entry and effective participation in politics. They could make more inclusive their candidate nomination processes to enhance women’s participation, implement party quotas, apply inclusivity principles in the party leadership and decision-making structures, enhance internal dispute resolution and

Output 4: Strengthened domestic election observation and monitoring.
- Support early planning and organization for robust domestic election observation[72] and oversight to increase integrity, transparency and accountability of the electoral process.[73]
  [72] The 2019 Policy Brief recommended funding an expansion of domestic monitoring to make it more comprehensive and inclusive in terms of reach and coverage. It noted that since 2007, the size of the domestic monitoring effort has been reduced, with greater focus on the running of a parallel vote tabulation (PVT) based on a sample of polling stations. As a result, domestic observers now cover less than a quarter of all stations.
  [73] As well as gaps in the legal and electoral frameworks and non-implementation of constitutional gender gains on inclusive representation; challenges to women’s political participation in elections, both as voters and candidates; discriminatory perceptions of women’s political participation in the media and the public domain, and safety and security of women during the election period.
- Support improved protocols for observation related to results transmission monitoring.[74] Support all stakeholders to develop technical skills to better understand result transmission technology (e.g. build ICT standards to enable forensic auditing).
  [74] The 2019 Policy Brief recommended that ‘If election technology is to be used again, DFID and other donors should provide stronger support to civil society groups and domestic observers more effectively to monitor and evaluate its usefulness. In particular, this should include building a common understanding within the main political parties, civil society groups and observers about how technology is supposed to work and developing an index of what constitutes acceptable performance (in terms of the percentage of polling stations with kits, the percentage of kits that work, usability of kits, level of satisfaction with usability and performance). It will also be important to build the skills and experience of domestic and international observers regarding how to monitor new election technology, working with observers and civil society groups to better understand how digital process can be observed both at the national (IEBC) and local (polling station) levels.
- Support ORPP to work with political parties to plan for training and deployment of party agents.

The programme will also engage with political parties to create an enabling environment (e.g. on campaign financing, gender and inclusion), and Political Party Liaison committees and the Political Party Dispute Tribunal (e.g. on dispute resolution).

Following approval of this business case, the DFID Kenya Governance and Security team will consult further with programme stakeholders develop to develop a results framework. The above outputs may be adjusted if needed to provide as clear and enabling a framework for the programme as needed.

There are many variables in the Kenyan context that may affect a credible, peaceful and inclusive 2022 general election, most significantly the actions of political leaders. The programmes contribution to the impact level is not therefore certain, and not all gains that are achieved at the output and outcome level will be sustained. From previous experience, significant cross-HMG working is required to contribute effectively to the intended impact, of which this programme is a core component. This will be achieved through the Political-Governance Group at the High Commission, which is chaired by the High Commissioner and involves all relevant political and governance advisors from the Foreign Office and DFID and other government departments as required. The slow but steady institutionalisation of better and better practice has proven to be sustained beyond the life of previous programmes and this should prove to be the case again, with this programme contributing to the long-term capacity of a wide range of Kenyan stakeholders to manage elections effectively.

The next section will appraise four options for how this programme can be effectively delivered. It will identify which interventions and delivery modalities will provide the greater return on investment and appraise the quality of supporting evidence and significance of the risks involved. It will provide a more detailed value for money argument for the preferred option (identifying specific cost drivers to be monitored during implementation) and will frame a programme theory of change to focus implementation efforts and unpack its assumptions.

To deliver the 4 programme outputs and outcomes outlined in the strategic case above, DFID requires implementing partners that will be able to:
  1. Provide technical support to government institutions to build on lessons from Kenya and other countries and improve standards (e.g. on transparent results transmission)
  2. Facilitate inter-institutional collaboration (e.g. between the IEBC, Judiciary and ORPP)
  3. Work with political parties and aspirants who are women, youth and PWDs
  4. Efficiently support targeted education and mobilization of voters.
  5. Support independent civil society domestic election observation.

Stage 2 Appraisal: Delivery options

Previous election support programmes in Kenya funded by the UK and other donors have proved that multilateral and non-profit organizations can all deliver a range of support to Kenyan government and non-government partners to strengthen electoral processes.

DFID Kenya has considered putting all programme resources into a new UN Basket Fund for Elections. But our experience from the UN Basket Fund on Elections set up to support the 2017 election was that procurement timelines and decision-making were slow and the programme’s technical approaches did not adapt flexibly to rapid changes in the political context. Achieving clear financial reporting, including value for money (VFM) reporting was also challenging and time consuming. We have therefore also ruled out this option. The UN Basket Fund did provide a common platform for donor support, but this can also be achieved by strong donor coordination.

DFID Kenya also considered procuring a private sector supplier to manage technical assistance and downstream partnerships. We have ruled out this option at the outset given that there are already many expert non-profit organisations available with long term election expertise in Kenya, that therefore offer good VFM and long-term sustainability of learning and application of good practice in this sector.

We also considered directly hiring experts and seconding them to Kenyan institutions but have also ruled out this option at the start, owing to platform pressures at the BHC in Nairobi, capacity constraints and the high level of political and reputational risk of direct government to government partnership on elections.

The four feasible options therefore considered below are:
- Option 1: A number of expert international and national non-profit civil society organizations, directly managed by DFID.
- Option 2: A non-profit consortium to manage the entire programme.
- Option 3: A non-profit consortium with a ringfenced budget for additional downstream partnerships to be managed by the consortium with DFID approval.
- Option 4: A non-profit consortium plus an allocation for the UN Basket Fund.

The potential strengths and weaknesses of each of these delivery options have been assessed against nine criteria:
- Criteria 1: Ability to strengthen intergovernmental relations.
- Criteria 2: Ability to work with IEBC and political parties.
- Criteria 3: Ability to strengthen civil society to improve citizen participation and election monitoring.
- Criteria 4: Ability to source and deploy high quality technical assistance.
- Criteria 5: Ability to start early, and level of DFID staff management time required.
- Criteria 6: Flexibility, innovation, use of evidence and responsiveness.
- Criteria 7: Longer term sustainability.
- Criteria 8: Simplicity and aid effectiveness.
- Criteria 9: Ability to offer robust VFM.

The outcomes are given in the table below and explained the subsequent paragraphs. Scores are from 1-5: where 1 is very weak and 5 is very strong.

	1	2	3	4	5	6	7	8	9	Totals
Option 1: a select number of expert international and national non-profit CSOs, directly managed	4	4	3	4	2	3	2	2	4	28
Option 2: a non-profit consortium to manage the entire programme	3	4	3	4	4	3	3	4	4	32
Option 3: a non-profit consortium with a ringfenced budget for additional downstream partnerships	4	4	4	4	3	4	4	3	4	34
Option 4: a non-profit consortium (2 or 3 above) plus an allocation for the UN basket fund.	5	4	3	4	3	4	4	3	4	34

Option 1: Provide support through a select number of expert international and national non-profit civil society organizations, each directly managed by DFID
DFID has had a good experience with non-profit organizations working on elections throughout the 2017 Kenya elections cycle. We were able to effectively monitor and influence technical approaches and delivery, directly manage risks and respond to changes in the political context, and directly account for UK funds and take action to ensure VFM. This option of DFID directly managing a select number of expert international and national non-profit CSOs, would give DFID quality control over partnerships and programme interventions.[75] Robust competition would lead to partnerships that can deliver the best potential results and VfM throughout the programme implementation.
[75] If partners are selected over the life of the programme, this would also enable maximum responsiveness to change in the Kenyan context and to emerging priorities identified though the UK’s engagement with Kenyan institutions and stakeholders.

However, this option would require a high level of DFID programme management time to ensure robust due diligence and compliance of multiple partners. This in turn would reduce the time available for DFID staff to advise and work closely with Kenyan institutions and the international community and limit our influence and impact overall. Overall this option scored highly on responsiveness to government and lowest on efficiency owing to the high DFID management burden entailed. This option is not preferred.

Option 2: Provide support through a non-profit consortium to manage the entire programme.
This option retains the benefit of competitive selection of non-for-profit partners in terms of identifying those that can deliver strong results and ensure VFM. It also reduces the management burden for DFID by reducing the number of agreements to be signed and individual partnerships to be managed (criteria 8) and therefore would enable more work to begin early (criteria 5).

This option scores higher than option 1. However, while this option simplifies the management required by DFID, it yet limits the potential responsiveness of the programme to the rapidly changing political context (for example an increased likelihood of violence) which could be addressed by keep some funding set aside for additional partnerships considered under options 3 and 4 below.

Option 3: Provide support through a non-profit consortium with a ringfenced budget for downstream partnerships to managed by the consortium with DFID approval.
This option retains the main benefit of option 2 in terms of simplifying the management burden of the programme. It also aims to ensure additional partnerships can be established where needed, using a ring-fenced budget, to ensure the programme is responsive to the changing context. A limited number of downstream partners would be identified by the consortium lead, at key times during implementation with DFID concurrence, and added to the consortium (for example to provide surge support is additional support for a referendum or boundary review is required, or to add additional support to domestic monitoring, or mediation efforts if required).

This option received a joint top score with option 4 below, scoring higher under criteria 3: the ability to strengthen civil society to improve citizen participation and election monitoring (as experience from 2017, demonstrated that domestic election monitoring work can be most efficiently supported directly by a non-profit consortium). It scored lower on criteria 1: ability to strengthen intergovernmental relations, as option 4 has the additional benefit of strengthening the range of donor technical engagement across key election institutions. The trade-offs between the two highest scoring options (3 and 4) will be considered below.

Option 4: Provide support through one of the CSO based options above with an additional allocation for a direct agreement between DFID and a multilateral organisation.
This option would retain the benefits of options 2 and 3 above, but also enable DFID to offer some support to a UN programme (in addition to our core UN funding) which would strengthen our joint donor working on some areas of election support. Adding this component does increase the management burden for DFID and adds complexity to the programme, but it also enhances aid effectiveness through supporting a joint donor funded programme. This option scores highest on criteria 1, as it maximises our engagement and influence across key government institutions.

We assume that a UN programme will be feasible, although at the time of writing the gap between available donor funds and the draft UN proposal remains large and further prioritization and joint donor engagement will be needed to arrive at a viable proposal. If a viable UN programme does not materialise, the ‘additional allocation for a direct agreement between DFID and a multilateral organisation’ could be transferred to the non-profit consortium to manage (we would revert to option 3). By allocating a relatively small portion of the programme budget to this component DFID would not undermine our primary investment though a non-profit consortium, while influencing robust prioritization of the UN programme. Given this option has achieved a joint high score with option 3, the trade-offs between these two highest scoring options will be considered below.

Stage 2 Conclusion: Approach to Delivery

As outlined above options 3 and 4 achieved a joint high score. Under both options a non-profit consortium would lead implementation and deliver directly, but also manage a fund for downstream partnerships. During the 2017 elections, we found that the expertise provided by specialist non-profit organisations was most highly valued by election institutions. Furthermore, DFID Kenya was able to effectively monitor and influence technical approaches and delivery, directly manage risks, respond to changes in the political context, account for UK funds and take action to ensure VFM. A consortium arrangement will help to foster collaboration between implementing partners and reduce the management burden on DFID, which will enable more time to be spent on influencing with Kenyan stakeholders and institutions and the wider international community. The responsiveness of the consortium can be enhanced by providing a ring-fenced budget for strategic additional partnerships to be identified when changes in the context might require this.

The key factor in choosing option 3 or 4, is whether to make a modest contribution to a UN Basket Fund for Elections, which is currently under design. Option 4 proposes this with the aim of ensuring the programme maximises its engagement across key government institutions and leverages other donor funding through making a modest contribution to a UN programme. The argument for not doing so, is that it requires time, effort and resources to direct the UN programme and make it effective and reduces funding available to the non-profit consortium.

Option 4 is recommended. It is worth the additional time, effort and resources to be part of, and influential in, a multi-donor UN Basket Fund on Elections. A modest contribution of £1.25m is proposed for the UN Basket Fund on Elections. However, as this UN programme is still under design, no firm commitment can be made now. If a credible programme is developed, that is well prioritised and adds value to the work of the non-profit consortium and offers good VFM, a formal commitment may be made. If this is not the case, the £1.25m would be added to DFID’s agreement with the non-profit consortium and additional expected results added to the terms of reference for the consortium.

An illustrative breakdown of the proposed budget is therefore as follows:
  1. Consortium £5m
  2. Budget for downstream partnerships £1m
  3. Budget for multilateral support £1.25m
  4. Evaluations and audits £0.25m

We will not use UK taxpayer money to pay for any costs that are the responsibility of the Kenyan Government. Based on experience, we will support expert international and national civil society organisations, and the UN, to engage with Kenya’s independent institutions to add value to the quality of elections planning and management. This approach also enables us to better monitor the context, influence the process, manage risks and respond to changes in the political context.

Implementing Partner/modality	Main Project Elements
Non-Profit Consortium. / Accountable grant with an NGO Consortium (£6m)	OP 1: Meaningful electoral reforms early in the electoral cycle and effective coordination between the IEBC, Judiciary, ORPP and Parliament. / OP 2: Kenyan institutions improve on standards achieved in the 2017 election, and incorporate lessons learned for more effective planning, management, strategic communication and stakeholder engagement to build public trust. / OP 3: Increased participation of women, PWDs and young people as voters and standing for election. / OP 4: Strengthened domestic election observation and monitoring.
UN Basket Fund for Elections (1.25m)	OP 1: Strengthen Inter-Governmental relations / OP 2: Support select components of technical assistance to Kenyan institutions to build on standards and lessons as agreed with other donors. / OP 3: Support components of increasing inclusion – such as UNWOMEN’s work with female candidates.

Economic Appraisal

We have assessed that the programme is needed. The preferred option will deliver high quality and responsive technical assistance to government as well as efficiently support civil society. It will be most effective delivered through a combination of a non-profit consortium with a modest contribution to a UN Basket Fund is a viable programme can be agreed.

More detailed VFM assessments follow in the sections below. At this point we consider the overall economic argument for proceeding with this preferred option as opposed to ceasing funding and simply working politically. At a cost of £7.5m, we assess that this programme will offer good VFM.

1. Not implementing this programme would save this amount, but would have negative impacts including increasing the risks that:
  1. 2022 elections fail to sustain the technical gains made in 2013 and 2017 and experiences a repeat of the 2018 political stalemate, or worse, the 2008 post-election violence.[76]
    [76] In a worst-case scenario, the post-election violence in 2008 provides an approximation of the costs of non-intervention by all parties. Post-election violence led to over 1,000 deaths, the internal displacement of around 350,000 people and disrupted trade and economic growth in Kenya, Uganda, Rwanda, Burundi and Eastern Congo. GPD growth reduced to 0% in 2008
  2. Election Institutions operate less effectively and are overwhelmed by political attacks and a lack of public confidence leading to a result that is not accepted by a significant part of the political elite and population.
  3. Inefficient management of elections increase the administration costs of the election itself and wasteful expenditure and questionable procurement, which in turn increase the number of protests and legal challenges in the post-election period, all of which are costly for the Kenyan government and taxpayers.[77]
    [77] As demonstrated by the ‘Chickengate’ scandal (http://www.printweek.com/print-week/news/1148334/smith-ouzman-denies-paying-gbp400k-bribes-chickengate) and the 2018 Auditor General’s report over the procurement of election materials (which revealed over 9bn KSH unaccounted for), weak election administration, which is more costly than necessary, is much more likely. Both 2013 and 2017 Kenya’s polls were rated to be the most expensive in the world, due to high cost of voter administration per person (around £15.57 compared to £1.25 - £1.88 in advanced democracies such as the UK and US), administrative inefficiencies and misappropriation of funds. The 2017 Kenya’s elections (both the August elections and repeat presidential elections in October 2017) cost KSH 60 billion (USD 600 million).
  4. Contested results lead to instability and increased political risk for investors, reducing investment in Kenya and economic growth.
  5. There are also much broader costs to society from the erosion of trust in the democratic process that results from poorly run elections, including negative impacts on poverty reduction and efforts to reduce corruption and inefficiency in the Kenyan system.

1. If this programme is successful it would yield good returns for our investment, and more than cover its cost. We would expect to see:
  1. A well-planned and managed election with reduced cost to the Kenyan taxpayer.
  2. Disputes resolved through due process such as through the ORPP pre-election and Judicial committee on elections post-election and low levels of violence across the country
  3. Limited negative impacts on investment and GDP growth
  4. An increased focus on development policy and poverty reduction in political campaigns, and as a focus of government business post 2022, as well as civil society and opposition efforts to hold government to account.

VFM statement for the preferred option

This programme offers good value for money. It will directly contribute to HMG priorities in Kenya and contribute to the sustainability of poverty reduction efforts. The choice of delivery partners maximises the programme’s ability to deliver effective assistance.

Cost effectiveness. At the highest level of cost effectiveness, the programme will ensure VFM is realized through promoting principles of development effectiveness including strong donor coordination and alignment with priorities of the Kenyan election institutions and building their institutional capacity. Given the complex nature of election programming we will promote adaptive programming to encourage implementing partners to experiment with different ways of delivering results more cost-effectively. Drawing from DDP’s mid-term review we will ensure that partners consider sustainability of their intervention to ensure cost effectiveness. We will also strengthen the linkages of this programme across DFID, HMG and other donors to ensure harmonization of technical, political and diplomatic efforts.

VFM will be ensured by allocating funding based on a continuous assessment of where the programme can have the most impact, both in terms of need and also potential for effectiveness. A continuous dialogue with government institutions and national level civil society will inform this assessment. Advice from election experts will also be regularly sought. We will second an A2L governance advisor to the non-profit consortium to ensure we do not subcontract out our engagement with key institutions and will continue to also facilitate high level engagement with the High Commission, other heads of mission and our DFID head of office.

We will aim to measure cost effectiveness by tracking changes in
  1. Inter-institutional cooperation
  2. Progress of legal and policy reform
  3. Capacity of core institutions
  4. Capacity civil society domestic monitors
  5. Effectiveness of delivery of core functions throughout the election cycle (ie updating the voter register, procurement, voter education, strategic communications, results transmission, etc)
  6. Public confidence and perceptions

Performance of implementing partners will be managed by DFID through a regular review of programme results, approaches and learning and a staggered commitment of programme resources to ensure they are directed to areas where implementing partners are demonstrating a clear ability to deliver results. More specifically we will assess implementing partner performance based on key performance indicators such as the following:
  1. Quality of political and technical analysis
  2. Effective generation and use of evidence
  3. Quality of technical approaches (including ability to deliver responsive bespoke support)
  4. Output and outcome level results achieved
  5. Strength of relationships with government stakeholders
  6. Ability to prioritise to ensure responsive adaptive programming and VFM
  7. Ability to coordinate and work with others

To enhance the programme’s effectiveness, DFID staff will work with colleagues across DFID and across HMG through the Political Governance group.

Efficiency. The programme’s efficiency will be ensured through a regular review of programme results and costs, to establish which investments and output level results are contributing most directly to outcomes and impact. Resources will be allocated based on performance over the life of the programme. Programme efficiency will be ensured by tracking implementing partner performance against a range of indicators and benchmarks to enable us to compare results and the costs of achieving these results, and to direct resources to implementing partners that are having the most impact. We will establish benchmarks to measure the speed, quality and quantity of assistance provided to project beneficiaries and will also compare the overall cost of the results achieved between types of partner, types of intervention and significance of results. External benchmarking against other similar programmes delivered in other countries will also be undertaken where possible. We will also focus on strong coordination and coherence of implementing partner interventions under this programme and with other donor funded programmes.

Economy: This programme will benchmark and compare key costs of providing national and international staff and consultants, transport, accommodation, workshops and other costs, throughout the life of the programme.

Equity: this programme will focus on inclusion of historically marginalised sectors of society including women, youth and PWDs. We will ensure the logframe has specific indicators to measure inclusion and we will seek to use and generate more evidence on barriers to inclusion.

We will select a consortium, downstream partners and components of a UN Basket Fund for Elections based on a thorough VFM assessment and this will be continuously reviewed over the life of the programme and adjustments made as needed to ensure strong VFM.

Theory of change

The programme’s theory of change aims at a more credible, peaceful and inclusive 2022 election at the impact level. The programme will work at higher levels of government and with independent civil society groups to build an enabling environment for effective elections. We will contribute to this by investing at the outcome level in improvements in institutional coordination and effectiveness and improved participation and independent monitoring.

To achieve these outcomes, the programme is organised around 4 outputs, which each require specific interventions under this business case. An improved legal and policy framework and improved inter-institutional coordination (output 1) requires early efforts to plan and agree approaches among key institutions. This investment proved an essential contribution to the improved management of the 2017 elections including the process of pre and post-election dispute resolution. Better managed elections (output 2) requires good planning and execution of the roles and functions of election institutions (including improving voter registers and registration, procedures for polling day and results transmission). This is a huge challenge and likely to be the main investment made by this programme. Improving inclusion and monitoring (outputs 3 and 4) are long-term challenges and require investment with political parties and civil society with each new election cycle to strengthen their role and impact.

Evidence of the effectiveness of programmatic investments in these output areas has been cited in the sections above. Evidence of their sustained impact at the outcome and impact level is more mixed. However, the generation of more evidence is a key priority for the programme and it will contribute to a growing body of evidence on Kenyan elections.

There are many assumptions underpinning this theory of change. This theory of change and key assumptions will be tested and reviewed periodically throughout the life of the programme to ensure the programme adapts, learns and remains relevant and focussed.

In planning support improve the legal and policy framework and institutional coordination (output 1) we have assumed that sufficient political consensus will emerge on the recommendation of the BBI report, and other pre-existing proposals, to allow reform bills to pass through parliament (or a referendum if required). If this is not the case, we assume that more minor reforms (such as those we have supported in 2019 under the DDP Programme which enable the IEBC to better plan for a referendum and boundary review) will continue to be feasible. If political reactions to the BBI report create a stalemate on all reforms and continued uncertainty over the future of the IEBC, then a significant increase in political engagement by the international community will be required.

In order to contribute to a well-administered 2022 elections (output 2), we have assumed that the IEBC, or its successor receives sufficient political and financial support from the government to undertake essential tasks prior to the election and ensure sufficient trained staff are in place to deliver. If political consensus determines that a reconstitution of the election management body is essential, then we assume this will happen early enough in the election cycle to enable it to function effectively prior to 2022. To mitigate the impact of this uncertainly, the programme will work with the staff of the IEBC secretariat as well as the commissioners to ensure that the plans and capacity developed will be relevant to any new commission. If the uncertainly persists close to the 2022 election, more political engagement will be needed and the programme strategy will need adjustment.

In aiming to contribute to an enabling environment that leads to more women and PWDs elected in representative posts (output 3), we have assumed that lessons from 2017 can be applied and that political parties in particular are open to engaging on this agenda and with the emerging evidence of what works.[78]
[78] noting results from 2017 were ultimately less progressive than 2013

In supporting strengthened domestic election observation and monitoring (output 4) We have assumed that other development partners can be mobilised early to commit funding and expertise, owing to the cost and effort required being significantly beyond the scope of this programme.

## C. Commercial Case

This section sets out the commercial arrangements for managing the preferred delivery option for this programme. As set out in the appraisal case above, the programme will be delivered through an accountable grant with a non-profit consortium and an MoU with the UN if a viable programme is agreed.

Non-profit consortium, selection through a competitive accountable grants process

Following approval of this business case, DFID Kenya will develop detailed terms of reference (ToR) for a competitive process of selecting the non-profit consortium. Due to the varied scope of work to be delivered, potential bidders will be encouraged to form a consortium, with each organization bringing their areas of strength into the programme. A competitive accountable grants process will enable a consortium to develop that has the strongest potential to deliver on the terms of reference.

DFID will publish this business case and then issue an open call for proposals. We will ensure that a wide range of potential implementing partners are informed through the Elections Donor Group and our state and civil society networks, as well as publishing documents on DFID’s supplier portal. We will seek cross-HMG views before proceeding to, owing to the shared cross-HMG interest in elections and shared political and reputational risk.

The call will specify an initial inception period of 3 months to enable the consortium lead to finalize agreements with other consortium partners and finalize work plans. DFID will set out clear expectations in terms of:
- VFM: bidders will be expected to specify how they propose to drive down the cost of implementation (economy) while ensuring there is gender, youth and disability inclusion.
- Innovation/sustainable exit strategy: bidders will need to propose innovative, sustainable ways to attain the specified outcomes, as well as a well-defined exit strategy. Capacity to deliver local solutions and past performance and likelihood of delivering results, as well as the strength of the methodology, will be key factors in the selection process

Based on previous experience, there are several election focused organizations that already have experience, networks and infrastructure in the country and have demonstrated the ability to build capacity, and work in partnership with a wide range of stakeholders to support Kenyan elections.

The selection of a non-profit consortium will follow the UK Cabinet Office’s grant standards.[79] The accountable grant agreement with the consortium lead, in addition to the minimum standards specified by the Cabinet Office, will retain the flexibility to scale up or down activities depending on the consortium’s performance, judged against pre-agreed key performance (output) indicators. DFID will, prior to grant award, fully scrutinize and challenge budgets and overhead costs in line with the allowable costs policy, ensuring resourcing and balance of inputs is appropriate to deliver the programme.
[79] Published on 2 December 2016 - https://www.gov.uk/government/publications/grants-standards/grant-standards

During the selection DFID will assess the proposals based on the bidders’ understanding of the ToR, ability to deliver, ability to offer strong VFM and past performance. Prior to awarding the grant, DFID will carry out a due diligence assessments using the new guidance, to ascertain fiduciary risk and the organization’s ability to deliver the programme. A risk mitigation plan will be developed and monitored in partnership with the grantee based on the outcome of the due diligence assessment. The grantee will be expected to carry out due diligence assessments on any sub-contractors, based on DFID’s due diligence framework. It is expected that the sub-grantees will implement activities directly, without any further sub-contracts or grants, except for specialized short-term technical assistance on a need basis.

DFID will use the revised accountable grant document for this arrangement. Accountable grant templates were revised in June 2019 following a review of DFID’s programme arrangements. The changes ensure that all grants are, at the minimum, compliant with UK legislation, Cabinet Office grant standards and the Smart Rules. The document specifies DFID’s standards on eligible expenditure, funds disbursement and financial reporting, audits and assurance, assets and inventory management, communication and branding, fraud, corruption, bribery, and other misuse of funds, among others. These standards including safeguarding will be discussed with the implementing partner prior to grant award.

Due diligence on potential partners will be done comprehensively. Quarterly payments will be on actual costs. Progress in implementation will be measured against agreed key performance indicators.

Potential support to a UN Basket Fund for Elections, through a memorandum of understanding (MoU)

A DFID MoU with the UN will be in the form of a contribution arrangement, which draws on the overarching framework agreement agreed between DFID and the UN headquarters. As part of the UN Reforms agenda, DFID centrally has generated agreements that are more demanding of the UN in terms of risk management, fraud prevention, transparency and accountability, as well as new performance agreements which set out the collective reforms that agencies must deliver to receive full UK funding.[80]
[80] In light of the appraisal above, a programme theory of change is outlined below. Over a seven-year timeframe this will require a regular process of context and political economy analysis, a regular review of programme results, approaches and learning and a staggered commitment of programme resources to ensure they are directed to priority area where counties and implementing partners are demonstrating results.

If a contribution to the UN Basket Fund for Elections can be agreed, this programme will use the most recent agreement templates provided centrally. Currently, there is little scope to negotiate on the administrative fees as this is negotiated and agreed at headquarter level – however, there will be no additional overhead fee charged. DFID will commit funds based on performance. As with the accountable grant, DFID will regularly assess performance and adjust funding commitments in response. DFID will carry out a due diligence assessment to further ascertain their ability to deliver and comply with safeguarding guidance. A risk mitigation strategy will be jointly agreed with UNDP following the outcome of the due diligence assessment prior to any disbursement. This will include safeguarding risk assessments.

DFID would only sign annual commitments with the UN and only renew based on performance and delivery of quality results. The UN will establish a steering committee including government which will meet quarterly to assess progress on results and approve any adjustments to the programme. DFID will also carry out independent spot check and discussions with beneficiaries. VFM for the UN programme will be achieved through close monitoring of their implementation and results. We will negotiate on costs wherever possible.

Evaluation and audit – contracted through a limited procurement process

Evaluation and audits will be procured on an individual basis as needed, either through a framework contract or a limited procurement undertaken by the Nairobi office.

The programme will not use cross-HMG funds. The East Africa Conflict Security and Stability Fund (CSSF) strategy excludes support for elections. Nonetheless the DFID Kenya Governance and Security Team will work very closely cross HMG including with DFID’s RE-INVENT programme which will support electoral security initiatives and with DFID East Africa Research Hub to coordinate investments in research and evidence. Regular update will be provided to the joint DFID-FCO Kenya Political Governance Group and advice sought.

There is evidence, from our experience of 2017, that the interventions under this programme can deliver benefits which are likely to outweigh the costs and associated risks and offer value for money for the UK. Proposals received will be judged against the VFM criteria of economy, efficiency, equality and effectiveness. Elements that will be considered include: competitive fee rates, total cost to deliver the programme, and provision of a clear and effective financial plan. An illustration of potential VFM indicators is given below:

Economy (cost of inputs)	Overhead costs compared to other similar programmes. / Cost of consultancy inputs for high quality assistance. / Evidence of the economy of inputs sourced through procurement systems.
Efficiency (inputs to outputs)	Effective coordination with other donors in country to avoid duplication / Routinely updated delivery partner problem-solving tracker. / Cost per beneficiary[81] for capability building activities. / Rate of implementation of reform plans.
Effectiveness (outputs to outcomes)	Measurable improvements in the preparation and management of the elections compared to the 2017 baseline. / Increases women’s political representation
Equity	Gender and social inclusion analysis underpin project design and is measured.
[81] Immediate recipients of capacity building and systems strengthening support.

Agreements will be carefully negotiated to control costs and achieve value for money. Quarterly payments will be on actual costs. The DFID KESP programme team will negotiate the accountable grant agreement for the consortium and MoU for the UN, to control costs and improve efficiency and effectiveness, including establishing VFM indicators which will be regularly reported against. DFID will finalize a VFM framework for the programme within the first 3 months of implementation to provide an overarching framework through which VFM will be monitored on a quarterly basis.

To ensure VFM under this programme, DFID will:
- Assess capacity of partner organizations to think and work politically and their experience of supporting electoral institutions as well as their political neutrality
- Assess the capacity of partner organizations to engage effectively with election institutions, establish key high-level relationships and manage risk
- Engage regularly with the consortium, including through a programme funded advisor to ensure timely adaptation to the evolving political context.
- Ensure partners are inform cross-HMG understanding of election dynamics while also responding to HMG priorities and coordinating with other HMG interventions.
- Ensure partners have robust theories of change and an ambitious but realistic results framework
- Negotiate with partners to ensure appropriate staffing, realistic overheads and reasonable costs
- Approve all sub grants and technical assistance contracts
- Review performance on a quarterly basis and ensure any under-performance addressed in a timely manner, including through the potential discontinuation if necessary
- Oversee due diligence on partners and maintain registers in the delivery plan for risk, safeguarding, fraud and due diligence and audit follow up.

## D. Financial Case

Cost

This business case will be resourced under the DFID Kenya Bilateral RDEL Budget. The £7.5m over 4 years equals approximately £2m per year for the first three years which is around 2% of DFID Kenya’s bilateral budget in recent years (which we expect to remain flat) and can be afforded. HMT approval will be sought.

Budget (resource) estimated per output

Component	Estimated amount
Output 1: Meaningful electoral reforms early in the electoral cycle and institutions play coherent and complementary roles.	£1m
Output 2: Kenyan institutions improve on standards achieved in the 2017 election, and incorporate lessons learned for more effective planning, management, strategic communication and stakeholder engagement to build public trust.	£4m
Output 3: An enabling environment leads to more women, youth and PWDs voting and elected to representative posts	£1.25m
Output 4: Strengthened domestic election observation and monitoring	£ 1.25m
Total Budget	£7.5m

A break clause will be inserted in all partner agreements to allow the programme to be discontinued or adjusted annually. A degree of financial flexibility within the overall approved budget will be required to respond to success and failure within the programme and variations within the governance context, particularly based around the risks.

The overall cost for this programme will be £7.5 million beginning in April 2020 and ending in December 2023. The table below shows the anticipated breakdown of the budget by programme component and UK financial year.

Budget profiles per year

	2019/20	2020/21	2021/22	2022/23	2023/24	Total
Consortium	0	1.5	1.5	1.5	0.5	£5m
Downstream partnerships	0	0.25	0.25	0.25	0.25	£1m
Multilateral support	0	0.4	0.4	0.4	0.05	£1.25m
Evaluation and audit	0	0	0.1	0	0.15	£0.25m
TOTAL	0	2.15	2.25	2.15	0.95	7.5m

The ToR for the non-profit consortium will outline DFID’s expectations of the proportion of costs that will go towards management and towards programme delivery for the consortium. The commercial evaluation of proposals will further assist in these negotiations. The consortium will absorb most of the funds provided as it will be the main vehicle for delivery. Downstream partnerships and components of the UN Basket Fund on Elections will be identified that add value to the core support delivered by the consortium.

Fund disbursement

Funds disbursement will be done based on approved workplans and budgets.

Funds will be disbursed directly by DFID to the non-profit consortium under an accountable grant agreement and UN through an MoU. This will enable DFID to monitor, report and account for all funds in a straightforward manner. DFID will closely monitor implementing partners to ensure that funds will be used for intended purposes, including closely monitoring any downstream partnerships.

Disbursement to the NGO-consortium will be done quarterly to the lead partner. The consortium lead will be required to submit quarterly narrative and expenditure reports, which DFID will approve before making follow-up disbursements. The lead partner will be responsible for disbursement and monitoring use of funds by all consortium members/ downstream partners. A funds flow map will be developed showing the movement of funds up-to the beneficiary level. DFID will carry out a thorough due diligence assessment on the consortium to ensure ability to deliver and that policies and procedures are in place for proper financial management. This will include reviewing the finance and project staff qualifications on grant management.

Disbursements to the UN Basket Fund on Elections will be paid quarterly in advance against agreed workplans.

Financial and fraud risks assessment

No direct financial support will be provided to government.

DFID will ensure the following controls for fraud and fiduciary risk management.
- Use of a comprehensive delivery plan to monitor financial forecasts, and follow up to partner due diligence and audits
- Spot checks, special audits, and procurement reviews.
- Asset management tracking on a quarterly basis
- Approvals of all downstream partner proposals and budgets
- External audit at midterm and end of programme
- Use of risk register to manage and mitigate on potential fraud and fiduciary risk;
- Annual performance and financial review through DFID’s annual review process
- Updated monthly financial forecasting
- Advance payments to non-profit organizations will not exceed 3 months of forecasted funds
- Beneficiary feedback and sustainability assessments
- Coordination with other donors in this sector

After mitigation, the risk of fraud and corruption is considered moderate. DFID will hold regular review of portfolio decision on funding and partnerships. All agreements will specify DFID’s requirement and timelines for reporting fraud or corruption, or any suspicions of fraud or corruption. Any DFID or partner concerns about fraud and corruption will be reported within the required timeframe to the Head of Internal Audit or the Counter Fraud and Whistleblowing Unit. DFID commits to raise awareness with all partners to ensure there is a mutual understanding of DFID’s expectations on fiduciary risk management especially reporting concerns and enhancing whistleblowing policies.

Monitoring, reporting and accounting for funds

All partners will provide a justification for any request for advance payments. Any follow-on disbursements will be made after receiving expenditure reports for the previous disbursements. The reports and invoices will be scrutinised for accuracy by a DFID programme officer and quality assured by the programme manager; any inconsistency would be resolved prior to the invoice being paid by DFID. Implementing partners will be expected to continuously monitor the progress of the programme and submit quarterly and annual progress reports to DFID. DFID will require detailed financial reporting by implementing partners to ensure that DFID funds are being spent in accordance with agreed work plans.

The non-profit consortium will also ensure that audit reports for funds dispersed to local partners will be made available to DFID, as well as their own annual audits. DFID will carry out ad-hoc risk-based audits of any aspects of partners’ work where we require further assurance. Partners will also have an obligation to make all records available for audit by DFID. Where applicable due diligence assessments will be conducted on the partner at its head offices by the DFID procurement team. DFID has already carried our due diligence assessments for UNDP, further light touch assessments will be carried out during the mobilization phase. DFID will carry out a close-out audit for the programme to ascertain all funds were used for the intended purpose of the programme.

All partners will be expected to conduct due diligence assessments to a DFID standard on all its local partners and any sub-grantees. The DFID Kenya team will conduct spot checks on the partners, which among others will include, reviewing the quality of some of the due diligence assessments conducted by the partner on sub grantees.

All assets procured under this project, will remain DFID assets and we will make recommendations for their disposal at the end of the programme. The partners will maintain a register of assets and will provide DFID with an updated list of all assets purchased every six months. The DFID programme team will maintain the master assets register and carry out spot-checks every 6 months.

The delivery chain for this programme will be very short. The consortium lead will hold a direct contract with all downstream partners, none of which will be permitted to sub-contract, reducing the risk that DFID is unsighted on any downstream partner.

The SRO will be accountable for the expenditure of funds under this business case, including decisions on which organisations will be funded. DFID’s ARIES system will be used to monitor and account for expenditure. With the approval of the concept note an ARIES “project” has been created for this business case, with separate components for each programme. The SRO will authorise disbursement of funds based on the agreed funding profile set out in the funding agreements and contracts and the assessment of partner performance.

The DFID Kenya Programme Officer will be responsible for producing reports on actual and forecast spend against each of the components on a monthly basis. These reports will be reviewed by the Governance and Security section, including the SRO. Any inaccuracies, risks or issues identified will trigger a discussion with the respective partners.

Management Case

Governance

Implementation of this programme will be overseen by a regular DFID engagement with the primary election institutions including IEBC, the Judiciary and ORPP. The UN component will be governed by a UN steering committee for the Basket Fund for elections. The consortium will be managed by regular DFID-consortium meetings, serving as a programme management board / comprising of DFID, consortium lead and periodic engagement from partner institutions to discuss context, risk, progress, results, and technical approaches.

DFID Kenya will proactively engage in the cross-HMG Political Governance group, and the Elections Donor Group to routinely review progress and monitor risk.

Staffing

The Senior Responsible Officer (SRO) is a DFID Kenya member of staff, based in Nairobi, who engages regularly with national and local stakeholders from the Government of Kenya, civil society and other international partners. The SRO for this Programme will be the Head of the Governance and Security Team (A1 Governance Adviser). The SRO will have a 15% of their time allocation for the work, supported by a programme funded A2L Governance Adviser at 100% of their time and a Programme Manager at 50%.
  1. The SRO will ensure that HMG stakeholders (including High Commissioner, DFID Head of Office and the political team) are regularly informed of progress so that political risk can be managed. The SRO will co-convene the X-HMG elections working group that will have oversight and governance over the elections programme, implementation, delivery, technical support and the politics. The role of the working group will be to influence, manage risks and ensure stakeholders in the High Commission and Whitehall are kept informed.
  2. The Technical Advisor and Programme Management and Risk lead will monitor and advise on political economy analysis and risk monitroing in advance of the 2022 election and will assist DFID to engage externally and manage risks and monitor implementing partner compliance and results. The UK will be represented in the Elections Donor Group to ensure coordination and aid effectiveness. The programme funded technical advisor to the consortium will monitor delivery, ensure coherence and coordinated approach and engagement with stakeholder on behalf of DFID at the consortium. The Programme Management and Risk Lead will play a lead role in helping the SRO to manage the elections portfolio in line with the Smart Rules, ensuring lessons are shared across the office and monitoring risk.
  3. The DFID Kenya Gender Adviser, Senior Political Advisor and Conflict Adviser will each spend 5% of their time. Quality assurance of the programme will be provided by the Deputy team leader who will spend 10% of her time.

Name	Position	Department	Involvement
Nikolai Hutchinson	Head of Governance and Security Team	DFID Governance and Security Team	Overall lead and SRO (15%)
Jerusha Ouma	Governance Adviser	DFID Governance and Security Team	Technical Advisor seconded to the consortium – programme funded (100%)
Nancy Muigei	Programme Management and Risk Lead	DFID Governance and Security Team	Advice and Programme Management and Risk (50%)
Robina Mwaura	Deputy Team Leader	DFID Governance and Security Team	Quality Assurance of programme management
Salome Zuriel	Conflict Adviser	DFID Governance and Security Team	Ensure coherence on Election security planning (5%)
Dan Katte	Second Secretary Political	FCO Political team	Counterpart technical lead on elections (10%)
Hannah Waddilove	FCO research analyst	FCO Political team	Analysis and advice on Political Risks (5%)
George Morara	Senior Political Advisor	FCO Political team	Advise on Political Risks and Human Rights (10%)
Josephine Gitonga	Social Development Advisor	DFID Kenya	Advise on Gender and Disability Inclusion (5%)
Joanne McFadden	Results Adviser	DFID Accountability and Results Team	Results framework (5%)
Bernahdette Omondi	Commercial Adviser	DFID Accountability and Results Team	Commercial and Procurement (5%)

The political nature of the devolution programme requires continuous and up to date understanding and appreciation of the political issues in the national and county space. In line with ensuring that the programme is flexible and adaptive, we will have continuous political economy analysis and perception surveys. We will also strengthen the forums for evidence sharing and analysis from the outgoing programme.

Delivery of the Programme

The main management tool for this programme will be the delivery plan (with various risk marixes included) combined with the programme log-frame. Results will be monitored through the logframe, quaterly reports and annual reviews. Implementing partner performance will be monitored continuously and assessed annually. Significant adjustments will be recommended by annual reviews.

Partners will have flexibility to use their own tools to manage delivery, so long as adequate information is created to inform the delivery plan and results framework. The formal monitoring tool will be an annual review, which will formally test the theory of change and underlying assumptions.

The DFID Governanve and Security team will ensure up to date strategies for regular conflict, gender and political economy analysis, real time programme learning and evidence, communications.

Monitoring, Evaluation and Learning

The programme will be robustly monitored and evaluated by DFID and implementing partners, including through independent assessments, and by a seconded DFID advisor. Ongoing monitoring is integrated into the programme design. Given the governance context in Kenya is volatile we will continue to monitor regularly the assumptions outlined in the Theory of Change and priority evidence gaps to be filled. Key information will be shared with government and other donors as a contribution to inform improvements across election programmes and learning in the sector.

We have a clear sense of the broad results at impact, outcome and output level, we also have a good idea of the range of possible interventions that can contribute to meeting each of the output areas. The indicators, milestones and targets will be clearer after the mobilisation phase once we agree specific results and deliverables with implementing partners, with the support of DFID Kenya’s Accountability and Results Team (ART).

DFID will ensure the following monitoring and evaluation measures
- Secondment of an A2L governance advisor to the consortium
- SRO approval of implementing partner inception reports and then all quarterly reports
- Conducting in depth annual reviews
- Commissioning an independent mid-term review
- Commissioning an independent final evaluation
- Commissioning an independent programme audit
- Completing a programme completion review
- Requiring from the consortium lead annual audits and due diligence of the downstream partners
- Direct monitoring of the programme and compliance by DFID staff including quarterly programme management meetings, independent spot-checks and independent meetings with election institutions, civil society and citizens (during field visits) amd open dialogue with the partners
- A budget of £250,000 will be set aside for midterm evaluation and end evaluation and audit; open calls will be issued for this strand of work

Monitoring and Evaluation of VFM

We will use the ITAD-DFID Nigeria Governance VFM diagnostic tools and indicators to develop our Governance VFM indicators.

For cost effectiveness we will aim to measure value for money in terms of the overall improvements delivered by the programme at the impact level. We will identify indicators in the top left corner of the matrix below. We will avoid stand-alone process indicators and seek trends and ideally benchmarks that can be measured quantitively (e.g improvements in bringing down the cost of Kenyan elections, and increasing the number of people effectively voting, levels of inclusion, levels of violence).

Cost-Effectiveness
	Benchmark	Trend	Stand Alone
Monetary
Quantitative
Qualitative
Process

For efficiency we will aim to measure value for money in terms of how much of the programme contributes to the desired outcomes. Again, we will avoid stand-alone process indicators and rather aim for the top left corner of the matrix below. (e.g improvements in institutional effectiveness, management of polling and results transmission, dispute resolution, domestic observation).

Efficiency
	Benchmark	Trend	Stand Alone
Monetary
Quantitative
Qualitative
Process

For economy we will aim to measure value for money in terms of the costs of inputs and activities, we will aim to measure this against benchmarks for DFID programmes in Kenya (ie local consultancy rates, conference costs, downstream partner operating costs, etc) rather than simply against the programme’s own budgets and plans (stand-alone process indicators). For example, IEBC have noted that procurement of ballot papers for recent bi-elections were 78% cheaper than for the 2017 owing to better planning.

Economy
	Benchmark	Trend	Stand Alone
Monetary
Quantitative
Qualitative
Process

We will develop indicators also for measuring Equity

Risk Management

The overall risk rating for this programme is Major. The primary risk for this programme is likely to be political. This is likely to be the programme with the highest political risk in DFID Kenya’s portfolio. As part of our overall portfolio, this is within DFID Kenya’s overall risk appetite.

Supporting Kenyan elections is a complex endeavour, requiring a whole of government approach to manage risk and work with other members of the international community, acting in concert, to build accountability and widespread recognition of the role of independent institutions.

Although involvement in Kenyan elections carries a high political risk, the UK is firmly committed to supporting credible and peaceful elections in Kenya. The UK has played a visible role during previous elections, in coordination with other embassies, calling for all actors to respect independent institutions and processes. We will monitor governance trends on a weekly basis, including the related areas of civil society space and media freedom. An elections strategy will be developed in addition to a communications strategy to be agreed cross-HMG.

During the mobilisation phase the DFID Kenya team will carry out thorough due diligence assessments on all proposed implementing partners to ensure they have strong safeguarding policies. Regular monitoring and spot-checks will seek to verify adherence to those policies. A conflict sensitivity analysis will be conducted on the programme to ensure the programme does no harm at all levels. We will build beneficiary feedback systems to ensure the programme will be informed by beneficiary views. We will also coordinate with centrally managed programmes.[82]
[82] such as with the Westminster Foundation for Democracy

DFID Kenya is developing a portfolio of complementary governance and conflict programmes, of which this proposed election programme will be a core component. The portfolio aims to address wider aspects of conflict and political economy in Kenya and deliver a DFID contribution to priorities identified in the Kenya Country Development Diagnostic and Kenya Business Plan in line with our new Strategic Approach to Africa. We assess that the modalities for implementation for each programme will provide sufficient scope to flex and adapt across priority areas of governance and conflict. For example, the DFID Kenya community security programme has the promotion of a peaceful 2022 election within its scope (including police accountability for public order management).

The SRO and lead advisor have been in place during the 2017 election and the wider governance and political team in the Kenya mission have a detailed knowledge of the context, sector, institutions, politicians and election dynamics in Kenya. The programme will be flexible and adaptive to changes in the context. The delivery modalities through non-governmental organizations will support this. A clear communications strategy will be agreed cross-HMG.

We will work with partners in close coordination with Government of Kenya institutions. This programme will support Kenyan institutions and strategies for the 2022 election and will be highly coordinated with the international community (at both the diplomatic and technical levels). It will be coordinated with other donors in country through the Donor Working Group on Elections to manage funding efficiencies, set priorities, manage risks, and share and learn with other donors. The Political and governance team will maintain a wide range of relationships, with political parties, civil society, media and private sector to keep the UK well informed and able to manage risks as well as to ensure the programme is as effective as possible in contributing to free, fair and credible elections in 2022. Investments in improved institutions and processes aim at sustainability. This programme will be closely coordinated with other governance programmes in Kenya (supporting community security, police reform and devolution) and will provide a source of political analysis for the whole mission and aid portfolio.

We will continue to undertake robust political economy analysis (and to collaborate with the East African Research Hub if additional research is needed) to help generate evidence to inform programme decision making, prioritization process, how we manage risks and how we make decisions.

This programme is within DFID’s risk appetite at the end of 2019. Our risk appetite is reviewed regularly. We have a:
- High appetite for external context risk. DFID works in fragile, conflict affected and volatile situations, and in contexts where political stability is low or where political or economic governance compromises the rights of citizens. We have a zero-tolerance approach towards and will work to prevent fraud and corruption, reporting and acting upon all suspicions.
- DFID has a low appetite for operational risk. We strive to ensure the highest possible professional competence, experience and appropriate level of resource in managing our programmes and funds. We have a low risk appetite for management failures but will always seek to learn lessons in order to improve.
- DFID has a low appetite for risk associated with unintended harm to people and to the environment as a result of our programmes. We expect all partners to follow our lead and to apply robust safeguards and reporting measures.
- DFID has a high appetite for delivery risk. We sometimes work in very difficult operating environments and we take an innovative approach to deliver high impact programmes. We will be flexible to accept a higher risk appetite in the contexts where these factors exist but seek to minimise and mitigate risks.
- DFID has a low appetite for reputational risk. DFID must seek to avoid significant reputational damage associated with poor management, the misuse of funds, or inadvertently doing harm through our actions. We are seeking to work more closely with the Government in a maturing development partnership on ambitious programmes of reform, and there is a reputational risk in doing so which will manage through robust cross HMG political economy analysis.

We will consider all risks in detail on a regular basis and maintain a more detailed live risk register, with detailed internal risk monitoring including fiduciary and safeguarding risks.

Key risks and mitigation strategies are outlined in annex 1.
ANNEX 1: Outline Risk Matrix

Risk Description	Like-lihood	Impact	Gross Risk	Mitigation Strategy	Likely-hood	Impact	Residual Risk
1. Contextual
Political: the political climate deepens divisions across government and the country	Likely	Major	Severe	Work across-HMG, and across donors, and across the political spectrum in Kenya to retain an impartial profile and remain a trusted partner	Likely	Moderate	Major
Security: election related violence occurs	Possible	Major	Major	Monitor the situation throughout the country through staff, partners and media. Ensure partners have procedures in place to mitigate, and the duty of care responsibility is clear	Possible	Moderate	Major
2. Operational Risk
2.1 Breadth and depth of capacity building is insufficient to establish a sufficiently credible 2022 election process.	Possible	Major	Major	Work closely across HMG and with other missions to monitor this risk and ensure our public narrative is consistent and regularly updated. Consider closing the programme if insufficient political will exists to hold a credible election	Unlikely	Major	Major
Security context deteriorates limiting programme’s access	Possible	Moderate	Major	Work with partners to deepen our shared understanding of the security context and strengthen mitigation measures.	Possible	Minor	Moderate
Delivery Risk
Disruptions at IEBC affect planning and management	Likely	Major	Severe	Use political and diplomatic levers to negotiate on areas causing tensions between political actors, and lobby for timely and effective appointments.	Possible	Major	Major
Rising debt leads to budget constraints in key institutions	Likely	Major	Severe	Lobby with treasury and government to ensure that election funding is prioritised given its impact stability and prosperity	Possible	Major	Major
Potential duplication of activities by partners	Possible	Moderate	Major	Ensure regular coordination between all partners and is complemented by donors at DGE and steering committees.	Unlikely	Moderate	Moderate
Inadequate funding for the UN programme to be viable	Possible	Moderate	Major	Support fundraising efforts through DGE. Redirect allocated budget to the non-profit consortium if UN programme unviable.	Unlikely	Moderate	Moderate
Partners perceived to be politically partisan.	Possible	Major	Major	Issue a clear communication to partners requiring impartiality through the election.	Unlikely	Moderate	Moderate
Poor Performance by implementing partners	Unlikely	Major	Major	Review implementing partner performance very regularly, with a seconded advisor in the consortium and regular reviews	Rare	Moderate	Minor
Safeguarding risk
Risk that the staff/consultants employed by implementing partners and their downstream partners use their position to cause harm to vulnerable people	Unlikely	Severe	Major	Carry out enhanced due diligence assessments on all partners. We will also provide additional capacity to first tier partners to manage the risks with downstream partners. Regular DFID-led risk discussions and spot-checks will provide assurances on management of this risk.	Rare	Major	Moderate
Fiduciary Risk
Funds may not be used for intended purpose (fraud, terrorist financing, political campaigns)	Unlikely	Major	Major	Exclude direct financial aid to Government. We will monitor fiduciary risks though fraud risk and due-diligence risk assessments, audits and spot checks (including beneficiary feedback and whistle-blowing checks). Procurement decisions will be monitored at higher levels.	Rare	Moderate	Minor
Reputational risk
Weak delivery by election institutions, and continued lack of public confidence damages reputation of UK/international community.	Possible	Moderate	Major	Ensure regular media monitoring, and partner and beneficiary feedback and coordination through the political governance group, Elections Donor group and other HoMs.	Possible	Minor	Moderate
Sustainability Risk
Risk the programme undermines sustainability of election institutions by substituting capacity rather than building it	Unlikely	Moderate	Moderate	Monitor closely all programme approaches to capacity building to ensure that all experts and advisors working with GoK have clear capacity building plans and exit strategies for specific workstreams	Unlikely	Minor	Minor

Annex 2: Bibliography

Evaluation Reports
1. The Evidence & Evaluation Base on the Impact of Election Assistance, DFID Guidance on elections: http://epe-insight/_layouts/QuestLinking/QuestLink.aspx?docid=4087509
2. UNDP Evaluation of UNDP Contribution to Strengthening Electoral Systems and Processes. UNDP, 2012
3. ICAI Evaluation of DFID’s Electoral Support through UNDP, Independent Commission for Aid Impact (ICAI), 2012
4. UNDP Post Election Evaluation Draft Report
5. IEBC Post Election Evaluation Report for 2017 Kenya Elections
6. USAID Assessment of Kenya’s 2017 Elections
7. IEBC the Post-election Evaluation Draft Report for the Fresh Presidential Elections
8. NDI A Gender Analysis of the 2017 Kenya General Elections
9. IFES Elections on Trial: The Effective Management of Election Disputes and Violations
10. ELOG Observation Report, 2017: One country, Two elections, Many voices. The Kenyan 2017 General Elections and the historic fresh presidential election
11. IDLO End of Project Evaluation: Outcome Harvesting Final Report, 2019
12. DDP Post Elections Deep Dive: A review of UK contribution to 2017 Kenyan Elections, March 2018
13. DDP Mid-Term-Review: Final Report, Sayara International for DFID Kenya, 30 September 2019

Observation Reports / Audit
1. Carter Centre Kenya 2017 General and Presidential Elections
2. European Union European Parliament Election Observation Delegation General Elections in Kenya
3. Carter Centre FINAL REPORT 2017 Kenya General and Presidential Elections March 7, 2018
4. European Union European Union Election Observation Mission 2017
5. KPMG Independent Audit of the Voter Register

Policy Briefs
1. EARH: RVI 2017 Study on women political participation in Kenya
2. EARH: RVI 2017 Kenya Election Monitoring Report
3. DDP Kenya’s Continuing Quest for Credible Elections, Elections Report and Policy Brief, November 2019
4. UNDP/IEBC, ‘Moving Kenya Towards a Stronger Democracy’https://www.iebc.or.ke/uploads/resources/V9UUoGqVBK.pdf
5. 50 Journeys: Stories of courage and transformation from women political leaders in Kenya’, https://www.genderinkenya.org/publication/50-journeys-stories-of-courage-and-transformation-from-women-political-leaders-in-kenya/;
6. Journey to Gender Parity in Political Representation: Search of a framework for the realization of the not more than two-thirds gender principle in Kenya, https://www.ngeckenya.org/Downloads/Journey-to-Gender-Parity-in-Politcal-Representation.pdf
7. The Milestones: Equality and Inclusion in the 2017 Kenyan General Elections (https://www.ngeckenya.org/Downloads/Equality-and%20Inclusion-in-the-2017-Kenyan-General-Election.pdf;
8. Promoting Participation of Special Interest Groups in the Electoral Cycle; Kenya’s 2017 General Election, https://www.ngeckenya.org/news/7188/participation-and-inclusion-of-special-interest-groups-in-the-electoral-process;
9. Brookings Foresight Africa viewpoint – Elections in Africa in 2018: Lessons from Kenya’s 2017 electoral experiences
10. Biometric Technology, Elections, and Privacy Investigating Privacy Implications Of Biometric Voter Registration In Kenya’s 2017 Election Process.

Academic Articles
1. Cheeseman, N., Maweu, J. and Ouma, S., 2019. Peace, But at What Cost? Media Coverage of Elections and Conflict in Kenya. In Media, Communication and the Struggle for Democratic Change (pp. 83-105). Palgrave Macmillan, Cham.
2. Cheeseman, N., Kanyinga, K., Lynch, G., Ruteere, M. and Willis, J., 2019. Kenya’s 2017 elections: winner-takes-all politics as usual? Journal of Eastern African Studies, 13(2), pp.215-234.
3. Bjorvatn, K., Galle, S., Berge, L.I.O., Miguel, E., Posner, D.N., Tungodden, B. and Zhang, K., 2019. Elections and Selfishness. Available at SSRN 3329948.
4. Kanyinga, K., 2019. Political Economy of Kenya & the 2017 General Elections.
5. Kanyinga, K., 2018. Elections without constitutionalism: votes, violence, and democracy gaps in Africa. African Journal of Democracy and Governance, 5(4), pp.147-168.
6. Mutahi, Patrick, and Mutuma Ruteere. "Violence, security and the policing of Kenya’s 2017 elections." Journal of Eastern African Studies 13, no. 2 (2019): 253-271.
7. Kanyinga, K. and Odote, C., 2019. Judicialisation of politics and Kenya’s 2017 elections. Journal of Eastern African Studies, 13(2), pp.235-252.
8. Lynch, G., Cheeseman, N. and Willis, J., 2019. From peace campaigns to peaceocracy: Elections, order and authority in Africa. African Affairs.
9. Molony, T. and Macdonald, R., 2019. Re-evaluating international observation of Kenya’s 2017 elections. Journal of Eastern African Studies, pp.1-20.
10. Wanyama, F.O. and Elklit, J., 2018. Electoral violence during party primaries in Kenya. Democratization, 25(6), pp.1016-1032.
11. Fjelde, H. and Höglund, K., 2018. Ethnic politics and elite competition: the roots of electoral violence in Kenya. Violence in African elections: between democracy and Big Man politics. London: Zed Books, pp.27-46.
12. Kovacs, M.S. and Bjarnesen, J. eds., 2018. Violence in African elections: between democracy and Big Man politics. Zed Books Ltd..
13. Long, J.D. and Gibson, C.C., 2015. Evaluating the roles of ethnicity and performance in African elections: Evidence from an exit poll in Kenya. Political Research Quarterly, 68(4), pp.830-842.
14. Molony, T. and Macdonald, R., 2019. Re-evaluating international observation of Kenya’s 2017 elections. Journal of Eastern African Studies, pp.1-20.
15. Cheeseman, N., Lynch, G. and Willis, J., 2018. Digital dilemmas: The unintended consequences of election technology. Democratization, 25(8), pp.1397-1418.
16. Ouma, Seth. (2018). Reporting for Democracy or Convenience? The Kenyan Media and the 2017 Elections. The Round Table. 107. 1-16. 10.1080/00358533.2018.1449299.

Annex 3: Illustrative interventions

Output 1: Meaningful electoral reforms early in the electoral cycle and effective coordination between the IEBC, Judiciary, ORPP and Parliament.
- Provide technical support to IEBC to respond to the reform priorities to be outlined in the report of the Building Bridges Taskforce, as required.
- Provide support to IEBC and parliament to ensure enabling legislation is in place to support a boundary review and referendum if required before 2022
- Support parliament’s Justice and Legal Affairs Committee (JLAC) to identify and consult key stakeholders on legal responses to recommended reforms.
- Support early joint planning between IEBC, Judiciary and ORPP.
- Inform diplomatic efforts to raise the issue of adequate financing and full composition of these institutions

Output 2: Kenyan institutions improve on standards achieved in the 2017 election, and incorporate lessons learned for more effective planning, management, strategic communication and stakeholder engagement to build public trust.
- Support IEBC to prepare voter registration and set up a national voter register well in advance.
- Support IEBC to build on improved protocols from the August and October 2017 elections (formats of forms, data management protocols).
- Support IEBC to strengthen administrative structures at both the headquarters and the devolved level, to promote integrity and leadership and train and re-train staff.
- Support IEBC to update and roll out voter education.
- Support IEBC to prepare and deliver an improved strategic communications strategy.
- Support IEBC to restructure to more clearly define roles and relationships between the Commission and the Secretariat, and between various departments within the secretariat.
- Support IEBC to develop and implement a strategic plan, strengthen administrative structures at both the headquarters and the devolved levels, and improve procurement processes
- Support IEBC to plan for more open and transparent results transmission.
- Support IEBC to plan for improved use of election technology for more transparency
- Support the Judiciary to prepare for high quality and timely election dispute resolution, including decentralising where possible.
- Support the Registrar of Political Parties, and Political Party Liaison Committees to ensure political party compliance with the law (including campaign financing laws).
- Support all stakeholders to develop technical skills to better understand result transmission technology (e.g. build ICT standards to enable forensic auditing)

Output 3: Increased participation of women, PWDs and young people as voters and standing for election.
- Support IEBC and civil society to plan and begin voter education early in the election cycle, with a focus on learning lessons from 2017 to better reach traditionally marginalised groups in the electoral process including women, persons with disability (PWD) and youth
- Support the Registrar of Political Parties, and Political Party Liaison Committees to support political parties to make more inclusive their candidate nomination processes to enhance women’s participation, implement party quotas, apply inclusivity principles in the party leadership and decision-making structures, enhance internal dispute resolution and create a favorable environment for women candidates.
- Support interventions with candidates who are women, youth and PWDs to develop peer cross party support networks.

Output 4: Strengthened domestic election observation and monitoring.
- Support early planning and organization for robust domestic election observation and oversight to increase integrity, transparency and accountability of the electoral process.
- Support improved protocols for observation related to results transmission monitoring.
- Support ORPP to work with political parties to plan for training and deployment of party agents