## Annual Review

Title: Support Economic Empowerment and Development in the OPTs (SEED)
Programme Value £ (full life): Up to £91 million		Review date: Jan 2025
Programme Code: [AMP ID#] / 300667	AMP start date: / Nov.2018	AMP end date: / March 2028

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300667/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300667/documents

A. SUMMARY AND OVERVIEW
Description of programme

Support for Economic Empowerment and Development in the Occupied Palestinian Territories (SEED OPTs) is an economic development assistance programme which aims to address the underlying constraints to sustainable economic growth and job creation in the OPTs. The programme seeks to increase the sustainable supply of water and energy (particularly in Gaza), increase trade, enhance freedom of movement and customs revenue, and promote greater Palestinian sovereignty. The programme is fully aligned with and supports the UK’s objectives of maintaining the viability of a two-state solution and improving the livelihoods of Palestinians.

SEED consists of the following main components:
- Support to the World Bank (WB) through its Partnership for Infrastructure Development (PID) in the West Bank and Gaza Multi Donor Trust Fund (MDTF), with UK funds focusing on the water and energy sectors;
- A Trade Facilitation and Customs Support programme (Tasdeer), delivered by Cowater (a commercial service provider);
- Support to the Office of the Quartet (OQ), a UN special project, undertaking analytical work and facilitation between the parties, with UK funding focused on water, energy, trade and movement, and clearance revenues and customs;
- Support to the European Bank for Reconstruction and Development (EBRD) MDTF to empower the private sector through energy and trade related interventions [funding for this component ended early, in 2021].

In November 2024, Ministers approved a cost and time extension for SEED, increasing its total lifetime budget to up to £91m and extending the end date to 31st March 2028. Through this extension, SEED will strengthen its support to Palestinians in response to the deteriorating economic situation across the OPTs resulting from the ongoing conflict in Gaza.

Context

The Gaza conflict and deteriorating conditions resulting from Israel’s occupation of the OPTs, is driving the OPTs towards economic collapse. This is particularly the case in Gaza, where there is a severe and worsening humanitarian crisis, but also in the West Bank where the effects of the conflict have been felt acutely. There has been a 35% decline in GDP during the first quarter of 2024, the highest economic contraction in the OPTs on record. The Palestinian Central Bureau of Statistics (PCBS) estimates GDP dropped by 31% during the 3rd quarter of 2024 in comparison to the 3rd quarter of 2023. The conflict has brought Gaza’s economy to the brink of total collapse with an 86% contraction in early 2024. With prices of basic commodities reaching 5 to 10 times their original prices, they are not within the capabilities of most families to buy, with unemployment on the rise. The entry of goods into Gaza has been highly restricted throughout the conflict, contributing to widespread food insecurity and severe shortages of water, fuel, and medical supplies. In parallel, the West Bank economy has also contracted approximately 25% during Q1 of 2024, with trade, services, construction, and manufacturing sectors experiencing the most decline. Israel has imposed further restrictions on commercial trade through the King Hussein Bridge (KHB) due to a security incident in September 2024, which has severely curtailed the ability of Palestinian traders from the West Bank to export or import goods. This resulted in an estimated total loss of $83 million which does not include reductions in trade volumes through KHB from 350 truckloads to 45. Statistics collected and initial assessments made by international organisations state that the conflict’s impacts to date have exceeded all previous economic crises which have taken place in the OPTs over the past two decades. This raises concerns about the conflict’s long-term implications for the Palestinian people and economy.
[note] World Bank Report: Impacts of the conflict in the Middle East on the Palestinian Economy - September 2024 Update - Question of Palestine
[note] https://www.pcbs.gov.ps/portals/_pcbs/PressRelease/Press_En_QNAQ32024E.pdf
[note] PalestinianEconomicUpdate-Sept2024-FINAL.pdf
[note] PalestinianEconomicUpdate-Sept2024-FINAL.pdf

Some of the key economic impacts:

- Even though inflation has been on the rise in the past few years, it has significantly increased due to the war. Palestinian Monetary Authority reporting shows that inflation was approximately 55% during Q3 of 2024 compared to 46.6% in Q2.
  [note] https://www.pma.ps/Portals/0/Users/002/02/2/Publications/English/Quarterly%20Reports/Inflation%20Reports/Inflation%20Rep%202024/Inf%20Rep_%202024Q3.pdf?ver=2024-12-24-081026-617&timestamp=1735020733450
- The conflict continues to exacerbate the Palestinian Authority (PA)’s pre-existing fiscal challenges, risking systemic failure amid wide-spread service disruptions and partial salary payments. As per the World Bank’s reports, the PA’s financing gap is projected to reach US$1.86 billion in 2024, which is more than double the gap in 2023.
- Due to Gaza’s economic collapse and the West Bank’s suppressed labour demand, unemployment has reached its highest rate ever recorded in the OPTs. The private sector in Gaza has endured extremely high losses, particularly in the commerce and trade sectors, with 88% of establishments either being damaged or destroyed. Despite reports indicating a 23% drop-in economic activity in the West Bank during the first half of 2024, the private sector in the West Bank continues to show resilience despite increasing unemployment, favouring underemployment over layoffs.
- Limitations on access to water severely hinder Palestinian economic growth by restricting agricultural productivity, industrial operations, and overall developmental potential. These constraints also stifle private sector investment and expansion, particularly in water dependent industries, due to unreliable and insufficient water supply. Water supply in the West Bank and Gaza (WB&G) was already constrained prior to the outbreak of the war in Gaza, with the growing demand for water across the OPTs not being met. Israeli imports have been increasingly relied upon to meet domestic water needs of a recommended 100 litres of water, per person, per day (60% of domestic water in the West Bank, and 15% in Gaza). As the war continues, Palestinians in Gaza are receiving less than half the daily water quota they need for short-term emergency survival and further depletion is inevitable given approximately 70% of water, sanitation, and hygiene facilities in Gaza have been destroyed or damaged. Any or all progress on crucial new infrastructure projects have been hindered due to movement restrictions and widespread destruction.
- The Palestinian and Israeli energy sectors are deeply intertwined; therefore, achieving a sufficient and sustainable energy supply continues to present challenges. As limitations to access electricity continue, Palestinian economic development continues to disintegrate causing disruption to business operations, manufacturing, and public services. This unreliable energy source supply also discourages private sector growth and investment. As per World Bank assessment reports, electricity infrastructure in Gaza will require extensive and urgent repairs and replacements due to the widespread destruction. These severe losses have crippled Gaza’s energy sector and its essential services while increasing reliance on costly and more polluting energy sources.
Summary supporting narrative for the overall score in this review

This Annual Review assesses SEED’s progress against the programme’s outputs for 2024. Based on the evidence on progress the overall score for the 2024 review is A, indicating the programme has met expectations at all output levels.

Partners demonstrated flexibility to pivot delivery in response to the increasingly challenging context, and work to address new challenges resulting from the war. Key to this was the rapid delivery of assistance through partners with robust systems and processes in place, allowing support services to be provided at scale within a dynamic context. The World Bank’s water programme has repurposed $ 9m of unallocated funds to deliver relief supplies including hygiene kits and collapsible water tanks of different volumes into Gaza. The World Bank’s Energy programme has been restructured to address needs in Gaza and successfully made progress in advancing the Liquidity Support and Account Payment System (LSAPS) to encourage private investments in renewable energy in the West Bank. The LSAPS was endorsed by the Palestinian Authority (PA) and the World Bank released the $20m into the PA’s Deposit account. The OQ supported efforts on the resumption of basic services in Gaza including for the water, energy and telecom services. This included development of technical non-paper documents that were endorsed by the PA and have facilitated international community engagement with Israel and the PA. Tasdeer has also pivoted to address the impacts of the conflict. For example, in partnership with the Palestinian Monetary Authority, Tasdeer launched an interest-free loan scheme, supporting 700 Palestinian workers that have lost their jobs in Israel to start new businesses or expand their existing businesses. Tasdeer supported the Palestinian Chambers of Commerce, Industry and Agriculture (FPCCIA) and the Palestinian Federation of Industries (PFI) to produce and publish critical Market Dynamics and Trade Flow weekly monitoring reports with valuable data and insights on the situation on the ground in Gaza.

Major lessons and recommendations for the year ahead

Lesson: To address the continuing and increasing needs from the conflict in Gaza the economic deterioration in the West Bank, and shifting political reality, SEED must remain flexible and adaptive. It should build on the achieved results to strengthen private sector resilience in the West Bank, as well as to contribute to early recovery in Gaza once conditions allow and support the PA to deliver its priorities. Despite the programme’s ability to adapt and scale up to respond to the crisis, the war has challenged assumptions within the original SEED theory of change (ToC). The ToC should be used as a living document to support SEED’s decision making on how to pivot its delivery.

Recommendation: By June 2025, FCDO will update the ToC to reflect the changing context and the extension including the logframe indicators and milestones. FCDO will work with partners on this and ensure that partners’ 25/26 workplans are updated to reflect the revised ToC. FCDO will also ensure that partners collaborate with one another, and activities complement each other.

Lesson: The flexibility required in the next 12 months through SEED’s delivery requires a review of the logframe to ensure that results captured are accurately and actively monitoring progress achieved by SEED.

Recommendation: Within the first quarter of 2025/26, FCDO will review and update the SEED logframe, including key performance indicators and milestones for 2025/26. Any changes to the logframe will be approved in accordance with FCDO’s Programme Operating Framework.

Lesson: Due to the ongoing situation, it has been challenging collecting accurate and tangible progress on yearly milestones.

Recommendation: FCDO to work with partners on finding other means for collecting progress against milestones. FCDO to check quarterly with partners on data collection.

Lesson: There is a breakdown of GoI/PA cooperation at all levels and increasingly restrictive Israeli policies make it increasingly difficult to achieve progress through programming alone.
There is a breakdown of GoI/PA cooperation at all levels and increasingly important that programming is accompanied by political and policy engagement.

Recommendation: FCDO to continue policy engagement and advocacy on economic issues with GoI, PA and International Community.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

SEED’s aim is to support inclusive and sustainable economic growth in the OPTs, contributing to achieving the UK’s vision for a two-state solution. This impact is expected to be achieved through tackling key barriers to inclusive growth through a) improved access to water b) improved access to sustainable energy c) reduced restrictions to trade and competitiveness, and d) enhanced PA fiscal sustainability. Combined action in these areas will collectively contribute to increasing growth, creating jobs and generating revenue for the PA. Inclusion will mean that the benefits of growth are spread more fairly throughout the Palestinian population, including to women and other marginalised groups, and this focus is mainstreamed across the programme. The main interventions of the SEED programme include:

- Engagement in policy dialogue
- Coordination of the parties
- Provision of technical assistance
- Support to infrastructure development
- Institutional capacity building of PA agencies and Palestinian companies.
- Support to private sector development and improving Palestinian trade performance and customs.
The war deeply impacted SEED’s stakeholders, partners, grantees and the wider private sector, causing the immediate cancellation of all activities in Gaza – including a new agriculture intervention in Gaza under Tasdeer, and the pause of some of the World Bank’s water and energy interventions. In the West Bank, the delivery of existing interventions has slowed due to restrictions on private sector activity and the wider economy, and the priorities of external partners has shifted. The underlying context has changed significantly, and the war has challenged some assumptions within the original SEED Theory of Change, such as the assumption that “Israeli and Palestinian technical relations continue and do not deteriorate as a result of politics”. While overall, assumptions in the ToC remain sound, and it has enabled a flexible approach, it is right to review this in the first quarter of 2025, as per the recommendation above, particularly as we are extending the programme to respond to the challenges arising from the Gaza conflict.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Post 7th October, the Palestinian economy including the water and energy sectors, have been significantly impacted especially in Gaza. Increased movement and access restrictions in the West Bank have also hampered commercial activities, exacerbating the PA’s weak fiscal situation. The politics of the war have also had a very negative impact on Israeli-PA dialogues. This overall context has negatively impacted the programme’s ability to achieve all its outcomes. Nonetheless, there has been continued engagement with the international community, the private sector, the US and other donors to support the PA in developing their plans for the Resumption of Basic Services both in Gaza and the West Bank.

Impacts:
Even though some progress has been made in 2024, the impact of the programme has been undermined across all activities due to the deterioration in the operating context. For example, water production in the OPTs was estimated at below 5%, there has been severe damage to electricity grid distribution networks as well as off-grid rooftop solar systems, and the private sector’s enterprises in the OPTs have decreased in 2024. This impacts the programme’s ability to deliver sustainable results.

Outcomes:

Within the ToC, SEED addresses the reduction of key barriers to inclusive economic growth in the OPTs through improved access to water, improved access to sustainable electricity, improved trade and competitiveness, and enhanced PA fiscal sustainability. The Gaza war has proposed challenges on many fronts including any progress on the water and electricity sectors. With extensive damage to water and electricity infrastructure in Gaza, Palestinians have very limited means of access to improved water quality and electricity. Despite this, under the Advancing Sustainability in Performance, Infrastructure, and Reliability of the Energy Sector (ASPIRE Phase I) programme for the West Bank and Gaza, the disbursement rate rose to 46% in June 2024, due to the achievement of important milestones including the disbursement of US$20 million for the Liquidity Support Account and Payment System (LSAPS), as well as the signing of the contract for the supply of the smart meters for Electricity DISCOs in the West Bank.

There were a number of significant and sustained changes to policies and practices in both the energy and water sectors, and on enhancing the financial stability of the PA. There has also been continued engagement with the international community, private sector and US to support the PA in developing their plans for the Resumption of Basic Services (which included water and energy) in both the Gaza Strip and West Bank.

Moreover, 8 new/improved products or solutions have been adopted within trade-related institutions and Ministries to reduce key barriers to trade. Tasdeer has significantly enhanced the capacity of the PA and trade-related institutions. The Ministry of Finance (MoF)/Customs have adopted 3 functions which have increased the PA’s capacity to administer customs duties, excise and VAT from imports. As a result of Tasdeer interventions, 359 workers have been hired by grantees/ supplier, creating jobs including seasonal, part-time and full-time.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The war in Gaza and security deterioration in the West Bank have significantly worsened the fundamental challenges facing the OPTs. As of end-January 2024, most Palestinians in Gaza are now multidimensionally poor and 74% are unemployed. Once the situation permits, Gaza will need effective reconstruction planning and immediate support to create jobs and restore businesses. In the West Bank, declining trade and private sector activity, reduced income due to job losses, and temporary cuts in public salaries led to a 22% contraction in GDP during Q4 of 2023. The subsequent fiscal crisis has restricted the PA’s ability to provide services to citizens, support businesses, and invest in a strengthened business environment. The ongoing conflict is also increasing the vulnerability of women, girls, people with disabilities, and other socio-economically excluded and marginalised groups. Structural constraints prevent marginalised groups from full economic participation. This leaves these groups exposed to shocks, including war and climate change, and exacerbates OPTs' weak economic growth. Addressing this requires equitable economic growth that integrates marginalised groups into the wider economy and builds economic resilience, for example through job creation for women.  In the OPTs, socio-economic vulnerability to climate change reinforces, and is reinforced by, poor economic performance. Whilst access to electricity is high in the West Bank, private sector competitiveness is restricted by high electricity costs and a reliance on Israel. Solutions that improve climate resilience whilst promoting economic growth – for example renewable energy solutions, efficient irrigation systems and agricultural land reclamation – are required to increase adaptive capacity and promote green growth.

Based on the context, the cost and time extension (up to £32m for 2.5 years) which has been approved will allow the programme to provide further support by capitalising on the results delivered and strong relations with our existing partners. Tasdeer will play an important role in strengthening private sector resilience in the West Bank, contribute to early economic recovery in post-war Gaza, and support the PA to deliver its priorities. Delivery through our current partners (the Word Bank, OQ, and Tasdeer) will provide assurances to minimise risks of fraud and aid diversion.

Despite the changing context due to the war, the business case’s original impact and outcome statements will remain the same.
Impact: Inclusive and viable economic growth supporting the vision of the two-state solution.

Outcome: key barriers to inclusive economic growth in the OPTs reduced.

Although SEED cannot transform the economic situation on its own, it will help prevent the situation from getting worse and help maintain the possibility of a two-state solution by supporting a sustainable and independent economy. Some of the expected results of the extension, depending on partners and scale of funding, will include:

- Preserved jobs in the West Bank by providing businesses with short-term liquidity support.
- Preservation of major West Bank businesses, with some initiation of sales growth.
- Reduced losses in the value and volume of exports from the OPTs
- Increased energy efficiency and renewable energy generating capacity, with less reliance on Israel.
- PA support to plan Gaza recovery and post-war trade frameworks. Basic water and energy services resumed in project areas in Gaza.
- PA’s water and energy institutions capacities improved including development of reconstruction plans.
- Water and energy infrastructure developed in support to stabilise the West Bank economy.
- Analytical work on the resumption of basic services in Gaza developed.
- Key asks developed to coordinate international efforts to lobby for resumption of basic services in Gaza.

C. DETAILED OUTPUT SCORING

Output Title	Improved water quality and strengthened capacity of selected institutions
Output number:		1	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Infrastructure built or rehabilitated in the project area (WB)	Project Restructured to address Gaza conflict and supplies delivered / Works contract subcomponents: / Subcomponent 1.1 Southern Main Carrier System funded by the Kuwait Fund for Arab Economic Development (KFAED). The works is divided in two contracts both of which were signed in March 2023. The works will start by November 2023. / Subcomponent 1.2 - Additional water supply and network improvement (KFAED). / Sub-Component 1.3- W01- Reconfiguration of Water Distribution System – Southern Gaza Governorates (Rafah & Khan Younis Gov.) – Works started in July 2023. / Sub-Component 1.4- Reconfiguration of water distribution system – Middle Area, Gaza and Northern Gaza. Works started in August 2022 and as of July 2023 show a physical progress of 77%	Met expectations. The project was restructured on March 26, 2024. The contract between UNICEF and the Palestinian Water Authority in Ramallah (PWA) was signed on July 21, 2024 for the delivery of fuel, hygiene kits, and other relief supplies to Gaza for the amount of US$7 million. 6,500 hygiene kits have been delivered. As of November 2024, delivery of supplies was still ongoing, and the contract was extended to December 2025. / Works contract subcomponents: / Subcomponents 1.1-1.4 were paused as project activities were revised to respond to urgent needs in Gaza. / The World Bank met with PWA and Project Management Unit (PMU) staff on September 1st, 2024 and agreed that PWA would prepare a proposal for utilising the undisbursed funds for emergency interventions in Gaza and the West Bank. / Milestones remain in the logframe for when activities re-start.
1.2 Number of key products to improve performance of water institutions developed and approved or published	Agreement between Bulk Water Supply Unit (BWSU) and the Coastal Municipalities Water Utility (CMWU) for the handover of the short-term-low volume (STLVs). / Studies: / National water sector policy and strategy. / Bulk Water and Rainwater Harvesting Masterplans. / National Service Providers Improvement Program. / Detailed design for priority investment projects for Bulk Water in the West Bank. / Design of Tulkarem Waste Water Treatment Plan (WWTP), and Northeast Ramallah WWTP. / Design for the North East Ramallah Waste Water (WW) Networks and West Nablus WW Conveyance System.	Met expectations. In August 2024, the agreement was signed between PWA (BWSU) and CMWU. / Studies: / Met expectations. Contract signed December 2024 & activities under implementation. / Met expectations. Completed. Activity is completed and assessed under previous AR. / Met expectations. Contract signed December 2024 and under procurement. / Did not meet expectations. Activity completed in October 2024; however, an extension has been granted until May 2025 due to security situation. / Met expectations. Contract expected to be signed by December 23, 2024. / Met expectations. Contract signed in December 2024.
1.3 (a) # of substantial analytical products and reports produced or updated by the OQ, and shared with stakeholders to improve the water and wastewater sector (annual) / (b) OQ quality and influence rating for water sector (OQ)	a) 6 / b) Initial survey conducted and plan in place for follow up	a) Met expectations. 6 produced and shared. / b) Met expectations. Quality survey implemented, and results published in March 2024, with a plan to repeat yearly. Stakeholders rated the OQ: / 4.8/5 [good] for quality of analysis and / 4.1/5 [good/satisfactory] for influencing effectiveness.

Briefly describe the output and provide supporting narrative for the score

Output 1 scored an A as most indicators have scored met expectations.

Support to the Water Sector

As the conflict in Gaza persists, accurate assessments of developments on the ground and the status of completed works, which are likely to have sustained substantial damage, are not possible. Task teams continue to monitor the situation and explore alternatives. Prior to the conflict in Gaza, support was directed towards a water security development programme, covering the associated works of the planned Gaza Central Desalination Plant. The Project Management Unit (PMU) is designed to support the effective implementation of the project and provide funds to ensure continued operations of vital water assets in Gaza. However, since the start of the war the PMU is no longer operational and the contractor’s access to the construction site in Gaza is impossible, resulting in the stoppage of all works. Therefore, the first restructuring of the project took place at the beginning of 2024 to repurpose US$9 million of unallocated funds to meet urgent, short-term water needs that have emerged in Gaza. An agreement for US$7 million was signed with UNICEF in July to provide internally displaced persons with a) fuel to operate critical WASH Facilities, b) hygiene kits, c) collapsible water tanks, and d) support to critical water supply operations such as water tankers and water trucking services. Another agreement is in preparation with UNDP to provide equipment and water tanker trucks for US$2 million. The project closing date was extended by one year to December 31, 2025.
To improve the performance of water institutions (indicator 1.2), the agreement between Bulk Water Supply Unit (BWSU) and the Coastal Municipalities Water Utility (CMWU) for the handover of the short-term low volume (STLVs) was signed in August 2024. The agreement stipulates that BWSU/PWA will supply (in bulk) the CMWU with large quantities of drinking water for distribution in the Gaza Strip. Even though a few contracts to improve the performance of specific components of the water networks are still under negotiation, the World Bank has generally met expectations. Out of the six consultancies conducted and prepared, three have been signed and implementation is underway, while the remaining three are still under negotiations.
Support to the Office of the Quartet

Throughout 2024, the OQ has worked with the International Community (IC) to support the PA in developing the Resumption of Basic Services (RoBS) non paper for water in the Gaza Strip. This was endorsed by the PA and then shared with the Government of Israel (GoI). Progress in resuming basic water services has been limited, falling far short of Gaza’s critical needs, though dialogue with the GoI is ongoing. The OQ has also supported the PA on challenges facing the West Bank in three areas: water supply, wastewater treatment and reuse, and Israeli deductions for water supply and wastewater treatment. They supported the PWA with an analysis “Differences between Palestinian and Israeli plans for addressing the water shortage problem” which involved collecting and compiling all data on current and projected water supply quantities. The OQ worked with the PWA and the International Community and introduced two studies to help address some of the challenges facing the wastewater sector: “The economic benefits for treatment and reuse of wastewater” and “The impact of advancing Israeli wastewater plan on Palestinian plan”. This helped the PWA and the IC to engage with the GoI and other stakeholders to advance the reuse of wastewater. The OQ also supported the PWA with two new pieces of analytical work: “Updating the tariff analysis for water supplied from Israel to the West Bank” and “Developing economic correlation for service providers’ performance” to address the challenges faced by the PA when the Israeli Water Authority (IWA) set new water prices.

The OQ conducts an annual ‘quality’ survey requesting stakeholders to assess the OQ’s work based on two rates: ‘quality’ and ‘effectiveness to influence’. Stakeholders’ overall assessment for both indicators was good. For ‘quality’ this includes good use of evidence, clear recommendations and structure, and analysis being timely. ‘Effectiveness to influence’ includes good relationships with most key players and having substantial influence in specific areas.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.-

Recommendations from 2023 AR	Progress
World Bank present to FCDO and other donors reviewed programme which will address the new needs arising from the war for future support consideration.	Proposal for water sector programmes have been submitted to the World Bank board for approval. As of yet, no definitive approval has been given.

Lessons Learned

- The critical need for a Contingency Emergency Response Component (CERC) to be included within the programme to respond in a timely way to emergencies.
- Enhanced coordination and exchange of information and agreements of cooperation during emergencies between the World Bank and UN organisations prior to conflicts.
- Inclusion of gender-sensitive crisis management and effective community engagement plans should be designed to be adaptable to maintain essential communication and grievance redress mechanism even during severe disruptions.
- While the OQ has strong technical expertise and have produced valuable reports, it is difficult to measure their use and impact using current indicators.
Recommendations

- FCDO to discuss with World Bank the rapid activation of CERC/ restructuring to quickly respond to post cease-fire in Gaza.
- World Bank to have periodic meetings with UN organisations to ensure effective coordination.
- World Bank to ensure and track inclusive gender-sensitive crisis management within World Bank’s delivery and M&E.
- FCDO to discuss with World Bank their plan for 2025 for early recovery and have indicators on activities that are relevant to SEED.
- OQ to ensure analytical products are shared with relevant parties proactively.
- FCDO to work with the OQ to assess and review the annual survey indicators. Although rating of the survey as ‘good’ there is room to further capture the benefits of this analytical work on stakeholders.

Output Title	Improved effectiveness, connectivity, and production of electricity
Output number per LF		2	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 (a) # of substantial products and reports in the energy sector (including for PETL) developed by the OQ and shared with partners; and (b)	a) 4	a) Met expectations. 4 produced and shared.
2.2 Number of a) connection points and b) MV and network distribution lines upgraded, and c) smart metres installed (WB)	(a) Connection points: / 1. Expansion of Sarra and Tarqumia substations. Procurement to start end of 2024. / 2. Beit Ula 11 KV project. Environmental & Social Management Plan (ESMP) to be updated and approved by the Bank for installation to begin. / (b) MV lines / 1. Hebron Electricity Distribution Company (HEPCO): Palestinian Energy and Natural Resources Authority (PENRA) is to accept infrastructure plan into operation. / 2. Northern Electricity Distribution Company (NEDCO): upgrading lines to evacuate solar energy from photovoltaic (PV) plant. / 3. Upgrading Tubas Distribution Electricity Company (TDECO) MV lines. / (c) Smart meters / The contract for the supply of the smart meters for Electricity DISCOs in the West Bank and Gaza.	(a) Connection points: / 1. Almost Met. Contract signed in January 2024, design phase completed in October 2024, and procurement started. / 2. Did not meet expectations Still pending Bank approval. / (b) MV Lines / 1. Met expectations. Lines installed November 2024 and awaiting (PENRA) approval. / 2. Met expectations. Project full installation of MV cable lines completed in December 2024. Limited Power Source (LPS) and auto closer expected to be delivered from Korea in January 2025, followed by the accepting stage. / 3. Met expectations. All construction works completed by November 2024 for ‘aerial’ and ‘underground’ in final stages of installation. / (c) Smart meters / Met expectations. Contract completed in June 2024. Negotiations with INHEMETER (the master data management supplier) completed in November 2024, 150 Smart Meters have been delivered and are being tested.
2.3 (a) Private capital mobilised for renewable energy (amount ($)) / (b) number of solar PV systems installed (of which female beneficiaries) (Also ICF indicators) (WB)	a) Progress on the Liquidity Support and Account Payment System (LSAPS) and network evacuation assessment for 5 solar sites. / b) / 97 Beneficiaries served by newly installed solar PV systems in Gaza. / Installation of Solar PV systems in 6 hospitals in West Bank with connections to grid.	a) Met expectations. World Bank released US$ 20 million in donor funds into the LSAPS Deposit Account in June 2024. Contract was issued in late November 2024 for the Transaction Advisor to help LSAPS Management Board. / b) / 1. Did not Meet expectations. Activity put on hold. No progress due to Gaza conflict. / 2. Moderately did not meet expectations. Solar panels installed for all 6 hospitals in December 2024; some have been connected to grid and some in process.

Briefly describe the output and provide supporting narrative for the score

On average, output 2 scored an A as most indicators met expectations.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Support to the Electricity Sector

The OQ continued its work with the International Community and the private sector on the ‘Resumption of basic energy services in Gaza’. The OQ produced a non-paper that was endorsed by the PA and shared with the GoI. This has informed the ICs engagement with the GoI and the PA, which the UK leads for the energy sector. As with the water sector, while this work is yet to bring material benefits to energy supply in Gaza, there is continued and positive engagement with both parties on this file.

Since the PA noted electricity imports to be at significant cost for the Palestinian economy, exceeding USD $700 million per year, the OQ produced the ‘Regional price benchmarking study’ helping PENRA to better understand pricing norms in the region and recent market changes in the Israeli electricity sector. The OQ also proposed a mapping analysis ‘Updates and mapping of solar energy generation in Area C’ to PENRA to support their efforts to identify additional sites totalling 1500-2000 MW. The Gas for Gaza (G4G) project, which is in line with FCDO’s fossil fuel policy, aims to facilitate the development of a natural gas pipeline from Israel to the Gaza Power Plant (GPP) which would help to address Gaza’s long term energy needs by providing a reliable, cost-effective and efficient alternative to diesel. The OQ supported with the detailed design phase for the project, but this is currently on hold due to the ongoing situation and the OQ will support the PA as and when this programme can be resumed.

Support to the World Bank Advancing Sustainability in Performance, Infrastructure and Reliability of the Energy Sector (ASPIRE) Programme

Progress on ASPIRE Phase 1 has been affected by the conflict in Gaza and the associated movement restrictions in the West Bank, in addition to ongoing delays in processing, procurement and environmental and social safeguards. Nevertheless, the disbursement rate of Phase I rose to 46% in June 2024, due to the achievement of important milestones including the disbursement of US$20 million for the Liquidity Support Account and Payment System (LSAPS) activity, as well as the signing of the contract for the supply of smart meters for Electricity DISCOs in West Bank and Gaza where 150 smart meters have been delivered and tested. The “Improvement of the Electricity Infrastructure in the West Bank and Gaza” component has enabled the supply of the low and medium voltage cables, steel materials, wires, and accessories. Despite the delays, most MV and network distribution lines in the West Bank have been upgraded and installed.

The Gaza solar PV systems installation activity, which includes female beneficiaries, has been on hold since the outbreak of war due to displacement of people and damage to infrastructure. In the West Bank, solar panels have been installed at six health facilities. The connection of some of these panels to the grid has been delayed in some cases.

Describe any changes to this output during the past year, and any planned changes as a result of this review

No changes made. However, due to the ongoing war and the SEED extension underway, we will work closely with the World Bank, the OQ and other stakeholders to develop plans to support energy recovery in Gaza.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from 2023 AR	Progress
Aim to agree with WB on result indicators for 2024 to allow FCDO to robustly track progress and monitor the plans as the conflict continues.	Milestones were finalised in July 2024
Discuss with the WB the potential to add gender/inclusion and climate progress milestones to progress cross-cutting issues.	WB together with PENRA have conducted activities in relation to GBV and have included milestones on gender. For example, ASPIRE Phase I has already exceeded one of its two gender indicators. 18 percent of engineers employed in public and private sector government agencies are now female, surpassing the goal of 12 percent. Women hold a range of technical positions, working as engineers both in the field and off field, at PENRA, the Palestinian Electricity Transmission Company (PETL) and the electricity distribution companies (DISCOs).
Consider with WB how to facilitate progress on LSAPS, including through direct FCDO engagement with Ministry of Finance (MoF)	FCDO has engaged and raised this with MoF to facilitate progress.
OQ to work with PENRA to highlight economic importance of advancing the 300 MW of Palestinian solar PV sites by FCDO staff conducting site visits	OQ supported PENRA’s tour to the sites by working with key partners, the EU and US. Site visit was attended by FCDO team member.

Lessons Learnt

- Collective lobbying, including from the UK with the PA on LSAPS, was important to achieve progress on the programme by addressing their concerns and providing TA to build their capacity.
- Collective engagement among donors, the OQ and PENRA, at the technical and political level, is essential to achieve meaningful progress on the resumption of basic energy services in Gaza.
Recommendations

FCDO to continue working closely with World Bank and OQ and other donors to review the energy programme to address the new needs arising from the war.

Output Title	Improved movement of cargo and capacity of trade related institutions and private sector firms to increase exports
Output number per LF		3	Output Score	A
Impact weighting (%):		35%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number, and example priorities, of (a) firms supported to increase exports and competitiveness and (b) policies functions or processes supported within trade-related institutions and ministries	a) 13 firms supported by Tasdeer / b) 16 products/solutions supported by Tasdeer. / Annual Priorities: / Process/guidance to develop the electronic certificate of origin platform / Areas for improving the quality of Palestine Post services and products identified	a) Met expectations.14 firms have been supported. / b) Moderately Did not meet. 12 processes, functions or structures within trade-related institutions and ministries have been supported this year. / Annual Priorities / 1. Completed and well-received by counterparts. / 2. Report identified areas to improve the quality.
3.2 Percentage of beneficiaries of Tasdeer trade interventions reporting that trade and private sector competitiveness interventions are re a) relevant to their needs, and b) satisfactory quality.	a) 90% and b) 90%	Met expectations 100% and 100% satisfied with relevance and quality respectively.
3.3 Number of activities implemented, and example priorities, to improve the understanding of Gender Equality and Social Inclusion (GESI) constraints and barriers to trade related activities, or activities implemented to address these constraints and barriers	Planned target for Y4 = 14 / Annual priority: / Grant designed for Occupational Health and Safety (OHS).	Moderately exceeded expectations. 16 GESI activities implemented this year. / Annual Priority / Grant delivering capacity building on OHS has been designed and launched. Activities are underway and will be completed by the beginning of 2025.
3.4 Number of Business to Business (B2B) meetings conducted by participants through the “iktashef UK” programme	200 B2B meetings planned to be conducted in Y4	Exceeded expectations. 722 B2B meetings were held as part of the “Iktashef UK” programme.
3.5 (a) # of substantial analytical products and reports developed by the OQ to improve trade and movement of people and cargo and shared with partners (annual);	a) 2	a) Met expectations. 2 produced and shared

Briefly describe the output’s activities and provide supporting narrative for the score

On average, output 3 scored an A, thus meeting expectations.

Support to Improving Trade Relations and Private Sector

Tasdeer contributes to inclusive private sector-led economic growth and fiscal sustainability by working closely with the private sector, Palestinian Authority, and trade-enabling institutions. Direct private sector support remains central to Tasdeer’s work. The 14 signed agreements have encouraged economic growth across diverse sectors, including manufacturing, agribusiness, information technology, and services. Among the 14 firms currently receiving support, four are owned or managed by women, and two are located in marginalised areas. Tasdeer continues to review and refine its grant eligibility criteria to maximise support for target groups and FCDO-priority thematic areas, for example introducing a new grant window focusing exclusively on solar energy. Beyond direct export-promotion grants, Tasdeer rapidly conceptualised, designed, and implemented new activities to directly support the private sector, including an incentive package to improve exporters’ competitiveness amid higher war-time transaction costs.

Remaining a trusted and credible partner for the PA, Tasdeer expanded their partners within Government to include the Prime Minister’s Support Office and Ministry of Industry, where they have embedded advisors to provide demand-driven, flexible advice on priority areas. Tasdeer also delivered several high-profile outputs addressing crucial issues, including a pre-feasibility study and plan for industrial and agricultural investment in Gaza, an incentive package for exporters disbursing $203,000 to 47 exporters across 13 sectors, and support during the planning for an electronic certificate of origin. Throughout this year, Tasdeer supported their partner trade-enabling institutions to navigate war-time economic uncertainty and restart progress on long-term organisational development. In partnership with the PMA, Tasdeer launched a flagship interest-free loan scheme, enabling 700 Palestinian workers that have become unemployed as a result of the war in Gaza to start new businesses or expand their existing businesses. The launch event, attended by the PA Prime Minister, FCDO representatives, and other distinguished ministers, was a major success. It generated positive media coverage and received widespread attention through Tasdeer’s communication channels. Of the 3,659 applications submitted, 74 loans have been provided with more to be granted.

Ensuring economic growth is GESI-sensitive and inclusive continues to be a priority for Tasdeer. They launched a capacity building grant to support Occupational Health and Safety (OHS) by providing certified training to designated employees. Tasdeer delivers GESI-specific interventions to empower women, including completing its long-standing collaboration with the Businesswomen’s Forum to deliver a leadership programme for female businesswomen and upgrade 10 women-owned businesses.

The UK Palestinian Tech Hub is an initiative of the British Consulate General (BCG) in Jerusalem implemented as part of the UK-funded Tasdeer programme. The objective of the UK Palestinian Tech Hub is to create and facilitate relevant connections and partnerships between the British and Palestinian technology ecosystems, with the goal of promoting cohesion and sustainability in the Palestinian tech sector. The hub serves as a gateway to the UK, while also bringing years of accumulated knowledge and expertise to Palestinian companies. The Tech-Hub continued to link Palestinian tech companies with prospective clients and partners in the UK, while also creating opportunities to develop strategic partnerships. During the June 2024 event, the participation of 12 Palestinian companies was successfully facilitated. The delegation achieved strong results with more than 700 business-to-business meetings documented, 6 engaging pitch presentations, and strong social media outreach. Follow-up feedback sessions with participants highlighted the delegation’s success in fostering new partnerships and increasing international visibility, and three companies have reported growth in exports securing deals worth $55,500 through connections established via the programme.

The OQ continued its efforts, working with stakeholders and the IC, to improve trade and movement of people and cargo. This included the Door to Door D2D programme – a programme which enables Palestinian producers to ship products to the Israeli market without undergoing costly and time-consuming back-to-back process at commercial crossings. Working closely with the PA’s Ministry of National Economy (MoNE), the OQ developed a draft concept to facilitate cement imports from Jordan. It includes identifying current logistical and regulatory challenges and proposing solutions to improve the process.

In close collaboration with the Palestinian Ministry of Industry and PFI, the OQ’s efforts are focused on identifying measures that preserve employment and assist manufacturers in bridging the current crisis to stabilise the situation in the West Bank. The OQ has collaborated with PFI to develop a ‘bridging programme’ aimed at delivering focused and limited financial injections to industrial facilities per pre-agreed criteria with the aim of preserving labour layoffs and maintaining operational continuity of industrial facilities. This is still under consideration.

Describe any changes to this output during the past year, and any planned changes as a result of this review
After an evaluation of Tasdeer’s achievements and the shifting economic dynamics driven by the current conflict, Tasdeer collaborated with FCDO to review and update their logframe. These revisions were formally approved in September 2024 within Tasdeer’s logframe. The main modifications under this output are outlined below.
- Output 1.1: Number of, and example priorities related to, new/improved products/solutions supported within trade-related institutions and ministries. The target increased to 34 products/solutions for 2024 and 37 for 2025.
- Output 1.5: Number of B2B meetings conducted by participants through the “iktashef UK” programme. The target increased to 200 B2Bs for 2024 from 60 B2Bs for 2023.
- Output Indicator 1.6: Installed capacity of clean energy as a result of International Climate Finance (MW). This is a new indicator with a new proposed target of 0.32 MWp. It measures total clean energy ‘installed capacity’ (in MW) from ICF-eligible expenditure, including installed capacity from on-grid and off-grid networks.
- Output 1.7: Number of applicants by formal former workers in Israel to loan facility. This is a new indicator that counts the number of applicants who apply for interest-free loans under Tasdeer’s Baader scheme via the PMA’s Munsha'ati platform.

The above modifications will be further reviewed to be included in the overall SEED’s logframe

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from 2023 AR	Progress
The war has already had deep impacts on the Palestinian private sector, including liquidity, revenue, and relationships with Israeli customers and suppliers. Tasdeer’s grant criteria and manual should be reviewed and, if necessary, updated to ensure that they are able to meet the needs of the Palestinian private sector. Tasdeer should remain open to different approaches in the West Bank and Gaza.	Tasdeer continues to innovate its approach to grants. It has piloted two new approaches to grants. / Tasdeer updated and streamlined its granting processes and criteria in existing windows, broadening support to include domestic sales.
Given FCDO priorities, Tasdeer should continue strengthening its climate change portfolio. It should commission expertise to assess performance against International Climate Finance indicators, and deliver a set of climate-focused activities.	Tasdeer developed support to businesses to install capacity of clean energy. 8 companies were supported that generated 0.374 MW.
In preparation for the ‘day after’, Tasdeer should continue scenario planning, establishing appropriate operational platforms, and designing interventions that would enable Tasdeer to deliver activities immediately in Gaza upon the end of the war.	Since the beginning of the war, Tasdeer has worked closely with FCDO to formulate scenarios and design future activities. These activities/scenarios mainly focus on the West Bank with potential re-entry into Gaza pending a ceasefire.

Lessons learned
- Piloting innovative approaches to engaging with the private sector proved essential to pivot and adapt to the current context.
- External economic and security context may impact progress on certain activities/interventions.
Recommendations
- Tasdeer to continue to scale up tested pilots and continue to pilot innovative approaches to engaging with the private sector for the extension.
- For ceasefire and the next phase in Gaza , FCDO to ensure Tasdeer maintains technical and operational readiness to rapidly roll-out activities in Gaza. These include; early recovery support to Gazan SMEs and farmers and replace critical parts and infrastructure to SMEs to resume operation.
- FCDO to further review the Tasdeer’s indicators 1.6 and 1.7 to be included in the overall SEED’s logframe.
- FCDO to discuss ways of measuring how OQ reports are being used/applied.

Output Title	Improved PA customs capacity to assume functions from Israel and increase revenues
Output number per LF		4	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 a) Number of new/improved products/solutions supported to improve PA customs capacity, with example priorities, and % of beneficiaries reporting that these interventions are b) relevant to their needs and c) good quality	a) Planned target for Y4 = 3 / b) 90% and c) 90%	a) Met expectations: 4 products/solutions that have been completed bringing the cumulative number to 10 / b) Met expectations.100% beneficiaries reporting satisfaction with relevance / c) Met expectations.100% beneficiaries reporting satisfaction with quality
4.2 (a) # of substantial technical products and reports related to PA customs IT infrastructure, systems, and capacities and clearance revenues, developed by OQ and shared with partners (annual); (b) OQ quality and influence rating for customs sector (OQ)	a) 2 (related to fiscal and financial stability) / b) Initial survey conducted and plan in place for follow up	Met expectations a) 2 produced and shared. / b) Met expectations. See Indicator 1.3

Briefly describe the output’s activities and provide supporting narrative for the score

This output aims to improve the PA customs capacity to assume functions from Israel and increase revenues from trade-related taxes. On average, output 4 met expectations, therefore scoring an A.

Support for the Trade Facilitation and Customs Support (Tasdeer) programme

Tasdeer supported four new products/solutions to continue improving MoF Customs capacities. Specifically, Tasdeer consistently provided support and maintenance for the Automated System for Customs Data (ASYCUDA) as well as for the IT department at the MoF. The contracted local IT service provider developed the front-end for the Electronic Certificate of Origin Module within the ASYCUDA system, which was adopted by the MoF/Customs department. More broadly, recognising the changing needs of their stakeholders, Tasdeer has pivoted towards offering technical assistance and advisory services to the Minister of Finance, concentrating not only on Customs issues but also on broader fiscal matters, including the issue of clearance revenues.

Support for the Office of the Quartet
The contraction of the Palestinian economy has led to a projected deficit of approximately 1.86 billion $ in 2024. Since clearance revenues represent around 65% of PA income, it has suffered tremendously as a result of the contraction. To address this, the OQ produced a comprehensive review of the Paris Protocol yielding recommendations which need to be addressed. It also provided substantial pieces of analytical work to improve fiscal and financial stability of the PA. These covered: e-VAT agreements, Allenby passenger fee sharing and updates or tracking matrices on e-VAT, customs transfers and fiscal files.
Describe any changes to this output during the past year, and any planned changes as a result of this review
Some of Tasdeer indicator targets have been adjusted this year to reflect changes in approaches. For this output, the annual target of output 2.1b: Number of new/improved products/solutions supported to improve PA customs capacity, with example priorities was raised to 7 for 2024 and reduced to 7 products or solutions for 2025.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from 2023 AR	Progress
Building on recent successes, Tasdeer should continue to expand its horizons, and work collaboratively with the MoF across customs, fiscal matters, and other thematic areas. It should remain open to supporting MoF in responding to new and emerging priorities, for example responding to the war on Gaza, even if these priorities are outside of the scope of customs.	By aligning its activities with emerging Governmental priorities and broadening engagement beyond Customs, Tasdeer has fostered close collaboration with the MoF, and remains a partner of choice for ad hoc technical advice. This enabled Tasdeer to navigate a period of political uncertainty, including onboarding and briefing the new Minister of Finance during their transition into the role.
Tasdeer should continue to advocate for a transfer of function, and support preparations within the relevant ministries. The customs transfer matrix, prepared by Tasdeer, provides a strong starting point for further advocacy, which should be tailored to reflect the new international operating context.	The Customs transfer matrix has been completed. However, due to the ongoing war, the MoF has redirected its focus towards addressing other pressing priorities, primarily concerning the PA’s fiscal situation.

Lessons learned
- The ongoing conflict has forced MoF to shift its priorities towards revenue generation. Tasdeer has also effectively provided ad hoc advisory support to MoF to directly address high-priority issues like clearance revenues.
- Tasdeer to be flexible and work closely with other UK funded programmes to complement activities.
Recommendations
FCDO to review how Tasdeer’s support to the MoF fits alongside a broader package of support through EPICS.

## D: VALUE FOR MONEY (1 page)
VfM performance compared to the original VfM proposition in the business case

SEED is explicitly designed to be adaptive to changes in the volatile political environment, and to test scalable and innovative interventions. A sufficient degree of flexibility to stop what is not working and to reallocate resources to where progress can be realised, enables SEED to take a measured risk approach to achieve results and vfm. The programme’s design supports interventions which directly reach individual beneficiaries and develops case studies which support evidence-based policy decision making. The ongoing war in Gaza has severely impacted the OPTs, impeding almost all activities/interventions of the programme. Nevertheless, the World Bank, OQ and Tasdeer have all been quick to adapt to the changes and challenges resulting from the war to continue to deliver value for money activities.

World Bank Water & Energy Sectors

Economy: For the water sector, the project has been restructured to use part of its uncommitted funds to procure urgent water needs in Gaza through UN agencies. For ASPIRE-I (energy sector) the procurement plan was updated on May 28, 2024. The disbursement of US$ 20 million related to the Liquidity Support Account and Payment System (LSAPS) activity has increased progress by 50%.

Effectiveness: The water project was restructured on March 26, 2024, to: (i) repurpose $ 9m of unallocated funds to deliver relief supplies to Internally Displaced People (IDPs) in Gaza; and (ii) extend the closing date of the project by one year to December 31, 2025. For the energy sector, the current conflict in Gaza has affected the implementation of four (4) contracts worth US$ 3.3 million.

Equity: The water project is a gender sensitive programme. Prior to the conflict, the project was compliant with the Bank’s environmental and social (E&S) safeguards, and the overall safeguard performance rating was satisfactory. As for the energy sector, gender activities under ASPIRE include the recruitment of female engineers, expansion of solar energy to vulnerable female head of households (FHHs), to support the livelihood of women-owned enterprises through better access to electricity and to strengthen gender actions in policies and strategies in the sector.

Office of the Quartet:

The main cost driver remains staffing. The quality survey and their achievements provide evidence that the OQ is well managed and effective at converting its expertise into results and outcomes.

Having strong technical expertise and strong diplomatic relations with the International Community , the OQ is uniquely positioned to help facilitate Israeli Palestinian dialogue despite the deteriorating context. Common efforts across the international community, including key FCDO partners, enable a more efficient use of resources when advocating for specific outcomes with both parties. Hence, we judge it remains good value for money.

Tasdeer:

Tasdeer has developed a VfM framework of key indicators and produces VfM reports for FCDO on a quarterly basis.

Economy: Tasdeer’s project management costs as a proportion of total budget was around 22% in 2024 (in 2023 and 2022 it was 18-19% and in 2021 it was 30%). This illustrates that the majority of the funding is going to the Flexible Fund, thus maximising project delivery. Assuming spending remains at around the same level, management spend is expected to remain at around 20-25% for the rest of the programme, reflecting the shift from starting up to programme implementation. Another approach to maximise VfM, Tasdeer uses international consultants only when necessary, reducing cost and making use of the highly skilled labour force in the OPTs.

Effectiveness: Tasdeer’s adaptive management approach has enabled it to continue delivering high-quality work by leveraging its established relationships with MoNE and MoF to immediately step-up and provide emergency technical assistance to the PA and to the private sector. For example, Tasdeer has successfully implemented a new institutional grant through a local organisation to strengthen agricultural value chains in Area C, implemented by the Palestinian Agricultural Relief Committee (PARC).

Equity: In 2024, Tasdeer had 33% women among its core team of long-term staff and consultants, compared with 31% in 2023 and 35% in 2022. This year, Tasdeer's GESI portfolio gained further traction through a targeted series of interventions aimed at achieving equity-focused outcomes of which include: supporting women entrepreneurs via the Business Women Forum, launching the Baader loan programme for displaced workers, integrating women into traditionally male-dominated sectors like agriculture and leather, and enhancing institutional capacity for gender-sensitive data and reporting. These efforts led to increased job creation, business growth, and improved access to services for women and marginalized groups, with all GESI targets exceeded and interventions rated highly for relevance and quality.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The overall risk of the SEED programme is major to severe due to the complex operating and security environment, as well as the deteriorating economic situation due to the war. Established war-time trends of increasing economic hardship, deteriorating security, and ongoing political uncertainty are three interlocking and mutually reinforcing risks that affect the overall the programme. SEED Implementing Partners follow a risk management framework in line with FCDO’s guidelines and risk management policy. Risk registers are regularly maintained by Implementing Partners and reviewed at the programme level with FCDO. To mitigate risks, it is important to continue to deliver a flexible and adaptive programme that meets the needs of beneficiaries by scaling interventions up or down, as needed.

Key risks include:
- Israel’s destruction of investments in Gaza includes Tasdeer’s grantees and the World Bank projects, all of which have been destroyed. The security situation does not permit entry into Gaza to assess the situation. Should a ceasefire take place, it is foreseeable that resources would be redirected to supporting Gaza businesses to re-build their infrastructure and operations, shifting some of Tasdeer’s export-focused priorities. FCDO and SEED partners are monitoring the situation and preparing plans for the next phase in Gaza.
- Connected to the above, mounting fiscal pressures on the PA (albeit somewhat attenuated by the EU’s recent injection of €400 million budgetary support in July 2024), combined with increased political instability and heightened tensions between the Palestinian Authority and Israel, raise the risk of further deterioration in the West Bank, across many dimensions including security, political, and economic. In the most extreme scenario, it could lead to the collapse of the PA. Deterioration in the West Bank will undermine SEED’s ability to deliver meaningful change, particularly on technical assistance interventions which are reliant on collaborating with government institutions.
- The ongoing war has reduced stakeholders’ ability to deliver existing interventions because of shifting priorities, operational impacts, and/or a deterioration in Israeli-Palestinian diplomatic relationships. For example, Israel’s heightened restrictions on Palestinian traders using the King Hussein Bridge have limited Tasdeer’s ability to enhance trade through KHB, which in turn has affected beneficiaries who rely on the bridge. The deteriorating Israeli-Palestinian diplomatic relationships since the start of the war have affected interventions that require bilateral agreement, such as the Joint Economic Committee (JEC).

Update on Partnership Principles (delete this section if n/a) [1/2 page]

FCDO’s assessment of the Palestinian Authority (PA) commitment to UK’s four Partnership Principles (PPs) underpins our engagement with the PA, including our Technical Assistance to PA institutions. FCDO’s assessment is that the PA demonstrates a partially credible commitment to the Partnership Principles. There is relatively strong progress on improving public financial management and a continued commitment to delivering effective services and reducing poverty, despite the challenges of Covid-19 and the impact of occupation. However, cases of abuses of human rights and restrictions on freedom of expression continue and there is potential for greater action to strengthen human rights protection and increase domestic accountability in areas within the PA’s control. The UK will continue to monitor these areas closely and raise with the highest levels of the PA.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

World Bank

For the Water Sector: the World Bank reviewed the Project’s Financial Management (FM) arrangements undertaken by the PWA. The review and discussions conducted during the mission concluded that PWA maintains a relatively sound FM system. The latest Interim Financial Report (IFR) covering Q1 2024 was submitted on 24 April 2024. The 2023 financial and technical audit reports are under progress and should be submitted before the agreed deadline. The Financial Management risk rating remains Substantial for the Project, and the performance rating continues to be satisfactory.

For the Energy Sector: the mission reviewed the Project’s Financial Management (FM) arrangements undertaken by the Project Management Unit (PMU) at PENRA and concluded that the PMU maintains a sound FM system. The FM risk rating remains Substantial for the project and the performance rating is upgraded to Satisfactory. Reasons for the risk ratings relate to the nature of the project activities and expenditures, in addition to the accounting and budgeting elements and implementation. The FM ISR performance rating is upgraded due to the improvement in the reliability and credibility of the project disbursement and budget and the refund of the ineligible severance payment made previously.

The Fiduciary risk remains substantial for both programmes.

FCDO continues to participate in biannual Trust Fund Steering meetings.

Office of the Quartet

To monitor the effectiveness of UK support, BCGJ conduct quarterly meetings with each of the supported teams. In the quarterly meetings, OQ teams and FCDO teams discuss progress, plans, risks and results. The quality survey completed by stakeholders also provides an overview of the OQ’s performance.

The OQ is administered as a project of the United Nations Office for Project Services (UNOPS). Since the main cost driver remains staffing for the OQ and UNOPS is responsible for the management of the finances, financial audited reports are submitted by UNOPS for review.

Trade Facilitation and Customs Support (Tasdeer) programme

Cowater International is a strong supplier for FCDO for the Tasdeer programme. In the most recent Strategic Relationship Management performance scorecards, Cowater received an 80/100. Cowater provides FCDO with robust and comprehensive delivery and financial updates. On a monthly basis, Tasdeer submits an update against interventions with Red-Amber-Green (RAG) ratings, which accompanies the monthly invoice to show the status of our workplan. Tasdeer provides more detailed narrative updates in quarterly progress reports, covering contextual changes, intervention-by-intervention technical updates, logframe results, as well as VfM analysis and financial performance. In addition, Tasdeer reports against contract KPIs every quarter covering forecasting variance; delivery against the workplan; and delivery against women’s empowerment initiatives.

Tasdeer and FCDO meet on a monthly basis, which has enabled FCDO to be actively involved in decision-making, and present a forum for discussion of achievements, changes in technical direction, risks, finances, and KPI progress. Informal meetings between Tasdeer and FCDO are conducted on an as-needed basis to discuss management, technical and stakeholder issues and changes to risks. Tasdeer also conducts ad hoc Political Economy Analysis meetings, to discuss contextual changes in Israel and the OPTs.

Tasdeer met its FY 2023/24 spending target (£3m) successfully, with a variance of £0.06%. On a monthly basis, any financial variances are explained with accompanying monthly invoices. These changes have been very much welcomed by FCDO. As a result of these changes and more rigorous financial management, Tasdeer’s timeliness and accuracy of invoices and forecasts has greatly improved. As of October 2024, Cowater and FCDO signed a contract amendment to better align the team’s roles and responsibilities with the budget and to enable retention of critical staff at increased competition in the market. Cowater – and its downstream partners – continues to comply with the Supply Partner Code and with Open Book Accounting.

The overall SEED programme spend to date is £54,791,851.39 (93% of overall budget). The programme’s flexibility allowed reductions and reallocations within the different components to meet ODA prioritisation. Disbursements made so far since the start of the SEED programme are as follows:
[note] This is in relation to the original budget of £59m. The new budget after the approved cost and time extension is up to £91m.

Partner / Project	Total spend (£)
World Bank Water and Energy Programme	38,000,000.00
EBRD	571,474.99
Office of the Quartet	4,255,953.71
1% Initiative (2019 and 2020 only)	39,610.95
Chief of Staff secondment to the OQ (2020 and 2021 only)	143,240.05
Tasdeer	11,781,571.69
Total	54,791,851,39

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

SEED‘s three components all have their own monitoring and evaluation (M&E) processes. Using the framework set out in the BCGJ’s Monitoring Strategy, the monitoring risk of SEED is moderate. The main risks are the high monetary value and risk of delivery given that economic growth is central to the BCGJ’s objectives, but the strength is the use of established and trusted partners.

All partners (World Bank, OQ, and Tasdeer) have established clear output and outcome indicators, which feed into the overall programme logical framework. Partners report on their workplan and indicators regularly (at least quarterly for OQ and Tasdeer, semi-annually for the World Bank).

Strong beneficiary accountability mechanisms across all interventions are encouraged to help ensure that UK support responds to real-world priorities. All partners are required to disaggregate M&E information, particularly for women and those with disabilities. The current operating environment especially in Gaza is not permitting implementing partners to conduct their planned activities, monitoring processes or needs assessments. To complement partners’ monitoring efforts the SEED programme team conducted the following activities during the reporting period:

- Maintained regular quarterly programme assurance meetings with all partners to assess progress on activities, compliance with FCDO PRoF, and review emerging risks.
- Monitored partners’ progress on logical framework milestones.
- Conducted high-level visits to monitor and evaluate successful implementation of projects. During visits, beneficiaries were asked for feedback about working with respective SEED partners.

Partner	Date of last narrative financial report	Date of last audited annual statement
World Bank PID MDTF	Received – February 2024	Financial audited statement for 2022/2023 – received February 2024
UNOPS/OQ	Received - October 2024	Financial Report and audited financial statements for the year ended 31 December 2023 – received November 2024.
Tasdeer	To be received – January 2025	Financial audited Statement for 2023 – received July 2024