Title: Support Economic Empowerment and Development in the Palestine (SEED)
Programme Value £ (full life): Up to £91 million		Review date: Feb 2026
Programme Code: [AMP ID#]300667	AMP start date: Nov 2018	AMP end date: March 2028

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A	A	A	A
Overall programme risk rating	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300667/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300667/documents

A. SUMMARY AND OVERVIEW [1-1 ½ pages]
Description of programme [1-2 paragraphs]

Support for Economic Empowerment and Development in Palestine (SEED) is an economic development assistance programme which aims to address the underlying constraints to sustainable economic growth and job creation in Palestine. The programme seeks to increase the sustainable supply of water and energy as a foundation of economic growth (particularly in Gaza), increase trade, enhance freedom of movement and customs revenue, and promote greater Palestinian economic sovereignty. The programme is fully aligned with and supports the UK’s objectives of maintaining the viability of a two-state solution and improving the livelihoods of Palestinians.

SEED consists of the three components:
- Support to the World Bank (WB) through its Partnership for Infrastructure Development (PID) in the West Bank and Gaza Multi-Donor Trust Fund (MDTF), with UK funding focused on the water and energy sectors. We also provide support through the Palestinian Fund for Reconstruction and Development (PFRD) MDTF, with a particular focus on the energy sector.
- A Trade Facilitation and Customs Support programme (Tasdeer), delivered by Cowater (a commercial service provider).
- Support to the Office of the Quartet (OQ), a UN special project, undertaking analytical work and facilitation between the Government of Israel (GoI) and Palestinian Authority (PA), and through its core contribution, the UK enabled work in water, energy, trade and movement, and clearance revenues and customs.

In November 2024, Ministers approved a cost and time extension for SEED, increasing its total lifetime budget to up to £91m and extending the end date to 31st March 2028.

Context

Since the last annual review, the political context arising from the war in Gaza, and Government of Israel’s (GoI) policies towards the occupied West Bank, and the closure of border crossings have continued to severely impact the Palestinian economy:

- Overall Palestinian GDP recorded an increase of 4% in 2025 compared to 2024; however, despite this modest improvement, it remains 24% lower than in 2023[1]. Disaggregated absolute GDP values for Palestine, the West Bank, and the Gaza Strip are not available in current official datasets, so the analysis reflects only the verified percentage changes. In the West Bank, GDP increased by 4.4% in 2025 relative to 2024, indicating a slight recovery in some productive sectors, while in the Gaza Strip, GDP contracted by a further 8.7% over the same period, underscoring the continued collapse of economic activity. [2]
  [1] https://www.pma.ps/en/Media/Press-Releases/the-performance-of-the-palestinian-economy-for-2025-and-economic-forecasts-for-2026
  [2] https://www.pma.ps/en/Media/Press-Releases/the-performance-of-the-palestinian-economy-for-2025-and-economic-forecasts-for-2026
- In Gaza, unemployment rose sharply from around 68%[3] in 2024 to more than 77%[4] in 2025, reflecting the near complete collapse of the labour market. In the West Bank, unemployment improved slightly, decreasing from approximately 31% in 2024 to about 28.5%[5] in 2025. However, this remains more than double pre-war levels, when unemployment stood at around 13% in 2022-early 2023, prior to the October 2023 conflict.[6]
  [3] The Performance of the Palestinian Economy for 2025, and Economic Forecasts for 2026
  [4] https://www.pcbs.gov.ps/site/512/default.aspx?lang=en&ItemID=6123
  [5] www.pcbs.gov.ps
  [6] https://unctad.org/news/unemployment-west-bank-nearly-tripled-six-months
- GoI continued to withhold PA clearance revenue resulting in a 50% decline in the PA’s primary source of income. This has led to an erosion of basic services and further reduction in civil servants’ salaries. The financial sector is under pressure due to cash accumulation arising from Israeli quotas on cash transfers with Israeli banks. Additionally, the legal waiver that allows Israeli banks to deal with Palestinian banks has been subject to short term renewals. Without this the Palestinian banking sector will be cut off from both Israeli and global financial systems.
- Access into Gaza has continued to be restricted during 2025. Since the ceasefire at the beginning of the year commercial crossings have largely remained closed. Shortage of basic goods is driving inflation within Gaza with basics goods up 20 times pre conflict levels[7].
  [7] https://temp.fscluster.org/sites/default/files/2025-04/Gaza%20Market%20Monitor%2C%20April%202025.pdf
- Overall international trade is 12% less in 2025 compared to 2023.[8] Due to security concerns the Allenby bridge has frequently been closed throughout 2025 further restricting trade, and trade through Israel has also been restricted. Compared to 2024, the Palestinian Central Bureau of Statistics (PCBS) data shows that there was no material rebound in trade volumes in 2025; the contraction in trade observed in 2024 persisted into 2025, indicating a continued downward trajectory rather than any improvement
  [8] PCBS | H.E. Dr. Awad, Presents the following: The Performance of the Palestinian Economy during 2025& the Economic Forecasts for 2026.
Summary supporting narrative for the overall score in this review [1-2 paragraphs]

This Annual Review covers delivery and results for 2025. Part of this annual review evidence was collected from delivery partners on their progress towards outputs and the programme’s outcomes and impact. Based on this evidence the overall score for the 2025 review is A indicating the programme is meeting expectations, with output 1 scoring A, output 2 scoring A and output 3 scoring A. This Annual Review covers delivery and results for the 2025 year. Evidence for the review was drawn from a range of sources, including programme monitoring data, regular programme review meetings, and qualitative change stories, alongside delivery partners’ quarterly and annual management reports on progress towards outputs, outcomes and impact.
Based on this triangulated evidence, the overall score for the 2025 review is A, indicating the programme is meeting expectations, with Output 1 scoring A, Output 2 scoring A and Output 3 scoring A.
The programme continued to flexibly respond to the changing context in Gaza and the West Bank, ensuring delivery has continued under the difficult operating environment; however, progress has not been achieved at the scale originally planned, as many activities in Gaza remain paused due to ongoing access and security constraints. In the water sector, the World Bank and the OQ have supported the Palestinian Authority (PA) in designing and communicating their plans for the recovery and reconstruction of Gaza whilst building the PA’s capacities in sector planning, coordination, and technical decision-making. In the electricity sector the World Bank has delivered new infrastructure in the West Bank despite an increasing difficult operating environment. Tasdeer has continued to support firms to reach new markets through engagement with trade enabling bodies and is providing resilience to businesses in the West Bank by providing loans to help them expand.

Major lessons and recommendations for the year ahead [1/2 page]

Lesson: There is a breakdown of GoI/PA cooperation at all levels, including on the economy and trade, and restrictive Israeli policies make it increasingly difficult to achieve progress through programming alone, requiring political solutions. Ongoing technical cooperation between GoI and the PA is necessary for the programme to achieve its outcomes.

Recommendation: By the end of Q2 2026, FCDO to work with the OQ and other partners to review and identify advocacy strategies, and messages to unblock political barriers and inform engagement efforts, along with other donors, with Israel and the PA on key policy issues.

Lesson: In 2025 the SEED logframe was updated with improved indicators and outputs. The inclusion of qualitative indicators has supported assessment of interventions and understanding of the impact of technical assistance. A new change story template has been tested as part of this annual review.

Recommendation: By June 2026, FCDO should work with partners to refine the logframe so that indicators accurately reflect the outputs of technical interventions and advice provided. By September 2026, FCDO and partners should finalize the revised change story template and ensure its integration into reporting.

Lesson: SEED has been successful in adapting delivery in light of the complicated political situation. However, as stated in lesson 1, programming is still dependant on collaboration between GoI and PA. Expectations of how much the GoI can be influenced on these matters differ between partners.

Recommendation:
By the end of the next reporting year, recognising evolving constraints on influence with the GoI, FCDO will continue structured coordination with OQ, donors and PA counterparts to ensure operating assumptions are regularly validated and reflected in programme planning and risk management. FCDO will also review activities planned for the final years of the programme, including the OQ light‑touch review through Palmel, to test ongoing relevance, deliverability and value for money, and to inform any necessary reprioritisation.

Lesson: Regular validation of the Theory of Change (ToC) is critical in volatile contexts. Assumptions that were valid at programme inception may shift due to political, economic, or security changes. A structured review process helps maintain strategic alignment, ensures interventions remain realistic, and supports adaptive management.

Recommendation: By end of Q2, 2026, FCDO should conduct a light touch review of the ToC to validate its underlying assumptions and ensure continued alignment with the evolving operating environment. This review should include consultation with delivery partners and incorporate any necessary adjustments to maintain relevance and effectiveness.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

SEED’s aim is to support inclusive and sustainable economic growth in Palestine, contributing to achieving the UK’s vision for a two-state solution. This impact is expected to be achieved through tackling key barriers to inclusive growth through a) improved access to water b) improved access to sustainable energy c) reduced restrictions to trade and competitiveness, and d) enhanced PA fiscal sustainability. Combined action in these areas will collectively contribute to increasing growth, creating jobs and generating revenue for the PA. Inclusion will mean that the benefits of growth are spread more fairly throughout the Palestinian population, including to women and other marginalised groups, and this focus is mainstreamed across the programme. The main interventions of the SEED programme include:

- Engagement in policy dialogue
- Coordination of the parties
- Provision of technical assistance
- Support to infrastructure development
- Institutional capacity building of PA agencies and Palestinian companies.
- Support to private sector development and improving Palestinian trade performance and customs.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The war has deeply impacted SEED’s stakeholders, partners, grantees and the wider private sector, resulting in the immediate cancellation of all activities directly in Gaza – including a planned agriculture intervention under Tasdeer – and the temporary pause of some World Bank water and energy interventions. In the West Bank, delivery of existing activities has slowed due to restrictions on private sector activity, a weakened economy, and shifts in external partner priorities. Since the programme extension, the war in Gaza and the subsequent political fallout have continued to challenge several assumptions underpinning the original SEED Theory of Change, including the assumption that Israeli and Palestinian technical relations would continue and not deteriorate because of political developments. Despite this, the SEED Theory of Change has remained sufficiently flexible to respond to the evolving context, and the programme’s overarching impact and outcome statements remain valid, with adaptations focused on delivery approaches and sequencing rather than strategic intent; however, given the continuing volatility, FCDO will monitor the ToC’s underlying assumptions and undertake a light touch review during the current reporting year to ensure continued alignment with the operating environment.

Impact

The programme’s impact remains heavily shaped by external conditions, including movement restrictions, reduced revenues, and weak private ‑sector activity. Recent PCBS data show only a modest increase in overall GDP per capita, rising from a baseline of $531 to $539 in Q4 2024[9], but this national figure masks a sharp divergence: PCBS’s 2024 economic performance report confirms a severe economic collapse in Gaza due to widespread destruction and job losses, while the West Bank experienced comparatively more stability. This indicates that progress is not currently on a trajectory to meet the 2025 logframe milestone of $560-$565 GDP per capita, with preliminary Q1 2025 data already indicating an additional 1% decline[10].
[9] https://www.lacs-mopic.ps/public/files/LACS%20Weekly%20Update/LACS%20Weekly%20Update%202025/May%202025/PCBS%20Performance%20of%20the%20Palestinian%20Economy%20%202024.pdf
[10] https://www.pcbs.gov.ps

Looking ahead, achieving the target will require a significant rebound in trade, investment, and employment. Programme efforts will therefore focus on supporting partners to stabilise economic activity where feasible, while adapting interventions to account for the continued economic contraction in Gaza and slower than expected recovery overall.

Outcomes

Overall, the programme shows a mixed but constructive picture of progress across its expected outcomes, shaped by the ongoing conflict and access constraints. In the water sector, continued difficulties in accessing Gaza during 2025 meant that no targets were set for improvements in reliable and continuous access to public water services, reflecting the severe disruption to systems on the ground; efforts have therefore focused on meeting immediate needs where possible rather than measuring longer term service outcomes. In energy, the programme remains broadly on track, with support to renewable energy contributing to increased solar capacity in the West Bank and helping businesses improve energy security and reduce operating costs in a highly constrained environment. The strongest performance has been in export and trade, where results have exceeded expectations: 1,165 jobs were created through Tasdeer supported activities, well above the milestone of 747, and preliminary evidence indicates strong growth in private sector performance, with 16 supported firms reporting increased sales or exports in 2025—significantly higher than the milestone of 3 and above the 2024 baseline of 12 firms. Together, these results demonstrate that while conflict related constraints continue to limit progress in some sectors and results at scale in others, the programme is delivering tangible economic benefits and supporting resilience where conditions allow.

Outcome Indicator	Baseline milestone 2024	Milestone 2025	Achieved 2025
Water: Proportion of people with reliable and continuous access to safely managed public water supply services in Palestine.	~85% of West Bank population has reliable and continuous access. / < 30% of Gaza population has such access / this reflects significant disparity in water access in Palestine, largely due to infrastructure damage, limited water source and restrictions on materials	Increase access to water (87-88%) in West Bank. / No target for Gaza, due to ongoing conflict.	Did not Meet: Latest verified data (2024 baseline: West Bank ~85%, Gaza <30%) shows no evidence of reaching the 2025 target of 87–88% for West Bank. Gaza remains far below acceptable levels, with no improvement due to conflict and infrastructure restrictions.
Water: Number of people benefiting from WASH supplies delivered in Gaza.	Zero people reached (war zone)	At least 250,000 people benefited from WASH supplies in Gaza.	Substantially Exceeded Expectation. ~2,000,000 IDPs[11]
Energy: Proportion of renewable energy capacity in West Bank (this includes all imports and domestic generation)	4.5%	12.5% increase in West Bank. / No target for Gaza due to ongoing conflict	Met Expectations. By March 2025, renewable sources accounted for approximately 12.5% of total energy capacity in the West Bank.
Export and Trade: number of programmes supported firms and cluster reported increase in sales/ exports	6	3 The 2025 milestone was set at a low level because this was a new, short‑term extension period, and several firms were only able to access support for a few months. Increasing exports or sales typically requires longer engagement, and one of the main instruments planned for this period — a pilot challenge fund — had uncertain uptake and timelines. To avoid overstating expected results, the milestone was therefore set conservatively.	Substantially Exceeded Expectation / 18
Private Sector Sales: number of jobs created as a result of Tasdeer's supported activities	330	747	Substantially Exceeded Expectation / 1214
[11] https://www.unhcr.org/sites/default/files/2025-06/global-trends-report-2024.pdf

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Despite the severe deterioration in the economic situation in both the West Bank and Gaza, SEED continues to demonstrate value and an ability to deliver results. While the programme alone cannot reverse macroeconomic decline, it has helped prevent further deterioration by supporting system level resilience—for example, reducing costly Palestinian dependence on Israeli infrastructure through investments in energy resilience, water and wastewater systems under the World Bank MDTF, and advancing Palestine Standard Institute (PSI’s) international accreditation, which decreases reliance on Israeli testing and certification. SEED has also strengthened the capacity of Palestinian institutions through OQ’s fiscal and economic policy support to the PA, Tasdeer’s institutional upgrades with bodies such as PSI and MoNE, and World Bank supported reforms in land administration and utility governance. In Gaza, the programme successfully pivoted to reconstruction planning, providing the PA with technical advice through OQ’s economic modelling and recovery sequencing analysis, complemented by internationally led assessments of damages and needs in Gaza (delivered by the World Bank working with the EU and UN), and Tasdeer’s rapid diagnostics on private sector recovery needs. In the context of the wider UK portfolio, continuing SEED aligns with current FCDO priorities on stability, economic resilience, institutional strengthening, and maintaining the viability of a two-state solution. Its focus on private sector resilience, infrastructure readiness, and PA capacity complements UK efforts in governance, humanitarian response and diplomatic engagement, ensuring a coherent, joined-up approach across the British Consulate Jerusalem’s work.

In its final years, the programme should focus on assessing the viability of its work in an increasingly fragile economic and fiscal context, with the PA moving ever closer to collapse with weakened institutions and basic service delivery at risk. In this context, SEED should seek to adapt to identify and deliver activities to support systems level improvements beyond the output level results. Constraints to this have been recognised above.
 This reflects a deliberate shift in emphasis in the programme’s final years, building on consistently strong output-level performance. The intention is to strengthen how delivered outputs contribute to sustainable outcomes and systems-level improvements, within the constraints of the current operating environment.

## C. DETAILED OUTPUT SCORING

Output Title	Expanded water supply and improved water quality
Output number:		1	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
Interim WASH Services Supporting Infrastructure Development / Under the Associated Works Project (AWP): / 1. Progress towards the reconfiguration of the water distribution system in southern and middle area governorates of Gaza. / 2. Number of hygiene kits delivered and 5,000 Litre collapsible tanks installed. / 3. Number of emergency WASH (filling points and water trucking service) and installation of the filling points.	By December 2025: / 1. Progress on reconfiguration is dependent on access permitted under Phase 2 of the ceasefire implementation plan, which had not yet begun during 2025. / 2. Delivery of 11,700 emergency hygiene kits into Gaza is completed & Installation of 100 collapsible tanks in Gaza is finalized. / 3. Supply and install 4 water filling points and daily water trucking services provided (estimated quantity is 450 cubic meter per day)	Work could not start in 2025 due to these phased‑access constraints. Activities are now sequenced to begin under Phase 2 conditions in 2026. / Substantially Exceeded Expectation: 46,000 hygiene kits were distributed benefitting over 276,000 people in both North and Southern Gaza. 100 water tanks installed benefitting over 50,000 internally displaced people (IDPs) in the South of Gaza. / Moderately did not meet Expectation: Two filling points were constructed: one in Gaza city and the other one in in Khan Younis. 77,297 cubic meters of clean drinking water delivered. The other two planned were cancelled in agreement with PWA due to the locations falling outside of the yellow area.
Capacity Building/Studies / AWP / a) Priority Investment planning consultancy services. / OQ / b) # of technical products completed and shared with relevant actors to help restore water supplies and wastewater supplies under the Gaza Resumption of Basic Services (RoBS) project in supporting the PA in advancing the Emergency & Recovery Action Plan / c) # of analytical/technical products on helping advance Palestinian water extractions from ground water to realize the Interim Agreement Quota and organise supply from Israel adopted by relevant actors / d) # of technical products agreed for adoption in supporting the PWA, Ministry of Agriculture (MoA), and Environment Quality Authority (EQA) plans in advancing non-conventional water sources for irrigation and for the sustainability of service providers / Qualitative Indicator: / e) Qualitative evidence of knowledge transfer and capacity building resulting from technical assistance provided by the World Bank (AWP) and OQ - including case studies or change stories.	a) By December 2025 under. Priority Investment Planning: / -Consultancy contract awarded and mobilized. / - inception report submitted of which include: / Detailed workplan and methodology / Stakeholder engagement strategy / Preliminary assessment of infrastructure needs / Initial outlines of: / Water Sector Policy and Strategy / Bulk Water Supply Master Plan / Water Harvesting Master Plan / Environmental & Social Impact Assessment (ESIA) screening for Nablus West Treated Wastewater Conveyance System and Reuse Scheme / OQ / b) 3 products / c) 2 products / d) 3 products / Qualitative Indicator: / e) One case study or success story will be developed to capture and assess the extent of knowledge transfer and capacity building resulting from the technical assistance provided by partners.	Substantially did not meet Expectations.: The consultancy services contracts are under development and progressing. The contracts were extended until April-June 2026, as the project has been extended to December 31, 2026. This is likely attributable to extended procurement timelines, security constraints, and complex challenges in the West Bank context. / Moderately Exceeded Expectation. 4 products. Weekly and daily updates on Gaza facilities operations provided to the PA. / Substantially Exceeded Expectation: 4 products. 1. Continued development of water and wastewater segments of Palestinian infrastructure map and excel workbook shared and engaged with the Palestinian Water Authority (PWA). / 2. Analysis of data from PWA on priority infrastructure. / 3. Developed comparison matrix of different PA priority plans including the National Development Pact for the future of Palestine (charting the pathway toward a self-resilient, inclusive and right-based Palestinian State). / 4. Shared water prices analysis with different stakeholders. / Moderately Exceeded Expectation: 4 products. / 1. Shared opportunity cost of transboundary wastewater with stakeholders. / 2. Shared summary of Israeli wastewater plans with different stakeholders. / 3. Prepared a technical briefing for the Political Water Group outlining Israeli wastewater development plans in the West Bank and their implications for Palestinian priority projects. This included analysis used to support draft PA positions to the GoI and draft IC messaging to the GoI. / 4. Developed comparison matrix of different PA priority plans. / Met Expectation: 2 change stories. Through the OQ work – “Strengthening PWA Leadership and Advocacy for Water Sector Development through Technical Assistance and Partner Alignment. Through the WB work - “Building Institutional Resilience and Water Security in Gaza through Technical Assistance and Emergency Response” both adopted by PWA.

Briefly describe the output and provide supporting narrative for the score

This output was assessed as A as overall progress against indicators met expectations. However, some milestones exceeded or did not meet expectations. The water sector in Palestine faces persistent challenges: in Gaza, 89% of water infrastructure is estimated to be damaged or destroyed, and physical access for infrastructure works remains impossible without a permanent ceasefire. In the West Bank, deductions from the Palestinian Authority’s revenues by Israel to clear utility bills limit available funding and hinder infrastructure improvements. Despite these conditions, the programme adapted effectively to ensure impact.

Under emergency WASH services, results far surpassed planned targets. A total of 46,000 hygiene kits were distributed, benefiting over 276,000 people across North and South Gaza. In addition, 100 collapsible water tanks were installed, providing safe water storage for more than 50,000 internally displaced persons in southern Gaza. While the target for water filling points was four, two were successfully constructed in Gaza City and Khan Younis, and 77,297 cubic meters of clean drinking water were trucked to affected populations. The remaining two filling points were cancelled in agreement with the Palestinian Water Authority due to security and location constraints.

Capacity building and technical assistance also exceeded expectations. Technical products supporting water and wastewater restoration were delivered beyond targets: four products under each category (b, c, and d) compared to planned targets of two or three. These included infrastructure mapping, water pricing analysis, and comparative matrices of priority plans, all shared with relevant actors. Importantly, two change stories were developed to capture the qualitative impact of this work. While the change stories themselves are internal learning tools, the underlying analysis and products they document were used by the Palestinian Water Authority in planning discussions and partner coordination throughout 2025.The first story, “Strengthening PWA Leadership and Advocacy for Water Sector Development through Technical Assistance and Partner Alignment,” shows how OQ’s support enabled PWA to lead sector recovery efforts more effectively by aligning partners and advocating for investment priorities. Through consultations with PA leadership and international partners, and the development of advocacy tools such as maps and project lists, PWA adopted a more proactive role in preparing and sharing master planning documents, reframing water development to link technical priorities with political context. This change was adopted by both PWA and international partners, who agreed to use common advocacy documents for engagement with the Government of Israel, improving coordination and reinforcing PA ownership. The second story, “Building Institutional Resilience and Water Security in Gaza through Technical Assistance and Emergency Response,” illustrates how World Bank interventions helped PWA maintain essential services during the crisis and integrate emergency response into long-term planning. These changes were not only documented but were underpinned by technical work that the PWA drew on during planning and coordination discussions throughout 2025, which contributed to our assessment of this output.

To improve clarity on the nature and contribution of the technical products developed this year, particularly in relation to non‑conventional water source planning, four products were delivered. Of these, two directly supported planning for non‑conventional water options—namely the analysis of opportunity costs for treated wastewater reuse and the technical briefing on wastewater developments that affect Palestinian reuse potential. The remaining products provided complementary sector planning inputs that informed PA and partner discussions but were not themselves non‑conventional water products. These materials were used by PWA and other stakeholders in internal planning and coordination processes during 2025, contributing to decision‑making in this area even though they were not formally “adopted.”

In addition, the World Bank reallocated funds to emergency response through UNICEF and UNDP, enabling the delivery of water trucking services and emergency supplies worth approximately $500,000. These actions ensured continuity of essential WASH services and supported the population during an unprecedented crisis. Taken together, these achievements—quantitative results that exceeded milestones and qualitative evidence of institutional impact—justify the assessment of this output as A, reflecting strong adaptation and delivery under extraordinary circumstances.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendations from 2024 AR	Progress
FCDO to discuss with World Bank the rapid activation of Contingency Emergency Response Component (CERC)/ restructuring to quickly respond to post cease-fire in Gaza.	During the year, progress was made in planning for a post ceasefire response in Gaza, with the World Bank and the Palestinian Water Authority discussing options to extend and restructure the AWP project to enable rapid reactivation once access allows. This included identifying priority recovery activities, keeping contracts open, and preparing the groundwork to move quickly when conditions permit, even though implementation has not yet been possible.
World Bank to have periodic meetings with UN organisations to ensure effective coordination.	Minutes of the meetings between the World Bank and UN organisations have been shared during donor meetings with the WB.
World Bank to ensure and track inclusive gender-sensitive crisis management within World Bank’s delivery and M&E.	The World Bank has confirmed its tracking of inclusive gender-sensitive crisis management is within delivery and M&E. This confirmation is based on multiple discussions with WB and documents (Annual report and aide memoires) shared by them.
FCDO to discuss with World Bank their plan for 2025 for early recovery and have indicators on activities that are relevant to SEED.	During the year, FCDO discussed with the World Bank its 2025 early recovery planning for the water sector, including priority activities and indicators intended to signpost ceasefire response. While implementation remains constrained by access, the existence of a defined plan and results framework provides a basis for SEED relevant monitoring once conditions permit.

Lessons Learned

- Coordination and collaboration across the international community and the PA is vital for engagement with the GoI. Early engagement between the IC and the PA helps build consensus faster and reinforces PA leadership.
- The fallout from the war has led to less engagement from the GoI on technical matters. PA expectations of the influence that the OQ has on the GoI need to be managed. PA expectations of the OQ’s role in GoI engagement need to be managed, particularly given that the OQ operates primarily as a facilitator and technical interlocutor supporting member state‑led influence.
Recommendations

By April 2026, FCDO should work with the PWA, World Bank and OQ to develop a short, prioritised “Gaza and West Bank water recovery pack” that consolidates key technical products (maps, priority projects, costings, and sequencing options) into a single set of advocacy materials. Drawing on lessons from the water output, this would support more coordinated engagement with the Government of Israel and donors and help unlock clearances for a small number of high‑feasibility interventions.

Output Title	Improved effectiveness, connectivity, and production of electricity
Output number per LF		2	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	yes

Indicator(s)	Milestone(s) for this review	Progress
2.1 Improving Infrastructure / World Bank Advancing Sustainability in Performance, Infrastructure and Reliability of the Energy Sector (ASPIRE) / 1. Capacity of Palestinian electricity network measured by: / a) Status rate (%) of Approvals/ Procurement for Increased capacity of Sarra and Tarqumiya substations (ASPIRE 1) / b) Length of upgraded/constructed Medium Voltage (MV) lines (Kilometres) (ASPIRE 1). / c)Status rate (%) of procurement for building new MV line of 8.7 km from connection point at Durra ending in Yatta. (ASPIRE 3) / 2. Number of smart meters delivered to 5 West Bank Distribution companies (ASPIRE 1) / 3. Status rate (%) of procurement of rehabilitation of grid connection points. (ASPIRE 3)	1. / a)100% of approvals/ procurement completed by Dec. 2025 to initiate expansion of the substations. / b) 69.4 km by Dec. 2025 / c)100% of procurement process completed. Contract to be signed by Dec. 2025. / 2. 35,000 smart meters delivered to 5 Distribution Companies by Dec. 2025 / 3. 100% of procurement process completed. Contract to be signed by Dec. 2025.	1) / Met Expectations: 100% approvals received from Israeli Transmission System Operator (NOGA). / Moderately did not meet Expectations: 87%. 60.4 km has been upgraded/constructed so far. Project is on track. Targeted completion by end of February 2026. / Moderately did not meet Expectations. 100% of procurement has been completed by 24 December 2025. The contract had not been signed in Dec. 2025 but should be signed in January 2026 / 2) Met Expectations. 35,000 smart meters delivered and currently under installation / 3) Moderately did not meet Expectations: 60%. Procurement is under processing, Bids under evaluation phase, contract signing expected in March 2026.
2.2 Renewable Energy Development and Access World Bank / a) Number of solar systems installed for health sector in West Bank. (ASPIRE 1). / b) Number of mobile photovoltaic PV kits supplied to support energy security for household and key sectors. (ASPIRE 1) / c) Progress on Liquidity Support and Account Payment System (LSAPS) (ASPIRE 1) / Tasdeer / d) Deployment of on-grid and off-grid solar (PV) networks measured in MegaWatts	6 by Dec. 2025 / 500 by Dec. 2025 / Bid-submission closing by Dec. 2025. (Request for Proposal was launched on September 15, 2025) / Tasdeer / 0.72-Megawatt peak (MWp) by Dec. 2025	Met Expectations. 6 solar systems installed. Milestone completed. / Met Expectations: 500 mobile PV kits supplied; milestone completed. / Substantially did not meet Expectations: bid submission extended to January 2026. Activity remained in procurement beyond the milestone date / Met Expectations. 0.768 MWp installed.
2.3 Technical Assistance & Capacity Building / a) Number of feasibility studies for priority infrastructure projects. It is a technical and financial feasibility assessment and cost estimate for PV system for 6 health facilities. (ASPIRE 1). / b) Status rate (%) of procurement for supply, installation, and configuration of Supervisory Control & Data Acquisition (SCADA) system (ASPIRE 3). / OQ / c)# of technical products agreed for adoption to help restore power supplies and support / # of technical products to increase electricity supply in Gaza and the West Bank adopted by PA / e) # of technical products to advance utility-scale solar PV development in Area C and West Bank adopted by relevant actors / Qualitative Indicator: / f) Qualitative evidence of knowledge transfer and capacity building resulting from technical assistance provided by the World Bank (ASPIRE) and OQ - including case studies or change stories.	a) 2 by Dec. 2025. / b) 100% of procurement process completed. Contract to be signed by Dec. 2025. / OQ / c) 2 products / d) 2 products / e) 7 products / Qualitative Indicator: / f) One case study or success story will be developed to capture and assess the extent of knowledge transfer and capacity building resulting from the technical assistance provided by partners.	Substantially Exceeded Expectations. 5 studies produced. On medium voltage lines, SCADA system, Voltage line project, MV lines, and PV systems for health sector. / Substantially did not meet Expectations: 50%. Technical specs are under review, since the design was delayed by the contract Procurement expected to be completed by May 2026. / Met Expectations, 2 products. Energy non-paper shared with the Palestinian Energy & Natural Resources Authority (PENRA) and accompanying map and analysis / Moderately did not meet Expectations: 1 product. Terms of Reference (ToR) have been developed to assess regional electricity pricing.​ This has been shared with the International Community members and PENRA for review in early October 2025. ​A second product is currently in internal review stages, identifying key policy levers for reducing electricity prices / Moderately did not meet Expectations 5 products: Ongoing Utility Power Based (PB) site identification study and technical analysis. Products completed: / ToR for Site Identification Study, / Preliminary sites list identified for study / Consultant Work Package Shared with PENRA, / Inception Report for Site Identification / Scoring Framework. / Yet to be completed: / Final Output Format, / Final Report and Site Scoring, final Grid Interconnections (GIS) Dashboard. / Met Expectations. 3 change stories. Under the World Bank – 1) Laying the Foundations of a National Supervisory Control & Data System (SCADA) 2) Solar Photovoltaic Systems for Public Health Facilities in the West Bank 3) Resumption of Basic Services for Gaza

Briefly describe the output and provide supporting narrative for the score

The score for this output is on average is an A as it met expectations. Most milestones for improving electricity infrastructure, connectivity, and renewable energy were either achieved or remain on track. Approvals from NOGA were fully secured, construction of medium voltage lines continued steadily with completion expected early 2026, and major procurement packages were finalised with contract signing scheduled in the coming months. Smart meter deployment advanced as planned, and renewable energy targets were largely met through installation of solar systems and supply of mobile PV kits.

While there was solid progress in several areas, delivery faced notable delays across key infrastructure components. Medium‑voltage line upgrades fell behind schedule, key procurement packages—such as the SCADA system and grid‑connection point rehabilitation—progressed more slowly than planned, and some contract‑signing milestones slipped into early 2026 due to extended technical reviews, access constraints, and dependencies on Israeli approvals. These challenges resulted in five milestones scoring B and two scoring C, reflecting substantive delivery constraints rather than minor delays. Despite these issues, momentum was maintained in areas less affected by external bottlenecks, including smart‑meter deployment, solar installations, and several technical studies, which together contributed to the overall A score.

In Gaza, where physical implementation remains constrained, the programme drove change through strategic coordination under the Resumption of Basic Services initiative. ASPIRE and the Office of the Quartet provided technical assistance and produced aligned plans, maps, and non-papers that guided engagement with the Government of Israel. Adoption was demonstrated through the Palestinian Authority’s use of these outputs in high-level diplomatic meetings and formal letters to Israel. This effort led to partial resumption of electricity, including the Kissufim feeder powering a desalination facility, which is vital for water security. The change strengthened institutional leadership and international alignment, ensuring credible recovery planning despite operational constraints.

Tasdeer’s deployment of on grid and off grid solar PV systems to firms provided a significant boost to energy resilience and cost reduction. These installations helped firms reduce their dependence on an unreliable electricity grid, lower operating costs, and maintain business continuity during power disruptions. Companies were able to quickly adopt the technology, integrating solar systems into their operations and benefiting from tangible savings, and improved resilience. The shift to solar also reduced reliance on fossil fuels and supported adherence to environmental standards. Tasdeer’s Mid-term Evaluation highlighted that these interventions demonstrated strong value for money, especially in a context of economic volatility and energy insecurity.

Taken together, these examples show that while infrastructure delivery and procurement targets were delayed, the programme achieved significant progress in renewable energy deployment, institutional capacity building, and strategic planning. The A score reflects this on average good achievement against planned indicators but strong evidence of transformative change and foundational work that will enable future improvements in electricity connectivity and production.

Describe any changes to this output during the past year, and any planned changes as a result of this review

During the past year, the output expanded through the approval of ASPIRE 3, which builds on the achievements and lessons from ASPIRE phase 1 and finances the upgrade and rehabilitation of a further 50 connection points. At the same time, outputs under ASPIRE phase 1 continue to be monitored due to the project extension. Under ASPIRE 3, additional output indicators and milestones were incorporated to strengthen result tracking.

As a result of this review, FCDO will further strengthen monitoring and reporting arrangements by improving oversight of indicators, milestones, and progress reporting across both ASPIRE 1 and 3, without changes to the scope or objectives of the output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from 2024 AR	Progress
FCDO to continue working closely with World Bank and OQ and other donors to review the energy programme to address the new needs arising from the war.	FCDO had multiple meetings with the World Bank and OQ, alongside other donors regarding recovery and reconstruction under the energy sector. Multiple projects are in pipelines.

Lessons Learnt

- Geographic flexibility in fund allocation is essential for planning with the changing political situation. By having the flexibility of not committing funds to the West Bank or Gaza the World Bank has been able to quickly pivot activities as the political situation allows.
- Producing simplified products alongside technical plans supported early engagement with the PA and allowed easier communication of technical advice.
- The fallout from the war has led to significantly reduced engagement from the Government of Israel on technical matters, limiting the ability of multiple stakeholders—including development partners and implementing agencies—to advance planned energy interventions. This is likely to continue affecting timelines for GoI dependent infrastructure projects and may require resequencing or prioritising Palestinian controlled components.
Recommendations

- By the end of Q2 2026, FCDO and partners should review and update all logframe dates and results to reflect any changes in plans or political context, ensuring updates are completed at least two months before the annual review.
- For the next annual review report (2026), FCDO along with implementing partners should assess the impact of reduced GoI engagement on programme implementation and adjust forward plans accordingly—by prioritising interventions that do not require Israeli technical approvals and progressing preparatory analytical and design work for larger projects until conditions allow implementation.
- FCDO and the World Bank should introduce targeted actions to address the areas that fell behind this year—particularly delays in medium‑voltage line upgrades, SCADA procurement, and grid‑connection point rehabilitation. This should include clearer internal deadlines for design completion, tighter follow‑up on procurement steps, and earlier escalation when bottlenecks emerge.
Output Title	Improved movement of cargo and capacity of trade related institutions and private sector firms to increase exports
Output number per LF		3	Output Score	A
Impact weighting (%):		60%	Impact weighting % revised since last AR?	YES

Indicator(s)	Milestone(s) for this review	Progress
3.1 Business Support for Market Growth / # of firms/ clusters supported to increase in exports, local sales and competitiveness	37 firms/ clusters supported to increase in exports, local sales and competitiveness by Dec. 2025.	Substantially exceeded expectation: 52 firms/clusters received support aimed at increasing exports.
3.2 Women's Skills Development and Empowerment	16 girls/ women trained to enhance their business and/ or technical skills by Dec. 2025.	Met expectations: 20 girls/women have been trained
3.3 Inclusive Business Financing and Loan Sustainability	a) 226 interest free loans provided to establish/expand business by Dec. 2025. / b) less than 10% rate of default loans	a) Substantially Exceeded Expectation, 478 loans have been provided / b) Met Expectation, default rate is 0%
3.4 (Capacity Building) / Tasdeer: / # of solutions (policy, process, system, service, guidance, plan, strategy) provided to improve trade delivered within trade-related institutions and ministries. / # of solutions provided to improve PA customs capacity. / # of solutions adopted within trade-related institutions and ministries to reduce key barriers to trade / OQ / Number of new company profiles developed to support the expansion of the D2D programme. / Number of proposals on financial and fiscal stability shared with relevant stakeholders. / Completion of a business model to guide the operational setup of the staging facility in support of PFI. / Qualitative Indicator / Qualitative evidence of knowledge transfer and capacity building resulting from technical assistance provided by Tasdeer and OQ - including case studies or change stories.	Tasdeer / By Dec. 2025, Improve PA Capacity through: / 9 solutions / 1 solution / 7 solutions / OQ / 3 / 4 / finalized and ready for use in stakeholder engagement, operational planning, and funding proposal development. / Qualitative Indicator: / One case study or success story will be developed to capture and assess the extent of knowledge transfer and capacity building resulting from the technical assistance provided by partners.	Met Expectation: 10 solutions have been provided / Met Expectation: 2 solutions have been provided / Moderately Exceeded Expectation: 11 solutions have been adopted with an additional solution expected to be adopted by the end of 2025 / OQ / Substantially did not meet Expectation. 0 companies. The political and security situation prevailing in the West Bank prevented the expansion of Door to Door (D2D). / Met Expectation. 4 produced. Fiscal file notes updated and circulated with the international community, strategic meetings with the PA and supported PA engagement with GoI. / Did not meet expectation. A draft Business model was shared with Ministry of Communications & Digital Economy (MoCA) and Israeli Civil Administration (ICA); however, MoCA have not engaged in further discussions, and no approvals have been granted. Focus has been on ensuring Palestinian Government ownership over meeting target timelines. / Met Expectation. 2 change stories. Under Tasdeer – Baader (The Palestinian Labour Support Programme), under the OQ – Increased Trade with Israel (Secured Joint Staging Facility and Door to Door Model)

Briefly describe the output’s activities and provide supporting narrative for the score

This output scored A as most indicators were met or moderately exceeded alongside some indicators not meeting the milestone. Tasdeer interventions provided targeted support that helped firms navigate an increasingly difficult economic environment, contributing to improved export readiness, reduced business constraints, and stronger trade‑enabling institutions. In 2025, 16 firms reported increased exports, with 52 firms enrolled for tailored support. Initiatives such as the Export–Domestic Window enabled companies across agrifood, cosmetics, ICT, and manufacturing to overcome bottlenecks and access new markets. One example is a cosmetics company that implemented a digital marketing campaign and accessed the U.S. market, increasing sales. Similarly, through the “Buy from Palestine” programme, Tasdeer supported PalTrade in developing a bilingual export catalogue and establishing a representative office in Saudi Arabia, creating direct channels for Palestinian products to reach Gulf markets and enabling SMEs to promote their goods internationally.

At the institutional level, Tasdeer strengthened trade-enabling bodies and provided technical advice to the Palestinian Authority. For instance, Tasdeer upgraded the Palestinian Standards Institute (PSI) by modernizing its management information system and supporting international recognition. A follow-up survey of 17 companies using PSI Quality and Halal certification showed that 59% increased exports to markets such as Germany, Saudi Arabia, Jordan, and Malaysia. Tasdeer also provided technical and legal support to the Ministry of Finance to modernize customs law and align it with international standards.

Gender inclusion was embedded across interventions, combining targeted skills‑building with broader efforts to mainstream women’s participation in trade and competitiveness initiatives. In the stone and marble sector—an industry traditionally dominated by men—Tasdeer supported an Occupational Health and Safety (OHS) supervisor training that engaged 13 companies and certified 14 supervisors, including six women who successfully completed vocational training. The training covered practical modules such as workplace safety assessments, risk identification, and correct use of protective equipment, and helped participating firms identify gaps to inform future regulatory reforms on hazardous classification. These efforts, though modest in scale, represent meaningful steps toward expanding women’s roles in non‑traditional sectors while improving safety practices and compliance across the industry.

Finally, Tasdeer worked with Ministries and trade-related institutions to adopt 13 policy, process, and system solutions—far exceeding annual targets. These included digitizing Certificates of Origin, introducing the National Industrial Policy Framework, and upgrading customs systems through ASYCUDA World (Automated System for Customs Data), a globally recognized platform developed by UNCTAD to modernize and streamline customs operations. Collectively, these reforms reduced barriers to trade, improved operational efficiency, and positioned Palestinian institutions for greater resilience and competitiveness under volatile conditions.

During 2025, SEED support delivered through Tasdeer and OQ strengthened Palestinian institutional capacity, drawing on embedded technical advisers placed in key bodies—including the Prime Minister’s Office, the Ministry of National Economy, the Ministry of Industry, and the Palestine Monetary Authority (PMA). These advisers, several of whom have been in post since 2023–24, provided legal, economic, and digital‑systems support that continued to be actively used by counterparts throughout 2025.

Tasdeer’s Baader Programme—designed in late 2023 and operational from 2024—was further scaled during 2025. Implemented with the PMA and nine banks and MFIs, it introduced Palestine’s first interest‑free loan scheme for workers displaced from Israel after October 2023. The PMA formally adopted the scheme and oversaw delivery, supported by Tasdeer’s embedded adviser. In 2025, 478 loans were disbursed (including 23 to women), supporting both start‑ups and business expansions and helping stabilise household income under crisis conditions.In parallel, OQ worked with the Ministry of National Economy (MoNE) and trade institutions to design and transfer practical policy tools, including a business model for a Secured Joint Staging Facility (SJSF) to expand access to the Door-to-Door (D2D) trade mechanism. D2D enables Palestinian firms to deliver goods directly to Israeli markets without costly back-to-back transfers. Despite political and security disruptions, MoNE integrated D2D into its policy framework and resumed operations within weeks, enabling Palestinian firms to continue direct deliveries to Israeli markets without costly back-to-back transfers. This rapid restoration of shipments and formal inclusion of D2D in MoNE’s trade policy provided clear evidence of institutional adoption and practical continuity under crisis conditions.

These changes were assessed through quantitative milestones and qualitative evidence, including stakeholder engagement and documented business models. Together, these interventions demonstrate how partner support focused on building durable Palestinian institutional capability—rather than parallel delivery—resulting in adopted systems, strengthened governance, and sustainable foundations for future impact.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from 2024 AR	Progress
Tasdeer to continue to scale up of tested pilots, and continue to pilot innovative approaches to engaging with the private sector for the extension.	Tasdeer scaled up proven pilots like the Solar Grant Window and Baader programme while launching innovative approaches such as the Jerusalem Grant Facility, Export Challenge Fund, and Geographical Indications registration, ensuring a balanced strategy of expanding impact and introducing new private sector engagement models.
For a ceasefire and the next phase in Gaza, FCDO to ensure Tasdeer maintains technical and operational readiness to rapidly roll-out activities in Gaza. These include early recovery support to Gazan SMEs and farmers, and replacement of critical parts and infrastructure to SMEs to resume operation.	Tasdeer maintained readiness and launched early recovery efforts in Gaza by starting the “Cultivating Recovery” project with PARC, focused on rehabilitating greenhouses and open fields for small farmers to restore food production and livelihoods.
FCDO to further review the Tasdeer’s indicators 1.6 and 1.7 to be included in the overall SEED’s logframe.	These indicators have been included in the updated logframe. (# of free interest loans and clean energy)
FCDO to discuss ways of measuring how OQ reports are being used/applied.	FCDO included a qualitative indicator and requested a change story to be provided. OQ produced studies and provided change stories.

Lessons learned
- Adaptive programming requires predefined contingency plans to enable timely scaling of interventions in response to changing contexts.
- Delivery in 2025 showed that while Tasdeer is capable of strong results, several interventions were slowed by programme‑level factors within our control—especially procurement bottlenecks, underestimated timelines for multi‑stakeholder coordination, early institutional resistance to new systems (e.g., PSI’s MIS upgrade and PPO’s e‑commerce readiness), and reliance on individual focal points (e.g., PalTrade). More design needed for some pilot projects. These experiences highlight the need for earlier preparation, stronger sequencing, and more structured engagement to ensure smoother delivery and maximise impact in the programme’s remaining two years.
Recommendations
- By the end of Q2 2026, FCDO and Tasdeer should establish a formal contingency plan with predefined criteria for scaling programme components up or down in response to changes in the economic and political context. This plan should include quarterly reviews of contextual risks and readiness indicators to trigger timely adjustments.
- By the end of Q1 2026, Tasdeer should develop and finalize a rapid-response implementation plan for post-ceasefire recovery, including pre-approved interventions, partner agreements, and resource allocations. This plan should identify priority sectors and institutions; outline fast-track procurement and delivery mechanisms and establish activation triggers so implementation can begin when the situation allows on the ground.
- FCDO and Tasdeer should focus on addressing the delivery challenges identified this year—procurement delays, weak early stakeholder uptake, and over‑reliance on individual focal points—by introducing early vendor engagement, structured consensus plans for multi‑actor reforms, and institutional capacity-building for key partners. This will improve delivery efficiency and ensure Tasdeer maximises results in its final two years.
- To strengthen performance over the next two years, FCDO and Tasdeer should introduce targeted delivery improvements that address this year’s bottlenecks. This includes earlier vendor engagement and clearer internal timelines to reduce procurement delays; formal consensus‑building plans for multi‑stakeholder reforms; upfront institutional readiness assessments for partners such as PSI, the Post Office, and PalTrade; and shifting from reliance on individual focal points to broader institutional ownership. At the same time, Tasdeer should focus resources on high‑impact, scalable interventions—such as Baader, solar energy systems, export‑domestic support, PSI accreditation, and PARC’s agricultural recovery model—to ensure the programme maximises impact within the remaining delivery window.
## D: VALUE FOR MONEY (1 page)
Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

The programme continues to demonstrate value for money, though performance is mixed at the project and output level, as well as the outcome level (although there are some constructive elements). This reflects the challenging context in which SEED operates. While SEED was designed to achieve systemic, scalable, and durable improvements across water, energy and trade, the extent to which systemic change has been achievable in 2025–26 has been significantly shaped by the political deterioration, movement restrictions, and operational constraints affecting both Gaza and the West Bank.

Several interventions continue to show strong potential for long‑term, system‑level returns. These include improvements in energy resilience, where renewable energy installations and smart metering are helping reduce energy losses and strengthen grid reliability; digital customs and trade reforms, which are modernising core systems and reducing clearance times; and institutional strengthening, including accreditation and regulatory upgrades in key Palestinian institutions such as PSI, PENRA, and MoNE. These interventions provide benefits that extend well beyond individual beneficiaries, supporting more efficient service delivery, strengthening public‑sector capability, and improving the enabling environment for the private sector.

However, other parts of the portfolio have delivered outcomes that are predominantly output‑level rather than systemic, due primarily to external constraints – for example, producing practical plans and identifying a small number of realistic activities that could still be taken forward despite political and institutional constraints. This has informed a more selective approach in the final programme years, prioritising deliverable activities where continued UK ODA can still demonstrate clear relevance and value for money.

In Gaza, sustained access restrictions have prevented infrastructure and institutional components from progressing to the stage where structural gains could materialise. In the West Bank, reforms that depend on coordination between Israeli and Palestinian authorities have slowed significantly, affecting progress in water sector development, utility governance, movement and trade facilitation, and large‑scale energy infrastructure. This divergence is also reflected in output scoring: while many milestones were met or exceeded, this does not consistently translate into the deeper system changes originally envisaged in the Business Case.

Within this context, value for money in 2025–26 has therefore been driven by SEED’s ability to:
• Pivot to resilience and preparedness, particularly in Gaza, where partners prioritised technical readiness, analytical work, and emergency support rather than undertaking activities unlikely to deliver results under current access constraints.
• Maintain the functionality of key institutions—including PENRA, PSI, MoNE, and the PMA—through technical assistance, analytical products, digital systems, and capacity‑building that preserve essential functions despite a constrained operating environment.
• Accelerate reforms that remain feasible, such as improvements in trade systems, energy access in the West Bank, and targeted institutional strengthening.
• Avoid expenditure on low‑impact activities, with partners pausing or re‑sequencing interventions that could not deliver credible returns under current political and security conditions.

Looking ahead, SEED’s VfM approach will continue to emphasise realistic pathways to systemic impact, grounded in the political and economic realities of the operating environment. Programme management will prioritise strengthening outcome‑linked monitoring, deepening the institutional resilience components that have demonstrated clear value, and ensuring that activities funded in the remaining programme period are those most capable of delivering durable benefits once conditions allow greater progress. As the political context changes further, uncertainty remains on the medium to long-term picture for both Gaza and the West Bank, not least due to the evolving governance structures across both. In a rapidly deteriorating fiscal and security context, this requires a frequent and consistent interrogation of the value for money case for all our programmes.

E: RISK [½ to 1 page]
Overview of risk management [1/2 page]

The principal risk facing SEED is the risk of not achieving the programme’s intended outcomes and impact due to a combination of prolonged access restrictions, political deterioration, and fiscal and economic instability. These factors simultaneously constrain partners’ ability to implement activities as designed, limit the PA’s institutional bandwidth, and weaken private‑sector resilience—collectively undermining the pathways through which SEED is expected to deliver systemic change.

In response, SEED has strengthened its programme‑level risk mitigation approach to focus on adaptive delivery, front‑loaded preparedness, and targeted support to the most feasible areas of influence. Across all components, SEED partners have updated re‑entry plans for Gaza, accelerated preparatory analytical work in the West Bank, and shifted resources towards interventions that remain politically and operationally deliverable. FCDO is also using quarterly assurance meetings to scrutinise progress, re‑sequence activities, and reduce exposure to stalled infrastructure or policy processes.

Key risks and mitigations include:
Risk: Damage and destruction of SEED investments in Gaza – This risk has already been realised, with confirmed damage to Tasdeer supported firms and World Bank–financed assets during the conflict. Even with a ceasefire, the security situation continues to prevent entry into Gaza, limiting partners’ ability to conduct damage assessments. Implementing partners are therefore maintaining remote monitoring and preparing updated re-entry and recovery plans for when conditions permit.
Mitigation: All partners have transitioned to a dual‑track delivery model, combining:
- immediate humanitarian‑adjacent support (e.g., emergency WASH through UNDP/UNICEF reallocation), and
- Readiness work (technical designs, sequencing, costed priority lists) to enable rapid activation once Phase 2 access is possible. Tasdeer and the World Bank maintain live re‑entry operational plans. Readiness work (technical designs, sequencing and costed priority lists) to enable rapid activation once access permits.
  Where implementation is paused, partners mitigate risk by sequencing activities, securely storing procured materials, and maintaining flexibility to repurpose or restart activities subject to access and governance approvals. Tasdeer and the World Bank maintain live re‑entry operational plans.

- Risk: Reduced capacity of partners to deliver interventions due to the ongoing war and deteriorating Israeli–Palestinian relations – This risk is both realised and active. Stakeholders across the system face shifting operational priorities and heightened restrictions, which have already disrupted planned activities. For example, Israel’s tighter restrictions on Palestinian traders at the King Hussein Bridge have directly limited Tasdeer’s efforts to enhance trade via this route, negatively affecting beneficiaries who rely on cross border movement. Bilateral deterioration has also impacted interventions requiring coordination or technical engagement across both sides.
- Mitigation: SEED now prioritises Palestinian controlled or donor negotiated interventions, while OQ provides consolidated advocacy materials (maps, project lis ts, fiscal briefings) for coordinated engagement with GoI.

- Risk: Strain on the Palestinian banking sector due to correspondent banking risks, excess cash and withheld clearance revenues – This is an active risk with potential to escalate. The banking sector is already experiencing liquidity pressures and operational strain, creating significant financial uncertainty. A deeper deterioration—including a potential breakdown in correspondent banking relationships—remains a serious forward-looking risk that could further undermine SEED’s ability to deliver results.
- Mitigation: SEED and the FDCO monitors liquidity and fiscal indicators quarterly and coordinates closely with PMA and the IMF. FCDO continues to advocate for sustaining the correspondent banking relationships and the release of clearance revenues.

- Risk: Continuation of the current political and economic situation leading to prolonged pauses in delivery, particularly for infrastructure projects in Gaza – This remains a major forward-looking risk. While several activities are already delayed or constrained, a sustained inability to progress Gaza based infrastructure could result in extended pauses across large components of the programme if conditions do not improve.
- Mitigation: Delivery partners are scaling back discretionary or long‑horizon reforms and focusing on critical functions (e.g., PSI accreditation, PENRA renewable energy planning, Ministry of Finance customs reform). Embedded advisers are being re‑tasked to short, high‑value outputs rather than wide portfolios.

Update on Partnership Principles (delete this section if n/a) [1/2 page]

This programme provides technical assistance to Palestinian Authority (PA) institutions through third-party delivery partners, rather than direct financial or budgetary support to the PA. As such, a full programme-level Partnership Principles (PP) assessment is not required.

Nevertheless, the programme has been designed and implemented with due consideration of the Partnership Principles, including governance, domestic accountability, and human rights. Delivery through experienced external partners ensures that support is targeted, results-focused, and aligned with UK objectives, while maintaining appropriate distance from direct financial transfers.

The programme supports PA reform priorities through technical assistance, capacity strengthening, and analytical inputs, in line with the UK–PA Memorandum of Understanding (2025), which emphasises the importance of a capable, transparent, and accountable Palestinian Authority. Results are delivered, monitored, and reported by contracted partners, with FCDO oversight ensuring compliance with programme safeguards and value for money.

This approach mitigates fiduciary and governance risks associated with direct engagement, while enabling continued support to institutional reform, improved service delivery, and strengthened governance systems. It also ensures alignment with broader UK commitments to support PA reform, accountability, and sustainable development outcomes within the framework of the bilateral partnership.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

During the reporting period, SEED has continued to be managed as a coherent programme, even though each delivery partner operates through its own independent delivery mechanism. The partners do not implement activities jointly, and collaboration between them varies depending on the sector and the operational realities of their mandates. Rather than relying on integrated delivery, coherence across the programme is achieved through FCDO’s oversight, which ensures that the separate workstreams remain aligned with SEED’s strategic objectives and complement one another.

FCDO maintains programme‑level coherence through regular assurance processes, structured monitoring of partner outputs and risks, and alignment of delivery plans. This management approach enables the programme to identify overlaps or gaps across components, adjust sequencing where needed, and ensure that work delivered by individual partners contributes to broader objectives in water, energy, and trade. This includes strengthening the clarity of outcome pathways, avoiding duplication, and ensuring that support across different institutions reinforces wider system resilience.

In relation to performance management, a small number of delivery partners continue to provide detailed and structured reporting against their workplans and indicators. Reporting from the third partner has been less consistently analytical, with gaps in how progress links to intended outcomes. In relation to performance management, reporting practices vary across delivery partners. Some partners consistently provide detailed and well‑structured reporting against agreed workplans and indicators, demonstrating clear links between activities, outputs and intended outcomes. Reporting from one partner has been less consistently analytical, particularly in articulating these links; this has been identified and is being addressed through ongoing performance management and support to strengthen a more systematic, outcome‑focused reporting approach.

To strengthen programme‑wide reporting quality, FCDO has clarified expectations for evidence‑based reporting and is applying more consistent monitoring standards across all components. Additional external monitoring and learning support has been commissioned to improve the consistency, outcome‑orientation, and comparability of reporting across the portfolio.

Looking ahead, FCDO will continue to emphasise a programme‑level approach that ensures each partner’s work remains relevant, aligned, and responsive to the rapidly changing context. This includes strengthening cross‑programme monitoring, improving transparency around progress toward outcomes, and maintaining clear strategic direction across independently delivered workstreams to ensure that SEED continues to deliver value and coherence in a challenging operating environment.

From a commercial and financial perspective, the programme has been implemented with appropriate discipline and care. Core costs have continued to focus on technical expertise, advisory support and analytical work, alongside selectively sequenced delivery activity where conditions allow. There is no evidence of unmanaged cost escalation. Where delivery has been constrained, particularly in Gaza due to access, security and material entry limitations, decisions have prioritised careful use of resources, avoiding expenditure on activities unlikely to deliver results under current conditions. This approach has helped protect public funds while preserving the ability to scale delivery once conditions improve. Overall expenditure reflects the programme’s multiparter delivery model, with the majority of funds channelled through multilateral partners and service suppliers and the remainder supporting technical assistance, advisory and coordination functions through the OQ. Financial management has been strong across Tasdeer and OQ, with clear systems, accurate reporting and disciplined cost control. Partners have also provided audited financial statements for the relevant reporting periods, supporting assurance over financial accuracy and compliance. For the World Bank pooled fund, direct monitoring of UK specific expenditure is inherently more complex; however, following FCDO requests, the Bank has improved the granularity of its financial reporting and now provides the most accurate possible UK related financial information, along with procurement timelines that allow us to monitor whether spend is progressing as planned.

Financial management and oversight arrangements across the programme have remained robust. Programme finances are monitored through established reporting processes and regular review meetings, supporting oversight of expenditure, forecasting accuracy and emerging risks. While fiduciary risks remain elevated due to the wider operating context, these risks are being actively managed through supervision, controls and adaptive delivery decisions, rather than reflecting weaknesses in financial management systems. Partners have communicated delays clearly and adjusted delivery plans accordingly. Within this, performance monitoring has also remained strong: Tasdeer continues to assess partner institutions against capacity building, digital transformation, standards compliance, GESI integration, Public Sector Equality Duty (PSED) considerations and safeguarding practices, and the World Bank provides structured results reporting against KPI frameworks. This combined approach provides assurance that programme delivery is being monitored effectively across institutions and implementation channels.

Asset management has remained proportionate to risk. In higher risk environments, physical delivery and asset exposure have been deliberately limited to avoid damage, loss or misuse. In areas where delivery conditions are more stable, activities and assets continue to be managed responsibly within agreed frameworks, with clear accountability and oversight. Tasdeer maintains an updated asset list, and annual asset spot checks have been conducted, with partners transparently reporting any damaged or missing items. This risk-based approach has supported both financial integrity and operational safety.

Engagement between FCDO and delivery partners has been active and collaborative throughout the year. Regular meetings and ongoing informal dialogue have supported problem solving, coordination and alignment across sectors and delivery channels. Several field visits were conducted during 2025 to verify delivery and engage with partners directly; however, access was not always feasible due to security risks and restrictions on movement, particularly in Gaza and some West Bank locations. Despite these constraints, partners have maintained strong communication, and FCDO has remained engaged through virtual, remote and alternative monitoring mechanisms. This close engagement has enabled the programme to respond flexibly to changing conditions while maintaining strategic focus. Looking ahead, FCDO’s effectiveness as a partner can be further strengthened through continued coordination across the wider portfolio, sustained efforts to address delivery constraints, and early communication on future priorities to support planning where opportunities for scaleup emerge.

Overall, there is sufficient evidence that delivery partners and FCDO are performing their roles effectively at programme level. Performance is being measured through clear institutional criteria and structured KPIs, including evaluation of GESI, PSED, safeguarding, digital systems, sector coordination and financial sustainability. Commercial, financial and delivery risks are well understood and actively managed, and the programme continues to be implemented in a manner consistent with good practice, transparency and responsible stewardship of public resources.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

SEED’s three components continue to operate through well-established monitoring, evaluation and learning (MEL) systems managed by each delivery partner. To strengthen monitoring for the remainder of the programme, work is underway to update and refine the monitoring of SEED so that it remains fully responsive to evolving delivery conditions and information needs. These risks are mitigated by the use of experienced and trusted partners with strong fiduciary, monitoring and reporting arrangements.
All delivery partners maintain clear output and outcome indicators aligned to their respective logical frameworks, which together feed into the overarching SEED results framework. Partners report regularly on progress against agreed workplans and indicators: at least quarterly in the case of OQ and Tasdeer, and semi-annually through formal reporting for the World Bank, complemented by ongoing portfolio level monitoring.

The operating environment, particularly in Gaza, continues to severely constrain the ability of implementing partners to undertake needs assessments or conduct in person monitoring. In response, partners have adapted their MEL approaches, drawing on remote engagement, analytical work, technical reporting and third party or partner generated data where appropriate. For example, World Bank supported analytical and advisory services continue to generate evidence to inform recovery planning, while OQ and Tasdeer have maintained regular logframe reporting and technical updates reflecting progress, constraints and emerging risks.

During the reporting period, a midterm evaluation was conducted for one of SEED’s delivery partners – Tasdeer – finding that the programme is delivering effectively despite a challenging context. The evaluation found that Tasdeer interventions have successfully strengthened trade readiness, institutional capacity and fiscal systems, even though visible economic impact remains constrained by external factors such as movement restrictions and conflict. It also highlighted adaptive management as a core strength, noting that the ability to pivot interventions—such as shifting Gaza activities from competitiveness to resilience—was a best practice that should be institutionalised through structured learning loops and adaptation logs. Finally, the evaluation confirmed that system level investments, including institutional capacity building and energy resilience measures, have delivered high value for money and created durable benefits, outperforming fragmented firm level support. These findings reinforce the programme’s strategic approach and provide lessons for future design, including deepening digitalisation and resilience interventions.

Strong beneficiary accountability and inclusion remain core principles across SEED. Partners are required to disaggregate monitoring data where possible, including by gender and disability, and to apply appropriate feedback and grievance mechanisms. World Bank–supported investments include citizen engagement and grievance redress systems, while Tasdeer and OQ have continued to gather feedback from businesses, institutions and stakeholders through surveys, change stories, consultations and short illustrative videos shared through their reporting. In addition, SEED staff participated in several partner led events and sector meetings during the year, which provided opportunities to hear directly from beneficiaries, private sector actors and institutional counterparts. These combined mechanisms—ranging from structured feedback tools to participatory engagements—help ensure that UK support remains closely aligned with real world needs and experiences.

Learning and adaptive management are increasingly important given the volatile context. Evidence and lessons generated through monitoring activities, feasibility studies, policy analysis and partner learning processes have informed adjustments to programme design, workplans and delivery approaches. This includes revisions to logframes, reprioritisation of activities and preparatory work to support potential recovery and reconstruction efforts when conditions allow.

To complement partner led monitoring during the reporting period, the SEED programme team:
- Maintained regular quarterly programme assurance meetings with all partners to review progress, compliance with FCDO Programme Operating Framework requirements and emerging risks.
- Monitored partners’ delivery against agreed logical framework milestones and outputs.
- Conducted high level monitoring engagements where feasible, including gathering feedback from beneficiaries and stakeholders on programme relevance and delivery.

Looking ahead, SEED will benefit from the British Consulate General Jerusalem’s newly launched Palestine Monitoring, Evidence and Learning programme (PaLMEL). PaLMEL aims to deliver robust Monitoring, Evaluation, Research and Learning (MERL) services in Palestine, supporting the BCGJ Country Plan. The programme is designed to assure results, inform strategic decisions, and improve accountability and value for money across BCGJ’s humanitarian, diplomatic and development activities. PaLMEL will provide independent third-party monitoring and learning support to SEED, strengthening evidence generation and adaptive management in a challenging and rapidly changing environment.

Partner	Date of last narrative Financial Report	Date of last audited annual statement
World Bank	For year 2024/2025, uploaded on their website September 2025	For year 2024/2025, uploaded on their website September 2025
UNOPS/OQ	For Financial year ending March 2024 & 2025, received 17 November 2025	For Financial year ending March 2024 & 2025, received 17 November 2025
Tasdeer	For year 2024, received 17 November 2025	For year 2024, received 17 November 2025