BUSINESS CASE ADDENDUM

PROGRAMME TITLE
Directorate/ Post	Research & Evidence	Contact name	Laura Munro
Original programme budget	£110,000,000	Country or region targeted	Non-specific region/country
Cost extension value (if applicable)	£76,000,000	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	Minister for Development
New increased or reduced programme budget (if applicable)	£186,000,000	Original programme start and end dates	09/08/23 – 01/10/26
Latest AR programme score	A (2025)	New programme end date (if applicable)	31/03/2030
		Programme ID	300671

Detailed information
Programme summary	The world is falling behind on its targets for climate, nature, and human well-being — the CGIAR’s unmatched track-record of global impact through agricultural science and innovation is a critical lever to accelerate progress towards the global goals. / This programme includes four strategic investments in the CGIAR to advance UK development priorities: / The CGIAR multilateral R&D portfolio. Co-funded with key allies and emerging science powers, this portfolio develops R&D solutions in partnership with national and local actors to tackle climate, nature, food insecurity, gender inequality and poverty. / International science partnerships that strengthen UK leadership and influence, support locally-led innovation and accelerate the translation of world-leading UK science to drive impact at scale. / A flexible central offer that leverages CGIAR’s science for policy influencing and programme development. This will evolve through the sustainable food offer under the Climate Resilience and Nature CoE. / Targeted bilateral investment to deepen the evidence base and technological solutions on emerging priorities such as FCAS resilience, migration and AI. / Results from the current phase have been exceptional. For instance, the CGIAR developed 471 innovations and worked with national partners to register 788 crop varieties, reaching 20 million farmers (2022-2024). CGIAR research also informed 315 policy changes and US$3.3 billion of third-party investment. / The programme has exemplified a strategic model for advancing the UK’s development priorities in a 0.3 world. The CGIAR’s multilateral portfolio has provided a crucial pathway to develop demand-driven solutions to global challenges in partnership with other funders and developing countries. The UK has played a critical leadership role in setting the strategic direction for the CGIAR in line with UK objectives, ensuring a high return on investment and value for money approach that leverages funding from others.
Changes	This addendum proposes a four-year costed extension to continue and evolve the four strategic investment areas set out above. In line with the UK’s modern development approach, the programme will: / Exercise UK leadership and influence to amplify the impact of the multilateral portfolio and system. This will include closer working with Posts and central teams to maximise coherence and influence for the UK. / Deepen links with advanced UK science capability through the UK-CGIAR centre on emerging priorities (e.g., AI and gene-editing) / Provide a streamlined, demand-led and accessible access to CGIAR science within the new CoE structure. CGIAR innovations and evidence will support policy influencing and programme development for Posts and Policy teams. This will include strengthened visibility of country-specific results from the multilateral portfolio and access to tailored innovations that are climate resilient, nature positive, low emissions and ready to scale for Category 1-3 countries. This offer has strong support from Posts and Policy teams. / Target bilateral investment to develop R&D solutions to emerging priorities, including resilience in FCAS contexts and addressing drivers of migration. The programme will flexibly manage the balance of multilateral/bilateral spend to maximise value for money and to respond to emerging issues. / If the programme was not extended, this would undermine years of R&D investment and jeopardise CGIAR’s ability to deliver results as it adapts to a low-ODA world. Exiting the multilateral fund would also have reputational risks given the UK’s historic role. UK funds could be invested in bilateral breeding projects; however, this is not the preferred option given the CGIAR’s results record, opportunity to leverage investment, and alignment with the UK’s modern development approach.
Implementation	The CGIAR partnership is managed via a Contribution Arrangement signed in 2017. The addendum will not require any amendments to this arrangement. / The existing programme management arrangements will continue, with a lead advisor/PRO working with a number of other advisors on thematic areas, and a programme manager. Up to two programme-funded posts will continue to maximise influence in the CG multilateral system and FCDO access to CG expertise.
Budget	Pre/post amendment finance profile: / Original budget: £110,000,000 / Total amount spent: £80,501,303 (Oct 25) / Amount of cost extension: £76,000,000 / Revised total: £186,000,000 / This programme is a flagship offer under RED’s climate/nature theme. All costs are CDEL and fall within the current SR period. / The proposed extension value has been set with due consideration of the wider portfolio FY2025/26 – 2029/30, recognising budget pressures and what would constitute a minimum viable investment. The programme has flexibility to refine bilateral spending levels in line with RED’s Business Plan. / The programme extension is not novel or contentious; there are no substantial changes that would necessitate HMT approval.
Impact	Impact of cost/time extensions on VfM (check relevant box): / ☒ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. Vfm is expected to increase as the annual budget will decline but results will be strengthened through the prioritised portfolio, deeper linkages with UK expertise and improved FCDO coherence.
Risk	We do not anticipate any new risks materialising as a direct result of this addendum. The risk profile over the course of the programme has been stable, and the addendum does not constitute any significant change that would shift this profile.
Results/Monitoring and Evaluation	The multilateral portfolio is prioritising workstreams to maximise vfm and results at both the output and outcome levels. It includes new programmes to accelerate scaling of proven innovations and exploit digital/AI opportunities. / By deepening UK science links, the addendum will generate new opportunities for UK leadership and impact. / The addendum’s expertise offer will equip posts and policy teams with cutting-edge science to strengthen impact across the network. This offer will be monitored on an annual basis and adapted as needed. / The theory of change has been reviewed and the approach taken is still valid based on the evidence for the BC addendum.