## Log Frame
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach |  |  |  | 2026 annual review
|  |  |  | 2025 results (calendar year) | 2026 results | 2027 | 2028 | 2029 | 2030
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
1. Climate Adaptation: Equip 500 million small-scale producers to be more resilient to climate shocks, with climate adaptation solutions available through national innovation systems 2. Environmental health and biodiversity: Stay within planetary and regional environmental boundaries, including consumptive water use in food production and fertiliser use, zero net deforestation, and maintaining the genetic diversity of seeds, cultivated plants and farmed and domesticated animals and their related wild species. 3. Food security and nutrition: End hunger for all and enable affordable healthy diets for the 3 billion people who do not currently have access to safe and nutritious food 4. Poverty reduction: Lift at least 500 million people living in rural areas above the extreme poverty line of US $1.90 per day (2011 PPP). 5. Women and girls: Close the gender gap in rights to economic resources, access to ownership and control over land and natural resources for over 500 million women who work in food, land and water systems. |  | Planned
Achieved
*Impact goals assume wide range of partners and collective effort |  |  | Source
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date) | Assumptions
By 2030, 21.7m farmers and producers adopting CGIAR-improved technologies 64.3m people, households and communities reached or benefiting from CGIAR-improved technologies 345 policies informed with CGIAR research 21 billion USD public and private investment informed, leveraged, or secured through CGIAR science and scaling activities. |  | Planned |  | no milestones | 1.1m farmers and producers adopting CGIAR-improved technologies | [5 empty] | Outcome targets assume W3/ bilateral contributions consistent with the ambition of a coherent, ‘all of CGIAR’ Portfolio
Achieved
Source
PPU
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
|  | Planned |  |  | 185,100 people, households and communities reached or benefiting from CGIAR-improved technologies
Achieved
Source
PPU
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
|  | Planned |  |  | 69 policies informed with CGIAR research
Achieved
Source
PPU
| Outcome Indicator 4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
|  | Planned |  |  | 3 billion USD public and private investment informed, leveraged, or secured through CGIAR science and scaling activities.
Achieved
Source
PPU
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) | Total (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date) | Assumptions
Output 1. Knowledge, evidence, and innovations developed and delivered to support the five impact areas | Number of new or improved crop varieties co-developed with national partners registered for release by national authorities that are more productive, nutritious and/or resistant to biotic and abiotic stress | Planned | 0 | No milestones | 150 | 150 | 150 | 150 | 150 |  | i. CGIAR targets its research efforts on the right problems, designs high quality research programmes and works with the right partners able to scale technology. ii. CGIAR delivers technology, knowledge and evidence that meets the demand of end users and is responsive to national context. iii. National systems have the capacity and resources needed to access and utilize CGIAR innovation and use CGIAR policy evidence. | Agreed to leave as is, as it reflects quantity and quality to meet standards for release (UPOV standards)
Achieved
Source - Results Dashboard
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
| Number of innovations developed, including products, technologies, services and institutional arrangements with high potential to achieve positive impacts at scale. | Planned | 0 | 414 | inc. 4 innovations developed for scaling by SMEs in FCAS
| of which, number of innovations developed for FCAS | Achieved
Source - Results Dashboard
| Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
| Number of innovations tagged with OECD DAC marker for Gender (Significant or Principle) | Planned | 0 | No milestones
Achieved
Source - Results Dashboard
| Output Indicator 1.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
| Number of innovations tagged with OECD DAC marker for Climate (Significant or Principle) | Planned | 0 | No milestones
Achieved
Source - Results Dashboard
| Output Indicator 1.5 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
| Number of peer-reviewed publications (including open access rates) | Planned | 0 | No milestones
Achieved
Source - Results Dashboard
| Output Indicator 1.6 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target 2027
| Gene-editing: CGIAR centres applying new precison breeding technology (conventional crispr cas-9 and prime editing) to address critical contraints to staple crop productivity. 5 new gene-edited crop products developed, tested and validated as transgene-free. 2 crops available for deployment. 1. PVY-resistant potatoes 2. Transgene-free banana wilt-resistant banana 3. Cassava varieties resistant to Cassava Bacterial Blight 4. Rice with improved resource efficiency in under low-input conditions. 5. Wheat more resistant to rust and powdery mildew | Planned | Five projects to gene-edit staple crops initiated in 2023. | Five centres developing new product lines using crispr and prime editing. | 5 products under development: Cassava: Edited plants produced through gene-knockout that display moderate resistance to Xpm strains. Wheat: Generate knockout lines of the wheat genes associated with susceptibility to rust and test under confined trials Potato: 7 constructs generated through prime editing guide RNAs (pegRNA) and progressed for testing. Generate edited calli for on-growing Banana: Generate banana plants that have been edited to disable susceptibility genes Rice: Generate transgene free rice (Asian and African) with significantly improved performance under low N conditions. | 2 new prodcuts approved for deployment and undergoing field trials. |  |  |  | Cassava: Transgene-free gene-edited cassava strains that are resistant to bacterial blight developed and tested in confined trials. Wheat: Development of rust-resistant lines for durable resistance using prime editing. Potato: To develop and validate the prime editing approach to building PVY resistance in potato. Banana: Generation of transgene-free genome-edited BBW resistant banana (bacterial banana wilt) Rice: Editing rice for nitrogen remobilisation to increase nitrogen use efficiency.
|  | Achieved |  | Completed
Source - IRRI GEDI Programme Report
| Output Indicator 1.7 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
| VACS: The development of farmer selected varieties of marginalised opportunity crops by applying modern genomic selection approaches . 1. High performing new varieties meeting farmer demand developed 2. Seeds of new varieties available to farmers 3. Links to markets developed 4. New knowledge generated 5. Genomics and Trait Genetics | Planned | VACS crops programme initiated in 2025 targetting 7 opportuntiy crops | African led breeding teams estbalished for seven crops including a mix of national ( NARS), CGIAR and other ARI partners. Key breeding targets idnetified through participatory slection with national partners. TPPs set for all seven crops | 1.1 New varieties released (number) 2.1 Companies/institutions marketing seed (number) 2.2 Seed commercialized (tons) 3.1 Partnerships with seed and input suppliers established (number) 5.1 Marker or selectable phenotype validated for a priority trait (number) | 1.1 18 New varieties released 2.1 18 Companies/institutions marketing seed 2.2 26.5 Seed commercialized (tons) 3.1 18 Partnerships with seed and input suppliers established (number) 5.1 8 Marker or selectable phenotype validated for a priority trait (number)
|  | Achieved |  | Completed
Source - CIMMYT
| Output Indicator 1.8 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
| Sustained long term improvements in the conservation and management of the International Treaty Article 7 gene banks; protecting agro-biodiversity and making this available globally. | Planned |  |  | TBC
Achieved
Source -
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) | Total (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date) | Assumptions
CGIAR operational effectiveness and efficiency of CGIAR improved through progressive governance reforms and through enhanced management of research and innovation. | Strengthened oversight and funding mechanisms driving prioritisation of research to ensure that the CGIAR resources are focused on major threats and opportunities for R&D | Planned |  | Prioritisation exercise completed, enabling refinement of 2026 activities and deliverables | Prioritisation model is refined, clarifying target population
|  | Achieved |  | Completed
Source - System Council
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
| Improved management of research using results-based management and effective evaluation | Planned |  | Completion of ISDC review, PORB with results for each Package of Deliverables | Centre reviews initiated | Agree timing of MOPAN review
Achieved
Source - SIMEC and PPU
| Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
| Strengthened governance arrangements across CGIAR balancing centre priorities with system-wide risk and programme management framework | Planned | Risk and Oversight Plan implementation | Approval of the Escalation Framework | New board in place, with clarity on roles and responsibilities, clear mechanisms to manage conflicts of interest, improved accountability and communication with SC | Completion of the evaluation of the new governance structure
|  | Achieved |  | Completed
Source - System Council
| Output Indicator 2.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
| Sustained improvement in the capacity of the CGIAR to carry out research responsibly in FCAS and deliver innovations suited for FCAS | Planned | N/A | Completion of the FCAS review | 2026-2030 CGIAR FCAS Action Plan / Roadmap developed and endorsed 50 individuals & external orgs attending capacity sharing FLEX sessions on FCAS review outcomes One FCAS Scaling Model and practical toolbox | TBC from roadmap - % of CG centres or programmes publishing/adopting FCAS strategies based on roadmap principles | Claire | Claire | Claire
|  | Achieved |  | Completed
Source - Food Frontiers and Security
IMPACT WEIGHTING (%) 40
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) | Total (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Output 3. New collaborative R&D partnerships between UK science and CGIAR initiatives targeting priority R&D delivery. | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date) | Assumptions
Output 3. Enhanced partnerships with UK Science and technical support for FCDO posts | 1. The UK CGIAR Centre for Science Collaboration is established with a functioning governance and management model able to identify and fund high quality research collaborations. 2. Number of collaborative grants made to new and existing collaborative research partnerships between UK elite universities, CGIAR centres and developing country partners, aligned with UK science priorities. 3. New funding secured to support the centre’s operations from outside the core CGIAR grant. 4. Number of research publications and other outputs generated through the research partnerships. | Planned | UK-CGIAR Centre launched in 2023. | The UK CGIAR Centre for Science Collaboration is established with a functioning governance and management model able to identify and fund high quality research collaborations. | 7 grants made to new and existing collaborative research partnerships between UK elite universities, CGIAR centres and developing country partners, aligned with UK science priorities. Co-funding secured from UKRI and from the FCDO RED non-ODA budget • 13 research publications generated through the research partnerships • 18 Innovations available to be handed onto next user • 4 Joint applications for additional funding submitted | • 16 research publications generated through the research partnerships • 14 Innovations available to be handed onto next user • 4 Joint applications for additional funding submitted • 2 new grants secured by UK-CGIAR teams. | • 13 research publications generated through the research partnerships (update from CABI) • 8 Innovations available to be handed onto next user • 4 Joint applications for additional funding submitted • N additional funding secured by UK-CGIAR teams. | • 3 research publications generated through the research partnerships (update from CABI) • 9 Innovations available to be handed onto next user • N Joint applications for additional funding submitted • N additional funding secured by UK-CGIAR teams. | • N research publications generated through the research partnerships (update from CABI) • N Innovations handed onto next user • N Joint applications for additional funding submitted • N additional funding secured by UK-CGIAR teams. | The UK CGIAR Centre for Science Collaboration is established with a functioning governance and management model able to identify and fund high quality research collaborations. • 63 research publications generated through the research partnerships (update from CABI) • 63 Innovations available to be handed onto next user • Joint applications for additional funding submitted • N additional funding secured by UK-CGIAR teams. | Posts have capacity and demand for CGIAR evidence and innovation CGIAR evidence is available in an easily accessible form.
|  | Achieved |  | Completed | completed
Source - UK CG Centre
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target (date)
| Number of FCDO-IFPRI technical support products with evidence of (informal) policy uptake (includes IFPRI analytical response and country action plans) | Planned |  | Refine IFPRI drawdown offer, develop action plans to support policy influencing. Plus technical support products: UK Benefits of CGIAR | At least 7 analyses to support FCDO delivery(4 country action plans, BBF, Best Buys, Iran fuel analysis, other rapid response requests), at least one example of policy uptake as a result of these analyses
|  | Achieved |  | Completed
Source - IFPRI / survey of FCDO teams
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) | Total (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Notes:
Nutrition Policy Marker Prof Guide encourages inclusion of nutrition in the logframe - but not a requirement. Opted not to include at this stage, as targets are not set and can still include in the narrative
Results Framework includes a much wider set of indicators
Note on B122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I.e. number and list IFPRI examples of rapid response requests and country action plans with evidence of policy uptake each year. Reply: Country action plans are 2026 calendar year