## Annual Review Template

Title: Developing science and technology solutions to the global food security and climate crisis with CGIAR (2023-25)
Programme Value £ (full life): £110,000,000		Review date: August 2024
Programme Code: 300671	AMP start date: 09/08/24	AMP end date: 01/10/26

Summary of Programme Performance
Year	2024
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	Business case / Business case addendum
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The world is off track for meeting targets on climate, nature, and people. Over 2bn are chronically food insecure; a number that has risen every year since 2015. Over 85% of the African population and 70% of the South Asian population can afford a healthy diet. Gender inequality is also increasing, 32% of women in the world were moderately or severely food insecure, compared to 28% of men. Food systems are the primary driver of biodiversity loss and are the second largest source of climate emissions after energy. Food production uses more than 80% of global fresh water, and it is threatened by a lack of available water in many vulnerable regions. Crop and livestock disease already responsible for losses of up to a quarter of production are spreading globally, exacerbated by climate change.

CGIAR is the world’s leading agricultural and food science and innovation organisation with an unmatched track-record of global impact going back 50 years. Its mission is to deliver cutting edge technology and evidence-based solutions to identify and tackle major challenges in the food system, supporting food security and growth in developing countries. CGIAR plays a key commissioning and directing role in global agricultural research, providing a focus for global research efforts aimed at developing and deploying evidence and technology to address the long-term term strategic challenges facing the food system. CGIAR-developed crop varieties are grown on over 200 million ha in developing countries, representing 60% of the total area sown to modern varieties. CGIAR research also delivers significant spillover benefits for global agriculture and for the UK.
The overall Goal of the programme is to contribute to the delivery of the high-level targets set out in the CGIAR 2030 Strategy.
This will be achieved by providing targeted funding to CGIAR that will:
- Support the delivery of high impact R&D programmes that it would be impossible to deliver using UK funding alone, reaching millions of people in Africa and Asia and delivering improved outcomes for women and girls
- Leverage UK advanced science capability and infrastructure to increase resilience to climate change, for example by delivering climate resilient crops and more efficient farming practices.
- Strengthen the UK global science leadership and influence, catalysing new international science partnerships with CGIAR funders and developing countries to exchange agriculture expertise, build national capacity and support locally led innovation.
- Enable FCDO to predict and respond to emerging food security threats by generating timely, high-quality, demand-driven evidence and analysis
Box 1: CGIAR 2030 Strategic Targets:
By 2030 CGIAR Research and Innovation along with complementary investments will:
1. Climate Adaptation: Equip 500 million small-scale producers to be more resilient to climate shocks, with climate adaptation solutions available through national innovation systems
2. Women and Girls: Close the gender gap in rights to economic resources, access to ownership and control over land and natural resources for over 500 million women who work in food, land and water systems.
3. Poverty reduction: Lift at least 500 million people living in rural areas above the extreme poverty line of US $1.90 per day (2011 PPP).
4. Food security and nutrition: End hunger for all and enable affordable healthy diets for the 3 billion people who do not currently have access to safe and nutritious food
5. Environmental health and biodiversity: Stay within planetary and regional environmental boundaries, including improved efficiency in water use, fertiliser use, zero net deforestation, and maintaining the genetic diversity of seeds, cultivated plants and farmed and domesticated animals and their related wild species.

The Purpose will be achieved through three interlinked Outputs:
Output 1. Knowledge, evidence, and innovations developed and delivered through CGIAR Research Initiatives to support the five impact areas.
- Output 2. CGIAR operational effectiveness and efficiency of CGIAR improved through progressive governance reforms and through enhanced management of research and innovation.
- Output 3. Enhanced partnerships with UK Science and technical support for FCDO posts
The programme was approved in August 2023, with an additional £20m addendum approved in October 2023. In addition to further support to the CGIAR research initiatives channelled through the multilateral CGIAR Fund, the addendum included £5m to the US-led VACS programme (Vision for Adapted Crops and Soils) and £5m to the Global Crop Diversity Trust (CropTrust) to protect the biodiversity held in the crop gene-banks, that hold over 700,000 crop and tree varieties in long-term storage. The VACS crop breeding programme will target crops with great potential in terms of nutrition, climate resilience and utilisation by farmers, but that have never been the target of selective breeding to improve their performance.

Summary supporting narrative for the overall score in this review
This is the first year of a new 4-year programme of support to CGIAR and builds on the work reported in the June 2024 Project Completion Report for the previous phase of CGIAR support (Project: 204764). The programme is proceeding well in its first year of delivery and scores an A. Highlights include the development of the UK-CGIAR centre for Science Collaboration which was announced in October 2023 at the Global Food Security Summit. The centre has made its first four grants to collaborative UK-CGIAR research projects. Significant new CGIAR impacts have been reported in the past year, set out in Box 2.

Box 2: CGIAR Impact Evidence reported in this year
1. CGIAR related crop technology has generated around £40bn in welfare benefits each year between 2016-20
2. CGIAR-related crop varieties of staple food crops were being grown on over 220m ha of land in developing countries in 2020 - around 50% of the area planted to modern varieties and representing around 10% of all global croplands.
3. 2.7 million households in Vietnam are growing rice resistant to the brown planthopper (BPH) and 2.4 million households are cultivating rice that is salinity tolerant.
4. Up to 1.2 million households are practicing climate smart Alternate Wetting and Drying rice production that can reduce water use, mitigate methane emissions and increase yields.
5. In Ethiopia the percentage of households growing hybrid maize increased from 62% to 75% between 2019 and 2022. The percentage of households growing drought tolerant maize increased by 16% to 49% over the same 3-year period.

1&2: https://www.sciencedirect.com/science/article/pii/S0305750X23003418
3&4: https://iaes.cgiar.org/spia/publications/preliminary-insights-adoption-cgiar-related-agricultural-innovations-vietnam
5: New evidence on the reach of CGIAR innovations in priority countries. In preparation.

CGIAR Research Initiatives: FCDO funding is allocated (designated) to specific research initiatives selected on the basis of their relevance to FCDO priorities, and the quality of science. A full list of allocations is set out in Annex 1. In 2023 CGIAR reported significant delivery of research outputs through the CGIAR Results Dashboard (see Box 2) and the CGIAR 2023 Annual report. The full list of 2023 annual technical reports from the FCDO funded initiatives is in Annex 1.

Box 3: Headline annual results in 2023
In 2023 CGIAR reported that it had:
- Delivered 3011 knowledge products including 700 journal articles. 85% were indexed on web of science
- Developed 873 innovations, ranked on an innovation readiness scale. 80% were at TRL* 3 (Proof of Concept) or higher.
- This included the 515 new improved crop varieties, proof of concept and value of improved agronomic practices and digital and crop/farm management tools, policy evidence and social innovations, soil and water conservation.
- Delivered 181 innovations into use. 74% were single innovations, 26% were part of an innovation package This includes crop varieties that are being adopted at scale, agronomic practices, tools and social innovations being applied by farmers, evidence and analysis influencing policy.
- 80% of the innovations were tagged against the OECD markers for Climate, either Principle (21%) or Significant (59%).
- 41 percent of results (2,487) reported by CGIAR addressed gender equality as a significant (30 percent) or principal (11 percent) objective. This is a marked increase from 35 percent of results in 2022.
- Of all CGIAR outcomes reported, 53 percent (189) related to gender equality (11 percent “principal” and 42 percent “significant”). Half of reported outcomes were innovation use results, including the application of gender-responsive agronomic practices, biocontrol agents, or advisory services, and some seed distributions.
- Reached 18m people with new innovations released in 2023. This is the total reported by CGIAR programmes in 2023, as opposed to the cumulative total reached.

Improved farming systems of agronomic practices
*Technology Readiness Level is measure of the maturity of technologies. TRLs are based on a scale from 1 to 9 with 9 being the most mature technology. TRL 1-3, basic research to proof of concept; 4-6 Technology development and demonstration; 7-9; delivery systems, scaling and adoption.

CGIAR uses the TRL scale to assess the scaling readiness of innovations. All innovations were scored against Scaling Readiness and Scalability Potential assessment which assesses the maturity of innovations and the likelihood that they will reach significant scale and deliver impact (Homepage | Scaling Readiness). In 2023 80% of the innovations reported through the M&E system had moved beyond Proof of Concept into product development.

UK-CGIAR centre: The first grants have been allocated and additional grants are being planned. Initial projects will support climate resilient agriculture, genome editing climate and disease resistant wheat, livestock productivity through improved fodder and better diets and nutrition outcomes for children and women (see Annex 2). A new phase of grant making is underway.

VACS: FCDO is currently working with USAID and CGIAR to develop the VACS crop breeding programme targeting the accelerated targeted breeding of 7 neglected crops of opportunity. The first seven crops were identified through climate and crop modelling to identify those with the most potential. These programmes will launch towards the end of 2024.

CropTrust: In 2023 FCDO made the decision to contribute to CropTrust, allocating funding in 2024 to support the maintenance of the international crop gene banks operating within the framework of the International Treaty*, the instrument that protects planet genetic resources from private acquisition and ensure they are maintained as an international public resource. This is in support of UK objectives to protect critical biodiversity that underpins productive resilient and sustainable agriculture in developing countries and in the UK.

Governance Reform: Significant progress has been made in establishing the new governance and management framework for CGIAR reported in 2023. Final agreement was reached on the integrated governance framework in October 2023 following the external review. This framework sets out the basic rules for the new CGIAR system. The details of the relationship between entities and the integration of functions across CGIAR are still being developed. A new Executive Management Director and Deputy EMD were recruited in late 2023, and the Integrated Partnership Board that will replace the System Board is being recruited now. Much remains to be done but progress is good.

Major lessons and recommendations for the year ahead

The lessons from the closure of the previous programme that transition into this programme were set out in the Project Completion Report approved in June 2024.

Review FCDO’s funding model for CGIAR by December 2024 to assess whether this has the right mix of bilateral and multilateral funding to deliver FCDO diplomatic, scientific, development and policy objectives set out in the new Business case and remains fit for purpose.

*The International Treaty for Plant Genetic Resources for Food and Agriculture.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

No change to the Theory of Change approved in 2023. The Theory of Change is included as Annex 4.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track.

## C. DETAILED OUTPUT SCORING

Output Title	Knowledge, evidence, and innovations developed and delivered through CGIAR Research Initiatives to support the five impact areas.
Output number:		1	Output Score	A
Impact weighting (%):		40	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Increase in the number of new crop varieties released/recommended for release that are more productive, nutritious and resistant to biotic and abiotic stress	Baseline set based on 2023 results dashboard.	Achieved. Baseline: 515 new or improved crop varieties were delivered in 2023.
Increase in the number of peer-reviewed and non-peer reviewed knowledge products delivered (including open access and altmetric rates)	Baseline set based on 2023 results dashboard	Baseline: Delivered 3011 knowledge products including 700 journal articles, working with over 1100 partners. 85% were indexed on web of science
Increase in the number of innovations tagged with OECD DAC marker for Gender (Significant or Principle)	Baseline set based on 2023 results dashboard	Baseline: 60% of the innovations were tagged against OECD DAC markers for Gender (Significant or Principle)
Number of people supported to better adapt to the effects of climate change (ICF KPI 1)	Develop indicator based on CGIAR Results Dashboard and reporting.	In progress: This indicator is being developed in the new logframe. FCDO are working with CGIAR to ensure the reporting formats are consistent with ICF reporting.
Accelerated development of under-utilized crops (VACS) addressing critical barriers to productivity and utilisation through targeted breeding.	Process underway to develop investment plans in high priority underutilised crops.	Achieved: VACS programme is developing investment plans for seven high priority crops with USAID and FCDO funding.
Sustained long term improvements in the conservation and management of the International Treaty Article 7 gene banks; protecting agro-biodiversity and making this available globally.	Funding allocated to the Global Crop Diversity endowment fund.	Achieved: Funding agreement developed; funding allocated to the GCDT endowment. FCDO has joined the CropTrust Funders Council.

Briefly describe the output’s activities and provide supporting narrative for the score.

CGIAR Research Initiatives: In 2023 FCDO allocated funding to specific research initiatives selected on the basis of their relevance to FCDO priorities and quality of science. A full list of allocations is set out in Annex 1. In 2023 CGIAR reported significant delivery of research outputs through the CGIAR Results Dashboard (see Box 2) and the CGIAR 2023 Annual report. The full list of 2023 annual technical reports from the FCDO funded initiatives in at Annex 1. Two programmes outside the CGIAR portfolio were selected for funding by FCDO because of their alignment with UK government priorities|:
- Genome Editing, funded with US, Gates Foundation and Australia
- ASEAN regional programme funded with Australia.

The CGIAR headline results are set out in Box 2.

VACS: FCDO is currently working with USAID and CGIAR to develop the VACS crop breeding programme targeting the accelerated targeted breeding of 7 neglected crops of opportunity. These programmes will launch towards the end of 2024. Seven proposals from collaborations between African partners, international centres (CGIAR and non-CGIAR) and advanced research institutes have been received and are being reviewed by a VACS breeding team. The programme is being overseen by a leadership committee with FCDO, USAID and African representation.

CropTrust: FCDO has rejoined CropTrust, allocating £7m funding in 2024 to support the maintenance of the international crop gene banks operating within the International Treaty for Crop Genetic Resources for Food and Agriculture (the International Treaty. Geoff Hawtin, the UK scientist who conceived of the CropTrust in the first place will be honoured by being awarded the World Food Prize later this year.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed),
N/A.

Lessons learned this year :
These were captured in the Programme Completion report for the previous CGIAR programme 2017-23 approved in June 2024.

Recommendations for the year ahead
Review FCDO’s funding model for CGIAR by December 2024

Output Title	CGIAR operational effectiveness and efficiency of CGIAR improved through progressive governance reforms and through enhanced management of research and innovation.
Output number:		2	Output score	A
Impact weighting (%):		40	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Strengthened oversight and funding mechanisms driving prioritisation of research to ensure that the CGIAR resources are increasingly focused on the major threats and opportunities	Independent Science for Development Council (ISDC) reappointed with new mandate. / The design of the new Research Portfolio (2025-30) is underway, and accurately reflects the challenges facing the food system and global food security and CGIARs comparative advantage.	On track: ISDC recruitment underway with a date of 2025. / Research Portfolio design process progressing well under the oversight of the CGIAR leadership. The process was delayed by the decision of the incoming Executive Managing Director (EMD) to transition to Mega-programmes.
Improved management of research using results-based management and effective evaluation	Appoint a new FCDO secondee into CGIAR to support the Portfolio Performance Unit on integrated management of the CGIAR portfolio	Achieved: A new secondee was appointed in February
Strengthened governance arrangements across CGIAR balancing centre priorities with system wide risk and programme management framework	Conclude the integrated governance framework and secure coherent and effective governance and management across CGIAR. / New System Board appointed by September 2024 / New leadership (EMD) appointed by March 2024	Achieved: The Integrated framework was agreed in November and ratified by all CGIAR centres in January. / The Integrated Partnership Board has been nominated and approved by System Council. Will take over from the SB by September. / EMD and Deputy EMD appointed in December 2023.

Governance Reform: Significant progress is establishing the new governance and management framework for CGIAR reported in 2023. The Integrated Governance Review was completed in October 2023. Final agreement was reached on the integrated governance framework in October 2023 following the external review. This framework sets out the basic rules for the new CGIAR system. The details of the relationship between entities and the integration of functions across CGIAR are still being developed. A new Executive Management Director and Deputy EMD were recruited in late 2023, and the Integrated Partnership Board that will replace the System Board has been nominated for approval to the System Council. Much remains to be done but progress is good.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed),
N/A

Lessons learned this year
These were captured in the Programme Completion report for the previous CGIAR programme 2017-23 approved in June 2024.

Recommendations for the year ahead
Conclude the implementation of all recommendations in the Integrated Governance Review and supporting actions needed to develop a robust and proportionate governance and management system by June 2025.

Output Title	Enhanced partnerships with UK Science and technical support for FCDO posts
Output number:		3	Output score	A
Impact weighting (%):		20	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Research outputs from new partnerships established with UK scientists and CGIAR initiatives targeting priority R&D Delivery	UK-CGIAR centre operational and disbursing funds to UK-CGIAR partnerships in priority areas.	Achieved: 4 partnerships have been funded, 2 further projects are in design and will be launched in 2025.
Number of FCDO requests for technical support supported with CGIAR knowledge and evidence	Planning commenced to provide targeted technical support to FCDO support based on demand. / Programme-funded secondment to the CGIAR was appointed to strengthen targeted technical support an connect FCDO demand to CGIAR evidence and analysis / Extend arrangement with IFPRI and design new mechanism to access full-CGIAR range of expertise.	On track: The development of a responsive programme run by the UK-CGIAR centre is underway led by FCDO secondee. / Achieved: Programme-funded secondment to the CGIAR was appointed in early 2024 to strengthen targeted technical support. ‘Ask Food’ Lead to support wider shopfront for food and agriculture expertise will be appointed in autumn 2024. / Achieved: MoU extended. Design work underway with CABI and CGIAR led by secondee.

UK-CGIAR centre: The centre was launched officially in November 2023. A secretariat was set up in CABI, governance mechanisms established, and financial and research management systems agreed with CGIAR and CABI. The first grants have been allocated and additional grants are being planned. Initial projects will support climate resilient agriculture, genome editing climate and disease resistant wheat, livestock productivity through improved fodder and better diets and nutrition outcome for children and women (see Annex 2). A new phase of project development is underway co-funded by UKRI.

A programme-funded secondment to the CGIAR was appointed in early 2024 to strengthen targeted technical support linked to the FCDO ‘Ask Food’ offer developed by the Food and Agriculture Head of Profession. Ask Food provides a wider shopfront for food and agriculture expertise, the head will be appointed in autumn 2024. The secondee is working closely with CABI, the F&A HoP and CGIAR to develop a responsive mechanism that can draw on all CGIAR areas of expertise to respond to demand within FCDO. The Ask Food coordinator is also funded through this programme.

The current MoU with IFPRI has been extended to provide a continued knowledge and evidence service for FCDO to draw on ahead of the wider mechanism being developed. This is providing L&D input, targeted seminars and a call-down component to respond to short term requests from FCDO for support in IFPRI’s core area of expertise. The FCDO secondee is leading this exercise

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed),
N/A

Lessons learned this year
These were captured in the Programme Completion report for the previous CGIAR programme 2017-23 approved in June 2024.

Recommendations for the year ahead
Conclude the design of the UK-CGIAR responsive programme by December 2024 for launch in 2025.
## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

The VFM analysis developed in 2023 has not significantly changed.

Assessment of whether the programme continues to represent value for money

The case made in the 2023 Business Case that CGIAR offers exceptional value for money for FCDO has not changed.

E: RISK

Overview of risk management
Overall, this programme consistently had a risk rating of moderate, unchanged from the business case development. CGIAR has a comprehensive Risk Management Strategy and Framework[1] and a Risk Appetite Statement[2] that balances reputational and operational risks, with the need to drive transformative innovation through a balanced portfolio of research and development and which allows for both high and low risk R&D. Each of the CGIAR centres have in addition risk frameworks appropriate for their contexts. The unified One CGIAR Governance Arrangements and the IGR provide the overall framework for Risk Management across the CGIAR[3]. A core principle of CGIAR’s framework is that risk management is performed closest to the risk to maximize effectiveness, therefore the Centres themselves manage Centre-level risks under the oversight and guidance of the System Board.
[1] The Risk Management Framework of the CGIAR System
[2] Risk Appetite Statement of the CGIAR
[3] Functions in the CGIAR System High Level Summary.
- Each Centre has in place risk management policies and practices overseen and routinely discussed by the Centre Board of Trustees.
- In all cases Directors General are responsible for implementation of risk management policies and are supported by or leading an Executive/Risk Management team at the Centre.
- Clearly established practice of reporting on risk to the System Board through the common Audit Finance and Risk Committee of the System Board at least bi-annually, providing an overview of key risks, risk changes, and risk-based action plans.
- The external Assurance and Oversight Committee acts on behalf of the System Council to review safeguarding and risk management across CGIAR, including internal and external audit, and reports to the SC biannually.
For all Centres, the role attributed to their respective Internal Audit provider is to review the design and effectiveness of the Centre’s risk management processes and advise their Boards on gaps.

The risk analysis in the 2023 Business Case is unchanged (see Annex 2). The risk register has been updated on AMP. The development of an integrated assurance system across CGIAR is underway under the guidance and leadership of the System Council Assurance and Oversight Committee (AoC) and the Audit Risk and Finance Committee (AFRC) of the System Board. This forms an element of work to develop a system-wide framework that integrates essential functions across CGIAR, focusing initially on Internal and External Audit and Ethics and Business Conduct. The so-called ICI (Integrate, Coordinate, and leave Independent) process will establish a common rules framework across CGIAR for risk financial, people and programme management. We expect this work to continue until early 2025.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The programme is on track and achieving its milestones across each output. In 2023/24, FCDO contributed £21,733,333 to the CGIAR under Window 1 (Designated) funding; a further £26,000,000 is scheduled to be disbursed via the same mechanism in 2024/25.

All FCDO funding was allocated to the best performing and most relevant CGIAR Research Initiatives and Platforms based on an agreed allocation formula. Allocations are based on an internal scoring system that considers relevance, performance, and the funding gap against agreed programme budgets for the year, in order not to over fund any Initiatives or Platforms. The allocation includes a 2% cost sharing percentage that supports CGIAR System Actions and Entities, and a percentage (varying across centres between 9% and 19%) to cover indirect cost in the research centres.[4]
[4] Overheads vary for a range of reasons, the costs of doing research is greater than other types of research and carries greater overheads, the location of the CGIAR centres and legacy liabilities soe centres carry.

The programme budget also covers costs of an FCDO Adviser to the System Office. The secondment has been extended until 2025.

The Audited Financial Statements of all CGIAR research centres and the CGIAR System Organization are prepared each year according to the accrual basis of accounting in compliance with IFRS or US GAAP. 11 of 14 centres have published audited annual accounts covering 2023, however CIMMYT, IITA and ICRISAT’s are outstanding; FCDO will follow up to ensure these are completed and published.

The analytical assessment of CGIAR System financing illustrated below is extracted from the CGIAR Financial Dashboard.

In 2023, CGIAR recognized revenue of US $870 million. Figure 1 shows a comparison of 2023 and 2022 funding and the breakdown by funding mechanism; overall funding to the CGIAR rose by 13% from 2022 to 2023.

Figure 1. CGIAR revenue by source of funding, 2023 and 2022

2023	2022

Further analysis of overall CGIAR System revenue since 2011 is shown in Figure 2 below:

Figure 2. CGIAR System revenue by source of funding, 2011–2022

Figure 3 shows the main categories of expenditure. Overall, expenses in 2023 increased by 12% to $859 million from $769 million in 2021, in line with the 13% increase in funding received. In 2022, 82% of expenditure was on research and collaboration costs with 18% on administrative costs, a similar split to 2022.

Figure 3. Expenditure by main category, 2023 and 2022

2023	2022

Date of last narrative financial report	July 2024 / (Per CGIAR Financial Report Dashboard)	Date of last audited annual statement	CGIAR – July 2024 / CIP – June 2024 / ILRI – July 2024 / IITA – June 2025 / AfricaRice – mid 2024 / ICARDA – June 2024 / ICRISAT – April 2023 / IFPRI – June 2024 / CIMMYT – June 2022 / CIAT – June 2024 / Bioversity – June 2024 / IRRI – May 2024 / IWMI – mid 2024 / World Fish – mid 2024 / https://www.cgiar.org/food-security-impact/finance-reports/

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
The Annual Review was carried out by the programme PRO and Deputy Programme Manager. Throughout the year the FCDO team was in regular contact with CGIAR and attended two in person CGIAR System Council meetings CGIAR19 November 2023, Rabat, Morocco and SC20 Brasilia, June 2024, and in addition attended a number of ad-hoc System Council calls and several drop-in sessions. FCDO Chair the CGIAR Strategy, Impact Monitoring and Evaluation Committee, which met multiple times during the year. The Annual Review team drew upon the following documents and evidence resources.

CGIAR Financial Report Dashboard
CGIAR 2023 Financial Report Highlights & Dashboards
CGIAR 2023 Annual Performance Report, Technical Reports and Initiative and Platform Annual Reports
CGIAR System Organisation Charter
CGIAR 2030 Research and Innovation Strategy: Transforming food, land, and water systems in a climate crisis
Minutes of the meeting of the CGIAR System Council 19 and 20, and the SC Decision Register.
CGIAR Investment Prospectus 2022–2024
2020 CGIAR Research Programme Evaluative Reviews
CGIAR Initiative Reviews by Independent Science for Development Committee. Tranche 1 and Tranche 2.
- CGIAR Business Case 2023– 2026
- The UK-CGIAR Centre - CABI.org

Annex 1: FCDO allocations to CGIAR Research Initiatives in 2024:
Science Group	Initiative/Region/Platform Name	Allocations
Resilient Agri-Food Systems	Livestock and Climate	£1,639,200
	Sustainable Animal Productivity	£1,814,200
	Excellence in Agronomy	£1,715,000
	Mixed Farming Systems	£1,108,000
	Nature-Positive Solutions	£694,200
	TOTAL	£6,970,600
Systems Transformation	NEXUS Gains	£675,000
	Agroecology	£687,500
	Climate Resilience	£2,050,000
	Rethinking Food Markets	£566,700
	Sustainable Healthy Diets	£927,500
	Low-Emission Food Systems (Mitigate+)	£927,500
	Gender Equality (HER+)	£975,000
	Foresight	£635,800
	Fruits and Vegetable	£933,000
	Fragility, Conflict, Migration	£565,800
	TOTAL	£8,943,800
Genetic Innovations	Genebank	£991,700
	Accelerated Breeding	£2,029,200
	Breeding Resources	£1,704,200
	Seed Equal	£1,863,000
	Market Intelligence	£775,000
	TOTAL	£7,363,100
Regions	Fragility to Resilience in CWANA	£1,079,200
	Diversification in ESA	£1,592,500
	TOTAL	£2,671,700
Platforms	Gender	£535,000
	Climate	£245,000
	Environment	£245,000
	Nutrition	£245,000
	Poverty reduction	£245,000
	TOTAL	£1,515,000
Total to W1 Designated to Initiatives		£27,464,200

The annual technical reports for each of the programmes and the overall portfolio narrative can be found here: CGIAR initiatives - Annual Technical Reports

Annex 2: UK-CGIAR Centre

Full project grants:

Topic 1 - Confronting Climate Change and Environmental Degradation through sustainable crop management and climate-smart agronomic practices

Project Title: iSPARK: innovation in sustainability, policy, adaptation and resilience in Kenya

Partners:
- UK: Leeds University,
- CGIAR: IITA, CIAT
- Developing Country: KALRO, Kenya
Summary: The core of iSPARK science is a development and implementation of a metric-based approach to Innovation in Sustainability, Resilience and Adaptation that can provide tailored evidence for pathways and innovations across scales (agronomic field-scale to regional policy). Evidence is co-produced with partners and tailored to i. farm context, including gender and youth; investment strategies, including the role of agri-business in developing and scaling up solutions; ii. policy instruments as effective policy implementation tools; and iii. nutrition security outcomes.

Topic 2 - Crop Genetic Improvement for Future Climate Resilience

Project Title: Leveraging genetic innovations for accelerated breeding of climate resilient and nutritious crops

Partners:
- UK: JIC, Norwich
- CGIAR: ICARDA, CIMMYT
- Developing Country: KALRO, Kenya, ARC Egypt, QAU Pakistan, Sokoine University Tanzania; AGIS Shenzhen (collaborating but not funded)
Summary: The purpose of this project is to deliver genetically improved, farmer-preferred varieties. While the focus is on wheat, the methods and pipelines can be employed to other crops. We will use genome editing to develop locally adapted wheat varieties with
(i) enhanced resistance to wheat rusts.
(ii) increased iron content, whilst also developing ‘big genome data’ approaches to accelerate genetic gain in traditional breeding approaches. The expected outcomes include:
• Reduced reliance on imports in major wheat importing countries
• Improved resilience to climate-change triggered rust epidemics
• Increased iron intake and improvement of women and children’s health in societies where wheat is a staple crop (e.g. Pakistan, Egypt, Kenya)

Partnership Development Grants

Topic 3: Increasing the intake of fruit and vegetables as components of healthier diets among marginalized populations:

Project Title: Fruits and Vegetables for Sustainable Healthy Diets (FRESH)-Expanded Network with UK Partners (FRESH-EN UP)

Partners:
- UK: LSHTM
- CGIAR: IFPRI
- Developing Country:, Sokoine University Tanzania.
Research Questions:
1. What are the characteristics of food consumption patterns in Tanzania (TZ) and what are the major drivers of fruit and vegetable (F&V) intake in TZ?
2. What are the priority policy-relevant and feasible interventions to increase F&V intake among households, women of reproductive age (WRA) and/or adolescents, and how could these be tested in the Fruit and Vegetables for Sustainable Healthy Diets (FRESH) Initiative study?
3. How can modelling approaches be adapted to analyse the costs, effectiveness and equity implications of scaled-up interventions to increase F&V consumption in Tanzania?
Topic 4 - Livestock improvement, animal health, nutrition, and welfare:

Project Title: Defining new Phenotypes for forage and crop by-products improvement based on rumen function and greenhouse gas (GHG) emissions

Partners:
- UK: SRUC
- CGIAR: ILRI
- Developing Country: None identified yet.
Project Summary: There is significant literature that identifies rumen utilisation as the key to efficient use of forages and by-products whilst minimising GHG emissions. Whilst it is possible to measure such properties, the lack of high throughput techniques has limited their use as effective phenotyping to improve plant breeding targets. Here we will develop and verify new high throughput screens to define new phenotypes for forage and crop residue improvement based on rumen function and greenhouse gas emissions.

Annex 3: CGIAR Risk Matrix.

Risk	How risks will be minimized and mitigated	Probability	Residual Risk	Risk Trajectory
External Context Risk
Public opinion in the target countries opposes specific technologies and products delivered by CGIAR.	CGIAR has released almost 5000 new conventional crop varieties in the past 10 years. The CGIAR is linked strongly into national research organisations in target countries and is responsive to national demand, ensuring that demand is assessed and met. Although novel genetic technology is funded, it is only deployed where national policy support this.	Unlikely	Minor
UK public opinion opposes international development funding generally and/or funding of agricultural research through international organisations	This funding follows a successful previous phase of funding which delivered excellent results. This provides strong communications material to raise awareness of the importance of agricultural research, not only for developing countries, but also the UK national interest. The programme will continue to deliver a pipeline of positive stories.	Possible	Minor
Exogenous shocks from conflict, climate change or other natural disasters have a negative impact on delivery or uptake of the research outputs.	CGIAR as a whole works in over 100 countries and all FCDO funded programme work in multiple locations. This means that, while the risk of individual research Initiatives being affected by exogenous shocks remains, the risk of this affecting the programme as a whole is minimal.	Possible	Minor
Delivery Risk
The evaluation function (secretariat, policy and framework) fails to deliver robust evaluation of research.	SIMEC oversees the delivery of evaluation a cross CGIAR. The actions taken following the 2019 MOPAN review have largely been addressed. The System Council will continue to track progress through SIMEC.	Possible	Moderate
CGIAR carries out poor quality research not relevant to developing country demand.	CGIAR has a strong track record in generating high quality research outputs and have robust governance mechanisms and scientific oversight. ISDC oversight and review provides independent assessment of development relevance. / The PRMF provide a core set of performance indicators that will be tracked annually by FCDO.	Unlikely	Minor
Low predictability and late release of funding undermines research delivery and confidence in the system.	The financial system developed in 2020, with Designated W1 and W3 funding increases flexibility and provides assurance that funding will be available. However, low predictability, the use of annual allocations released late in the year will continue hinder CGIAR financial management.	Possible	Moderate
Donors continue to use bilateral research, undermining the new One CGIAR management arrangements. Changes to CGIAR funding and reduction in overall predictability of funding undermines the coherence of the CGIAR	The new integrated suite of research, funded fully and designed using the agreed 13 Eschborne Principles, provide the assurance that large bilateral donors need in order to increasingly pool funding to the Initiatives. The development of agreed and harmonised reporting frameworks designed to meet donor requirements, and the development of the PRMF builds confidence in the CGIAR systems.	Possible	Moderate
Lack of competition in research commissioning results in poor quality research being funded.	ISDC-led peer review of all new research is the main means for independent quality control. This has involved external peer-review of the Initiatives. In addition the integrated research management system will assess research performance. / FCDO selects research based on our own assessment of the quality, relevance and potential impact of research.	Possible
Safeguarding Risk
A lack of sensitivity to important gender dimensions in programme design limits the programme’s impact and potentially exacerbates gender inequalities, as well as those surrounding other marginalised groups.	Gender issues are firmly integrated into the programme, and FCDO will continue to monitor the performance and progress against gender targets, working with other donors. Actions following the 2019 MOPAN review, include the development of a gender and social inclusion impact platform. / CGIAR’s own G,D and I reporting allows us to track progress within CGIAR.	Unlikely	Minor
Operational Risk
The SMO fails to establish the results-based management framework.	We will work closely with the System Office, and with lead donors to ensure the PRMF and reporting system meets demand. We will continue to support this with a secondee into the System Office Programme Performance Unit.	Unlikely	Minor
Fiduciary Risk
Financial mismanagement or fraud on the part of the Centres and System Organisation is not identified or the response is inadequate or ineffective.	As part of programme management and annual review processes, FCDO will review audited accounts annually. The Annual Review will also consider financial management issues. In case of any mismanagement/fraud, FCDO procedures would be followed, and issues will be escalated where necessary to the Board of the Centre involved. In the worst case, FCDO would suspend funding. / Audit arrangements across the CGIAR are overseen by the Audit and Oversight Committee, which provides donor assurance of compliance with best practice.	Unlikely	Moderate
Reputational Risk
The key reputational risk for FCDO is that any of the above risks are realised without appropriate measures in place to mitigate the impact.	The sections above describe the mitigation measures FCDO has in place for each category of risk, which reduce the likelihood and residual impact of each risk to an acceptable level within FCDO’s risk appetite. This programme is based on an earlier successful programme of funding, and FCDO will build on the positive, strategic working relationships already established to continue to closely monitor their performance.	Unlikely	Moderate
CGIAR is locked into a programme of research and unable to respond to new priorities.	The CGIAR has shortened the duration of the business plan to 3 years and has adaptive management and stage-gating systems across the portfolio. SIMEC oversees the strategy and foresight work of the ISDC which identifies new priorities. CGIAR has demonstrated an impressive ability to pivot toward new issues (Covid -19, Russia’s invasion of Ukraine) meeting FCDO and global demand for new research outputs	Unlikely	Minor
CGIAR fails to establish effective partnerships drawing on international research expertise.	There are over 200 partnerships already established between the CGIAR and Advanced Research Institutions (ARIs). FCDO have held back funding specifically to build partnerships between leading UK centres of academic excellence and CGIAR research initiatives and centres.	Unlikely	Moderate

Annex 4: Theory of Change