## Annual Review Template

Title: Developing science and technology solutions to the global food security and climate crisis with CGIAR (2023-25)
Programme Value £ (full life): £110,000,000		Review date: August 2025
Programme Code: 300671	AMP start date: 09/08/24	AMP end date: 01/10/26

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	Business case / Business case addendum
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

The world is falling behind on its targets for climate, nature, and human well-being—and transforming the food system is a critical lever for achieving global goals. Food production is not only highly vulnerable to climate change, but it is also the second-largest source of greenhouse gas emissions after the energy sector. Moreover, food systems are the leading driver of biodiversity loss, consume over 80% of the world’s freshwater resources, and are increasingly threatened by water scarcity in many vulnerable regions.

More than 2 billion people face moderate to severe food insecurity—a number that has risen steadily since 2015. In Africa, over 85% of the population cannot afford a healthy diet, while in South Asia, the figure stands at 70%. Gender inequality in food access is also worsening: 32% of women globally are moderately or severely food insecure, compared to 28% of men.

CGIAR is the world’s leading agricultural and food science and innovation organisation with an unmatched track-record of global impact going back 50 years. Its mission is to deliver cutting edge technology and evidence-based solutions that advance the transformation of food, land, and water systems in a climate crisis. CGIAR-developed crop varieties are grown on over 200 million ha in developing countries, representing 60% of the total area sown to modern varieties. The UK has funded CGIAR research and contributed to the development of the multilateral approach and governance over many decades.

The overall goal of this FCDO programme is to contribute to the delivery of the high-level targets set out in the CGIAR 2030 Strategy (Box 1). The UK’s contribution to these goals will be achieved by:
- Working with other funders to strengthen the integrated partnership model and provide strategic oversight of a high-impact R&D portfolio that it would be impossible to achieve using UK funding alone
- Accelerating the development of innovations and evidence on what works that can be scaled to reach millions of people in Africa and Asia.
- Catalysing new international science partnerships that leverage the UK’s advanced science capability in key areas to accelerate R&D solutions to global challenges.
- Equipping FCDO with high-quality, demand-driven analysis; evidence-based policy advice; and innovations to strengthen the impact of FCDO programmes and diplomatic engagement.

Box 1: Collective Global 2030 Targets:[1]
Working with others, the CGIAR will contribute to the following collective global targets for transformation of food, land and water systems:
1. Climate Adaptation: Equip 500 million small-scale producers to be more resilient to climate shocks, with climate adaptation solutions available through national innovation systems
2. Environmental health and biodiversity: Stay within planetary and regional environmental boundaries, including consumptive water use in food production and fertiliser use, zero net deforestation, and maintaining the genetic diversity of seeds, cultivated plants and farmed and domesticated animals and their related wild species.
3. Food security and nutrition: End hunger for all and enable affordable healthy diets for the 3 billion people who do not currently have access to safe and nutritious food
4. Poverty reduction: Lift at least 500 million people living in rural areas above the extreme poverty line of US $1.90 per day (2011 PPP).
5. Women and girls: Close the gender gap in rights to economic resources, access to ownership and control over land and natural resources for over 500 million women who work in food, land and water systems.

[1] https://cgspace.cgiar.org/items/f5fb41f0-6ea8-4583-b96d-b72a3fc96187

The objectives of the FCDO programme will be achieved through three interlinked Outputs:
Output 1. Knowledge, evidence, and innovations developed and delivered through CGIAR Research Initiatives to support the five impact areas.
- Output 2. CGIAR operational effectiveness and efficiency of CGIAR improved through progressive governance reforms and through enhanced management of research and innovation.
- Output 3. Enhanced partnerships with UK Science and technical support for FCDO delivery
Summary supporting narrative for the overall score in this review

2024 is the second year of this three-year programme, building on past phases of support to CGIAR. New evidence of CGIAR impacts at the global and national levels have been published in the past year (see Box 2). Building on long-term investments in R&D pipelines, annual results have also been achieved (highlights in Box 3 and selected examples in Box 4). The programme is on track across all outputs and scores an A for this annual review.
Box 2: CGIAR impact evidence reported in this year
- A new study from Fuglie and Echeverria (2024) estimated that, from 2016 to 2020, CGIAR-related1 crop improved crop varieties were sown on 190 million hectares across low- and middle-income countries, covering 26% of the land area of those crops. CGIAR-supported pest, water, and soil management techniques were applied to an addition 31 million hectares. This generated US$47 billion annually in economic welfare gains.
- Baldos et al. (2025) found that the adoption of agriculture-related technologies contributed to reductions in cropland expansion (9.7-million-hectare reduction), greenhouse gas emissions (2.42 billion metric tons of CO₂e reduction), and biodiversity loss (713 avoided species extinctions) between 1961 and 2015.
- 300 million people were estimated as consuming CGIAR-supported biofortified foods by 2024. This is about 10% of the number of people worldwide who cannot afford an adequately nutritious diet.
- Independent country-specific studies found that agricultural innovations linked to CGIAR research were adopted by more than 5.8 million households in Ethiopia (est. 44% of rural households in Ethiopia); 3.8 million households in Vietnam (est. 28% of rural households); and 8 million households in Bangladesh (est. 53% of rural households).2
- By supporting economic development and income growth in low- and middle- income. countries, new modelling estimates indicate that CGIAR investments have also delivered substantial economic benefits for the UK. This includes (i) demand for an additional GBP2.6 billion in annual exports from the UK and (ii) reductions in the cost of a healthy diet in the UK by 1.24%—an annual saving of GBP 46 per family of four—and increased the amount of dairy, fruits and vegetables consumed by British families.3
1. CGIAR related crops are those directly bred by CGIAR centres and varieties developed by other institutions using CGIAR germplasm for parent material
2. Country Studies | IAES | CGIAR Independent Advisory and Evaluation Services
3. FCDO-commissioned study by the International Food Policy Research Institute

CGIAR Research Initiatives: FCDO 2024 funding was allocated (designated) to specific research initiatives selected on the basis of their relevance to FCDO priorities and the quality of science. A full list of allocations is set out in Annex 1. In 2024, CGIAR reported significant delivery of research outputs through the CGIAR 2024 Annual report, annual initiative-level reports, and the CGIAR Results Dashboard.

Aggregate results are presented in Box 3 and selected examples are presented in Box 4. These results draw on available evidence from the pooled-fund portfolio and, in selected cases, large bilateral projects. Only a subset of these results can be attributed to FCDO support; FCDO is one of many funders of the CGIAR and provides strategic oversight of the pooled-fund portfolio through its seat on the System Council and various committees.

Box 3: Headline results achieved in 2024
- 323 CGIAR-related innovations were reported in use by all actors, including extension services, private sector, NGOs, government, researchers. 169 of these innovations were reported in use by 9.4 million farmers. CGIAR-supported innovations include crop varieties, agronomic practices, tools and social innovations being applied by farmers, evidence influencing policy, among others.
- CGIAR research and innovation informed 196 policy changes and more than $960m in investments.
- CGIAR Genebanks provided more than 70,000 germplasm samples in 83 countries to 945 requestors to help advance breeding and germplasm multiplication efforts.
- More than 4.5 million farmers, extension agents and policy actors used CGIAR-related innovations to support climate change adaptation and/or mitigation in 2024.
- Of all CGIAR outcomes reported in 2024, 54 percent related to gender equality (11 percent “principal” and 43 percent “significant”). Almost half of the reported outcomes on gender equality were innovation use results, including the application of gender-responsive agronomic practices, biocontrol agents, or advisory services, and some seed distributions.
- 287 new crop varieties developed by CGIAR working with national partners were registered and released for use. 58% varieties were climate-resilient and 26% were biofortified and directed to lower malnutrition among women and children, or are aimed at reducing cooking time with a gender differential impact.
- Average scaling readiness of CGIAR innovations increased from 4.9 in 2022 to 6.0 in 2024 (on a scale of 0-9).1 The number of innovations that CGIAR’s Initiatives worked on increased from 477 in 2022 to 1,018 in 2024. 162 reached level 9 and were classified as “proven innovations”, i.e. they were validated as reaching specific impacts in uncontrolled settings. Level 9 innovations will be incorporated into a clearinghouse model for investors through the scaling programme from 2025.

Box 4: Selected examples of new CGIAR innovations, CGIAR contributions to policy outcomes, and country-level partnerships and results[2]
[2] The Kenya example draws on the CGIAR Impact Report 2022 – 2024: Type II report

Examples of advancements in innovation development and use:

- CGIAR-related varieties are advancing climate change adaptation at scale in Bangladesh: In 2024 39% of farmers grew CGIAR-related varieties in the monsoon “amon” season, rising to 52% in the irrigated “boro” season. Adoption of flood tolerant rice has steadily increased, with 7% of all famers growing CGIAR-supported rice with the “sub-1” gene in the flood prone amon season.
- Saline tolerant “saltol” rice developed by CGIAR IRRI and Vietnamese partners has achieved widespread adoption. Varieties released between 2002-2020 are grown by 31% of rice-producing households (2m) with adoption concentrated in the flood-prone Mekong and Red-River Deltas.
- A real-time virtual model of the 400,000 km² Limpopo River Basin has integrated hydrological, climate, and water quality data across four Southern African countries. LIMCOM, the transboundary water management authority, has adopted the model as a strategic asset to test river management scenarios, assess risks, and facilitate coordinated responses to droughts, floods, and water quality issues.
- Machine learning models enabled delivery of localised climate advice to over 100,000 farmers with local partners in Kenya and Peru by 2024.
- Advanced breeding techniques, such as marker-assisted selection and genomics, are enabling faster, more precise screening of nutrient-rich and resilient varieties. By scaling an integrated digital collection of phenotyping data and AI-powered analysis, breeding cycles are projected to accelerate from 10 to 5 years and to reduce costs by 30%.
Examples of CGIAR research in policy uptake:

- CGIAR policy guidance on water-energy-food environment nexus approaches was adopted by the Niger Basin Council of Ministers.
- The Food and Agriculture Organization of the United Nations (FAO) integrated evidence from CGIAR into FAO Guidelines on Water Quality in Agriculture
- CGIAR research informed the United Nations High Commissioner for Refugees (UNHCR) Strategic Framework on Climate Action.
- CGIAR’s Genebanks informed the adoption of supportive text by the Plant Treaty at CoP and the Southern African Development Community.
- The Women’s Empowerment in Agriculture Index (WEAI), the first comprehensive and standardised measure of women’s empowerment and inclusion in the agricultural sector, has been adopted by at least 279 organizations in 69 countries.
- The Gender Impact Platform helped shape global policies, including FAO’s global report on the Status of Women in Agrifood Systems and the Voluntary Guidelines on Gender Equality and Women’s and Girl’s Empowerment in the Context of Food Security and Nutrition
Example of country-level results: the case of Kenya

CGIAR collaborations with local partners are supporting demand-driven research and innovation uptake in Kenya. From 2022 to 2024:
- 1.8 million users of 63 CGIAR-supported innovations were reported in Kenya. These innovations related primarily to improved seed systems and agronomy; agroecology and nature-positive solutions; livestock and mixed crop-livestock systems; participatory development, scaling, finance, and credit; digital innovations; and gender equality and social inclusion
- 37 policy changes were also reported. Examples of specific policy contributions included strengthening seed certification regulations for vegetatively propagated materials, contributing to a National Agroecology Strategy under the leadership of Kenya’s Ministry of Agriculture and Livestock Development, and supporting national and local responses to climate change.
- 90 percent of outcomes were achieved in partnership with other institutions: county governments were the most frequently reported national partner, followed by Kenya’s Agriculture and Livestock Research Organization (KALRO).

Global engagement and leadership: CGIAR global influence grew in the last year through strong leadership and engagement in key forums such as the Nutrition for Growth Summit, the RHS Chelsea Flower Show, and the first prominent presence at UNGA and the WEF Davos. Highlights include CGIAR engagement in negotiations of the 3 Rio Conventions (Climate, Biodiversity and Desertification), showcasing science to inform decisions and building partnerships. This engagement included contributions to 3 negotiation outcomes in COP16 and 3 outcomes in COP29. CG leadership also participated in the G20 (Ag track) and G7 (Ag and Dev tracks), successfully leading to CGIAR priorities included in ministerial communiqués. Over the last year, CGIAR visibility increased (42% increase in social media engagement; 320,000+ additional followers on social media; 30,000+ media mentions). The Executive Managing Director of the CGIAR was also recognised as one of the 100 Most Influential People of 2025 Time List.

An important focus in 2024 was the conclusion of the initiatives and design of a streamlined science and innovation portfolio for 2025-2030. The design process included an in-depth prioritisation exercise, comparative advantage analysis, demand assessment and engagement with key partners[3], and mapping of bilateral projects to the new simplified portfolio structure. A new Chief Scientist was appointed, and directors for the 25-30 science programmes will be finalised in 2025.
[3] As an example of partner engagement and co-design, the CGIAR Advisory Committee in Bangladesh has been in place for over eight years and has played a central role in aligning CGIAR’s research with national priorities and fostering institutional ownership. The committee periodically engages with senior officials from the Ministry of Agriculture and the Ministry of Fisheries and Livestock to align research priorities, share evidence, and support the delivery of integrated solutions across Bangladesh’s agrifood systems.

To ensure the CGIAR is future-fit, senior leadership has significantly expanded its use of digital and data innovations to enhance agricultural research and improve the resilience of global food systems. A digital transformation strategy is under development to (i) mainstream AI and digital innovations to accelerate CGIAR science and innovation; (ii) drive organizational efficiency, operational excellence and innovation using digital and AI; and (iii) foster global public goods and partnerships to promote equitable, gender-inclusive digital transformation in the agri-food system.

During the last year, the FCDO secondee to CGIAR initiated a review of CGIAR’s work in fragile and conflict affected situations (FCAS). The aim of the review is to support CGIAR to articulate and leverage its expertise where relevant for stabilisation, peace-building and recovery after conflict and disasters in FCAS contexts. It will also inform FCDO research on strengthening resilience in FCAS contexts.

Finance: In 2024, the CGIAR made significant efforts to simplify leadership structures and to reduce system office costs in line with the integrated partnership model. These budget reductions softened – to some degree – the impact of budget cuts in 2025 due to the closure of USAID and pressure on funding from other donors including the UK.

Declining budgets for Windows 1/2 portfolio funding and Window 3/bilateral project funding highlight the critical need for the CGIAR portfolio to remain focused, impactful and agile in the current global context. It is also an opportunity for innovative approaches to engage and leverage the expertise of key science powers and NARS worldwide. This programme offers a strong foundation for leveraging advanced science capability in key areas of UK strength and complementarity with CG expertise; deepening engagement with other science powers such as China and Brazil will be an important focus for 2025 onwards. More detailed financial analysis is included in Section F.

Governance Reform: Significant progress has been made in strengthening governance of the new CGIAR integrated partnership model. The global leadership team (which now includes the Executive Managing Director, the Chief Scientist and Director Generals from the CG Centres) developed a comprehensive Risk & Oversight Plan to strengthen integration and coordination on internal audit, external audit, ethics & business conduct and risk management across CG Centres. This plan is an important step forward in improving information sharing and efficiencies across the system. 2025 will focus on delivery of the plan (including the appointment of key assurance executives) and other critical governance processes such as finalisation of the internal rules framework.

The Integrated Partnership Board replaced the System Board, and was expanded with the induction of new members in October 2024. Much remains to be done, but progress is good.

Leveraging UK science: The UK-CGIAR centre awarded 8 grants to support projects running between UK research groups, CGIAR research centres and developing country partners. A full table of the projects underway is in Annex 4. Two of these projects are designed to align with the objectives of the VACS Breeding programme (below), drawing on UK expertise to transform under-utilised neglected crops with high potential (see Box 5).

Box 5: UK-CGIAR science partnerships to accelerate breeding of “orphan” crops
Neglected (“orphan”) crops have valuable traits like climate tolerance or nutritional value, and may be cultivated widely in localised areas, but they have not benefited from modern intensive breeding efforts to remove unfavourable traits. As a result, orphan crops play a major role in food security in localised areas and have high potential, particularly under likely climate scenarios, to have wider food security impacts with modern breeding.

FCDO and UKRI jointly fund two projects to improve the performance of two important orphan crops – Pigeon Pea and Bamara Ground Nut – working with partners in Africa and the CGIAR to generate a new generation of crops that can be adopted widely, building resilience among low-income farming households. UK advanced bioscience in Nottingham and Cambridge Universities is being applied to identify critical traits and translate these into new productive, resilient and nutritious varieties that meet farmer demand.

VACS: The VACS programme aims to accelerate targeted breeding of 7 orphan crops. The programme commenced with legacy USAID funding allocated to CIMMYT. Detailed milestones and targets for FCDO’s committed funds will be agreed by October 2025.

CropTrust: FCDO’s 2024 allocations to the trust supported the maintenance of international crop genebanks operating within the framework of the International Treaty (the instrument that protects planet genetic resources from private acquisition and ensures they are maintained as an international public resource). This is in support of UK objectives to protect critical biodiversity that underpins productive resilient and sustainable agriculture in developing countries and in the UK. UK funding was instrumental in the upgrading of the Africa Rice genebank in Cote D’Ivoire in 2024, enabling it to reach the performance standard needed to access long-term Crop Trust endowment funding through a Long-Term Partnership Agreement.

Major lessons and recommendations for the year ahead

1. Develop targets and milestones for 2025-2030 linked to the current budget, disaggregated within each impact area. Engage with CGIAR colleagues to find the best way to start tracking results on support to people with disabilities. [Global Leadership Team, November 2025]
2. Review outcomes of the portfolio prioritisation exercise and assess balance across the five impact areas. Review the logframe to incorporate 2025-2030 targets and milestones, and to ensure the programme remains impactful and agile in the context of declining budgets and geopolitical shifts. Assess the balance of bilateral and multilateral funding to deliver FCDO diplomatic, scientific and development objectives in a low-ODA world [FCDO, December 2025]
3. Work with others to manage risks associated with the budget decline. Develop a Business Case Addendum to strengthen predictability of UK funding for future years [FCDO, other funders and the Global Leadership Team, December 2025]
4. Conclude effective implementation of the Risk & Oversight Plan and Internal Rules Framework [Global Leadership Team, December 2025]
5. Review areas of UK advanced science capability and assess opportunities for the UK-CGIAR Centre to deepen partnerships that accelerate programme objectives [FCDO, February 2026]

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

No change to the Theory of Change approved in 2023. (See Theory of Change in Annex 2.)

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track to contribute to all expected outcomes. While the multilateral budget has declined, a prioritisation exercise is underway for the 25-30 portfolio to focus on activities with the highest impact potential and for which there is strong beneficiary demand. Moreover, CG innovations are now tracked using the technology readiness level index, ensuring the most promising innovations are prioritised. The new scaling programme for 2025-2030 has been designed to strengthen access to CG innovations and ensure pathways to scale.

The theory of change will remain under review in the coming year to ensure the programme continues to remain impactful and agile in the context of declining budgets and the current geopolitical context.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the outcome, output, theory of change and VfM analysis, there is strong evidence that the programme continues to represent good value for money and delivers on the UK’s development objectives, including climate and nature (providing a significant contribution to ICF results); preventing humanitarian need, global health and growth.

In a low-ODA world, the CGIAR’s multilateral approach to advancing research and development (R&D) solutions provides significant value for money and serves as a crucial pathway to achieving solutions with aligned partners.

## C. DETAILED OUTPUT SCORING

Output Title	Knowledge, evidence, and innovations developed and delivered through CGIAR Research Initiatives to support the five impact areas.
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)		Milestone(s) for this review	Progress
Number of new crop varieties co-developed with national partners registered for release by national authorities that are more productive, nutritious and/or resistant to biotic and abiotic stress		Increase in the number of varieties registered (relative to 250 on average in 2022-2023). / The Type II Report released in July 2025 will enable milestones to be set from next year onwards.	Achieved. Building on past breeding work, 287 new crop varieties were registered for release in 2024. 58% varieties were climate-resilient and 26% were biofortified. Varieties included: Barley, Beans, Cassava, Chickpea, Faba bean, Groundnut, Lentil, Maize, Millet, Potato, Rice, Sorghum, Soybean, Sweet potato, Wheat and Yam. 150 varieties were registered in Africa (18 countries), 94 in Asia (11 countries), 39 in Latin America (11 countries) and 4 in high-income countries.
Number of innovations developed, including products, technologies, services and institutional arrangements with high potential to achieve positive impacts at scale.		Increase in the number of innovations developed. / The Type II Report released in July 2025 will enable milestones to be set from next year onwards.	Achieved. The number of innovations that CGIAR’s Initiatives designed, tested or validated on increased from 477 in 2022 to 1,018 in 2024. 67% were incremental innovations; 24% were radical innovations; 7% were disruptive innovations and 2% were other.[4] 162 reached level 9 and were classified as “proven innovations”
Number of innovations tagged with OECD DAC marker for Gender (Significant or Principle)		Increase in the proportion of innovations with the Gender marker during the initiative period (2022 to 2024)	Achieved. In 2024, 42 percent of outputs (3,107) addressed gender equality as a significant (31 percent) or principal (11 percent) objective — a marked increase from 35 percent of output results in 2022. Gender equality remains the least addressed among CGIAR’s Impact Areas, an important issue to review in the 25-30 portfolio.
	Number of innovations tagged with OECD DAC marker for Climate (Significant or Principle)	Increase in the proportion of innovations with the Climate marker during the initiative period (2022 to 2024)	Achieved. In 2024, 62 percent of CGIAR outputs were tagged as climate “significant” or “principal”. In 2022, 50 percent of CGIAR’s reported output results were classified as climate relevant — demonstrating its growing focus on tackling this pressing global challenge.
	Number of peer-reviewed publications (including open access rates)	Increase in the number of peer-reviewed knowledge products	Achieved. The CGIAR published 770 journal articles in 2024 (compared to 700 in 2023). Of the 4,234 CGIAR knowledge products produced in 2024 93.5% were open access.
[4] Incremental innovations are innovations that already exist and undergo constant, steady progress and improvement. Radical innovations are new and replace existing products, systems, services and/or policies but do not cause or require major reconfiguration of farming, market and/or policy/business models. Disruptive innovations are new and cause or require major reconfiguration of farming, market and/or policy/business models.

Indicator(s)	Milestone(s) for this review	Progress
Genome editing bilateral project: Number of foreign gene free edited lines obtained / evaluated by 2026 / Potato: Develop a PVY-resistant potato variety using genome editing / Develop transgene-free disease-resistant banana / Develop cassava varieties resistant to Cassava Bacterial Blight / Enhance nitrogen remobilization in rice to improve resource efficiency under low-input conditions. / Enhance wheat resistance to rust and powdery mildew by editing key susceptibility genes	By 2025 progress made against WP2 outcomes. / Potato: gene-editing approach validated. / Guide RNAs designed for precise mutations in susceptibility gene / Banana: develop genome edited cultivars of relevant varieties. / Cassava: MeSWEET resistance gene promoters edited in cassava / Rice: genome edited plants evaluated. / Wheat: editing underway targeting two key fungal resistance genes (Lr67 and MLO)	Significant progress towards all output and on track to complete. / Potato. Off track: Protocols for protoplast isolation and culture developed. Calli generation has delayed this work. / Banana: On track 100 genome-edited events in banana cultivar Sukali Ndiizi. PiggyBac excision was applied to remove transgenes. / Cassava: On track edited lines / ready for crossing and field validation to assess resistance levels. / Rice: On track Laboratory testing of performance underway with good results. / Wheat: On track 12 lines with Lr67 gene edits generated. MLO edited plants generated and under selection.
Accelerated development of under-utilized crops (VACS) addressing critical barriers to productivity and utilisation through targeted breeding. / Effective efficient breeding pipelines established for VACS crops able to deliver demand driven improved varieties of priority VACS crops / New improved varieties that meet target product profiles being delivered and are available and accessible for end users	Milestones and targets set by October 2025.	In progress. FCDO funding to VACS was delayed due to uncertainty following the withdrawal of USAID support (financial and technical) and the uncertainty regarding UK ODA. Funding will begin in 2025. Milestones and targets for UK funding are being agreed with CIMMYT and finalised in October.
Sustained long term improvements in the conservation and management of the International Treaty Article 7 gene banks; protecting agro-biodiversity and making this available globally.	Initiate a review of the operational efficiency and performance of CropTrust.	Achieved: An external review is underway which will generate evidence on the performance management and governance of the CropTrust as well as evidence on the status and operations of the international genebanks.

Briefly describe the output’s activities and provide supporting narrative for the score.

CGIAR Research Initiatives: In 2024, FCDO allocated funding to specific research initiatives selected on the basis of their relevance to FCDO priorities and quality of science. A full list of allocations is set out in Annex 1. The CGIAR reported significant delivery of research outputs across these initiatives through the CGIAR Results Dashboard and the annual technical reports.

Selected results achieved by the pooled portfolio are captured in the table above, including number of new crop varieties registered, number of innovations developed overall (and with gender and climate specific objectives), and number of publications. The table also highlights progress made on the genome editing bilateral project, VACS initiative and investment in the Crop Trust.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Additional indicators were included in this output to track the genome editing project and the proportion of innovations under development to tackle climate change.

The VACS project support was revised following the withdrawal of USAID technical support and leadership for VACS, and VACS crop breeding.

Progress on recommendations from the previous AR (if completed)

N/A.

Lessons learned this year:
The 33 CGIAR Initiatives have achieved significant results in three years, including a strengthened focus on uptake and working in partnership. The Type II report was a decisive step forward in terms of measuring results; however, the complexity of the portfolio was also apparent in this exercise. The simplified structure of the 25-30 portfolio and upfront investment in setting targets and milestones will improve efficiency going forward.

Recommendations for the year ahead
1. Develop targets and milestones for 2025-2030 linked to the current budget, disaggregated within each impact area. Engage with CGIAR colleagues to find the best way to start tracking results on support to people with disabilities. [Global Leadership Team, November 2025]
2. Review outcomes of the portfolio prioritisation exercise and assess balance across the five impact areas. Review the logframe to incorporate 2025-2030 targets and milestones, and to ensure the programme remains impactful and agile in the context of declining budgets and geopolitical shifts. Assess the balance of bilateral and multilateral funding to deliver FCDO diplomatic, scientific and development objectives in a low-ODA world [FCDO, December 2025]
3. Work with others to manage risks associated with the budget decline. Develop a Business Case Addendum to strengthen predictability of UK funding for future years [FCDO, other funders and the Global Leadership Team, December 2025]

Output Title	CGIAR operational effectiveness and efficiency of CGIAR improved through progressive governance reforms and through enhanced management of research and innovation.
Output number:		2	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Strengthened oversight and funding mechanisms driving prioritisation of research to ensure that the CGIAR resources are focused on major threats and opportunities for R&D	Multi-step prioritisation process initiated / Approval of the new portfolio	Achieved. The design process included an in-depth prioritisation exercise, including assessment of need, comparative advantage analysis, and demand assessment and engagement with key partners. Further prioritisation will be needed for 2026. / The new portfolio concept was approved by the System Council in December 2024, subject to an ISDC review of the inception reports in summer 2025 (currently on track).
Improved management of research using results-based management and effective evaluation	Portfolio 22-24 reports delivered meeting funder demand.	Achieved. All technical reports were completed by July 2025: / - Type 1 reports (Annual initiative reports) / - Type 2 report (CGIAR Impacts 2022-24). The is the first time that CGIAR has produced a comprehensive synthesis of CGIAR’s progress toward impact including the pooled-funded portfolio, bilateral projects and the impacts of prior investments. / - Type 3 report – Portfolio Narrative (a synthesis of Portfolio coherence, synergies and collective progress across initiatives, impact platforms and science groups).
Strengthened governance arrangements across CGIAR balancing centre priorities with system-wide risk and programme management framework	Risk & Oversight Plan development and approval	Achieved. A comprehensive Risk & Oversight Plan was developed to strengthen integration and coordination on internal audit, external audit, ethics & business conduct and risk management across CG Centres. This plan is an important step forward in improving information sharing and efficiencies across the system. 2025 will focus on delivery of the plan (including the appointment of key assurance executives) and other critical governance processes such as finalisation of the internal rules framework.
Improved overhead costs for the CGIAR system	Reduction in management and business function costs to reflect the integrated partnership model	Achieved. Following a first wave of cuts initiated in the revised 2024 budget, and as a result of a thorough review, the structure and costs of business functions have been further streamlined allowing, in 2025, the corresponding budget to be permanently reduced by another 20%. For the first time in 5 years since 2019, business functions were fully funded by the 2% CSP without further recourse to Window 1 funds. The reductions highlight Management's commitment to cost control, efficiency, and an operational structure prepared to deliver integration and coordination in the integrated partnership model

Governance Reform: Significant progress has been made in strengthening governance of the new CGIAR integrated partnership model, including appointment of the Integrated Partnership Board and development of the Risk & Oversight Plan to strengthen integration and coordination on internal audit, external audit, ethics & business conduct and risk management across CG Centres. 2025 will focus on delivery of the plan (including the appointment of key assurance executives) and other critical governance processes such as finalisation of the internal rules framework. Much remains to be done, but progress is good.

Lesley Torrance of James Hutton Institute was appointed as the new chair of the Independent Science for Development Council (the ISDC). The ISDC is a panel of senior academics and development specialists with appropriate expertise and disciplinary range whose role is to advise CGIAR System Council on investment priorities.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed),
Integrated Governance Review recommendations have progressed. Development of the Risk and Oversight Plan highlighted above is the next stage.

Lessons learned this year
A detailed approach to integration and coordination is critical to manage risks and improve efficiencies in an integrated partnership model.

Recommendations for the year ahead
Conclude effective implementation of the Risk & Oversight Plan and Internal Rules Framework [Global Leadership Team, December 2025]

Output Title	Enhanced partnerships with UK Science and technical support for FCDO posts
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Number of research outputs from new partnerships established with UK scientists and CGIAR initiatives targeting priority R&D Delivery	6 partnership underway, funding research projects.	Achieved: 7 projects underway. Co-funding from UKRI secured for three of these (See Annex 4 for further details).
Number of FCDO requests for technical support supported with CGIAR knowledge and evidence	Pilot expertise offer to FCDO posts to inform wider drawdown offer	Achieved. The “Ask Food” pilot tested a technical support offer to 3 FCDO posts (Ethiopia, Uganda and Kenya) to inform design of a long-term partnership model with selected posts next year. / IFPRI analysis and technical advice also had wide reach across FCDO through the seminar series, L&D sessions and selected policy research requests.

UK-CGIAR centre: The centre has allocated all available funding this year and awarded 8 grants to research collaborations between UK research groups, CGIAR research centres and developing country partners. A full table of the 7 projects currently underway is in Annex 4. Two of these projects are designed to align with the objectives of the VACS Breeding programme (below), drawing on UK expertise to transform under-utilised neglected crops with high potential. New work is also underway to identify possible opportunities for new research collaborations aligned with UK strategic priorities and advanced science capability, including in AI and engineering biology.

A UK-CGIAR Centre Science Forum in 2025 showcased the centre’s work and generated valuable lessons for future centre operations. The centre has enabled FCDO to navigate existing and new high-potential partnerships with the CGIAR. Several international partners have approached the UK to learn how the centre operates and seeking to replicate the model to leverage national expertise to accelerate global solutions in the context of ODA reductions.

CGIAR Technical Support to FCDO: Recognising the breadth and depth of CGIAR expertise with direct relevance to FCDO’s development and diplomatic priorities, the programme-funded secondee to the CGIAR (appointed in early 2024) regularly brokered linkages between CGIAR scientists and FCDO policy teams and Posts. An MoU with IFPRI provided a knowledge and evidence service for FCDO to draw on, including L&D sessions, targeted seminars with wide attendance, and a call-down component to respond to short term requests from FCDO for support in IFPRI’s core area of expertise (see annex 6).

“Ask Food” was also designed to provide a wider shopfront for food and agriculture expertise. The Ask Food Lead was appointed in Autumn 2024 and is funded through this programme. The Ask Food Pilot tested approaches to evidence uptake by Posts. Pilot countries (Ethiopia, Kenya and Uganda) were selected based on need (poverty, climate vulnerability, agriculture sector prominence), IFPRI capability in country, and post demand. IFPRI provided a snapshot analysis of food security in country and political economy analysis followed by a set of evidence-based policy and programme opportunities. The pilot highlighted the value of senior buy-in and the need for a clear VFM case to invest in food and agriculture interventions versus other sectors. The pilot also informed design of a refined 'model' for future analyses and drawdown support, in particular for private sector and climate and nature programmes. Next year, IFPRI drawdown support will adopt a partnership model with priority countries, enabling greater impact and lower transaction cost delivery. This pilot has also informed a new joined-up expertise offer on food and agriculture across FCDO: Next steps will be to consult on and support development of a cross-team expertise facility and clear processes to link policy and delivery with evidence and innovation.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed),
Ask Food was designed and piloted in early 2025 to response to FCDO demand for expertise.

Lessons learned this year
UK partnerships with CGIAR scientists are wide-reaching. The UK-CGIAR Centre is commencing a more extensive mapping exercise to capture existing relationships that were not revealed in the bibliometric analysis.

Recommendations for the year ahead
Review areas of UK advanced science capability and assess opportunities for the UK-CGIAR Centre to deepen partnerships that accelerate programme objectives [FCDO, February 2026]
## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

The VFM case for this programme has not materially changed since the Business Case stage in 2023; the Business Case sets out numerous examples of CGIAR innovation leading to enhanced crop yields, improved nutrition, higher incomes for farmers, and reductions in carbon emissions, among many other benefits.

5 Es	Summary of performance
Economy	CGIAR centre overhead of 17% (average across 11 centres) plus 2% additional funding for the system entities represents good value for money. The 17 + 2% is levied against all funding and the recovery rate of these overheads is good, approaching 90%. As set out above, reviews have found a core overhead cost for research grant management of between 10-20% with additional costs embedded within grants themselves. The cost of managing grants within CGIAR is broadly comparable with the costs levied through our bilateral grants, and if embedded costs are considered, then it is lower. / The Cost Sharing Percentage (CSP) allows the funders to equitably share the non-research cost burden (that is the cost associated with the running of the System Organisation). Currently the CSP is set at a rate of 2% for all CGIAR funding representing good VFM. / Science Management costs have been reduced by 46% since 2024 - these represent administrative costs linked to the delivery of CGIAR programmes. / Business Functions costs reduced by 38% since 2024 – these encompass the Office of the Executive Managing Director (EMD), and Deputy EMD and associated teams including Business Operations and Finance, Communications and Advocacy, Donor Relations & Business Development, Legal Affairs, Strategic Planning & Risk, Gender Diversity and Inclusion, and People and Culture.
Efficiency	This programme provides around 5% of all CGIAR funding (2024), and around 12% of pooled funding, but we leverage our investment to directly influence the governance and management of CGIAR in line with FCDO’s multilateral reform agenda. The UK has been able to influence CGIAR in the past, to bring about significant restructuring and reform and we retain a leading role in shaping the future direction of international agriculture R&D, building UK leadership within CGIAR and strengthening links with UK organisations. / Management and administrative costs are proportionately low. By using CGIAR fund we can limit our own management costs and target our technical inputs to driving the performance of CGIAR as whole, rather than managing small-scale, short-term grants. / An independent bibliometric analysis of CGIAR publications from 2024 shows the CGIAR produces more high-quality peer-reviewed publications than other comparable organisations.
Effectiveness	This programme is highly effective. Refer to Box 2 (pg. 3) for examples related to the Effectiveness criteria.
Equity	This programme is compliant with the Gender Equality Act. Gender results are tracked as a key indicator under Output 1. The Gender Impact Platform was developed to increase the quality and scope of gender research in the initiatives; the Gender Accelerator will build on this in the 25-30 portfolio. / More than 40% of CGIAR programming is measured as having a principal or significant gender focus.
Cost-effectiveness	The FCDO Best Buys analysis rated CGIAR crops R&D as a ‘mega buy’, the best rating for VfM possible. Evidence generated through previous iterations of this programme strengthens the case that CGIAR is among the investments with the greatest rates of return for FCDO. / Over an approximately 20-year period, CGIAR’s rice breeding efforts generated benefit:cost ratios of 115:1 in Bangladesh and 7:1 in the Philippines. CGIAR contributed to Bangladeshi rice yields more than doubling in the last four decades, increasing from1.75 tons per hectare to 4.57 tons per hectare.[5]
[5] Returns to Research Investments in Rice Varietal Development: Evidence from the Philippines and Bangladesh. Global Food Security 33, 100646

Assessment of whether the programme continues to represent value for money

The programme continues to produce robust VFM evidence for continued investment in the CGIAR research system. CGIAR research, as outlined above, present solid rates of return on investment, and our seat on the System Council allows the UK to influence the strategic direction of the CGIAR as a whole for a relatively modest contribution in cash terms, compared to the overall CGIAR budget. We assess the VFM proposition set out in the Business Case to still be valid, with the programme continuing to represent very strong value for money.

E: RISK

Overview of risk management

CGIAR has a comprehensive Risk Management Framework and a Risk Appetite Statement that balances reputational and operational risks, with the need to drive transformative innovation through a balanced portfolio of research and development and which allows for both high and low risk R&D. In addition, each CGIAR centre has risk frameworks appropriate for their contexts.

To effectively support the new integrated partnership model of the OneCGIAR, the ‘Combined Assurance Model’ has been devised (here). This new model ensures that each member of the Integrated Partnership has appropriate assurance mechanisms in place, while also enabling a clear chain of accountability across the entire partnership. This model allows governance bodies, such as the System Council and the Integrated Partnership Board, to maintain a unified view of risk and assurance across all entities. It also promotes consistent standards, coordinated oversight, and continuous improvement throughout the organisation.

The new model also includes appointment of an Integrated Partnership Risk Management Executive to oversee risk management and internal control functions. This role is responsible for developing a global risk framework, ensuring consistent practices across the partnership, and reporting key risks to the Integrated Partnership Board’s Audit, Finance and Risk Committee (IPB-AFRC). The executive also leads training and capacity-building efforts to strengthen risk management across all centres.

The CGIAR programme risk profile for 2025 remains largely consistent with the previous year, with the overall risk level remaining at Moderate. Some minor changes have been made to existing risks, with two new risks added (one moderate and one minor).

Declining ODA levels among key donors (including the UK) leading to reduced budgets for the CGIAR is assessed as a moderate risk. CGIAR is reviewing the level of ambition in their portfolio to adapt to this changing outlook, with activities being prioritised to fit within a likely smaller baseline budget.

A minor risk has been added on internal governance in the CGIAR, around the potential for issues at Centre level to not be escalated and managed appropriately within the broader One CGIAR structure. This is being addressed through the implementation of the Integrated Partnership Risk & Oversight Plan, scheduled to be completed by the end of 2025.

The 2025 Risk Register is included as Annex 3.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The programme is on track and achieving its milestones across each output. FCDO contributed £26,000,000 to 2024 portfolio activities via Window 1 (Designated) funding.

All FCDO funding was directed towards the highest-performing and most relevant (to UK/FCDO priorities) CGIAR Research Initiatives and Platforms, following a predefined allocation formula. This formula uses an internal scoring system that evaluates relevance, performance, and the funding shortfall relative to the agreed annual programme budgets, ensuring no Initiative or Platform receives excess funding. The allocation also includes a 2% cost-sharing contribution to support CGIAR System Actions and Entities, along with an indirect cost recovery rate – ranging from 9% to 19% depending on the centre – to cover overheads at the research centres.

This programme also funds several projects outside the CGIAR Research Initiatives:

- ASEAN Innovate for Food Regional Program with the International Rice Research Institute (IRRI): £666,666 funding provided in 2024/25.
- Accelerating Crop Improvement Through Genome Editing project with IRRI: £666,666 in 2024/25.
- Crop Trust Endowment Fund: £4 million in 2024/25.
- IFPRI Policy Advice & Learning Seminars: £136k in 2024/25.
Additionally, the programme budget funds:

- The secondment of an FCDO Adviser into the CGIAR System Office, ending December 2025.
- Ask Food programme funded post to strengthen technical support for posts, ongoing contract.
Overview of CGIAR finances

The overview of CGIAR System financing illustrated below is extracted from the CGIAR Financial Dashboard. In 2024, CGIAR received revenue of US $1.04bn. Figure 1 shows a comparison of 2024 and 2023 funding and the breakdown by funding mechanism; overall funding to the CGIAR rose by 19.5% from 2023 to 2024.

Trend analysis of overall CGIAR System revenue since 2011 is shown in Figure 2, showing funding increases in cash terms in each of the last five years. As noted above, this trend is likely to reverse in the short-to-medium term as donors reduce funding.

Figure 3 shows the main categories of CGIAR expenditure. 2024 expenses increased to $1.04bn from $859m, in line with the 21% increase in funding received, and the ratio of spend on research/collaboration vs overheads remained stable and within acceptable limits.

Figure 1. CGIAR revenue by source of funding, 2024 and 2023

2024	2023

Figure 2. CGIAR System revenue by source of funding, 2011–2024

Figure 3. Expenditure by main category

2024	2023

Overview of UK-CGIAR Centre finances

FCDO funds CABI to run the Secretariat function of the UK-CGIAR Centre: the Secretariat plays the central role in coordinating and delivering the Centre’s objectives by identifying research opportunities, managing partnerships, overseeing governance and communications, and ensuring responsive support to FCDO and UK research priorities. It leads the commissioning process, monitors project performance, and promotes the Centre’s work through targeted outreach and knowledge sharing. Funding to the Secretariat is non-ODA funding of around £650,000 per financial year, which is disbursed via a separate programme (301601), but managed & reported under this programme.

Funding to UK institutions is paid via CABI, while funding to overseas institutions is paid via Bioversity International, which then disburses funding to the project partners.

2024/25 was the second year of the Centre’s Round 1 projects (refer to Output 3 for project details). As Secretariat for the Centre, CABI oversees the budget management of the projects - spend so far has been in line with forecasts. £2.2m is still be disbursed in 25/26 towards the Round 1 projects. 25/26 is the first year of the Round 2 projects (Output 3), which run for the next three financial years. Annex 5 shows a breakdown of the Centre’s finances by year & project.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The Annual Review was carried out by the programme PRO, Deputy Programme Manager and Lead Advisers. Throughout the year the FCDO team was in regular contact with CGIAR and attended two in-person CGIAR System Council meetings in Berlin (SC21, December 2024) and Penang (SC22, June 2025), in addition to a number of ad-hoc System Council calls and drop-in sessions. FCDO also chaired the CGIAR Strategy, Impact Monitoring and Evaluation Committee and has now joined the Nominations Committee, which met multiple times during the year. The Annual Review team drew upon the following documents and evidence resources.

In relation to CGIAR research, there has been little research on disability and agri-food systems or on how CGIAR innovations could be targeted at people with disabilities. There are very few CGIAR research publications that address disability. Furthermore, there is no formal reporting on research on disability.  All CGIAR initiatives and science programmes report on how the research address the Gender Equality, Youth and Social Inclusion Impact Area, but this is not disaggregated so there is no data specifically on disability. Recommendation no. 1 in this annual review states this will be reviewed with CGIAR colleagues to determine the best way to gather the relevant data from CGIAR projects.

CGIAR Financial Report Dashboard
- CGIAR 2024 Annual Report (draft version, not yet published)
- Initiative and Platform Annual Reports
- CGIAR Impact Report 2022 – 2024
- CGIAR System Organisation Charter
CGIAR 2030 Research and Innovation Strategy: Transforming food, land, and water systems in a climate crisis
Documents & minutes from System Council 21 and 22, and the SC Decision Register.
CGIAR Investment Prospectus 2022–2024
- CGIAR Business Case 2023– 2026
- The UK-CGIAR Centre - CABI.org

Date of last narrative financial report	July 2025 / (per CGIAR Financial Report Dashboard)	Date of last audited annual statement	CGIAR – July 2024 / CIP – June 2024 / ILRI – June 2025 / IITA – June 2025 / AfricaRice – June 2025 / ICARDA – June 2025 / ICRISAT – May 2025 / IFPRI – June 2024 / CIMMYT – April 2024 / CIAT – June 2025 / Bioversity – June 2025 / IRRI – June 2025 / IWMI – June 2025 / World Fish – July 2025 / https://www.cgiar.org/food-security-impact/finance-reports/

Annex 1 – 2024 allocations to Research Initiatives
Science Group	Initiative	USD Budget	UK Allocation
Resilient Agri-Food Systems	Livestock and Climate	28,100,000	1,405,000
	Sustainable Animal Productivity	31,100,000	1,814,167
	One Health	19,400,000	0
	Excellence in Agronomy	29,400,000	1,715,000
	Plant Health	15,100,000	0
	Mixed Farming Systems	19,000,000	1,108,333
	Nature-Positive Solutions	11,900,000	694,167
	Resilient Cities (UPU)	11,900,000	0
	Aquatic Foods	16,600,000	0
	TOTAL	182,500,000	6,736,667
Systems Transformation	NEXUS Gains	16,200,000	675,000
	Agroecology	16,500,000	687,500
	Climate Resilience	24,600,000	1,845,000
	Rethinking Food Markets	13,600,000	519,333
	Sustainable Healthy Diets	15,900,000	795,000
	Natinal Policies & Strategies	12,900,000	0
	Low-Emission Food Systems (Mitigate+)	15,900,000	795,000
	Gender Equality (HER+)	11,700,000	877,500
	Digital Innovation	14,100,000	0
	Foresight	10,900,000	545,000
	Fruits and Vegetable	11,200,000	840,000
	Fragility, Conflict, Migration	9,700,000	566,667
	TOTAL	173,200,000	8,146,000
Genetic Innovations	Genebank	23,800,000	991,667
	Accelerated Breeding	48,700,000	2,029,167
	Breeding Resources	40,900,000	1,654,000
	Seed Equal	44,700,000	1,862,500
	Market Intelligence	18,600,000	775,000

	TOTAL	176,700,000	7,312,334
Regions	AgriLAC Resiliente	18,500,000	0
	Transforming Agrifood-WCA	18,500,000	0
	Fragility to Resillience in CWANA	18,500,000	925,000
	Diversification in ESA	27,300,000	1,365,000
	Asian Mega-Deltas	18,500,000	0
	Transforming Agrifood -South Asia	27,000,000	0
	TOTAL	128,300,000	2,290,000
Platforms	Gender	10,700,000	535,000
	Climate	4,900,000	245,000
	Environment	4,900,000	245,000
	Nutrition	4,900,000	245,000
	Poverty reduction	4,900,000	245,000
	TOTAL	30,300,000	1,515,000
Total to Window 1 Designated to Initiatives		691,000,000	26,000,001

Annex 2 – Theory of Change

Annex 3. Risk Register

Risk Description	Mitigation Strategy	Likelihood	Residual Risk
Low predictability and decline in ODA by many funders undermines programme stability and research delivery.	The financial system with Designated W1, W2 and W3 funding increases flexibility and provides assurance that funding will be available. However, the use of annual allocations released late in the year and the decline in ODA from many funders will continue hinder CGIAR financial management. The level of ambition for the new portfolio is being reviewed and activities are being prioritised to fit within a smaller baseline budget.	Possible	Moderate
Donors continue to use bilateral research, undermining the new One CGIAR management arrangements. Changes to CGIAR funding and reduction in overall predictability of funding undermines the coherence of the CGIAR	The new integrated suite of research, funded fully and designed using the agreed 13 Eschborne Principles, provide the assurance that large bilateral donors need in order to increasingly pool funding to the Initiatives. The development of agreed and harmonised reporting frameworks designed to meet donor requirements, and the development of the PRMF builds confidence in the CGIAR systems.	Possible	Moderate
The evaluation function (secretariat, policy and framework) fails to deliver robust evaluation of research.	SIMEC oversees the delivery of evaluation a cross CGIAR. The actions taken following the 2019 MOPAN review have largely been addressed. The System Council will continue to track progress through SIMEC.	Possible	Moderate
The SMO fails to establish the results-based management framework.	We will work closely with the System Office, and with lead donors to ensure the PRMF and reporting system meets demand. We will continue to support this with a secondee into the System Office Programme Performance Unit	Unlikely	Minor
UK public opinion opposes international development funding generally and/or funding of agricultural research through international organisations	This funding follows a successful previous phase of funding which delivered excellent results. This provides strong communications material to raise awareness of the importance of agricultural research, not only for developing countries, but also the UK national interest. The programme will continue to deliver a pipeline of positive stories.	Unlikely	Minor
Public opinion in the target countries opposes specific technologies and products delivered by CGIAR	CGIAR has released almost 5000 new conventional crop varieties in the past 10 years. The CGIAR is linked strongly into national research organisation in target countries and is responsive to national demand, ensuring that demand is assessed and met. Although novel genetic technology is funded, it is only deployed where national policy support this.	Unlikely	Minor
A lack of sensitivity to important gender dimensions in programme design limits the programme’s impact and potentially exacerbates gender inequalities, as well as those surrounding other marginalised groups.	Gender issues are firmly integrated into the programme, and FCDO will continue to monitor the performance and progress against gender targets, working with other donors. The new portfolio includes a gender accelerator to support the portfolio in maximising impact on gender, youth and inclusion. CGIAR’s own G,D and I reporting allows us to track progress within CGIAR.	Unlikely	Minor
CGIAR is locked into a programme of research and unable to respond to new priorities.	The CGIAR has adaptive management and stage-gating systems across the portfolio. SIMEC oversees the strategy and foresight work of the ISDC which identifies new priorities. CGIAR has demonstrated an impressive ability to pivot toward new issues (Covid -19, Russia’s invasion of Ukraine) meeting FCDO and global demand for new research outputs	Unlikely	Minor
Financial mismanagement or fraud on the part of the Centres and System Organisation is not identified or to response is inadequate or ineffective.	As part of programme management and annual review processes, FCDO will review audited accounts annually. The Annual Review will also consider financial management issues. In case of any mismanagement/fraud, FCDO procedures would be followed, and issues will be escalated where necessary to the Board of the Centre involved. In the worst case, FCDO would suspend funding. Audit arrangements across the CGIAR are overseen by the independent Audit and Oversight Committee (System Council) and the Audit Finance and Risk Committee (System Board) which provides donor assurance of compliance with best practice.	Unlikely	Minor
CGIAR fails to establish effective partnerships drawing on international research expertise	There are over 200 partnerships already established between the CGIAR and Advanced Research Institutions (ARIs). FCDO have held back funding specifically to build partnerships between leading UK centres of academic excellence and CGIAR research initiatives and centres	Unlikely	Minor
The key reputational risk for FCDO is that any of the above risks are realised without appropriate measures in place to mitigate the impact.	The sections above describe the mitigation measures FCDO has in place for each category of risk, which reduce the likelihood and residual impact of each risk to an acceptable level within FCDO’s risk appetite. This programme is based on an earlier successful programme of funding, and FCDO will build on the positive, strategic working relationships already established to continue to closely monitor their performance.	Unlikely	Minor
Lack of competition in research commissioning results in poor quality research being funded.	ISDC-led peer review of all new research is the main means for independent quality control. This has involved external peer-review of the Initiatives. In addition the integrated research management system will assess research performance. FCDO selects research based on our own assessment of the quality, relevance and potential impact of research.	Possible	Minor
CGIAR carries out poor quality research not relevant to developing country demand	CGIAR has a strong track record in generating high quality research outputs and have robust governance mechanisms and scientific oversight. ISDC oversight and review provides independent assessment of development relevance. The PRMF provide a core set of performance indicators that will be tracked annually by FCDO.	Unlikely	Minor
Exogenous shocks from conflict, climate change or other natural disasters have a negative impact on delivery or uptake of the research outputs	CGIAR as a whole works in over 100 countries and all FCDO funded programme work in multiple locations. This means that, while the risk of individual research Initiatives being affected by exogenous shocks remains, the risk of this affecting the programme as a whole is minimal.	Unlikely	Minor

Annex 4: Projects Commissioned through the UK-CGIAR Cente for Science Collaboration

Round 1 Projects
Research Portfolio	Project Title	CGIAR Lead Centre	Other CGIAR partners	UK Lead	Other UK partners	NARS	Intervention location
Research Area 1: Confronting climate change and environmental degradation through sustainable crop management and climate-smart agronomic practices	iSPARK - innovation in sustainbility, policy, adaptation and resilience in Kenya	CIAT	IITA	University of Leeds		KALRO	Kenya
Research Area 2: Crop Genetic Improvement for future climate resilience	Leveraging genetic innovations for accelerated breeding of climate resilient and nutritious crops	ICARDA	CIMMYT	John Innes Centre	University of East Anglia	KALRO (Kenya), ARC (Egypt), QAU (Pakistan), AGIS - Shenzhen	Kenya, Egypt Pakistan, China
Research Area 3: Enhancing Nutrition	Fruits and Vegetables for Sustainable Healthy Diets (FRESH-EN UP)	IFPRI		LSHTM		Sokoine University of Agriculture (SUA), Tanzania	Tanzania
Research Area 4: Livestock improvement, animal health, nutrition and welfare	Defining new phenotypes for forage and crop by-products improvement based on rumen function and greenhouse gas (GHG) emissions.	ILRI		SRUC			Relationship development - UK - Ethiopia - Kenya

Round 2 projects
Programme Portfolio	Project Title	CGIAR Lead Centre	Other CGIAR partners	UK Lead	Other UK partners	NARS	Intervention location
Research Area 1: Confronting climate change through sustainable crop management and climate-smart agronomic practices	A Climate-Smart Agronomy Vision for Adapted Crops and Soils (AgVACS). Supporting smallholder farmer decision making through participatory experimental-modelling networks in West Africa	IITA	ABC	Rothamsted	University of Nottingham, University of Warwick	University Kano Savanna Agricultural Research Institute Tamale, Ghana	Ghana and Nigeria
Research Area 2: Crop Genetic Improvement for future climate resilience	Deciphering the root-soil interface to develop efficient N2 fixing, climate-smart pigeon pea cultivars with improved yields	ICRISAT	CIMMYT	Nottingham		KALRO, Agricultural Research Institute of Mozambique (IIAM), Tanzania Agricultural Research Institute, Chitedze Agricultural Research Station, Malawi, Indian Institute of pulses research (IIPR), University of Agricultural Sciences (India), Acharya Ranga Agricultural University (India)
Research Area 3: Enhancing Nutrition	Genetic Improvement of Bambara Groundnut (Vigna subterranea) for Future Nutrition and Climate Resilience	IITA	ICRISAT	Cambridge	NIAB	University of KwaZulu-Natal (KZN), University of Nottingham
Research Area 4: Livestock improvement, animal health, nutrition and welfare	Defining new phenotypes for forage and crop by-products improvement based on rumen function and greenhouse gas (GHG) emissions.	ILRI		SRUC		Ethiopia Institute of Agricultural Research (EIAR)

Annex 5: UK-CGIAR Centre budget overview

Secretariat (non-ODA)		23/24	24/25	25/26	26/27	27/28
To CABI		465,277	729,598	650,000	650,000	650,000
Status		Paid	Paid

Round 1 Projects (2023-26)		Y1 23/24	Y2 24/25	Y3 25/26
Through CGIAR-Designated Centre (ABC)		942,208	1,372,460	1,421,514
Through Payment Agent (CABI)		632,000	911,112	826,976
Total		1,574,208	2,283,572	2,248,490
Status		Paid	Paid		Inactive	Inactive

Round 2 Projects (2025-28)				Y1 25/26	Y2 26/27	W3 27/28
Through CGIAR-Designated Centre (ABC)				644,212	574,279	557,588
Through Payment Agent (CABI)				BBSRC funded	BBSRC funded	BBSRC funded
Total				644,212	574,279	557,588
Status		Inactive	Inactive	Paid

Annex 6: Outputs from MoU with IFPRI

FCDO has a MoU with IFPRI for IFPRI to provide FCDO with expert analysis on food security and agricultural policy, through seminars, policy research and learning and development events.

Seminar Series

Seminar 1: Acute food insecurity trends and drivers – evidence from the 2024 Global Report on Food Crises (May 2024)

Seminar 2: Impact of Multiple Shocks on Food Security in Low Income Countries (June 2024)

Seminar 3: Agricultural Transformation, Growth and Poverty Reduction (October 2024)

Seminar 4: Risks to Rice Production in Asia and Impact on the Global Rice Market (December 2024)

Seminar 5: The Impact of US tariffs on Developing Countries (March 2025)

Seminar 6: The Impact of US ODA Cuts on Africa, with a Case Study from Malawi (April 2025)

Commissioned Studies

Global Rice Market: Current Outlook and Future Prospects (October 2024)

Agricultural Transformation, Growth and Poverty Reduction (January 2025)

Ask Food Pilot Country Analyses and briefings for SLT at Post in Ethiopia (December 2024), Uganda (May, 2025) and Kenya (June, 2025)

UK Benefits of Investing in CGIAR (June 2025)

Learning and Development Sessions

Session 1: Understanding Agricultural Policy Support Measures (June 2024)

Session 2: Transmission of global price shocks to domestic prices and perverse effects of ‘insulation policies’ (September 2024)