## Annual Review

Title: Low Carbon Development Initiative (LCDI) Phase 2
Programme Value £ (full life): £ 27,200,000		Review date: October 2025
Programme Code: [AMP ID#] / 300675	AMP start date: / 04/10/2021	AMP end date: / 31/07/2027

Summary of Programme Performance
Year	2021- 2022	2022-2023	2023-2024	2024-2025
Overall Output Score	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-300675 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	S30067520.pdf

A. SUMMARY AND OVERVIEW
Description of programme
The Low Carbon Development Initiative is anchored in the principle that economic growth and environmental sustainability must advance together, not in opposition. As the Stern Review underlined, climate action is an economic necessity; failure to reduce greenhouse gas (GHG) emissions undermines long-term growth, fiscal stability, and human welfare, while well-designed low-carbon policies create efficiencies, innovation, and resilience. In Indonesia, this requires shifting planning and financing systems so that every rupiah of investment drives both growth and emissions reduction. The Low Carbon Development Initiative Phase 2 (LCDI2) therefore was designed not as a climate “add-on” but as a structural economic reform programme—embedding low-carbon pathways in national and provincial planning, strengthening budgetary incentives, and enabling innovation, technology and social inclusion.
LCDI2 is the UK Government’s flagship climate partnership programme with Indonesia. It was initiated at the request of the Ministry of National Development Planning (Bappenas) and is governed through a Steering Committee comprising of FCDO, Bappenas, and the Ministry of Home Affairs (MoHA). Running from 2021 to 2027 with a total budget of £27.2 million under UK International Climate Finance (ICF), LCDI2 supports Indonesia’s commitment to its green and sustainable growth, including ambitions towards its Nationally Determined Contribution (NDC) under the Paris Agreement and its ambition to reach net zero emissions by 2060 or sooner. It does this by helping Indonesia to decouple economic growth from greenhouse gas emissions and environmental degradation, while ensuring that growth is inclusive, resilient, and socially just.
The programme focuses on four complementary areas of work (“workstreams”)
1. National policy and planning — supporting integration of LCD pathways into the long-term development plan (RPJPN 2025–2045), the medium-term development plan (RPJMN 2025–2029), sectoral strategies, and fiscal frameworks.
2. Subnational planning and implementation —assisting provinces to prepare Regional Low-Carbon Development and Climate Resilience Plans (RPRKBID) as a technical and analytical foundation for integrating low-carbon pathways into their Regional Mid-Term Development Plans (RPJMDs).
3. Stakeholder engagement — building coalitions among parliament, civil society, academia, media, private sector, and interfaith groups to sustain political commitment and drive legislative or budgetary action.
4. Innovation and Technology Fund (ITF) — piloting scalable low-carbon solutions through the Indonesia Environment Fund (BPDLH), combining technology adoption with inclusive development.
The programme is delivered by Oxford Policy Management (OPML) which provides programme management, technical leadership, and oversight of sub-partners including  the Institute for Development of Economics and Finance (INDEF),  International Council for Local Environmental Initiatives (ICLEI), Dala Institute, Prakarsa, Indonesia Business Council for Sustainable Development (IBCSD),  International NGO Forum on Indonesian Development (INFID), and the Carbon Trust. OPML holds accountability for overall delivery, quality assurance, and coherence across workstreams. The programme has a Monitoring, Evaluation and Learning (MEL) partner, delivered by NIRAS. NIRAS provides an independent assurance function, including oversight through outcome harvesting, VfM assessment, process evaluation, and quarterly reviews. While OPML and NIRAS have generally coordinated effectively with Bappenas and provinces, role clarity and timely use of MEL findings remain areas for further strengthening.
Response to Last Year’s Annual Review
In response to the recommendations of the 2024 Annual Review, the programme has taken steps to strengthen its strategic clarity, responsiveness, and pace of delivery, although in practice these have been applied inconsistently and are ongoing to fully embed the changes. These were:
No	2024 Annual Review Recommendations	Program Response and Progress 2024-2025
1	Consensus Building: Achieving consensus on the workplan and logframe took more time than expected, due to differing stakeholder views and implementer’s capacity constraints. It is recommended that OPML proactively implement regular check-ins with Bappenas and FCDO and conduct trilateral meetings on bi-monthly basis. This approach is suggested to ensure ongoing alignment with Bappenas and other stakeholders, facilitating collective decision-making, and address any emerging issues promptly. Regular meetings will help maintain momentum and address potential challenges before they escalate, improving program overall quality.	Formal mechanisms with Bappenas and technical committees were established to maintain alignment during Indonesia’s political transition. / However, engagement with key ministries such as the Ministry of Home Affairs (MoHA) remains limited, and ownership beyond Bappenas is still a challenge. / Engagement with UN-PAGE, GIZ, and UK PACT improved visibility but there are more opportunities for synergies between programmes.
2	Scaling up team: OPML and NIRAS should ensure key roles are appropriately filled and inform FCDO early on of any issues. OPML must find ways to expedite recruitment in crucial roles that remain vacant, such as the provincial liaison officers. OPML should learn lessons from its experiences with recruitment and personal in this year, and apply these to the future to improve the resilience and effectiveness of its team.	Recruitment of key roles has progressed, and the consortium delivered training on modelling, Monitoring, Reporting and Verfication (MRV), and the Bappenas’ platform that manages and provides access to data on low-carbon development in Indonesia, supporting evidence-based planning and better data integration across sectors (AKSARA) across four provinces. These have strengthened technical capacity at the subnational level, but uneven efficacy on technical support at both the national and subnational suggests the deployment of expertise should be revisited.
3	Political Context and Election Timing: Given the impact of the sub-national elections on workplan activities, OPML should integrate political timelines into future planning. By anticipating these events, the team can avoid delays and ensure provincial engagements proceed smoothly, even during election periods. In the meantime, OPML should prioritise engaging with technical level counterparts while awaiting clearer political conditions.	Four provinces finalised draft of Low Carbon Development and Climate Resilience Plan (RPRKBID) documents aligned with provincial government cycles, showing progress in planning delivery. However, delays caused by regional elections or changing of officials again disrupted timelines. This confirms the need for systematic integration of political calendars into future workplans, as recommended last year.
4	Quality and regularity of communications: OPML and NIRAS both need to continue improving the clarity and regularity of their communications with FCDO. Specifically, issues including underspending, personnel changes, or missed target deliverables, need communicating earlier. One reason is so FCDO can ensure effective internal budget management. Both organisations have been adjusting their approaches already which FCDO appreciates, and this should continue.	Communications with FCDO improved through more regular reporting and strategic updates. However, while OPML increased the volume of activity reporting, the annual review process found that the reporting can miss evidence of impact of activities.
5	Update Log frame and MEL plan / Data management for MEL also needs urgent attention: this annual review process has shown weaknesses in this respect. The programme log frame needs reviewing to ensure relevance and effectiveness. This applies to indicators, targets, data sources. FCDO, OPML and NIRAS should also consider the alignment of the log frame targets with the annual review period: currently these are out of sync, and some adjustments must be made to ensure the Annual Review has the evidence it needs. Finally, there is a need to integrate the GEDSI framework to ensure gender equality, disability, and social inclusion considerations are effectively addressed.	The logframe was updated in April 2025, and adaptive workshops and outcome harvesting were introduced. Despite this, data quality - especially for GEDSI indicators - remains inconsistent, and MEL insights are not yet systematically used for adaptive management. / Gender and inclusion language has been embedded in RPJMN, RPRKBID, and ITF governance. However, there are further opportunities for better disability inclusion and measurable equity outcomes.

In summary, the programme has responded to last year’s recommendations with some tangible improvements, particularly on coordination, capacity-building, and GEDSI integration. Yet, several issues flagged in 2024 remain unresolved. The priority for the coming year will be to consolidate gains by focusing on fewer, higher-value actions, politically informed engagement, and demonstrating proof of concept.
Summary supporting narrative for the overall score in this review
This Annual Review scores the LCDI2 programme as A (outputs met). The programme has made some progress over the past year, particularly in advancing Indonesia’s national and provincial planning for low-carbon development. The output workstream ratings are:
Workstream 1, A: At the national level, LCDI2 contributed directly to the integration of low-carbon development principles into Indonesia’s long- and medium-term planning frameworks. Notably, the programme supported the inclusion of low-carbon and Green Economy Index (GEI) indicators within the RPJMN 2025–2029 performance framework and the adoption of emission intensity targets as part of the RPJPN 2025–2045 national vision. One emerging success is the ongoing effort to link AKSARA—Bappenas’ planning platform for tracking low-carbon and green economy indicators—with SRN, the Ministry of Environment’s registry for emissions and mitigation actions. Interoperability between these systems would align policy planning with verified GHG data, creating a unified national monitoring framework for low-carbon development. This progress has been facilitated by LCDI’s role in brokering collaboration across key institutions—particularly Bappenas and MoE—during a period of political transition. However, the technical expertise of the consultants have been queried, while the focus remains on Bappenas rather than embedding within other ministries; therefore the quality of the outputs must be better evidenced in subsequent years to ensure the programme is achieving its aims.
Workstream 2, A: At the provincial level, LCDI2 supported four provinces—North Sumatra, Maluku, Bengkulu, and West Nusa Tenggara (NTB)—to prepare draft RPRKBID (Regional Low-Carbon Development Plans) aligned with the subnational development planning cycle (SPPN) and provincial RPJMDs. These plans set emission reduction targets and low-carbon priorities within regional planning frameworks. As of August 2025, North Sumatra and Maluku have completed final drafts, Bengkulu’s governor regulation is under MoHA review, and NTB’s draft is going through final consolidation. The programme also delivered training on low carbon modelling, MRV, and the AKSARA system, providing provincial Bappeda and Regional Government Agencies (OPDs) with a foundation for integrating LCD targets into planning. Overall, this workstream achieved its aims, although some opportunities were missed to better integrate provincial agencies into the planning process, and some of the training was limited in quality and efficacy.
Workstream 3, B: During the review period, over 20 engagements were delivered, including the Shaping Tomorrow: Intergenerational Action Towards a Low-Carbon and Green Economy and the North Sumatra Policy Dialogue, which convened the provincial parliament (DPRD) leadership, Bappenas, provincial governments, CSOs, academia, and private sector representatives. These dialogues served to raise awareness and facilitate alignment between RPRKBID development and RPJMD planning processes. However, outcome harvesting and KIIs indicate that these engagements remain largely reactive and process-oriented, with “very significant changes” reflecting political endorsement rather than measurable institutional outcomes. Knowledge and communications products—such as the LCDI Communications Strategy, Green Economy Expo outputs, and GEDSI Action Plan—improved visibility but lack systematic dissemination and monitoring of policy uptake, constraining the ability to demonstrate value for money or contribution to change pathways.
Workstream 4, A: The Innovation and Technology Fund (ITF) has advanced from design to operational readiness, establishing critical governance, fiduciary, and policy frameworks required for implementation. Under the leadership of the Carbon Trust, the programme supported the Indonesia Environment Fund (BPDLH) in formalising its role as fund manager, aligning ITF procedures with national public finance and fiduciary standards. Key milestones achieved during the review period include the finalisation of the Fund Operations Manual, the development of project selection criteria incorporating Gender, Equality, Disability and Social Inclusion (GEDSI) and social value metrics, and the near-completion of the Master Grant Agreement between BPDLH and OPML.
OPML has provided consistent programme management and technical delivery, though consortium coordination and the strategic use of partners remain areas for improvement. NIRAS has added value by providing independent assurance through MEL and VfM reviews, identifying optimism bias and highlighting where activity delivery has not yet translated into outcome-level influence. The delivery partners have contributed in mostly complementary ways, although more work is needed to prevent overlap on areas such as MEL. Both partners have integrated effectively with Bappenas, but clearer role delineation and more timely feedback will be essential going forward.
On balance, LCDI2 has laid the groundwork to deliver strategically relevant results and for Indonesia’s low-carbon transition. The tangible benefits of certain activities will not necessarily be realised in the short to medium term, and so the programme needs time to advance and embed work carried out so far, while also looking to maximise opportunities beyond the initial sphere of influence in government. Yet progress has been inconsistent and slow, and so there is an expectation of better evidence of outcomes in the following year. Sustaining momentum will require sharper prioritisation of activities for clearer impact and deeper institutionalisation of work. With these course corrections, the programme remains well positioned to achieve outcomes within timeframe and budget, while contributing to FCDO’s climate and sustainable growth objectives.
Major lessons and recommendations for the year ahead
There were several lessons learned during this review period:
- Translating outputs into outcomes remains a challenge. While the LCDI2 delivered a high volume of technical products and planning documents, systemic influence - such as a measurable shift in sectoral regulations, remains limited. The link between outputs and impact is not always clear, and some assumptions in the Theory of Change (ToC) require revisiting. This will rely on high quality outputs that are targeted for maximum impact coupled with clearer evidence of their link to outcomes.
- Further strategic direction and prioritisation is needed. An incredible number of outputs have been produced in the last year, although quality and impact has been variable. This has been in part due to the adaptive nature of the programme, as focus has been drawn to ad hoc requests from stakeholders. A stronger overall vision is needed for the programme to better prioritise, leading to efforts spent on activities which are most impactful.
- Stakeholder engagement needs deeper focus, and a link to implementation. Workstream 3 (WS3) delivered numerous activities, but feedback from government, civil society, and private sector actors suggests limited follow-up and weak integration into policy processes. Coalition-building efforts have yet to demonstrate durable influence. A shift is needed from delivering isolated technical products to delivering definable and measurable change.
- More ministerial buy in is needed for impact and programme resilience. National elections and leadership changes in Bappenas created uncertainty and delayed approvals. While momentum has now resumed, the programme remains highly dependent on Bappenas champions, with limited engagement from other relevant ministries i.e. Home Affairs, Finance and Environment. This highlights the lesson that cross-ministry institutionalisation is essential to sustain LCD adoption while also providing better integration of LCD.
- Establishment of a full operation of a new fund requires longer than expected. The key lesson is that institutional design, while essential, requires time to follow GoI internal requirements, as well as the need to allow time for the lengthy procurement process.
- Programme management improved, but consortium gaps remain especially with respect to technical capacity development. OPML filled key vacancies and improved forecasting but needs stronger oversight of sub-partners and earlier communication of risks to FCDO. Several of the programme beneficiaries noted that the technical assistance fell short of their expectations or were too short / insufficient to ensure mastery of the technical assistance by recipients.
- Maximising synergies between OPML and NIRAS in MEL functions. Clearer delineation of roles and strengthened coordination would help to avoid duplication and unlock greater synergies. This would enable both organisations—particularly NIRAS—to make an even more strategic contribution to programme learning and adaptive management.
- GEDSI integration remains partial. Gender considerations are visible in national and provincial planning documents, but disability inclusion and measurable impact on marginalised groups are still limited and require more meaningful mainstreaming.
Based on these lessons and the results outlined below, the following recommendations are made for LCDI to incorporate in Year 3:

No	Recommendation	Who	When
1	Strategic direction and governance: Strengthen programme governance mechanisms to streamline work and ensure best possible impact, including better defined parameters of the programme. Regular, structured forums for joint decision-making between Bappenas, FCDO and OPML should continue, while allowing flexibility to adapt the format and frequency as needed. This will help ensure the programme remains responsive, politically informed, and able to adjust course as the context evolves, but also ensures alignment with an agreed strategic direction and a clear forum for decision-making.	OPML, FCDO	By March 2026
2	Strengthen reporting by clearly showing how programme outputs, such as policy influence, lead to real-world implementation and measurable improvements. Outcome harvesting has helped identify changes, but greater clarity is needed on how policies are put into practice and their impact on the ground. Setting clear milestone targets at intermediate outcome will help track progress, ensure changes are on course, and demonstrate tangible results over time.	OPML NIRAS	By December 2025
3	Harmonisation of MEL roles to enhance strategic value: NIRAS, as the independent MEL partner, has scope to add greater strategic value by sharpening its role in adaptive management and evidence translation. Clearer division of responsibilities between OPML and NIRAS, combined with stronger collaboration, would ensure MEL serves not only as an assurance function but also as a driver of learning and programme adaptation. This would reduce duplication, improve timeliness of insights, and maximise the contribution of both partners.	NIRAS / OPML	By December 2026
4	Workstream 3 and consortium capacity and performance: Ensure WS3 engagement translates into policy traction rather than counting activities, while strengthening the consortium’s ability to deliver it. NIRAS should continue to provide independent MEL assurance, while FCDO will escalate persistent gaps to drive accountability and corrective action.	OPML, NIRAS	By March 2026
5	Broaden national ownership. The programme should strengthen engagement with MoHA, MoE, MoForestry, MEMR, and MoFinance, as well as further relationship building with sectoral ministries at the subnational level, to ensure better integration of LCD commitments in regulations, budgets, and sectoral plans.	OPML	By January 2026
6	Financial management: Provide earlier notice of underspend, ITF slippage, and consortium performance issues which impact spending in order to better enable FCDO budget management and course correction.	OPML, NIRAS	Ongoing (quarterly)
7	ITF operationalisation: ensure at least three pilot disbursement in 2026-2027 to demonstrate proof of concept.	OPML	By August 2026
8	GEDSI mainstreaming: evaluate GEDSI interventions and, using political economy analysis, identify entry points for better impact.	OPML, NIRAS	By March 2026

ODA adaptation line (mandatory): The reduction in UK ODA has been noted and communicated to Bappenas, OPML and NIRAS, but it has not affected the delivery of LCDI2 during this review period. This year’s activities and results have proceeded in line with the workplan approved by Steering Committee of LCDI2. However, future ODA allocations may require the programme to adjust its scope and streamline activities in subsequent years. This Annual Review therefore reflects on a programme that is currently on track, but which will need to adapt in the future to ensure resources continue to deliver at maximum impact.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Program Theory of Change
LCDI2’s Theory of Change (ToC), developed during inception and refined in 2024, sets out how targeted technical assistance, stakeholder engagement, and innovation finance can help Indonesia decouple economic growth from greenhouse gas emissions, while supporting inclusive and climate-resilient development. The programme’s intended impact remains reduced GHG emissions intensity against a business-as-usual scenario, aligned with Indonesia’s NDC target. The ToC is operationalised through four mutually reinforcing pathways, that reflect Indonesia’s complex multi-actor policy system:
1. National policy and planning (WS1): Integration of low-carbon pathways into RPJPN 2025–2045, RPJMN 2025–2029, sectoral strategies, and budgeting systems.
2. Subnational planning and implementation (WS2): Support for provinces and districts to develop Regional Low-Carbon Development Plans (RRPRKBID) and align them with provincial RPJMD cycles.
3. Stakeholder engagement (WS3): Building coalitions among parliament, civil society, interfaith groups, private sector, and media to sustain political support for LCD and drive legislative/budgetary action.
4. Innovation and Technology Fund (WS4): Piloting scalable low-carbon solutions through BPDLH as fund manager, demonstrating models for replication and financing.

Figure 1: Workstream Theory of Change

The workstreams are designed to reinforce each other; for example, WS3 engagement with parliament helps unlock budgetary support for WS1 and WS2 planning, while WS2 pilots provide evidence for WS1 policy design. WS4 investments are intended to demonstrate practical applications that strengthen both planning and coalition-building.
The LCDI2 log frame was updated in April 2025 to better reflect the programme’s delivery approach. This Annual Review assesses progress against outputs from 1 September 2024 to 30 September 2025, based on data available up to August 2025 and planned activities through September. The log frame includes four outputs, with revised indicators aligned to current ways of working.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
LCDI2 has delivered planned outputs across WS1 and WS2, with policy traction at the national level and initial adoption at provincial level. However, stakeholder engagement (WS3) continues to fall short of intended outcomes, and WS4 has progressed on governance but not yet on disbursement.
LCDI2 has delivered a workplan with important milestones, but its ability to demonstrate how these outputs are translating into behavioural change, budget allocations, or emissions reductions is limited. This is not unusual in development programming, but at this stage in the programme cycle needs to be addressed. It is understood that outcomes will be shaped by multiple actors, political dynamics, and external shocks. LCDI2 operates within a complex ecosystem where change is non-linear, emergent, and often indirect. Its theory of change and accompanying MEL systems need to recognise this.
The ToC rests on assumptions only partially validated through implementation: WS3 assumes that broad stakeholder engagement will produce durable coalitions capable of shifting incentives and mobilising finance. Evidence suggests this has not materialised; outputs have raised visibility but have not delivered systemic influence. WS2 assumes that embedding RPRKBID into draft RPJMDs will automatically translate into sectoral adoption. Key Informant Interviews (KIIs) in Maluku and North Sumatra show this is unlikely without MoHA endorsement, functioning MRV systems, and budgetary support.
The ToC is ambitious, and the programme has navigated complex systems, capacity gaps and political cycles. To account for this LCDI2 has begun to incorporate outcome harvesting and sense-making workshops. Strengthening feedback loops between evidence and decision-making should help further test and refine the theory of change, lead to workplan changes in response to the evidence, and ultimately improve the prospects for outcomes and impact.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The programme remains strategically important as the UK’s flagship climate partnership with Indonesia. As a new UK-Indonesia Strategic Partnership is agreed in 2025, climate, energy and nature will be at its heart and the LCDI2 programme speaks to this strategic priority. Within the wider portfolio of the embassy LCDI2 remains the only multi-year programme with a dedicated focus on climate action, but it is strongly complemented by sectoral work in energy, sustainable commodities, and infrastructure as well as centrally managed forestry, ocean, and nature programming. It continues to coordinate closely with UKPACT and other ICF investments to ensure complementarity and avoid duplication.
On its merits, LCDI2 is performing well enough to justify continuing. This is evidenced by its results (official low-carbon plans) and its potential (coalition-building and demonstration effects). It has, to some extent, overcome challenges and adapted, but has areas of improvement that are noted in this review’s recommendations.
The foundations have been laid, but the next year needs to consolidate policy gains, secure legal adoption at the provincial level, reframe coalition engagement around key decision points, and prove the ITF concept through tangible pilot financing. This strategic shift from breadth to depth will be essential to deliver the systemic transformation envisaged by the programme.
The reduction in UK ODA has been noted and communicated to partners, but it has not affected LCDI2 delivery during this period. Looking ahead, the programme may need to streamline activities to maintain strategic focus and impact within a tighter funding envelope.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Technical assistance to support LCD adoption with national ministries
Output number:		1	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1: Number of high-quality contributions to national plans.	Targets to be achieved / by August 2025: 7 contributions / Calculation of Green Economy Index (GEI) achievement of 2011-2023 (GEI Report 2024) / Reassessment of GEI score target for 2025-2029 in RPJMN target / Regional workshop in East Indonesia (Makassar) was held (supported by LCDI team) / LCD 5 years plan for achieving targets for RPJMN 2025-2029 (LAPI Study) / One pager report, elaborating the emission intensity reduction as part of RPJMN Macro indicators referring to existing formal sources and other LCD references / Analysis of LCD-related RO nomenclature from KRISNA (Bappenas planning platform) / Calculation of 38 Provincial GHG Emissions Intensity Reduction targets set based on technical analysis support from LCDI	Achieved / By August 2025: 7 contributions to national plans completed / Calculation of GEI achievement 2011-2023 completed along with re-assessment of GEI score target for 2025-2029. / The provision of technical assistance for the 2025–2029 RPJMN has been completed, including a study by LAPI ITB on the LCD 5-Year Plan and a one-pager on emission intensity for RPJMN macro indicators. LCDI2 also contributed to the regular update of GHG Emissions Intensity Reduction targets for all 38 provinces- strengthening methodological consistency and data quality across subnational governments and enabling Bappenas to set more informed provincial targets and provide high-level estimates of potential GHG reductions. / All evidence for Indicator 1.1 can be accessed here. Permission will be granted by OPML upon request
1.2. Number of high-quality technical assistance products that contribute to implementation of LCD plans (e.g. policy, finance and reporting)	Targets to be achieved / by August 2025: 12 Technical Assistance (TA) products / Grand Design of Green Economy (under revision) / Policy Note – FOLU / Policy Note – Agriculture / Policy Note – IPPU / Policy Note – Marine / Policy Note – Waste / Policy Note – Energy / Policy Note – Transportation / LCD Strategy and Phasing Roadmap for RPJPN 2025-2045 / Policy note on carbon trading / Comparison of targets in SNDC with framework SNDC, LTS LCCR, RPJPN, LCDI model, and ENDC / Framework for LCDI Decision Making at the National Government Level	Achieved / by August 2025: 12 TA products completed / Among these are the launch of the Low Carbon Development (LCD) Strategy and Phasing Roadmap for RPJPN 2025–2045, along with policy notes from seven sectors, presented at the high-level public dialogue “Shaping Tomorrow: Intergenerational Action Towards a Low-Carbon and Green Economy” hosted by Bappenas (the Ministry of National Development Planning), the UK Government, and the Foreign Policy Community of Indonesia on 8 May 2025. / In May 2025, the LCDI2 technical team provided recommendations on the carbon economic value and its implications for carbon pricing regulation. Specifically, Bappenas recommended a review of Presidential Regulation (Perpres) No. 98/2021 on the Carbon Economic Value (Nilai Ekonomi Karbon/NEK). / These recommendations were based on a carbon trading policy brief developed by member of consortium, INDEF. Bappenas conveyed the recommendations in a letter addressed to the Ministry of Environment and Forestry and the Coordinating Ministry for Food Affairs. / In the same month, the LCDI2 technical team contributed to the analysis on draft review of the Second Nationally Determined Contributions (SNDC) 2031–2035. The recommendation provided through Letter issued by Deputy for Food, Natural Resources, and Environment of Bappenas to the Deputy for Climate Change Control and Carbon Economy Governance of the Ministry of Environment. / In addition, LCDI has completed the Green Economy Grand Design supported by member of consortium, the Prakarsa, which serves as the foundation for the Green Economy Roadmap to guide sectoral implementation of green priorities. Grand Design also include GEDSI objective that ensure the participation of gender and vulnerable groups. LCDI2 produces framework for LCDI decision making at the national government level. / In addition to above output, LCDI2 also contributes to development of a framework for LCDI decision making at the national government level. Some reports are still in drafting process which are: / Assessment report on opportunities and barriers for LCD in national budget (draft) / Assessment report on key finance issues on Carbon Trading (draft) / Assessment report on potential special allocation fund (DAK) for LCD (draft) / Op-ed on potential special allocation fund (DAK) for LCD (draft) / Assessment report on potential special allocation fund (DAK) for LCD (draft) / Assessment on DIF (Fiscal Incentive Fund) (initial result’s presentation) / All evidence for Indicator 1.2 can be accessed here. Permission will be granted by OPML upon request

Output 1 has shown strong progress during the review period. By August 2025, LCDI2 has contributed to seven national-level planning documents and produced 12 technical assistance (TA) products to support the adoption of low-carbon development approaches by national ministries. These TA products include tools, guidelines, and policy inputs that are expected to inform planning and decision-making processes across sectors. Key achievements include contributions to embedding the Green Economy Index (GEI) and Circular Economy Roadmap into the RPJPN 2025–2045 and draft RPJMN 2025–2029, recalculating provincial GHG intensity targets, and producing sectoral policy notes (energy, transport, agriculture, FOLU, waste, marine, IPPU). These contributions represent early signs of policy traction and demonstrate that LCD considerations in Indonesia’s long-term and medium-term planning frameworks. However, for certain TA products there is limited evidence of uptake beyond key stakeholders such as Bappenas. Furthermore, given the new administration’s competing priorities beyond climate, e.g. free school meals, sustained engagement is required to ensure that these inclusions are operationalised and embedded across sectoral strategies and budgets rather than remaining at the level of planning documents.
Technical outputs, such as the GEI and Circular Economy Roadmap are widely recognised for their analytical quality and policy relevance, with integration into national planning documents (e.g. RPJPN, draft RPJMN) demonstrating uptake. Again, it is noted that effectiveness of these tools will depend on consistent use by line ministries and sustained cross-ministry coordination. Other products, like the national systems dynamics model and provincial models, are technically sound with improvement needed on accessibility and stronger stakeholder validation to enhance credibility and impact. Some reports, such as those on LCDI indicator targets and emissions reduction, require clearer presentation and closer alignment with ministry expectations to maximise their utility.
On GEDSI, integration has been achieved at the narrative level in RPJMN documents and some policy briefs, with disability inclusion absent and women’s participation in energy, forestry, and fisheries not systematically embedded. On this basis, the output is scored A (met expectations).

Changes during the year
The log frame was refined in April 2025 to align milestones with RPJPN and RPJMN cycles. A Technical Committee was formally established under a ministerial decree to strengthen inter-ministerial coordination, though its practical effectiveness remains untested. Emphasis shifted from broad technical modelling to politically anchored outputs (e.g. Green Economy Index -GEI roadmap, AKSARA–CBT-SRN interoperability).
Progress on last AR recommendations and lessons learned
The 2024 AR recommended stronger QA, prioritisation, and wider ministerial engagement. Progress has been mixed. QA has improved through the establishment of a Technical Committee, but output quality still varies since not all outputs gone through Technical Committee.
Recommendations for 2025–26
- Strengthen coordination with key national ministries—especially MoHA and MoF—to help local governments adopt LCDI approaches and explore how fiscal policies (like budget transfers and incentives) can support low-carbon planning at the regional level.
- Enhance usability for ministries by simplifying technical outputs (e.g., models, GEI tools, briefs), strengthen quality assurance, conduct validation workshops and collate feedback to ensure products are practical, trusted, and integrated into planning and budgeting processes.

Output Title	Technical assistance to support LCD adoption with sub-national governments
Output number:		2	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of high-quality contributions developed to integrate LCD into sub-national plans	Targets to be achieved / by August 2025: 5 contributions / RRPRKBID of North Sumatera (final draft) / RRPRKBID of Maluku (final draft) / RRPRKBID of NTB (draft) / RRPRKBID of Bengkulu (draft) / Support to RPJMD and Renstra North Sumatera	Achieved / By August 2025: 5 contributions achieved and additional 3 new contributions, Total 8 / Additional new contributions / Support to RPJMD and Renstra Maluku – completed / Support RPJMD and Renstra NTB - completed / Support RPJMD and Renstra Bengkulu – completed / On the request of local governments, LCDI2 has delivered eight high-quality contributions against its numeric targets. Two provinces (North Sumatra, Maluku) now have near-final RPRKBID documents fully aligned with their RPJMD cycles, while two others (Bengkulu, NTB) have draft RPRKBID under active review by the Ministry of Home Affairs (MoHA). These products are not only technical drafts but include supporting studies on GHG intensity, sectoral data baselines, and financing pathways that enhance the credibility of the plans. / These are positive signs of institutionalisation at sub-national level implementation by translating LCD objectives through Governor’s Regulations (Pergub). The integration process demonstrates that LCDI2 contributions are increasingly embedded into provincial planning architecture, although sustainability will depend on MoHA endorsement,which would embed RPRKBID within the national planning framework and provide a legal basis for sectoral adoption. / All evidence for Indicator 2.1 can be accessed here. Permission will be granted by OPML upon request.
2.2 Number of high-quality technical assistance products that contribute to implementation of LCD plans (e.g. policy, finance and reporting)	Targets to be achieved / By August 2025: 7 products / Draft of Pergub of RRPRKBID North Sumatra / Draft of Pergub of RRPRKBID Maluku / Draft of Pergub of RRPRKBID NTB / Draft of Pergub of Bengkulu / Report on Sawahlunto national action plan / Study on Government Needs Assessment for Climate Action Financing North Sumatra / Study on Government Needs Assessment for Climate Action Financing Maluku	Achieved / By August 2025 achieved 7 products and an additional 11 products, 18 total / Additional new products: / Study on Government Policies for Climate / Action Financing North Sumatra / Study on Government Policies for Climate Action Financing Maluku / Study on Financing Opportunities for North Sumatra / Study on Financing Opportunities for Maluku / Stakeholder landscape and institutional analysis for climate action and development report North Sumatra / Stakeholder landscape and institutional analysis for climate action and development report Maluku / Strengthening sub-national climate action: Enhancing MRV systems and climate finance at Provincial Level / Strengthening Indonesia climate finance infrastructure – mobilizing resources for LCD / Study on integrated low carbon development initiative – North Sumatra / Study on integrated low carbon development initiative – Maluku / 11. Study on low carbon development implementation, aligning actions, needs, financing and monitoring in Maluku / By August 2025, the programme has produced 18 technical assistance products, exceeding the agreed workplan. These include sub-national financing studies, institutional analyses, and integrated LCD assessments in North Sumatra and Maluku, alongside MRV and climate finance infrastructure frameworks. Several outputs have achieved direct policy traction—feeding into draft provincial regulations (Pergub RRPRKBID in four provinces), informing RPJMD annexes, and shaping MoF–Bappenas dialogues on innovation and technology fund. / All evidence for Indicator 2.2 can be accessed here. Permission will be granted by OPML upon request
2.3 Number of provinces receiving high-quality training	Targets to be achieved / By August 2025: 4 trainings delivered / Training of AKSARA for NTB government officials / Training on modelling and system dynamics in North Sumatra (Sumut) / Training on modelling and system dynamics in Maluku / Training on modelling and system dynamics in Bengkulu	Partially achieved / By August 2025 : 4 trainings delivered and an additional 1 training, 5 total. / LCDI2 has delivered 5 training workshops reaching 257 government officials across four provinces, with 37% women participants. The trainings focused on system dynamics modelling and the AKSARA tool, directly supporting the preparation of RRPRKBID and ensuring timely alignment with provincial RPJMD cycles. This shows strong responsiveness to sub-national planning needs and contributes to systemic capacity-building by equipping Bappeda and line agencies with analytical tools. / • Additional new training: Advanced modelling and system dynamics training in NTB (deepening scenario analysis capacity and integration into provincial LCD planning). / While uptake and relevance were high, several participants raised concerns about the short duration of sessions and lack of technical detail, which limited opportunities for in-depth practice. Therefore it is only partially achieved as the quality did not meet expectations. / All evidence for Indicator 2.3 can be accessed here. Permission will be granted by OPML upon request

The number of outputs for WS2 exceeded the agreed workplan and its activities were well-received by sub-national government. This shows that the programme has provided relevant expertise to deliver within the agreed timeframe. The review noted that subnational engagement has been one of LCDI2’s most visible areas of activity. The programme has supported four provinces (North Sumatra, Maluku, Bengkulu, NTB) to prepare RRPRKBID documents and align them with the 2025–2029 RPJMD. The RPRKBID provides the evidence base—through low carbon development modelling, emissions baselines, and scenario analysis—that enables provinces to set measurable targets and identify priority interventions. By developing the RPRKBID first, local governments can ensure that LCD integration in RPJMDs is data-driven, consistent with national emission-reduction trajectories, and linked to sectoral budgeting and monitoring systems.
- Policy traction: In North Sumatra and Maluku, RPRKBID drafts are at an advanced stage, with integration into RPJMD close to finalisation. In Bengkulu, a draft Pergub is under review by MoHA, signalling potential legal adoption. The programme has also navigated administration and personnel changes at the subnational level due to elections at the end of 2024.
- Capacity-building: Five trainings (257 officials, 37% women) on system dynamics and AKSARA have been delivered, alongside stakeholder mapping and climate finance assessments. There was mixed feedback on the efficacy of these workshops, pointing to limited technical expertise sharing, highlighting the need for sequenced and extended training alongside collecting feedback to understand impact.
- Innovation: In North Sumatra, LCDI2 facilitated a feasibility study for a solar-powered water pump in Samosir, endorsed by the provincial environmental agency. This project demonstrates operationalisation of LCD principles by linking renewable energy to GHG emissions avoided, rice productivity gains, and ecosystem restoration.
On this basis, the output is scored A (Met Expectations). Provincial engagement has expanded beyond original targets; however, concern remains over the quality and depth of technical assistance. While the programme has delivered the planned TA and training activities, feedback indicates that sessions were often too short to build practical expertise, and further support will be needed to ensure skills are embedded at the sectoral level. Strengthening institutional capability, MRV systems, MoHA endorsement, and GEDSI integration will be critical to ensure durable adoption and systemic change. The priority for 2025 will be to secure MoHA guidance, enhance the quality and impact of TA Delivery, strengthen sectoral adoption of LCD indicators, and move pilot feasibility studies such as the North Sumatra solar pump towards implementation.
Changes during the year
The log frame for Output 2 was refined in April 2025 to capture RRPRKBID adoption and subnational training. A notable change was the expansion of provinces from 2 (in 2023–24) to 4 (by 2025), increasing the scale of engagement.
Progress on last AR recommendations and lessons learned
The 2024 AR recommended scaling provincial engagement, embedding LCD in RPJMD, and strengthening capacity-building. Progress has been made: four provinces are actively drafting RRPRKBID, and training was delivered beyond targets. However, the depth of institutionalisation remains limited, and lessons from last year — the need for sustained, sequenced training and stronger MoHA involvement — have not yet been fully addressed.
Key lessons this year: Aligning TA with provincial planning cycles enhances ownership, but short-term engagement is insufficient; this must move to sequenced capacity-building with evidence of impact provided. MoHA engagement is critical to ensure provincial LCD plans are formalised and sustained. GEDSI mainstreaming must move beyond gender quotas to practical integration in sectoral policies.
Recommendations for 2025–26:
- Deepen technical assistance on MRV systems and financing at provincial level.
- Review the volume of outputs in future years, and set out a clearer logic for how existing, and any further outputs, will deliver meaningful change through influence on (or adoption of products / recommendations) by stakeholders.
- Allocate more time and effort to following up on the usage and implementation of technical outputs and recommendations, including collecting feedback for any capacity building.
- Secure MoHA commitment to embed LCD into national planning regulations for provinces.
- Ensure GEDSI integration is built into provincial sectoral strategies, not just planning documents., especially in Social Inclusion and Disability

Output Title	Engagement with relevant LCD stakeholders to build support for LCD
Output number:		3	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of high-level or high-profile stakeholder engagements to build support for LCD	Targets to be achieved / by August 2025 : 15 high level / high profile stakeholders engagement / Mapping for private sector / Report on the Potential Role of the Private Sector in Financing and Investment for Low Carbon Development / Report on Tackle inequality in the process of realising LCD business and investment / Report on unlocking potential of CE and cleaner production for industrial LCD actions / Audience with Eddy Suparno / Audience with Rahayu Saraswasti / Audience with Green Economy Caucus Mercy Barends / Training for Trainers (part of Capacity Building for Religious and interfaith engagement) / National training (part of Capacity Building for Religious and interfaith engagement) / Interfaith dialogue (part of Advocacy works on Religious and Interfaith) / Rapid assessment report of implication of National Election to LCDI / Rapid assessment of implications of provincial election results for LCDI in Maluku / Rapid assessment of implications of provincial election results for LCDI in North Sumatra (Sumut) / Rapid assessment of implications of provincial election results for LCDI in Riau / Rapid assessment of implications of provincial election results for LCDI in Sawah Lunto	Partially Achieved / By August 2025 : 15 high level / high profile stakeholders engagement achieved, with an additional new 7 engagement and reports, Total 22 / Additional new engagements and reports: / Report on Policy Gaps in Low-Carbon Development in Indonesia / Report on provincial context assessment Maluku / Report on provincial context assessment North Sumatra (Sumut) / Report on provincial context assessment Riau / Report on provincial context assessment Sawah lunto / Mass media engagement - Rachel Kyte visit event (Public Dialogue on 8 May) / LCD policy dialogue in North Sumatra (27-28 August 2025) / Outcome harvesting and KIIs confirm that most reported “very significant changes” under WS3 were expressions of support rather than evidence of systemic influence. Parliamentary engagement has improved, exemplified by the August 2025 policy dialogue in North Sumatra led by INFID, which brought together DPRD leadership, Bappenas, provincial governments, CSOs, and the private sector to discuss integrating LCD priorities into RPJMD and Renstra. However, its influence remains preliminary, with no follow-up yet translating into motions, budget amendments, or formal regulations. / All evidence for Indicator 3.1 can be accessed herehere. Permission will be granted by OPML upon request
3.2 Number of high-quality knowledge products that build support for LCD	Target to be achieved / by August 2025: 8 knowledge products / LCDI Communication Strategy / LCD Glossary / LCD Flyer/factsheet / GE Expo Proceeding / Materials for supporting Bappenas in COP29 / GEDSI action plan / GEDSI strategy / Podcast Katadata with SDGs	Partially Achieved / By August 2025: 8 knowledge products achieved, an additional 5 new products, Total 13. / Additional products: / LCDI branding and guidelines / Mapping and identification of religious and interfaith organisation / Study on the Capacity and Impact of Religious Organisations in Managing Environmental Risks / Policy brief on Urgent Need for Involvement of Interfaith Organisation in Indonesia's Low Carbon Development (part of Advocacy works on Religious and Interfaith) / Press release for Public Dialogue on 8 May 2025 / A range of knowledge and communications products — including the LCDI Communications Strategy, Green Economy Expo proceedings, factsheets, policy briefs, podcasts, and GEDSI Action Plan — have improved the programme’s visibility and outreach across government and non-government audiences. However, evidence of uptake or policy utilisation remains limited. There is little indication that these products have informed decision-making processes in key ministries, DPRD committees, or provincial planning offices. Dissemination mechanisms remain ad hoc, and no systematic tracking of citations, downloads, or references in policy documents has been established. This constrains the ability to demonstrate value for money and contribution to outcome-level influence. use, and influence, ensuring that outputs contribute demonstrably to planning, budgeting, or public discourse. On this basis, the workstream moderately did not meet expectations. / All evidence for Indicator 3.2 can be accessed here here. Permission will be granted by OPML upon request

Workstream 3 has achieved a high volume of activities, creating visibility for LCDI across parliament, civil society, business, and faith-based groups. The programme is recognised as an important platform for convening dialogue on low-carbon development. However, while visibility has increased, the workstream continues to demonstrate weak evidence of outcome level change. Its activities have not convincingly demonstrated that stakeholder engagement is shifting political incentives, securing parliamentary support for budgets, influencing private sector investment decisions, or strengthening the capacity and influence of civil society organisations. Much of the engagement has been disjointed and focused on providing additionality to existing events, resulting in a largely reactive rather than a strategically driven approach. Because of this, the decision was made to pause the naming of commissioners for LCDI2 until there is better articulation of their value add and to mitigate reputational damage in the absence of a clear strategy.
The fundamental ToC assumption — that stakeholder dialogues and products would lead to durable coalitions for higher ambition —remains unproven in practice and there is a lack clarity on the outcomes they aim to influence. For example, parliamentary engagement did not align with budget cycles or committee hearings, missing critical entry points to shape resource allocations. Similarly, business engagement by member of consortium remained at the level of mapping exercises, without translating into investment partnerships.
During the year, OPML expanded the number of engagements beyond plan and produced an internal communications strategy, while the consortium engaged religious organisations to understand their role in climate action. This latter initiative offers a promising avenue for influence, given the reach and legitimacy of faith-based networks in Indonesia. However, activities still lack prioritisation and cohesion, evidence of how it contributes to overall changes, while the volume-driven approach risks crowding out quality and meaningful follow-up.
On this basis, the output is scored B (moderately did not meet expectations): activity levels and knowledge products surpassed milestones, yet the workstream remains event-driven with limited evidence of systemic influence or coalition-building.
Progress on last AR recommendations and lessons learned
The 2024 AR already flagged WS3 as underdeveloped and recommended: stronger political economy analysis to target parliamentary and business actors; sustained follow-up rather than one-off dialogues; and monitoring of knowledge product uptake. Progress has delivered effort and volume but has not addressed the core challenge i.e. providing direction to achieve systemic impact.
An urgent course correction is needed to bring clarity and drive behaviour change – this may mean seeking to influence fewer stakeholders but to have deeper influence.
Key lessons this year:
- Events ≠ coalitions: High-profile dialogues create visibility but do not substitute for structured parliamentary or business advocacy.
- Consortium partners must be better mobilised: INFID and IBCSD hold the networks yet must be better utilised in a strategic manner.
- Better evidence of impact: Knowledge products must have evidence to demonstrate their use and influence to ensure VfM.
- NIRAS’s MEL role is critical: Their evidence-based challenge to OPML’s claims ensures accountability and helps FCDO push for strategic adaptation.
Recommendations for 2025–26
- Reframe WS3 around political economy priorities. Focus on parliamentary budget cycles, sectoral commissions, and influential business associations.
- Use consortium partners better, with a sharper definition of roles, under the strategic guidance of the team leader. This may involve focusing on fewer stakeholder groups rather than continuing to engage all originally identified audiences.
- Prioritise quality over quantity by better utilising fewer, more strategic engagements with structured follow-up (e.g., working groups, memoranda, caucuses). Develop a dissemination and uptake plan for knowledge products while tracking usage in official policy documents, parliamentary briefings, and/or provincial regulations.
- Make clearer the links and synergies of WS3 with WS1 and WS2 by ensuring engagement directly supports policy reforms and subnational RRPRKBID adoption.
- Strengthen MEL feedback loops by incorporating NIRAS’s outcome harvesting to test whether engagements are translating into genuine influence.
- Strengthen leadership within WS3 to provide clearer strategic direction and coordination. Stronger leadership—whether through OPML or by designating a more visible WS3 lead—would help ensure that stakeholder mapping, engagement sequencing, and follow-up are coherent and politically informed, rather than activity-driven. This would also create clearer accountability for mobilising consortium partners such as INFID and IBCSD, whose networks remain underutilised, and provide a focal point for linking WS3 more directly to WS1 and WS2 outcomes.

Output Title	Support to LCD adoption through the Innovation and Technology Fund (ITF)
Output number:		4	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of high-quality technical assistance products developed to set up and disperse funds	Targets planned to be achieved / by August 2025: 5 TA products / 1. GEDSI Social Value input for the ITF [GEDSI Input incorporated] / 2. Feasibility study on Solar Powered irrigation system (Solar PV) [GEDSI Input incorporated] / 3. Detail Engineering Design (DED) Document on Solar Powered irrigation system (Solar PV) / 4. Comparative analysis on Fund Managing Entity developed by Carbon Trust / 5. ITF project selection criteria presentation [GEDSI Input incorporated]	Achieved / by August 2025 : 5 products and an additional 3 new products, Total 8 / Fund operation manual / Master grant agreement on fund implementation / Non-disclosure agreement / In 2024-2025, led by the Carbon Trust, the ITF progressed from concept to implementation stage. The Indonesia Environment Fund/ IEF (Badan Penyelenggara Dana Lingkungan Hidup /BPDLH) was selected as the fund manager, with governance structures established and GEDSI social value criteria embedded in project selection. Key documents, including the Fund Operations Manual and draft Master Grant Agreement, have been advanced. However, the ITF is not yet operational—no funds have been disbursed, and pilot projects remain at the planning stage. / All evidence for Indicator 4.1 can be accessed here here. Permission will be granted by OPML upon request

The ITF was established to provide a demonstration mechanism for financing innovative, low-carbon and climate-resilient solutions. During 2024–25 the Carbon Trust, part of the LCDI consortium members responsible for ITF design, has made progress on institutional design and governance. Key achievements include: the appointment of Indonesia Environment Fund (IEF) / BPDLH as fund manager, the signing of an NDA, the finalisation of the Fund Operations Manual, the development of project selection criteria incorporating GEDSI and social value filters, and the near-completion of the Master Grant Agreement.
Despite delays, the ITF is on track to achieve its design-stage targets, with preparations for launch now at an advanced stage. The pilot has taken longer than anticipated due to administrative delays in finalising governance arrangements with BPDLH and in completing the Fund Operations Manual and Master Grant Agreement, both prerequisites for disbursement.
Although funding hasn’t been released yet, the pilot is expected to begin implementation in 2026, meaning it’s close to entering the demonstration phase. Stakeholder expectations at provincial level remain high, but given progress on governance and technical design, the risk of reputational damage from non-delivery is now considered lower. On this basis, the output is scored A: met expectation on institutional preparation, with pilot implementation expected in the coming year.
Changes during the past year
The most significant change is the formal anchoring of ITF within BPDLH, Indonesia’s national climate finance entity. The expectation is that this will ensure long-term ownership and alignment with government systems, but has also meant progress follows government pace and procedures. The Fund Operations Manual was finalised mid-2025, while no changes to output targets or indicators have been made. Planned changes for the coming year include a focus on moving from design to implementation, with at least three pilots expected to reach disbursement stage before the next review.
Progress on last AR recommendations and lessons learned
Last year’s review recommended clarifying fund governance and accelerating operational readiness. This has largely been achieved: governance documents are complete or near final, and the fund manager is in place. However, the recommendation to demonstrate early disbursement has not been met.
The main lessons this year are:
1. Anchoring in BPDLH enhances legitimacy but slows delivery. Alignment with state systems has ensured fiduciary safeguards, but also lengthened preparation timelines. This trade-off is necessary to safeguard VfM and ensure sustainability.
2. Design-first was the right choice. Establishing governance and fiduciary frameworks before disbursement has reduced the risk of rushed or poorly targeted financing
3. Expectation management is essential. While provincial stakeholders are interested in potential financing, the ITF will realistically only support a limited number of pilots in the near term. Clearer communication of scope and timelines will help avoid unrealistic assumptions.
4. Additionality must be demonstrated. The ITF should support genuinely innovative pilots that complement rather than duplicate existing BPDLH funding windows.
Recommendations for the year ahead
- Build momentum, which includes timeliness for first pilot contracting.
- Demonstrate proof of concept by delivering at least three live disbursements in 2026-2027.
- Communicate proactively with provincial partners on ITF timelines and criteria to manage expectations and ensure buy in.
- Use NIRAS MEL to test whether the ITF’s GEDSI/social value filters are genuinely influencing project operationalization, thus effectively monitoring results.
## D: VALUE FOR MONEY
Key cost drivers and performance
The LCDI2 Business Case proposed that investing £27.2m of UK ICF in high-quality technical assistance, strategic partnerships, and catalytic pilots would deliver VfM by embedding low-carbon pathways into Indonesia’s planning systems. This was expected to yield long-term emissions reductions and climate-resilient growth, at a cost far below the social cost of carbon avoided. The VfM framework developed for LCDI2 (owned by OPML and reviewed by NIRAS) applies FCDO’s 4E model: economy, efficiency, effectiveness, and equity.
Economy
Inputs continue to be procured competitively, with national and international expertise engaged at market-reflective rates. Inflationary pressures and increased post-election demand for technical consultations and coordination workshops, linked to renewed government planning process following leadership transitions, led to higher workshop and travel costs. However, these were partly offset by in-kind GoI contributions (venues, staff time, data access). Fiduciary assurance remains sound with no fraud identified. OPML has recruited almost 80% local staff and consultants, consistent with GoI preference for nationally led technical assistance that builds local ownership and sustainability. This approach has strengthened contextual relevance and cost efficiency. However, the extent to which this approach consistently translates into VfM through uptake and impact of outputs is mixed. Procurement delays (e.g. INDEF, INFID) increased transaction costs and highlight pipeline planning weaknesses, while feedback on their technical expertise has not always been positive.
For NIRAS, cost-effectiveness remains under review. While technical inputs have been delivered, linkages to decision-making and programme adaptation are limited, reducing VfM. Stronger alignment of MEL outputs with adaptive management is needed. Budget utilisation in 2025 shows 55% (~£2.5m) spent on implementation and 5% (~£230k) on MEL — appropriate overall but underscoring the importance of ensuring MEL delivers actionable insights.
Efficiency
Efficiency has improved in Workstreams 1 and 2 (national and subnational TA), with the number of outputs delivered above target. However, challenges remain around efficient use of time and coherence of outputs:
- Training sessions were short and of varying quality, limiting depth of learning and requiring further time dedicated to the same outputs.
- The number of TA products exceeded expectations, but many lack evidence of uptake beyond their initial circle of influence.
- The number of stakeholder events and engagement has exceeded expectations, but often have been reactive and visibility focused; fewer, more targeted engagement would be appropriate.
On NIRAS, while their MEL role provides assurance, their recommendations have insufficiently translated into actionable programme adjustments. The added value of their inputs is therefore less visible, and in some cases duplicative of OPML’s own reporting. To ensure VfM, NIRAS must sharpen its analysis, provide more targeted feedback, and link MEL findings directly to decision-making and adaptive management, rather than producing parallel assessments that consume time without shifting delivery.
Effectiveness
Effectiveness is mixed but improving, with LCDI2 contributing to systemic outcomes such as:
• Green Economy Index embedded in RPJPN 2025–2045 and RPJMN 2025–2029.
• LCD targets recalculated for all 38 provinces.
• Four provinces advanced RRPRKBID drafts aligned with RPJMD cycles.
These shifts confirm LCDI2’s influence on Indonesia’s planning architecture. However, systemic change remains fragile and uneven. While planning outputs are strong, they have yet to translate into tangible, behavioural, budgetary or institutional shifts, which could be in part due to the inconsistent quality of capacity building. Engagements under Workstream 3 have nor consistently produced follow-up actions or durable coalitions. Many dialogues resulted in expressions of support rather than policy adoption or resource mobilisation. Similarly WS4 remains limiting demonstration of impact. These gaps underscore that programme’s technical progress must now be matched with stronger political traction and inter-ministerial engagements (particularly MoHA, MoF and sectoral ministries). NIRAS’s MEL role remains valuable in surfacing these limitations, but its strategic contribution would be strengthened through clearer, timelier adaptive recommendations and closer integration with OPML’s delivery function to ensure evidence is translated into concrete adaptive actions.
Equity
Progress on GEDSI is steady but partial. Gender considerations have been incorporated into RPJMN drafts, RRPRKBID processes, and ITF criteria, with a modest increase in women’s participation in training. However, disability and vulnerable groups remain largely excluded, limiting fulfilment of the Business Case equity ambitions. NIRAS has identified equity gaps, but recommendations remain high-level and underutilised. A more meaningful approach would link low-carbon pathways to community-level impacts and equity assurance would be strengthened by embedding measurable indicators in RRPRKBID MRV systems, ITF disaggregation, and targeted support for communities most affected by transition.
Overall VfM assessment
Economy: Strong — costs remain controlled, procurement competitive, in-kind contributions add value.
Efficiency: Variable — high outputs delivered, but WS3/WS4 less efficient (while outputs have been produced, their influence is not proven, which then effects efficiency of resources).
Effectiveness: Variable – mostly on track in WS1/2; off track in WS3; WS4 yet to prove.
Equity: Partial — GEDSI visible in planning texts, but operationalisation weak.

Judgement
LCDI2 continues to represent acceptable value for money, but should not continue to rest on economy and volume. The original Business Case proposition — that modest ICF investment can mainstream LCD in Indonesia’s planning and unlock large-scale emissions reductions — remains valid. The programme is strongest in national and provincial planning support (WS1/2) but weaker in coalition-building and innovation finance (WS3/4).

FCDO judges that the programme should continue, LCDI2 remains a flagship of the UK’s ICF portfolio in Indonesia, contributing directly to FCDO’s Outcome Delivery Plan and HMG’s climate diplomacy objectives.

E: RISK
Overview of risk management
The LCDI2 programme has maintained a structured and responsive approach to risk management, guided by FCDO’s Risk Appetite Statement and aligned with corporate standards. Risks are reported on a quarterly basis by the implementing partners, with FCDO review and challenge. The LCDI2 risk register is maintained at AMP and discussed at Embassy Programme Reviews. This process has been effective in capturing risks across political, delivery, fiduciary, people and financial contexts, which overall remain assessed as moderate risk.
Risk appetite review:
- Delivery/operational risks (minor, within appetite): There was a risk of a difficult relationship with partners in the Government of Indonesia. This has improved over the past quarter through regular communication and engagement, which has helped strengthen collaboration.
- Financial/fiduciary risks (moderate, within appetite): Fraud and corruption remain material risks. Controls are in place (procurement, segregation of duties, spot checks). No cases identified to date. In addition, the reduction of ODA to 0.3% presents a significant risk to the continuity and scale of programme implementation. FCDO is maintaining close coordination with the implementation partner and the Government of Indonesia to prioritise high-impact activities and mitigate risks to outcome delivery.
- Safeguarding (SEAH/child protection) (minor–moderate, within appetite): Mitigation is strong, with mandatory training completed and quarterly checks by FCDO. No incidents reported.
- People risk (minor, within appetite): Staff turnover risk is managed through shared ownership of relationships and recruitment pipelines.
- Reputational risk (minor, within appetite): Failure to meet Bappenas needs and those of other parts of the Government of Indonesia. Whether due to poor delivery or unrealistic expectations, a shortfall in meeting the GoI's needs will damage the relation and lead to ineffective project implementation
- Policy/programme risk (moderate, within appetite): Political transitions in Bappenas slowed delivery early in the year but engagement is now stable under the new Deputy. Provincial elections caused some activity delays.
- Security risk (minor, within appetite): Stable operating context, no incidents affecting delivery.

Trends over the last year: Political transitions and provincial elections temporarily increased delivery risks, especially on subnational workplans. These were mitigated by adaptive scheduling. Safeguarding assurance is strong with no incidents reported. Financial risks remain stable but require vigilance given ODA budget pressures. Climate/environment risks remain low, as LCDI2 contributes positively to Paris alignment through integration of LCD in RPJPN/RPJMN.
Assurance on equalities and safeguarding: LCDI2 remains compliant with the Gender Equality Duty and PSED. GEDSI is increasingly embedded in RPJMN and provincial RRPRKBID drafts, and ITF design has integrated GEDSI/social value into project selection criteria. Disability inclusion, however, remains weak and will require stronger focus next year. Safeguarding against SEAH is managed effectively, with due diligence complete and no cases reported. Counter-terrorism financing and AML risks are assessed as low.
Due diligence (DDA): The market engagement and due diligence has been assessed during the procurement process by Procurement and Commercial Department for OPM and NIRAS; mitigation actions are being followed.
Recommendation: The programme should consolidate a clearer coalition strategy under WS3 to mitigate reputational and delivery risk. A live ITF pilot should be prioritised to reduce the risk of “design without delivery.” Disability inclusion should be strengthened to meet equalities commitments. Forward planning will be essential to manage reduced UK ODA allocations while keeping delivery within risk appetite.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
As of September 2025, the total expenditure for all projects under LCDI2 amounts to £5,871,098.65 representing 21.58% of the overall programme budget. This figure also includes partial funding for two programme funded staff and delivery costs charged to the programme, such as travel and events. Within the total business case value, £9,344,500 (around 34% of the total programme budget) has not yet been allocated to any contract or projects. While acknowledging potential reductions in ODA for future years, FCDO encourages the delivery team to model different expenditure scenarios to manage this low spend rate and to prioritise high-impact, politically significant activities that demonstrate tangible outcomes within the remaining timeframe.
The full implementation of LCDI2, delivered by OPML, is funded through both Resource Departmental Expenditure Limits (RDEL) and Capital Departmental Expenditure Limits (CDEL). RDEL covers day-to-day programme costs such as technical assistance and staffing, while CDEL is used for capital investments, including infrastructure or equipment. During the 2024–2025 period, OPML reported challenges in utilising the CDEL budget, resulting in the postponement of planned capital activities to the 2025–2026 financial year. As of this review, RDEL expenditure has reached 25% of the original business case allocation, while CDEL expenditure remains below 1%.
The establishment of a contractor for Workstream 4 is expected to improve the performance and anticipated to boost CDEL spending.
Performance Management and Delivery
Key Performance Indicators (KPIs) were applied to OPML throughout the 2024–2025 review period, with quarterly assessments conducted between October 2024 and September 2025. For NIRAS, KPI implementation began in the 2025–2026 financial year, following amendments to its commercial contract. Both partners have received full payment against their KPIs to date.
- Workstream 1 (national technical assistance): 19 products delivered against a target of 19 (100% of milestones).
- Workstream 2 (subnational technical assistance): 24 products delivered against a target of 16 (150%).
- Workstream 3 (stakeholder engagement): 35 engagements recorded against a target of 25 (140%), though evidence of outcome-level influence remains limited.
- Workstream 4 (Innovation and Technology Fund): 8 governances delivered against target of 5 (160%).
Despite these achievements, areas for improvement remain. OPML has maintained strong engagement with Bappenas but has areas across the workstreams as detailed in this report.
For NIRAS, while its Monitoring, Evaluation and Learning (MEL) and Value for Money (VfM) work has been valuable in identifying optimism bias and challenging delivery assumptions, its recommendations have at times been too diagnostic and insufficiently operational. To enhance its contribution, NIRAS should focus on producing more timely, actionable insights that can be directly integrated into programme decision-making and workplans.
Contract and Personnel Management
Both OPML and NIRAS have demonstrated sound financial forecasting and reporting. However, maintaining key personnel has been a challenge for both partners, resulting in contract amendments during the review period. One amendment was processed for OPML to reflect changes in personnel and fee structures, while two amendments were made to NIRAS’s contract to address staffing changes and the introduction of KPI assessments.

Financial management
In terms of financial management, both OPML and NIRAS have provided a timely submission of forecasting and reporting. Regarding the programme’s overarching financial performance, actual spend did not exceed its budget allocation. To ensure spending confidence, the programme relied on financial reporting from OPML and NIRAS that was timely per agreed cycles, a spot checking was conducted by FCDO part of invoice review submission.
Recommendations:
FCDO recommends the following actions in 2025–26:
- Enhance programme management structures: FCDO expects OPML to improve team resilience through timely recruitment, retention strategies, and stronger mobilisation of consortium partners. NIRAS should improve the operational utility of its evaluations, ensuring recommendations are timely, practical, and integrated into workplans.
- Embed strategic direction: The consortium should use quarterly steering sessions (FCDO–OPML–NIRAS) not only to review delivery but also to re-test the Theory of Change, adapt to political economy shifts, and align with Indonesia’s policy calendar. This will ensure outputs translate into meaningful influence and quality outcomes.
- Strengthen programme governance and collaboration: Consider revising how the Steering Committee operates to enable more strategic oversight and adaptive decision-making. The consortium could benefit from clearer roles, shared planning tools, and more structured collaboration mechanisms to improve coherence and responsiveness across partners.
- Minimise duplication: There is value in NIRAS carrying out the independent MEL function, and responsibility lies with them for this. Feedback channels should be more effectively used between OPML and NIRAS to ensure accurate monitoring for adaptive programming.

G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
Through the review period, the LCDI programme’s monitoring activities have developed well, supporting both accountability and programme improvement. MEL implementation has been led by OPML as the delivery partner, with NIRAS acting as the external MEL supplier. NIRAS has been working closely with OPML and FCDO, facilitating regular coordination meetings to discuss progress, share lessons, and consult on programme management.
Field visits have enabled the team to capture contextual differences in capacity and progress, while quarterly reviews and outcome harvesting provided regular feedback loops. Engagement with stakeholders, including Bappenas, FCDO, and provincial partners, was central to the process, with beneficiary feedback informing adjustments to provincial workplans and highlighting the need for tailored approaches.
Despite these improvements, the MEL system is still used more as a reporting mechanism than as a driver of adaptive management. Partners consistently noted that significant effort goes into reporting, but the information is not always prioritised or used effectively for decision-making. This reflects both the scale and complexity of LCDI2 and the ambiguity of roles between NIRAS and OPML. While communication has improved, there is still no clear division of responsibility for who should lead on learning and programme adaptation. This limits the ability of MEL to deliver on its potential as a tool for steering strategy.
Evidence
Evidence underpinning the programme has expanded over the past year. At national level, analytical products and technical briefs supported the integration of the Green Economy Index into RPJPN and RPJMN. At subnational level, RRPRKBID drafts in four provinces provided new evidence of provincial capacity but also highlighted the importance of MoHA endorsement for sustainability.
Disaggregated evidence on gender and inclusion is emerging but remains limited. References to GEDSI appear in planning documents, yet few activities have systematically tracked differentiated outcomes by age, sex, disability, or geography. Strengthening inclusive data will be a priority, in line with the Inclusive Data Charter and SDG’s “Leave No One Behind” agenda.
Learning
Learning has been captured through quarterly reflection sessions with partners, outcome harvesting, and knowledge product dissemination. These processes have helped highlight that events and outputs alone do not equate to influence; what matters is political anchoring and timing. Provincial ownership has emerged as a decisive factor — technical drafts are insufficient without wider Government of Indonesia approval and uptake. A further lesson is that credibility in innovative finance requires proof of concept through pilot disbursements.
For the wider FCDO portfolio, LCDI2 underscores the importance of embedding evidence in decision-making processes and ensuring that coalition-building efforts are strategically linked to fiscal and political cycles.
Looking forward, partners agreed that a consolidated MEL plan is required for 2025–26, setting out clear priorities, responsibilities and adaptive learning cycles. Regular trilateral meetings between FCDO, NIRAS and OPM will be institutionalised, and provincial field visits will continue to provide grounded insights. With these adjustments, the MEL system can shift from being primarily compliance-driven to becoming a genuine driver of adaptive management and strategic decision-making.

Date of last narrative financial report	4 August 2025	Date of last audited annual statement	31 March 2024