Low Carbon Development Initiative Phase 2 (LCDI2)

2025 Process Evaluation Draft Report
Foreign, Commonwealth and Development Office
Date: 6th February 2026

Contents

# Executive Summary
The Low Carbon Development Initiative (LCDI) is a partnership between the UK Government’s Foreign, Commonwealth and Development Office (FCDO) operating through the British Embassy Jakarta (BEJ) and Indonesia’s Ministry of National Development Planning (Bappenas), funded by UK International Climate Finance (ICF). The first phase (2017–2021) successfully integrated Low Carbon Development (LCD) into Indonesia’s 2020-2024 National Medium Term Development Plan (RPJMN). Now in its second phase (2023–2027), LCDI2 aims to support the implementation of LCD at both national and sub-national levels to help Indonesia achieve its 2025-2029 emissions reduction targets, with delivery led by Oxford Policy Management Ltd (OPML), oversight by FCDO via the BEJ, Bappenas as the main GoI counterpart, and NIRAS as the Evaluation Management Unit.
LCDI2 aims to:
- Build political support for LCD within and outside of government;
- Build knowledge and understanding of the LCD approach among those who are responsible for implementing it within the GoI;
- Support the implementation of LCD through provincial and national development plans; and
- Raise LCD ambition to the highest levels.
Implementation is through four Workstreams (WS) which focus on partnerships with national line ministries (WS1), sub-national governments (WS2), stakeholder engagement (WS3), and an innovation and technology fund (WS4).
## Context
LCDI2 operates in a complex political environment (see section 1.3), often with competing political priorities (see political economy analysis in Annex 9 for further details). Several challenges to effective LCD outcomes have been identified, including the planning process, the legal and policy framework, information and accountability challenges regarding MRV systems, financial and technology barriers, institutional capacity and political engagement. Given the current political environment in Indonesia and the mid-way point of LCDI2 programme delivery, this process evaluation is considered well-timed to understand what within the programme design is working well, as intended and why. In addition, the evaluation is timed to align with the 2024-2025 FCDO Annual Review and taking place alongside UK Government budget changes to ODA funding.
## EMU objectives and scope
NIRAS as the EMU has been contracted by FCDO from March 2024 to March 2028 to deliver MEL services. The primary purpose of the EMU is to maximise LCDI2 programme’s efficiency, effectiveness, impact and sustainability. The secondary purpose is to strengthen the FCDO – and global – evidence base on how to foster green, resilient economic growth. The primary audience is FCDO and LCDI2 Delivery Partners and the secondary audience is other GoI institutions.
This report forms the Process Evaluation output, which aims to analyse whether the programme is being implemented as intended; including issues around whether the design is working and what is working more well or less well than intended and why. The approach to the Process Evaluation was agreed with FCDO in March 2025 and finalised in July 2025 in the Approach paper. The evaluation focuses on LCDI2 activities, results and outcomes covering the period 2023 to September 2025.
## Findings
Findings in the report are presented by their cross-cutting nature and are presented against for key themes (Table 1).
Table 1 Summary of high-level findings in the evaluation report
Findings	Relevant EQs	Page
LCDI2 Design relevance and coherence
Finding 1: The underlying theory of LCDI2 is well aligned to supporting the green transition in Indonesia, blending national and sub-national TA activities to accelerate multi-level progress. However, while initial flexibility supported adaptability of the programme, the breadth and flexibility of the ToC has resulted in reduced clarity around the causal pathways, intermediate outcomes and assumptions, and there is a need to sharpen these to increase clarity.	EQ1.1, EQ1.3, EQ2.2	12
Finding 2: LCDI2 is broadly coherent with the green economy sector in Indonesia, both in terms of the key institutions it seeks to engage and the activities of other development partners and interventions. However, there remains a lack of clarity about LCDI2’s role within the ecosystem and scope to widen engagement, particularly with other GoI ministries and Directorates in Bappenas.	EQ2.1, EQ2.2, EQ1.3	14
Programme results and sustainability
Finding 3: LCDI2’s adaptive design and strategic partnership with Bappenas have allowed it to effectively navigate certain barriers inherent to the dynamic political context, but initial delays in starting and fully resourcing the programme hindered progress towards Outcomes until later in 2024. It continues to face significant risks from external developments.	EQ5.1, EQ3.1	17
Finding 4: LCDI2 has achieved several key results during its first two years of implementation, particularly across WS1 and WS2, building on the momentum generated by LCDI1 and embedding LCD in key policies and planning documents.	EQ5.1	18
Finding 5: LCDI2’s progress under WS3 and WS4 has been more limited compared to WS1 and WS2, though important foundational steps have been taken that could enable stronger results in the future.	EQ5.1	21
Finding 6: LCDI2 has been designed with longevity and sustainability in mind, and several elements of its approach suggest a strong potential for long-term impact, but there are also notable gaps such as the exit and transition strategies and financial and policy instruments that, if left unaddressed, could limit the durability of its achievements.	EQ5.2	23
Gender equity, disability and social inclusion
Finding 7: The integration of GEDSI into LCDI2 is still in its early stages. While a GEDSI Strategy has now been developed, its implementation faces continued challenges including a lack of dedicated resource and collective team understanding. The MEL system would benefit from further alignment with GEDSI.	EQ6.1, EQ6.2, EQ1.2, EQ3.1	26
Finding 8: GEDSI integration in LCDI2 has made important strides, particularly at the provincial level, but remains uneven across workstreams and limited in operational depth.	EQ6.1, EQ4.3	29
Finding 9: GEDSI integration in LCDI2 reflects a cautious but evolving approach, shaped by limited foundations, uneven senior engagement, and limited direction from FCDO and Bappenas, as well as emerging opportunities for strategic influence.	EQ6.1, EQ6.2	31
Programme management
Finding 10: LCDI2’s MEL system architecture has evolved and adapted to emerging needs well, albeit at a relatively slow pace and the monitoring system is currently in a state of transition. It is broadly appropriate for the programme’s context but there is scope for a range of improvements to enhance its contribution to effective Programme Management.	EQ3.1, EQ4.2, EQ1.2	33
Finding 11: LCDI2 resources are generally being used economically and appropriately, with good results on spending performance and KPI reporting results. The programme is monitoring VfM well through a number of frameworks and processes and there are relevant examples of a VfM lens having been used appropriately for adaptive management and management of cost drivers.	EQ4.1, EQ4.4, EQ1.2	38
Finding 12: LCDI2’s efforts to optimise Efficiency have been moderately successful. There has been good progress in establishing governance structures and building productive relationships between the key actors, with the programme evolving well in response to learning. However, efficiency is being hindered by a variety of factors that have reduced the timeliness, delivery quality, and impact of some outputs.	EQ3.1, EQ4.1	39
Finding 13: LCDI2 is showing positive signs of Effectiveness and Equity in its delivery, although it remains too early to assess in-depth. In both cases, more strategic thinking would be beneficial to sharpen the focus on Outcome achievement.	EQ4.2, EQ4.3, EQ6.1	41

## Conclusions
LCDI2’s story so far is one of strategic relevance, adaptive delivery, and meaningful contributions to Indonesia’s LCD agenda. Its achievements in policy integration, capacity building, and stakeholder engagement have laid a strong foundation for systemic change, while its challenges in coherence, sustainability, and operational depth highlight the complexities of driving transformation in dynamic contexts.
As LCDI2 continues it must balance flexibility with strategic focus, embedding sustainability into institutional frameworks, and deepening the integration of equity and inclusion. The programme’s journey reflects both the progress made and the ongoing challenges that must be navigated to ensure lasting impact. In doing so, LCDI2 offers valuable insights into the pathways and pitfalls of supporting low-carbon, climate-resilient development at scale.
The conclusions (section 4) can be summarised as follows:
- LCDI2 is a highly relevant and adaptable programme supporting Indonesia’s low-carbon development, but it faces ongoing challenges with coherence, sustainability, and operational depth in delivering systemic change across national and sub-national levels.
- LCDI2’s ToC closely aligned with Indonesia’s green transition ambitions, with an adaptive delivery model that has enabled it to remain relevant and gain strong government ownership and credibility at both national and sub-national levels.
- The wide scope and adaptability of LCDI2’s Theory of Change have led to challenges in maintaining clarity and coherence, occasionally resulting in resource strain and a diluted strategic focus.
- LCDI2’s main achievements lie in its successful support for policy integration and building capacity, notably by helping Bappenas set ambitious green targets and advancing the inclusion of green economy and circular economy principles in key national planning documents, such as the RPJMN.
- LCDI2 has helped four provinces (North Sumatera, Bengkulu, NTB, and Maluku) integrate LCD principles into their long-term and medium-term development plans, establishing frameworks and building capacity through targeted initiatives.
- Strategic partnerships, especially with Bappenas and provincial agencies, have enabled LCDI2 to embed its work within government systems and foster multi-level stakeholder engagement.
- Despite progress, the programme faces ongoing challenges such as disrupted activity sequencing, institutional fragmentation, and limited technical capacity at the sub-national level.
- The sustainability of LCDI2's achievements depends on robust financing, institutionalised systems, and a clear exit strategy, with current constraints posing risks to long-term impact.
- Financial limitations, especially at the sub-national level and the lack of binding regulations threaten the realisation of LCD plans, while operational integration of GEDSI principles remains inconsistent.
- LCDI2’s management mechanisms have improved, with better monitoring and resource efficiency. Strategic leadership, effective governance structures, and productive relationships between key actors have contributed to delivery efficiency but issues remain in procurement, coordination, and mobilising expertise.
## Lessons Learned
The EMU highlights eight lessons learned from the evaluation (section 5), applicable to LCDI2 programme delivery and also wider ODA funded programmes (Table 2).
Table 2 Eight lessons learned from the process evaluation
Lessons
Lesson 1 Adaptive governance structures are essential to achieve results in dynamic political contexts, but must be matched with clarity of responsibilities, strategic coherence, and appropriate resource management	45
Lesson 2 Effective MEL systems are essential enablers of adaptive management in policy-focused TA programmes.	46
Lesson 3 Strategic partnerships with the right institutions can be critical to programme success, but they require both formal engagement mechanisms and informal trust-building and can become dependent on key interpersonal relationships.	46
Lesson 4 Embedding change in national and sub-national planning systems is a critical foundation but sustainability of implementation depends on the capacity to act on those plans or policies; LCDI2 and similar policy-oriented TA programmes must bridge the gap between policy and practice.	46
Lesson 5 Sustainability planning should begin early and be treated as a design principle, not an end-phase activity.	47
Lesson 6 Political transitions and bureaucratic complexity must be anticipated as core risks, not externalities, in LCDI2-type TA programmes.	47
Lesson 7 Where direct funding is included within a broader programme, it can be an effective tool for advancing objectives and securing ownership provided there is clear alignment with other interventions and activities.	47
Lesson 8 For GEDSI to move from aspiration to impact at the provincial level, programmes must invest in tailored support, clear monitoring frameworks, and ongoing engagement with both government and civil society as well as other stakeholders, ensuring that inclusive development is embedded not just in plans, but in practice.	48

## Recommendations
The evaluation report presents 11 recommendations (section 6). A summary is provided in Table 3.
Table 3 Evaluation Recommendations
Recommendations
Recommendation 1 In the next phase of LCDI2, the impact of activities should be further enhanced via a sharpened focus on priorities.	49
Recommendation 2 There is an opportunity to strengthen alignment across workstreams by designing activities under WS3 and WS4 to strategically support WS1 and WS2, with a focus on high-impact goals and political economy challenges.	49
Recommendation 3 More focus within WS2 is needed on generating resources for LCD implementation and sustainability at the Provincial level as the primary enabler for success.	50
Recommendation 4 WS3 should develop a sharper overall focus and strategy. It has high potential for trans-formative effects and needs appropriate resource allocation.	51
Recommendation 5 The LCD narrative across WSs should be better linked with economic growth, job creation, and benefits for Indonesian people, including alignment to the needs of political actors to seek voter/community support.	52
Recommendation 6 LCDI2 should try to strengthen its institutional position as a key GoI partner through building relationships beyond Bappenas.	52
Recommendation 7 More focus within WS1 is needed on the development of annual LCD monitoring at the national level and enhancing knowledge management and sharing systems across GoI, providing practical guidance and mentorship under AKSARA or other monitoring systems.	53
Recommendation 8 The resourcing available and ambitions of the GEDSI strategy require review considering the findings of the evaluation.	53
Recommendation 9 To ensure the resourcing model for WS4 is optimal for funding new activities, several strategic and operational factors should be considered.	55
Recommendation 10 There are a range of potential ways to further strengthen the MEL System to support more effective programme implementation.	55
Recommendation 11 There is significant scope for LCDI2 to enhance linkages with other FCDO programmes and those of other Development Partners in LCD-related sectors, such as in leveraging technical expertise and joint planning or inter-linkage of goals.	56

# Acronyms Table
Acronym	Definition
ADB	Asian Development Bank
AI	Artificial Intelligence
AKSARA	Low-Carbon and Climate-Resilient Development Planning and Monitoring Application (Aplikasi Perencanaan dan Pemantauan Pembangunan Rendah Karbon dan Ketahanan Iklim)
AP	Approach Paper
APBD	Regional Budget (Anggaran Pendapatan dan Belanja Daerah)
APBDes	Village Budget (Anggaran Pendapatan dan Belanja Desa)
APBN	State Budget (Anggaran Pendapatan dan Belanja Negara)
APR	Annual Progress Report
AR	Annual Review
Bappeda	Regional Development Planning Agency
Bappenas	Ministry of National Development Planning
BAU	Business as usual
BEJ	British Embassy Jakarta
BIMS	Business Integrity Management System
BMKG	Meteorology, Climatology and Geophysics Agency
BNSP	National Professional Certification Agency
BPDLH	Environmental Fund Management Agency (Badan Pengelola Dana Lingkungan Hidup)
BUMN	State-Owned Enterprise
CARA	Climate Action and Resource Allocation
CHA	Change
COI	Conflict of Interest
CO2	Carbon Dioxide
CSO	Civil Society Organisation
CT	Contribution Tracing
DAC	Development Assistance Committee
DD	Doubly Decisive
ELQ	Evaluation and Learning Question
EMU	Evaluation Management Unit
EQ	Process Evaluation Question
EQUALS	Evaluation, Quality Assurance and Learning Service
FCDO	Foreign, Commonwealth and Development Office
FGD	Focus Group Discussions
FIDIC	International Federation of Consulting Engineers (Fédération Internationale des Ingénieurs-Conseils)
GDPR	General Data Protection Regulation
GIZ	Deutsche Gesellschaft für Internationale Zusammenarbeit
GEDSI	Gender Equality Disability and Social Inclusion
GEI	Green Economy Index
GHG	Greenhouse Gas Emissions
GoI	His Majesty
HM	Government of Indonesia
HMG	His Majesty’s Government
ICF	International Climate Finance
IO	Intermediate Outcome
ISO	International Organization for Standardization
KII	Key Informant Interview
KMS	Knowledge Management System
KPI	Key Performance Indicator
LCD	Low Carbon Development
LCDI	Low Carbon Development Initiative
LCDI1	Low Carbon Development Initiative Phase 1
LCDI2	Low Carbon Development Initiative Phase 2
LKD	Learning and Knowledge Dissemination
Logframe	Logical Framework
LPG	Liquefied Petroleum Gas
LQ	Learning Question
MEL	Monitoring Evaluation and Learning
MEMR	Ministry of Energy and Mineral Resources
MENTARI	UK–Indonesia Low Carbon Energy Partnership (Menuju Transisi Energi Rendah Karbon Indonesia)
MoEF	Ministry of Environment and Forestry
MoF	Ministry of Finance
MoHA	Ministry of Home Affairs
MoU	Memorandum of Understanding
MRV	Measurement, Reporting and Verification
NDC	Nationally Determined Contributions
NGO	Non-Governmental Organisation
NTB	West Nusa Tenggara (Nusa Tenggara Barat)
OECD	Organisation for Economic Co-operation and Development
OPD	Regional Government Agency (Organisasi Perangkat Daerah)
OPML	Oxford Policy Management Ltd
PEA	Political Economy Analysis
Perda	Regional Regulation (Peraturan Daerah)
PIRS	Performance Indicator Reference Sheet
PRKBID	Provincial Low Carbon and Climate Resilient Development Initiative
PV	Photovoltaic
QA	Quality assurance
QMS	Quality Management System
Renstra	Strategic Plan
RPJMD	Regional Mid-Term Development Plan
RPJMN	National Mid Term Development Plan
RPJPD	Regional Long-Term Development Plan
RPJPN	National Long Term Development Plan
RPRKBID	Regional Low Carbon and Climate Resilient Development Plan
SETAPAK	Save Forests and Land through Governance Improvement (Selamatkan Hutan dan Lahan Melalui Perbaikan Tata Kelola)
SG	Smoking Gun
SNA	Social Network Analysis
SRN	National Registry System for Climate Change (Sistem Registri Nasional)
TA	Technical Assistance
TKDN	Regional Content Requirement
ToC	Theory of Change
ToR	Terms of Reference
UK	United Kingdom
UNDP	United Nations Development Programme
UNFCCC	United Nations Framework Convention on Climate Change
VfM	Value for Money
WS	Workstream
WRI	World Resources Institute
WWF	Worldwide Fund for Nature

# Introduction
## Report overview
This report forms the Process Evaluation output, which aims to analyse whether the Low Carbon Development Initiative (LCDI) is being implemented as intended; including issues around whether the design is working and what is working more well or less well than intended and why. The rest of section 1 provides an overview of the programme, the national regional and global context and an overview of the Evaluation Management Unit (EMU). Following this section, the report covers the following structure:
Section 2: Methodology Summary
Section 3: Findings for each ELQ
Section 4: Conclusions
Section 5: Lessons Learned
Section 6: Recommendations

The report includes the following Annexes.
Annex 1 – The EMU terms of reference
Annex 2– The LCDI2 theory of change overview
Annex 3 – The evaluation methodology
Annex 4 – Evaluation matrix
Annex 5 – Learning use and influence plan
Annex 6 – Contribution tracing results
Annex 7 – Case studies
Annex 8 – ToC assessment
Annex 9 - Political Economy Analysis
Annex 10 – EQUALs criteria checklist
Annex 11 – Programme documents reviewed
Annex 12 – Bibliography
## Low Carbon Development Initiative programme overview
The Low Carbon Development Initiative (LCDI) is a partnership between the UK Government, represented by the Foreign, Commonwealth and Development Office (FCDO) operating through the British Embassy Jakarta (BEJ), and Government of Indonesia (GoI), represented by the Ministry of National Development Planning (Bappenas). Funded through the UK International Climate Finance (ICF), the first phase of LCDI was implemented between 2017 to 2021 (LCDI1) and successfully led to the integration of Low Carbon Development (LCD) into the National Medium Term Development Plan (RPJMN) 2020-2024.
The programme is currently in its second phase (LCDI2), which runs from 2023 to 2027. It aims to build on the success of LCDI1 by supporting the implementation of LCD at the national and sub-national levels to enable the GoI to set and meet its emissions reductions targets as set out in Indonesia’s RPJMN 2025-2029. The key actors for LCDI2 are: a delivery consortium led by Oxford Policy Management Ltd (OPML) contracted by FCDO to lead the implementation of LCDI2 (referred to in this report as the Delivery Partner); FCDO working via the BEJ as the LCDI2 donor; Bappenas as the primary GoI counterpart; and NIRAS as the Evaluation Management Unit (EMU, see section 1.4 below).
The specific aims of LCDI2 are to:
- Build political support for LCD within and outside of government;
- Build knowledge and understanding of the LCD approach among those who are responsible for implementing it within the GoI;
- Support the implementation of LCD through provincial and national development plans; and
- Raise LCD ambition to the highest levels.
An overview of LCDI2 outcomes and impact is provided in Figure 1.
Figure 1 Overview of LCDI2 outcomes and impact

Outcome 1: Implementation of strategic plans, policies, roadmaps, capacity building plans, financial and technical options, procedures and other TA products

Outcome 2: Greater support for higher ambition on low carbon development action by the Government of Indonesia

Outcome 3: Implementation of pilots on low carbon development technology.
IMPACT
Reduced GHG emissions against base case (aligned to NDC target) through reduced emission intensity.
Implementation of LCDI2 is via four Workstreams (WS):
- WS1: Partnerships with National Line Ministries. The programme will partner with key ministries to develop policies and plans to implement a LCD pathway. A particular focus is working with Bappenas to integrate LCD targets into the National Medium Term Development Plan (RPJMN 2025-2029) and align to the National Long Term Development Plan (RPJPN). Technical interventions include policy development, budgeting and reporting, and stakeholder engagement.
- WS2: Partnerships with Key Sub-National Governments. The programme will partner with selected provincial, district, and city governments in advancing the LCD agenda. At the provincial level, LCDI2 works with seven provinces, North Sumatera, Bengkulu, Maluku, NTB, Riau, West Papua, and South Sulawesi. These provinces and districts will be supported to mainstream LCD interventions into their Provincial Long Term Development Plan (RPJPD) 2025-2045 and Provincial Medium Term Development Plan (RPJMD) 2025-2029.
- WS3: Stakeholder Engagement. The programme will support key organisations to work politically and strategically to build domestic and international coalitions of support to encourage and support governments to deliver the GoI’s LCD goals.
- WS4: Innovation and Technology Fund. A competitive funding mechanism will be established to test scalable approaches for addressing the barriers to higher ambition LCD scenarios, including public policy, political, and technology constraints.
The Theory of Change (ToC) for LCDI2 can be found in Annex 2 and provide further details regarding expected programme outputs. The ToC was updated in April 2025 by the Delivery Partners in collaboration with FCDO to provide WS-specific ToC and identify intermediate outcomes. This updated ToC has been used within this Process Evaluation.

The Programme recognises that Gender, Equality, Disability and Social Inclusion (GEDSI) considerations require integration across the Workstreams to ensure outcomes with equitable benefits for women and vulnerable groups, that there is meaningful participation of women and vulnerable groups in the implementation of outputs, and that the Programme seeks to raise awareness among decision-makers within the programme team and Government agencies about the importance of GEDSI for the LCDI. Developing and implementing an appropriate GEDSI action plan is one of the key objectives of LCDI2. The LCDI2 GEDSI Action Plan targets a ‘twin-track’ approach as per the figure below and identifies a wide range of potentially beneficial actions to support the GEDSI agenda. Details and related findings are explored in section 3.3 of this evaluation. A GEDSI focused case study also explored the integration of GEDSI within the Low Carbon Development framework in the Medium Long Term Development Plan (RPJMN) and the Regional Medium Term Development Plan (RPJMD).

Figure 2 LCDI2 Twin Track approach to GEDSI[1]
[1] From LCDI2 GEDSI Strategy 2025

## National, regional and global context
Indonesia is the seventh largest emitter of CO2 globally.[2] Historically Indonesia’s economic model has been anchored in national resource extraction and carbon intensive industries, such as coal, palm oil and mining. LCDI1 represented a shift in the GoI approach to development, combining approaches to economic growth, social equity and environmental sustainability. It developed tools to support the implementation of LCD by achieving the emissions reduction targets as set out in the RPJMN (2020-2024). These include a standardised Green Economy Index (GEI) using system dynamic modelling, comprised of environmental, social and economic parameters to measure LCD progress at national and provincial levels. An online monitoring platform named AKSARA was also launched by Bappenas to measure LCD implementation at national and provincial levels. LCDI1 provided technical assistance (TA) to seven pilot provinces identified by Bappenas, including three provinces supported by FCDO. An overview of Indonesia’s policy journey on low carbon development from 1994 is provided in Figure 2.
[2] https://www.iea.org/countries/indonesia/emissions
LCDI1 culminated in the LCDI Report launched in 2019, “Low Carbon Development: A Paradigm Shift Towards a Green Economy in Indonesia”.[3] The LCDI Report provides an evidence and science-based roadmap of activities, results, and investment required to meet Indonesia's unconditional NDC target of a 29% reduction in GHG emissions compared to business-as-usual (BAU) (the medium ambition scenario) and conditional NDC target of a 43% reduction in GHG emissions (the high ambition scenario) by 2030.[4] The LCDI Report's targets were incorporated into Indonesia's five-year RPJMN (2020-2024). The Net Zero ambition was assessed in more detail in 2021, with a second LCDI Report charting the path to Net Zero GHG emissions via the implementation of a green post-Covid recovery plan. This Report presents several scenarios, with a zero emissions target by 2045, 2050 and 2060, as well as early and late action. It also presents the investment required, avoided costs and added benefits resulting from the realisation of such scenario.
[3] Low Carbon Development: A Paradigm Shift Towards a Green Economy in Indonesia, 2019. https://lcdi-indonesia.id/wp-content/uploads/2022/03/Low-Carbon-Development-A-Paradigm-Shift-Towards-a-Green-Economy-in-Indonesia-Full-Report-2019.pdf
[4] The reduction of emissions by 43% reflects the LCDI high ambition scenario modelled by Bappenas in their Indonesia Vision 2045 and INDOBIOM models.

Figure 2 Indonesia’s policy journey towards Low-carbon development

Despite the inclusion of LCD targets in the RPJMN and the subsequent exchanges in the context of post-Covid recovery and long-term Net Zero targets, Indonesia faces significant obstacles in transitioning to green and blue economies. As such, LCDI2 operates in a complex political environment, often with competing political priorities, such as President Prabowo Subianto’s policy priority of 8% annual growth (see political economy analysis in Annex 9 for further details). The barriers which LCDI2 has been designed to address and are identified in the LCDI2 ToC (Annex 2) include:
- Planning process: lack of LCD targets and objectives in strategic planning processes at national and sub-national level.
- Legal and policy framework: poor cross government commitment, legal and policy options and frameworks to integrate LCD.
- Information and accountability: ineffective monitoring, reporting and verification (MRV) systems and indicators including for tracking LCD progress.
- Financial: lack of harmonisation between LCD plans, policies and budgeting options and low private sector investment in LCD.
- Institutional capacity: difficulty in designing implementable LCD projects.
- Political engagement: low levels of engagement with LCD ambitions by stakeholders beyond Bappenas.
- Technology: low update of potentially available technology and potential to explore new technologies.
Furthermore, there is an urgent need to avoid exacerbating existing inequalities when pursuing a low-carbon economic transition. Efforts to mainstream LCD into national and sub-national development planning needs to be complemented with measures to offset the costs on the most affected sectors to ensure an inclusive and just transition.
During the RPJMN 2020-24 implementation, Bappenas prepared five building blocks for the mainstreaming of LCD and policy interventions, both at national level and with key provinces. Aligned with Bappenas’ LCD building blocks, LCDI2 intends to realise a low-carbon, resilient, inclusive economic development pathway for Indonesia. LCDI2 aims to provide a basis for implementing these building blocks through integration into the next National Long-Term Development Plan (RPJPN) 2025-45 and Indonesia Vision 2045.
In the context of the low-carbon sector, the Government of Indonesia has integrated GEDSI principles into the Long-Term Strategy for Low Carbon and Climate Resilience 2050 (LTSLCCR 2050). The strategy emphasises gender equality and women’s empowerment as key supporting factors for achieving long-term sustainable low-carbon development. Many of Indonesia sectoral plans also recognise the importance of GEDSI. For example, the government’s FOLU roadmap, released by the Ministry of Environment and Forestry (KLHK), acknowledges the need for inclusive, community-based partnerships, particularly those that elevate women, youth, and vulnerable groups in decision-making. But a key challenge for LCD is building effective strategies to reach ambitious agendas, with a low starting point in many sectors, such as the energy sector having only 5% of women in decision-making roles.[5] During 2025, LCDI2 completed the development of a GEDSI Action Plan, reflecting on what actions could be proportionate in terms of the Programme supporting GEDSI integration in LCD overall.
[5] https://www.ap-lawsolution.com/actio/electrifying-equitable-future-gender-inclusion-progress-in-the-just-energy-transition-partnership-of-indonesia
Given the current political environment in Indonesia and the mid-way point of LCDI2 programme delivery, this process evaluation is considered well-timed to understand what within the programme design is working well, as intended and why. In addition, the evaluation is timed to align with the 2024-2025 FCDO Annual Review and taking place alongside UK Government budget changes to ODA funding. The evaluation will also consider coherence of other relevant FCDO programmes operating in Indonesia, for example MENTARI, a four-year programme that aims to develop low-carbon energy in Indonesia between the Ministry of Energy and Mineral Resources (KESDM) of the Republic of Indonesia and the British Embassy Jakarta. The work of other relevant development partners in Indonesia will also be considered, for example UNDP and GIZ.
## Evaluation Management Unit overview
### EMU objectives and scope
NIRAS provides the Evaluation Management Unit (EMU) for LCDI2. The EMU has been tasked with providing Monitoring, Evaluation, and Learning (MEL) services over the course of the programme to FCDO and the LCDI2 Delivery Partners, principally via engagement with OPML as the consortium lead, from March 2024 to March 2028. FCDO and the Delivery Partners are the primary audience for MEL services for LCDI2. The Learning Use and Influence Plan in Annex 5 sets out the EMU’s approach for wider dissemination to secondary and tertiary audiences.
The primary purpose of the EMU is to maximise the LCDI2 programme’s efficiency, effectiveness, impact and sustainability. The secondary purpose is to strengthen the FCDO – and global – evidence base on how to foster green, resilient economic growth. It is expected the secondary audience for this Process Evaluation will be other GoI institutions, such as the Ministry of Home Affairs (MoHA) and Ministry of Finance (MoF).
As per the Terms of Reference (ToR), MEL services include providing support on request to the LCDI2 MEL system and monitoring framework, co-leading with the Delivery Partners on planning and delivering Learning and Knowledge Dissemination (LKD), leading on ICF KPI reporting, and providing an interim Process Evaluation in Year 2 (2025) and a final Impact Evaluation in Year 4 (2027). A full description of the MEL ToR can be found in Annex 1. The aims of the evaluations are:
a) A Process Evaluation will analyse whether the programme is being implemented as intended; including issues around whether the design is working and what is working more well or less well than intended and why.
b) Impact Evaluation, and/or impact assessment, will investigate what changes have occurred as a result of the programme, the scale of those changes, and an assessment of the extent to which they can be attributed to the programme.
#### Process Evaluation
This report is the Process Evaluation output. The approach to the Process Evaluation was discussed and agreed with FCDO in March 2025. It is set out in the EMU Process Evaluation Approach Paper[6], which was reviewed by EQUALs and received final approval from FCDO in June 2025. The scope of the evaluation outlined in this report does not represent any major changes to those set out in the Approach Paper or ToR, however some evaluation methodologies have been further refined in agreement with FCDO and the Delivery Partners, as further discussed in Annex 3. This evaluation focused on and collected data on activities, results and outcomes for LCDI2 delivery, covering the period from 2023 up until September 2025. The data collection period for the evaluation ran from July to September 2025. The scope includes data collection at the international, national and subnational level, including through field visits in LCDI2 supported provinces North Sumatera, Bengkulu and West Nusa Tenggara (NTB). A first draft of this report was shared with FCDO and Delivery Partners and their feedback has been incorporated. The time period for the Process Evaluation coincided with the FCDO Annual Review process for 2025, therefore activities were coordinated with the Annual Review activities to reduce burden on stakeholders.
[6] Information and documents relating to the EMU can be found on Devtracker: https://devtracker.fcdo.gov.uk/programme/GB-COH-01250443-GB-GOV-1-300675/summary
#### Terminology in this evaluation report
In this report the term EMU is used to refer to the Evaluation Management Unit delivering the evaluation. Delivery Partner refers to organisations delivering work under the LCDI2 programme, such as OPML and other consortium members. LCDI2 is used to refer to all actors involved in the delivery of the LCDI2 programme, including FCDO, Bappenas, and LCDI2 Delivery Partners.
### Inclusion of cross cutting issues within the evaluation
#### Gender, disability and social inclusion
The Process Evaluation has examined how LCDI2 plans to integrate Gender Equity, Disability and Social Inclusion (GEDSI) into implementation through a specific ELQ focusing on GEDSI and through a case study considering LCDI2’s contribution to the integration of GEDSI into planning documents relating to the RPJMN. The EMU has also considered the sampling approach for key informant interviews (KIIs) to ensure a socially balanced sample of KIIs as much as possible. In total 40% of KIIs described their gender as female.
#### Consideration of FCDO’s commitment to human rights, poverty and anti-corruption
Ultimately, LCDI2 is not directly targeting human rights or poverty alleviation, and so these were not central lines of enquiry for the EMU Process Evaluation. It is, however, expected that development benefits such as poverty alleviation, improved human rights, and enhanced anti-corruption measures will be reflected as indirect outcomes of LCDI2. The EMU has sought to evidence these where appropriate. This is likely to apply more to the Impact Evaluation, as opposed to the Process Evaluation.
#### Exploration of the Paris Principles
The Paris Declaration on Aid Effectiveness aims to improve the quality of aid and its impact on development. It outlines five fundamental principles: ownership, alignment, harmonisation, results, and mutual accountability. The ELQs listed in Section 2 explore these issues in various ways. In terms of the ownership principle, analysis was conducted for ELQ 1 regarding programme relevance to needs under the auspices of the Paris Climate Change Agreement. For alignment, the EMU assessed creation of capacities within local systems (relevant for ELQ 2 and 3). Harmonisation relates to the extent which LCDI2 promotes collaboration and coordination across different systems which was included within ELQ 2. The results and mutual accountability principle was supported by the strong evaluation component.
#### Conflict sensitivity
LCDI2 does not directly target conflict sensitivity as part of the programme, therefore it was not a central line of enquiry for this Process Evaluation. The EMU has considered any issues around conflict regarding ethical procedures in evidence collection, a consideration of sampling approach for KIIs, and in its duty of care to the EMU team members particularly when conducting field visits.
### EMU governance and management
The EMU has engaged with FCDO and the LCDI2 Delivery Partners through regular meetings throughout the evaluation to update on progress. A timeline for presenting findings from the evaluation was agreed with FCDO, including through sense-making workshops where the EMU presented early findings to FCDO for feedback and incorporation into the report. The EMU has also provided updates on specific methodologies, such as contribution tracing, political economy analysis and the case study approach to FCDO and Delivery Partners for feedback. This helps to ensure that outputs are fit-for-purpose.
The EMU coordinated a trilateral workshop with the Delivery Partner and FCDO in December 2025 to discuss MEL and governance adaptations resulting from the findings in this evaluation report and the FCDO 2024-2025 annual review. The workshop was used to gain FCDO and Delivery Partner insight in an annual learning cycle, and details around use and dissemination of the evaluation report, including for key secondary audiences such as Bappenas. The Learning, Use and Influence Plan (Annex 5) sets out how the evaluation outputs will be used and how the impact of their use will be monitored. A key objective for the EMU is to support adaptive programme management and decision-making. This evaluation will set out key priorities for adaptive management, including the identification of learning and knowledge products to support adaptive management.
Full governance arrangements, principles for collaboration and approach to conflict management are fully described in Annex 3.
### Ethics and safeguarding
The EMU has adhered to ethical principles in the conduct of evaluation activities by following the comprehensive set of systems and processes NIRAS has built for this: the NIRAS Business Integrity Management System (BIMS) and Code of Conduct. The EMU has also applied the FCDO’s Ethical Guidance for Research, Evaluation and Monitoring Activities (2019) to guide data collection and reporting to ensure that methods used adhere to the appropriate ethical principles and standards. A full description of the EMU’s ethical protocols are available in Annex 3.
Use of digital tools: The EMU has used a range of AI and digital tools to support the Evaluation, as set out in Table 23, Annex 3. The EMU has adhered to the FCDO Digital Strategy and AI Playbook for UK Government and has ensured appropriate quality assurance of any outputs generated by AI. A full description of the principles followed can be found in Annex 3.
# Methodology Summary
## Methodology overview
The EMU used a mixed methods approach for the Process Evaluation methodology. The methods used have been tailored to handle the complexity and challenges of the climate policy and strategic development space to generate robust contextualised findings and practical recommendations for future-UK programming. The EMU approach has been designed collaboratively with FCDO and OPML and has been adapted to fit the current programme delivery status. There have been no major changes from the ToR or Approach Paper; in some instances, methodologies have been further refined. For example, in the Approach Paper the EMU outlined a case study approach to Value for Money (VfM). The EMU has further developed this to instead integrate a VfM component across all the case studies (see Annex 3 for further details). Secondly the EMU has further defined and set out how digital tools were used to support the evaluation, such as Copilot. The principles applied are fully described in Annex 3.
This section provides an overview of the ELQ selection process, a summary of the methods used, evidence sources and limitations. Further details regarding the methodology can be found in the Annex 3.
## Evaluation and Learning Questions (ELQs)
Based on the priorities set out for the Process Evaluation from feedback from FCDO and OPML, the EMU developed six ELQs. The ELQs have been mapped onto primary and secondary DAC criteria. A set of Evaluation Questions (EQs) and Learning Questions (LQs) have been developed under each overarching ELQ (Table 4). In general:
- EQs reflect the evaluative purposes of the Process Evaluation. They are more open to capture a wide range of evidence to inform accountability and adaptive management, and
- LQs reflect the objective to produce learning and knowledge outputs alongside evaluative outputs. They aim to address issues related to the EQs but focus on more specific learning priorities. They should support longer term decision-making to optimise the programme’s impact in line with emerging developments in its wider context.
Together, the ELQs provide the overall framework for analysis and synthesis.
Table 4 ELQs including sub EQs and LQs
ELQ 1 To what extent is the LCDI2 programme design and ToC relevant for the delivery context and what adjustments could be beneficial?
Primary DAC Criteria: Relevance. Secondary DAC Criteria: Impact, Effectiveness, Coherence.
EQ 1.1 How can the ToC or the delivery model be improved to help support LCDI2’s intended Outcomes? Including in relation to: / Assumptions and causal pathways being clear and relevant to current and future delivery contexts. / Identification of Intermediate Outcomes / known effects of outputs delivered in WS1. / Capturing linkages between workstreams. / EQ 1.2 To what extent are approaches to monitoring the ToC fit for purpose? What adaptations, if any, need to be made? / EQ 1.3 What alternative pathways for achieving intended impacts can be identified? Particularly in respect of supporting Contribution Tracing.	LQ 1.1 What mechanisms should allow for LCD plans at central and provincial level to contribute positively to the LCDI2’s intended outcomes? / LQ 1.2 How could WS3 best support the other WSs? Considering conditions affecting Provincial developments and at the national the level in the coming years.

ELQ 2 How does LCDI2 fit within the broader landscape of climate initiatives in Indonesia?
Primary DAC Criteria: Coherence. Secondary DAC Criteria: Effectiveness, Impact, Sustainability.
EQ 2.1 How coherent is LCDI2 with related initiatives and partnerships both within and outside of FCDO and Bappenas? To what extent do synergies or overlaps exist? / EQ 2.2 Is LCDI2 building an effective network to influence the achievement of LCD objectives?	LQ 2.1 What are the most relevant initiatives and programmes for LCDI2 to consider in its delivery planning, and why, and how could they be better aligned with LCDI2?
	LQ 2.2 Is the initial context assessment for LCDI2 still relevant to changing GoI priorities?
ELQ 3 How can the effectiveness of LCDI2 programme management mechanisms be optimised?
Primary DAC Criteria: Effectiveness. Secondary DAC Criteria: Efficiency.
EQ 3.1 How can the effectiveness of LCDI2 programme Management mechanisms be optimised? With reference to operational arrangements, governance frameworks, and the working environment, considering: / the successes and challenges and what factors have influenced the achievement or non-achievement of results? / how well has the programme overcome or mitigated barriers and risks to its effectiveness?	LQ 3.1 What lessons from LCDI2 should inform improvements in programme Management for similar or related programmes?
ELQ 4 Is LCDI2 delivering value for money (VfM) against the 4Es framework?
Primary DAC Criteria: Efficiency.
EQ 4.1 Are programme resources being used Economically and Efficiently to deliver results? / EQ 4.2 What evidence is available that approaches to the programme are or will be Effective? / EQ 4.3 What evidence is available that approaches to the programme are or will be Equitable? / EQ 4.4 How well is the programme monitoring VfM and is there evidence of VfM evidence being used for resource allocation or other programmatic decision making?	LQ 4.1 What lessons about VfM could help improve the design and implementation of similar programmes?

ELQ 5 To what extent is the LCDI2 programme likely to contribute to sustainable change?
Primary DAC Criteria: Impact. Secondary DAC Criteria: Effectiveness, Sustainability
EQ 5.1 How effectively is the LCDI2 progressing towards the achievement of its intended outcomes and impacts? What are the key factors influencing this progress? / EQ 5.2 How well does the programme design reflect factors that will enhance its sustainability?	LQ 5.1 How can sustainability for LCDI2 best be defined and planned for? Including: / What is needed for it in different stakeholder contexts over the next 5-10 years? / What is needed around the commitment of stakeholders and technical and organisational capacity?
	LQ 5.2 How to ensure the resourcing model for WS4 is optimal for funding new activities?
ELQ 6 Is the GEDSI strategy effectively designed and integrated into LCDI2?
Primary DAC Criteria: Effectiveness. Secondary DAC Criteria: Sustainability
EQ 6.1 How well does the GEDSI strategy align with LCDI2 objectives and resources? Including: / What improvements can be made to enhance its effectiveness? / What are the gaps in GEDSI mainstreaming and what actionable recommendations can be made for its improvement? / Are adequate resources and processes allocated to GEDSI mainstreaming? / EQ 6.2 How can the logframe and ToC be strengthened in relation to achieving the GEDSI strategy?	LQ 6.1 What are the potential opportunities and challenges facing the effective implementation of the GEDSI strategy in the respective provinces?

## Summary of Approach
The Process Evaluation has used a range of methods to collect evidence for the ELQs, which have acted as the overarching framework for analysis and synthesis. The methods used include Contributing Tracing, ToC Assessment, Political Economy Analysis, Social Network Analysis, VfM and GEDSI Assessment. A full description of each method can be found in Annex 3. The Evaluation matrix is provided in Annex 4 which set outs the relevant ELQs, evidence sources and methods. The methods selected allowed for multiple routes of enquiry and required a broad evidence base.
The primary source of evidence for the Process Evaluation was key informant interviews (KIIs). The EMU conducted 99 semi-structured KIIs remotely and in-person across July to September. Overall, the EMU took a purposive sampling approach, ensuring careful consideration of data protection and ethical and safeguarding procedures. The EMU managed risks around limited stakeholder engagement set out in the risk management process (Annex 3) in Table 22. Where there are limitations in the evidence gathered in KIIs it has been noted in section 2.4.
To supplement the KIIs, the EMU also collected evidence through direct observation and engagement, for example during provincial field visits. Field visits took place to North Sumatera in July and September, Bengkulu in September and West Nusa Tenggara (NTB) in September. Secondary evidence was used through a desk review of existing programme documentation and secondary literature. A list of the programme documents reviewed can be found in Annex 11, and a bibliography is provided in Annex 12. This helped to inform the design of the KIIs and align to existing information and documentation as much as possible to minimise duplication.
Six case studies were conducted by the EMU to generate robust contextualised evidence of change. The case studies were designed to generate evidence for and align to the contribution tracing stories. Case study topics were selected to align with specific pathways of change in the ToC and informed by the Delivery Partner’s Change Harvesting results. The case study topics were:
Figure 3 EMU fieldwork in North Sumatera
1. Improving the interoperability of AKSARA with other databases
2. Revision of the National Energy Policy
3. Solar PV pilot in Samosir District
4. TA support to Provincial Government
5. Engagement of key parliamentarians
6. Integration of GEDSI into LCD in RPJMN
All case studies followed the same methodological approach to ensure consistency. A set of research questions was developed for each case study, which linked to the OECD DAC criteria and align to multiple ELQs.
All evidence was coded qualitatively using a framework based on the ELQs and categories identified from the document review. Coding occurred in MAXQDA and was exported to an Excel matrix. The EMU applied a process to assess the triangulation and saturation of the evidence used in the report. This has mitigated the risk of self-reported data from stakeholders. Throughout the report the EMU has provided a qualitative description of the evidence, highlighting any situations where information is provided by a single source or has limited triangulation. This ensured the EMU followed the principles of credibility and accuracy throughout the Evaluation and maintained independence and impartiality. Descriptive and explanatory synthesis have also been applied throughout the Evaluation. Throughout the evaluation, the EMU has also ensured independence and impartiality in the evaluation design. The EMU has closely managed potential conflicts to interest around the EMU’s independence, the process for this is described fully in Annex 3. Quality assurances process and risk management also provide mechanisms to ensure impartiality and independence, which are also described in Annex 3.
In this evaluation report, a summary of the KIIs and programme documentation has been included in each section of the findings.
### The Evaluation Team
The EMU team were able to work freely without interference during the evaluation. The team consisted of a Team Leader, who was well-qualified to lead the Process Evaluation with over ten years of experience in monitoring and evaluation. The Team Leader was supported by a core team of expert Evaluators, bringing together a range of experience relevant to the Process Evaluation including GEDSI expertise, VfM expertise, stakeholder engagement and policy expertise. The team is further described in Annex 3.
## Limitations
Limitations for the Process Evaluation are described below.
Programme delivery stage
LCDI2 is a four-year programme seeking to influence policy development through the provision of TA. However, policy development, from conception to presidential approval, can take several years with some recent examples taking four to five years. Also, LCDI2 is in its second year of delivery, and, according to the information available to the EMU, LCDI2 activities have largely focused on WS1 and WS2 to date. As such, the EMU is not table to fully demonstrate achievement of certain outcomes across all WS, particularly 3 and 4 during this Process Evaluation or fully assess the contribution to them. The EMU used this evaluation as an initial assessment for impact, with the expectation to more fully understanding contribution to impact in the Impact Evaluation.
Availability and comprehensiveness of evidence sources
The EMU aimed to use a diversity of evidence sources and include a range of stakeholders as much as possible throughout the evaluation process. It is noted that one limitation to the sampling of KIIs is that it was challenging to obtain KIIs with other GoI ministries. GoI included represent the views of individuals which may be a small sample of individuals. The EMU mitigated this limitation as much as possible through maintaining close conversations with FCDO and OPML and providing stakeholders with a letter of introduction for engagement. Despite this it was not possible to fully engage all relevant GoI ministries in the evaluation.
As noted in the SNA methodology, there is relatively more documented evidence available for programmes fully completed, for example LCDI1. This presents the risk of over-representing evidence and stakeholders from these programmes in the results. The EMU worked to mitigate this by carefully triangulating evidence from multiple sources to reduce the risk of bias, and by involving a diverse range of stakeholders in KIIs to capture a range of perspectives. Having said that, requests for KIIs with FCDO staff working on related ongoing FCDO Programmes did not come to fruition. There is therefore a significant gap in the evaluation’s understanding of lessons from and for those programmes and any potential efficiencies that could be made for LCDI2 through enhanced coordination with other FCDO programmes.
The EMU also requested to directly observe a wide range of programme activities throughout late 2024 and during 2025. Invitations were eventually limited to only two Policy Dialogue events and the Steering Committee in July 2025. This presents limitations on the analysis provided in the evaluation, particularly related to nuances regarding the quality of outputs, understanding the challenges for and success of activity implementation, and understanding the dynamics of stakeholder interactions.
Due to the sensitive and confidential nature of cost data, the EMU could not access specific cost breakdowns of activities of WS-level data from OPML. Overall cost data was shared. Therefore, the VfM assessment is based on information shared by OPML through their VfM assessment, information from alternative programme documents and qualitative data from KIIs. The quantitative analysis methods used in the EMU’s assessment was not possible. For example, it was not possible to complete the following:
- Cost driver analysis/key cost categories analysis;
- Unit cost analysis (for any standardised costs);
- Budget execution/ variation analysis; and
- Cost efficiency analysis of delivery costs.

The VfM assessment has focused on a qualitative assessment.
Evidence collection windows and site visit limitations
Site visits took place in September 2025, which was a month later than originally planned. Site visits were challenging to coordinate with activities happening for the Annual Review, requiring a longer period than expected to coordinate with stakeholders. This resulted in a condensed analysis and synthesis period which should be acknowledged as a limitation. In addition, in some cases it was not possible to conduct a site visit. For example, for the case study focused on the solar panelled water pump it was not possible for the EMU to directly visit Samosir. This was based on OPML’s advice concerning the risk of managing stakeholder expectations with regards to the progress of the solar panelled water pump. The EMU used alternative evidence sources such as wider KIIs and document review for the case study and any further evidence gaps will be considered as part of future learning products.
Bi-lingual evidence sources
Evidence from programme documentation and KIIs is in two languages, English and Indonesian, which has required specific support for coding, interpretation and translation. Evaluation experts fluent in Indonesian have supported the interpretation, but there is a small risk of misinterpretation of information from non-Indonesian speakers.

# Findings
In this section we present the key findings generated by our evidence synthesis. The EMU did not have any unexpected results. Rather than being grouped by ELQ, due to the cross-cutting nature of the findings identified, they are presented against four key themes of LCDI2 design, relevance and coherence, programme results and sustainability, gender equity, disability and social inclusion and programme management. The themes cover the agreed OECD-DAC criteria. For each finding, the relevant EQs are provided for clarity.
## LCDI2 Design, Relevance, and Coherence
Key EQs	ELQ 1 To what extent is the LCDI2 programme design and ToC relevant for the delivery context and what adjustments could be beneficial? / ELQ 2 How does LCDI2 fit within the broader landscape of climate initiatives in Indonesia?

Findings around the programme’s design, relevance, and coherence in relation to GEDSI are considered separately in section 3.3. A key success highlighted in that section is the development of an appropriate action plan for GEDSI. It also underlines that challenges now include ensuring appropriate programme resources are available for implementation alongside understanding of the action plan, ensuring the plan has traction across GoI stakeholders, and the importance of guidance from FCDO about priorities for resource use.
The evidence for the following findings includes programme documentation such as iterations of the ToC, logframe and correspondence around their development, the MEL Plan and Performance Indicator Reference Sheets (PIRS), quarterly and monthly programme reports, LCDI1 and LCDI2 Business Cases, the LCDI2 GEDSI strategy, a range of LCDI2 documents including the inception report, annual reviews, workplan tracker, and communication and outreach strategy, the LCDI2 provincial context assessments, and technical outputs such as the Green Economy Roadmap Indonesia 2021-2024.
Evidence from the wider literature includes RPJPN 2025-2045 and RPJMN 2025-2029, public material on other LCD development projects, and guidelines for AKSARA.[7] The section draws on previous EMU deliverables, such as the learning review on reflections from the implementation of LCDI1.[8] Figure 4 provides a summary of the KIIs used to evidence the findings in this section. A total of 49 KIIs have informed the findings in this section. 45% of the participants in the KIIs were female. The coding system described in section 2 was used to identify and analyse information for the relevant ELQs. A case study focused on engagement of key parliamentarians has also been referenced as an evidence source.
[7] https://lcdi-indonesia.id/pedumjuknis-aksara
[8] The EMU produced the learning piece on Reflection on the implementation of LCDI1 in April 2025, which sets out key lessons from implementation in Riau, South Sulawesi and West Papua.
Figure 4 A summary of KIIs per stakeholder group and disaggregation by gender ((ELQ 1 and 2)

Finding 1 The underlying theory of LCDI2[9] is well aligned to supporting the green transition in Indonesia, blending national and sub-national TA activities to accelerate multi-level progress. However, while initial flexibility supported adaptability of the programme, the breadth and flexibility of the ToC has resulted in reduced clarity around the causal pathways, intermediate outcomes and assumptions, and there is a need to sharpen these to increase clarity.	Relevant EQs / (Table 4)
	EQ1.1, EQ1.3, EQ2.2
[9] This refers to the latest version of OPM’s ToC, as shown in Annex 2.

As per the PEA (Annex 9), Indonesia has been trending towards green economy outcomes over the past two decades, but progress has been relatively slow, primarily hindered by limited technical capacity and shifting political motivations. In this context, the central theory underpinning LCDI2, that TA related to policy development and green economy modelling for key GoI institutions, appears highly relevant. The ToC assessment (Annex 8: ToC Assessment) scored the ToC highly on relevance to local context, providing a clear overall narrative, plausible causal pathways, and appropriate use of key terms and concepts.
Each of the four workstreams offers a distinct pathway contributing to the achievement of intended outcomes. Interview participants highlighted the provision of evidence-based TA at both the national (WS1) and provincial (WS2) level as being both relevant and necessary to ensure the implementation of LCD plans. There was a more mixed perspective of WS3 and WS4, with participants typically finding them to be partially relevant, but in some cases expressing confusion about their inclusion within the programme or distinction from the other workstreams, particularly regarding WS3.
The adaptive delivery model embedded within the ToC is also found to be relevant to the context. Shortly after the programme start up, Indonesia held national elections which resulted in a change of President and key figures in LCDI2 partner ministries, impacting delivery priorities. The flexible nature of the LCDI2 ToC has enabled a relatively dynamic response to those shifts in the political context, although some interview participants have stated that the programme offers too much flexibility and is too responsive to ad hoc requests of GoI such as last-minute inputs to presentation materials or unplanned research, which can create unexpected strains on programme resourcing.
Interview participants specifically noted the positioning of LCDI2 as working through or alongside key institutional frameworks such as the RPJMN/RPJPN, Renstra and RPJMD as being the right “home” for the programme, anchoring its delivery within national policy frameworks. As a result of this positioning, GoI respondents recognised ownership of LCDI2, referring to it as part of an “official planning system”.
However, while the overall programme theory and structure is relevant, there have been challenges identified in the details of the ToC and activity design. A key issue noted by interview participants and in the ToC review is the lack of concrete intermediate outcomes to measure delivery progress and articulate clearly how programme outputs will lead to the desired outcomes. So far, the programme has deliberately kept a broad range of intermediate outcomes and outcomes to allow for adaptability in programme delivery and embed learning. A key concern raised by stakeholders is this creates confusion on LCDI2’s objectives and the purpose of some activities. A further concern raised by interview participants is the current ToC is trying to accommodate too many activities. Whilst this allows for flexibility, it creates challenges through the lack of tangible higher-order targets against which the programme is assessed.
The ToC assessment also highlighted that the programme assumptions are relatively limited and generic. This is attributable to the broad and adaptive nature of the ToC. The articulation of more specific assumptions is now necessary to test and ensure causal links between outputs and outcomes are working as intended and to allow the programme to make strategic targeted adaptations where they are not. Assumptions are made at the overall ToC level, rather than for each workstream, although workstream specific assumptions are noted in limited cases. Therefore, some workstreams, most notably WS4, are underrepresented in the assumptions. In several cases, assumptions are made about the quality of the LCDI2 delivery (i.e. that outputs are useful or that stakeholder engagement approaches remain relevant) rather than the context in which delivery is undertaken, reflecting elements which should be within the programme’s control and implicit within the ToC inputs.
An early challenge in achieving coherence between the workstreams has been the need for the programme to be highly responsive to GoI needs and priorities alongside political delays and disruptions. This has negatively impacted the programme’s ability to sequence activities coherently. However, the ToC assessment found a lack of explicit linkages between workstreams, which limits internal coherence and obfuscates the theory. There are implicit interconnections between the workstreams (such as national policy developments under WS1 inform sub-national work under WS2; building political engagement under WS3 accelerates policy buy-in for WS1; etc.) but these are not articulated in the ToC and it is unclear the extent to which these linkages inform activity design. One point highlighted in interviews is the delayed start of project support under WS4, which has potential to incentivise engagement with WS2 activities and ground local policy decisions with tangible results, but this linkage has not been effectively leveraged to date.
In terms of alternative pathways to change, the evidence broadly agrees that LCDI2 has selected appropriate pathways (i.e. TA for national and sub-national GoI institutions, complemented by political mobilisation and pilot project funding) but interview participants expressed a variety of perspectives on how these pathways could be better operationalised. Common points raised include working with other GoI institutions at a national level to expand policy influence, providing more long-term embedded support to key institutions, widening the engagement strategies under WS3 to better integrate private sector and civil society via coalition building, and the point noted above about using WS4 pilots to inform and ground WS2 policy decisions and implementation plans. This speaks further to the points raised above, that the level of flexibility within the LCDI2 programme and ToC design can create confusion. The current ToC can accommodate many of these activities, but stakeholders do not have a clear understanding as to whether it should or will deliver them.
Finding 2 LCDI2 is broadly coherent with the green economy sector in Indonesia, both in terms of the key institutions it seeks to engage and the activities of other development partners and interventions. However, there remains a lack of clarity about LCDI2’s role within the ecosystem and scope to widen engagement, particularly with other GoI ministries and Directorates in Bappenas.	Relevant EQs / (Table 4)
	EQ2.1, EQ2.2, EQ1.3

LCDI2 has made significant strides in engaging a diverse and relevant set of stakeholders essential for advancing LCD in Indonesia. The social network analysis and the programme’s own stakeholder mapping, supported by interview respondents, reveal that LCDI2 is anchored within Indonesia’s core planning institutions, holding a close relationship with Bappenas via the Directorate of Environment. It also highlights the programme has reached out to and engaged provincial planning agencies such as the Bappedas and other line ministries including MoHA, MoF and MEMR. This engagement is further enriched by informal collaboration with international development partners such as GIZ, United Nations Development Programme (UNDP), World Resources Institute (WRI), and UK Partnering for Accelerated Climate Transitions (UK PACT), ensuring that LCDI2’s work is informed by global best practices and avoids duplication.
However, the 2024 Annual Review (AR) underlined that there is also significant scope for joining up with other FCDO initiatives in the selected provinces. Suggestions from the AR include work on climate budget tagging through Climate Action for a Resilient Asia (CARA) and or environmental policies alongside SETAPAK. Other options could be alignment with the Low Carbon Energy Partnership’s (MENTARI) brokerage strand and WS4, or synergy in monitoring and reporting GHG emissions linked to environmental degradation alongside Investing in Nature, Forests and Land Use (INAFOLU). Little evidence was available of enhanced collaboration among such FCDO initiatives during the period since the 2024 AR and stakeholders in general encouraged more coordination across FCDO and wider LCD-related initiatives in Indonesia to drive gains in the efficiency and effectiveness of LCDI2.
Overall, LCDI2’s stakeholder engagement approach is well-suited to the complex and evolving landscape of LCD in Indonesia. The programme’s strategy is characterised by flexibility, technical credibility, and a willingness to adapt to changing political and institutional contexts. Stakeholders consistently and positively acknowledge LCDI2’s ability to convene diverse actors and respond to shifting political priorities. The programme has demonstrated an ability to adjust its strategies in response to political turnover, fiscal constraints, and evolving stakeholder needs. This flexibility has helped maintain relevance and continuity, even as Indonesia’s policy environment undergoes rapid change.
At the heart of the LCDI2 approach is a multi-level engagement strategy that targets central government agencies, provincial and district governments, development partners, CSOs, academia, and the private sector. LCDI2 has fostered multi-stakeholder platforms, such as the recently established Technical Committee and provincial working groups, that facilitate dialogue and coordination across sectors and governance levels. These platforms have reportedly enabled the integration of LCD concepts into national and provincial planning documents and have facilitated capacity building through initiatives like the Green Academy and AKSARA trainings.
At the provincial level, there is evidence that LCDI2 has supported the establishment of LCDI Task Forces in North Sumatera, Maluku and West Nusa Tenggara (NTB) to lead, coordinate, and drive the implementation of LCD and development of the Regional Low Carbon and Climate Resilient Development Plans (RPRKBID).
More broadly, LCDI2 operates with a high degree of coherence within Indonesia’s LCD ecosystem. The programme’s technical and policy support is well embedded in Bappenas’s planning processes. It has positioned itself to coordinate collaboration across ministries, provinces, and development partners, although evidence of this coordination has been limited to date. LCDI2’s work is closely aligned with national priorities, including the Net Zero 2060 commitment, the Clean Indonesia Vision, and the Green Economy Transformation agenda.
While LCDI2’s reach is impressive, some sectoral ministries (such as Industry and Transportation) remain less involved, with institutional silos and bureaucratic layering limiting cross-ministerial engagement. Interview respondents raised challenges regarding the engagement with Bappenas, noting that there has been limited collaboration with other relevant Directorates (such as Forestry and Water Resources, or Energy, Mineral and Mining Resources), finding that the Directorate of Environment can be a bottleneck for engagement. Gaining influence and managing effective coordination across GoI beyond Bappenas is recognised as likely requiring significant effort, requiring resources, time, and careful additional planning by LCDI2 including FCDO and Bappenas. This is further complicated by a lack of coherence with LCD priorities among certain GoI policy sectors, such as Energy and Agriculture, which is expected to hinder or at least complicate cross-ministerial coordination.
At the sub-national level, while the programme is targeting the right stakeholders for participation, interview respondents have raised issues relating to resource and capacity constraints, noting that more in-province presence and engagement would be beneficial to building long-term, trusted relationships. Across both levels, engagement with non-governmental actors and the private sector has, to date, reportedly been responsive and ad hoc, rather than systematic. At the same time, interviews highlighted the competition for human resources between related initiatives in Indonesia which have increased difficulties of any one initiative being able to recruit and mobilise technical expertise in a timely way, a challenge experienced by LCDI2 per Finding 12 and an unexpected consideration when exploring programme coherence.
Under WS3, the programme is specifically targeting parliamentarians with a view to increasing their public support for LCD in Indonesia. As highlighted in Case Study 5 (Box 1), the first of these engagements has been with two parliamentarians (one of whom has since announced their retirement) who had an existing favourable position concerning LCD. It is unclear from the ToC whether the intention under WS3 is to build on existing LCD support, or to broaden support across parliamentary actors. If the former, while interview respondents disagreed on exactly who should be engaged, it does seem the programme has made appropriate selections. If the latter is the intention, the programme will need to adjust and expand its parliamentary engagement. This raises an important consideration for the LCDI2 programme: if measuring LCD support on a scale of one to ten, is it more impactful to move stakeholders from a seven to an eight, or from a two to a five?

Box 1 Engagement of key parliamentarians (ELQ1, 2, 3, 4 and 5) / Research Question: How has LCDI2 contributed to Eddy Soeparno and Rahayu Saraswati expressing increased support for LCD action publicly? / Scope: Case Study 5 examined how LCDI2 contributed to the engagement of key parliamentarians, Eddy Soeparno and Rahayu Saraswati, and increased public support for LCD. Under WS3 LCDI2 aims to foster inclusive and strategic stakeholder engagement, recognising the importance of collaboration for successful LCDI2 delivery; this study assesses one dimension of WS3 related to LCD champions at parliamentary level. / Evidence Sources: KIIs with the Delivery Partner, FCDO and Bappenas, as well as programme observers and other development partners, supported by a review of public sources and media articles related to the parliamentarians. It was not possible to interview the parliamentarians themselves during this Process Evaluation. / Key Findings: The following key insights were generated by the case study analysis. / The Importance of Engaging Parliamentarians / Engaging members of parliament is a critical component of LCDI2’s policy advocacy strategy, particularly given their roles in legislation and budget allocation. Interview participants from CSOs highlighted the relevance of this engagement, noting that some parliamentarians are perceived to represent fossil fuel interests, underscoring the need for proactive outreach to balance perspectives and promote LCD. / In February 2025, LCDI2 Delivery Partners undertook a comprehensive political landscape assessment. This included mapping key political stakeholders, analysing party platforms, and reviewing legislative agendas relevant to LCD implementation. The assessment drew on a literature review, Discourse Network Analysis of 198 media articles, and interviews with influential members of the national parliament (DPR) to better understand their positions and potential influence on climate-related policy and budgeting. / From this, Eddy Soeparno and Rahayu Saraswati emerged as particularly strategic figures due to their existing public advocacy, political influence (both personal and party-based), and prominent roles within parliament. / No Evident Shift in Parliamentary Support / Both Eddy Soeparno and Rahayu Saraswati had publicly expressed support for climate action and energy transition prior to any engagement with LCDI2. This was evident through various public statements and media articles. While LCDI2 has initiated contact with both individuals, there is currently no indication that this engagement has led to a shift in their views or positions; their support appears consistent with their pre-existing stance, rather than a result of programme influence. Likewise, there is no evidence yet that the engagement has influenced other parliamentarians to increase support for LCD. / Efficiency and Challenges in the Engagement Process / The process of engaging high-profile parliamentarians has faced several operational challenges. Delays were experienced due to the need for careful wording in the ToR for proposed candidates, as well as difficulties in scheduling meetings with busy individuals. These factors have contributed to reduced efficiency in the engagement process. / Based on these results, the case study identified several lessons: / Engagement of key parliamentarians is a promising strategy to facilitate better integration of climate priorities into policy and regulation. / There is a need for continued mapping of champions, capacity building, and linking LCD narratives to broader economic and social priorities. / Delivery Partner team members are often engaged at the activity level; for parliamentarian engagement, they also need to be informed about the progress on other workstreams, such as LCD integration in development plans at the national and sub-national levels, to facilitate better parliamentarian support.

## Programme Results and Sustainability
Key EQs	ELQ 5 To what extent is the LCDI2 programme likely to contribute to sustainable change?

Findings around the programme’s results and sustainability in relation to GEDSI are considered separately in section 3.3. That section underlines the GEDSI Action Plan implementation is in its early phases. More resources are needed to enhance results and effectiveness with greater attention is needing on ensuring integration across all Workstreams.
Evidence used to inform the following findings was drawn from 24 programme documents including LCDI2 Business Case, ToC and logframe documents, the MEL Plan and Performance Indicator Reference Sheets, quarterly and monthly programme reports, annual LCDI2 reports. Wider literature reviewed includes LCDI1 documentation and government development plans, such as RPJPN, RPJMN, RPJPD, and RPRKBID. The EMU notes that a limitation in the evidence is that they have not yet received and assessed the RPRKBID and RPJMD in all priority provinces, including Bengkulu, NTB and Maluku. Figure 5 provides an overview of the number of KIIs conducted per stakeholder category. In total 71 KIIs were coded for the findings. Evidence was extracted from the KIIs using the coding approach described in Section 2. The contribution tracing results have been used to support the findings alongside case study findings from case studies focusing on TA support to Provincial Government in NTB, Bengkulu and North Sumatera and solar PV pilots in Samosir District.
Figure 5 Summary of KIIs per stakeholder category and disaggregation by gender for ELQ 5

Finding 3 LCDI2’s adaptive design and strategic partnership with Bappenas have allowed it to effectively navigate certain barriers inherent to the dynamic political context, but initial delays in starting and fully resourcing the programme hindered progress towards Outcomes until later in 2024. It continues to face significant risks from external developments.	Relevant EQs / (Table 4)
	EQ5.1, EQ3.1

Progress towards Outcomes must be seen in the dynamic context in which LCDI2 operates. While each of the workstreams has been influenced by different drivers, there are several factors common across the workstreams. These have enabled effective results achievement and progress towards key Outcomes. Foremost among these is the strategic partnership with Bappenas. Building and maintaining an effective working relationship with Bappenas has provided continuity between the phases of LCDI, ensured the programme is plugged directly into national planning processes, and provided national credibility to the activities and outputs of LCDI2. LCDI2’s responsiveness to Bappenas’ evolving priorities, while sometimes disruptive to internal coherence, has helped build trust and ensure delivery reflects emerging priorities.
This partnership approach has similarly been an enabling factor at a provincial level, with sub-national government institutions in North Sumatera, Bengkulu, NTB, and Maluku acting as key partners in integrating LCD into RPJMDs and RPRKBID documents. However, some in Bappenas consider the LCDI2 programme as a ‘think tank’ to provide bespoke TA and analysis rather than a more strategic, embedded partner. This undermines the potential of the programme and its ToC, reducing its utility to key GoI partners. This is linked to evidence suggesting a perception of a lack of concrete actions being taken to navigate funding challenges.
Maintaining effective relationships has required an adaptive approach. Six months after the start of the programme, the general election was held in Indonesia. Among wider political changes, this also resulted in personnel changes within Bappenas and other key institutions, triggering delays in delivery due to onboarding of new counterparts late in the Inception Period. At the sub-national level, frequent rotation of government personnel and limited technical capacity have undermined continuity in key relationships and required a dynamic approach to delivery. Interview participants have offered differing perspectives on this challenge, with some arguing that longer-term embedded support is needed for continuity and others suggesting a nimbler approach to offer a more responsive and value for money option.
Institutional fragmentation has also posed a major challenge. Government ministries and agencies often operate in silos, with overlapping mandates and differing terminologies (e.g., LCD, green growth, sustainable development). This has complicated coordination and has slowed the integration of LCD across sectors. Even within Bappenas, navigating multiple directorates and leadership changes has required frequent adaptation. Interview respondents often describe a bottleneck represented by the Directorate of Environment through which the programme needs to work, and which results in slow engagement with other line ministries of directorates.
Alongside the personnel turnover, several other factors have contributed to delays in delivery. The first is that the programme itself started later than originally planned, delaying the mobilisation of the delivery team and the start of core activities, compressing the timeline for achieving early milestones. This additionally created a gap period between LCDI1 and LCDI2, meaning greater effort was required to restart delivery momentum.
Once the programme entered its Inception Phase, interview respondents noted there were significant delays in recruiting key personnel, including the Deputy Team Leader, Workstream Leads, and MEL Manager. This was compounded by requests for technical support from Bappenas to feed into the RPJPN coming sooner than anticipated by the team, although it should be noted the need to begin providing technical inputs during the Inception Phase was referenced in the programme ToR. The LCDI2 delivery team were able to accelerate mobilisation to meet these early demands, but this caused significant disruption to the inception process and finalisation of the programme design. It also created early relationship tensions between the key LCDI2 parties which has required dedicated effort to rebalance.
Finding 4 LCDI2 has achieved several key results during its first two years of implementation, particularly across WS1 and WS2, building on the momentum generated by LCDI1 and embedding LCD in key policies and planning documents.	Relevant EQs / (Table 4)
	EQ5.1

Evidence including the programme reporting, technical outputs and KIIs, further supported by public policy documents, indicates that LCDI2 has made a meaningful contribution to policy-level change in Indonesia, particularly in embedding LCD principles into national and sub-national planning frameworks. Both the Contribution Tracing and Change Harvesting also identified some important changes attributable to recent and older programme activities, particularly in terms of integration of LCD in national planning and legislation, provincial capacity building, and early signs of increased political motivations. A summary of results against the LCDI2 logframe is provided in Table 5.
Table 5: Summary logframe results as of August 2025
Indicator	Target 2025 (Sep 24–Aug 25)	Achieved (Aug 25)
Outcomes
1.1 LCD is integrated into government planning at national and provincial level	LCD targets are integrated in RPJPD and RPJMN	LCD integrated in RPJPN
1.2 Government actions decisions support LCD planning implementation	3 actions (with meaningful LCD impact and LCDI contribution)	Ongoing
2.1 Increased ambition for LCD by key stakeholders	1 (new indicator for Y2/2025)	N/A
3.1 Successful pilots of LCD technology	BPDLH has signed Fund Agreement (new indicator Y2/2025)	N/A
Outputs
1.1 Number of high-quality contributions developed to integrate LCD into national plans	7	7
1.2 Number of high-quality TA products for LCD implementation (national)	12	12
2.1 Number of high-quality contributions developed to integrate LCD into sub-national plans	5	8
2.2 Number of high-quality TA products for LCD implementation (sub-national)	7	18
2.3 Number of provinces receiving high-quality training	4	5
3.1 Number of high-level/high-profile stakeholder engagements	15	22
3.2 Number of high-quality knowledge products that build support for LCD	8	13
4.1 Number of high-quality TA products for Innovation and Technology Fund	5	5

At the national level, interview respondents mostly agree that the programme’s TA, particularly through systems dynamic modelling and scenario development, has so far helped Bappenas define ambitious targets for emissions reduction and green growth. LCDI2 played a pivotal role in shaping the inclusion of the Green Economy Index (GEI) and circular economy principles within the RPJPN and RPJMN as highlighted in Box 2. It contributed to the production of the GEI through TA and technical inputs, which was incorporated into the RPJPN as a key indicator with a 2045 target of 90.65%. LCDI2 also contributed to the development of the Circular Economy Roadmap and Action Plan, which was launched at the Green Economy Expo 2024 and integrated into the RPJMN draft.[10] Emerging evidence also points to LCDI2’s role supporting sectoral policies per Box 3.
[10] https://www.un-pageindonesia.org/en/publication/read/circular-economy-roadmap-and-national-action-plan-for-2025-2045
Box 2 Contribution tracing results: integration of LCD into national planning / Contribution story: By providing Bappenas with studies and roadmaps for integrating LCD in priority sectors, Bappenas is informed of the options for integrating LCD in priority sectors, enabling them to integrate LCD into national planning through its inclusion in the RPJPN 2025-2045. / Evidence snapshot: The RPJPN 2025-2045 was published in November 2024 and clearly includes LCD targets. Evidence is emerging of the LCDI2 contribution to LCD inclusion in the RPJPN. Multiple sources including KIIs with Delivery Partners and programme documentation such as LCDI2 Quarterly Reports and LCDI2 annual reviews show that LCDI2 provided modelling targets and policy scenarios for sectors to Bappenas to support the development of the RPJPN. Bappenas acknowledged the technical contributions of LCDI2 inputs into the RPJPN in KIIs, providing a strong piece of evidence for contribution. / Level of confidence: Overall the EMU has a medium level of confidence in the contribution of LCDI2 in the integration of LCD in the RPJPN at this stage. The full contribution tracing can be found in Annex 6.

Strategic partnerships have been central to the achievement of programme results, especially with Bappenas, which provided a direct channel into national planning processes. According to programme reporting, technical support including modelling and sectoral assessments reportedly gave planners the tools and evidence needed to integrate LCD into policy. Capacity building efforts, such as the Green Academy and training on system dynamics, helped institutionalise knowledge and build long-term capability within government agencies. These contributions have been partially recognised by beneficiaries in interviews.
At sub-national level, one of the most tangible outcomes has been the integration of LCD into provincial development plans in provinces such as North Sumatera, Bengkulu, NTB, and Maluku (Box 4). These provinces have adopted key indicators, such as the GEI and GHG reduction targets, into their planning frameworks, aligning them with national goals. In some cases, such as Maluku, the targets are even more ambitious than those at the national level. LCDI2 also supported the development of RPRKBIDs, which provide detailed, long-term guidance for implementing LCD strategies. These documents have become reference points for provincial governments and sectoral agencies, helping to ensure that LCD is not just a policy aspiration but a practical planning priority.
Box 3 Contribution tracing results: alignment of policies and plans / Contribution story: By conducting analysis, modelling exercises and briefing GoI Ministries, GoI Ministries are able to deploy the requisite expertise to develop policies, plans and strategies that integrate LCD and align to the RPJPN. / Evidence snapshot: The EMU has observed LCD integration in various policies, sectoral plans and strategies: / The revised National Energy policy[11] includes the integration of LCD strategic in in Article 13. / Bappenas published ‘Low carbon development strategies and stages in the in the 2025-2045 RPJPN efforts to achieve net zero emissions[12], which was signed by the Minister. / The RPJMN 2025-2029 was published in February 2025, which includes strategies and targets for LCD. / The publication of the ‘low carbon development strategies and stages in the in the 2025-20245 RPJPN efforts to achieve net zero emissions’ provides strong evidence of contribution. Signed by the Minister, the document credits OPML staff and the LCDI2 programme in supporting its development. / Level of confidence: Overall, the EMU finds a high confidence in the contribution of the LCDI2 team regarding some of the specific outcomes evidenced to date. The full contribution tracing can be found in Annex 6.
[11] https://lestari.kompas.com/read/2025/02/04/170500486/rpp-ken-disetujui-ebt-bakal-digenjot-hingga-70-persen-pada-2040-
[12] https://lcdi-indonesia.id/wp-content/uploads/2025/05/Strategi-dan-Penahapan-Pembangunan-Rendah-Karbon-dalam-RPJPN-2025-2045-Upaya-mencapai-Net-Zero-Emissions.pdf

The programme’s success at the sub-national level has again been underpinned by strong engagement with provincial planning agencies, the Bappedas, which play a central role in coordinating development planning. LCDI2 provided TA including training on system dynamics modelling to help these agencies set realistic and evidence-based targets. However, while the modelling has increased awareness and support, capacity gaps remain, particularly in the ability of local officials to independently apply these tools.
Beyond planning, LCDI2 facilitated multi-stakeholder workshops and policy dialogues, bringing together government officials, parliamentarians, civil society, and academia to build consensus and commitment around LCD. In Bengkulu, for example, LCDI2 helped broker agreements between Bappeda and sectoral agencies to integrate LCD into strategic plans, with documented commitments to identify and align relevant programmes and activities.
It should be noted that the programme is substantially exceeding certain logframe targets, in some cases exceeding the end target such as output indicator 2.2. This presents a good opportunity for the Delivery Partners to reassess programme ambition and reflect on the appropriateness of other targets within the logframe given these early results.
Finding 5 LCDI2’s progress under WS3 and WS4 has been more limited compared to WS1 and WS2, though important foundational steps have been taken that could enable stronger results in the future.	Relevant EQs / (Table 4)
	EQ5.1

WS3 was designed to strengthen political support for LCD by engaging national and sub-national legislators, building coalitions, and fostering policy advocacy. While the programme has made some initial strides, progress has been slower and more fragmented than anticipated. At the national level, LCDI2 undertook efforts to identify and engage influential parliamentarians who could champion the LCD agenda. Notably, the programme mapped and approached figures such as Eddy Soeparno and Rahayu Saraswati as potential LCDI commissioners, per Box 1. These individuals were seen as strategic allies capable of advancing LCD within legislative processes. However, the momentum was disrupted by procedural delays, particularly the lengthy review of the ToR for parliamentary engagement, and by the resignation of Rahayu Saraswati from parliament in September 2025. These setbacks have limited the programme’s ability to formalise and operationalise its engagement strategy at the national level.
Despite these challenges, LCDI2 did manage to initiate dialogue with sub-national political actors. In North Sumatera, for example, the programme facilitated a policy dialogue that brought together provincial parliament leaders, government officials, civil society organisations, and media. During this event, parliamentarians reportedly expressed interest in supporting LCD initiatives and acknowledged their limited understanding of the topic, highlighting a clear need for capacity building. This engagement is promising, as it suggests a willingness among sub-national legislators to learn and participate in the LCD agenda, provided they receive the necessary support.
There is not yet evidence that these engagements have translated into sustained political action or formal commitments. Interview respondents point to the absence of a comprehensive communication strategy and delays in forming a steering committee of national figures as being key constraints. As noted in Finding 2 above, WS3 has also largely engaged parliamentarians who are known for being pro-LCD – Eddy Soeparno has, for example, been actively and publicly advocating for carbon trading, green finance, and low carbon economy integration as key growth opportunities in Indonesia for several years. While this is a valid strategy to launch the political engagement activities, it somewhat undercuts LCDI2’s contribution to the result, if the targeted individuals are already strongly supportive.
Box 4 TA support to Provincial Governments in NTB, Bengkulu and North Sumatera Relevant for ELQs 1 – 6) / Research Question: How has delivering TA supported the technical capacity building of Provincial Government to integrate LCD in the RPRKBID and the RPJMD? / Scope: Case Study 4 aimed to explore how LCDI2 TA to provincial government in NTB, Bengkulu and North Sumatera supported the development of RPRKBID and the integration of LCD in RPJMD. LCDI2 aimed to support the development of RPRKBID and the RPJMD through strategic partners in each province to facilitate workshops and discussions and develop scenario modelling. / Evidence Sources: Over 36 relevant KIIs were synthesised for this case study, including from Delivery Partners, provincial government institutions across all three provinces, and external experts and development partners. This was complemented by a review of programme documentation, secondary literature and a field visit to each province. / Key Findings: The following key insights were generated by the case study analysis. / According to local stakeholders, TA strengthened provincial governments’ awareness, commitment, and capacity to integrate LCD into planning documents including the RPRKBID and RPJMD. / Interviewees from provincial governments stated the training in system dynamics was useful but too short at this stage to develop sustained modelling skills. They indicated more time for training in GHG emissions calculations would be useful. / Workshops and discussions facilitated by the Delivery Partners were reportedly effective in building capacity to integrate LCD, but provinces report need ongoing support and access to relevant technologies and financing for implementation, monitoring, and evaluation. / Provincial RPRKBIDs and RPJMDs were developed in reference to national LCD targets set in RPJMN 2025–2029, as required by law and government regulations. / North Sumatera: RPRKBID completed and in process of enactment as Governor’s Regulation. The document provides strategic guidelines for LCD and climate resilience, mapping roles of government, business, and CSOs. LCDI2’s facilitation and technical support are explicitly acknowledged in the document foreword. / Bengkulu: MoU signed in 2023, followed by RPRKBID drafting and workshops. Agreement reached to include LCD programmes in RPJMD and sectoral plans following LCDI2 engagement. Bapperida Bengkulu emerged as a local champion, ensuring LCD integration during strategic plan reviews. / NTB: Initial RPRKBID developed with Islamic Relief support; LCDI2 facilitated revision in 2025, improving data, modelling, climate resilience, GEDSI inclusion, and action plans. Workshops and focus groups supported integration into RPJMD and sectoral plans. / Several ongoing challenges were also identified during the case study, primarily highlighted in interviews with provincial government representatives: / Training duration for system dynamics and GHG modelling was too short; provincial staff require longer, more in-depth support to independently conduct modelling and emissions calculations. / Frequent rotation of government personnel undermines continuity of capacity building; trained staff are often reassigned. / Limited financial resources and reduced fiscal transfers from national government constrain implementation of LCD plans. / Competing priorities (e.g., infrastructure, health) may divert budget away from LCD initiatives. / Private sector and civil society organisation participation in LCD remains low; most activities rely on government leadership. / Quality of modelling and data inputs varies; some stakeholders noted that analysis was overly simplified or detached from ground realities.

It should also be noted that the programme is performing well against its logframe indicators for WS3, exceeding the target for indicator 3.1 and 3.2. As with output 2 noted above, this raises questions about programme ambition and whether targets should be increased. In the case of WS3, these results may be a consequence of the breadth of the monitoring indicators used and there is a risk of overlap with other indicators. For indicator 3.1, reported engagements range from audiences with parliamentarians to capacity building and training for interfaith engagement to reports on topics like the policy gaps in LCD in Indonesia. These latter results seem more aligned with other workstreams, such as TA and training under WS1 or communications outputs under WS3 indicator 3.2. Indicator 3.2 includes outputs such as the GEDSI strategy and LCDI branding guidance, which are less knowledge products that build support for LCD, and more internal governance and guidance documents. Further specificity as to the type of output to be counted under these indicators would be beneficial.
WS4 is designed to support the mobilisation of resources and the scaling of innovative solutions that enable LCD through the establishment of a technology and innovation fund. Progress in designing the fund has been slower than anticipated due to challenges in aligning expectations for the fund across key institutions (i.e. Bappenas, FCDO, development partners), the design complexity for the fund mechanisms which had to comply with both FCDO standards and GoI requirements, and the shifts in implementation prioritisation as noted in previous findings (i.e. responding to urgent ad hoc requests). A partnership has now been formalised with BPDLH (Indonesia’s Environmental Fund) to serve as the fund management entity. The programme has since developed an operational manual, with the fund scheduled for launch in October 2025. This collaboration is strategically significant: BPDLH is a government-backed institution with the mandate and infrastructure to manage climate-related financing, and its involvement lends credibility and potential scalability to the fund. By working through BPDLH, LCDI2 aims to attract additional investment and foster innovation across sectors such as energy, waste, agriculture, and forestry.
However, the programme has not yet demonstrated tangible results in terms of fund disbursement, pilot implementation, or measurable impact. There are concerns that the fund’s potential contribution to impact may be limited by short funding cycles owing to delays in the fund set up. In terms of the supported projects, lessons from other initiatives, such as the FCDO-funded Mentari programme, suggest that at least one year of post-construction support is needed for technology operation and maintenance, and several additional years for scaling and replication – this support represents an additional timeframe beyond the initial project identification and financing stage. The delays in setting up the fund are reportedly due to challenges in agreeing the scope for the fund between the Delivery Partners, FCDO and Bappenas, a prolonged fund manager identification process, and the need for the programme to focus on competing demands.
Interview respondents have also noted that the link between the fund and the broader LCDI2 objectives needs to be more clearly articulated (see Finding 1) – while there are recognised alignments between WS2 and WS4 in terms of anchoring policy developments with pilot or demonstration projects, these have not been explicitly explored. As noted in Finding 10 below, there are also significant monitoring gaps for WS4 in the current logframe which will need to be addressed if the results of the fund are to be sufficiently captured.
Finding 6 LCDI2 has been designed with longevity and sustainability in mind, and several elements of its approach suggest a strong potential for long-term impact, but there are also notable gaps such as the exit and transition strategies and financial and policy instruments that, if left unaddressed, could limit the durability of its achievements.	Relevant EQs / (Table 4)
	EQ5.2

Supporting the case for sustainability, LCDI2 has successfully embedded LCD principles into Indonesia’s formal planning systems. The integration of LCD into the RPJPN (2025–2045), RPJMN (2025–2029), and provincial RPJPD and RPJMD documents means that LCD is now part of the country’s legally mandated development agenda. These planning instruments guide national and sub-national priorities over five to 20 years, offering a robust institutional foundation for continuity. The programme has also aligned its work with existing government systems for budgeting, monitoring, and reporting, such as AKSARA. This alignment increases the likelihood that LCDI2’s tools and approaches will be maintained beyond the programme’s lifespan, with clear government ownership of the central framework.
The Innovation and Technology Fund, despite delays in its set up, is a promising mechanism for sustaining investment in LCD-related innovations due to its management by BPDLH, a long-term institutional actor in green economic financing. Capacity building has been another important pillar of sustainability. LCDI2 has trained national and provincial government personnel and is increasingly engaging local universities to build technical expertise in system dynamics modelling and LCD planning. These efforts aim to create a pool of skilled actors who can support implementation over time, although efforts to validate the efficacy of this training have not yet been undertaken.
However, there are critical gaps that could undermine sustainability. Most notably, the programme lacks a clear exit or transition strategy, although it is understood one is currently in development as of Q3 2025. While LCDI2 has helped institutionalise LCD in planning documents, it is not yet clear who will own and maintain the systems, tools, and coordination mechanisms once external support ends given noted capacity constraints within Bappenas and sub-national government agencies.
Financing is another major risk to sustainability. Many sub-national governments lack the fiscal resources to implement LCD plans at this stage and, without access to alternative funding such as results-based payments, special allocation funds, or international climate finance, the plans supported by LCDI2 are unlikely to come to fruition. The programme has begun exploring these options, but more concrete mechanisms are needed for the development of practical implementation plans.
Finally, the programme remains at risk of political shifts or turnover undoing the progress that has been made to date. Policy instruments that lock in LCD practices are limited. Few binding regulations, such as ministerial decrees or circulars, have been issued to ensure that LCD remains a priority across political cycles. This leaves the programme vulnerable to shifts in leadership or national priorities. Institutional fragmentation and high staff turnover, especially at the provincial level, pose ongoing challenges to the maintenance of results. While training helps, knowledge retention is fragile unless supported by institutional memory or embedded in local centres of excellence.
Overall, LCDI2 has laid a strong foundation for sustainability through integration into planning systems, alignment with government processes, and strategic partnerships. However, without a clear transition plan, stronger financing mechanisms, and more robust policy instruments, the long-term durability of its impact remains at risk. Addressing these gaps will be essential to ensure that LCDI2’s contributions continue to shape Indonesia’s development trajectory well beyond the programme’s end.

Box 5 Solar PV Pilot in Samosir District (relevant for ELQ 1) / Research Question: How have the feasibility studies produced by LCDI2 for the solar PV pilot contributed to the preconditions for fiscal uptake and implementation of public financing in Samosir District Government and Village Government? / Scope: Case Study 3 examined LCDI2’s contribution to the development of planning document for solar water pumps in Samosir District. LCDI2 is supporting Samosir Regency in addressing water-related challenges by planning the installation of solar photo voltaic (PV) powered water pumps to enhance irrigation on Samosir Island. / Evidence Sources: This study drew on evidence from 16 KIIs from a range of stakeholders, as well as a review of programme documentation and relevant public materials associated with the pilot site. A field visit also took place to North Sumatera although the EMU did not directly visit Samosir. / Key Findings: The following key insights were generated by the case study analysis. / The LCDI2 feasibility study was seen as more comprehensive by local government actors compared to previous feasibility studies for solar pumps in the district. / Samosir district government committed to providing financial support for the solar PV through a letter to Bappenas in April 2025 outlining 18 activities they will conduct including operator’s salary, training, and maintenance costs. / Financial commitments are dependent on clear timelines for implementation. KIIs noted that budget commitments are dependent on the provision of a clear timeline for implementation. The EMU notes this timeline is not yet established. / The inclusion of GEDSI, operation and maintenance guidance, and community aspects in the feasibility study will support increased sustainability of the upcoming solar PV. Long term sustainability is dependent on the community’s ability to optimise their use. / LCDI2’s commitment to cover the investment costs of the solar PV pilots serves as a critical precondition for enabling the district’s financial uptake, particularly in relation to funding the operation and maintenance of the solar-powered water pumps. / However, many activities have been conducted previously by Samosir District Government in support of solar pilots from 2020-2024 as highlighted by Bappelitbangda Samosir, indicating LCDI2 is not the only contributing factor. These existing solar pumps are still funded by the Samosir District Fund. / Case Study 4 also generated several important lessons: / Local ownership mechanisms are important in ensuring fiscal uptake and readiness for local projects. / Integrating LCD projects in local planning systems requires evidence-based analysis to influence key stakeholders and processes. / Sustainability is strengthened when co-financing structures are clearly established to balance costs between provincial government, district government and development partners or donors. / Framing the pilot as a development intervention to focus on agricultural productivity and rural development allowed the absorption of the climate related infrastructure into existing budget lines, demonstrating the importance of strategic positioning of initiatives in government planning. / An adaptive, data-driven design is valuable in providing resilience amid shifting fiscal priorities.

## Gender Equity, Disability and Social Inclusion
Key EQs	ELQ 6 Is the GEDSI strategy effectively designed and integrated into LCDI2?

The evidence used to inform these findings includes programme documentation such as the GEDSI Strategy, GEDSI Action Plan Development Report, LCDI2 GEDSI Action Plan, ToC and logframe iterations, MEL meeting minutes, quarterly and monthly reports and documents such as presentations related to the GEDSI integration in the RPRKBID. Wider literature used includes Bappenas’ Strategy on the LCD Phasing of RPJMN, entry points for draft RPJMN Lampiran I, International Women and Girls Strategy 2023-2030[13] and Integrating Gender into the Design, Implementation and Monitoring of Carbon Credit Projects.[14]
[13] https://www.gov.uk/government/publications/international-women-and-girls-strategy-2023-to-2030
[14] https://www.gov.uk/government/publications/integrating-gender-into-the-design-implementation-and-monitoring-of-carbon-credit-projects
The findings draw on evaluation methods including case studies, contribution tracing and the political economy analysis. A wide range of KIIs were used as evidence, as shown in Figure 6. In total 44 KIIs were coded to inform these findings. Over 50% of participants were female. Evidence was extracted from the KIIs using the coding approach described in section 2. The EMU notes that it was not possible to have a KII with either the Ministry of Women’s Empowerment nor MoHA.
Figure 6 Summary of KIIs per stakeholder category and gender disaggregation for ELQ 6

Finding 7 The integration of GEDSI into LCDI2 is still in its early stages. While a GEDSI Strategy has now been developed, its implementation faces continued challenges including a lack of dedicated resource and collective team understanding. The MEL system would benefit from further alignment with GEDSI.	Relevant EQs / (Table 4)
	EQ6.1, EQ6.2, EQ1.2, EQ3.1

The LCDI2 programme produced its Gender Action Plan Development Report in April 2024. The purpose of the report was to develop a GEDSI Action Plan that will serve as a blueprint for executing GEDSI aspects within the LCDI2 programme, ensuring that GEDSI principles are mainstreamed throughout. The Action Plan involved a multi-stakeholder consultation process with national and provincial GoI representatives as well as CSOs/ NGOs. The ToR for the GEDSI Strategy was developed in mid-2024 and the preparation of the strategy kicked off in October 2024. A draft of the GEDSI Strategy was presented to FCDO in January 2025 and shared with the EMU in February 2025. The final GEDSI Strategy, which includes the GEDSI Action Plan, was available mid-2025. The GEDSI Strategy advances a twin-track approach of mainstreaming GEDSI principles into all activities even when GEDSI is not the focus, and targeted stand-alone initiatives focused on promoting GEDSI in LCD. The Strategy is well articulated and sets out a range of actions to be undertaken in the second half of LCDI2.
Figure 7 LCDI2 GEDSI Strategy
The delivery of the Strategy, particularly the operationalisation of the Action Plan, requires consistent interaction, stakeholder influencing, and technical leadership, which is expected to require significant input. At the time of writing, the LCDI2 Delivery Partner has no full-time GEDSI expert. The programme relies on part-time contributions[15] with some shared responsibilities across Delivery Partner core team members.
[15] The GEDSI team in Jakarta is comprised of the GEDSI Focal Point or GEDSI Coordinator, assigned 60% to LCDI2 and receives GEDSI technical support from part time GEDSI Adviser, allocated 50 days/ year or 4 days/ month input, and the Deputy Team Leader.
According to the GEDSI Strategy, the main GEDSI Coordinator focuses on delivering the day-to-day activities of the overall LCDI2 work plan applying GEDSI considerations. The GEDSI Adviser guides the Delivery Partner team on implementing the Strategy. Additional support is provided by the Programme Director who is responsible for high level leadership of the GEDSI Strategy implementation supported by the Deputy Programme Director; the Technical Advisers who are responsible for integrating the GEDSI Strategy into their technical expertise areas; and the MEL Manager who oversees the MEL processes related to the GEDSI Strategy. The programme also has provincial focal points, but the extent to which they have been provided training on GEDSI and to follow up on the implementation of GEDSI activities needs to be clarified. Additionally, the programme contracted short-term gender consultants to support the integration of GEDSI into the PRPKBID.
Several interview respondents underlined that the absence of a fulltime technical GEDSI expert has hampered day-to-day engagement of stakeholders and reduces the Delivery Partner’s ability to monitor and execute proposed activities in the GEDSI Action Plan. It has also been noted that the reduced capacity could limit influence within Bappenas and its directorates, as well as other GoI ministries, on mainstreaming GEDSI in LCD policymaking due to a lack of concentrated, consistent interaction. There is also no dedicated budget for GEDSI and so the focus of delivery to date has been mainstreaming via integration into workstream activities rather than undertaking GEDSI-targeted activities.
Within the LCDI2 MEL system, there continues to be a lack of GEDSI integration, particularly notable in the logframe and ToC, despite feedback in the 2024 AR and EMU-led logframe review. Within the ToC narrative, the Delivery Partner explicitly addresses this, noting that GEDSI is included at a generic level rather than a specific level due to concerns that GEDSI may not be relevant for each intervention. This appears to be linked to the Finding 1 point around the breadth of the ToC. It also further speaks to the value of sharpening focus moving forward.
In the absence of explicit GEDSI integration to the ToC, the narrative provides for GEDSI assessments to be undertaken for each intervention to assess what role GEDSI consideration should play and how in each intervention. While the challenge of integrating GEDSI in each workstream is acknowledged, the ToC narrative does not consider the use of cross-cutting pathways which could explicitly integrate the GEDSI Strategy. The current approach risks marginalising GEDSI within both the programme theory and activity design, relegating GEDSI integration to an implicit consideration of how activities are carried out as opposed to an explicit objective of LCDI2 in terms of promoting GEDSI-sensitive policies and processes for the LCD transition.
Alongside the ToC, the indicators in the current logframe are not well linked to measuring GEDSI achievements or providing sufficient disaggregation. Outcomes 1.2 and 2.1 speak to a need that the government actions taken and the choice of stakeholders to engage must “demonstrate that they have taken account of GEDSI considerations” but it is unclear what standard these are held to and the threshold that would result in otherwise valid results being excluded.
Beyond these two examples, there are significant opportunities to enhance GEDSI monitoring within the programme logframe such as disaggregation of participants at training events or subject to WS3 engagements, or the inclusion of specific GEDSI indicators at the output and outcome level as further explored in Recommendation 8 below. Having clear GEDSI indicator measurement for the programme would set a good example to stakeholders at the national and sub-national levels who are reportedly also finding it a challenge to integrate GEDSI indicators.
At the sub-national level, interviewees mentioned scoring of levels of gender integration: GEDSI sensitive, GEDSI responsive, and GEDSI transformative. Currently no consistent nomenclature for GEDSI is used. For uniformity of monitoring and reporting, the programme should agree with national and sub-national level stakeholders and with FCDO on the nomenclature to score gender integration. Consideration is required of what level of GEDSI integration that the Programme is aspiring to. This will influence the design of GEDSI approaches and processes in implementing activities across workstreams. This would be relevant for AKSARA and programmatic reporting.
In the Change Harvesting workshop, the programme used GEDSI markers to describe the level in which gender equality is integrated for internal team use per Figure 8. A Gender Code 0 means that gender is not reflected in any component of the project. The highest code is Gender Code 2b which translates into targeted actions aimed to advance gender equality. Understandably these codes match with the twin-track approach described in the GEDSI strategy. The EMU notes that the gender markers were only for internal Delivery Partner use and not shared with FCDO and Bappenas. The KIIs at the national, sub-national, and programme levels revealed the familiar reference to gender sensitive, empowering, and transformative categories of gender mainstreaming or integration. The programme must use a common gender mainstreaming categorisation that can be adopted at the national and sub-national level.
Figure 8 GEDSI Assessment Markers

Finding 8 GEDSI integration in LCDI2 has made important strides, particularly at the provincial level, but remains uneven across workstreams and limited in operational depth.	Relevant EQs / (Table 4)
	EQ6.1, EQ4.3

Despite delays in developing the GEDSI Strategy, the evaluation has found that LCDI2 has made deliberate efforts to integrate GEDSI into its planning and delivery, particularly through support to provincial governments in developing RPRKBID documents. GEDSI integration was undertaken in NTB, North Sumatera, Bengkulu, and Maluku, with varying levels of depth and success per Figure 9.
Figure 9 Summary of LCDI2 GEDSI Activities at Provincial Level

In NTB, the GEDSI integration activities aligned with the province’s flagship NTB Inklusif programme, creating synergy between climate action and inclusive development, and were welcomed by the NTB Bappeda for that reason. The process was described by stakeholders as an “eye-opener” and a crash course in applying gender analytic tools during Case Study 6. The LCDI2 activities providing the NTB government participants with a concrete situation to analyse and act on in the context of GEDSI-sensitive LCD planning.
In North Sumatera, a multi-stakeholder collaborative workshop was led by Bappenas and attended by local government agencies, parliamentarians, academics, private sector, CSOs, and NGOs working on environmental issues, women’s empowerment, and disability rights. It facilitated inclusive dialogue on accelerating inclusive LCD and was supported by disaggregated data and legal frameworks.
In Maluku, the GEDSI activities built on the foundation from LCDI1 and adapted the twin-track to integrate GEDSI into the RPRKBID by facilitating capacity development needs assessments targeted to Organisasi Perangkat Daerah (OPDs), identifying data needs, and integrating gender issues reflected from the RPJMD into the RPRKBID.
In Bengkulu, the planning process stimulated discussions on ensuring that perspectives on the potential impact on vulnerable groups of LCD plans, especially persons with disabilities, are addressed.
Despite these achievements, the level of GEDSI integration across workstreams remains inconsistent. As noted above, a GEDSI assessment tool was developed to determine relevance of GEDSI to different interventions, but its application has reportedly been limited.[16] GEDSI experts have had minimal involvement in reviewing or strengthening planning documents, and capacity building efforts have been insufficient. For example, during the RPRKBID workshop in NTB, time allocated for capacity building on GEDSI concepts was reportedly limited. Some OPDs were confused about where to integrate GEDSI aspects in their own activities and how to apply the Gender Analysis Pathway methodology. The understanding on GEDSI was narrow, focusing mainly on male-female difference and missed the chance to elaborate on the intersectionality of gender, disability, and social marginalisation.
[16] A review of the GEDSI assessment tool was not undertaken.
At the systems level, demand for GEDSI indicators is clear, both within LCDI2 and in national platforms like AKSARA. However, AKSARA currently lacks GEDSI-specific indicators and disaggregated data, and there is no guidance on how to integrate GEDSI into climate monitoring, despite perceptions from interview participants that this is an important requirement for gender-responsive climate planning. Interview participants revealed mixed views on whether LCDI2 should lead this integration, with some suggesting a pilot under WS4 to test GEDSI data collection and analysis could be an appropriate option. GEDSI disaggregated data would further support the identification of GEDSI related issues in LCD.
Finally, interview participants consistently emphasised that integration of GEDSI into planning documents such as the RPJMN, RPJPD, and PRPKBID alone is not sufficient. It must be translated into actionable policies, programmes, and budgets, with sustained resources and institutional commitment to GEDSI. Monitoring and reporting mechanisms at the provincial level are not yet in place, and further support is needed to build understanding and capacity among OPDs and communities to understand, implement and monitor GEDSI-responsive actions.
Finding 9 GEDSI integration in LCDI2 reflects a cautious but evolving approach, shaped by limited foundations, uneven senior engagement, and limited direction from FCDO and Bappenas, as well as emerging opportunities for strategic influence.	Relevant EQs / (Table 4)
	EQ6.1, EQ6.2

The LCDI1 demonstrated limited integration of GEDSI considerations. As a result, LCDI2 begins with a relatively weak foundation in this area. Recognising this, the GEDSI Strategy for LCDI2 adopts a pragmatic approach, starting small and focusing on realistic, achievable goals. In alignment with the GEDSI Strategy, LCDI2 aims to mainstream GEDSI across all workstreams, engaging both national and sub-national government stakeholders. Bappenas has recommended prioritising primary beneficiaries such as women’s groups and people with disabilities, while also acknowledging the intersectionality of gender with ethnicity and disability.
Despite this guidance, Delivery Partner interviewees observed that LCDI2 has taken a cautious approach to avoid overwhelming GoI counterparts. Collaboration to date has largely focused on conceptual discussions and identifying potential GEDSI entry points. However, there remains a lack of consensus among key stakeholders such as FCDO, Bappenas, and Delivery Partners, on how best to advance GEDSI implementation.
Interview respondents emphasised the need for stronger engagement with Bappenas, particularly with high-level officials and decision-makers. At the same time, there is a reported lack of clarity from both FCDO and Bappenas regarding GEDSI priorities, including the types of changes expected and what is feasible in terms of improving access and participation for women and addressing disability within the LCD framework.
From the GoI perspective, Bappenas expects LCDI2 to proactively develop strategic and visionary ideas, including measurable indicators for GEDSI implementation. These indicators should be suitable for integration into national development plans and budgets. Bappenas envisions LCDI2 functioning more as a think tank, producing strategic, impactful outputs, rather than operating as a short-term development partner. This includes advancing indicator development and advocating for their inclusion in planning documents and medium-term development plans, but it is not clear whether this is within LCDI2’s scope or not.
While GEDSI team members recognise the importance of collaboration with Bappenas, they report that engagement has been challenging. Most interaction has occurred through a staff member in the Directorate of Environment who is familiar with gender issues, but engagement with senior officials remains limited. Communication typically takes place through formal channels such as workshops and events and the preparation of the annual workplan, which are often attended by junior staff and analysts who do not hold decision-making authority.
Efforts to engage Bappenas’ Directorate of Women Empowerment, Child Protection, Family Welfare, Youth and Sport have not progressed significantly. However, the inclusion of the Ministry of Women Empowerment and Child Protection in the Technical Committee is seen as a potential pathway to strengthen links with the relevant Bappenas Directorate. The Ministry was expected to formally join the Technical Committee by September 2025.
Some Delivery Partner stakeholders have expressed that clearer guidance from FCDO on GEDSI implementation would be beneficial. At the time of the KIIs, BEJ reportedly did not have a dedicated GEDSI focal point, which contributed to confusion. One example cited was a request for reporting on beneficiary-level impact, which a Delivery Partner staff member felt was outside their scope given that GEDSI efforts are primarily focused at the policy level. Nevertheless, LCDI2’s targeted GEDSI approach, particularly in WS4, does hold potential for supporting GEDSI outcomes at the community level.
## Programme Management
Key EQs	ELQ 3 How can the effectiveness of LCDI2 programme management mechanisms be optimised? / ELQ 4 Is LCDI2 delivering value for money (VfM) against the 4Es framework?

The evidence included all programme documentation such as ToRs, Quarterly and Monthly Reports, Annual Reviews, workplan trackers, minutes of Steering Committee meetings, Inception Report, MEL plan and logframe, MEL system reviews, LCDI2 VfM Framework, LCDI2 VfM Assessment Report, LCDI2 Change Harvesting exercise results and the LCDI2 Business Case. Nearly full access was given to non-confidential programme documentation but review was limited to those of most relevance to the priority focuses of the evaluation. The evaluation has not examined the detail of certain types and sections of documents such as Standard Operating Procedures and Finance Manuals and other detailed manual type documents, which were not identified as a priority for review by FCDO or the Delivery Partner.
The following evaluation methods contributed to the findings: ToC Assessment, Case Studies, a latest review of the logframe, and the Social Network Analysis. Case study topics included improving the interoperability of AKSARA with other databases. A wide range of evidence from KIIs was also used. In total, 35 KIIs were conducted. Figure 10 provides an overview of the number of KIIs per stakeholder group. Overall, 51% of participants in KIIs were female.
Figure 10 KIIs conducted per stakeholder group and gender disaggregation for ELQ 4 and 5

One limitation of the evidence for these findings is that it was not possible to interview managers of other related programmes managed by FCDO in Indonesia in the timeframe available. A further limitation is that cost data, including source documentation, was not shared with the EMU due to its confidential nature (see Limitations section 2.4).
### MEL and effective governance
Finding 10 LCDI2’s MEL system architecture has evolved and adapted to emerging needs well, albeit at a relatively slow pace and the monitoring system is currently in a state of transition. It is broadly appropriate for the programme’s context but there is scope for a range of improvements to enhance its contribution to effective Programme Management	Relevant EQs / (Table 4)
	EQ3.1, EQ4.2, EQ1.2

Programme management governance mechanisms in terms of the range and types of meetings between FCDO, OPML, Bappenas, and the EMU have evolved well and all stakeholders are generally satisfied that they are organised at the right regularity with the right kinds of focus. At the same time, evidence from KIIs and the logframe review also suggests that while the monitoring and reporting system continues to fulfil its core accountability functions - particularly in tracking deliverables and reporting against quantitative indicators - it is still developing and integrating the processes necessary to best support adaptive management and demonstrate the programme’s broader systemic contributions. The Delivery Partners have shown that they have been active in generating ideas and exploring ways to strengthen programme management mechanisms in balance with overall available resources and many ongoing initiatives and emerging requests for action in this area and programme delivery.
Within that, the LCDI2 monitoring system remains largely shaped by linear monitoring approaches. This is partly due to the expectations and institutional requirements of FCDO and GoI counterparts; where the LCDI2 Delivery Partners initially sought to develop a more cross-cutting ToC and accompanying monitoring framework, the workstream oriented structure had to be maintained leading to a more conventional monitoring approach to primarily support accountability. Relatedly, there is a degree of hesitation with the LCDI2 programme around modifying monitoring indicators mid-cycle, even when doing so might better reflect evolving realities on the ground.
It is clear from programme documentation, engagement and consultations on the MEL system between the Delivery Partners and EMU, and KIIs, that since the 2024 AR there has been significant improvements made to many elements of the system in line with emerging needs. A review of the MEL system by the EMU from November 2024 to January 2025 included recommendations to support required improvements. Evidence of progress against these recommendations, as evidenced before and during the evaluation, is set out in Table 6 below.
Table 6: Summary of MEL System Review
Area	Details	Progress by August 2025
Improvements to the Monitoring & Reporting Knowledge Management System (KMS) and evidence flows	Operationalise a milestone tracker and document management system and inventory list. / Keep under review cost and benefits of programme reporting requirements and potential adjustments / EMU’s Annual Progress Report to be replaced with more direct inputs into FCDO’s Annual Review	The initiatives mentioned have been integrated into monthly and quarterly reporting. No issues raised during the evaluation. However, in relation to what is being monitored, stakeholder demands for enhanced technical output quality and timeliness could be better met by ensuring the quality of outputs and their uptake is integrated better into the MEL system and adaptive management decisions. / The evaluation identified significant concerns about the size/scale of the monitoring information being processed and reported in terms of its cost-benefit ratio. / EMU provided emerging evidence from the Evaluation to FCDO as relevant to the 2025 AR at various points during the AR process.
Optimising MEL system activities in 2025	More regular face-to-face three-way discussions on MEL integrated into existing timetable of meetings. / Adjust the timing and focus of some key MEL system evidence collection activities in line with optimising burdens on stakeholders, adjustments to the Change Harvesting process, and other developments.	Regular three-way discussions were found not to be practical, but there has been more regular and reportedly effective coordination between the three parties throughout 2025. / The evaluation, AR, and Change Harvesting processes were closely coordinated, although it is recognised that the timing of these three crucial processes was less then optimal.
Learning, Knowledge, and Dissemination (LKD)	Revised strategy in line with emerging needs.	The Delivery Partners and FCDO have only been able to provide limited inputs on their needs for support on LKD products during the first half of 2025. There is now general agreement that the results of the evaluation and AR should drive the development of the next LKD cycle, which should have a clearer action plan and more efficient processes agreed. / There is evidence of some LKD products being produced well and used, such as OPML’s ongoing PEA work and its review of lessons learned about LCDI Commissioners, and the EMU’s review of lessons from LCDI1 in pilot provinces. However, timeliness has been challenging in some cases. This is likely due to a lack of adequate coordination and planning around the Annual Learning Cycle and lengthy approval processes.
Socialisation of MEL system	Ensure system users had a shared understanding of evidence flows, storage, and use.	Activities in early 2025 supported improved understanding of the complexities of the MEL system among FCDO and Bappenas stakeholders. New Bappenas leader briefed shortly after his appointment in July 2025.
Monitoring system enhancements	Advice provided by EMU on improvements to data quality and Performance Indicator Reference Sheets (PIRS).	EMU’s advice on many aspects was well-integrated by the Delivery Partner into a revised logframe by May 2025.

Despite these advancements, the MEL system still appears somewhat fragmented, with planning, monitoring, and learning tools evolving in parallel rather than in concert. This has led to duplicated reporting efforts and weakened the causal coherence of the programme’s results framework. While some workstreams (notably WS1 and WS2) benefit from structured monitoring indicators, others (WS3 and WS4) lack clarity around what constitutes measurable progress, making it difficult to assess their contribution to systemic change. For example, following the 2025 logframe adjustment, WS3 has two output indicators, monitoring the number of stakeholder engagements (3.1) and the number of communications outputs (3.2), and one outcome indicator, evidence of greater support for higher ambition in LCD action. Regarding the outputs, indicator 3.1 adopts broad definitions for both stakeholders and engagements which limits specificity, lacks disaggregation metrics, and only monitors whether the engagements have occurred rather than using a measure to monitor the quality of the engagements (i.e. the distinction between activity monitoring and output monitoring). Reporting against this indicator seems to include reporting outputs as well as engagement events which overlaps with 3.2; 3.2 in turn has counted outputs including the programme GEDSI strategy and LCDI branding guidance which appear to be internal outputs.

Box 6 Improving the interoperability of AKSARA with other databases (relevant for ELQ 1 and 5) / Research Question: How did provision of the technical methodologies to Bappenas and engagement with GoI ministries contribute to the improved interoperability of AKSARA with other databases? / Scope: Case study 1 examined the support to the implementation of AKSARA under LCDI2 with a particular focus on improving interoperability and sub-national uptake. LCDI2 aims to align AKSARA with SRN/SIGN-Smart, managed by MoF, and top-down climate data managed by Indonesia Agency for Meteorology Climatology and Geophysics (BMKG). / Evidence Sources: KIIs with at least nine stakeholder groups including Bappeda NTB, MoHA, MoEF, BMKG, Local Governments for Sustainability (ICLEI), WWF, Islamic Relief, FCDO, and Bappenas. KIIs were supplemented by programme document review and a field visit to NTB in September 2025. / Key Findings: Overall, LCDI2’s provision of technical methodologies have initiated the process of interoperability of AKSARA with other low carbon databases, although challenges remain. / The key successes identified are: / Improved institutional coordination: A key role of LCDI2 has been to facilitate engagement between Bappenas and relevant line ministries regarding interoperability. LCDI2 established a coordination platform and technical working discussions that allowed Bappenas, MoEF, MoHA, and BMKG to identify data overlaps and explore integration pathways. / Improving provincial data integration: In NTB, LCDI2 provided training to the Bappeda, the provincial Environment and Forestry Agency and sectoral agencies led to improved data entry and alignment with national indicators. / Methodologies for interoperability: LCDI2 developed methodologies to align AKSARA to SRN, Sign-Smart and BMKG systems, but technical integration is yet to take place. / However, challenges to interoperability remain including: / Lack of clarity in use of databases: Despite progress made in initiating conversations between ministries, KIIs consistently expressed confusion about which platform to prioritise, and noted the duplication of data entry and double counting remain a challenge. / Inclusivity Gaps: AKSARA currently excludes non-government actors (NGOs, civil society), limiting the system’s ability to capture the full scope of climate action, especially on GEDSI, according to other development partners working in the space. / Sustainability: Currently interoperability of AKSARA is dependent on LCDI2 facilitation. Sustainability would be improved through a clear budget mechanism or operational framework beyond LCDI2. / Based on these results, the case study identified several lessons: / Interoperability in multi-dimensional and requires technical and institutional support, clear mandates and sustained collaboration. / Embedding AKSARA within policies such as the Indonesia data governance framework and in decrees at the provincial level may help to support adoption. / Sustained use of ASKARA depends on continuous capacity development for provincial staff and local governments. / Expanding AKSARA to include non-government and community-based reporting, and integrating GEDSI indicators, will improve representativeness and equity.

WS4 is only represented by one output indicator, the number of TA products developed to set up the fund and make disbursements, with no metrics related to the number of projects supported or grants disbursed[17], the quality of the fund delivery mechanisms, the volume of applications, or disaggregated metrics about the types of fud applicants or technologies supported, all of which could be valuable metrics for target setting, accountability, and learning for subsequent funds. Outcome 4 does measure the successful pilot projects with an end target of ten and proposes disaggregation metrics, but it is challenging to assess the appropriateness of this target without monitoring indicators for the total number of projects the fund intends to support (i.e. accounting for rates of failure in innovation or pilot projects).
[17] It is noted that project feasibility assessments and selection reports are included as TA products under indicator 4.1, but this does not facilitate effective target setting.
While the monitoring and reporting system is fit for purpose in terms of compliance and accountability, it is not yet well-developed in enabling real-time learning, adaptive planning, and strategic course correction. Strengthening the approach to monitoring WS3 and WS4 and capturing higher order results will be essential if the system is to evolve into a truly adaptive and learning-oriented framework.
As noted above, there are also limitations in the intermediate outcomes resulting in challenges integrating them effectively in the monitoring system in a way that is both verifiable and meaningful. For example, with WS3 there is a significant gap between engaging stakeholders at the output level and their public endorsement of LCD at the outcome level, and the monitoring system currently lacks assessments of whether engaged stakeholders increase capacity or knowledge because of the engagement. The absence of cross-workstream indicators and shared milestones further limits the programme’s ability to assess its collective impact. It should also be noted that the revised logframe no longer includes ICF KPIs such as KPI15 for contribution to transformational change or KPI11/12 for finance leveraged, which reflect important impact and outcome achievements respectively that the programme should monitor. Examples of indicators which could be added are provided in Recommendation 11.
The internal Delivery Partner MEL team has made commendable efforts to pilot adaptive tools, facilitate reflection sessions, and introduce a Change Harvesting approach to narratively capture and demonstrate the programme’s contribution to key changes over time. Interview participants report that these practices are continuing to be developed with the Change Harvesting now embedded as a methodology to evidence Outcome 1 and 2. That being noted, they also found that insights from reflection workshops and exercises have historically been inconsistently documented and not fed into adaptive planning in a systematic way. This limits the programme’s ability to learn from emerging results and contextual factors but is recognised as an area under active development by the LCDI2 MEL team.
It appears that the Quarterly Reports, as a key tool for adaptative management, map back to the agreed workplan, monitoring KPIs, and there are clear approval and escalation pathways. Safeguarding policies, audit trails and risk registers are explicitly referenced. However, Delivery Partner stakeholders reported that the volume and frequency of reporting can be burdensome, sometimes detracting from implementation activities or efforts to fine-tune the Monitoring system or higher-value MEL activities, such as Change Harvesting. From all KIIs with relevant FCDO and Delivery Partner staff, it is not clear if all the reporting information is being used by or is particularly useful to FCDO. This seems dependent on individual preferences of FCDO team members for the format of the reporting and relative to the workloads of those individuals at the time of use. Stakeholders more broadly considered that the ToC and logframe were used, but that they were not always user-friendly or fully integrated into management decisions.
While a risk register is maintained and reported quarterly, there is little evidence of Programme Managers having a meaningful focus on managing risks. This includes at the two Steering Committees observed by the Evaluation team. Experience from other Programmes, backed up by KIIs with other Development Partners during the Evaluation, indicates that a focus on risk management in reporting and adaptive management can be highly beneficial and highly risky if it is not regularly used.
### Value for Money (VfM)
Finding 11 LCDI2 resources are generally being used economically and appropriately, with good results on spending performance and KPI reporting results. The programme is monitoring VfM well through a number of frameworks and processes and there are relevant examples of a VfM lens having been used appropriately for adaptive management and management of cost drivers.	Relevant EQs / (Table 4)
	EQ4.1, EQ4.4, EQ1.2

LCDI2’s resources were used economically, underpinned by managing key cost drivers and a cost-conscious approach to finances. In the procurement of routinely used inputs such as flights, accommodation and technical expertise, Delivery Partner analysis showed that there was a good performance. For example, for procuring technical expertise the Delivery Partner secured lower fee rates compared to the ’proforma’ rates agreed with FCDO. The rates were lower overall and in job family comparisons. It was also reported in the Delivery Partner documents that, through negotiations and comprehensive market exploration, the Delivery Partner paid lower rates on flights and accommodation than their original budgeted unit costs. The Delivery Partner also tracked the value of these cost savings, which amounted to over £300k last year. In terms of categories of costs in overall expenditure, there was roughly a 13%-87% split between management and other programmatic costs[18], which is a similar trend to other FCDO-funded TA focussed programmes.
[18] This is based on the last year reported. The previous year trend is assumed to be similar.

Benchmarks or targets were either set out in the Delivery Partner contract with FCDO or further specified in the KPI reporting.[19] From KIIs and review of Quarterly Reports, KPIs were monitored effectively on a quarterly basis and were integrated into decision-making. If the aggregate scores in a period were under a certain threshold over a quarter, a percentage of fees would be withheld. The KIIs confirmed that withholding of fees has not happened to date. Through this system it is apparent that there was a good performance on budget execution by the Delivery Partner with 91% result compared to the benchmark of >90%.
[19] KPI reporting is a quarterly mechanism based on a set of pre-agreed measures and criteria, where scoring is done both by FCDO and OPML. Explanations are also provided for each score to justify them.
There are several tools and frameworks for monitoring VfM. The main ones are the LCDI2 VfM Framework and the Quarterly KPI reporting. VfM monitoring is undertaken quarterly and annually. Quarterly Reports include a VfM section that summarises economy performance and budget execution. The more comprehensive VfM assessment against the programme VfM framework is carried out annually and presented in the VfM report.
There has only been one comprehensive VfM self-assessment so far covering the July 2024-June 2025 period. In practice, KPI reporting is used more frequently by the Delivery Partner and FCDO for tracking VfM in delivery, due to the delivery-linked payment retention. The KPI schedule itself is in many ways like an additional VfM framework that covers many aspects of financial and technical performance.
The annual VfM assessment report prepared by the lead Delivery Partner was comprehensive and used other performance and MEL trackers like the KPI schedule, the logframe, and Change Harvesting. This reflects good practice as VfM data cannot be fully understood in isolation; it is better articulated and assessed when it is integrated in other programme evidence and processes. Earlier in 2025, the Delivery Partner pro-actively sought the views of EMU for a critical-friend review of the VfM framework and various improvements were implemented as a result.
Examples of how the Programme applied a VfM lens to the financial and technical management of the programme include the reported over £300k of cost savings through securing lower rates for TA fees, and a further £80k savings through travel and accommodation. Last year, the programme team had to over-spend on their MEL and GEDSI budget due to the need to incorporate GEDSI-related activities. LCDI2 programme also facilitated activities that were outside of their workplan, supporting Bappenas to delivery their key priority activities relevant to LCD. Arguably, VfM related decision making is constant and routine for the Delivery Partner when it comes to assessing the feasibility of Bappenas requests, as discussed below.
Finding 12 LCDI2’s efforts to optimise efficiency have been moderately successful. There has been good progress in establishing governance structures and building productive relationships between the key actors, with the programme evolving well in response to learning. However, efficiency is being hindered by a variety of factors that have reduced the timeliness, delivery quality, and impact of some outputs.	Relevant EQs / (Table 4)
	EQ3.1, EQ4.1

Discussions with the LCDI2 parties and the wider set of KIIs conducted for the evaluation highlighted some positive views on efficient delivery. This included a common view that significant efficiencies have been achieved by cost-sharing with GoI partners. In-kind contributions were reported in the form of using Bappenas offices and staff time, leveraging institutional resources which enhanced delivery efficiency and credibility.
The 2023 AR highlighted the need for balancing early delivery of key strategic priority activities while being flexible and adaptable in delivery. It also underlined the need for timely and effective communication between the Delivery Partners and FCDO, embedding the principle of equal partnership with Bappenas, and managing the programme in a way that supports getting buy-in and influence from government bodies outside of Bappenas (i.e. MoHA and MoF). While a joint governance structure between FCDO and Bappenas had reportedly been complicated to establish and had delayed delivery in the initial phases of LCDI2, evidence now points to more positive conditions being in place to support effective strategic decision making between the LCDI2 parties.
There is broad agreement among FCDO, Bappenas and Delivery Partner stakeholders that lines of communication and coordination between these three key parties have developed positively, enhancing programme efficiency. Regular, structured discussions take place and were largely effective in facilitating day-to-day decisions. Stakeholders external to LCDI2 echoed the importance of clear communication and alignment between the lead Delivery Partner and its consortium members, noting that these relationships were essential for smooth delivery. However, not all experiences were consistent; while some consortium members felt that processes for their involvement were working well, others observed that misalignments sometimes led to delays and ambiguity around roles and responsibilities.
A recurring theme raised by several stakeholders was the need for stronger strategic leadership within LCDI2. They suggested that enhanced leadership skills could help streamline engagement with Bappenas and other government entities, especially at senior levels, thereby improving overall efficiency going forward. While the Steering Committee and the soon-to-be-established Technical Committee were appreciated by most stakeholders for offering high-level guidance and approvals, there remained a notable absence of informal spaces for open discussion among partners who participated in these forums. This gap hindered swift decision-making and limited opportunities for adaptive management, as informal dialogue often helps resolve issues more quickly and flexibly. Finally, despite the general welcome for the Technical Committee, many stakeholders expressed doubts about whether it would be able to achieve sufficient progress in the limited time remaining for the Programme.
One recurring efficiency challenge highlighted by interview participants is that the procurement for staff or consultants had occasionally exceeded planned timeframes, especially when being undertaken in response to either emerging or unplanned needs, and that the programme had occasionally struggled to find the find experts at the right time. One stakeholder pointed out that this could sometimes take longer than the implementation of a task. In particular, the reviewing of ToRs for various assignments was often perceived as taking too long and being an inefficient process. An example for this was the lengthy review period for the ToRs in engaging key Parliamentarians, which took nearly four months.[20] This was further compounded by lengthy reviews of reports or ToRs by Bappenas, leading to cost extensions being issued for some of the consortium members to manage higher than anticipated feedback and shifting expectations.
[20] More details on this can be found in the Case Study on this specific activity, carried out as part of this evaluation.
Long turnaround times led to reduced relevance and potential positive results of interventions. For example, Sawahlunto, a post-mining city, was selected as a pilot to show how LCD can be integrated into local planning and support a just transition. The study was conducted by LCDI2 Delivery Partners. However, the findings were not presented to the district stakeholders on time, which meant the opportunity was missed to inform the Medium-Term Plan development early this year.
Interview participants point to several underlying reasons for inefficiencies when it comes to allocating and mobilising resources. Firstly, the Indonesian labour market faces a persistently high demand for specialised skills, but the supply remains limited. This makes it particularly difficult to find and recruit the right expertise at the right moment. Compounding this, the Delivery Partner teams were often stretched thin, as they juggled the implementation, monitoring, and reporting of numerous activities across different workstreams. The situation was further complicated by unanticipated requests for support from Bappenas, FCDO or the EMU, which divert resources and add to the workload.
Another key challenge lies in the complex approval and coordination processes involving FCDO and various levels within Bappenas, sometimes even spanning multiple Directorates. These layers of bureaucracy significantly slowed down decision-making. While FCDO was generally supportive of the LCDI2 technical delivery, its involvement in technical matters fluctuated. This inconsistency at times led to uncertainty about the expected degree of autonomy for the programme and the processes to be followed. Frequent leadership changes within Bappenas since LCDI2’s inception have also posed challenges, disrupting continuity and slowing progress. Lastly, both the GoI and its implementing partners continue to grapple with significant gaps in human and financial resources. These shortages were especially acute when it comes to facilitating cross-ministerial coordination, securing technical expertise, and mainstreaming GEDSI across activities, which delayed engagement with LCDI2 decision-making and resource mobilisation processes.
Additionally, considering the points raised in Finding 2 above, there appears to be a missed opportunity for wider efficiency through coordination with other actors in the sector. This may be unlikely unless one of them takes the initiative to invest in demonstrating and driving the potential synergies across initiatives, which could be a role played by LCDI2 in the short term, but may be better owned by a long-term institutional actor. This is not an unusual situation in development partner ecosystems, which relevant stakeholders underlined in KIIs. However, as also indicated in KIIs, the current coordination between related programmes within the FCDO portfolio seems to be infrequent, with minimal integration or coordination on detailed work planning, which was arguably a missed opportunity for LCDI2 given its cross-sectoral position.
In line with these challenges, a broad range of expert stakeholders during the KIIs underlined the need to ensure that LCDI2 resources should now be concentrated on driving progress towards outcomes, rather than stretching them over an increasing long list of activities, to sharpen its strategic focus to avoid being fragmented over too many interventions. Indeed, while FCDO and OPML had agreed to be responsive to ad hoc Bappenas work requests initially, to cement the key relationship for Programme success, this led to activities lacking coherence and relevance to the ToC. There has been a tension between the Programme being responsive to such ad hoc requests for technical support from both Bappenas and FCDO and the Programme’s ability to focus its resources on its long-term goals. Within this context, it can be challenging to understand and decide upon the right balance between supporting the ToC, managing reputational risk, and enhancing VfM.
In terms of the use of the wider programme budget, interview respondents across FCDO, the Delivery Partner and the EMU recognise that the EMU has a comprehensive budget to provide MEL-related services. It is also broadly agreed that, while there has been good collaboration between the Delivery Partner and EMU to date, there is scope for better utilisation of the EMU resourcing and opportunities to enhance efficiency between the organisations, given the risk of duplication in MEL activities.
Interview respondents from across the LCDI2 parties recognised that there were challenges in developing a clear and shared understanding of roles and responsibilities with respect to the MEL system, partly due to the misalignment of contract start dates with the EMU commencing work during the last month of the delivery inception phase and partly due to the focus of the FCDO and Delivery Partner teams on delivery priorities as opposed to monitoring and learning. However, interview respondents also agreed that the engagement between the parties is significantly improved, with a clearer division of responsibilities and consensus that the Process Evaluation results should provide an appropriate opportunity to guide how the EMU’s resources can best be allocated to support the success of LCDI2.
Finding 13 LCDI2 is showing positive signs of Effectiveness and Equity in its delivery, although it remains too early to assess in-depth. In both cases, more strategic thinking would be beneficial to sharpen the focus on Outcome achievement.	Relevant EQs / (Table 4)
	EQ4.2, EQ4.3, EQ6.1

As highlighted in Finding 4, there is evidence of emerging Outcome level results under WS1 and WS2, particularly regarding the development of LCD friendly policies and planning documents. However, it is too early at this stage to conclude whether the results have generated returns above and beyond the funding that was spent to date. This is due to several factors, the first the programme maturity. A second factor is the inherent challenge in measuring and articulating VfM in any policy-oriented TA programme. The LCDI2 VfM framework recognises this and seeks to define value for the purposes of the programme, although it also relies on qualitative, non-costed indicators to measure Effectiveness, which limits the opportunity to quantitatively assess value in the context of Outcome achievement. Finally, moving towards desired outcomes within the LCDI2 ToC seems highly dependent on sustained increases in financial and technical capability among GoI and provincial institutions over the long term, metrics which are not currently being monitored by the programme and for which there is limited evidence at this stage.
That being noted, there is some evidence at this stage indicating positive results under Effectiveness. For example, LCDI2’s work in pilot provinces under WS2 (per Box 4 TA support to Provincial Governments in NTB, Bengkulu and North Sumatera) is deemed of high significance across many of the experts interviewed for the evaluation. Generally, the approaches are felt to have been effective and are encouraged to be continued and deepened. Embedding provincial coordinators/advisors in North Sumatera and Maluku is widely supported as a good step towards deepening the provincial engagement and expanding capacity over time. It was also reported in several KIIs that the trainings were received well in terms of content. Whether the trainings have led to improved technical capacity cannot yet be measured due to the short time that had lapsed since the trainings[21] and so assessing the Effectiveness of this workstream is not fully possible; despite this, the preliminary evidence offers confidence that the Outcome level achievements will be recognised and that the programme will perform Effectively from a VfM perspective, at least for WS2.
[21] Case Study on TA to Provincial Governments.
Equity in terms of VfM is about extending a project’s benefits to include marginalised or disadvantaged groups and avoiding unintended negative consequences. In the case of LCDI2, such groups will include women, people with disabilities, and low-income groups who are at risk of losing their livelihoods because of LCD implementation. However, both the PEA and Finding 9 above point to lack of political commitment in terms of GEDSI integration at a policy level which is expected to be an obstacle to ensuring GEDSI-sensitive outcomes. In addition, LCDI2 and its outputs are somewhat removed from the ultimate beneficiary levels, which limits the extent the programme can be expected to have a direct impact on the equitable distribution of benefits in practice. While the Delivery Partner noted efforts to engage gender balanced stakeholders at the national and sub-national level for trainings and other engagements, it should be acknowledged that the primary counterparts for these activities are GoI institutions and, as such, the Delivery Partner has limited influence over the participants.
Given the complexities of the delivery, achieving the expected Effectiveness and Equity VfM results is likely to require a highly strategic approach. As noted in Finding 7 and Finding 9 above, there is a growing perception among programme stakeholders that a more focused approach is required to target specific outcomes over the next two years which could enhance both the achievement and measurement of Effectiveness. Similarly, a more strategic perspective is required to enhance GEDSI integration and Equitable results, although it has been noted that resource constraints are a reported issue hindering this.

# Conclusions
The LCDI2 programme stands at a pivotal juncture in Indonesia’s journey towards a low-carbon, climate-resilient future. Over its first two years, LCDI2 has demonstrated both the promise and complexity inherent in supporting systemic change across national and sub-national levels. The findings illustrate a programme that is highly relevant to Indonesia’s evolving policy landscape, strategically positioned within core government planning processes, and capable of adapting to shifting political and institutional contexts. At the same time, LCDI2’s experience highlights the persistent challenges of coherence, sustainability, and operational depth that accompany ambitious, multi-faceted interventions.
LCDI2’s underlying ToC is well-aligned with Indonesia’s green transition ambitions, blending TA at national and sub-national levels to accelerate progress. The programme’s adaptive delivery model has proven beneficial, particularly in the wake of national elections and subsequent shifts in government priorities. This flexibility has enabled LCDI2 to remain responsive and relevant, anchoring its work within key institutional frameworks such as the RPJMN/RPJPN and provincial planning systems. The result is a programme that is recognised by government partners as part of the “official planning system,” with strong ownership and credibility.
However, the breadth and flexibility of the LCDI2 ToC have also introduced challenges. Stakeholders have noted reduced clarity around causal pathways and intermediate outcomes, leading to confusion about objectives and the purpose of some activities. The lack of explicit linkages between workstreams has limited internal coherence, and the accommodation of a broad suite of activities has sometimes strained resources and diluted strategic focus. These tensions reflect the inherent trade-offs in designing programmes that must balance adaptability with the need for clear, measurable progress.
LCDI2’s most significant achievements are evident in its contributions to policy integration and capacity building. At the national level, the programme’s TA, particularly in systems dynamic modelling and scenario development, has helped Bappenas define ambitious targets for emissions reduction and green growth. LCDI2 played a pivotal role in shaping the inclusion of the GEI and circular economy principles within the RPJPN and RPJMN, and supported the development of the Circular Economy Roadmap and Action Plan.
At the sub-national level, LCDI2 has facilitated the integration of LCD principles into provincial long-term and medium-term development plans in North Sumatera, Bengkulu, NTB, and Maluku. These provinces have adopted key indicators and targets aligned with national goals, and in some cases, set even more ambitious objectives. The establishment of LCDI Task Forces and the development of RPRKBIDs have provided tangible frameworks for implementation, supported by targeted capacity building initiatives such as the Green Academy and AKSARA trainings.
These achievements are underpinned by strategic partnerships, particularly with Bappenas and provincial planning agencies, which have enabled LCDI2 to embed its work within existing government systems. The programme’s ability to convene diverse stakeholders and foster multi-level engagement has been consistently recognised as a strength, contributing to the institutionalisation of LCD concepts and practices.
Despite these successes, LCDI2 continues to face significant challenges that shape its trajectory and impact. The need to be highly responsive to government priorities has sometimes disrupted the sequencing of activities and limited the programme’s ability to leverage synergies across workstreams. Institutional fragmentation, frequent personnel turnover, and limited technical capacity, particularly at the sub-national level, undermine continuity and require ongoing adaptation.
Integrating GEDSI effectively into LCDI2 activities will be highly challenging without adequate resources and buy-in to shared objectives across key stakeholders and within the LCDI2 programme team. While the GEDSI action plan sets appropriate targets and strategies, significant attention is now required on implementation and risk management.
Sustainability remains a central concern. While LCDI2 has successfully embedded LCD principles into formal planning documents, the durability of these achievements depends on the development of robust financing mechanisms and the institutionalisation of systems and tools beyond the programme’s lifespan, as well as a clear exit and transition strategy for LCDI2.
Financing constraints, especially at the sub-national level, pose risks to the realisation of LCD plans, and the absence of binding regulations to lock in LCD practices leaves the programme vulnerable to political shifts. The integration of GEDSI principles, while advancing, remains uneven and limited in operational depth, with challenges in dedicated resourcing and alignment with monitoring and evaluation systems.
LCDI2’s management mechanisms have evolved in response to emerging needs, with improvements in monitoring, reporting, and adaptive learning. The programme has demonstrated good performance in resource use, cost savings, and value for money. Strategic leadership, effective governance structures, and productive relationships between key actors have contributed to delivery efficiency, though challenges persist in procurement, coordination, and mobilisation of specialised expertise.
The programme’s effectiveness is most evident in the achievement of output-level results, particularly in policy integration and stakeholder engagement. However, measuring higher-order outcomes and systemic change remains challenging, reflecting the complexity of policy-oriented TA and the need for sustained capacity and financial resources. Equity considerations, especially in extending benefits to marginalised groups, are recognised but constrained by the programme’s focus on institutional counterparts and limited influence over ultimate beneficiaries.
LCDI2’s story so far is one of strategic relevance, adaptive delivery, and meaningful contributions to Indonesia’s LCD agenda. Its achievements in policy integration, capacity building, and stakeholder engagement have laid a strong foundation for systemic change, while its challenges in coherence, sustainability, and operational depth highlight the complexities of driving transformation in dynamic contexts.
As LCDI2 moves forward, its experience underscores the importance of balancing flexibility with strategic focus, embedding sustainability into institutional frameworks, and deepening the integration of equity and inclusion. The programme’s journey reflects both the progress made and the ongoing challenges that must be navigated to ensure lasting impact. In doing so, LCDI2 offers valuable insights into the pathways and pitfalls of supporting low-carbon, climate-resilient development at scale.

# Lessons Learned
In this section, we provide the lessons learned based on the findings presented above, aligned to our LQs. Table 7 below provides a summary of the key lessons.
Table 7: Summary of Lessons Learned
Lesson	LQ	Findings
Lesson 1 Adaptive governance structures are essential to achieve results in dynamic political contexts, but must be matched with clarity of responsibilities, strategic coherence, and appropriate resource management.	LQ3.1, / LQ4.1	1, 3, 12, 13
Lesson 2 Effective MEL systems are essential enablers of adaptive management in policy-focused TA programmes.	LQ3.1	1, 7, 10
Lesson 3 Strategic partnerships with the right institutions can be critical to programme success, but they require both formal engagement mechanisms and informal trust-building and can become dependent on key interpersonal relationships.	LQ1.1, LQ1.2, LQ5.1	2, 3, 4, 12
Lesson 4 Embedding change in national and sub-national planning systems is a critical foundation but sustainability of implementation depends on the capacity to act on those plans or policies; LCDI2 and similar policy-oriented TA programmes must bridge the gap between policy and practice.	LQ1.1, LQ1.2, LQ5.1	4, 6
Lesson 5 Sustainability planning should begin early and be treated as a design principle, not an end-phase activity.	LQ5.1	6
Lesson 6 Political transitions and bureaucratic complexity must be anticipated as core risks, not externalities, in LCDI2-type TA programmes.	LQ2.2, LQ4.1	1, 4, 11, 12
Lesson 7 Where direct funding is included within a broader programme, it can be an effective tool for advancing objectives and securing ownership provided there is clear alignment with other interventions and activities.	LQ5.2	5
Lesson 8 For GEDSI to move from aspiration to impact at the provincial level, programmes must invest in tailored support, clear monitoring frameworks, and ongoing engagement with both government and civil society as well as other stakeholders, ensuring that inclusive development is embedded not just in plans, but in practice.	LQ6.1	7, 8, 9

Lesson 1 Adaptive governance structures are essential to achieve results in dynamic political contexts, but must be matched with clarity of responsibilities, strategic coherence, and appropriate resource management. LCDI2’s governance model, anchored in the trilateral arrangement between FCDO, OPML, and Bappenas, was designed to enable flexibility, responsiveness, and co-ownership. This structure has allowed the programme to adapt to shifting political priorities and contexts, respond to ad hoc requests from both FCDO and GoI counterparts, and maintain political relevance. However, the evaluation found that this adaptability came with trade-offs: decision-making processes have been less structured and certain, and the balance between strategic coherence (within the ToC) and responsiveness has been difficult to maintain creating challenges in effectiveness and efficiency. For other TA programmes operating in a similar space, this highlights the need to design governance structures that permit flexibility but include clear roles, responsibilities, and decision-making processes from the outset. Such programmes should consider mapping decision-making flows and identifying bottlenecks early where possible. MEL systems should also be well embedded to track the impact of governance adaptations on delivery and outcomes. This also shows the need to balance responsiveness to ad hoc requests and the trust that fulfilling them can generate with programme resources, strategic delivery priorities and coherence in activity design and delivery. In complex policy environments, governance is not just a structural issue, it is a strategic enabler. Adaptive governance must be designed not only to respond to change, but to manage it coherently and Delivery Partners need to invest in capacity for strategic oversight.
Lesson 2 Effective MEL systems are essential enablers of adaptive management in policy-focused TA programmes. In complex, politically dynamic environments like LCDI2, the ability to adapt strategically is critical. However, adaptation without direction risks drifting from the causal pathways of the ToC. The evaluation found that while LCDI2’s MEL system is relatively comprehensive and effectively facilitates communication with key stakeholders such as FCDO and the EMU, it has not been as consistently leveraged to inform programme decisions or guide strategic shifts as it could be (although it is acknowledged in the findings above that this is improving). To support adaptive management, MEL systems must do more than track compliance and core results; they must generate insights, facilitate reflection, and inform strategic choices. This includes: designing MEL tools that are user-friendly and decision-relevant, not just donor-facing; embedding learning and reflection moments into programme cycles, such as quarterly reviews or pause-and-reflect sessions; ensuring MEL outputs are interpreted collaboratively by Delivery Partners and government counterparts; and using qualitative methods (e.g. Change Harvesting) to capture insights about influence, delivery contexts and complexity. Comparable programmes should treat MEL as a strategic asset, not an administrative function, and resource it accordingly. LCDI2 also highlights the opportunity of engagement with strategic MEL partners (in this case, the EMU) and that while there may be challenges in managing collaboration between entities, there is also significant opportunity to enhance the effectiveness of MEL systems as adaptive tools by leveraging external insights and learning.
Lesson 3 Strategic partnerships with the right institutions can be critical to programme success, but they require both formal engagement mechanisms and informal trust-building and can become dependent on key interpersonal relationships. In policy-focused TA, formal structures provide legitimacy but informal trust enables influence. Programmes must cultivate both to navigate complex governance environments and achieve sustainable change by fostering meaningful collaboration and long-term ownership. LCDI2’s partnerships with Bappenas and the Bappedas highlight the benefit of establishing strategic partnerships early with formal frameworks, such as the MoUs and Steering Committee, and using responsive and relational engagement to build and maintain trust over time. They also demonstrate the potential risk of key inter-personal relationships, particularly in shifting political ecosystems where turnover is high, highlighting the need to form embedded institutional relationships. A more explicit mapping of both formal and informal engagement pathways with government counterparts could be beneficial for future programmes, as well as developing strategies to institutionalise influence, such as embedding staff in counterpart agencies or co-developing tools and frameworks.
Lesson 4 Embedding change in national and sub-national planning systems is a critical foundation but sustainability of implementation depends on the capacity to act on those plans or policies; LCDI2 and similar policy-oriented TA programmes must bridge the gap between policy and practice. LCDI2 has achieved notable success in embedding LCD in Indonesia’s national and provincial planning frameworks. However, evidence indicates that planning integration alone does not guarantee implementation. Provincial governments in particular often lack the financial resources, technical capacity, and political continuity needed to translate plans into action. For example, while LCD targets are included in RPJMDs, budget allocations and operational strategies have not yet been aligned. As such, programmes must recognise that planning integration is a strategic entry point, not an endpoint, and that this should be paired with implementation capacity building, financing strategies, and the development of monitoring systems to ensure sustainable implementation. This can be further enhanced via multi-level alignment, ensuring that national priorities are matched with sub-national capabilities and incentives. One approach that LCDI2 and other initiatives can consider is developing strategies to link planning outputs to operational mechanisms, such as budget tagging, performance indicators, and local delivery systems. There is also a need to monitor whether planning integration leads to actual behaviour change among implementing agencies to better understand levers of change. For FCDO and other international donors, this highlights that policy uptake is necessary but not sufficient for long-term change and that funding needs to also support downstream implementation and institutional strengthening.
Lesson 5 Sustainability planning should begin early and be treated as a design principle, not an end-phase activity. In LCDI2, the absence of a clear exit strategy and long-term ownership plan has created uncertainty about the durability of results. The evaluation highlighted that sustainability is not just about continuation—it’s also about embedding capacity, ownership, and financing mechanisms. For example, the lack of a full-time GEDSI lead and limited provincial capacity for dynamic modelling raised concerns about whether key functions could be sustained post-programme. Future programmes need to define sustainability pathways during inception, including institutional ownership, financing, and capacity development. Any exit strategies or transition plans should be co-owned by government counterparts to ensure they influence their development and can bring a practical lens to the design.
Lesson 6 Political transitions and bureaucratic complexity must be anticipated as core risks, not externalities, in LCDI2-type TA programmes. In policy-focused programmes, political transitions and bureaucratic complexity are not unexpected disruptions, they are the norm. Success depends on anticipating and adapting to these dynamics with strategic intent. LCDI2 has navigated national elections, leadership changes, and bureaucratic restructuring affecting both the pace and direction of delivery. In doing so it has demonstrated the benefit of using political economy analysis to understand institutional dynamics and political trends; while the programme could have integrated this further, it does show that PEA can be used as a dynamic management tool provided it is revisited and updated, especially during transition periods. As noted above, LCDI2 has also generated learning about the importance of maintaining strategic institutional relationships to whether political headwinds. Donors and implementing agencies must recognise that policy engagement is inherently political, and support programmes to invest in PEA, relationship management, and adaptive planning. This should include minimising rigid delivery expectations during known transition periods, allowing for strategic recalibration. Developing transition protocols, including onboarding materials for new counterparts, flexible workplans, and rapid re-engagement strategies could be useful mitigation strategies for future political shifts.
Lesson 7 Where direct funding is included within a broader programme, it can be an effective tool for advancing objectives and securing ownership provided there is clear alignment with other interventions and activities. The WS4 experience to date, and the perceptions of key stakeholders in relation to its deployment, underscores the importance of strategic alignment, operational clarity, and sustained support in innovation funding for LCD. The establishment of the Innovation and Technology Fund, while promising in its partnership with BPDLH, revealed that early and explicit connections between fund objectives, broader programme outcomes and priorities of key stakeholders are essential to build consensus and streamline decision-making and mobilisation. Early discussions around WS4 also indicate that capacity building and post-implementation support are likely to be needed to ensure the sustainability and scalability of pilot projects, which could effectively be supported through other workstreams. Conversely it is expected that leveraging these pilots to inform policy and practice will enhance the ownership and incentives associated with those policies. Lastly, the experience to date highlights a need to balance flexibility with robustness in the resourcing of similar funds, as further described in Recommendation 9. Ultimately, early evidence related to WS4 shows that innovation funds must be more than financial mechanisms, they must be strategically embedded and aligned with the broader ToC.
Lesson 8 For GEDSI to move from aspiration to impact at the provincial level, programmes must invest in tailored support, clear monitoring frameworks including GEDSI disaggregated data, and ongoing engagement with both government and civil society, ensuring that inclusive development is embedded not just in plans, but in practice. The experience of LCDI2 at the provincial level demonstrates that meaningful GEDSI integration requires more than the inclusion of principles in planning documents, it demands intentional design, dedicated resources, and sustained capacity building including participatory and accountability mechanisms. Provinces such as NTB, North Sumatera, Bengkulu, and Maluku have shown that aligning GEDSI activities with local flagship programmes and facilitating multi-stakeholder workshops can create synergy between climate action and inclusive development and foster genuine dialogue on the needs of vulnerable groups. However, the depth and consistency of GEDSI integration remain uneven, often limited by resource constraints, lack of dedicated expertise, and insufficient operational guidance. Capacity building in future programmes or interventions must go beyond basic gender sensitivity to address intersectionality and empower local actors to translate GEDSI concepts into actionable policies and budgets.

# Recommendations
In this section we provide eleven recommendations derived from the findings and lessons learned. The recommendations are presented in priority order, reflecting both the importance and urgency of the recommended action for the programme’s delivery. Intended audiences have also been provided split into primary audience, the party expected to own the recommendation, and secondary audiences, the parties expected to facilitate the recommendation. Further development of the recommendations has been undertaken collaboratively with FCDO and the LCDI2 Delivery Partners through workshops in December 2025.
## LCDI2 Process Evaluation Recommendations
Priority	Recommendation 1 In the next phase of LCDI2, the impact of activities should be further enhanced via a sharpened focus on priorities. / The programme’s TA should be strategically concentrated on a smaller set of high-priority interventions that align closely with both the ToC and national development objectives. While responsiveness to GoI requests has built trust and established LCDI2 as an important technical partner for Bappenas, it is now time to leverage this position and pursue a more selective suite of TA activities with a sharper focus on long term sustainability, capability development, and knowledge transfer and management to consolidate and ensure longevity of the results achieved to date. / To facilitate this, activity planning should be based on a framework that assesses which activities will add most value within the ToC in terms of the achievement of the intended outcomes. Additional prioritisation criteria should be drawn from alignment with the emerging priorities from the evaluation and the AR, and VfM considerations. This will require a clearer articulation by the programme of specific outcome results (both intermediate and long-term) which are expected to be achieved within the ToC and monitoring framework to ensure accountability and guide activity selection. A robust, shared prioritisation framework between the LCDI2 team and FCDO, and ideally Bappenas, is needed which sets out these priority outcomes and related TA activities. Concentrating resources on areas with the greatest potential for catalytic change, such as financing mechanisms, institutional capacity building, and GEDSI mainstreaming, is recommended at this stage. This might include training of the trainers on key supported tools such as systems dynamic modelling or GHG monitoring practices or developing institutional capacity to build teams and sustainable resources to support LCD policymaking post-programme. / This reprioritisation should provide for ad hoc, resource-intensive requests from Bappenas, FCDO, or other partners to be turned down. Reducing responsiveness to ad hoc demands for TA across central and provincial government will be necessary for the programme to build greater momentum and critical mass behind key activities. While some flexible activities should be prioritised to retain influence, the programme should focus more on achievable results which require concentrated TA support.
High
Primary Audience
LCDI2 Delivery Partners (OPML)
Secondary Audience
FCDO, Bappenas
Related Findings
1, 4, 5, 6

Priority	Recommendation 2 There is an opportunity to strengthen alignment across workstreams by designing activities under WS3 and WS4 to strategically support WS1 and WS2, with a focus on high-impact goals and political economy challenges. / As highlighted in the findings, while WS1 and WS2 have made strong progress in embedding LCD into national and sub-national planning systems, WS3 and WS4 have operated with less strategic clarity and less tangible objectives. Moving forward, LCDI2 should enhance internal coherence by ensuring that WS3 and WS4 are more explicitly designed to reinforce the objectives and delivery of WS1 and WS2. / Political engagement under WS3, particularly with parliamentarians, could play a catalytic role in enabling WS1 and WS2 delivery. Parliamentarians influence budget allocations, legislative mandates, and political narratives that shape the implementation of LCD policies. By engaging strategically with national and provincial legislators, WS3 can help: / Secure political buy-in for LCD-integrated planning to increase the likelihood of implementation and funding; / Champion policy coherence across ministries and sectors helping to overcome institutional silos highlighted in the evaluation findings; and / Support sub-national delivery by encouraging provincial parliaments to endorse LCD-aligned plans and allocate resources accordingly. / WS3 could evolve into a more targeted communications and advocacy platform, supporting stakeholder engagement and political buy-in around programme priorities to drive support for specific outcomes supported by LCDI2 TA under WS1 and WS2. Further recommendations related to specific WS3 activities are noted in Recommendation 4. / For WS4, pilot projects implemented and managed under the fund provide an opportunity to build relationships between WSs, including providing input to AKSARA, creating a model for GEDSI integration under WS1 and WS2, and anchoring provincial policy decisions with physical results and incentives. / To enhance internal coherence across the workstreams, more on-the-ground support is recommended, particularly in terms of embedded support for sub-national institutions. A stronger presence within key institutions could serve to better coordinate workstream activities and ensure government partners understand the linkages. It is also strongly recommended that the linkages between the workstreams be made explicit within the ToC to identify opportunities for consolidated support and key assumptions.
High
Primary Audience
LCDI2 Delivery Partners (OPML)
Secondary Audience
N/A
Related Findings
5

Priority	Recommendation 3 More focus within WS2 is needed on generating resources for LCD implementation and sustainability at the Provincial level as the primary enabler for success. / The evaluation found that, while LCDI2 made strong progress in integrating LCD into provincial planning documents (e.g. RPJMDs and RPRKBIDs), the ability of sub-national governments to implement these plans remains constrained by limited financial and technical resources. In particular, provinces face challenges in accessing funding streams, mobilising internal budgets, and sustaining LCD activities beyond the programme’s lifecycle. / By prioritising resource mobilisation and financial sustainability, WS2 can move beyond planning integration to support real-world implementation, ensuring that LCDI2’s contributions translate into lasting development outcomes at the provincial level. To address this, WS2 should place greater emphasis on: / Supporting provinces to identify and access alternative financing mechanisms, including results-based payments, special allocation funds (DAK), donor grants, and private sector investment. / Developing and facilitating public-private partnerships, potentially coalescing around pilot projects under WS4. / Strengthening budget tagging and planning systems to ensure LCD activities are reflected in annual workplans and budget submissions, to ensure they receive the necessary political and financial attention. / Building institutional capacity for financial planning, proposal development, and engagement with national ministries and funding platforms. / Facilitating partnerships with local universities, CSOs, and private actors to co-finance and co-deliver LCD initiatives.
High
Primary Audience
LCDI2 Delivery Partners (OPML)
Secondary Audience
Bappenas, FCDO
Related Findings
4, 6, 8

Priority	Recommendation 4 WS3 should develop a sharper overall focus and strategy. It has high potential for transformative effects and needs appropriate resource allocation. / The ambition of WS3, working initially with “friendly” stakeholders, could be raised in the following years of LCDI2 to try and build a larger coalition, cultivate new voices, and bring new actors to the table. This includes engaging prominent political or private sector figures who may not be friendly towards LCD, or at least not explicitly so, and seeking to bring them to the table. / To achieve this, a clearer, evidence-based prioritisation of target groups for WS3 would be beneficial. Existing outputs including the LCDI2 stakeholder mapping and Social Network Analysis could be better leveraged to support this. LCDI2 should also build on and update its interest/influence mapping of parliamentarians and other political figures in order to assess which actors have the greatest potential voice and which are likely or unlikely to be open to increased engagement. Further power-interest mapping of key national actors may be beneficial. / A review of the monitoring indicators for WS3 is also recommended. Indicator 3.1 uses a broad definition of “engagements” which spans meetings, capacity building and training sessions, and technical report outputs, the latter of which may also overlap with Indicator 3.2. Therefore, its targets have been significantly exceeded. It is recommended that the programme either review the level of ambition aligned to the broad definition of engagement or narrow the definition to increase the workstream’s focus. Additionally, the programme should consider introducing quality measures for these engagements to move beyond counting activities and begin assessing the results of those activities (i.e. post-engagement surveys, for example).
High
Primary Audience
LCDI2 Delivery Partners (OPML)
Secondary Audience
FCDO
Related Findings
2, 5, 11

Priority	Recommendation 5 The LCD narrative across WSs should be better linked with economic growth, job creation, and benefits for Indonesian people, including alignment to the needs of political actors to seek voter/community support. / To deepen impact and increase local ownership, LCDI2 should refine its narrative across all Workstreams to emphasise how LCD contributes directly to Indonesia’s economic transformation, employment generation, and community well-being. This is not concerned with altering LCDI2’s objectives and ToC but how the programme communicates about LCD. In doing so, at the same time, this is likely to significantly and efficiently benefit the implementation the GEDSI Action Plan. The inclusion lens more systematically applied could leverage significant overall gains in Programme effectiveness. / LCDI2 has made technical progress in integrating LCD into planning systems, the narrative framing has not always resonated with political actors or the wider public. WS3, in particular, should be leveraged to communicate LCDI2’s relevance to political actors and their voters or communities, to disseminate how LCD-aligned policies can support livelihoods, unlock green jobs, and improve local resilience. This framing is especially important in engaging parliamentarians, who are responsive to public-facing development narratives and can play a pivotal role in the endorsement and operationalisation of LCD priorities. This approach should be embedded in strategic communications, stakeholder engagement plans, and policy dialogues, ensuring that LCD is positioned not only as a technical solution but as a politically compelling and socially relevant development strategy.
Medium
Primary Audience
LCDI2 Delivery Partners (OPML)
Secondary Audience
FCDO
Related Findings
1, 7

Priority	Recommendation 6 LCDI2 should try to strengthen its institutional position as a key GoI partner through building relationships beyond Bappenas. / It is recognised that the while the programme is already trying to strengthen its position in this way, current efforts would benefit from review especially in terms of the balance of resources placed on this versus other activities. While Bappenas has been a central and effective partner for LCDI2, the programme’s reliance on a single Directorate within Bappenas has created limitations in reach, influence, and sustainability. To improve results and ensure broader institutional ownership, LCDI2 needs to expand and improve where possible its engagement across a wider set of government actors. This may benefit from allocating more of the right kind of resources quickly to providing strategic influence across the GoI beyond that envisaged via LCDI Commissioners. / Within Bappenas itself, the programme has primarily worked through the Directorate of Environment. While this directorate has been committed and responsive, its mandate covers only a fraction of the sectors relevant to LCD. Other directorates such as those overseeing energy, infrastructure, finance, Women Empowerment, Child Protection, Youth and Sports and regional development are also critical for developing and implementing LCD policies. The programme needs to explore how best to systematically engage these units to reduce the risk of siloed implementation. / Beyond Bappenas, LCDI2 should strengthen its relationships with line ministries that are directly responsible for sectoral policy and delivery. For example, MoEF, MEMR, and MoF all have mandates that intersect with LCDI2’s objectives. These ministries also manage key data systems and reporting platforms (e.g., SRN, SIGN SMART) that need to be harmonised with LCDI2’s tools like AKSARA. Improved coordination would enhance policy coherence and reduce duplication or stakeholder fatigue. Options could include the provision of embedded technical expertise or the commissioning of research or technical outputs via the LCDI2 programme which would be specifically beneficial to the role of these other ministries. / At the sub-national level, LCDI2 has made progress in engaging provincial governments, but further institutionalisation is needed. This includes working with provincial sectoral agencies, not just planning bodies, to ensure that LCD is reflected in operational strategies and budgets. Formalising these relationships through MoUs or joint workplans could help embed LCDI2’s approaches more deeply.
Medium
Primary Audience
LCDI2 Delivery Partners (OPML)
Secondary Audience
N/A
Related Findings
2, 3, 12

Priority	Recommendation 7 More focus within WS1 is needed on the development of annual LCD monitoring at the national level and enhancing knowledge management and sharing systems across GoI, providing practical guidance and mentorship under AKSARA or other monitoring systems. / While WS1 has made notable progress in developing the analytical and technical underpinnings for Indonesia’s low-carbon transition, such as modelling, policy scenario development, and preparations for interoperability between AKSARA and other systems, these efforts have not yet resulted in a unified national monitoring system or interoperability. Currently, data and reporting are fragmented across separate platforms (AKSARA, SRN, SIGN SMART, and various ministry-level databases), making it difficult to consistently track progress towards RPJMN and NDC targets. / To address this, WS1 should prioritise the creation of an integrated annual monitoring function that brings together these disparate systems. This would help position LCDI2 as the key technical support for Indonesia’s climate reporting and policy alignment efforts. / There is also a pressing need for clear, practical guidance and mentorship for users of AKSARA and related systems. Indonesia’s monitoring architecture is currently split between bottom-up (AKSARA, supporting sub-national data integration) and top-down (SRN, SIGN SMART, acting as national registries) approaches, which limits the ability to aggregate sub-national activities towards national climate targets. WS1 is well-placed to bridge this gap by providing technical harmonisation and mentorship, helping provincial Bappeda and DLH offices with data validation, indicator alignment, and effective use of AKSARA alongside SRN and SIGN SMART. Through sustained mentorship and the establishment of "learning loops" between national and local stakeholders, WS1 can help transform AKSARA into an effective link between on-the-ground actions and Indonesia’s national climate accountability framework.
Medium
Primary Audience
LCDI2 Delivery Partners (OPML)
Secondary Audience
N/A
Related Findings
1, 4

Priority	Recommendation 8 The resourcing available and ambitions of the GEDSI strategy require review considering the findings of the evaluation. / To ensure GEDSI is meaningfully integrated into LCDI2, the programme must adopt a strategic, well-resourced, and contextually grounded approach. This begins with the recognition that GEDSI integration cannot be incidental, it requires dedicated resources, leadership, and collaboration. / A full-time GEDSI Adviser should be appointed, equipped with both technical expertise and a deep understanding of the local context. This role is essential not only for implementing the GEDSI Strategy and Action Plan but also for identifying entry points across sectoral priorities and facilitating capacity building within the programme team and relevant stakeholders. The adviser should be supported by a segregated GEDSI budget, ensuring that GEDSI activities are not diluted within broader programme expenditures. Periodic engagement with external GEDSI experts can further enrich the programme with fresh perspectives and critical insights. / The programme’s ToC should be revisited to explicitly articulate GEDSI touchpoints. These touchpoints will serve as anchors for the logframe and monitoring strategy, ensuring that GEDSI outcomes are tracked and evaluated systematically. A review of the GEDSI Action Plan is also necessary, identifying which actions have been completed, which require adaptation, and which may be beyond the programme’s scope. These actions and their associated targets should be directly linked to the programme’s logframe to reinforce accountability. / Recognising the limitations of current regulatory and policy frameworks in Indonesia, the GEDSI team should consider initiating a policy review and advocacy process. This could include the development of a policy brief and convening dialogues with stakeholders to promote GEDSI-sensitive reforms. If deemed a priority, this work could significantly enhance the enabling environment for GEDSI integration. / Effective communication and coordination among partners is vital. The programme should evaluate its collaboration strategy with Bappenas, focusing on aligning expectations and developing step-by-step approaches to gender integration. Establishing designated GEDSI focal points within FCDO and Bappenas would facilitate regular dialogue and ensure that GEDSI efforts remain realistic and within the programme’s remit. / Capacity building must be ongoing. The initial integration of GEDSI in PRPKBID was a valuable orientation, but it should not be a one-off event. Training should evolve beyond binary gender distinctions and delve into deeper, intersectional understandings of inclusion. Innovative mentoring and expert-led discussions can help sustain attention to GEDSI and improve the quality of planning and implementation. / Budgeting remains a critical challenge. GEDSI integration must be reflected in actionable programmes with appropriate nomenclature and budget allocations. The Ministry of Finance’s budget tagging initiative offers a foundation, but it needs to be expanded across line ministries. Bappenas along with the State Ministry of Women Empowerment can play a key role in facilitating consensus and supporting this process. Adopting a standardised GEDSI categorisation framework will also aid in monitoring and reinforce shared understanding at both national and sub-national levels.
Medium
Primary Audience
LCDI2 Delivery Partners (OPML)
Secondary Audience
FCDO, Bappenas
Related Findings
7, 8, 9

Priority	Recommendation 9 To ensure the resourcing model for WS4 is optimal for funding new activities, several strategic and operational factors should be considered.[22] / An optimal resourcing model for WS4 must be designed to balance flexibility, strategic alignment, and operational robustness. First, it is essential to establish clear and explicit connections between the fund’s objectives and the overall programme outcomes, so that resources are directed toward activities that demonstrably advance LCDI2’s strategic goals. Early and collaborative planning with key institutional partners, BPDLH and FCDO, should define roles, responsibilities, and decision-making processes, ensuring that the fund’s management is both credible and agile. / Timeliness is critical: the model should include streamlined procedures for fund setup, project selection, and disbursement, reducing bureaucratic delays and enabling rapid response to emerging opportunities. The resourcing approach should also allocate sufficient capacity for post-implementation support, recognising that pilot projects require ongoing TA and monitoring to achieve sustainability and scalability. / A robust MEL framework is needed for the fund, with resources dedicated to tracking not only the number and quality of funded activities, but also their longer-term outcomes and lessons learned. This includes gathering data on the diversity of applicants, the impact of innovations, and the integration of GEDSI principles. / Finally, the model should be adaptive, allowing for periodic review and reallocation of resources in response to evolving needs, risks, and opportunities. By prioritising high-impact projects, embedding inclusive design, and ensuring sustained support, the resourcing model for WS4 can maximise VfM and promote accelerated change in Indonesia’s LCD landscape.
Medium
Primary Audience
LCDI2 Delivery Partners (OPML)
Secondary Audience
N/A
Related Findings
5, 11
[22] This recommendation responds to a specific request from the Delivery Partner during the Process Evaluation approach development to explore funding processes for WS4 per LQ5.2. This was requested prior to the arrangement with BPDLH but, given the fund is still mobilising and there is significant scope for early learning, the recommendation has been maintained.

Priority	Recommendation 10 There are a range of potential ways to further strengthen the MEL System to support more effective programme implementation. / Proposed actions should be considered in line with proportionality in respect of resource allocations across Delivery Partners, overall reporting burdens, and potential benefits. Priorities in order of urgency include: / Establishing monitorable Intermediate Outcomes and further strengthening the logframe. Further reflection on the Evaluation and Annual Review results could lead to agreement on a range of objectives, but these should include: / Developing IOs Iin line with the emerging priority areas for programme activities, evaluation research and findings, Change Harvesting results, further inputs from relevant stakeholders, assessment of SMART criteria, and agreement of feasibility between MEL stakeholders. Categories of potential high relevance to supporting enhancements to the ToC and monitoring system include: the human resource capacity of specific stakeholders/organisations; the capacity of key infrastructures, such the LCD One Portal Database, AKSARA, and the establishment of an LCD Academy; and the commitment of stakeholders to LCD/LCDI. / Improving measurement of the quality of outputs including via the Change Harvesting process in terms of supporting quality management decision-making and ensuring the outputs support Intermediate Outcomes. / Establishing the goals and mechanisms for a new Annual Learning Cycle based on the priorities and evidence gaps emerging from the evaluation, which aligns well with programme management decision making schedules through to the FCDO’s Annual Review process for 2026. An initial set of potential activities to support this are provided below. / More focus on risk management in the MEL and programme management systems and reporting. As LCDI2 faces many significant challenges and barriers outside the programme’s immediate control. Barriers and opportunities for delivery should be better reflected in the identification of risks around the ToC’s assumptions. Within this, the programme would likely benefit from systematic and regular monitoring of the political economy at national and provincial levels, including recommended and documented adaptations to it integrated into the Quarterly reporting process. Options for resourcing this include via any reductions identified in current reporting burdens on the Delivery Partner and via leveraging support in this area from the LCDI2 MEL partner. / Developing and monitoring appropriate GEDSI indicators for the logframe based on further clarification from FCDO about expectations on GEDSI and further work for understanding how best to mainstream GEDSI into the ToC and to better integrate the Change Harvesting results into understanding for GEDSI results monitoring. Evaluation evidence was not yet sufficient to make specific proposals in this area and further discussion and agreement will be needed with MEL stakeholders. / Re-adjusting resourcing balance and clarity on roles and responsibilities on MEL across FCDO-OPML-NIRAS. This could be usefully aligned with emerging priorities from the evaluation and resources required to address some of its recommendations. / Review reporting burdens. It is currently unclear if the volume of information created and processed for monitoring and reporting purposes is proportionate to the uses made of it. Moreover, there is evidence that the reporting burden inhibits the use of OPML resources which could be focussed on other MEL priorities. Efficiencies should be explicitly linked with freeing up resources to enhance approaches to other areas of potential improvements to the MEL system.
Medium
Primary Audience
LCDI2 Delivery Partners (OPML)
Secondary Audience
FCDO
Related Findings
1, 7, 10

Priority	Recommendation 11 There is significant scope for LCDI2 to enhance linkages with other FCDO programmes and those of other Development Partners in LCD-related sectors, such as in leveraging technical expertise and joint planning or inter-linkage of goals. / Investments here can drive efficiency gains and enable LCDI2 to play a leading role in contributing to wider, more coherent and systemic change. This is a view also shared by managers of related initiatives but there is also a shared lack of willingness to invest more on coordination. However, it would be appropriate for FCDO to develop feasible objectives in this area in the period to its next Annual Review and favourable if they would be willing to take a lead on coordination in the sector. Feasible objectives include around advancing coordination with other development partners working with Bappenas to develop shared strategies to ensure optimal responses to ad hoc work requests. More broadly, exploring more in-depth collaboration with other FCDO programmes in Indonesia could be beneficial and of relatively low resource intensity.
Low
Primary Audience
FCDO
Secondary Audience
LCDI2 Delivery Partners (OPML)
Related Findings
2, 12

## Recommended Knowledge, Learning, and Dissemination (LKD) priorities for LCDI2 in its next phase
Based on the Evaluation results, including the limitations on the evidence collected, Table 8 sets out an initial set of Learning, Knowledge, and Dissemination (LKD) products that could form important components of the Learning Cycle and inform adaptive management within LCDI2’s evolving context. The EMU received initial feedback from FCDO and the Delivery Partner on these proposals at a MEL and governance workshop on 9th December 2025. High-level concepts are provided in the table and it has been agreed to further develop these and timetable them during workshops in January 2026. A draft Learning Use and Influence Plan for this evaluation can be found in Annex 5 and will be subject to development in the context of ongoing discussions around the development of the Annual Learning Cycle.
Table 8 Potential LKD topics
LKD topic and potential objectives	Rationale and links to the Evaluation
Quarterly or 6-monthly Sustainability Review / Further evidence collection around the needs for sustainability, subject to regular review, and integrated into adaptive work planning. Further research can explicitly support the development and updating of the exit strategy and inform workstream design adaptation. This would help understand the future institutional form of LCDI2 after the current delivery phase (2027). / Can be carried out in alignment with proposed PEA work below.	There is evidence that FCDO and OPML, with Bappenas, have deep insights into the Political Economy and this influences their decision making. Given the importance of the changing Political Economy to the success of the programme and how it affects the sustainability of its results, these proposals support the recommended increased focus on risk management and aim to ensure the MEL system reacts appropriately, systematically, and regularly to both established and emerging needs related to the wider context in which LCDI is being implemented. / The intention is to go beyond existing channels for considering these issues, as LCDI2 moves into is later phase with a sharper strategic focus. / The EMU will consider how these LKD products could be further linked to GoI agendas and used to strengthen the wider LCD agenda.
Quarterly Political Economy Analysis / Develop a process for a light touch Quarterly review of the PEA and update of the PEA targeted at informing workstream adaptations to be integrated into the Quarterly Reporting process. / Can be carried out in alignment with the proposed Sustainability work above.
Toolkit for translating evidence into policy-ready formats / Establish standard templates (briefs, dashboards, RPJMD annex inserts, etc) for converting WS1 and WS4 outputs into user-friendly products for planners and decision-makers.	The evaluation found that some stakeholders often see technical outputs as too complex or inaccessible. Providing ready-made formats strengthens cross-workstream coherence and improves adoption prospects at both central and provincial levels.
Guidance on multi-stakeholder partnerships and non-state actor engagement / Develop a structured approach to strengthen the participation of non-governmental stakeholders in LCD. The guidance could investigate how WS3 can strategically mobilise coalitions (CSOs, faith-based groups, private sector) and map their contributions into policy influence chains within the current and changing context of the LCDI2.	The evaluation found that non-state mobilisation is a recognised important indirect pathway to influence. A well-developed guidance product could help standardise engagement practices and improve the traceability of coalition contributions.
Guidance on sub-national LCDI2 secretariat development / Provide a practical framework for establishing and operationalising LCDI Secretariats at the provincial and district/city levels based on more in-depth understanding of local conditions.	The evaluation evidence points to the critical nature of establishing LCDI Secretariats at the sub-national level in ensuring that Indonesia’s LCD is effectively implemented and institutionalised across all levels of government. More work in supporting this development could be beneficial. / The LCDI2 Delivery Partner noted that Bappenas is also conducting work to develop this guidance and that any LKD products should align and complement Bappenas’s work.
Learning about previous piloting and replication adoption of LCD activities in related initiatives / In-depth examination of relevant piloting for example in the FCDO-funded MENTARI programme and the community-based renewable energy initiative supported by the Millenium Challenge Account Indonesia, and assessing the facilitating and inhibiting factors in adoption, continuation, and replication.	Several initiatives to facilitate piloting of LCD activities have been implemented in Indonesia. It is important to gather learning from those initiatives to develop better strategy for future implementation.
Learning from and with other FCDO Programmes / The evaluation results underline a range of potential benefits from further learning in this area. There is also a gap in relevant evidence and learning form the evaluation that could guide specific objectives (with no KIIs possible with other FCDO Programme teams). Moreover, learning objectives in this area need to be feasible, strongly guided by inputs from FCDO, and based on analysis about why previous attempts at designing an LKD product in this area in late 2024/ early 2025 did not gain traction. Nevertheless, the 2025 Evaluation provides an excellent opportunity to consider how dissemination of its results to wider FCDO stakeholders could leverage at least some initial learning for all related FCDO Programmes and allow for scoping how further learning could best be designed. FCDO have noted that this learning piece would be timely given the proposed cuts to UK aid funding, and would benefit from focusing on how learning can be framed and applicable to wider programmes beyond LCDI2.
Learning to support GEDSI mainstreaming / An area of learning proposed by the LCDI2 Delivery Partner is to develop and disseminate learning products to support GEDSI mainstreaming. Specific proposals for lessons learned from the integration of GEDSI will be further developed by the EMU and Delivery Partner in January 2025.
Other proposed learning products / The EMU will also explore other LKD products beyond those listed in Table 8 as proposed by Delivery Partners and FCDO. One such suggestion is the development of a unified LCDI2 narrative for all stakeholders engaged in the programme. The EMU will consider the development of this narrative document with the purpose of encouraging GoI Ministries including Bappenas to converge and agree a core narrative that suits a broad range of sectoral policy priorities.

# Annex 1: Terms of Reference
## Background
1. The Foreign, Commonwealth and Development Office (FCDO) pursues the UK’s national interests and projects the UK as a force for good in the world. We promote the interests of British citizens, safeguard the UK’s security, defend our values, reduce poverty and tackle global challenges with our international partners. In Indonesia, the UK’s development objectives are focused primarily on supporting Indonesia’s objectives in tackling climate change.
2. The British Embassy Jakarta (BEJ) is seeking a supplier for an Evaluation Management Unit (EMU) to carry out the independent evaluation of FCDO funded activities under the Low Carbon Development Initiative (LCDI) Phase 2 programme in Indonesia for duration of four years (2023-2027).
### The Low Carbon Development Initiative
1. The LCDI is a longstanding partnership between UK and Government of Indonesia (GoI), represented by the Development Planning Ministry (Bappenas), since 2017. During the first phase of LCDI (2017- 2021), Bappenas led the production of different development scenarios for achieving net zero emission targets. A key result was the launch in 2019 of a report called “Low Carbon Development: A Paradigm Shift Towards a Green Economy in Indonesia” (the LCDI report) 1 . Findings and policy scenarios from this report have since been integrated into Indonesia’s National Mid-Term Development Plan (RPJMN) 2020-2024.
2. The LCDI Report provides a clear, evidence-based set of scenarios, for an ambitious, low-carbon pathway for Indonesia that also delivers growth, jobs and poverty reduction. If the most ambitious scenario in the LCDI Report is implemented, the following benefits are predicted to be realised by 2045:
  1. the Indonesian economy will grow on average by 6% p.a. 2019-45,
  2. over USD 5.4 trillion will be added to GDP in 2045,
  3. 15.3 million more jobs will be created (which are greener and better paid),
  4. air quality and living conditions will improve.
Since the COVID-19 pandemic, the modelling that produced as part of LCDI report has been revised to consider the impacts of COVID-192 on Indonesia’s economy, society and environment.
Bappenas has requested a continuation of bilateral cooperation on the low-carbon development agenda. A second phase of LCDI is anticipated to commence in mid-2023.
## Objectives and Scope of LCDI Phase 2
1. LCDI Phase 2 is a four-year programme (2023-2027) which will be funded through UK International Climate Finance. Phase 2 will build upon the foundations laid by Phase 1, with a view to mainstreaming low carbon development both at national level and with key provinces, during and beyond the current RPJMN (2020-24), towards the next National Medium and Long-term Development Plans (RPJPN 2025-45) and Indonesia vision 2045.
2. The programme is described in the approved business case, available online here: 90000769.odt (live.com). Annex C presents the Theory of Change set out in the business case. Annex D contains the ToR for Invitation to Tender for the LCDI 2 Supplier contract, which is highly relevant to the EMU Supplier’s expected objectives and delivery model.
3. Indicative outcomes – to be refined in programme’s initial inception phase - are:
1. Low-carbon growth commitments are integrated into national and provincial medium and long- term development plans, underpinned by strong Monitoring, Reporting and Verification (MRV) systems.
2. Broad and deep political support is mobilised for low carbon development to achieve the 1.5- degree target.
3. Cross-sectoral and thematic policy reforms, spanning green and blue economy, enable the achievement of a high-ambition low carbon development scenario.
To deliver the outcomes of LCDI Phase 2, there are four key workstreams as follows.
Workstream 1: Partnerships with National Line Ministries. The Programme will partner with key ministries such as Bappenas, Ministry of Finance and Ministry of Home Affairs as well as sectoral ministries including the Ministry of Environment and Forestry, Ministry of Energy and Ministry of Agriculture to develop the policies and plans to implement a low carbon development pathway. Anticipated activities will include:
1. Develop low carbon plans, policies, budgets, and interventions.
2. Integrate low carbon targets and approaches into government and sectoral ministries’
annual and/or strategic plans.
1. Advance the design and application of the LCDI Model3 as a key input to inform the process of formulating targets and policy mix within the RPJMN 2025-2029 and RPJPN 2025-2045.
2. Strengthen Indonesia’s approach to monitoring and reporting GHG emissions, in particular by improving linkages and coherence between different systems (eg: AKSARA4, and sectoral MRV systems).
Workstream 2: Partnerships with Key Provincial Governments. Led by the Government of Indonesia, partnerships will be strengthened and/or established with provincial governments to advance the low carbon development agenda at the sub-national level. Partner provinces will include at a minimum the three pilot provinces from LCDI Phase 1, which are Riau, South Sulawesi and West Papua. The anticipated indicative activities will include:
1. Developing low carbon plans, policies, budgeting and interventions to mainstream the integration of the low carbon development indicators into provincial-level development planning and associated plans and regulations.
2. Develop LCDI model for application in the development of (1)
3. Promoting institutionalisation and long-term buy in to the low carbon development agenda at the sub-national level.
4. Technical assistance to operationalise the new integrated LCDI Monitoring, Evaluation and Reporting (MER) system, and to ensure synchronicity between provincial and national MER approaches.
Workstream 3: Political Engagement. LCDI Phase 2 will support key organisations to work politically and strategically to build domestic and international coalitions of support to drive Indonesia’s ambition on low-carbon development. This will require building effective relationships with parliament, private sector, academia, and other non-state actors.
Workstream 4: Innovation and Technology Fund. Currently, the GoI considers that key barriers exist to realising the higher ambition scenarios of LCDI – including public policy, political and technology constraints. LCDI Phase 2 will establish a competitive funding mechanism to support GoI to test new and scalable approaches for addressing these barriers.
## Purpose and objective of the Contract
1. The primary purpose of the EMU contract is to maximise the LCDI 2 programme’s efficiency, effectiveness, impact, and sustainability. The secondary purpose is to strengthen the FCDO – and global - evidence base on how to foster green, resilient economic growth.
2. The objectives of the evaluation are set as following:
1. Strengthening the monitoring framework of the LCDI Phase 2 Supplier, to ensure ongoing, systematic collection of information for assessing the LCDI 2 progress toward the outputs, outcomes, and impacts.
2. Undertaking independent evaluation to:
  1. Assess the programme’s contribution to intended outcomes and impact, and the prospect for sustainability of effects immediately beyond programme’s exit and in the long-term;
  2. Identify whether the programme has contributed to any unintended consequences or effects (positive or negative);
3. Facilitating learning and knowledge dissemination to process, present and reflect on the information generated from monitoring and evaluations (and from any other evidence generating activities) and use this to:
  1. continuously improve the programme’s ability to achieve results, noting that LCDI2 is intended to be an adaptive programme.
  2. Expand the UK Government’s and global evidence base on what works and what does not
work for building low carbon development and green economy.
## Audience and stakeholder landscape
1. The primary audience and receipt for the activities and services under this contract is the British Embassy Jakarta, specifically the LCDI Phase 2 programme team. Secondary audiences include the programme’s partners, particularly within the Government of Indonesia (eg: Bappenas, provincial governments); and other teams in HMG working in the region and/or working on low carbon development. In addition, actors beyond the UK government who are engaged in climate change mitigation and green economy globally.
2. The EMU Supplier will be expected to assess the wider landscape of stakeholders working on low carbon development in Indonesia, and engage as needed with those stakeholders where doing so will enhance the delivery of the contract. These may include other donors and development partners who are supporting or delivering related programmes (eg: UNDP, GIZ, WRI); other programme teams in British Embassy Jakarta and/or wider HMG (eg: Mentari, UK PACT, Climate Compatible Growth); other NGOs/CSOs, private sector and commercial actors involved in delivery, financing governance and/or advocacy relating to low-carbon development in Indonesia.
## Scope and outputs of the contract
In order to achieve the objectives of this contract the EMU supplier will deliver a set of specific outputs as outlined below. The Supplier bid should set out the proposed approaches and methodologies that will be used to meet the requirements as outlined below. The Supplier should set out the deliverables to be produced under the contract, with a justification for the timing and sequencing. A work plan should be provided. Deliverables should include those described below at a minimum.
The EMU Supplier will need to work closely with the LCDI2 Supplier in the delivery of the services: the distinction and complementarity between their roles in relation to MEL is explained below.
A summary of key deliverables is provided in Annex A.
MEL approach, framework and systems
Support to MEL system: the EMU Supplier will undertake a light touch assessment of LCDI 2 Supplier’s overall system and approach to MEL5. The purpose is to ensure that MEL systems are effectively aligned with, and thus can support, the overall objectives of the LCDI 2 programme. This assessment should also consider MEL aspects of the programme’s risk management approach, if applicable. This assessment will primarily involve desk-based review of documentation produced by the LCDI2 Supplier, eg: theories of change (see below), MEL plans. Based on this assessment, the EMU Supplier will issue recommendations for improvement, and work with the LCDI2 Supplier to integrate the implementation of those recommendations into the LCDI 2 work plan.
The LCDI2 Supplier will be expected to refine the Theory of Change provided in the business case (see Annex C) during their inception phase, and will have primary responsibility for TOC product(s) through the programme lifetime. The EMU Supplier will provide quality assurance in the development and periodic review of the TOC, and will provide recommendations to the LCDI2 Supplier and the FCDO. The LCDI2 Supplier will be expected to respond to those recommendations, either implementing them or providing justification acceptable to BEJ in cases where they do not. This will be the case for all cases in which the EMU Supplier undertakes a quality assurance role of work undertaken by the LCDI2 Supplier (including 14b and 14c below).
Monitoring
1. Support to Monitoring Framework: the development of a monitoring framework will be the responsibility of the LCDI2 Supplier6. The EMU supplier will provide expert advice and quality assurance in relation to the monitoring framework, prior to its finalisation and at appropriate review points throughout the programme framework (to be agreed with the LCDI2 Supplier and BEJ). The purpose of the EMU Supplier’s involvement is to ensure the monitoring framework provides a clear and robust way of tracking the LCDI 2 programme’s progress toward its intended outcomes and impacts.
2. Support to ICF KPIs: As LCDI 2 is funded through UK ICF, it is necessary to identify and include relevant ICF KPIs within the monitoring framework. The LCDI 2 Supplier is responsible for doing this, and the EMU will provide expert advice and quality assurance in relation to KPI selection, methodology for data collection, incorporation into the monitoring framework, and robustness of the data collected. Where necessary the EMU Supplier will perform further investigations to ensure that data presented by projects is accurate and robust.
Evaluation
The EMU Supplier will undertake independent evaluation of the LCDI 2 programme.
The specific objectives of evaluation 7 include: assess the programme’s contribution to intended outcomes and impact, and prospects for sustainability of effects immediately beyond the programme’s exit and in the long-term; identify whether the programme has contributed to any unintended consequences or effects (positive or negative); generate evidence and learning to inform programme design and implementation to maximise operational effectiveness.
The Supplier will meet these objectives through the delivery of two evaluation components:
1. Process evaluation, whose purpose primarily to analyse whether an intervention is being implemented as intended; whether the design is working; and what is working more or less and why.
2. Impact evaluation and/or impact assessment8, to investigate what changes have occurred as a result of the intervention, the scale of those changes, and an assessment of the extent to which they can be attributed to the intervention.
The LCDI2 programme, and wider FCDO, will use evaluations for purposes of learning and accountability. Learning includes managing risk and uncertainty of the intervention and its implementation; improving the programme by providing evidence to make better decisions; gaining a general understanding of what works, for whom and when, and generate examples for future policymaking; and developing evidence to inform future interventions. Accountability includes generating evidence of effectiveness of the programme, for Reviews and in response to scrutiny and challenge from public accountability bodies.
The Supplier will be expected to consider evaluation use and impact in their evaluation design process
– this should include an assessment of audience, through stakeholder mapping, and timing and dissemination of outputs.
Approach to evaluations should recognise beneficiaries as key stakeholders unless there is a clear rationale for omitting this. Supplier bids should show a clear attempt to ‘close the feedback loop’ through a specific consideration of appropriate methods to engaging beneficiaries in one-way or two- way feedback interactions. This should be evident throughout the evaluation cycle, including in the evaluation design, evidence gathering, validation and analysis, and dissemination phases. Justified exemptions from this include where programme activities do not interact directly with beneficiaries or cases where direct engagement with beneficiaries might cause a disproportionate burden to fall upon them.
Learning
1. Learning and knowledge dissemination strategy : the EMU Supplier will be expected to develop an approach for learning and knowledge dissemination throughout the lifetime of LCDI 2. This will include synthesising of evidence generated from monitoring and evaluation activities; for synthesis of monitoring outcomes, in particular, the EMU Supplier will need to work closely with the LCDI2 Supplier to ensure sufficient and timely access to data. The strategy should comprise, at minimum, objectives, approach, audience, process, outputs, targets and indicators.
2. Learning materials: the EMU Supplier will produce key learning material from the evaluation activities for example papers, reports, journals, op-eds, etc and disseminate to wider stakeholders. At least some of these knowledge/research products should relate to the evaluation questions.
1. The bidder should show consideration to gender and disability in the approach they propose, noting specifically that the programme’s results framework should report on gender and comply with the UK’s International Development (Gender Equality) Act 2014 and the Disability Discrimination Act 2005.
2. Bidders should include an assessment of relevant risks, challenges and mitigating factors in their proposal. See Annex B for an initial assessment of risks relating to the delivery of this contract.
## Contract phasing
1. The Inception Phase will last for no more than 3 months beginning from the signing of the contract between FCDO and the successful bidder. Activities will include:
  1. Preparation of an inception report
  2. Integration and/or alignment between relevant elements of EMU and LCDI Phase 2 approach, including: work plans, stakeholder mapping, communications and knowledge management, and governance.
  3. Identification of programme monitoring data required for evaluation purposes, and agreement upon responsibilities for primary data collection;
  4. Review of LCDI Phase 2 Theory of Change to ensure effectiveness and appropriateness for evaluation purposes;
  5. Recommendations regarding the overall data collection system including suggested revisions to project level monitoring systems and any primary data collection needs;
2. Under the Implementation Phase the supplier will operationalise the plans, approaches, and strategies agreed with FCDO in the Inception phase to deliver the MEL contract’s objectives, as per the scope of work outlined above. The Implementation phase will begin immediately after the end of the Inception phase and will last until the end of LCDI programme.
### Inception and progress reports
The Supplier will deliver an Inception Report at the end of the inception phase. This report will detail the approaches, plans, methodologies, and strategies proposed to deliver the objectives of the contract (expanding on the information provided in the bid).
FCDO will review the Inception Report, and grant final approval. Before the report is finalised and approved, the supplier must address all feedback as provided by FCDO. The report will be treated as a milestone under this contract with a payment linked to its satisfactory completion.
1. The inception report should provide further detail on the outputs to be delivered, in line with the scope and outputs section above (point 14). This should include the MEL system review, the Monitoring Framework review (including selection of ICF indicators, and delivery of learning materials. The Learning and Knowledge Dissemination Strategy will be produced by the close of the inception phase.
2. The inception report should contain a comprehensive description of evaluation design, and detail on the specific outputs envisaged and their timing (eg: draft and final evaluation reports). Evaluation design should comprise:
- Evaluation approach, methodology and evaluation questions,
- A list of evaluation questions. Each question should be accompanied by: explanatory comments, judgement criteria, quantitative and qualitative indicators, methodological approach to data collection and analysis. The set of questions should be able to answer relevance, efficiency, effectiveness, sustainability, and impact of the LCDI 2 programme.
- A review of the main risks and challenges for the evaluation and how these will be managed,
- A proposal on the collection of primary data, if appropriate, including details of the division of responsibilities for data collection between LCDI 2 Supplier and the EMU,
- Discussion of how to ensure that the design and application of methods will be ethically sound and which relevant ethical standards will be applied,
- Assessment of the probable quality and credibility of the identified datasets and sources and implications for primary data collection and the evaluation,
- A detailed evaluation workplan, including field missions and costings.
- Detailed approach to quality assurance
The evaluation approach, and selection of methodology, must take into account the following considerations. Detailed Information on FCDO’s general approach to evaluations can be found in HMG’s Magenta book.
- The overall design must be methodologically rigorous and credible.
- The approach must demonstrate relevance to the context of low-carbon development in Indonesia, including political and institutional dynamics, interlinkage of social, economic and environment themes, and sectoral scope.
- The approach must demonstrate relevance to the objectives and types of interventions under LCDI 2, including capacity-building, policy influencing, science-policy interface, fostering and scaling innovation, multi-stakeholder convening and partnerships, and institutional change.
- Conditions for replication and scale-up. The evaluation design should allow generalisation from the programme level and should identify key contextual factors expected to affect the effectiveness, sustainability and external validity.
- Assessment of Value for Money
Each year, in advance of LCDI 2’s Annual Review, the EMU Supplier will produce a comprehensive progress report that summarises progress toward programme outcomes, using indicators as per the monitoring framework. The report will contribute to FCDO’s AR process, which considers the extent to which the programme is delivering against the outputs of the outcomes of the programme’s logical framework. The EMU Supplier will rely on the monitoring data supplied by the LCDI 2 Supplier.
## Governance Arrangements and Quality Assurance
1. The EMU will report to the LCDI Senior Responsible Owner (SRO). On occasion, the Supplier may be requested to participate in LCDI 2 Steering Committee and/or other elements of the governance structure, for example, to present key findings. The exact nature of LCDI2 programme governance is to be determined during the inception phase of the LCDI 2 Supplier, likewise its make-up, but it will include representatives from BEJ and Government of Indonesia.
2. BEJ will agree a work plan with the EMU Supplier during the inception phase, which will be revisited regularly and adjusted when necessary. The SRO, with input from an FCDO MEL Advisor, will sign off on the design, methodological approach and tools proposed for achieving the scope of the contract during the inception phase. It is expected that the Supplier will independently manage the implementation plan but consult the SRO before decisions are taken or changes are made. Regular progress meetings will be held, likely monthly.
3. The EMU Supplier and the LCDI2 2 Supplier are both separately accountable to FCDO, and are not accountable to one another. However, they will need to work closely together to share information, adapt approaches and ensure economy and efficiency. Bidders should explain how they propose to build a good working relationship with the LCDI 2 Phase 2 Supplier, ensuring clear delineation of responsibility and accountability.

Key deliverables under this contract (including inception report, interim and final evaluation reports) will need to be reviewed and signed off by FCDO’s Evaluation Quality Assurance Service. Bidders should provide detail on their internal quality assurance processes relevant to the services being delivered.
## Timing and Budget
1. It is envisaged that the start of this contract will be 1 December 2023. The budget for this work will be up to £1.4 million for four years inclusive of any local government taxes but exclusive of VAT. The contract will include an option to extend by up to an additional 24 months in duration and up to £600,000 in value.
2. The contract will contain break clauses that can be exercised at the conclusion of the inception phase and at the end of Year 2. These break clauses can be utilised in the event that FCDO intends to appoint an alternative MEL partner for the implementation phase of LCDI2.
3. FCDO reserve the right to scale down or discontinue this programme at any point in line with the Terms and Conditions. Scaling Down is at FCDO’s discretion and may occur for a number of reasons including but not limited to a change in the security and/or political circumstances of the country, supplier performance or shortage of funds.
4. Bidders should propose a budget for this contract which clearly corresponds to the approach and deliverables set out. Bidders should also propose a Payment by Results schedule, and should demonstrate how they will ensure Value for Money. All proposals should be aligned with FCDO cost eligibility for commercial contracts.
## Payment and Key Performance Indicators (KPIs)
1. During the inception phase, expenses will be reimbursed on actual expenditure and fees will be paid on the successful delivery of the inception phase deliverables—the inception report. The inception report will be treated as a milestone and payment will be made on its satisfactory completion.
2. Under the Implementation phase, payments will be scheduled on a quarterly basis, in line with the UK fiscal year (April to March). Fees will be paid on a hybrid basis, with 80% of fees linked to deliverables/sub-outputs included in the bid, and 20% linked to KPIs to be paid on their achievement. Where payments against deliverables are tied to KPIs, note that payment will be subject to FCDO’s approval of KPI achievement.
3. As mentioned above, FCDO will follow a hybrid approach for making payments against the deliverables agreed under the inception phase of the contract. As such, deliverables will be evaluated against the following KPIs.
  1. Timeliness: FCDO will use Delivering on Time as a key criterion for performance evaluation against the deliverables.
  2. Quality (1-6): FCDO will assess the quality of deliverables using FCDO standards and the extent to which a deliverable achieves the purpose it is meant to serve. For major evaluation deliverables, FCDO will use our Independent Quality Assurance processes to provide further validation of findings. We expect to rate deliverables based on their relevance, accuracy, clarity and coherence. We expect to use a 1-6 scale to rate the deliverables on their quality. Payments will be made once the BEJ programme team scores a deliverable 5 or above. If there is a dispute over the quality of a deliverable (e.g., a report), then feedback will be provided, and the supplier allowed an opportunity to improve the deliverable to the required standard. FCDO will make 100% payment for final version of a deliverable that receives score 6 on the 1-6 scale. FCDO will reduce the payment by 20% for every one-point reduction in score.
  3. Lessons Learned, captured, and shared (1-6): For reports, evaluations products, research products—if meant to capture learning— FCDO will evaluate them also on the basis of how well the learning is captured and shared.
  4. Financial management: regular and accurate forecasts within 5% maximum variance threshold and invoices (quarterly), linked to progress reporting, are submitted on time.
## Skill and experience required
FCDO encourages bids from teams/consortia with a proven record of delivering MEL for multi- component programmes of a comparable value, with a strong emphasis on policy and institutional change.
The EMU Supplier should have a demonstrated understanding of a range of evaluation designs and research methods and be able to identify the strengths and limitations of different designs.
Essential requirements:
- Technical expertise and experience of carrying out MEL in relation to (a) climate change mitigation (b) policy and policy influence
- Track record of designing and implementing mixed methods evaluations testing causal pathways (i.e., using theory-based approaches) and undertaking contribution analysis.
- Physical presence in Jakarta to enable close working with BEJ, LCDI 2 Supplier and stakeholders
- Relevant experience and track record in the South-East Asia region and a demonstrated understanding of relevant national and regional context.
- Ability to communicate complex studies and findings in an accessible way for non- technical readers, including presentation of data in visually appealing ways, highly structured and rigorous summaries of findings and robust and accessible syntheses of key lessons.
The composition of the team should include a balance of international and national consultants, and take into account other diversity considerations (e.g. age, gender, disability).
## Other requirements
### Reporting and Monitoring
The EMU Supplier is required to submit formal reporting against an agreed work plan, and attend periodic meetings to discuss progress and future work plans with BEJ.
### Data responsibilities
1. The General Data Protection Regulation (GDPR) is a legislation that came into force on 25th May 2018. GDPR builds on data protection legislation, with a focus on governing the processing of personal data. Personal data is information relating to an identified, or identifiable living person. Further information on personal data and general responsibilities under GDPR legislation is available at The Data Protection Act. Under GDPR, the contract must be clear on the roles and responsibilities relating to the Controller and the Processor.
2. The EMU Supplier should consider the use of digital elements to maximise value for money while ensuring the programme remains inclusive and fully accessible. Any proposed digital elements will require approval in line with FCDO’s Programme Operating Framework (PrOF) Guides and must follow the UK Government’s standards. Full guidance on Digital spend can be found Here.
All digital content produced by the Supplier is subject to UK government digital principles as set out by the Government Digital Service (GDS). All digital developments should:
1. put the needs of users first
2. learn from and improve these services over time
3. be freely available for other DFID programmes to use
1. The successful Supplier will be responsible for ensuring full adherence with the guidance on when and how to use UKaid branding on all elements of the Programme. Full guidance on how and when to use the UKaid logo and branding can be found at https://www.gov.uk/government/publications/uk-aid- standards-for-using-the-logo.
2. It should be noted that all data and metadata are owned by FCDO, and bidders should ensure in the initial design, and methods that all data is rigorously documented. The EMU is required to provide all underlying data to FCDO, anonymised and in a suitable consumable format.
### Fraud and Corruption
1. FCDO has a zero-tolerance approach to corruption. The Supplier will have full responsibility for monitoring and mitigating the risk of fraud and corruption in the delivery of research. The EMU will need to comply with FCDO’s policies on fraud and anti-corruption and cooperate with any checks required from them for the duration of the evaluation e.g. annual audited statements, policies on management of funds, etc.
2. All suspected cases of fraud must be reported immediately to FCDO, and the Supplier will be expected to put in place a comprehensive risk management system which is appropriate to the context and consistent with FCDO’s own methodologies
### Modern Slavery
Do not commit any acts which contribute to exploitative practice (e.g. modern slavery/child labour). This includes failing to report concerns or suspicions regarding an act by another member of staff or staff from a partner or Supplier. FCDO has zero tolerance of staff or Suppliers contributing to exploitation including modern slavery or child labour. We consider this to constitute gross misconduct, and therefore grounds for termination of contract. Other action may also be taken, e.g. reporting criminality when applicable.
### Disability
For FCDO, disability inclusive development means that people with disabilities are systematically and consistently included in and benefit from international development. To this effect, and in compliance of the Disability Discrimination Act 2005, the supplier will outline how people with disabilities will be consulted and engaged in the delivery of this contact.
### Duty of Care
1. The Supplier is responsible for the safety and well-being of their Personnel and Third Parties affected by their activities under this contract, including appropriate security arrangements. They will also be responsible for the provision of suitable security arrangements for their domestic and business property.
2. FCDO will share available information with the Supplier on security status and developments in- country where appropriate. FCDO will provide the following: A copy of the FCDO visitor notes (and a further copy each time these are updated), which the Supplier may use to brief their Personnel on arrival.
3. The Supplier is responsible for ensuring appropriate safety and security briefings for all of their Personnel working under this contract and ensuring that their Personnel register and receive briefing as outlined above. Travel advice is also available on the FCDO website and the Supplier must ensure they (and their Personnel) are up to date with the latest position.
### General Data Protection Regulations
The EU General Data Protection Regulation (GDPR) and the Data Protection Act (2018) came into force in May 2018. The legislation means that everyone in the FCDO must comply with GDPR when handling personal data regardless of where they are located or the nationality of the people whose personal data it is (the data subjects). The Act implements a wide range of data protection reforms across the UK and introduces 4 distinct data protection regimes into UK Data Protection law. The schedule to be completed by Parties before processing personal data under the Contract is provided at Annex E. Please refer to the details of the GDPR relationship status and personal data (where applicable) for this project as detailed in Annex E and the standard clause 33 in section 2 of the contract.
### Safeguarding and Do not Harm
The supplier must demonstrate that it has proper procedures and policies in place to address and eliminate the risk of poor human rights practices within the delivery chain of the contract. These practices include exploitation, abuse and harassment, all forms of child abuse and inequality or discrimination on the basis of race, gender, age, religion, sexuality, culture, or disability. There must be protection from violence, exploitation, and abuse, direct or indirect. This includes sexual exploitation and abuse but should also be understood as all forms of physical or emotional violence or abuse and financial exploitation. The supplier must place an emphasis on the control of these and further unethical or illegal employment practices, such as modern slavery, forced labour, and other forms of exploitative and unethical treatment of workers.
### Other Requirements
1. Compliance with Environmental and Social Safeguards and the Ethical Guidance for Research, Evaluation and Monitoring Activities.
2. Consider whether external ethics approval is needed. For evaluations, monitoring and other activities, submission to Institutional Review Board (IRB)/Research Ethics Committee (REC) (and the relevant regulatory authority in the country) is not generally required, however FCDO expects the planning of data collection and analysis to reflect active consideration of ethical principles and standards.
3. FCDO will have unlimited access to the material produced by the supplier in accordance with our policy on open access to data as expressed in our general conditions of contract.
## List of key deliverables
List of key deliverables
Deliverable	Timeframe
Inception Report, including evaluation design / and work plan.	By end month 3
Learning and Knowledge Dissemination Strategy	By end month 3
Annual progress report	Annually, exact dates TBC
Review of MEL framework	TBC but anticipated by month 6
Reviewing of Monitoring Framework, including / ICF KPI selection	TBC but anticipated by month 6
Process evaluation	TBC but anticipated in Year 2
Impact evaluation and/or impact assessment	TBC but anticipated in Year 4
Learning materials	TBC periodic publication

# Annex 2: LCDI2 Theory of Change
Figure 11 OPML’s ToC overview in relation to the four WS

# Annex 3: Evaluation Methodology
## Evaluation Design
The Methodology for the Process Evaluation was set out in the Approach Paper, which was approved by FCDO in June 2025. This provided an updated methodology from the EMU Inception Report based on emerging needs and priorities for programme delivery. This Evaluation focuses on key components that were identified by FCDO and OPML, shown in Table 9. The Process Evaluation has developed learning outputs to help prepare for decision-making regarding future work.
Table 9 Key focus areas for the Process Evaluation
Priority Area for Process Evaluation	Details
EMU ToR	The Process Evaluation focused on evidence and learning to inform programme design and implementation to maximise operational effectiveness. It supported the 2025 Annual Learning and Knowledge Dissemination Cycle.
Contributing to the Annual Review	Data collection for the Process Evaluation coincided with FCDO’s Annual Review finalisation. It was agreed that the Process Evaluation would support the development of the Annual Review though dissemination of evidence where relevant. Robust and appropriate.
Supporting refinement of the logframe	A new version of the logframe was shared with the EMU in March 2025. The Process Evaluation design has integrated a review of the new logframe.
Emerging adaptive management priorities for the Process Evaluation	The Process Evaluation has been designed around the following adaptive management priorities: / The extent to which outputs from WS1 have had the intended effects, or unintended effects, and the causal factors. / Testing assumptions within the ToC in terms of current activity, particularly around: / Testing the causal pathways of the ToC, including the assumed influence of Bappenas on national and Provincial developments; / The assumed level of impact developing low carbon development (LCD) policy and planning documents has had and will have in facilitating LCD in Indonesia. / Understanding the effect of any elasticity in the programme’s scope and its responsiveness to key stakeholder requests. / Complementarity of LCDI2 with similar/related initiatives and partnerships. / Effectiveness of the GEDSI strategy and indicators. / Level of coherence of the management of interventions across Workstreams.
Emerging adaptive management priorities for Learning	The Process Evaluation was designed around the following priorities for adaptive learning: / Understanding the enablers for long term sustainability to be addressed at this stage, including learning about the sustainability of LCDI1. / Integrating learning from similar/related FCDO programmes into programme design. / Testing the assumptions in the ToC (for Evaluation) and to inform future activity, including for understanding better: / How to measure and plan for the challenges and successes of relationship building and generating long-term commitment to LCD across different sectors; / How the programme needs to adapt to conditions affecting Provincial developments, including the political environment and the rationale for selection of pilot projects; / The potential impact of wider GoI policies on the intended causal pathways. / How to develop a robust resourcing model for new activities (WS4)? / How to communicate/story-tell around the successes of the programme so far?

## Evaluation Methods
The EMU has used a range of evaluation methods for the Process Evaluation which are described below. The methodologies used broadly align to the approach set out in the Approach Paper. As highlighted in the Approach Paper, the EMU refined the methods used in the workplanning and literature review stage of the Process Evaluation and based on FCDO and OPML feedback. No major deviations from the Approach Paper are seen, but in some cases the methods were further developed to be greater aligned to the delivery context.
### Contribution Tracing
The EMU has trialled a Contribution Tracing (CT) approach in the Process Evaluation to assess outcomes observed and the contribution of LCDI2 towards achievement of those outcomes. As delivery of LCDI2 is still at an early stage, the EMU expected the outcomes to have not fully materialised and that it was not possible to fully quantity the contribution or assess alternative contribution factors at this stage. Therefore the EMU has applied a light-tough approach to CT and plans to repeat this methodology to further build the picture of contribution in the Impact Evaluation.
CT is a theory-based approach which seeks to determine whether expected outcomes have materialised, and, if so, whether there is a causal inference between the intervention and the outcome. This methodology was useful for assessing the contribution of the LCDI2 outcomes where evidence is expected to be highly subjective. The EMU has used this methodology in support of all the ELQs, but particularly for understanding impact and sustainability. The EMU has followed a six-step process shown in Figure 12.
Figure 12 Approach to CT

The EMU made a contribution claim at the programme level. The revised LCDI2 ToC offers four outcome statements and an impact statement. At the impact level, the focus is solely on reduced emissions reductions through lower emission intensity. It is unlikely that clear evidence of contribution against this impact will be identified during the programme’s lifetime and so our contribution claim was made against the outcome statements, considering the common threads tying them together across the workstreams. As such, the overall contribution claim for LCDI2 can be stated as “By LCDI2 providing technical assistance, capacity development, and political facilitation to national and provincial institutions in Indonesia, the Government of Indonesia is able to mainstream LCD into national and provincial planning, policy and budgets at higher levels of ambition, leveraging long-term financial and political commitment for LCD in Indonesia.” The EMU has not made any conclusions for the contribution claim in the Process Evaluation because outcomes are only starting to emerge. Contribution tracing at this stage has focused on the contribution stories described below. The overall contribution claim will be further tested in the Impact Evaluation.

Development of contribution stories. The EMU developed six contribution stories as hypotheses of change to assess the contribution towards the overall contribution claim. The contribution stories were developed in collaboration with FCDO and OPML. The stories align to the initial results from OPML’s Change Harvesting exercise, which took place in Quarter two (July – September), and specific pathways of change from the ToC. The EMU designed the case studies (see below) to specifically align to the CT stories and generate evidence for the CT stories as well as the ELQs. The contribution stories tested in the Process Evaluation are shown in Table 10.
Table 10 Contribution stories
WS	Contribution Story (ToC Pathway)	Example Alternative hypotheses
1	Integration of LCD into national planning: By providing Bappenas with studies and roadmaps for integrating LCD in priority sectors, Bappenas is informed of the options for integrating LCD in priority sectors, enabling them to integrate LCD into national planning through its inclusion in the RPJPN 2025-2045.	LCDI2 programme support to other sectoral ministries, such as Ministry of Environment, Ministry of Forestry leads to the integration of LCD in the RPJPN 2025-2045. / Other LCDI2 programme activities, such as the provision of baseline data to Bappenas result in the inclusion of LCD in the RPJPN 2025-2045. / Other programmes provide technical assistance and research to Bappenas which results in the integration of LCD in RPJPN 2025-2045. / LCD is not integrated into priority sectors in the RPJPN 2025-2045. / Bappenas integrate LCD into the RPJPN 2025-2045 without support from the LCDI2 programme.
1	Improved monitoring and reporting of LCD: By providing technical support for emissions monitoring systems in terms of methodologies and integration, LCDI2 facilitates the establishment of AKSARA as the primary national emissions reporting database, resulting in improved monitoring and reporting for national planning and international commitments.	Bappenas does not require inputs from LCDI2 to align databases in AKSARA for the RPJPN. / Bappenas does not improve monitoring and reporting of LCD in national plans. / Databases do not align to AKSARA. / Information provided by an alternative source helps to establish AKSARA as a primary national emissions reporting database. / Other ministries continue to use separate databases for monitoring and reporting.
1	Integration of LCD and alignment of policies and plans: By conducting analysis, modelling exercises and briefing GoI Ministries, GoI Ministries are able to deploy the requisite expertise to develop policies, plans and strategies that integrate LCD and align to the RPJPN.	Other programmes provide technical assistance and research to GoI Ministries which results in the integration of LCD into policies and plans. / LCD is not integrated into policies and plans. / GoI Ministries integrate LCD without support of the LCDI2 programme.
2	Increasing public finance for LCD pilots: By undertaking feasibility studies for LCD pilot projects, local government have the technical roadmap for developing LCD projects resulting in an allocation of public financing to projects proposed in the feasibility studies.	Low carbon solutions are cheaper than high carbon projects to implement. / There are other external influences on GoI to allocate more public financing to LCD pilot projects. / Public funding is increased to LCD pilot projects, but not those included in the feasibility studies. / No additional funding is allocated to LCD pilot projects. / Provincial governments use alternative sources of evidence to make decisions to increase public funding to LCD pilot projects. / Provincial governments already implement local carbon projects.
2	TA support to Bappeda and Pokja for including LCD in the RPR KBID: By delivering technical assistance, Bappeda & Pokja in four pilot provinces have the technical capacity and information to integrate LCD into the Low Carbon Development and Climate Resilient Programme Development Plan (RPR KBID) and the Provincial Medium-Term Development Plans (RPJMD).	LCD is not integrated into provincial planning documents in the four provinces. / Other LCDI2 programme activities in the four Provinces result in Bappeda and Pokja integrating LCD into provincial planning documents. / Other external influences result in Bappeda and Pokja integrating LCD into provincial planning. / Bappeda and Pokja use alternative evidence sources to integrate LCD into provincial planning.
3	Parliamentarian support for LCD action: By identifying key parliamentarians and convening strategic meetings with them, LCDI provides the necessary information to increase publicly expressed political support for the initiative and higher ambition for LCD action.	Parliamentarians already showed support for LCD before the engagement with LCDI programme team. / Another source of information results in Parliamentarians showing support for LCD. / Parliamentarians do not show support for LCD.

At the start of the CT process, the EMU established the types of evidence anticipated if the contribution stories were true, known as evidence signifiers. These were developed in collaboration with FCDO and OPML and are shown in Table 11. They represent the existing output indicators within the ToC and the understanding generated by the EMU of programme delivery. Each signifier has been tagged with the corresponding evidential test it represents.
Table 11 Contribution stories and evidence signifiers
Contribution Story	Evidence signifiers
Integration of LCD into national planning: / By providing Bappenas with studies and roadmaps for integrating LCD in priority sectors, Bappenas is informed of the options for integrating LCD in priority sectors, enabling them to integrate LCD into national planning through its inclusion in the RPJPN 2025-2045.		Wording in the RPJPN directly mirrors wording in the LCDI2 developed studies and roadmaps (DD). / The RPJMN target refers to the RPJPN target that was contributed to by LCDI (DD). / Bappenas publicly credit LCDI2 studies and roadmaps with informing the RPJPN and targets in the RPJMN (DD). / Other government stakeholders (in addition to Bappenas) state that the LCDI2 programme supported the development of RPJPN (SG). / Bappenas credit LCDI2 studies and roadmaps with informing the RPJPN in KIIs (SG). / Other ministries state the LCDI2 programme team outputs were used in the development of RPJPN (SG). / The LCDI2 team provide Bappenas with studies and roadmaps in priority sectors in a timely manner to allow integration into RPJPN (H). / Bappenas acknowledge receipt of the materials shared by LCDI2 programme team (H). / Bappenas engage with the material shared by LCDI2 programme team by attending meetings / sharing emails to discuss the content (H). / The RPJPN integrates LCD at higher ambition levels (H). / Bappenas request specific research/outputs/support of LCDI2 to inform RPJPN planning (H) / RENSTRA documentation includes enhanced targets linked to LCDI outputs (SG) / Internal ministerial communications reference LCDI outputs / data in relation to national planning (SG) / Updates/ adjustments made to budget codes in the APPD align to LCD priorities (H) / LCDI2 evidence is cited in policy memos (SG).
Improved monitoring and reporting of LCD: / By providing technical support for emissions monitoring systems in terms of methodologies and integration, LCDI2 facilitates the establishment of AKSARA as the primary national emissions reporting database, resulting in improved monitoring and reporting for national planning and international commitments.		Targets in LCD national plans reflect information providing from the LCDI2 programme team technical support (DD). / Bappenas publicly state the LCDI2 programme support helped them set LCD targets (DD). / Bappenas state the technical support, including capacity building, helped them set LCD targets in KIIs (SG). / Bappenas acknowledge strengthened monitoring and reporting in AKSARA and alignment of the interoperability of AKSARA and other LCD databases (e.g., SRN & Sign Smart) (H). / Other government stakeholders state that LCDI2 support has improved LCD monitoring and reporting (SG). / Other government stakeholders state that LCD targets are evidence based and have improved (H). / Other government stakeholders state that the interoperability of AKSARA and other databases has improved. (SG) / The LCDI2 programme team provide Bappenas with technical support (H). / Bappenas engage with the LCDI team on the technical methodologies through emails and attendance at meetings (H). / Bappenas state they read the information shared by the LCDI programme team on methodologies (H). / RENSTRA documents include LCD targets (H). / Policymakers state LCDI2 programme contribution in LCD targets in the media. / Non-government stakeholders (such as think tanks, NGOs, UNDP) state that LCD targets are evidence based and have improved (H).
Integration of LCD and alignment of policies and plans: / By conducting analysis, modelling exercises and briefing GoI Ministries, GoI Ministries are able to deploy the requisite expertise to develop policies, plans and strategies that integrate LCD and align to the RPJPN.		The LCDI2 programme team share information on analysis and modelling exercises with GoI Ministries, including Bappenas and the National Energy Council (H). / Bappenas propose a LCD target for inclusion in the National Energy Policy (H). / The LCDI2 programme team conduct briefing meetings on integrating LCD into policies and plans with relevant GoI Ministries (H). / Briefing meetings conducted by LCDI2 programme team are well attended by the relevant staff from GoI Ministries (H). / GoI Ministries credit LCDI support as helping them integrate LCD into policies and plans in KIIs (SG) / GoI Ministries make public statements regarding the support of LCDI2 in the media (DD). / GoI representatives state that LCDI2 has supported their knowledge/skills development in relation to LCD. / Wording in policies and plans directly mirrors information and analysis shared with GoI ministries in briefing sessions (DD) / GoI Ministries publicly credit LCDI for information LCD integration in policies and plans (DD). / Non-programme stakeholders (for example World Bank, UNDP) state that the LCDI programme supported the integration of LCD in policies and plans (SG). / RENSTRA documents include LCD targets aligned to RPJMN (H). / Sectoral Ministries acknowledge the use of LCDI2 training materials (SG).
Increasing public finance for LCD pilots: / By undertaking feasibility studies for LCD pilot projects, local government have the technical roadmap for developing LCD projects resulting in an allocation of public financing to projects proposed in the feasibility studies.		Provincial budgets and plans reference the LCDI2 feasibility studies or data contained within (DD). / Bappenas states the feasibility studies supported an increased allocation of public funding to LCD projects (SG). / Provincial government stakeholders acknowledge the feasibility studies provided information necessary to increase public funding to LCD pilot projects in KIIs (SG). / Other stakeholders state the pilot projects feasibility studies supported increased public funding to LCD projects in provincial planning documents (SG). / LCDI2 programme team conduct feasibility studies for LCD pilot projects and share them with local provincial government (H). / Provincial Governments acknowledge the receipt of feasibility studies (H). / Local Government representatives acknowledge/report they have sufficient expertise/information (H). / Increased public funding is allocated to LCD pilot projects in provincial plans (H). / Public funding for LCD projects in the provinces has increased following LCDI2 support (SG). / National and provincial budgets include increased public funding to pilot projects (H). / APBD includes budget for LCD pilot projects (H).
TA support to Bappeda and Pokja for including LCD in the RPR KBID: / By delivering technical assistance, Bappeda & Pokja in four pilot provinces have the technical capacity and information to integrate LCD into the Low Carbon Development and Climate Resilient Programme Development Plan (RPR KBID) and the Provincial Medium-Term Development Plans (RPJMD).		The RPJMD refers to the guidelines for the RPR-KBID (SG). / Bappeda & Pokja in the four provinces credit the LCDI programme team in supporting them to integrate LCD into RPR-KBID and RPJMD (SG). / Bappenas state the LCDI programme team support resulted in the integration of LCD into RPR-KBID and RPJMD (SG). / Other stakeholders in the four provinces state LCDI2 supported the integration of LCD into RPR KBID and RPJMD (SG). / LCD is integrated into RPRKBID and RPJMD in the four provinces (H). / Bappeda and Pokja in the four provinces engage with the LCDI2 programme team in workshops, focus groups and discussions (H) / The LCDI2 programme team deliver workshops, focus groups and discussions with the Bappeda and Pokja in the four provinces (H). / Bappeda and Pokja attend the focus groups and workshops delivered by the programme team in the four provinces (H). / Local regulations (PERDA) reference LCD (H). / Bappeda acknowledge use of LCDI2 tools such as GEI and AKSARA in their annual planning processes. / Non LCDI2 provinces replicate LCDI2 tools or planning approaches for the integration of LCD (SG).
Parliamentarian support for LCD action: / By identifying key parliamentarians and convening strategic meetings with them, LCDI provides the necessary information to increase publicly expressed political support for the initiative and higher ambition for LCD action.		Political mapping and analysis identifies parliamentarians (H). / The LCDI programme team engage with key parliamentarians (H). / Key parliamentarians engage with the LCDI programme team via email and attending meetings (H). / Key parliamentarians publicly support LCDI2 and wider LCD action (SG). / Key parliamentarians publicly note that the LCDI2 programme team engagement resulted in their support of LCDI2 and LCDI action (DD). / Other stakeholders note that key parliamentarians have increased support for LCDI (SG). / Parliamentarians’ positions change following LCDI engagement (H) / Other stakeholders note that key parliamentarians have increased support for LCD (SG).

The EMU gathered analysed and synthesised evidence against the contribution stories. The EMU gathered evidence from KIIs, wider literature and programme documentation to assess whether the contribution stories were accurate or not. The evidence signifiers were used to guide the process and as a tool to help assess the value of each piece of evidence. All evidence gathered was coded against the relevant contribution story used the evidential tests drawn from Process Tracing. The tests reflect the inherent strength or value of the data based on its content and the likelihood that the evidence will be identified if the story is correct or if it could still be identified if the story is incorrect. The test are shown in Table 12. The EMU applied the tests by answering a yes or no question shown in the table and scored each piece of evidence based on the positive answers to the questions. An initial question was asked of ‘does the evidence say if the story is true or false?’ to indicate whether the evidence was in support for or against each story being true. All evidence was coded in an Excel matrix. The matrix was analysed with respect to the tests, with hoop test evidence being considered stronger than straw in the wind, and smoking gun evidence considered stronger than hoop test. Throughout the analysis and coding phase, the EMU also recorded any alternative stories emerging from the evidence. Alternative stories are other pathways that may be contributing to the change seen.
Table 12 A description of the evidential tests used in the CT approach
Test	Definition	Question
Straw in the Wind	Relevant to the contribution story but insufficient to decisively prove or disprove a hypothesis; could be observed whether the story is true or not.	Is the data/evidence relevant to the contribution story?
Hoop	Evidence proves a necessary condition for the hypothesis to be confirmed, but is insufficient in itself to confirm the hypothesis; high likelihood to be observed even if the story isn’t true.	Does the data/evidence prove/disprove that one or more necessary part of the story is true?
Smoking Gun	Highly persuasive evidence which can confirm hypothesis but which does not eliminate other rival hypotheses; unlikely to be observed if the story isn’t true.	Does the evidence prove / disprove the whole story?
Doubly Decisive	Confirms the hypothesis as correct and eliminates all other hypotheses; only observed if the story is definitely true.	Does the evidence disprove alternative stories?

A contribution court was held by the EMU on 16th October. This interactive workshop was attended by FCDO and OPML and was used as an opportunity to collaboratively test and validate the evidence and wording of three CT stories. The EMU presented three contribution stories and asked FCDO and OPML to rate how confident they were each story was true. The scoring system used is shown below.

Based on the presented evidence, which of the below scores do you feel is appropriate for this story?
1 = Practical certainty claim is not true
2 = Reasonable certainty claim is not true
3 = High confidence claim is not true
4 = Moderate confidence claim is not true
5 = More confident than not claim is not true
6 = More confident than not claim is true
7 = Moderate confidence claim is true
8 = High confidence claim is true
9 = Reasonable certainty claim is true
10 = Practical certainty claim is true
The EMU presented a snapshot of the evidence in relation to each story, including positive and negative evidence and alternative stories. This was to facilitate a discussion over the evidence and understand from FCDO and OPML whether they thought it was an accurate reflection of the story, whether any evidence was missing, suggestions for alternative stories and any reflections or feedback on the story wording. Participants were then asked to score how true they thought the story was based on the discussion.
Alternative stories were identified. Based on the evidence gathered and the feedback from the contribution court the EMU identified alternative stories. It was not possible at this stage to assess the relative contribution or impact of the alternative stories, only that they may also be contributing to the change.

Present an overall confidence rating for each story. The EMU assessed the feedback from the contribution court and the evidence coded to propose a level of confidence in each contribution story being true at this stage, noting that the evidence base is likely to be further developed and the confidence ratings likely to change in the Impact Evaluation. The CT analysis can be found in Annex 6.
### ToC Assessment
The EMU reviewed the latest version of OPML’s ToC (Annex 2) to understand the extent to which the LCDI2 programme design is relevant for the delivery context and how LCDI2 fits within the broader landscape of climate initiatives. The components of the ToC were qualitatively assessed using a matrix approach. Table 13 sets out the questions the EMU has used to review the ToC. This was developed based on NIRAS’s experience of other HMG evaluations. For each question the EMU has scored the response on a scale of one to five, where one is the question is not included / well considered, and five is where it is well addressed and considered.
Table 13 ToC review questions and scoring
Question	Score (1 – not included/ considered to 5 – well included/considered)	Actions Needed
Development process
Is the process and rationale for ToC development and any recent updates fully described in the ToC narrative?
Did the ToC have appropriate engagement for co-design?
Overall structure
Does the ToC contain elements which are obsolete or confusing?
Does the ToC require extensive knowledge of programme elements not reflected in the theory to correctly understand its structure?
Can the reader easily understand the logic and structure of the ToC?
Does the ToC appropriately consider the local context?
ToC components
Is the wording of the outcomes and intermediate outcomes explicit and clearly defined? Are they specific, measurable, relevant to the activities and achievable?
Is the timeframe for results (intermediate outcomes and outcomes) reasonable?
Does the ToC cover all LCDI activities under the workstreams?
Are there any gaps within the ToC that should be addressed to achieve the stated impact?
Are the causal pathways and process of change appropriately defined?
ToC Assumptions
Are the assumptions underpinning the change process clearly defined at each level of the change pathways?
Will the assumptions hold true over the lifetime of the project?
Are there any assumptions at risk that should be addressed?
Are there any assumptions missing?
ToC Narrative
Does the ToC contain appropriate use of key terms and concepts?
Is the narrative written using simple language and understandable?
Is there a narrative assessment of each workstream?
Do the ToC core pathways to change make sense/ are they plausible?
Does the narrative set out the anticipated timing of the outputs / outcomes
Does the ToC show synergies and linkages between outputs?
Does the ToC identify how the outcomes will be sustained beyond the life of the programme?

A RAG rating was used to assess the assumptions in the ToC and the extent to which they hold true. The matrix used is shown in Table 14. A green score signified the assumption holds true, amber signified the assumption needs a review and further consideration and a red score signified the assumption is not true.
Table 14 Assumptions included in the ToC March 2025 to be tested.
Assumption	RAG score	Comments
Group A: problem identification, technical intervention, stakeholder engagement and outputs
Entry points for a dialogue with government agencies can be effectively identified and utilised
LCDI consortium staff are perceived as credible interlocutors for government agencies
Ad hoc/on-demand flexible requests from Bappenas remain proportionate/appropriate to LCDI programme resources and outcome objectives.
Group B: output to intermediate outcome (IO):
Evidence for technical approaches is relevant; outputs are useful and demand to adopt outputs sufficiently remains strong
The process of securing Bappenas official authorisations (MoUs, letters of support etc) occurs in a timely and resource appropriate manner to prevent bottlenecks
Willingness and ability of key stakeholder for political engagement via legislative / parliament office as well with the private sector and non-government organisations.
Government budget availability remains stable overall (e.g., ministerial budget allocations to Bappenas and other key ministries).
Group C: IO to outcome:
Engagement methods remain relevant for identified stakeholders who may act as key levers of change
AKSARA users have sufficient incentives and resources to report targets and maintain accountability
1Interest can be stimulated amongst key government, private sector and civil society stakeholders to prioritise LCD.
The political economy space remains conducive to LCD integration/mainstreaming, including the financial and business environment (e.g., global and national economic environment).
Group D: cross-cutting:
State-based planning remains an essential requirement for Indonesia, to make the switch to a low carbon development pathways. Including that Bappenas LCD planning is a sufficient base to influence LCD integration across ministries to catalyse plans into actions and budgets.

### Social Network Analysis
The social network analysis (SNA) aimed to understand a community by mapping the relationships that connect them as a network and then trying to draw out key organisations and connections between them. The EMU used a network mapping tool called KUMU to map LCDI2 stakeholders and generate SNA metrics. The SNA was updated throughout the Process Evaluation to provide a visual representation of the network. Four metrics were used – Degree, Closeness, Betweenness and Eigenvector, which are described in Table 15. The SNA has been used to feed into the ELQ responses, for example how LCDI2 actors fit into the broader landscape of climate initiatives and understand OPML’s stakeholder engagement and the community in which LCDI2 is operating. Data used for the SNA included KIIs, case studies and programme documentation. The EMU will continue to update the SNA annually with FCDO and OPML to show how the role of actors changes over time.
Table 15 Social Network Analysis Metrics
Metric	Name	Definition	What the metric describes
Degree	Hubs	Degree is based simply on the number of connections held by each actor.	To assess whether the organisations are sufficiently well connected within their network and acting as network Hubs.
Closeness	Sensers and Spreaders	Closeness scores each actor based on their shortest path to all other actors in the network.	For finding actors best placed to influence the entire network most quickly (Spreaders) or have the best oversight of the network (Sensers). Low closeness actors are often on the fringes of the network and indicate actors which may need to be “brought to the table” or better supported to grow their network.
Between-ness	Brokers and Bottlenecks	Betweenness measures the number of times an actor lies on the shortest path between other actors.	For finding actors which are either information Brokers (i.e. facilitators) or Bottlenecks (i.e. actors which need to be engaged to reach the full network). A high betweenness score can indicate influence, whereas low betweenness scores in a network can indicate high volume of partnerships or cross working.
Eigenvector	Leader	Network Leaders are measured based on the number of links they have to other well-connected actors in the network.	Eigenvector is a good overall SNA score to assess which actors are likely to be the most influential players in a network. In general, elements with high eigenvector are the Leaders of the network, though they may not have the strongest local influence in global networks.

### Political Economy Analysis
The EMU conducted a political economy analysis (PEA) at the national and sub-national level in the provinces where LCDI2 operates to understand and interrogate the context in which LCDI2 is implemented. The EMU built on the PEA conducted during LCDI1[23] focusing on the time period from 2020-2025 to highlight key changes that have taken place since 2020, such as changes in the relationships between key actors. The EMU conducted a two stage process for the PEA, firstly by producing a preliminary PEA assessment based on literature and to guide and inform evidence collection from KIIs, and a more in-depth analysis based on all evidence gathered from the Process Evaluation. The preliminary PEA assessment was shared with FCDO and OPML in July 2025 for their feedback.
[23] Please see Strengthening Indonesia’s Low Carbon Development Institutions for Effective Implementation, Political Economy Analysis.
The EMU PEA addressed four main objectives:
1. Diagnose structural drivers and constraints
2. Map power relationships and stakeholder incentives
3. Analyse multi-level governance dynamics
4. Inform strategic recommendations for LCDI2
The EMU used a multi-level governance framework and political economy methodology.[24] A qualitative assessment was completed to understand who the key actors are and their level of influence over LCD in Indonesia. The EMU qualitatively assessed which stakeholders have the most power and the formal and informal relationships between stakeholders. The EMU has aimed to identify political, social and economic drivers that influence decision-making for LCD and how important these drivers are for different stakeholders. GEDSI has been integrated into these drivers. Particular consideration was given to minorities and marginalised groups to understand informal or hidden power structures alongside formal decision-making mechanisms. The EMU has summarised the most influential drivers for LCD at the national and sub-national level. A comparison of the national and sub-national drivers has been examined to highlight similarities and differences. The EMU has identified barriers and opportunities for LCD and which are the most important for LCDI2 delivery. Based on this analysis of the political context, the EMU has reviewed LCD polices to understand their framing and development, how they link to the broader development agenda and other development programmes in Indonesia compared to other GoI Priorities. As part of the analysis the EMU has considered how LCDI2 programme activities influence and interact with the current social, economic and political context for LCD in Indonesia.
[24] Hudson & Leftwich 2014; DFID 2018
### VfM Assessment
The EMU has assessed VfM to understand how effectively and efficiently the LCDI2 programme delivered results and identified recommendations or learning which may lead to improved delivery going forwards. The VfM Assessment has contributed to ELQ 4.
The EMU has reviewed the OPML managed VfM framework and used this as a starting point for analysis. The OPML framework uses the FCDO 5E approach, with indicators and metrics set at each level. It was agreed with FCDO that in the Process Evaluation the fifth E of cost-effectiveness (overall value from input to impact) would not be assessed and instead be a focus of the Impact Evaluation.
Based on the evidence available, the EMU assessment of VfM has focused on a qualitative approach. Only high-level cost data was shared with the EMU due to the confidential and sensitive nature of the cost data, which was a limiting factor in the quantitative analysis that could be conducted. Qualitative data was obtained through KIIs. VfM-related questions were integrated into KIIs and other primary evidence gathering activities. VfM themes explored in the KIIs and other primary evidence gathering activities were as follows: timeliness in delivery, cost controls and cost-conscious management, quality of procurement, fund utilisation, resource sharing, cost savings, roles and responsibilities in VfM, adaptive management, influencing and replication, leveraging of financing, counterpart/ stakeholder satisfaction, stakeholder perceptions of cost-effective delivery, inclusive approaches, lessons with regard to VfM in TA programmes for example, VfM challenges with regard to indirect delivery, time lag of programme results, visibility of results.
Integration into the case studies. In the Approach Paper it was suggested to design a case study with a specific focus on VfM. Upon discussion and agreement with FCDO and OPML, it was agreed that instead the selected case studies would all integrate an element of VfM to provide a comprehensive review of each case study, rather than conducting a VfM-specific case study. This represents a change to the Approach Paper, but was agreed to be appropriate given the design process for the case studies to align to Change Harvesting and the CT stories.
### GEDSI Assessment
The GEDSI assessment was anchored on relevant UK policies.[25],[26],[27],[28] These bought the focus of the assessment on how GEDSI is mainstreamed in LCDI2, particularly around the planning and design of activities and allocation of resources and other inputs to attain the programme’s objectives, and how learnings are used to improve programme implementation. Two EQs 6.1 and 6.2 and one LQ (LQ 6.1) were addressed.
[25] UK International Development (Gender Equality) Act 2014
[26] Women and Girls Strategy 2023-2030, Disability Discrimination Act (2005)
[27] Safeguarding Against Sexual Exploitation and Abuse and Sexual Harassment with in the Aid Sector (2020)
[28] Leaving No One Behind: Our Promise (2019).
To undertake the GEDSI assessment, the following methods were used:
1. Secondary data analysis. This included analysis of the GEDSI Strategy, GESDI Action Plan, programme reports, and other documents to investigate how well the GEDSI strategy is aligned with the LCDI2 objectives and resources. The GEDSI assessment examined how GEDSI is explicitly mainstreamed into national medium-and long-term carbon growth development plans as well as in actions to advocate for policy change(s) that is gender empowering or transformative as well as socially inclusive.
2. Semi-structured key informant interviews (KIIs) Open-ended questions were used to cross check findings from the secondary data analysis and provide explanatory evidence where possible. KIIs captured opportunities and challenges in implementing the GEDSI strategy in the provinces. Understanding these factors was crucial for effective GEDSI mainstreaming into the implementation processes. Moreover, the KIIs documented positive and negative emerging outcomes of change processes and these were used to inform the formulation of actionable recommendations and subsequent implementation of improvements.
3. Analysis of the TOC and Logframe – The GEDSI Assessment built on the ToC review and assessment by examining the extent to which change processes enable the achievement of the programme’s impact while also contributing to institutional and the desired level of GEDSI mainstreaming (aware, empowering or transformative). The EMU considered whether changes would directly target or consider GEDSI. This was analysed against evidence of what change is occurring, how and for who to understand whether the ToC is appropriately capturing the GEDSI impacts. Change is not always linear, so it was important to interrogate how lessons were being integrated to improve programme implementation. Related to the programme’s logframe and monitoring processes, the assessment examined how the programme was keeping track of the progress in implementing the GEDSI strategy. The EMU reviewed programme monitoring data for consideration of GEDSI.
4. Case studies – A GEDSI-focused case study was designed (see below). GEDSI was also integrated across all case studies were appropriate.
The EMU ensured that GEDSI data collection was integrated across all its evaluation activities and that a coordinated approach to data collection occurred.
## Evidence sources
The Process Evaluation methods described above allowed for multiple routes of enquiry and, as such required a broad evidence base. The ELQs served as the overarching framework for analysis and synthesis. To generate the necessary evidence for each method, the EMU has used both primary and secondary evidence, described below.
### Primary evidence
The primary source of evidence for the Process Evaluation has been key informant interviews (KIIs). The EMU undertook 99 semi-structured KIIs across July to September, online and in-person. KIIs were conducted across stakeholder groups (Table 16) and different categories (Table 17) to capture a range of stakeholder views. KIIs followed a do no harm principle. A list of interviewees was shared with FCDO and OPML to coordinate stakeholder engagement and reduce stakeholder burden, but all information regarding the content of the interviews was confidential and anonymous. Interviews were conducted in English and Indonesian. The sampling strategy used was purposive with an initial sampling framework developed based on the SNA. Primary evidence tools were developed using the expertise and knowledge within the EMU team. KII interview scripts were tested and adapted as needed throughout the KIIs, particularly considering stakeholder expertise. Due to the sampling approach, interviewees were not selected in alignment with rigorous disaggregation, and it is not possible to compare findings across all stakeholder groups.
As highlighted in Table 16 and Table 17, the actual number of KIIs deviated from the sampling expectations outlined in the Approach Paper. Overall, more KIIs were conducted than expected, but fewer KIIs in the private sector, academic institutions and wider market experts were conducted compared to the expectations in the Approach Paper. This is in part due to an overlap in the classification of stakeholders, for example individuals working for NGOs may also be considered wider market experts. This is also a reflection of the convenience sampling approach taken by the EMU and based on stakeholder availability.
Table 16 Summary of KIIs per stakeholder group
Stakeholder group	Definition	Estimated sample size from Approach paper	Actual number of KIIs completed
Primary	The core group of stakeholders most important for the LCDI2 evaluation. It includes all organisations that have been directly involved in the Process Evaluation.	14	35
Secondary	Stakeholders identified as having a high influence on the network and have been recipients of technical assistance in LCDI2 or organisations that OPML have engaged with.	29	43
Tertiary	Stakeholders identified as providing important context for the Process evaluation and allowing for triangulation of data points.	23	21
Total		66	99

Table 17 Summary of KIIs conducted per stakeholder category
Stakeholder category[29]	KII purpose	Target number from Approach Paper	Actual number of KIIs completed
Delivery Partner	To provide an overview of current implementation phases, including results achievement, challenges and programme adaptations	8	29
Funder	To provide an overview of current implementation phases, including results achievement, challenges and programme adaptations. Also to provide insight into sector activities, changes observed in Indonesia at a regional level for wider learning and understanding.	4	6
GoI	Provide both beneficiary perceptions/opinions and insight into national strategy and context, and validate or verify evaluation findings, recommendations and learning for future Indonesia interventions	8	10
Historic Delivery Partner	Understand the implementation challenges and programme learning, as well as outcomes achieved.	7	3
Provincial Authorities	Provide both beneficiary perceptions/opinions and insight into sub-national strategy and context.	14	28
NGOs and civil society	Provide insight into sector activities, ongoing advocacy and grassroots initiatives, and whether they align with LCDI2.	7	10
Comparable programmes	Benchmark LCDI2 performance and better understand synergies, collaborative action and/or duplication and overlap	3	5
Private Sector	Understand market drivers for low carbon development and influence of LCDI2 on private activities or strategies.	5	2
Academic Institutions	Provide understanding of ongoing research and GoI engagement among academicians in Indonesia.	5	3
Wider market experts	Provide deep, contextualised expertise and practical knowledge for case studies or other sector specific analyses.	5	3
Total		66	99
[29] Please note that some stakeholder categories have overlap between participants, participants have included been included in one category to prevent duplication.

Table 18 The percentage of male and female participants in the KIIs
Gender	Percentage of KII participants
Male	60%
Female	40%

Overall, 40% of the participants in the KIIs described their gender as female (Table 18).
Where feasible and possible, the EMU collected evidence through direct observation and engagement. This occurred through case study provincial visits (see below) and observation of policy dialogues. This evidence built an understanding of programme delivery by providing insights into the content, quality and effectiveness of technical assistance activities.
### Secondary evidence
The EMU completed a desk review of existing programme documentation and secondary literature to consolidate information regarding achievements and learning of the programme and identify evidence gaps for the primary evidence collection. Secondary evidence included programme documentation, historic LCDI1 documentation and wider literature such as media reporting, academic articles and government outputs. The EMU used online search engines to identify relevant materials. Team members fluent in both English and Indonesian reviewed the documents.
A document catalogue was established to track the review of materials and ensure that data was extracted for the relevant ELQs. The Evaluation Manager was responsible for ensuring all secondary documentation was reviewed and added to the catalogue. The literature review informed the design of topic guides for the KIIs and acted as an evidence source for the Process Evaluation. A key aim of the secondary literature review was to align to existing documentation and information collection, such as through other phases of LCDI or other comparable programmes and relevant to the context in Indonesia, to minimise duplication through the KIIs in this Evaluation.
### Case studies
The EMU has completed six case studies to generate robust contextualised evidence of change. Case studies were designed to generate evidence for the CT stories and inform understanding of programme impact in line with specific pathways of the TOC. The case studies were informed by OPML’s Change Harvesting results and designed in collaboration with FCDO and OPML. Case studies were selected to cover a range of selection criteria (Table 19). A set of research questions was developed for each case study, which linked to the OECD DAC criteria and the ELQs. Case studies followed the same methodological approach, with evidence collection via KIIs, document review and field visits where relevant. A case study report template was developed to ensure a consistent report structure.
Table 19 Case studies and selection criteria
Criteria	Improving the interoperability of AKSARA with other databases	Revision of the National Energy Policy	Solar PV Pilot in Samosir District	TA support to Provincial Government	Engagement of key parliamentarians	Integration of GEDSI into LCD in RPJMN
Province	National	National	North Sumatera	North Sumatera, NTB and Bengkulu	National	National, NTB
Government Partner	Bappenas, Ministry of Finance, MoE	MoEMR, MoF, Bappenas, MoT, MoI,	Bappenas, Ministry of Home Affairs (MoHA), Bappelitbangda North Sumatera Province, Samosir District Government, Village Government of Sibonor Ompuratus and Pakpahan	Bappeda and Pokja	NA	Bappenas, Bappeda,
WS	1	1	2	2	3	1, 2
Consortium members involved	OPML	LCDI energy specialist and modelling team	Econova, OPML	PTHI	Prakarsa and INFID	OPML
Sector	LCD	Energy	Energy	LCD	LCD	GEDSI
Intervention type	Technical capacity building	National policy support	Project investment support	Technical capacity building	Political facilitation	Technical capacity building

## Evidence coding
All evidence was coded against the ELQ framework and based on categories developed as key areas of interest during the document review. Evidence was qualitatively coded in a software called MAXQDA, which generated a matrix of the coded evidence in Excel. The matrix provided an evidence map for transparency and future review, which can be sanitised and provided to FCDO at the conclusion of the EMU assignment. The EMU has assessed the triangulation and saturation of the evidence used in the report. Throughout the report the EMU has provided a qualitative description of the strength of the evidence related to each of the four themes presented in the Findings in section 3, based on the quality and availability of data supporting the theme and associated findings and outlining the data sources, data triangulation, convergence and saturation of evidence used. The EMU has sought to use a diversity of data sources throughout the evaluation, and where information is provided by a single source or has limited triangulation it is clearly highlighted in the findings. It was not possible to provide a disaggregation of the evidence by stakeholder category or gender due to the purposive sampling method applied for KIIs. These triangulation protocols aimed to ensure the EMU analysis was accurate and follow the principle of credibility.
## Synthesis Approach
The EMU has used both descriptive and explanatory synthesis approaches in the evaluation.
Descriptive synthesis is a process of collating and aggregating evidence and describing it at a given level with limited evaluative judgement; the aim is to describe what the evidence is, not why it has been observed. It focused on verifiable and quantitative evidence and was used to report on the aggregation of reported results against the LCDI2 logframe and the VfM analysis. This type of evidence synthesis was used to explore questions of effectiveness and efficiency.
Explanatory synthesis, on the other hand, was used for those ELQs where a much greater use of evaluator interpretation and contextualisation was required, where reliance on qualitative data was higher and greater consideration of the contextual factors contributing to programme success was required. The primary tool for explanatory synthesis was the CT methodology, with evidence synthesised under one or more contribution stories to describe how and why results have been achieved. Explanatory synthesis was used to interpret evidence related to transformational change analysis, SNA, and GEDSI assessments, as well as to add narrative understanding to VfM and other quantitative activities regarding why specific results might have been observed where relevant. Where an ELQ is not directly aligned with a contribution story or one of the other methods detailed in this report, explanatory synthesis was used to draw together evidence as relevant from across other evaluation activities to provide an aggregated, qualitative response to the ELQ.
## Limitations
 Key limitations of the Process Evaluation are set out below.
Programme delivery stage
LCDI2 is a four-year programme seeking to influence policy development through the provision of TA. However, policy development, from conception to presidential approval, can take several years with some recent examples taking four to five years. Also, LCDI2 is in its second year of delivery, and, according to the information available to the EMU, LCDI2 activities have largely focused on WS1 and WS2 to date. As such, the EMU is not table to fully demonstrate achievement of certain outcomes across all WS, particularly 3 and 4 during this Process Evaluation or fully assess the contribution to them. The EMU has used this evaluation as an initial assessment for impact, with the expectation to more fully understanding contribution to impact in the Impact Evaluation.
Availability and comprehensiveness of evidence sources
The EMU has aimed to use a diversity of evidence sources and include a range of stakeholders as much as possible throughout the evaluation process. It is noted that one limitation to the sampling of KIIs is that it was challenging to obtain KIIs with other GoI ministries. GoI included represent the views of individuals which may be a small sample of individuals. The EMU mitigated this limitation as much as possible through maintaining close conversations with FCDO and OPML and providing stakeholders with a letter of introduction for engagement. Despite this it was not possible to fully engage all relevant GoI ministries in the evaluation.
As noted in the SNA methodology, there is more documented evidence available for programmes fully completed, for example LCDI1. This presents the risk of over-representing evidence and stakeholders from these programmes in the results. The EMU has worked to mitigate this by carefully triangulating evidence from multiple sources to reduce the risk of bias, and by involving a diverse range of stakeholders in KIIs to capture a range of perspectives. Having said that, requests for KIIs with FCDO staff working on related ongoing FCDO Programmes did not come to fruition. There is therefore a significant gap in the evaluation’s understanding of lessons from and for those Programmes and potential gains in efficiency for LCDI2 via enhanced coordination within FCDO.
The EMU also requested to directly observe a wide range of Programme activities throughout late 2024 and during 2025. Invitations were eventually limited to only two Policy Dialogue events and the Steering Committee in July 2025. This presents limitations on the analysis provided in the evaluation, particularly related to nuances regarding the quality of outputs, understanding the challenges for and success of activity implementation, and understanding the dynamics of stakeholder interactions.
Due to the sensitive and confidential nature of cost data, the EMU could not access specific cost breakdowns of activities of WS-level data from OPML. Overall cost data was shared. Therefore, the VfM assessment is based on information shared by OPML through their VfM assessment, information from alternative programme documents and qualitative data from KIIs. The quantitative analysis methods used in the EMU’s assessment were limited. For example, it was not possible to complete the following:
- Cost driver analysis/key cost categories analysis;
- Unit cost analysis (for any standardised costs);
- Budget execution/ variation analysis; and
- Cost efficiency analysis of delivery costs.

The VfM assessment has focused on a qualitative assessment.
Evidence collection windows and site visit limitations
Site visits took place in September 2025, which was a month later than originally planned. Site visits were challenging to coordinate with activities happening for the Annual Review, with a longer time period than expected to coordinate with stakeholders. This resulted in a condensed analysis and synthesis period for the EMU for this evaluation which should be acknowledged as a limitation. In addition, in some cases it was not possible to conduct a site visit. For example, for the case study focused on the solar panelled water pump it was not possible for the EMU to directly visit Samosir. OPML advised of the risk of managing stakeholder expectations with regards to the progress of the solar panelled water pump. The EMU has used alternative evidence sources such as wider KIIs and document review for the case study and any further evidence gaps will be considered as part of future learning products.
Bi-lingual evidence sources
Evidence from programme documentation and KIIs is in two languages, English and Indonesian, which has required specific support for coding, interpretation and translation. Evaluation experts fluent in Indonesian have supported the interpretation, but there is a risk of misinterpretation of information from non-Indonesian speakers.
## EMU management approach
### The EMU team structure
The EMU team were able to work freely without interference during the evaluation. The team consisted of a Team Leader, who was well-qualified to lead the Process Evaluation with over ten years of experience in monitoring and evaluation. The Team Leader was supported by a core team of expert Evaluators, bringing together a range of experience relevant to the Process Evaluation including GEDSI expertise, VfM expertise, stakeholder engagement and policy expertise. The EMU considered GEDSI in the design of the team structure; the team consists of a range of genders, both junior and senior team members, and includes a range of national and international experts. The structure of the team is set out in Table 20.
Table 20 EMU Process Evaluation team roles and responsibilities
Expert	Role
Team Leader (based in Indonesia)	Lead overall Evaluation design, work planning, and implementation. / Technical support to and quality assurance of inputs from team members.
Deputy Team Leader (based in Indonesia)	Support Evaluation leadership (as above) and provide Evaluation expertise (as below).
Evaluation Experts (based in Indonesia)	Researching and initial concluding in dedicated areas of the ELQs. / Inputs, QA, and peer review into overall work planning, research, and outputs across the ELQs. / Flexibility in carrying out KIIs and other primary evidence collection activities in English or Indonesian. / Support to dissemination activities, particularly around LKD outputs.
Data and Evidence Processing Expert (based in Indonesia)	Support on data and coding tasks through the evaluation, such as coding evidence for contribution tracing, translation of KIIs. / Support ongoing data management, including for ICF KPI reporting.
NIRAS UK Contract Director	Input into final design, workplans, and support management of Evaluation activities. / Secondary level of quality assurance on draft outputs. / Technical support where needed.
GEDSI Technical Expert	To lead on GEDSI analysis during the Process Evaluation. / To lead on the integration of GEDSI findings within learning outputs.
VfM Technical Expert	To lead on VfM during the Process Evaluation.
NIRAS UK Evaluation Manager	Input into final design, workplans, and support management of Evaluation activities. / Provide secondary level of quality assurance on draft outputs.
NIRAS Indonesia Contract Director (based in Indonesia)	Facilitation of client engagement in-country and oversight of evaluation activities. / Supporting quality through hands-on relationship management with stakeholders as needed
NIRAS Indonesia Project Manager (based in Indonesia)	Support organisation of Evaluation activities in Indonesia and stakeholder relationships. / Supporting quality through hands-on relationship management with stakeholders as needed.

### Governance and ways of working
FCDO and OPML were the primary users for the Process Evaluation. FCDO is the EMU client and the EMU operated as an agent of FCDO in undertaking independent evaluation activities. OPML and the LCDI2 delivery consortium was the primary focus for the Process Evaluation, requiring a collaborative working relationship. As such, engagement with FCDO and OPML was carefully integrated into the workplanning for the Process Evaluation. This has included written review of draft materials and face-to-face discussions of emerging conclusions and sense-checking and validation workshops. This has ensured outputs are fit-for-purpose.
The EMU agreed a workplan with FCDO as shown in Figure 13. The frequency of meetings between the EMU, FCDO and OPML has been in relation to the agreed workplan. A sense-making workshop was conducted with FCDO on 16th September and OPML on 13th October to provide opportunity to feed into the initial findings. The timeline for review was carefully coordinated with FCDO to align with the timeline for the creation of the Annual Review. A validation workshop was conducted on 20th October with FCDO and OPML to collaboratively design and discuss initial recommendations.
Figure 13 overview of EMU workplan for the Process Evaluation

Bappenas as the key GoI partner for LCDI2 holding a bilateral institutional relationship with FCDO was also a key user of the Process Evaluation’s results. The EMU’s approach to engaging Bappenas is included in part of the learning, use and influence plan (Annex 5).
In the Inception Phase, the EMU developed principles for collaboration with OPML that recognised the political dynamics and complexities of the programme. The following principles guided collaboration:
1. Collaborative mindset. Encourage active teamwork and a shared sense of purpose. Whilst remaining impartial, working together to problem solve and develop solutions to problems.
2. A culture of empathy, respect, and valuing different perspectives. Ensure active listening, culture sensitivity, and remain flexible and adaptive to others’ needs and preferences.
3. Clear communication and documentation. Engage in routine meetings with agreed agenda. Develop communication protocols and mutually agreed processes to manage potential disputes.
4. Clear lines of decision making. Ensure accountability and transparency.
Clear roles and responsibilities were agreed between OPML and the EMU to support effective collaboration and minimise conflict (Table 21).
Table 21 Roles and responsibilities for LCDI2
MEL components	EMU responsibilities	LCDI2 programme responsibilities
Overall MEL system, including ToC	Light touch assessment of overall MEL system and approach to MEL / Quality assurance and periodic review of ToC / Provide recommendations for improvement and support implementation of recommendations	Develop and implement system and approach to MEL / Refine the LCDI2 ToC in the business case and responsible for ToC products throughout the programme lifetime / Respond to recommendations made by EMU
Monitoring	Periodic review of monitoring framework, provide expert advice and quality assurance / Provide expert advice and quality assurance in relation to ICF KPI selection, methodology for data collection, incorporation into the monitoring framework, and robustness of the data collected / Provide expert advice and quality assurance of GEDSI and VfM indicator selection, data collection method, and incorporation into the monitoring framework / Perform further investigation to ensure accuracy and robustness of data if necessary	Develop monitoring framework and approach to data collection / Develop logframe and indicators, set targets on indicators in agreement with FCDO and Bappenas / Collect monitoring data and periodically report on logframe indicators / Identify and include relevant ICF KPIs in monitoring framework and periodically report on ICF KPIs / Respond to recommendations made by EMU
Evaluation	Design and deliver two evaluations, one Process Evaluation and one impact evaluation in close collaboration with LCDI2 programme team, FCDO, Bappenas and other stakeholders to ensure feedback loop / Disseminate evaluation findings and learnings and facilitate evaluation use	Provide feedback throughout the evaluation process / Provide EMU access to relevant data and support evidence gathering / Participate in evaluative learning and dissemination activities / Respond to recommendations made by EMU
Learning and communication	Produce learning materials from evaluations and disseminate to FCDO/BEJ, Bappenas and wider stakeholders / Identify learnings across LCDI2, produce learning materials and disseminate to FCDO/BEJ, Bappenas and wider stakeholders	Facilitate programmatic learning within the LCDI2 programme team / Communicate learnings emerged from LCDI2 programme implementation to FCDO/BEJ and GoI stakeholders
Annual review	Based on the draft Annual Review produced by the LCDI2 programme team, work with FCDO to provide quality assurance, support the development of recommendations, and finalise the Annual Review	Provide results data and report on logframe indicators, and produce a draft Annual Review to FCDO

### Data sharing procedures
The EMU was committed to compliance with the General Data Protection Regulation and Data Protection Act 2018 requirements. The EMU set up a secure SharePoint site for data sharing between FCDO, the LCDI programme team and the EMU. This file sharing platform follows HMG compliance requirements, including GDPR. The SharePoint folders had restricted access. All information stored on the SharePoint site was managed by NIRAS. Data was managed in accordance with NIRAS internal policies and procedures and all information was retained in accordance to schedules defined in contracts. All personal data will be deleted on completion of the contract in 2027.
Evidence collection approaches required informed consent be obtained before individuals provide data about themselves or other information, that our analysis was inclusive of all relevant stakeholders, and that personal harm and unnecessary burden on respondents was avoided. Personal data was kept in a clearly identifiable location and access to all information processed was restricted to only those who need it. To seek informed consent, we explained to the individual engaged the context of LCDI2 Process Evaluation, process of evidence and data collection, and how information they have provided will be used. Where appropriate, we provided an indicative list of questions or discussion points prior to engaging an individual in evidence collection process. All interviewees were made aware their names would be shared with OPML and FCDO as participants in the evaluation, but that all information shared as part of the interview was confidential.
The EMU signed a non-disclosure agreement with OPML to facilitate sharing of personal data in a secure way. The EMU agreed a process with OPML for sharing data, ensuring full confidentiality for any commercially sensitive or confidential data or information. A Word document data request was compiled and shared with OPML. The OPML uploaded relevant documents to the SharePoint, providing updates on progress and what was possible through the tracking Word Document. Where needed, the EMU requested FCDO support in sharing relevant information or providing contacts for KIIs.
### Risk management
Throughout the Process Evaluation the EMU maintained a risk register to manage potential risks and mitigate their impact. Any changes to risks were reported to FCDO on a regular basis. Risks were scored using a traffic light system where red represented a high risk, amber represented a medium risk and green represented a low risk. Most risks in the Process Evaluation relate to evidence quality, and a copy of the EMU risk register can be found in Table 22.
Table 22 Risk register
Risk	Level of risk	Mitigating actions
Overlap between the Process Evaluation’s needs and OPML’s programme implementation and MEL activities	Medium	The EMU closely engaged with OPML on work planning for the Process Evaluation. Early and continual exchange was needed on potential overlap in: / Activity related to MEL outside of the Process Evaluation (e.g. OPML’s collection/provision of evidence for the monitoring system and Change Harvesting workshops); / Timetable and nature of programme delivery events and activities. / Also, EMU: / Clearly communicated plans to interview stakeholders and the timelines for interview with OPML to reduce the burden on stakeholders. / Set strict time limits for the KIIs of one hour to reduce the time commitment.
Lack of availability of secondary evidence	Low	The EMU closely engaged with OPML and FCDO on the development of a document register mapped onto the ELQs and on the provision of documentation is needed. The EMU continued to work with OPML and FCDO to update this.
Lack of availability of primary evidence	Medium	Stakeholders identified in the sampling frame (see Annex B) had competing demands for their time. The EMU: / Developed, with input from FCDO and OPML, early general communication mechanisms to ensure all potential stakeholders were aware of the Process Evaluation in advance of receiving requests for interviews. / Identified and used informal channels, including those already established by FCDO and OPML to encourage participation. / Built in a buffer time to interview schedules to allow for delays in responses. / Engaged a higher number of individuals than needed with the expectation that not everyone will be available to participate in an interview. / Protocols on confidentiality, ethics and data protection were shared with all interviewees to encourage participation. These are fully described in this methodology section. / Set strict time limits for the KIIs of one hour to reduce the time commitment. / Aligned primary evidence collection activities with other events in negotiation with the owners of those events. / If KII sampling targets appear at risk of not being met by mid-August, alternative evidence collection sources were considered as appropriate to the sampling group concerned, including: / Written responses from key informants to the KII semi-structured questionnaire or parts of it. / Focus Group Discussions (FGDs), or similar, as opposed to multiple individual KIIs, particularly where groups of people from the same sampling group are available in the same location at the same time, or where sense-checking was considered to be useful around emerging conclusions. / Stakeholder surveys could be used where a business case can be made based on an assessment of potential quality of responses, response rates, and relevance to emerging evidence needs and gaps.
Subjectivity and bias in secondary evidence	Low	Written documentation risks being biased towards author/audience needs. Therefore: / Where possible the document register identified documents by a range of types of authors pertaining to the same ELQ. / Potential biases were identified by the EMU’s experts and consideration of them integrated into the semi-structured questionnaire for the KIIs. / EMU provided sense-checking and validation workshops for the Evaluation’s key users before finalising conclusions linked to both secondary and primary evidence.
Risk of AI	Low	Use of AI in the evaluation represents a risk of bias and inaccurate information, particularly around the use of unverified AI content. The EMU mitigated this risk through a multi-stage QA process highlighted in this Annex, triangulation processes and use of different data sources.

### Conflict of Interest
NIRAS were committed to early identification and ongoing monitoring of potential conflict of interest (CoI) risks. All EMU members were required to complete a Conflict-of-Interest disclosure form to declare any potential or perceived CoI. Any identified CoI risks were recorded in a CoI register. The Evaluation Manager was responsible for monitoring the implementation of mitigation actions under the guidance of the Contract Director and NIRAS Operations Lead.
No known CoIs were identified relevant to the Process Evaluation. It should be recognised that the Indonesian climate policy environment is a relatively small market, and the EMU team members are often known to stakeholders who are expected to act as key informants – where this was the case, any potential bias was mitigated by ensuring at least two team members participate in discussions.
### Approach to Quality Assurance
The EMU committed to a multi-layer quality assurance system, which addressed all dimensions of quality, including evaluation design, evidence, process, outputs, capacity, and timeliness. The quality assurance (QA) approach for the EMU contract is built on NIRAS’ ISO9001 Quality Management System (QMS) and the assessment of the measures that need to be in place to deliver high quality MEL services for LCDI2. The QA process for the Process Evaluation followed the structure outlined in Figure 14 below.
Following submission of outputs (Approach Paper, Learning products, draft Evaluation Reports), both FCDO and OPML were expected to review and provide feedback in the first instance, with Bappenas and other key programme partners provided an opportunity to provide feedback at a later stage. All feedback received was reviewed by the EMU and collated in a comments matrix. All comments have been responded to directly or integrated into this version of the evaluation report. This report has been submitted to EQUALS for review and relevant feedback incorporated.
Figure 14 EMU QA process

Output is submitted to FCDO for review and approval.
Final verification
Contract Director reviews output and sign off for submission.
Interdisciplinary verification
EMU QA panel review output against QA checklist. Internal assessment against EQuALS guidance if appropriate.
NIRAS verification
The author/preparer submits Output to Contract Director for review. After which, it is submitted to the EMU QA panel.
Preliminary draft review
Preliminary findings are shared with FCDO and LCDI2 programme team for feedback.
Concept review
EMU and FCDO agree on basic expectations and goals of the output. Draft outlines are shared with FCDO and LCDI2 programme team for review and comments.

## Ethics and safeguarding procedures
Adherence to ethical principles in the conduct of activities followed the comprehensive set of systems and processes NIRAS has built for this: the NIRAS Business Integrity Management System (BIMS) and Code of Conduct. The publicly available BIMS is implemented and communicated internally and externally and includes anti-bribery and corruption, whistleblowing and safeguarding information and training as a requirement for all contractors and staff. The BIMS complies with international recommendations on combatting bribery and corruption in business, including those from the OECD, FIDIC guidelines and Transparency International’s Assurance Framework. The latest FCDO guideline under the Common Approach to Protection from Sexual Exploitation, Abuse and Harassment is also being incorporated into the BIMS and will be followed by the EMU under guidance of the NIRAS Safeguarding Manager.
Across the Process Evaluation activities, the FCDO’s Ethical Guidance for Research, Evaluation and Monitoring Activities (2019) guided data collection and reporting to ensure that methods used adhere to the appropriate ethical principles and standards. The EMU’s overall evaluation methodology underwent GEDSI proofing. This entailed examining the appropriateness of qualitative and quantitate data collection methodologies, framing of questions, sample selection, and analyses. The EMU’s GEDSI Expert supported evidence collection tools development from the outset, and provided technical review of analytical outputs. This allowed cross-analysis and -learning with the other parts of the Process Evaluation, e.g., VfM, and specifically uncovering gender relations in the SNA.
The EMU followed the guidelines specified in HM Treasury’s Magenta Book: Central Government guidance on evaluation (2020) which contains ethical considerations in evaluations. For the LCDI2 Process Evaluation, this included actions towards (a) respondents- protecting confidentiality, doing no harm, minimising respondent burden and avoiding intrusion, and avoiding manipulation or deception; and (b) FCDO and OPML - reporting findings that may cause reputational risks, avoiding additional burden associated with data collection and sharing, and properly citing data sources.
The EMU sampling methodology ensured that social groups are well-represented and that interview techniques facilitated their participation.
In terms of stakeholder engagement, the EMU ensured all processes were inclusive, transparent and aligned with the Do No Harm principle. We engaged a wide range of stakeholders as data sources, participants or learning recipients and ensured all engagement was considerate of socio-economic characteristics including gender, age, disability, geographic location, socio-economic status and other demographic factors. There was no engagement with community members or other vulnerable groups. Due to the political nature of the intervention, the security of all stakeholders engaged were considered prior to engagement, and throughout the engagement period.
Data collectors were provided training on ethical data collection practices. They were also provided with a prepared introductory statement to obtain consent from the respondents. This included consent to taking photos as part of documentation.
NIRAS takes full ownership of its Duty of Care to its employees and sub-contractors. All team members when travelling in connection with the EMU assignment were covered by the NIRAS Corporate Travel Insurance and had access to the NIRAS Guardian app. Our internal security officer was available to provide guidance as required, aligned with the FCDO Foreign Travel Advice guidance.
### Use of digital tools
The Process Evaluation used a range of AI and digital tools as shown in Table 23 for the Approach Paper. The use of AI represents an update to the Approach Paper and helped to increase the efficiency and quality of quality of delivery and maximise value for money for FCDO.
Table 23 Digital tools used in the evaluation and their use of AI
Digital tool	Summary	AI used?
Microsoft SharePoint	SharePoint was used to securely store and share data for the Process Evaluation, in line with GDPR.	No
MAXQDA	Used for qualitative coding of KIIs	No - the AI function in MAXQDA was not used for this evaluation.
Copilot	Copilot was used as a tool to support translation and initial research. All outputs were checked for factual accuracy.	Yes
Microsoft Teams	Microsoft Teams was used for online KIIs and meetings. The AI function was used to support transcription of KIIs and creating summaries. All AI summaries were used in conjunction with notes from the evaluation teams.	Yes
Kumu	Kumu was used to create a map for the social network analysis.	No

The use of AI adhered to the FCDO Digital Strategy and the AI Playbook for UK Government. The following principles and measures were applied:
- Transparent about how we used AI. We specified exactly where and how we used AI. We sought approval from the stakeholders we were engaging with before using AI so that all stakeholders were comfortable with the way AI was used. AI was used for transcription, translation, and assisting with the drafting of text.
- AI was used to augment not replace the work of the EMU. In our experience, AI is best used as an assistant, providing inputs to the work of the evaluators who ultimately design and conduct the evaluation activities. We used AI on this project to improve efficiencies of tasks, for example through summarising meeting notes. We recognised the need for our team members to always have oversight of how AI was used and review any AI outputs that were produced.
- Maintain an awareness of evolving limitations and risks of AI and develop mitigation strategies. The limitations and risks of AI are continually evolving. We ensured that we correctly identified the potential risks and developed mitigation strategies as detailed in the risk register Table 22. The key ongoing risks included AI model biases that can entrench problematic views and the climate impact on the environment from an energy intensive AI model.
- Ensuring data security standards were maintained. Only AI tools that had enterprise-grade security standards were used to ensure that the data sent to the AI platforms was secure.

# Annex 4: Evaluation Matrix
Table 24 Process Evaluation Matrix to show the evidence sources and methods per EQ
ELQ	Sub-EQs	OECD-DAC	Potential evidence sources	Proposed methodologies
ELQ 1 To what extent is the LCDI2 programme design and ToC relevant for the delivery context and what adjustments could be beneficial?	EQ 1.1 How can the ToC or the delivery model be improved to help support LCDI2’s intended Outcomes? Including in relation to: / Assumptions and causal pathways being clear and relevant to current and future delivery contexts. / Identification of Intermediate Outcomes / known effects of outputs delivered in WS1. / Capturing linkages between workstreams. / EQ 1.2 To what extent are approaches to monitoring the ToC fit for purpose? What adaptations, if any, need to be made? / EQ 1.3 What alternative pathways for achieving intended impacts can be identified? Particularly in respect of supporting Contribution Tracing.	Primary DAC Criteria: Relevance. / Secondary DAC Criteria: Impact, Effectiveness, Coherence	Programme design documentation including business case, Inception Report, and all ToC development and adaptation documents. / Secondary literature review. / Data and documentation from comparator programmes. / KIIs with primary stakeholders including LCDI2 Delivery Partners, FCDO and Bappenas. / KIIs with secondary stakeholders including historic Delivery Partners such as WRI Indonesia, Government of Indonesia. / KIIs with tertiary stakeholders such as coherent and comparable programmes operating in Indonesia.	ToC Assessment / SNA / Political Economy Analysis / Contribution Tracing
ELQ 2 How does LCDI2 fit within the broader landscape of climate initiatives in Indonesia?	EQ 2.1 How coherent is LCDI2 with related initiatives and partnerships both within and outside of FCDO and Bappenas?[30] To what extent do synergies or overlaps exist? / EQ 2.2 Is LCDI2 building an effective network to influence the achievement of LCD objectives?	Primary DAC Criteria: Coherence. / Secondary DAC Criteria: Effectiveness, Impact, Sustainability.	KIIs with primary stakeholders including LCDI2 Delivery Partners, FCDO and Bappenas / KIIs with secondary stakeholders including historic Delivery Partners such as WRI Indonesia, GoI. / KIIs with tertiary stakeholders such as coherent and comparable programmes operating in Indonesia. / Programme documentation from LCDI1 and LCDI2. / Secondary literature review.	Political Economy Analysis / ToC Assessment / SNA
ELQ 3 How can the effectiveness of LCDI2 programme management mechanisms be optimised?	EQ 3.1 How can the effectiveness of LCDI2 programme Management mechanisms be optimised? With reference to operational arrangements, governance frameworks, and the working environment, considering: / the successes and challenges and what factors have influenced the achievement or non-achievement of results? / how well has the programme overcome or mitigated barriers and risks to its effectiveness?	Primary DAC Criteria: Effectiveness. / Secondary DAC Criteria: Efficiency.	Primary data including KIIs with all relevant stakeholder groups. / Programme documentation from LCDI1 and LCDI2, including reports, Annual Reviews, Inception Report and business cases. / Secondary data sources, including relevant literature such as media reporting, academic articles, government outputs. / Annual reviews from other relevant HMG programmes	Contribution Tracing / ToC Assessment / Political Economy Analysis / GEDSI Analysis / SNA / Case studies
ELQ 4 Is LCDI2 delivering value for money (VfM) against the 4Es framework?	EQ 4.1 Are programme resources being used Economically and Efficiently to deliver results? / EQ 4.2 What evidence is available that approaches to the programme are or will be Effective? / EQ 4.3 What evidence is available that approaches to the programme are or will be Equitable? / EQ 4.4 How well is the programme monitoring VfM and is there evidence of VfM evidence being used for resource allocation or other programmatic decision making?	Primary DAC Criteria: Efficiency.	Programme cost data from LCDI2 / Programme documentation, including VfM progress reports, logframe, ToC, etc. / KIIs with primary stakeholders such as OPML, LCDI2 Delivery Partners and FCDO / Cost data from comparator programmes including other HMG/ICF programmes	VfM Analysis / GEDSI Analysis / Case studies
ELQ 5 To what extent is the LCDI2 programme likely to contribute to sustainable change?	EQ 5.1 How effectively is the LCDI2 progressing towards the achievement of its intended outcomes and impacts? What are the key factors influencing this progress? / EQ 5.2 How well does the programme design reflect factors that will enhance its sustainability?	Primary DAC Criteria: Impact. / Secondary DAC Criteria: Effectiveness, Sustainability	Primary data including KIIs all relevant stakeholder groups. / Programme documentation from LCDI1 and LCDI2, including reports, Annual Reviews, Inception Report and business cases. / Secondary data sources, including relevant literature such as media reporting, academic articles, government outputs. / Annual reviews from other relevant HMG programmes	Contribution Tracing / ToC Assessment / Political Economy Analysis / GEDSI Analysis / SNA / Case studies
ELQ 6 Is the GEDSI strategy effectively designed and integrated into LCDI2?	EQ 6.1 How well does the GEDSI strategy align with LCDI2 objectives and resources? Including: / What improvements can be made to enhance its effectiveness? / What are the gaps in GEDSI mainstreaming and what actionable recommendations can be made for its improvement? / Are adequate resources and processes allocated to GEDSI mainstreaming? / EQ 6.2 How can the logframe and ToC be strengthened in relation to achieving the GEDSI strategy?	Primary DAC Criteria: Effectiveness. / Secondary DAC Criteria: Sustainability	Programme documentation, including GEDSI strategy, GEDSI Action Plan, logframe, ToC, programme Reports. / Secondary literature / KIIs with primary stakeholders such as OPML, LCDI2 Delivery Partners and FCDO. / KIIs with secondary and tertiary stakeholders, including historic Delivery Partners, GoI, provincial authorities, NGOs and civil society organisations, academic institutions and the private sector.	GEDSI Analysis / VfM Analysis / SNA / ToC Assessment / Case studies
[30] Including RPJPN and the Just Transition Roadmap – However, LQ2.1 should elaborate on the most important initiatives in scope.

# Annex 5: Learning use and influence Plan
## Primary audience
The core objective for this Process Evaluation is to deliver an Evaluation Report to FCDO and OPML to support adaptive management. The EMU has organised and attended two workshops with FCDO and OPML around MEL and governance on 9th December 2025 and LCDI2 strategy and workplan on 10th December 2025 where recommendations from the evaluation were discussed and priorities and next steps for adaptive management agreed.
## Secondary audiences
A key secondary user for this evaluation will be Bappenas. The EMU will brief Bappenas on the findings, lessons learned and recommendations from this evaluation through a presentation at the Steering Committee meeting in January 2026.
## Tertiary audiences
At the time of drafting the evaluation report, the EMU are in discussion with FCDO and Delivery Partners in terms of identifying appropriate tertiary audiences for tailored dissemination outputs, and their means and timing.
## Learning products and dissemination method
In addition to the learning, knowledge and dissemination products proposed in section 6.2, the EMU has proposed the following dissemination and learning for products of the Evaluation Report (Table 25).
Table 25 Learning products for dissemination of the evaluation report
Learning product from the evaluation	Target audience	Dissemination method
Draft findings to support FCDO’s annual review	FCDO	Written report, discussion sessions
Draft evaluation report	FCDO and LCDI2 delivery partner	Written report, workshops
Final evaluation report	Primary, secondary and tertiary audiences	Written report, publicly available via DevTracker
Presentation of results from the evaluation / Presentation of results and learning from the evaluation	Bappenas / Other FCDO Programmes in Indonesia, cross HMG and cross BEJ	In-person meeting / Seminars and virtual webinars
Four policy learning briefs: / Sustainability / Adaptive management / GEDSI / Leveraging relationships	Primary, secondary and tertiary audiences, including GoI ministries, wider development partners and delivery partners implementing projects in Indonesia	Written briefs
Learning presentation	Cross HMG / cross BEJ	In-person meeting and virtual webinar

## Lessons learned from stakeholder engagement
The EMU engaged a wide variety of stakeholders during the evaluation and notes the following lessons learned from this engagement process. The EMU will apply this learning to future stakeholder engagement for the evaluation.
- Bi-lingual dissemination works well to engage a broad range of stakeholders.
- Communication via Whatsapp alongside emails is beneficial to increase engagement.
- Government ministries can be challenging to engage due to bureaucratic processes. The EMU notes that leveraging FCDO relationships was helpful for engaging ministries.
- The EMU provided advance notice of the interviews through a communication brief, which was co-signed by FCDO and Bappenas. This was particularly useful for facilitating introductions to provincial governments.

## Our approach to monitoring dissemination effectiveness
The EMU will follow-up with key stakeholders directly through regular meetings and written feedback to gain an understanding for how the outputs have been used and how they inform decision-making. After the dissemination of each output the EMU will ask for feedback to understand which learning outputs have been the most effective.
# Annex 6: Contribution Tracing Results
As described in the methodology (Annex 3), the EMU undertook a contribution tracing assessing using six contribution tracing stories which were developed collaboratively with FCDO and OPML. The contribution stories aligned to the case studies. The evidence for the stories was coded according to the evidential tests. The contribution tracing analysis in this evaluation is an early-stage assessment which the EMU has trialled. The EMU will build on this approach for the impact evaluation. Outcomes from delivery may not have emerged yet and it is not yet possible to fully quantify the contribution or other alternative stories. This annex intends to qualitatively summarise for each story whether the EMU has found evidence of emerging outcomes, provide a description of evidence found in relation to the contribution and provide a rating for the level of confidence in the contribution of LCDI2 to the intended outcome.
The EMU has assessed the level of confidence in each story being true based on three factors:
1. Whether the outcome has been observed or not. Given the early stage of this contribution tracing assessment, it might not yet be possible to evidence all the outcomes. In these cases, it will not be possible to say how true or not the story is, but only to provide an early indication of whether the story will hold true or not.
2. Value of the evidence test. Smoking gun evidence, which is highly persuasive evidence of LCDI2 contribution to the outcome is valued higher than hoop test evidence. Hoop test evidence indicates a condition for the story to be true but is not sufficient in proving the whole story. It provides only one piece of the puzzle. Smoking gun evidence provides a higher value of confidence in the story being true, and the LCDI2 programme contributing to the outcome observed.[31] The EMU has considered the quantity of evidential tests and the type of tests in the assessment, for example whether multiple pieces of hoop test evidence were observed or whether smoking gun was observed.
  [31] It is unlikely that doubly decisive evidence will be observed.
3. Triangulation of the evidence. The triangulation of evidence refers to the number and type of sources the EMU has found supporting each piece of evidence. The EMU has considered how verifiable and plausible each source is in the assessment, and whether the evidence reviewed is subjective or influenced by biases.
Table 26 provides a summary of how the EMU has assessed the level of confidence in the story being true using the evidence test and triangulation of the evidence.
Table 26 Confidence ratings based on the value of evidence test and the triangulation of evidence
Evidence test	Triangulation of evidence
	Single piece of evidence	Triangulation of the evidence from at least one other source	Triangulation of evidence from multiple sources
Straw in the wind	Very low confidence in the story being true / not true– not included in the findings	Low confidence in the story being true or not true	Low – medium confidence in the story being true or not true
Hoop	Low confidence in the story being true or not true	Low - Medium confidence in the story being true or not true	High confidence in the story being true or not true
Smoking gun	Medium confidence in the story being true or not true	High confidence in the story being true or not true	Very high confidence in the story being true or not true

In this analysis the EMU has indicated where we have found evidence of alternative stories, noting that these may only be starting to emerge. This will help us to provide further understanding for how the pathways envisioned for LCDI2 are materialising and how different pathways within the programme and other factors outside of the programme speak to each other. It is not possible to understand which story has the largest contribution to change at this stage; as the programme progresses the EMU will further collect evidence against the stories to understand the strength of different factors to contribution.
Feedback and changes to the story wording have been integrated based on the discussion from the contribution court on 16th October, which provided FCDO and OPML an opportunity to validate and review the findings.
## Overview
Table 27 provides an overview of the level of confidence in each story being true based on the current assessment of evidence. It is expected the confidence ratings will change as delivery progresses as part of the assessment in the impact evaluation.
Table 27 Summary of EMU confidence rating for each contribution story based on current delivery and evidence collected up until September 2025
Contribution story	Level of confidence the story is true based on emerging evidence
Integration of LCD into national planning: / By providing Bappenas with studies and roadmaps for integrating LCD in priority sectors, Bappenas is informed of the options for integrating LCD in priority sectors, enabling them to integrate LCD into national planning through its inclusion in the RPJPN 2025-2045.	Medium confidence the story is true
Improved monitoring and reporting of LCD: / By providing technical support for emissions monitoring systems in terms of methodologies and integration, LCDI2 facilitates the establishment of AKSARA as the primary national emissions reporting database, resulting in improved monitoring and reporting for national planning and international commitments.	Low - Medium confidence the story will hold true
Alignment of policies and plans: / By conducting analysis, modelling exercises and briefing GoI Ministries, GoI Ministries are able to deploy the requisite expertise to develop policies, plans and strategies that integrate LCD and align to the RPJPN.	High confidence the story is true
Public finance for LCD pilots: / By undertaking feasibility studies for LCD pilot projects, local government have the technical roadmap for developing LCD projects resulting in an allocation of public financing to projects proposed in the feasibility studies.	Medium confidence the story will hold true
TA support to Bappeda and Pokja: / By delivering technical assistance, Bappeda & Pokja in four pilot provinces have the technical capacity and in-formation to integrate LCD into the Low Carbon Development and Climate Resilient Programme Development Plan (RPR KBID) and the Provincial Medium-Term Development Plans (RPJMD).	High confidence the story will hold true
Parliamentarian support / By identifying key parliamentarians and convening strategic meetings with them, LCDI provides the necessary information to increase publicly expressed political support for the initiative and higher ambition for LCD action.	Low confidence the story will hold true

## Integration of LCD into national planning
### Contribution story:
By providing Bappenas with studies and roadmaps for integrating LCD in priority sectors, Bappenas is informed of the options for integrating LCD in priority sectors, enabling them to integrate LCD into national planning through its inclusion in the RPJPN 2025-2045.
### Has the outcome been observed?
In November 2024 the RPJPN 2025-45 was published by Bappenas. The plan clearly includes LCD targets, for example green economy and low carbon development is mentioned in Chapter 2 and targets for green economic implementation are mentioned.
### Summary of the evidence for contribution
Based on a review of the evidence the EMU can see a picture of contribution emerging from the LCDI2 programme activities. Through KIIs with the Programme team and programme documentation such as the LCDI2 Quarterly Reports and LCDI2 Annual Review, the EMU found evidence that the LCDI2 programme provided modelling targets and policy scenarios for priority sectors to Bappenas in a timely manner to support the development of the RPJPN. The EMU was able to triangulate this from over five different evidence sources. Secondly, the EMU found evidence that Bappenas engaged with the materials shared by the LCDI2 programme team at meetings. Evidence for this included briefing presentations for Bappenas prepared Delivery Partners. Only one piece of evidence was found by the EMU demonstrating Bappenas engagement with Delivery Partners through presentations. Both the LCDI2 activities of developing and sharing technical materials with Bappenas, and engaging with Bappenas in meetings provide hoop-level evidence tests for the LCDI2 programme contributing to the development of LCD targets in the RPJPN. One piece of evidence was identified by the EMU through KIIs where Bappenas acknowledged the technical contribution modelling inputs from LCDI2 into RPJPN. This smoking gun evidence provides strong support for the LCDI2 programme contribution and for the whole story being true, but it should be noted by the EMU that it was not possible to triangulate this piece of evidence with other sources, and it represents the opinion of one individual. This evidence also does not allow the EMU to rule out other possible contributing factors.
Whilst the majority of evidence found by the EMU suggest the LCDI2 programme had a positive contribution towards developing LCD targets for inclusion in the RPJPN, one piece of evidence did suggest that LCDI2 may not have contributed, and other factors had a larger role. One KII indicated that the energy nuclear targets included in the RPJPN were agreed before the input of the LCDI2 programme team, suggesting that the timing of LCDI2 programme support may not have been appropriate to support the development of the RPJPN and that other factors may have contributed to the development of that particular target. The EMU was not able to triangulate this through other sources.
The evidence for contribution for this story is derived mainly from sources working closely with programme delivery or Bappenas. Confidence in the contribution would be further strengthened by evidence from additional sources, such as other government stakeholders, or evidence to suggest that LCDI2 outputs were included within other relevant documents such as RENSTRA documentation or internal ministerial communications.
Overall, given that LCD has been integrated into the RPJPN and the EMU found several pieces of hoop test evidence, some of which could be triangulated, and a single piece of smoking gun evidence, there is a medium level of confidence in the contribution of LCDI2 towards the integration of LCD in the RPJPN.
### Emerging alternative stories
The EMU found evidence from previous LCDI Annual Reviews of a possible alternative story, where activities completed by WRI before the start of LCDI2 contributed to the support to Bappenas for including LCD in the RPJPN:
By WRI providing Bappenas with scenario planning and projections on the green economy and the Low Carbon Development Index, WRI supports Bappenas to link indicators from the Green Economy Index in the RPJPN, enabling them to include LCD in the RPJPN 2025-2045.
No other evidence of alternative stories was found at this stage, but the EMU expects a clearer picture of contributing factors may emerge as delivery progresses.
### Proposed changes to the story wording
This story was not discussed as part of the contribution court. The EMU proposes to retain the wording of the story and to collect further evidence to assess how likely it is this story is true alongside any other potential alternative stories as part of the Impact Evaluation in 2027. As programme delivery progresses, it is expected that more evidence will be found relating to the story.
### Relevance for ELQs
Relevant ELQ:
EQ 5.1	How effectively is the LCDI2 progressing towards the achievement of its intended outcomes and impacts?
EQ 1.3	What alternative pathways for achieving intended impacts can be identified?

In OPML’s TOC the purpose of WS1 is to integrate LCD into planning. After assessing the evidence the EMU has a medium level of confidence that the story is true, and that LCDI2 contributed to the inclusion of LCD in the RPJPN. It provides evidence that the technical support provided by the programme team to Bappenas has been effective in the integration of LCD in the RPJPN and that LCDI2 is progressing towards achievement of its intended outcomes. The identification of the alternative story around WRI’s support also presents an alternative pathway for achieving the intended impacts.
## Improved monitoring and reporting
### Contribution story:
By providing technical support for emissions monitoring systems in terms of methodologies and integration, LCDI2 facilitates the establishment of AKSARA as the primary national emissions reporting database, resulting in improved monitoring and reporting for national planning and international commitments.
### Has the outcome been observed?
The EMU notes that it is too early in delivery to have observed the outcome of the establishment of AKSARA as the primary emissions database. No improvements to monitoring and reporting of LCD targets as a result of this establishment have therefore been observed. It is noted that interoperability between databases is a complex process with activities underway in July 2025 to compile methodologies for AKSARA, SRN, IPC and CDM. In addition, the Delivery Partner noted that the interoperability work has not been a key focus for resources for this year’s delivery, which may also reflect on why limited evidence was found by the EMU.
### Description of the evidence
Despite the early stage of delivery, the EMU has found some evidence of the contribution of LCDI2 activities in working towards this goal. Quarterly reports, monthly progress reports and programme KIIs indicated that the LCDI2 programme team has provided Bappenas with technical support on updating methodologies for the interoperability of AKSARA. The support provided included updating annual GHG emissions values and compiling and assessing methodologies for each sector across SRN, AKSARA, IPCC and CDM. The EMU has been able to triangulate this evidence through multiple sources. In addition, the EMU was able to evidence that Bappenas engaged with Delivery Partners in the technical methodologies through focus group discussions and internal conversations, as evidenced through KIIs and programme documentation. Again, this was triangulated through multiple sources. Both the technical support on the methodologies and evidence of LCDI2 engaging Bappenas provide pieces in the picture of contribution that may contribute towards the overall outcome. At this stage, the EMU found no evidence of Bappenas using the methodologies or acknowledging LCDI2 support to improve monitoring and reporting of LCD targets for AKSARA. No evidence from other government stakeholders stating LCDI2’s contribution to the establishment of AKSARA as the primary database and improved interoperability was found.
In evaluation terms, the EMU has observed two types of hoop test that can be validated through multiple sources in support of the story being true. Therefore, the EMU currently has a low-medium level of confidence in the story. However, as the outcome has not yet been fully observed this should be understood as confidence that the story will hold true. In the contribution court on 16th October, after a presentation of the evidence to OPML and FCDO, participants expressed light confidence the story might be true, in that 50%[32] were more confident than not that the story was true.
[32] Based on eight participants.
### Emerging alternative stories
The EMU found evidence of two alternative stories that may contribute to the outcome. KIIs, Quarterly Reports and the business case indicated that GIZ has played a role in the establishment of AKSARA:
Training and support from GIZ to Bappenas have contributed to the establishment of AKSARA as the primary national emissions reporting database.
Secondly, the EMU found evidence from programme documentation and KIIs that LCDI2 has played a role in facilitating engagement and buy-in from other ministries such as the Ministry of Environment to AKSARA. An MOU is now established for this interoperability work between Bappenas and the Ministry of Environment and Forestry. This work represents an alternative pathway for change:
The LCDI2 programme team conduct engagement activities to increase buy-in from other relevant ministries, contributing to the establishment of AKSARA as a primary national emissions reporting database.
These alternative stories were presented to OPML and FCDO during the contribution court on 16th October. It was acknowledged that the alternative stories are a reflection of the complex, political situation in which the LCDI2 programme is operating to improve reporting.
### Proposed changes to story wording
The contribution court provided an opportunity to collaboratively test and validate the evidence and reflect on the wording for the story. The current story wording focuses on the aspiration of the establishment of AKSARA as the primary emissions database for international commitments and national planning. OPML reflected delivery is more focused on supporting the interoperability of AKSARA with other databases rather than establishing it as the primary database, representing a change in the aspiration. In addition, given the complex political environment and the role of the Ministry of Environment and SRN, which is recognised internationally as the means for reporting on NDCs internationally, it was discussed that aiming to establish AKSARA as the primary database may not be an appropriate aim. OPML reflected the current aim of this work is to improve the ease of reporting for stakeholders and reduce the reporting burden through interoperability between databases. Given the EMU’s understanding of the evidence and based on contribution court reflections, the EMU proposes a change to the wording of the contribution story:
By providing technical support for emissions monitoring systems in terms of methodologies and integration, LCDI2 facilitates the interoperability of AKSARA with other national emissions reporting databases, resulting in increased ease of monitoring and reporting for national planning.
The EMU proposed to further test this story during the Impact Evaluation in 2027.
### Relevance for ELQs
Relevant ELQ:
EQ 1.1	How can the ToC or the delivery model be improved to help support LCDI2’s intended Outcomes?
EQ 1.3	What alternative pathways for achieving intended impacts can be identified?

In the TOC the goal of WS1 is to improve reporting to more effectively monitor progress towards LCD. The TOC states an intermediate outcome relating to reporting of AKSARA system methodologies enables accurate reporting alignment across NDC, LCD and RPJPN. Given the revision of the story wording to focus on improving interoperability and reducing the reporting burden, there may now be a misalignment with the current TOC pathway and the delivery activities. The TOC could be strengthened through a clearer articulation for how interoperability will result in improving monitoring and reporting, or whether this is an assumption that should be stated.
The identification of two alternative stories regarding training provided by GIZ and LCDI2 activities to engage ministries highlight potential alternative pathways for achieving the intended impact.
## Alignment of policies and plans
### Contribution story:
By conducting analysis, modelling exercises and briefing GoI Ministries, GoI Ministries are able to deploy the requisite expertise to develop policies, plans and strategies that integrate LCD and align to the RPJPN.
### Has the outcome been observed?
Due to the breadth of this story’s wording, the EMU collected evidence for the LCDI2 programme’s contribution across a range of policies, sectoral plans and strategies. Various outcomes have been observed, for example:
The revised National Energy policy[33] includes the integration of LCD strategic in in Article 13.
[33] https://lestari.kompas.com/read/2025/02/04/170500486/rpp-ken-disetujui-ebt-bakal-digenjot-hingga-70-persen-pada-2040-
Bappenas published ‘Low carbon development strategies and stages in the in the 2025-20245 RPJPN efforts to achieve net zero emissions[34], which was signed by the Minister.
[34] https://lcdi-indonesia.id/wp-content/uploads/2025/05/Strategi-dan-Penahapan-Pembangunan-Rendah-Karbon-dalam-RPJPN-2025-2045-Upaya-mencapai-Net-Zero-Emissions.pdf
The RPJMN 2025-2029 was published in February 2025, which includes strategies and targets for LCD.
### Description of the evidence
The EMU found evidence for LCDI2 providing technical support to Bappenas to support the development of policies plans and strategies. LCDI2 activities included conducting analysis, scenario modelling and developing targets. This evidence has been triangulated through multiple sources. There is clear evidence of the LCDI2 programme team engaging GoI institutions such as Bappenas and staff from the relevant ministries in the integration of LCD into policies, plans and strategies through programme documentation such as invitations to GoI for focus group discussions, summaries of focus group discussions with line ministries of sectors, and minutes from meetings with sectoral ministries.
Again, the EMU did not find evidence for how GoI engaged and used information shared by the LCDI2 team but did find two pieces of evidence where GoI acknowledge the contribution of the LCDI2 programme team. Firstly, the publication of the document ‘Low carbon development strategies and stages in the 2025-2045 RPJPN efforts to achieve net zero emissions’30 which was signed by the Minister at Bappenas credits OPML staff with contributing to the document and credits LCDI2. This provides one strong piece of evidence the story is true. It does not however rule out contribution from other factors. In KIIs, Bappenas also expressed LCDI2 provided technical support for the development of the Grand Design for Indonesia’s Green Economy, which again shows a contribution of the LCDI2 programme team.
Not all the evidence found by the EMU suggests a positive contribution of LCDI2 activities. In a couple of instances, the evidence suggested the timing of some technical inputs and recommendations were not made at an appropriate time to contribute to the development of the RPJMN.
Overall, with multiple pieces of smoking gun evidence and hoop test evidence from a variety of sources despite a couple of examples of negative hoop test evidence, the EMU finds a high confidence in the contribution of the LCDI2 team regarding some of the specific outcomes evidenced to date, such as the RPJMN and the Bappenas strategies and stages for LCD development document. However, at this stage, the EMU has a lower level of confidence in the contribution of LCDI2 towards the development of the National Energy Policy revision as only hoop test level evidence was found. One particular challenge in examining the contribution of this story is the breadth of the story wording to cover a wide range of policies, plans and activities, which makes it harder to assess a consistent level of contribution across all policy outcomes. Further deep dives through case studies in the Impact Evaluation will allow for further assessment of contribution towards individual policies.
### Emerging alternative stories
The EMU found limited evidence for alternative stories at this stage. One reference to an alternative story was found from programme documentation indicating that GIZ, the Net Zero World Initiative and Pertamina Energy Institute provided modelling contributions for energy planning in the RPRMN 2025-2029.
### Proposed wording changes
We propose to retain the story wording for further testing in the impact evaluation. As delivery progresses and policies, plans and strategies are finalised we expect to see further examples of higher test evidence appearing, such as smoking gun evidence and more evidence for the link between how LCDI2 activities result in the outcomes observed.
### Relevance for ELQs
Relevant ELQ:
EQ 5.1	How effectively is the LCDI2 progressing towards the achievement of its intended outcomes and impacts?
EQ 1.3	What alternative pathways for achieving intended impacts can be identified?

A higher level of confidence in the contribution of LCDI2 for this story provides support EQ5.1 that LCDI2 is progressing towards its achievements and intended impacts. The story aligns to the goals of WS1 in the TOC and suggests that the technical contributions of the programme team have been effective in supporting achievement of outcomes, such as LCD integration in the RPJMN. The limited evidence for the alternative story relating to additional modelling support from other programmes provides some evidence for EQ1.3.
## Public finance for pilots
### Contribution story
By undertaking feasibility studies for LCD pilot projects, local government have the technical roadmap for developing LCD projects resulting in an allocation of public financing to projects proposed in the feasibility studies.
### Has the outcome been observed?
The Samosir Regional Government drafted a letter in April 2025 to Bappenas which outlines the activities to support the solar PV pilot project, which was proposed by LCDI2. The letter includes costs for operator’s salaries, training and pump maintenance, demonstrating an increase in commitment to public funding. It is expected that as the WS4 Innovation Technology Fund progresses in delivery, more projects will be proposed by LCDI2 and there may be more opportunities to observe the outcome of increasing the allocation of public financing to pilots at the wider provincial level.
### Description of the evidence
The LCDI2 programme has completed the planning stage of the solar PV project and shared a feasibility study. It is noted that the pilot in Samosir has not yet been implemented In addition, OPML recommended that the EMU did not visit Samosir directly for a site visit due to the potential to raise expectations of stakeholders regarding project delivery, which is a limitation to the evidence collection for this contribution story.
The letter from the Samosir Regional Government in April 2025 to Bappenas provides strong evidence for contribution of the LCDI2 programme team, as it indicates commitments to funding following the LCDI2 activities. In addition to this, the LCDI2 programme team conducted the feasibility study for the solar PV pilot, which was shared with the local government. The range of evidence for this story was more limited compared to the other stories. However the Samosir Government letter represents smoking gun evidence due to the mention of LCDI2 directly and reference to LCDI2 activities such as field visits and meetings. However, this letter does not directly reference the feasibility study completed by Delivery Partners. Alongside other evidence supporting the completion of the feasibility study the EMU can have a medium level of confidence in this story being true.
### Emerging alternative stories
Case study 3 notes that a KII from Bappelitbangda Samosir suggests that the Samosir District Government has previously committed financial support through operator salaries, training and pump maintenance to five solar PV pumps operating in Samosir District from 2020-2024. This suggests that there may be other factors also contributing to the increase in public finance to the LCDI2 solar PV pilot. The case study notes that the five existing solar PV pumps’ operation costs are also still covered by the Samosir District Government. The EMU notes that further exploration of alternative stories would be beneficial.
### Proposed wording changes
We propose to retain the current story wording and to continue to test this story during the Impact Evaluation, particularly as WS4 progresses.
### Relevance for ELQs
Relevant ELQ:
EQ 5.1	How effectively is the LCDI2 progressing towards the achievement of its intended outcomes and impacts?

In particular, the letter of Samosir Government support suggests that LCDI2 has made progress in WS2 towards achieving the intended outcome of increased allocations to LCD in provincial budgets.
## TA support to Bappeda
### Contribution story:
By delivering technical assistance, Bappeda & Pokja in four pilot provinces have the technical capacity and information to integrate LCD into the Low Carbon Development and Climate Resilient Programme Development Plan (RPR KBID) and the Provincial Medium-Term Development Plans (RPJMD).
### Has the outcome been observed?
At the time of writing, the EMU notes the RPRKBID is finalised in North Sumatera and refers to the RPJMN. It describes a profile for LCD and climate resilience programme including LCD policies, strategies and programmes. The EMU has not yet seen the RPRKBID for Bengkulu, or the RPRKBID for NTB which was updated in 2025. We have also not yet received or reviewed the RPJMD for the four priority provinces. However, KIIs from the provincial government have noted that the draft documents for RPRKBID and RPJMD include LCD.
### Description of the evidence
Based on the field visits, KIIs and programme documentation a picture of contribution is emerging from LCDI2 activities towards the development of RPRKBID and RPJMD and the inclusion of LCD.
Firstly, the LCDI2 programme team delivered workshops, focus groups and discussions with the provincial authorities to provide technical support for the integration of LCD in the RPRKBID and its integration into RPJMD. This was seen across NTB, Bengkulu and North Sumatera and triangulated from various evidence sources such as KIIs with partners, the programme team, provincial authorities and programme documentation such as minutes from policy dialogues and Quarterly Reports. It is also clear that the LCDI2 programme provided support by directly developing technical inputs through modelling support and analysis into drafts of the RPRKBID documents, which is evidenced from a variety of sources.
Building on this evidence, the EMU notes that provincial governments, an NGO and other GoI ministries acknowledged the technical contribution of LCDI2 in supporting the inclusion of LCD in the development of RPRKBID and RPJMD. The acknowledgement of LCDI2 support from multiple sources does indicate a strong case for the contribution of the programme to achieving the outcome.
From an evaluative perspective, the multiple pieces of smoking gun evidence, supported by hoop test evidence with triangulation from multiple sources suggests that we can have a high confidence in the contribution of the LCDI2 programme. We note that in some provinces, such as NTB and Bengkulu the EMU has not yet received the finalised version RPRKBID or RPJMD, therefore the outcome has not yet been fully observed. The confidence should be understood as confidence the story will hold true. In the contribution court on 16th October, the EMU presented the evidence as an opportunity for discussion and validation with FCDO and OPML. After reviewing a snapshot of the evidence, 50% of participants felt they were reasonably certain the claim was true.[35]
[35] Based on a total of eight participants.
### Emerging alternative stories
Despite the case for contribution of the LCDI2 programme, one alternative story emerged from the evidence as alternative pathway for contribution. In NTB, KIIs suggested that Islamic Relief played a role in the development of the RPRKBID in 2023:
Islamic Relief supported the development of the RPRKBID by investing in local capacity and systems, helping to integrate LCD into the RPRKBID.
It is valuable to further review and understand the factors that might be contributing to the outcomes seen and the EMU hopes to explore this further in the Impact Evaluation.
Secondly, evidence is emerging of a second alternative story from KIIs and programme documentation of LCDI2 support to the Ministry of Home Affairs (MoHA) contributing to the inclusion of LCD in the RPRKBID:
Other LCDI2 programme activities, such as the support provided to MoHA in developing LCD guidelines for provinces has supported the integration of LCD in RPRKBID.
### Proposed wording changes
In the contribution court, OPML suggested that the story would benefit from a clarification that the LCDI2 programme supports capacity building of provincial government, but also directly contributes to the development of RPRKBID and RPJMD:
By delivering technical assistance through capacity building activities and technical contributions to documents, Bappeda & Pokja in four pilot provinces have the technical capacity and information and are supported to integrate LCD into the Low Carbon Development and Climate Resilient Programme Development Plan (RPR KBID) and the Provincial Medium-Term Development Plans (RPJMD).
### Relevance for ELQs
Relevant ELQ:
EQ 5.1	How effectively is the LCDI2 progressing towards the achievement of its intended outcomes and impacts?
EQ 1.3	What alternative pathways for achieving intended impacts can be identified?

The high confidence that the story will hold true provides support for LCDI2 progressing towards the outcome for WS2 mentioned in the TOC, whereby LCD is integrated into policies at the provincial level. It suggests that the delivery activities conducted by LCDI2 in terms of the workshops, capacity building events and technical contributions have been effective. It is also useful to note the influence of Islamic Relief and support to MoHA as an alternative pathways for EQ1.3.
## Parliamentarian support
### Contribution story
By identifying key parliamentarians and convening strategic meetings with them, LCDI provides the necessary information to increase publicly expressed political support for the initiative and higher ambition for LCD action.
### Has the outcome been observed?
It is too early within delivery to have observed increased public support and higher ambition for LCD action from key parliamentarians. The political assessment to identify parliamentarians was completed earlier in 2025, with a four-month period before engagement of the parliamentarians. Initial engagement with parliamentarians was described in the April – June 2025 Quarterly Report, indicating that engagement is at an early stage and it will not yet be possible to observe outcomes in relation to this story.
### Description of the evidence
From the evidence collected it is difficult for the EMU to understand the picture of contribution for this story. This may be a reflection of the early delivery stage, and due to the nature of this story we expect that most of the evidence collected will be perspective based and dependent on opinions.
It is clear that LCDI2 has conducted relevant activities for this story through the political landscape assessment to identify parliamentarians. Similarly, programme documentation suggests that the parliamentarians have also been approached by LCDI2. Both of these factors are necessary components for the contribution story being true. However, we have not been able to find evidence for the change that resulted from this work, for example how the parliamentarians engaged with LCDI2 and what changed as a result of this engagement. The picture for contribution of the LCDI2 programme is further complicated by one piece of evidence from KIIs suggested that other parliamentarians may have been a better choice for having a greater influence and level of power. Furthermore, one of the parliamentarians selected by LCDI2 resigned from Parliament in August 2025 due to political pressure and it is not yet clear how this might influence the contribution of the LCDI2 programme or the achievement of the intended outcome.
Given the mix of evidence in support for and against the story and that the value of the evidence is at the hoop test level, the EMU assesses a low confidence in the contribution of the LCDI2 programme. Given the outcome has not yet been observed, the EMU has a low confidence that the story will hold true. Interestingly, 55% participants in the contribution court stated they felt a high confidence the claim was true after a presentation of the evidence.[36] The EMU feels revisiting this story in the Impact Evaluation will help to provide a clearer picture of the contribution.
[36] Based on eight participants.
### Emerging alternative stories
Numerous public media sources[37] and KIIs have identified that the two selected parliamentarians already had a strong level of support for LCD issues prior to engaging in the LCDI2 programme. This suggests an alternative pathway for achieving the outcome is being used, which focuses more on leveraging existing commitment and support:
[37] For example: Rekam Jejak Partai Politik di Isu Iklim dan Transisi Energi: Analisis atas Temuan Media dan Platform Partai and Eddy Soeparno Dorong UU Pengelolaan Perubahan Iklim Bisa Segera Dijadikan Prolegnas and https://www.fraksigerindra.id/hadiri-ktt-perubahan-iklim-pbb-rahayu-saraswati-ingatkan-negara-kaya-harus-bantu-negara-miskin-dalam-pendanaan-hijau/
By engaging parliamentarians who are already supportive of LCD, LCDI2 leverages existing commitment to LCD to increase wider support for LCDI2 from stakeholders and higher ambition for LCD action.
### Proposed wording changes
Based on contribution court feedback the EMU proposes to amend the story to clarify that it is considering engagement at the national level:
By identifying key parliamentarians at the national level and convening strategic meetings with them, LCDI2 provides the necessary information to increase publicly expressed political support for the initiative and higher ambition for LCD action.
Given the early stage of programme delivery in parliamentarian engagement, the EMU proposes to continue to collect evidence for this story in the Impact Evaluation.
### Relevance for ELQs
Relevant ELQ:
EQ 1.1	How can the ToC or the delivery model be improved to help support LCDI2’s intended Outcomes?
EQ 1.3	What alternative pathways for achieving intended impacts can be identified?

In the TOC the outcome of WS3 is strategic stakeholders demonstrate support for higher ambition in LCD action. The EMU notes that LCDI2 activities so far to engage parliamentarians have focused more on identifying parliamentarians with an existing high level of public commitment to LCD. The TOC and intermediate outcomes may be strengthened from a clearer articulation on how engagement of parliamentarians leads to support for higher ambition in LCD and a definition for what is considered higher ambition. For example, whether this is improving parliamentarian commitment to LCDI2 or leveraging their existing commitments of LCD to a wider range of stakeholders.

# Annex 7: Case studies
The case studies have been shared as a separate document.
# Annex 8: ToC Assessment
The EMU reviewed the latest version of OPML’s ToC (Annex 2) to understand the extent to which the LCDI2 programme design is relevant for the delivery context and how LCDI2 fits within the broader landscape of climate initiatives. The components of the ToC were qualitatively assessed using a matrix approach. For each question, the EMU has scored a response on a scale of one to five where one is the question is not included / well considered, and five is where it is well addressed and considered. The findings are presented in Table 28. The full methodology is described in Annex 3.
Table 28 EMU review of the ToC, questions and scoring
Question	Score (1-5)	Actions Needed	EMU commentary
Development process
Is the process and rationale for ToC development and any recent updates fully described in the ToC narrative?	3	Document the process of development and updates. / Introduce a version history and changelog. / Clarify linkages with logframe and MEL.	The ToC narrative explains why it exists and what changed in broad terms, but it does not fully document the process used to develop/update it (e.g., who was consulted, decision steps, version history, formal change log).
Did the ToC have appropriate engagement for co-design?	3	Determine a structured co-design loops with actors to be involved. / Document co-design participation & decisions for later revision(s). / Embed co-design evidence in MEL.	The ToC is explicitly demand-led via Bappenas, with the programme “at the heart” of a partnership with Bappenas and plans to reach parliament, private sector, CSOs, and provinces. However, the narrative does not evidence a co-design process (who was engaged, when, and how decisions were taken).
Overall structure
Does the ToC contain elements which are obsolete or confusing?	4	Make pathways less vague by providing “most-likely intermediate outcomes” with concrete adoption signals that are specific, observable, and time-bound. Particularly for WS3-WS4. / Make GEDSI operational by adding 1–2 standing mechanisms per workstream (e.g., GEDSI gate in WS1 policy notes; GEDSI participation metric in WS2 clinics; stakeholder segment targets in WS3; inclusive beneficiary criteria in WS4).	Nothing obsolete as the core directions (RPJMN/RPJPN alignment; WS1–WS4); AKSARA/SRN/SIGN-SMART) remain current. Some structural issues may cause confusion for the reader and present navigational challenges.
Does the ToC require extensive knowledge of programme elements not reflected in the theory to correctly understand its structure?	4	Add essential context inside this ToC, e.g., the TOC purpose and audience, glossary, and roles of each actor. / Provide “most-likely intermediate outcomes” with concrete adoption signals, that is easier to understand for user without/lack of insider knowledge.	The TOC relies on specialised programme terms and systems (RPJMN/RPJPN, Renstra, RPR-KBID, AKSARA/SRN/SIGN, WS4 fund mechanics) with limited in-document explanation, raising the “entry cost” for non-core audiences. The 2025 ToC defers key detail to earlier documents (e.g., assumptions to the Feb-2024 framework/annexes), so readers must consult prior materials to fully grasp the causal routes and risks. Adaptive sections keep outputs/outcomes generic, which is defensible, but without working knowledge and examples this feels vague and forces readers to know the unwritten programme context to interpret pathways. However, those are acceptable considering its limited audience.
Can the reader easily understand the logic and structure of the ToC?	4	Provide “most-likely intermediate outcomes” with concrete adoption signals in simple language, particularly for WS3-WS4.	Logic is present, but not always easy to follow. The ToC lays out a coherent 4-workstream structure (WS1–WS4) that covers national planning, sub-national planning, stakeholder engagement, and innovation but generic outputs/outcomes make the flow harder to trace—users may not see how activities lead to results without insider knowledge.
Does the ToC appropriately consider the local context?	5	No action needed.	The ToC is anchored in GoI planning and budgeting cycles, considers local MRV systems (AKSARA, SRN, etc.), and acknowledged local political and stakeholder realities.
ToC components
Is the wording of the outcomes and intermediate outcomes explicit and clearly defined? Are they specific, measurable, relevant to the activities and achievable?	3	Rewrite outputs and IOs as SMART statements (per WS) where possible. / Add an Indicator List in the ToC or make the logframe as an integrated part of the ToC.	Outcomes/IOs align to Indonesia’s planning/budget/reporting systems (RPJPN/RPJMN, RPJPD/RPJMD, RPRKBID, AKSARA/SRN/SIGN SMART) and to the four workstreams—so they are specific, relevant and anchored in real decision instruments but the ToC mostly uses generic verbs (“adopted”, “integrated”, “used”) and examples rather than canonical, time-bound statements with clear evidence sources/ownership. Generally, the ToC is plausible and supported by GoI processes, but assumption-heavy and without consistent milestones or thresholds per IO/outcome inside this document (probably would be detailed in the logframe).
Is the timeframe for results (intermediate outcomes and outcomes) reasonable?	4	Add a simple, dated results calendar for IOs, e.g., by 2026, by FY-2027, etc.; or / Make the logframe as an integrated part of the ToC.	The ToC anchors to Indonesia’s real planning/budget cycles , which makes the implied timing broadly reasonable. However, the ToC does not assign dates or phase-gates to most Intermediate Outcomes (IOs) and Outcomes—timelines are kept generic due to the adaptive approach (probably would be detailed in the logframe).
Does the ToC cover all LCDI activities under the workstreams?	4	List the activity families under each Technical Intervention type that could easily tied to the relevant IOs.	LCDI activities under the workstreams are mostly covered, at the level of “intervention types”. However, because the document keeps outputs/outcomes generic by design (adaptive management), some concrete activities are not spelled out and must be inferred from the intervention types and examples.
Are there any gaps within the ToC that should be addressed to achieve the stated impact?	4	Make the linkage between WS1-2 (policy and governance) and WS3-4 (engagement and piloting) clearer in terms of expected LCD actions.	The ToC names politics as a factor but doesn’t embed concrete levers/tactics to ensure the actors, e.g. line ministries, to comply with the targets in RPJMN. WS2 is strong conceptually, but the ToC doesn’t spell out the strategy to enable provinces/districts develop or implement instruments, incentives, and budget hooks that move the regions from guidance to implementation, e.g. by facilitating private investment in LCD.
Are the causal pathways and process of change appropriately defined?	4	Make the linkage between WS1-2 (policy and governance) and WS3-4 (engagement and piloting) clearer in terms of expected LCD actions. / Provide “most-likely intermediate outcomes” with concrete adoption signals.	The ToC lays out Outputs, Intermediate Outcomes, Outcomes per workstream (WS1–WS4) with example IOs, and lists cross-cutting assumptions and an adaptive approach. This gives a recognizable causal scaffold at national (RPJMN/Renstra), sub-national (RPJMD/RPRKBID), stakeholder (DPR/private/CSOs), and pilot/tech levels (ITF/BPDLH). However, pathways rely on generic verbs (“adopted/used/integrated”) and implicit mechanisms (e.g., how WS3 influence converts to WS1/WS2 decisions). Inter-WS feedback loops and necessary/sufficient conditions are not explicit which making it hard to see how outputs reliably turn into IOs/outcomes without insider knowledge.
ToC Assumptions
Are the assumptions underpinning the change process clearly defined at each level of the change pathways?	4	Link assumptions to specific change in each WS pathway. / Categorise and tag assumptions by risk. / If the WS assumptions are listed in the logframe, make the logframe a part of the ToC.	The ToC explicitly recognises that LCDI2 operates in an uncertain, adaptive context and therefore includes cross-cutting assumptions (Group A–D). Examples cover: political will, budget/data availability, and stakeholder engagement. However, they are not clearly attached to specific links in the change pathways.
Will the assumptions hold true over the lifetime of the project?	3	Elaborate the approach to monitor the key assumptions. / Consider the risks for each assumption in the Risk Register.	Many core assumptions (e.g., sustained political will, budget/data availability, DPR engagement, sub-national incentives) are high-risk and subject to external shocks (elections, fiscal constraints, policy shifts, GoI personnel change). The ToC acknowledges uncertainty but doesn’t provide systematic mechanisms for stress-testing them. Assumptions are not tied to specific causal links (e.g., “data availability” should be linked to WS1/2 modelling to RPJMN/D), which makes it hard to tell which assumptions are most vulnerable.
Are there any assumptions at risk that should be addressed?	3	Consider the risks for each assumption in the Risk Register. / Develop and implement the risk mitigation strategies.	See above.
Are there any assumptions missing?	4	Include GEDSI-related assumptions.	Most likely there are no assumptions missing at the high level since the ToC’s assumptions were general. However, there are technical level assumptions that are not spelled out in the ToC but do belongs to the assumption groups A-D. Examples of not stated assumptions but belongs to the groups: reporting platforms continuity (AKSARA, SRN, etc.), institutional mandate clarity, LCD financing availability, GEDSI understanding among stakeholders, etc. However, GEDSI-related assumptions are not spelled out in the ToC.
ToC Narrative
Does the ToC contain appropriate use of key terms and concepts?	5	No action needed.	Indonesia-specific concepts are used correctly and anchor the ToC in the local policy system.
Is the narrative written using simple language and understandable?	5	No action needed.	The ToC narrative uses consistent terminology and provides structured explanations of the problem statement, intervention types, outputs, IOs, and outcomes. Most part is written in simple language (e.g., explaining that “low carbon development refers to emission reduction together with economic growth”) but still need insider knowledge to understand it – which is acceptable considering the ToC’s audience.
Is there a narrative assessment of each workstream?	5	No action needed.	Each workstream (WS1–WS4) has a section in the ToC with a short introduction, outputs, IOs, and outcomes.
Do the ToC core pathways to change make sense/ are they plausible?	5	No action needed.	The core pathways align to Indonesia’s planning/budget/reporting systems (RPJPN/RPJMN, RPJPD/RPJMD, RPRKBID, AKSARA/SRN/SIGN SMART)—so they’re specific, relevant, plausible and supported by GoI processes.
Does the narrative set out the anticipated timing of the outputs / outcomes?	4	Add a simple, dated results calendar for IOs, e.g., by 2026, by FY-2027, etc.; or / Make the logframe as an integrated part of the ToC.	The ToC narrative does reference Indonesia’s development plans and planning cycles (RPJMN 2025–2029; RPJPN 2025–2045; RPJMD/RPJPD; Renstra 2025–2029). This indirectly anchors when LCD-related outputs/outcomes should happen. However, the narrative doesn’t provide a results calendar or phase-gates (e.g., Q2-2026, Q4-2027) for intermediate outcomes and outcomes – probably included in the logframe.
Does the ToC show synergies and linkages between outputs?	3	Add a cross-WS relationship diagram. / Narrate the linkages in each WS section. / Reflect linkages in MEL/change-harvesting, e.g. change in WS4 is affecting change in WS2 or vice versa.	The document shows four workstreams and an overall ToC diagram (“Overview of theory of change for all four workstreams”), signalling that outcomes are interconnected and reinforcing. Each WS page lists outputs and (example) IOs/outcomes, but cross-WS linkages (e.g., WS3 enabling WS1/WS2; WS4 pilots feeding WS1/WS2 policy/budget updates) are mostly left to the reader to infer rather than being drawn or narrated explicitly beside the outputs.
Does the ToC identify how the outcomes will be sustained beyond the life of the programme?	3	Narrate the synergies and linkages between outputs using sustainability lens. / Include activity families under each Technical Intervention type that is supportive to project results sustainability. / Include sustainability-related risks and its mitigation strategy in the Risk Register.	The ToC aims to integrate LCD into RPJMN/RPJPN/Renstra and provincial RPJMD/RPJPD, which implies post-programme continuity through Indonesia’s own planning/budget systems. Sustainability is hinted via continued use of AKSARA aligned with SRN/SIGN for monitoring/reporting, and via a BPDLH-hosted PMO for the Innovation & Technology Fund but there isn’t a clear exit/transition plan (who owns what after LCDI2), no explicit financing plan for ongoing ops (e.g., provincial clinics, pilots), and limited detail on policy instruments that lock in practices (decrees/circulars), so long-term durability is not guaranteed.

The current ToC assumptions were assessed according to a RAG rating, as described in Annex 3. A green score signified the assumption holds true, amber signified the assumption needs a review and further consideration and a red score signified the assumption is not true. The qualitative analysis is provided in Table 29.
Table 29 Assessment of ToC assumptions based on a RAG rating.
Assumption	RAG score	EMU comments
Group A: problem identification, technical intervention, stakeholder engagement and outputs
Entry points for a dialogue with government agencies can be effectively identified and utilised		LCDI2 relies on Bappenas (Environmental Directorate) as the entry point for a dialogue with other agencies. It was working well but could be leveraged to reach other stakeholders out.
LCDI consortium staff are perceived as credible interlocutors for government agencies		LCDI2 consortium members are deemed as not working on their core competence (Bappenas), not active or slow (NS Bappelitbangda)
Ad hoc/on-demand flexible requests from Bappenas remain proportionate/appropriate to LCDI programme resources and outcome objectives.		FCDO, OPML and Bappenas have contradicting views on this topic.
Group B: output to intermediate outcome (IO):
Evidence for technical approaches is relevant; outputs are useful and demand to adopt outputs sufficiently remains strong		Support for RPRKBID and modelling training are deemed as useful and interest for leveraged support exists.
The process of securing Bappenas official authorisations (MoUs, letters of support etc) occurs in a timely and resource appropriate manner to prevent bottlenecks		FCDO, OPML and Bappenas have contradicting views on this topic.
Willingness and ability of key stakeholder for political engagement via legislative / parliament office as well with the private sector and non-government organisations.		With currently minimal interaction with legislative/parliament office, this assumption will need review and further consideration.
Government budget availability remains stable overall (e.g., ministerial budget allocations to Bappenas and other key ministries).		With shifting development priorities, Bappenas and other key ministries as well as regional government were faced with budget cuts that effected their LCD budget allocation.
Group C: IO to outcome:
Engagement methods remain relevant for identified stakeholders who may act as key levers of change		Communication strategy developed by LCDI2 is not well received by FCDO nor bought in by Bappenas.
AKSARA users have sufficient incentives and resources to report targets and maintain accountability		Government personnel in regency/city level often missed in submitting report through AKSARA for Bappeda review. This is perceived as caused by lack of capacity and/or commitment.
Interest can be stimulated amongst key government, private sector and civil society stakeholders to prioritise LCD.		Key ministries for GHG emissions reduction (i.e. ESDM) is just recently approached by LCDI2. ESDM interested in LCDI2 support which may true for other line ministries provided they are approached as appropriate. Private sector and CSO2 (beyond LCDI2 current Delivery Partners) are minimally approached to date so there is no clear indications on their interest. However, some CSOs (i.e. Walhi) expressed their interest to receive LCDI2 support.
The political economy space remains conducive to LCD integration/mainstreaming, including the financial and business environment (e.g., global and national economic environment).		While LCD was institutionalized in the RPJMN, Indonesia haven’t submit its 2nd NDC therefore its climate commitment’s strength beyond 2030 is not known yet. However, the recently issued National Energy Policy have displayed road map toward net zero emissions of the energy sector by 2060. National and global dynamics like shifting development priorities and geopolitics instability, also pose challenges for leveraging LCD investment in Indonesia but on the other hand, Indonesia finance authorities remain committed to sustainable finance. / By strategically addressing these barriers and leveraging emerging opportunities, Indonesia can accelerate its transition toward a low-carbon economy while advancing national development priorities. LCDI2’s success will depend on its ability to navigate these political economy dynamics, align incentives, and build the coalitions necessary for sustained and transformative change (PEA, 2025).
Group D: cross-cutting:
State-based planning remains an essential requirement for Indonesia, to make the switch to a low carbon development pathways. Including that Bappenas LCD planning is a sufficient base to influence LCD integration across ministries to catalyse plans into actions and budgets.		While it is true that state-based planning remains essential, particularly with LCD targets inclusion in RPJMN, its ability to become a sufficient base to influence LCD integration across ministries needs a review and further consideration. This is due to the existence of sectoral development plans, e.g. National Energy Policy, that has no observed causal relationship with RPJMN’s targets.

# Annex 9: Political Economy Analysis (PEA) for LCDI2 (November 2025)
Contents

## Executive Summary[38]
[38] (Citations: BAPPENAS 2019, 2020; MoEF 2024, 2025; MEMR 2025; MoF 2024; Perpres 110/2025; PP 40/2025; RPJMN 2025–2029; RPJPN 2025–2045.)
Indonesia’s emerging low carbon development ecosystem
Indonesia’s pathway toward a low-carbon economy has reached a decisive turning point. In 2025, the Government of Indonesia (GoI) consolidated a suite of major policy reforms that embed low-carbon development (LCD) into the core of national development planning, fiscal architecture, and institutional coordination. The LCD framework—first introduced through the RPJMN 2020–2024—has now evolved into a national governance mechanism connected to the RPJMN 2025–2029, the National Energy Policy (PP 40/2025), and the Carbon Economic Value regulation (Perpres 110/2025). Alongside the forthcoming Second NDC (SNDC 2025–2035), these instruments define a more coherent policy ecosystem for achieving Indonesia’s long-term climate and development goals.
### PEA’s purpose and analytical lens
This Political Economy Analysis (PEA) provides an analytical foundation for the LCDI2 Process Evaluation (2025), examining the formal and informal political, economic, social, and institutional dynamics shaping Indonesia’s low-carbon transition. Through document reviews, interviews, and systems mapping, the PEA identifies the incentives, networks, and structural constraints that influence climate decision-making at national and subnational levels. The analysis also clarifies how LCDI can transition from a planning initiative to a durable, government-owned governance mechanism.
The analysis builds on earlier PEA work carried out for LCDI1 (BAPPENAS 2020) and LCDI2, and incorporates social network analysis, key informant interviews (KIIs) (2024–2025), and a review of the latest available documentation and regulatory developments since 2021. It situates Indonesia’s transition within a complex political economy characterised by decentralisation, sectoral fragmentation, and competing narratives around sovereignty, growth, and sustainability.
The PEA also offers suggestions for the “next phase”, referring to the potential evolution of LCDI into a formal governance mechanism that can strengthen national institutionalisation of the LCD framework, cross-ministerial coordination, vertical integration, data systems, and fiscal alignment.
### Key findings
A new political narrative is reshaping the space for LCD
Under the administration of President Prabowo Subianto (since early 2024), climate policies gain traction when framed as drivers of economic competitiveness, industrial upgrading, energy sovereignty, and fiscal resilience, rather than purely environmental imperatives. This reframing is central for securing political buy-in.
Institutional fragmentation remains the most binding constraint
Despite stronger policy alignment, coordination remains weak across BAPPENAS, Ministry of Environment (MoE), Ministry of Energy and Mineral Resource (MEMR), Ministry of Forestry (MoFo), Ministry of Finance (MoF), Ministry of Home Affairs (MoHA), and provincial governments. Planning, budgeting, implementation, and Monitoring, Reporting, and Verification (MRV) processes are not sufficiently integrated, limiting the impact of LCD policies.
Financing is the core bottleneck
Indonesia requires USD 472.6 billion in climate investment (2025–2035), yet fiscal space is limited, climate budget tagging covers only 3.2% of spending, and subnational governments lack access to climate finance. Domestic carbon pricing could be transformative, but implementation is nascent.
Subnational governments determine implementation success
Provinces and districts control key mandates (land-use, waste, local infrastructure). But they face capacity and fiscal constraints. Vertical alignment between RPJMN, RPJMD, and village planning remains weak.
Data fragmentation undermines accountability and carbon-market readiness
Key relevant data management systems, including SRN-PPI, AKSARA, SIGN-SMART, SIDIK, SIS-REDD+, and ProKlim remain insufficiently interoperable, complicating GHG accounting, carbon trading, and performance-based fiscal transfers.
Behavioural and bureaucratic incentives shape policy outcomes
Ministries respond to Key Performance Indicators (KPIs), budgets, political signalling, and rent structures. Without aligned incentives, LCD remains secondary to sectoral priorities.
### Strategic implications for LCDI2
The current PEA finds that LCDI2’s added value lies not in producing more technical analysis, but in making the system work. Strengthening coordination, fiscal architecture, and data infrastructure are needed to operationalise Indonesia’s low-carbon transition.
LCDI2 should pivot toward five strategic functions:
1. Governance integration – Strengthen existing coordination platforms, especially the NEK Steering Committee and Green Planning Budgeting Framework (GPBF).
2. Fiscal and financial enablement – Connect LCD planning with budget systems, carbon pricing revenue, Green Intergovernmental fiscal transfers (DAK Hijau), and Environmental Fund Management Agency (BPDLH) finance.
3. Vertical alignment acceleration – Institutionalise LCD in RPJMDs, village planning, and provincial budgeting.
4. Building unified MRV and data systems – Deliver AKSARA–SRN-PPI interoperability and support One Data Climate integration.
5. Building a strategy for effective transition narratives – Reframe LCD as an economic and sovereignty agenda, aligned with national priorities.
### Conclusion
Indonesia now possesses a robust policy architecture for low-carbon transformation. But implementation is constrained by political incentives, institutional fragmentation, and financing gaps. The PEA concludes that LCDI2’s final two years present a rare opportunity to consolidate Indonesia’s transition pathway by:
- aligning incentives,
- strengthening coordination,
- improving data and fiscal systems, and
- grounding climate action in national development priorities.
LCDI2 needs to be positioned to help Indonesia move decisively from planning low-carbon development to delivering it at scale.
Opportunities for LCDI2 include supporting institutional coherence, mobilising innovative financing, empowering subnational actors, strengthening data integration, and positioning LCD as a governance mechanism that bridges ambition and implementation specifically through the current climate governance transformation. By linking political economy insights to adaptive management, the current PEA points towards LCDI2 optimal position being both a national reform driver and a developer of models for decentralised climate governance.

## Chapter 1: Introduction and purpose
### Background to the Low Carbon Development Initiative (LCDI)
Indonesia is navigating a fundamental transition as it seeks to reconcile rapid economic development with its long-term climate commitments. As one of the world’s top carbon emitters—and a country deeply dependent on coal, land-use change, and extractive industries—Indonesia’s development model is undergoing structural change. Between 2000 and 2020, these sectors contributed up to 65% of export earnings and more than 25% of GDP (MoF 2023). But they have also driven deforestation, peat degradation, and fossil-fuel emissions, placing Indonesia among the top global contributors to climate change (World Bank 2022).
But the past decade has seen an integration of low-carbon strategies into national planning. This began with the first phase of LCDI (LCDI1) which demonstrated that low-carbon growth could sustain 6% annual GDP growth while significantly reducing emissions.
These dynamics underscore the political economy tension at the heart of Indonesia’s growth model: a dependence on extractive sectors that both sustain and constrain development.
Recognising these contradictions, the Government of Indonesia (GoI) launched the LCDI in 2017 through the Ministry of National Development Planning (BAPPENAS), supported financially and technically by the Government of the United Kingdom through the UK–Indonesia Partnership for Low Carbon Development. The first phase (LCDI1) sought to demonstrate that economic prosperity, social equity, and environmental sustainability are not mutually exclusive but mutually reinforcing.
By 2025, Indonesia entered a new phase. The National Medium-Term Development Plan (RPJMN) 2025–2029, PP 40/2025 (National Energy Policy), and Perpres 110/2025 (Carbon Economic Value) collectively establish a more unified governance architecture that embeds LCD across planning, fiscal policy, sectoral strategies, and carbon markets. The Second Nationally Determined Contribution (SNDC) 2025–2035 builds on LCDI modelling and further institutionalises low-carbon pathways as national commitments.
However, these reforms occur in a changing political context. The Prabowo administration has reoriented the national development narrative around sovereignty, economic resilience, and industrial competitiveness, reframing the political space in which climate policies must operate. This creates new opportunities but also new constraints for the LCD agenda.
LCDI2 operates at this intersection, tasked with transitioning LCD from an analytical-planning initiative into a durable and government-owned governance mechanism capable of supporting whole-of-government delivery across sectors and levels.
Against this backdrop, Indonesia’s journey toward a low-carbon economy is both urgent and complex, demanding coordinated action across governance levels, alignment of diverse interests, and a recalibration of development narratives.
### Purpose of the PEA
This Political Economy Analysis (PEA) provides an analytical foundation for the LCDI2 Process Evaluation in 2025 and future programme design adaptations. Its purpose is to unpack and summarise how power, incentives, political narratives, fiscal constraints, and institutional capacities shape the feasibility of Indonesia’s low-carbon transition. Future PEAs carried out for LCDI2 may benefit from following broadly the same framework.
Specifically, the PEA aims to:
Diagnose structural drivers and constraints
Identify how political, economic, fiscal, social, and governance factors enable or inhibit LCD implementation.
Map power relations and stakeholder incentives
 Understand how ministries, subnational governments, state-owned enterprises (SOEs), and private actors shape policy outcomes.
Analyse multi-level governance dynamics
Assess vertical integration challenges between national targets and subnational implementation.
Generate actionable insights for LCDI2
Translate PEA findings into strategic priorities for the programme’s final two years.
### Analytical framework and approach
The PEA adopts a multi-level governance framework anchored in political economy methodology,[39] emphasising the interaction between structure (institutions), agency (actors), and incentives (political and economic interests). The framework recognises that Indonesia’s low-carbon transition is not purely a technical challenge but a contest of ideas, interests, and power across multiple arenas.
[39] Hudson & Leftwich 2014; DFID 2018
Key analytical dimensions include:
- Political drivers: leadership narratives, electoral incentives, and inter-ministerial coordination.
- Economic drivers: market structures, subsidy regimes, and investment incentives.
- Social drivers: inclusion, justice, and local agency.
- Governance drivers: institutional capacity, accountability, and data systems.
Evidence sources encompass policy reviews (Perpres 110/2025; PP 40/2025; RPJMN 2025–2029), programme documentation (LCDI2 ToR, Learning Review from LCDI1 in the provinces, and so on), KIIs (BAPPENAS, Ministry of Environment and Forestry (MoEF), MEMR, MoHA, MoF, Ministry of Villages (MoV)), and a range of other documentation.
### PEA report structure
The report is organised as follows:
- Chapter 2: National political-policy context and evolving climate governance
- Chapter 3: Historical and institutional evolution of low-carbon development
- Chapter 4: Drivers of LCD - political, economic, social, governance, and emerging technological drivers
- Chapter 5: Critical barriers ranked by impact, including structural and non-structural barriers
- Chapter 6: National-subnational dynamics, fiscal flows, and multi-level governance
- Chapter 7: Implications and strategic recommendations for LCDI2 and FCDO for until 2027
Together, these analyses aim to provide a comprehensive understanding of the incentives, constraints, and opportunities that shape Indonesia’s low-carbon transition, and the practical leverage points where LCDI2 can add greatest value.

## Chapter 2: Political and policy context
### Indonesia’s climate commitments and policy frameworks
Indonesia’s climate governance architecture has matured into a complex yet increasingly coherent system linking international commitments, national strategies, and sectoral policies. The country’s policy evolution from environmental management to full economic integration of climate goals marks a paradigm shift in national development planning.
At the core of this transformation is a 2025 policy triad that operationalises Indonesia’s long-term decarbonisation vision through legally binding and mutually reinforcing instruments:
1. National Medium-Term Development Plan (RPJMN) 2025–2029 (Perpres No. 12/2025);
2. Government Regulation No. 40/2025 (PP 40/2025) on National Energy Policy (Kebijakan Energi Nasional or KEN); and
3. Presidential Regulation No. 110/2025 (Perpres 110/2025) on the Implementation of Carbon Pricing Instrument and GHG Control (Penyelenggaraan Instrumen Nilai Ekonomi Karbon dan Pengendalian Emisi Gas Rumah Kaca Nasional).
These frameworks are strategically aligned with the National Long-Term Development Plan (RPJPN) 2025–2045 and the Second Nationally Determined Contribution (SNDC, 2025–2035). Together these aim to establish a policy continuum linking near-term action with long-term climate neutrality. These work alongside a range of other of other highly relevant policy drivers.
#### RPJMN 2025–2029 (Perpres No. 12/2025)
The RPJMN embeds sustainability and low-carbon growth at the heart of Indonesia’s economic strategy. Unlike earlier plans that treated climate objectives as environmental add-ons, the 2025 RPJMN positions low-carbon development (LCD) as a driver of structural transformation, linking emission reduction targets with industrial policy, infrastructure investment, and human capital development (BAPPENAS 2025).
The RPJMN adopts a “green competitiveness” paradigm, asserting that economic sovereignty and growth are compatible with decarbonisation. It introduces explicit mandates for cross-sectoral integration—requiring energy, land-use, transport, and industrial policies to align with emission reduction targets—and institutionalises vertical coordination through BAPPENAS and the Coordinating Ministry for Economic Affairs (Kemenko Ekon).
Critically, the RPJMN establishes a Medium-Term Climate Investment Framework (2025–2029) and links planning processes to carbon market revenues under Perpres 110/2025. These provisions operationalise fiscal coherence between development and decarbonisation goals.
#### Long-Term Development Plan (RPJPN) 2025–2045
The RPJPN represents Indonesia’s “Golden Indonesia 2045” vision: a high-income, equitable, and sustainable economy by its centenary of independence. It explicitly embeds a net-zero target by 2060 or earlier, with clear sectoral trajectories across 38 provinces (RPJPN 2025).
Unlike previous long-term plans, the RPJPN provides an integrated transition blueprint linking climate policy with competitiveness, poverty reduction, and industrial upgrading. It defines enabling conditions for decarbonisation: energy diversification, circular economy innovation, digital transformation, and governance reform. By doing so, it situates LCDI within a broader national transformation narrative - from resource dependence to green industrial leadership.
The RPJPN also emphasises subnational implementation by mandating provinces to align their Regional Development Plans (RPJMD) with national emission-reduction and adaptation goals. This reflects a deepening of Indonesia’s decentralisation model toward multi-level climate governance.
#### Enhanced NDC and Second NDC (SNDC, 2025–2035)
Indonesia’s Enhanced Nationally Determined Contribution (ENDC) (MoEF 2022) committed Indonesia to a 31.89% domestic and 43.2% conditional reduction in GHG emissions by 2030. The Second NDC (SNDC, MoE 2025) extends the target year to 2035 and aligns these commitments with the Long-Term Strategy for Low Carbon and Climate Resilience (LTS–LCCR 2050) and the RPJPN 2025–2045.
Crucially, the SNDC makes repeated reference to the LCD framework as the analytical, modelling, and planning foundation for its sectoral pathways. The SNDC adopts the two national LCD pathways developed by BAPPENAS as its official mitigation trajectories: Low-Carbon Compatible with the Paris Agreement - Low (LCCP-L) and High (LCCP-H). These pathways, derived from LCDI1 modelling, demonstrate the feasibility of sustaining 6–8% annual economic growth while achieving a national GHG emissions peak by 2030 and progressing toward Net Zero by 2060 or earlier.
Institutionally, the SNDC formalises the distribution of roles across key ministries in a manner consistent with the LCD framework/governance logic:
- MoE retains responsibility as UNFCCC focal point and manages the National Registry System (SRN);
- BAPPENAS integrates SNDC targets into national and subnational development plans (RPJMN and RPJMD), ensuring alignment with LCDI2 modelling and planning;
- MoF supports climate financing through budget tagging, green financing instruments, and fiscal incentives.
Through these provisions, the SNDC fully embeds LCDI2’s analytical methodologies, modelling assumptions, and planning frameworks into Indonesia’s national climate governance architecture, elevating LCDI2 from a technical initiative to the core reference point for national climate policymaking.
#### National Carbon Pricing Policy (NEK) (Presidential Regulation No. 110/2025)
The issuance of Perpres 110/2025 represents a milestone in integrating carbon pricing into Indonesia’s fiscal and regulatory architecture. Replacing Perpres 98/2021, it establishes the NEK which monetises emissions through a hybrid of market and non-market mechanisms.
Key provisions include:
- Articles 55–65 establish carbon trading, performance-based payments, and carbon levies;
- Articles 75–88 create the Sistem Registri Unit Karbon (SRUK), complementing the SRN-PPI system;
- Article 60 re-opens participation in international carbon markets (Paris Agreement, Article 6).
Notably, the regulation omits the earlier carbon tax clause, signalling a political shift toward market incentives rather than direct fiscal imposition.
Perpres 110/2025 operationalises LCDI’s economic logic by linking emissions reduction with fiscal value creation. It mandates a cross-ministerial steering committee (Arts. 93–96) and earmarks carbon revenues for climate finance and adaptation programmes (Arts. 30–54). In doing so, it provides the financial backbone for low-carbon transitions across sectors and governance levels.
#### National Energy Policy or KEN (Government Regulation No. 40/2025)
The new KEN (PP 40/2025) aims to modernise Indonesia’s energy strategy, replacing Perpres 79/2014, and to reflect new technological, financial, and geopolitical realities. It seeks to balance energy sovereignty with decarbonisation, targeting peak energy emissions by 2035 and net-zero by 2060 or sooner.
KEN 2025 emphasises:
- Energy availability, accessibility, affordability, and sustainability;
- Development of domestic value chains for renewables and clean technology;
- Early retirement of coal plants in coordination with Perusahaan Listrik Negara (PLN)[40];
  [40] PLN is the state-owned electricity company in Indonesia.
- Fiscal incentives for green industry, energy efficiency, and electric mobility.
While developed through separate processes, KEN 2025 is highly complementary to the objectives and financing structure of the Just Energy Transition Partnership (JETP). Both frameworks share three core priorities:
Accelerating coal phase-down: KEN is the policy anchor; JETP is the financing mechanism.
- Scaling renewable energy and grid modernisation: KEN sets sectoral targets; JETP mobilises investment to make them feasible.
- Strengthening investment certainty and fiscal incentives: KEN reforms domestic rules; JETP provides external de-risking.
Together, KEN and JETP form a policy–finance ecosystem. KEN provides the national policy direction, sector pathways, and regulatory clarity. JETP mobilises USD 20 billion in blended public–private finance, supporting KEN-aligned priorities such as grid investment, energy efficiency, and coal retirement. Yet the continued uncertainty of JETP financing elevates the importance of Indonesia’s emerging domestic pathways for funding the energy transition.
### Political realignment and evolving climate narratives
The 2024–2025 political realignment under President Prabowo Subianto has significantly reshaped Indonesia’s development narrative. The administration’s “Sovereign Indonesia” agenda emphasises food, water, and energy self-sufficiency, industrialisation, and an ambitious 8% GDP growth target, all framed as essential pillars of national resilience and independence.
Within this framework, the political narrative around LCD is undergoing an important transformation. Under President Prabowo, climate action is most likely to gain political traction when presented not as an environmental imperative but as a strategic enabler of core state priorities - enhancing economic competitiveness, driving industrial growth, strengthening fiscal resilience, and advancing energy sovereignty.[41]
[41] A news-piece titled “Energy sovereignty in motion: Indonesia’s four-year path…” on ObserverID: “As Indonesia enters a new political chapter under President Prabowo … one of the nation’s most defining challenges lies … in the pursuit of energy sovereignty.”
Consequently, LCDI2 must adapt to this evolving political economy, positioning low-carbon strategies as integral to Indonesia’s pursuit of national strength and economic transformation. This means reframing mitigation and adaptation measures as instruments of sovereignty and competitiveness, demonstrating their contribution to industrial upgrading, technology localisation, and energy diversification.
As President Prabowo has articulated, energy self-sufficiency and the transition to renewables are being framed as national sovereignty and industrial growth objectives (80th UNGA Session).[42] At the same time, President Prabowo has articulated ambitious climate and environmental objectives, acknowledging Indonesia’s dual identity as both a major global emitter and a resource-rich country with strategic influence. The administration has signalled interest in asserting global climate leadership via leveraging Indonesia’s forests, carbon markets, and renewable potential as diplomatic and economic assets.
[42] Prabowo said: “We are shifting decisively from fossil-fuel based development towards renewable‐based development. … Our goal is clear: to lift all of our citizens out of poverty and make Indonesia a hub for solutions to food, energy, and water security.” This links low-carbon/renewable development with poverty reduction, and with national positioning (energy & water security) rather than purely “environment”.
Realising these ambitions will require overcoming deep-rooted implementation, financing, and governance challenges. Achieving net-zero by 2050 (if formally adopted), retiring fossil-fuel plants within 15 years, ensuring sustainable land use, and maintaining integrity in carbon markets all demand sustained political will, regulatory consistency, and institutional capacity.
While this sovereignty-oriented policy stance could risk marginalising environmental priorities, it also presents a powerful reframing opportunity. LCD can be redefined as a tool of national resilience - reducing fuel imports, expanding domestic industries, generating green employment, and enhancing fiscal independence through carbon pricing and investment in clean technologies.
To remain relevant in this context, evidence points to a need for LCDI2 to shift its framing from “climate mitigation” to “climate-enabled competitiveness.” By aligning low-carbon initiatives with national development goals, LCDI2 can position climate action as a driver of industrial modernisation and economic sovereignty. This perspective echoes the position articulated by Indonesia’s Special Envoy for Energy and Environment, Hashim S. Djojohadikusumo, who has emphasised pragmatic engagement, technology partnerships, and finance mobilisation as cornerstones of Indonesia’s emerging climate diplomacy.[43]
[43] COP29, 2024
Institutional landscape and coordination challenges
Indonesia’s institutional landscape for low-carbon governance is multi-layered and fragmented. While BAPPENAS leads on planning and integration, implementation depends on coordination across ministries with distinct mandates and incentives as summarised in Table 30.
Table 30: Institutions mandates and influences related to LCDI2
Institution	Mandates and influences
BAPPENAS: High–High	Leads LCDI2, embeds LCD into RPJMN & RPJPN; strong ownership.
MoE: High–High	Leads NDC & SNDC, MRV/SRN, carbon markets, and FOLU; high political stake.
MEMR: High–Med	Energy is core to decarbonisation but political interest fluctuates due to fossil sector pressure.
MEMR: High–Med	Energy is core to decarbonisation but political interest fluctuates due to fossil sector pressure.
MoF: High–Variable	Key gatekeeper for fiscal reforms; interest rises when tied to revenue/tax reforms.
MoHA & MoV: Med–Underutilised	Formal mandate exists, but LCD uptake uneven due to capacity & priority gaps.

Despite the presence of coordination mechanisms such as inter-ministerial committees, overlapping mandates, policy silos, and competing sectoral agendas persist. The dissolution of the National Council on Climate Change (DNPI) in 2015 removed a key high-level coordinating body, leaving no single agency with cross-sectoral authority. This vacuum exacerbates policy incoherence: for instance, while BAPPENAS promotes emission reduction targets, MEMR may prioritise coal for energy security, and the Ministry of Agriculture may focus on productivity at the expense of land-use emissions.
Budgetary dynamics further complicate coordination. The MoF’s dominant role means that only around 3.2% of the state budget is tagged as climate-related, and line ministries often pursue siloed spending priorities. At the subnational level, provinces lack dedicated LCD funds despite signing MoUs with BAPPENAS. Without stronger direction from MoHA, many local governments continue business-as-usual planning, highlighting the need for vertical integration mechanisms that link national objectives with subnational implementation.
To address this, Perpres 110/2025 (Arts. 93–96) established a new Steering Committee for Carbon Economic Value Implementation. This could evolve into a central coordination platform for LCD, including LCDI2. Ensuring synergy with BAPPENAS and the Coordinating Ministry for Economic Affairs (Kemenko Ekon) will be critical.
Other opportunities for enhanced coordination concern the ability of the SNDC to promote and extend the LCDI agenda across three interlinked domains: policy, finance, and data systems:
- The issuance of Presidential Regulation No. 110/2025 on carbon economic value, Government Regulation No. 40/2025 on the National Energy Policy, and Government Regulation No. 26/2025 on Environmental Protection and Management provides the legal infrastructure that embeds LCD principles within sectoral planning and national carbon-pricing architecture.
- The SNDC’s projected investment requirement of USD 472.6 billion for 2025–2035 underscores the need to expand LCD’s blended-finance strategies through public–private partnerships, BPDLH financing, and sustainable fiscal incentives.
- The adoption of the One GHG Data Policy and the integration of systems such as SIGN-SMART, SIDIK, SIS-REDD+, and ProKlim under the SRN and others like AKSARA and APELGATRIK, could create an institutional bridge between planning, monitoring, and financing, mirroring LCDI’s emphasis on evidence-based policymaking.
### Decentralisation, sub-national realities, and village-level opportunities
Indonesia’s decentralisation reforms (Law No. 32/2004; Law No. 6/2014) devolved planning and fiscal authority to local governments. This created policy innovation opportunities but also fragmentation and capacity disparities, so that high-performing provinces such as East Kalimantan, West Java, and North Sumatera have integrated LCD principles into regional plans (RPJMDs), often supported by international partnerships, while lagging regions continue to prioritise short-term economic gains and remain dependent on extractive sectors for fiscal stability.
The dana desa mechanism, allocating up to IDR 70 trillion annually, represents an underutilised platform for local climate action. But targeted guidance is needed from MoHA and MoV about using this mechanism to supplement village funds for financing reforestation, renewable energy, and resilience infrastructure thereby transforming Indonesia’s villages into engines of local adaptation and mitigation.
Despite these challenges, subnational actors are increasingly recognised as pivotal to achieving national climate goals. Strengthening their capacity, incentivising alignment with national targets, and embedding LCDI into local planning processes (RPJMDs and village plans) are essential for bridging the gap between policy ambition and on-the-ground implementation.
### International context and global influence
Indonesia’s low-carbon transition is deeply shaped by its engagement with the global climate regime. Its commitments under the Paris Agreement, participation in initiatives like JETP, and role in platforms such as the G20 not only influence domestic policy direction but also affect access to finance, technology, and diplomatic capital.
International climate finance remains a cornerstone of Indonesia’s low-carbon strategy, with an estimated 83.6% of required climate investment (≈ IDR 4,002 trillion by 2030) expected from private and international sources. Mechanisms such as green bonds, carbon pricing, and blended finance are increasingly central to Indonesia’s approach, while partnerships with countries such as Korea, Germany, and Japan support technology transfer, capacity building, and infrastructure development
At the same time, shifts in global climate finance, such as the funding challenges faced by JETP, underscore the need for Indonesia to strengthen domestic financing mechanisms and build resilience against external uncertainties. Aligning domestic policy priorities with global climate goals, while asserting national development objectives, will be key to Indonesia’s leadership role in the global low-carbon transition. Strengthening domestic financing mechanisms, such as carbon pricing revenues, green sukuk, and fiscal transfers linked to emissions performance, will ensure resilience against external volatility (MoF 2025).
The SNDC should consolidate LCDI’s role as the operational backbone of Indonesia’s low-carbon transition. It situates the LCDI not merely as an analytical platform, but also as a governance framework that connects national targets to subnational action, fiscal reforms, and international cooperation, ensuring that the pursuit of economic transformation remains fully compatible with the Paris Agreement and Indonesia’s long-term sustainable-development vision. Collectively, these instruments form a multi-layered policy ecosystem that connects short-term priorities (RPJMN, NDC) with medium-term strategies (LTS-LCCR, JETP) and long-term transformation goals (RPJPN 2045). Their integration represents a significant advance in Indonesia’s climate governance, embedding low-carbon development within the country’s broader development narrative and institutional machinery.
However, their effectiveness will depend on how well they are coordinated, financed, and implemented across sectors and levels of government. While LCDI provides a unifying framework, implementation depends on sectoral ministries, state-owned enterprises (SoEs), subnational governments, and private actors, each with distinct mandates, interests, and capacities. Strengthening vertical and horizontal policy coherence, enhancing institutional capacity, and aligning incentives for public and private actors will be critical to translating these strategies into tangible emissions reductions and climate-resilient growth.
In 2024, President Prabowo Subianto appointed Hashim S. Djojohadikusumo as his Special Envoy for Energy and Environment. While not publicly documented as part of LCDI’s formal governance arrangements, the Special Envoy has functioned as a high-level diplomatic and resource-mobilisation actor that complements LCDI objectives. At COP29 the Special Envoy led Indonesia’s delegation and was associated with securing a €1.2 billion green financing package with KfW/PLN for pumped storage hydro and transmission projects. A tangible outcome that supports Indonesia’s energy transition priorities.
Public statements from the Special Envoy indicate an emphasis on national sovereignty, scaled investment, and pragmatic engagement with international partners. He has also criticised delayed or insufficient funding under some multilateral initiatives (e.g., JETP), signalling a negotiating posture that prioritises concrete finance and outcomes.
While the Special Envoy strengthens Indonesia’s capacity to mobilise finance and international partnerships, these dynamics suggest action is needed to avoid mixed signals and to optimise coherence. In this sense, LCDI2 should benefit from clarifying how the Envoy’s diplomacy and financing role interfaces with BAPPENAS-led planning, sector ministries, and subnational implementation
Indonesia’s participation in COP 30[44] will be pivotal in demonstrating credible progress on NDC implementation and just transition. Outcomes will influence national ambition in methane, adaptation, and subnational engagement, reinforcing LCDI2’s analytical and coordination roles.
[44] Belem, 2025
### Synthesis of LCDI2’s leverage points within the policy framework
The 2025 policy landscape establishes a robust legal and institutional foundation for low-carbon transformation but requires deliberate coordination, fiscal integration, and subnational empowerment. Table 31 below summarises how key 2025 policies align with LCDI2’s core drivers.

Table 31 Key policies in 2025 and alignment to LCDI2
Policy / Regulation	Primary Focus	Political Drivers	Economic Drivers	Social Drivers	Governance Drivers	Overall Relevance to LCDI2
RPJMN 2025–2029 (Perpres No. 12/2025)	Medium-term development plan embedding sustainability, resilience, and low-carbon growth.	Reaffirms LCDI2 as a national political priority; links climate and economic sovereignty; aligns ministries through BAPPENAS coordination.	Integrates green industrialisation, renewable energy investment, and sustainable infrastructure as growth engines.	Includes just transition and GEDSI (Gender Equality, Disability, and Social Inclusion) to ensure equitable access and benefits.	Mainstreams LCDI2 targets into national and subnational planning and budgeting (RPJMN–RPJMD alignment).	Strategic anchor for LCDI2, ensuring coherence between policy, planning, and fiscal alignment across sectors.
Government Regulation No. 40/2025 (PP 40/2025) on National Energy Policy	Long-term national energy policy to ensure energy security, affordability, and sustainability toward Net Zero Emissions 2060.	Positions energy sovereignty as compatible with decarbonisation; builds alignment between MEMR, DEN, and LCDI2 objectives.	Expands renewable share (19–23% by 2030, 70–72% by 2060); promotes nuclear, bioenergy, EV, and clean-tech industries for green jobs.	Supports energy access and affordability; mitigates social risks via domestic value chains and workforce transition programmes.	Integrates RUEN–RUED; strengthens National Energy Council (DEN) oversight and multi-level coordination mechanisms.	Anchors the energy transition pillar; links industrial competitiveness, energy access, and sustainability outcomes.
Presidential Regulation No. 110/2025 (Perpres 110/2025) on the Implementation of Carbon Pricing Instrument and GHG Control	National carbon-pricing and GHG control framework establishing market-based mechanisms for emission reduction.	Transforms climate ambition into market-based incentives; enhances political legitimacy. through fiscal neutrality.	Creates carbon trading, levies, and performance-based payments; mobilises private and international investment in low-carbon sectors.	Integrates adaptation (Articles 30–54); promotes co-benefits for local communities and climate resilience. in development planning.	Introduces dual registries (SRN-PPI, SRUK) and inter-ministerial steering committee to enhance MRV and transparency.	Serves as the financing and market backbone of LCDI2, aligning emissions control, investment, and policy coherence.

## Chapter 3: Historical and institutional evolution of LCD
### From resource driven growth to sustainability narratives
Indonesia’s developmental trajectory has been profoundly shaped by its vast natural endowments of forests, minerals, and fertile land and the political institutions that govern their extraction and use. Since independence, successive governments have viewed natural resources as the foundation of economic growth, fiscal stability, and social development. But this reliance has also embedded structural dependencies that complicate the transition toward low-carbon development.[45] Table 32 shows a summary of the evolution of LCD in Indonesia’s development strategies.
[45] Booth 2016; BAPPENAS 2019
Table 32: The evolution of LCD in Indonesia’s Development Strategies.
Period	Institutional Milestones for LCD	Implications for LCD
Pre-1998 (New Order)	Centralised control; weak environmental oversight	Growth prioritised over sustainability; rent-seeking entrenched
1998–2014 (Reformation)	Decentralisation and the now defunct National Council on Climate Change (DNPI) established	Democratisation of authority but fragmented governance
2014–2020	MoEF consolidation; Law 23/2014 recentralisation	Improved regulatory coherence and data management
2020–2025 (LCDI1)	LCDI integrated into RPJMN; SRN-PPI launched	Institutionalisation of low-carbon planning
Post-2025 (LCDI2)	Carbon market (Perpres 110/2025); KEN reform (PP 40/2025)	Transition from planning to fiscal and market implementation

### The New Order era (1966–1998) - Centralised growth and environmental degradation
Under President Suharto’s New Order, Indonesia pursued an export-oriented, state-led industrialisation model characterised by centralised control and patronage-based governance. The regime’s developmental strategy hinged on resource rents from timber, oil, and minerals, which financed large-scale infrastructure and social programmes.[46]
[46] Robison & Hadiz 2004
Environmental regulation was weak, and the Ministry of Environment, established in 1978, held little authority relative to economic ministries. Deforestation surged, driven by concessions to politically connected conglomerates. The environmental costs were severe. By 1997, Indonesia had one of the world’s highest deforestation rates, contributing substantially to global GHG emissions (MoEF 2020).
The New Order institutionalised a political economy of resource extraction. Elite networks linked to the presidency controlled lucrative rents. Environmental sustainability was subordinated to growth imperatives and local communities had limited participation or ownership over resource governance.
### Reformation and decentralisation (1998–2014) - Shifting power, fragmented governance
The Asian Financial Crisis (1997–1998) and subsequent fall of Suharto triggered a democratic and administrative transformation. The Reformation Era introduced sweeping decentralisation laws (Law No. 22/1999; Law No. 32/2004), devolving authority for planning, licensing, and resource management to provincial and district governments.
This shift democratised local decision-making but also fragmented environmental governance. Many local governments, heavily dependent on resource-based revenues, prioritised short-term economic gains. The resulting proliferation of permits for mining and palm oil plantations accelerated deforestation and carbon emissions.[47]
[47] World Bank 2010
During this period, Indonesia began to engage more substantively in global climate diplomacy. The ratification of the Kyoto Protocol (Law No. 17/2004) and the establishment of the National Council on Climate Change (DNPI, 2008) marked early institutional recognition of climate change as a policy concern. However, coordination remained weak, with overlapping mandates between DNPI, MoEF, and BAPPENAS.
### Recentralisation and climate governance reform (2014–2020) - Toward policy Integration
Recognising the fragmentation caused by decentralisation, the government enacted Law No. 23/2014 on Regional Governance, which re-centralised key functions—particularly in forestry and environment—to the national level. The merger of the Ministry of Environment and Ministry of Forestry (MoEF) created a stronger regulatory body with unified authority over land use, conservation, and climate mitigation.
At the same time, BAPPENAS advanced a new development paradigm through the LCDI1, integrating climate modelling into national planning.[48] The study’s evidence that a low-carbon path could sustain 6% GDP growth while reducing GHG emissions by 43% by 2030 was transformative. It reframed climate action as economically beneficial rather than constraining.
[48] BAPPENAS 2019
This reframing catalysed a mainstreaming process culminating in the inclusion of LCD in the RPJMN 2020–2024, marking the first time that emissions reduction and environmental sustainability became national development targets (Perpres No. 18/2020).
### Institutional consolidation and transition (2020–2025) - From planning to implementation
The 2020–2025 period saw the emergence of Indonesia’s climate governance infrastructure as a multi-level system. LCDI1 established technical frameworks, modelling tools, and cross-sectoral coordination structures under BAPPENAS. However, implementation challenges persisted due to limited enforcement power and inter-ministerial competition.[49]
[49] EMU 2022; LCDI Learning Review 2023
By 2024, the election of President Prabowo Subianto and the reorganisation of the Coordinating Ministries marked a new political phase. The transition of cross-sectoral coordination authority from Kemenko Marves to Kemenko Ekon and the newly created Kemenko Pangan altered the institutional configuration for climate policy. While this realignment reflects the administration’s focus on economic and food security, it risks diluting environmental priorities unless explicitly reintegrated through LCDI2’s governance structure.
### Institutional evolution of climate governance
Indonesia’s climate governance has evolved from a fragmented, environment-centric model to an integrated system embedded within national development planning. This evolution reflects both global pressures and domestic policy learning.
BAPPENAS remains the policy integrator[50], but implementation relies on sectoral ministries and subnational government. The challenge ahead lies in establishing horizontal coordination mechanisms (across ministries) and vertical alignment (with provincial and local authorities). The Perpres 110/2025 Steering Committee on Carbon Pricing Implementation could evolve into the de facto coordination platform, linking the LCDI2 programme, national carbon pricing, and sectoral transition plans.
[50] A policy integrator refers to an institutional mechanism that harmonises cross-sectoral policies and implementation pathways to ensure coherence and alignment toward shared national objectives.
Indonesia’s decentralised political system has made subnational governments indispensable actors in climate policy implementation. Provincial and district governments, through their development planning agencies (Bappeda / Bappelitbangda), are responsible for integrating LCDI2 priorities into regional development plans (RPJMDs). However, capacities vary widely: some provinces, like East Kalimantan and West Java, have leveraged international partnerships and technical support to advance low-carbon agendas, while others struggle due to resource constraints and competing local priorities
Village governments have also emerged as potential climate actors through the dana desa mechanism, established under Village Law No. 6/2014. In some provinces, the total development funds managed by villages exceed those controlled by provincial governments. This fiscal autonomy offers a powerful platform for bottom-up climate initiatives, such as reforestation, renewable energy deployment, and climate-resilient infrastructure. However, these opportunities remain largely untapped due to limited technical capacity, weak coordination with national ministries, and the absence of clear climate-related mandates for village governments
### Policy evolution and milestones in LCD
Indonesia’s progressive institutionalisation of climate governance can be traced through a series of landmark policies as highlighted in Table 33 below.
Table 33: Key climate governance policies
Year	Policy / Regulation	Relevance to LCDI2 and Low-Carbon transition
2014	Village Law (No. 6/2014)	Introduced dana desa fiscal transfers, enabling localised climate action
2015	Paris Agreement Ratification (Law No. 16/2016)	Anchored international emission reduction commitments
2020	RPJMN 2020–2024 (Perpres No. 18/2020)	Mainstreamed LCD into national planning
2022	FOLU Net Sink 2030 Plan (MoEF)	Set forestry and land-use as the key mitigation sector
2023	JETP Launch	Mobilised climate finance for early coal retirement
2025	RPJMN 2025–2029	Deepened low-carbon integration into national economic policy
2025	PP 40/2025 (KEN)	Updated national energy policy to align with NZE 2060
2025	Perpres 110/2025 (NEK)	Established carbon pricing and market mechanisms
2025	Draft SNDC (MoEF 2025)	Extended NDC targets to 2035; aligned with LCDI2 scenarios

### Emerging paradigms and ongoing challenges
Indonesia’s climate policy transformation is not merely institutional but paradigmatic. Five shifts define its current trajectory:
From environmental management to development planning
Climate policy is now an economic strategy integrated into growth models (BAPPENAS 2019).
From centralisation to multi-level governance
LCDI2 recognises subnational governments as agents of change, though vertical alignment remains inconsistent (MoHA 2024).
From voluntary action to market instruments
Carbon pricing under Perpres 110/2025 represents a fiscal evolution toward performance-based mitigation.
From sectoral projects to systemic transitions
The FOLU Net Sink and KEN reforms connect land-use and energy transitions as interdependent pillars.
From short-term targets to long-term visioning
The RPJPN 2045 and SNDC 2035 embed low-carbon pathways within a 20-year development horizon.
Yet challenges persist, including institutional fragmentation, uneven subnational capacity, and financing gaps continue to constrain implementation. LCDI2 should therefore pivot from analytical integration to institutional consolidation, linking fiscal instruments, data systems, and capacity-building in one coherent framework.

## Chapter 4: LCD drivers - Interactions, priorities, and strategic implications
Indonesia’s low-carbon transition is shaped by the dynamic interplay between political leadership, fiscal and industrial reform, social legitimacy, and institutional coherence. While multiple conditions enable implementation, only a subset of these factors truly drive adoption. That is, they create tangible incentives for government, industry, and communities to pursue low-carbon pathways.
This chapter refines earlier analysis by (1) assessing the relative importance of different driver categories, (2) distinguishing between structural drivers and contextual enablers, and (3) highlighting new domains - technological, environmental, and international - that increasingly influence Indonesia’s pathway toward net zero. Table 34 provides an overview of the types of drivers and their influence on LCD.
Table 34: Relative Importance of Key Drivers
Driver Category	Relative Importance	Summary of influence on LCD
Political	Very High	Presidential commitment and the framing of “economic sovereignty” determine policy momentum. When LCD is positioned as a vehicle for growth, energy independence, and competitiveness, political traction increases dramatically.
Economic	Very High	Fiscal reform, carbon pricing, and green-industry diversification are the operational backbone of transition. Without fiscal incentives and investment, policy narratives remain aspirational.
Governance / Institutional	High	Implementation hinges on coherent institutions and coordination among BAPPENAS, MoF, MoEF, and subnational governments. Weak coherence remains a binding constraint.
Technological	High (Emerging)	Falling renewable-energy and electric-vehicle costs, coupled with domestic industrialisation policies, are creating market-based pressure for LCD adoption.
International	High	External finance (JETP, GCF), trade standards (EUDR, CBAM), and global climate diplomacy shape Indonesia’s fiscal and investment environment.
Social	Moderate-High	Public support, just-transition measures, and social inclusion enhance legitimacy and long-term stability but are not yet strong policy drivers.
Environmental / Ecological	Moderate	Biodiversity conservation, peat and mangrove restoration, and disaster resilience reinforce climate policy but rarely determine core economic choices.

### Political drivers - Framing, incentives, and stability
Presidential and ministerial leadership remain the most powerful enablers of reform. Under President Joko Widodo (2014–2024), the narrative of “green growth through innovation” anchored the inclusion of LCD into the RPJMN 2020–2024, with BAPPENAS assuming a central policy-integration role (BAPPENAS 2019). Meanwhile, under President Prabowo Subianto, the narrative of economic sovereignty and industrial resilience has replaced earlier “green growth” discourse. This reframing creates both risks and opportunities. It could marginalise environmental priorities, but it also allows LCD to be sold politically as a route to self-reliance, domestic manufacturing, and fuel-import reduction.
LCDI2 should therefore emphasise climate-enabled competitiveness, aligning its messaging with the government’s sovereign-development narrative. Policy continuity across administrations, anchored through the RPJMN 2025–2029 and Perpres 110/2025, also ensures that LCD objectives remain institutionally embedded beyond electoral cycles.
### Economic and financial drivers - From fiscal reform to market signals
Economic incentives now form the central axis of Indonesia’s low-carbon transition.
- Carbon pricing under Perpres 110/2025 monetises emissions reductions and channels revenue to climate programmes.
- Green fiscal reforms—including green sukuk, blended-finance facilities, and the planned DAK Hijau intergovernmental transfer—are converting fiscal policy into a climate instrument.
- Domestic finance is evolving: OJK’s Green Taxonomy (2023) and growing ESG mandates push banks toward sustainable portfolios.
- Industrial diversification in electric vehicles, bioenergy, and circular-economy manufacturing links low-carbon policy directly to growth and employment goals.
Together, these mechanisms transform climate ambition into fiscal and market reality—the critical bridge between political commitment and implementation.
### Technological and environmental drivers - Shifting the cost curve
Rapid cost declines in renewable technologies, energy-storage systems, and EV supply chains are eroding the economic rationale for fossil dependence. Indonesia’s mineral wealth (nickel, copper) positions it to capture value from green manufacturing and battery industries. Technological progress thus acts as a self-reinforcing driver. The more competitive low-carbon technology becomes, the stronger domestic incentives are to adopt it.
Environmental drivers, especially the FOLU Net Sink 2030 commitment, biodiversity conservation, and climate-disaster resilience, strengthen the moral and ecological rationale for LCD. As international trade increasingly requires environmental compliance (e.g., EUDR, carbon border adjustments), ecological performance also becomes an economic asset.
### International drivers - Finance, trade, and diplomacy
International engagement remains pivotal. Partnerships such as the Just Energy Transition Partnership (JETP), Green Climate Fund (GCF) projects, and bilateral deals with Japan, Germany, and Korea continue to shape access to concessional finance and technology. But funding delays and donor dependency underscore the importance of building a resilient domestic climate-finance ecosystem.
At the same time, global trade and investment regimes are rewarding low-carbon production. Compliance with Environment, Social, and Governance (ESG) standards and carbon-accounting norms is increasingly essential for market access. LCDI2 should therefore integrate international alignment into its economic strategy, not as external compliance, but as a competitiveness advantage.
### Social drivers - Inclusion, justice, and resilience
Social factors shape the legitimacy and equity of Indonesia’s transition.
- Just transition frameworks are essential to mitigate job losses in coal-dependent regions and ensure fair redistribution of benefits.
- Poverty alleviation, energy access, and public health co-benefits reinforce social acceptance of decarbonisation policies.
- Climate resilience particularly against floods, droughts, and haze has become a lived reality for millions, strengthening bottom-up demand for sustainable solutions.
- GEDSI integration ensures that women, people with disabilities, and marginalised groups participate in and benefit from transition programmes.
These dimensions, while not primary political drivers, are essential for maintaining a durable social contract around low-carbon reform.
### Governance and institutional drivers - From planning to execution
Institutional coherence remains the hinge between ambition and delivery. Indonesia’s planning system, anchored by BAPPENAS, has strong strategic capabilities, yet implementation often falters due to fragmented inter-ministerial coordination. For example, while the SNDC draws heavily on LCD modelling developed for the RPJMN through initiatives such as LCDI2, the actual adoption of these analytical inputs depends on consistent buy-in from other ministries, notably MoE, MEMR, and MoF. The LCD mechanism/architecture developed under LCDI2 therefore needs to reinforce not duplicate existing coordination structures such as the National Coordination Team for Carbon Economic Value and the Green Planning–Budgeting Framework (GPBF), ensuring that modelling, planning, and budgeting processes move in step (BAPPENAS 2025).
Local governments, meanwhile, are indispensable for translating LCD commitments into real-world outcomes but frequently lack the fiscal space, technical capacity, and performance incentives needed for effective action. Integration of LCD indicators into RPJMDs and Renstra SKPD remains uneven. Although MoHA’s Permendagri No. 90/2019 provides a national performance indicator system that could align subnational planning with national emissions goals, enforcement and uptake are limited. Through its provincial pilots and MoUs, LCDI2 can help institutionalise vertical planning instruments, such as updated RAD-MAPI processes and intergovernmental fiscal transfer mechanisms linked to carbon performance, to create stronger incentives for subnational alignment.
Key enablers include:
- The Steering Committee for Carbon Economic Value (Perpres 110/2025 Arts. 93–96) as a strengthened cross-ministerial coordination platform.
- The Green Planning–Budgeting Framework (GPBF) as the integrator linking LCD, RPJMN targets, and fiscal instruments.
- Vertical planning integration via MoHA and MoV to embed LCD indicators and climate-screening requirements into provincial and village-level planning systems.
- Data governance reform that integrates SRN-PPI and AKSARA within a unified One Data Climate Platform to support measurement, reporting, and accountability.
Together, these governance mechanisms shift LCDI2 from a primarily modelling-based initiative into a full-scale management, coordination, and accountability system capable of driving sustained low-carbon development outcomes.
Recognising the distinction between drivers and contextual enablers should help LCDI2 target its interventions toward factors that create incentives for change, not only those that facilitate execution. See a summary in Table 35.
Table 35 Distinguished drivers from contextual enablers
True drivers (adoption incentives)	Contextual enablers (implementation conditions)
Political leadership and framing	Institutional capacity and coordination
Carbon pricing and fiscal reform	Data systems (SRN-PPI, AKSARA)
Green-industry competitiveness	Decentralisation and planning procedures
International finance and trade standards	Stakeholder engagement platforms
Social justice and public demand	Capacity-building and communication strategies

## Chapter 5: Barriers
Indonesia’s low-carbon transition is shaped by a constellation of structural, political, and systemic barriers that constrain the effectiveness of the LCD agenda and the broader LCDI framework. While several challenges are well recognised, including institutional fragmentation, financing gaps, and subnational capacity constraints, this chapter deepens the analysis by:
- identifying the most critical barriers at this moment;
- explaining why each barrier matters; and
- highlighting non-structural barriers (political, narrative, behavioural) that are equally consequential but often overlooked.
### Why barriers matter now
Despite the strong policy architecture established through the RPJMN 2025–2029, PP 40/2025 (National Energy Policy), and Perpres 110/2025 (Carbon Economic Value), Indonesia’s ability to translate ambition into implementation depends on overcoming a narrowing set of bottlenecks. These barriers are not simply technical or operational, they are deeply political, economic, and institutional.
The barriers that matter most today are those that:
- directly prevent implementation of national targets;
- shape sectoral incentives and ministerial behaviour;
- control flows of public and private finance; and
- determine whether subnational governments can act.
Collectively, they explain why Indonesia’s LCD transition remains uneven and why LCDI2 must prioritise governance, coordination, fiscal architecture, and political incentives, beyond technical modelling or planning support.
### Critical barriers ranked by importance
Table 36 provides an overview of the critical barriers and their importance for LCD.
Table 36 Critical barriers and their importance
Critical barrier	Criticality	Why it matters
Institutional Fragmentation and weak coordination	Very High / This is the single most binding constraint. Indonesia’s climate governance remains fragmented across planning, budgeting, sectoral strategies, and MRV systems. Cross-ministerial coordination mechanisms exist but lack enforcement and incentives. BAPPENAS’ role as policy integrator is strong in planning but weaker in implementation phases.	Fragmentation is the root cause behind inconsistent modelling, delayed financing decisions, and contradictory sectoral policies (e.g., coal commitments vs. energy transition plans). Without whole-of-government alignment, LCD remains a planning framework rather than an operational system.
Political resistance and vested interests	Very High / Indonesia’s political economy remains anchored in coal, palm oil, mining rents, and land-based revenue streams. Local governments benefit from royalties, and political actors retain ties to extractive sectors. This produces political resistance to rapid decarbonisation, early coal retirement, and land-use shifts.	Transition decisions are politically negotiated, not technical. Without addressing political incentives, technical solutions, such as LCD modelling or NEK implementation, have limited traction.
Financing gaps and limited fiscal space	High / Indonesia’s climate investment needs for 2025–2035 are estimated at USD 472.6 billion. This is well beyond current budget allocations and donor flows. Only 3.2% of the national budget is climate-tagged, and subnational governments lack fiscal autonomy.	High ambition but low execution persists. Sector ministries often cannot fund transition-relevant programmes; regional governments cannot co-finance implementation; and donor finance (e.g., JETP) faces regulatory and political uncertainty.
Subnational implementation gaps	High / Provinces and districts hold most implementation mandates (land use, waste, transport, spatial planning) but lack stable funding, technical capacity, and institutional clarity. RPJMDs frequently diverge from national climate targets.	Indonesia’s transition will not be delivered in Jakarta. Unless local governments can plan, finance, and execute LCD actions, national targets will remain aspirational.
Data fragmentation and weak MRV systems	Medium-high / Indonesia has multiple data systems, including SRN-PPI, SIGN-SMART, SIDIK, SIS-REDD+, ProKlim, AKSARA, each fulfilling specific mandates but lacking interoperability.	Data inconsistencies undermine carbon markets, climate budgeting, and evidence-based decision-making. Without a unified MRV system, fiscal incentives cannot be tied to verified outcomes.

### Barriers beyond structural constraints
In addition to structural constraints, several non-structural barriers significantly shape the pace and direction of Indonesia’s low-carbon transition, as shown in Table 37.
Table 37 Non-structural barriers and their importance to LCD
Non-structural barrier	Criticality	Why it matters
Narrative and political framing barriers	Medium – high / Climate policies gain traction in the current administration when framed as economic competitiveness, industrial upgrading, or sovereignty, and not environmental protection.	If LCD is framed as “environmental”, it loses political momentum. If framed as “energy sovereignty” or “industrial transformation”, it gains traction.
Behavioural and bureaucratic incentives	Medium / Currently, Ministries are rewarded for disbursement and project volume, not emission reductions or cross-sectoral collaboration. Subnational leaders prioritise visible infrastructure due to electoral incentives.	LCD outcomes remain secondary to the bureaucratic incentive system. Without incentive reform, coordination mechanisms have limited impact.
Knowledge and capacity barriers	Medium / Subnational governments often lack capacity in GHG inventories, project development, MRV, or climate budgeting. Staff turnover after elections erodes institutional memory.	Even well-designed national policies cannot be translated into bankable, implementable projects at subnational levels.
Stakeholder trust and accountability deficits	Medium / Concerns over carbon market integrity, regulatory inconsistency, and delays in transition financing reduce private-sector confidence.	Without trust, investment slows. Carbon markets, blended-finance platforms, and public-private partnerships depend on predictable governance and credible MRV.

### Synthesis of which barriers matter most and why
A tiered view helps identify where reform efforts must focus.
- Tier 1 – Binding constraints (highest priority)
  - Institutional fragmentation
  - Political resistance and vested interests
  - Financing gaps and fiscal constraints
These barriers block implementation regardless of technical capability.
- Tier 2 – Systemic constraints (shape incentives and performance)
  - Subnational capacity and fiscal dependence
  - Data/MRV fragmentation
  - Bureaucratic incentive misalignment
These barriers slow implementation even when political conditions are favourable.
- Tier 3 – Narrative and social constraints (shape legitimacy and demand)
  - Narrative/political framing
  - Social and just transition concerns
  - Limited public and CSO participation
These barriers influence social licence, legitimacy, and the long-term sustainability of LCD.
Indonesia’s most critical barriers to low-carbon development are not only structural, but they are also political, fiscal, and narrative in nature. Institutional fragmentation and vested interests remain the binding constraints. But gaps in subnational capacity, data governance, behavioural incentives, and narrative alignment determine whether the LCD framework can translate into implementation.
To improve LCDI2’s effectiveness, it must function not only as a technical assistance programme but as a governance reform mechanism strengthening whole-of-government coordination, aligning incentives, integrating fiscal architecture, and reframing low-carbon pathways as drivers of resilience, competitiveness, and national sovereignty. Table 38 provides an overview of the barriers most relevant for LCDI2.
Table 38 List of barriers and potential LCDI2 interventions
Barrier	Why it is critical	Underlying cause	Potential interventions
Institutional fragmentation	Prevents coherence across planning–budgeting–implementation	Siloed mandates	Use Perpres 110/2025 Steering Committee as coordination platform
Political resistance	Blocks coal phase-down, land-use reform	Fossil rents, local elites	Reframe LCD as economic sovereignty
Financing gap	Limits implementation of NEK, KEN, NDC	Weak fiscal space; donor uncertainty	Carbon revenue, BPDLH, DAK Hijau
Subnational capacity	National plans fail at local level	Fiscal dependence, technical gaps	LCDI2 sub-national support + MoHA guidance
Data fragmentation	Undermines MRV, carbon markets, fiscal accountability	Non-interoperable systems	Integrate SRN-PPI, AKSARA, and GPBF
Bureaucratic incentives	Ministries not rewarded for LCD outcomes	KPI misalignment	Embed LCD indicators in MoHA & MoF systems
Narrative mismatch	Climate seen as “environmental” not “economic”	Political framing	Sovereignty-based LCD messaging
Just transition gaps	Risk of social backlash	Coal region dependence	National Just Transition (JT) guidelines + re-skilling
Public participation	Weak legitimacy	Low awareness	Expand CSO & youth engagement via LCDI2

## Chapter 6: National vs. subnational dynamics in Indonesia’s Low-Carbon transition
### Introduction - Why vertical dynamics matter
Indonesia’s governance model is deeply decentralised. Since the enactment of Law No. 22/1999 and Law No. 32/2004 on Regional Governance, political and fiscal authority has been devolved to provinces and districts, making local governments pivotal actors in the implementation of development and environmental policies.
This decentralisation has fostered local innovation and accountability but also fragmented national coherence. The political economy of low-carbon development therefore hinges on the ability of the central government to translate national policies into subnational action, aligning incentives, capacities, and fiscal transfers.
LCDI2 must function as the primary instrument for bridging this national–subnational divide — converting planning integration into operational coherence.
### Decentralisation and its policy consequences
#### Administrative Decentralisation
Indonesia’s decentralisation framework grants local governments authority over land-use planning, licensing, and environmental management. However, national ministries retain regulatory control over key sectors such as energy, forestry, and mining. This has created a dual governance system:
- Local governments wield political legitimacy but limited fiscal and technical resources.
- Central ministries hold regulatory power but limited local enforcement capacity.
This structural dualism often leads to policy incoherence, particularly in sectors like forestry, where provincial spatial plans (RTRWP) frequently diverge from national zoning regulations (MoFo 2024). The result is a patchwork of overlapping mandates and inconsistent enforcement.
#### Fiscal Decentralisation
Fiscal transfers (Dana Alokasi Umum – DAU and Dana Alokasi Khusus – DAK) constitute the primary financing mechanism for local governments, accounting for over 60% of regional budgets. Yet these transfers are formula-based, not performance-based, providing little incentive for emission reductions or sustainable planning.
The dana desa (Village Fund, Law No. 6/2014) adds a further layer of decentralisation, providing villages with significant discretionary budgets - IDR 70 trillion annually (MoF 2024). However, without a regulatory framework for climate-related expenditure, most funds are allocated to basic infrastructure.
LCDI2 can leverage these fiscal instruments by linking transfers to low-carbon performance—a strategy consistent with MoF’s emerging Green Fiscal Policy Framework (2025).
### Subnational capacity and political incentives
#### Heterogeneity of Capacity
Indonesia’s 38 provinces and over 500 districts exhibit significant disparities in capacity, resources, and leadership.
- High-capacity regions such as West Java, East Kalimantan, and Bali have integrated low-carbon strategies (RAD-GRK or RAD-MAPI) into their RPJMDs and have piloted climate budgeting tools (BAPPENAS 2024).
- Lagging regions continue to depend heavily on extractive revenues, limiting fiscal flexibility and institutional bandwidth for reform.
These disparities are compounded by staff turnover following local elections and by limited technical support from central ministries. Strengthening the institutional presence of MoHA’s Directorate General of Regional Development and MoV’s village planning units should be key for sustaining LCDI2 implementation.
#### Political Economy of Local Decision-Making
Local elites play a decisive role in determining development priorities. Political incentives are shaped by:
- Short-term electoral cycles, emphasising visible infrastructure;
- Local revenue dependence on resource rents (coal, palm oil, mining); and
- Patronage networks linking business and political interests.[51]
  [51] Hadiz 2022
This dynamic often leads to the prioritisation of projects that boost short-term revenues but undermine environmental objectives. LCDI2 must therefore combine top-down fiscal incentives with bottom-up accountability mechanisms, ensuring that climate-aligned decisions yield tangible benefits for local leaders and constituents.
### Vertical coordination and institutional interfaces
The absence of effective vertical coordination mechanisms has long undermined Indonesia’s policy coherence. While national plans (RPJMN) define strategic objectives, their translation into subnational plans (RPJMDs) depends on guidance and compliance from MoHA and BAPPENAS.
LCDI2 can bridge these interfaces through an inter-ministerial and regional coordination platform, linking BAPPENAS, MoHA, MoF, MoV, and provincial Bappeda offices (Table 39). The National Coordination Team for Carbon Pricing Implementation (Perpres 110/2025) could serve as the institutional anchor for this vertical alignment. Some important opportunities are set out in Table 39.
Table 39 Opportunities for enhanced coordination
Coordination interface	Current status	LCDI2 entry point
National ↔ Provincial planning	RPJMN–RPJMD alignment remains voluntary	Institutionalise LCD indicators in MoHA’s planning guidelines
BAPPENAS ↔ MoHA ↔ Bappeda	Weak communication channels	Establish LCD Working Groups at provincial level
Sectoral Ministries ↔ Local Agencies	Fragmented technical coordination	Create integrated technical assistance missions
MoF ↔ Regional Treasury offices	Limited fiscal guidance on climate allocation	Embed green tagging into subnational transfers (DAK Hijau)

### Subnational innovation and best practices
Despite structural challenges, several provinces and districts have emerged as laboratories of low-carbon innovation (Table 40).
Table 40 Lessons from the LCDI’s priority provinces
Region	Innovation	Outcome / relevance for LCDI2
West Java Province	Integrated climate budgeting and low-carbon indicator framework	Reduced budget fragmentation; improved data-driven planning
East Kalimantan	Low-Emission Development Strategy (LEDS) linked to FOLU Net Sink 2030	Alignment of land-use policy with national GHG targets
North Sumatera	LCDI pilot for integrated energy and land-use management	Demonstrates subnational scaling model for LCDI2
Bali Province	Circular economy and sustainable tourism policies	Illustrates green competitiveness potential
Yogyakarta Special Region	Community-based adaptation through dana desa co-financing	Model for integrating climate resilience into local fiscal policy

These case studies infer that innovation emerges when fiscal autonomy, leadership, and technical support align. Replicating such conditions across Indonesia requires institutionalised vertical support and financial incentives.
### Fiscal decentralisation for climate action
The integration of climate performance into Indonesia’s intergovernmental fiscal system represents one of the most promising yet underdeveloped opportunities for accelerating LCDI2 implementation.
#### Green Intergovernmental Fiscal Transfers (DAK Hijau)
Under MoF’s Green Fiscal Reform Framework (2025), the government is piloting DAK Hijau, a climate-linked fiscal transfer that rewards provinces achieving emission reduction or environmental performance targets. This mechanism aligns directly with LCDI2’s objective of incentivising local climate action.
LCDI2 can support DAK Hijau implementation by:
- Establishing performance indicators consistent with LCDI2 data systems (SRN-PPI, AKSARA);
- Providing technical assistance for subnational MRV and budgeting;
- Developing a pipeline of low-carbon projects eligible for DAK funding.
#### Village Funds (Dana Desa) as Climate Finance
With appropriate regulatory guidance, the Village Fund could become a decentralised climate financing instrument. LCDI2 can collaborate with MoV to:
- Integrate climate activities into Village Development Plans (RPJMDes);
- Develop simple MRV templates for community-led mitigation and adaptation;
- Pilot climate-linked grants for reforestation, renewable energy, and food resilience.
This approach not only strengthens local resilience but also builds political ownership and community legitimacy for Indonesia’s climate transition.
### Multi-Level data systems and accountability
Effective vertical coordination requires integrated data systems linking local and national performance. The One Data Climate Platform, envisioned under Perpres 39/2019 and Perpres 110/2025 (Arts. 75–88), can become the technological foundation for this integration.
LCDI2 could operationalise this by:
- Expanding the AKSARA system for subnational data collection and analytics;
- Synchronising SRN-PPI with regional dashboards to ensure transparency;
- Institutionalising annual provincial climate reports, feeding directly into national MRV systems.
This data integration will enhance accountability and provide a factual basis for performance-based fiscal transfers.
### Synthesis of options for multi-Level Governance for LCDI2
Indonesia’s low-carbon transformation will succeed only if the national framework translates into actionable, financed, and accountable subnational initiatives. LCDI2 should serve as the integrative architecture, linking policy, finance, and data across levels of government. Key strategic directions include:
1. Institutionalise LCD in RPJMDs through mandatory guidance from MoHA and BAPPENAS.
2. Operationalise DAK Hijau as a fiscal incentive for low-carbon performance.
3. Leverage dana desa for local climate resilience and adaptation projects.
4. Strengthen provincial coordination mechanisms (LCD Working Groups).
5. Integrate AKSARA and SRN-PPI into a unified national–subnational data platform.
6. Develop annual performance reports linking fiscal allocation with verified climate outcomes.
By embedding these mechanisms, Indonesia can move beyond symbolic integration toward genuine multi-level governance for low-carbon transformation.

## Chapter 7: Strategic implications and recommendations
This chapter synthesises the key findings and translates them into strategic implications for the final two years of LCDI2. It identifies where LCDI2 can realistically generate impact given Indonesia’s shifting political context, structural governance constraints, and opportunities emerging from recent regulatory reforms.
### Six cross-cutting insights
The PEA surfaces six systemic dynamics that fundamentally shape the feasibility of LCD implementation in Indonesia:
Climate ambition is rising, but political traction depends on narrative framing.
Climate policies succeed when aligned with sovereignty, industrial upgrading, economic resilience, and competitiveness—not environmental imperatives.
Institutional fragmentation remains the single most binding constraint.
The planning–budgeting–implementation chain is misaligned. BAPPENAS integrates LCD into RPJMN, but execution depends on MoF, MoEF, MEMR, MoHA, provinces, and villages.
Financing is the core bottleneck.
USD 472.6 billion is needed for 2025–2035 but fiscal space is limited and subnational governments lack access to finance. Carbon pricing could be transformative, but implementation is nascent.
Subnational government capacity and incentives determine implementation success.
LCD targets will fail without provincial and district alignment, yet RPJMD responsiveness, technical capacity, and fiscal autonomy remain weak.
Data fragmentation undermines MRV, carbon markets, and fiscal linkage.
SRN-PPI, AKSARA, PROKLIM, SIGN-SMART, SIDIK, and SIS-REDD+ remain insufficiently interoperable.
Behavioural, bureaucratic, and incentive-based barriers are as important as structural ones.
Sector ministries and local leaders respond to KPIs, budgets, rents, prestige, and political signalling, and not so much to technical climate evidence.
### Priorities for action under LCDI2
The PEA points towards five priorities for LCDI2 work planning and design.
Priority 1: Strengthen institutional coherence through existing national mechanisms
Fragmented coordination across BAPPENAS, MoEF, MEMR, MoF, and MoHA continues to impede effective implementation of the RPJMN, the National Energy Policy Direction (Perpres 110/2025), and KEN (PP 40/2025). LCDI2 should not introduce new coordination bodies. Instead, it must activate, strengthen, and operationalise mechanisms that already hold legal mandates and political legitimacy, including:
- The Steering Committee for Carbon Economic Value (Perpres 110/2025 Arts. 93–96)
- The Green Planning–Budgeting Framework (GPBF)
- LCDI Working Groups in priority provinces
- MoHA–BAPPENAS alignment mechanisms for RPJMD indicators
LCDI2 can add value by addressing practical gaps within these existing mechanisms, such as Secretariat support, technical and analytical capacity, and coordination tools that connect LCD modelling to GPBF processes and ministry budgets. Strengthening joint workplans, cross-ministerial monitoring, and harmonised reporting will also be essential.
Through this approach, BAPPENAS remains the central policy integrator, ensuring alignment across planning, budgeting, and MRV, while line ministries and subnational governments operate within a coherent, unified low-carbon governance architecture.
Priority 2: Support the building of a unified national–subnational MRV and data architecture
Indonesia’s MRV ecosystem remains fragmented, weakening the credibility of carbon markets, the effectiveness of fiscal incentives, and the accountability required for SNDC implementation. LCDI2 can play a pivotal role in anchoring One Data Climate integration by linking:
- SRN-PPI (national GHG registry)
- AKSARA (subnational climate-performance platform)
- GPBF data flows (planning–budgeting alignment)
- Provincial dashboards and village-level reporting templates
LCDI2 could further contribute by:
- Developing interoperability standards across platforms and ministries.
- Piloting integrated climate-data dashboards in 3–5 provinces as proof-of-concept for national scale-up.
- Building technical capacity for provincial and district climate-data teams to manage and interpret integrated datasets.
Through this intervention, Indonesia gains a unified, coherent data backbone that enables reliable carbon pricing, climate-budget tagging, and performance-based fiscal transfers for subnational governments.
Priority 3: Better Linking LCD to fiscal reform and climate finance architecture
Financing remains the core bottleneck: without fiscal incentives, even the strongest planning tools have limited influence on behaviour or implementation. LCDI2 should prioritise operationalising the fiscal instruments emerging under Indonesia’s evolving climate and carbon governance regime, including:
- Perpres 110/2025 (carbon markets, results-based payments, and carbon levies)
- MoF’s Green Fiscal Policy Framework
- DAK Hijau (green conditional transfers for provinces and districts)
- Village Fund climate-allocation guidance
LCDI2 could deliver high-value support by:
- Designing carbon-revenue allocation models that incentivise sectoral and subnational performance.
- Linking provincial and district performance to DAK Hijau eligibility and formula adjustments.
- Developing a national climate-finance investment pipeline that integrates public budgets, BPDLH financing, and private capital.
- Supporting BPDLH to align funding windows and criteria with SNDC and RPJMN low-carbon priorities.
By enabling these mechanisms, Indonesia’s fiscal system could start rewarding low-carbon performance, creating sustained incentives for ministries and subnational governments to adopt and implement LCD measures.
Priority 4: Support the reframing of LCD as an economic and sovereignty agenda
Climate framing must align with national political narratives that prioritise industrial upgrading, energy sovereignty, and fiscal resilience. Communication is not an accessory, it is a strategic political intervention that determines whether low-carbon measures gain traction or resistance.
LCDI2 could focus on:
- Developing coherent narrative frameworks tailored for sectoral ministries and provincial leaders.
- Framing LCDI2 results as drivers of competitiveness, resilience, and industrial transformation, not just environmental benefits.
- Emphasising job creation, food–water–energy security, and reduced import dependence as core LCD co-benefits.
With this strategic positioning, the LCD agenda becomes politically attractive and directly aligned with the Prabowo administration’s priorities, increasing the likelihood of ministerial buy-in and sustained implementation.
Priority 5: Support the institutionalisation of a Just and Inclusive transition framework
Just transition risks, ranging from job losses in coal-dependent regions to livelihood vulnerability and widening inequality, pose real threats to public legitimacy and political buy-in for the low-carbon agenda. Addressing these risks is not optional, it should be essential for ensuring durable reform.
LCDI2 could embed social equity across its interventions and provide targeted support by:
- Developing national Just Transition Guidelines in collaboration with Ministry of Law and Human Rights (MoLHR) and BAPPENAS to standardise principles, processes, and safeguards.
- Supporting transition roadmaps for coal-producing regions, including economic diversification pathways, skills development, and social protection measures.
- Integrating GEDSI considerations into fiscal incentives and provincial planning instruments, ensuring that benefits and opportunities are equitably distributed.
By institutionalising these measures, Indonesia can advance a low-carbon transition that is socially legitimate, politically resilient, and less vulnerable to resistance from affected communities and local elites.
### Recommended strategic focus
Based on the political economy constraints and opportunities identified, a prioritisation is recommended in Table 41.
Table 41 Prioritisation for interventions
Priority area	Why it matters	LCDI2 potential intervention
1. Institutional coherence & coordination	Enables implementation; addresses fragmentation	Convene; fund coordination; support Steering Committee
2. Fiscal integration & carbon pricing operationalisation	Unlocks finance; aligns incentives	Support MoF + carbon revenue models
3. Data/MRV interoperability	Enables accountability and carbon markets	Fund AKSARA–SRN integration; pilot systems
4. Narrative and political framing	Enhances political traction	Strategic communications + economic framing
5. Just transition & social inclusion	Reduces resistance; ensures equity	JT guidelines; coal-region pilots

It is imperative that LCDI2 shift from analysis to consolidation and operationalisation. This requires moving beyond technical modelling toward embedding low-carbon development within the machinery of government. In practice, this means:
- Positioning the LCDI2 mechanism as a whole-of-government delivery system, not a stand-alone technical project.
- Embedding LCD approaches into budgeting processes, fiscal incentives, MRV systems, and provincial planning cycles.
- Strengthening coordination through existing legal mandates—including the NEK Steering Committee and the Green Planning–Budgeting Framework (GPBF).
- Building national–subnational alignment through performance-based incentives, integrated data systems, and consistent planning instruments.
- Reframing LCD as a driver of economic competitiveness, resilience, and sovereignty, ensuring political relevance and ministerial buy-in.
This transition will allow LCDI2 to consolidate past analytical work into an operational, government-owned mechanism capable of delivering sustained low-carbon outcomes.
LCDI2 may present a rare opportunity to translate Indonesia’s ambitious policy architecture into concrete implementation. The PEA indicates that LCDI2’s greatest value lies in:
1. Making the system work—not adding new systems
2. Aligning fiscal and political incentives with low-carbon outcomes
3. Strengthening provincial delivery capacity
4. Building a unified national–subnational MRV and data architecture
5. Embedding just transition principles into sectoral reforms
6. Positioning LCD as an economic and sovereignty agenda
With focused support from FCDO, LCDI2 can help Indonesia move from “planning low-carbon development” to delivering low-carbon development at scale.

## Selected references
### Primary Laws and Regulations
- Law No. 16/2016 on Ratification of the Paris Agreement.
- Law No. 6/2014 on Villages.
- Law No. 23/2014 on Regional Governance.
- Government Regulation No. 40/2025 on Kebijakan Energi Nasional (KEN).
- Presidential Regulation No. 18/2020 on the RPJMN 2020–2024.
- Presidential Regulation No. 12/2025 on the RPJMN 2025–2029.
- Presidential Regulation No. 110/2025 on Nilai Ekonomi Karbon (NEK).
- Presidential Regulation No. 39/2019 on Satu Data Indonesia.
### National Strategies and Reports
- BAPPENAS (2019). Low Carbon Development: A Paradigm Shift Towards a Green Economy in Indonesia.
- BAPPENAS (2024). LCDI Process Evaluation and Institutional Review.
- BAPPENAS (2025). LCDI2 Design Framework.
- MoEF (2022). Enhanced Nationally Determined Contribution (ENDC).
- MoE (2025). Second NDC (SNDC) Draft Submission to UNFCCC.
- MoF (2024). Climate Fiscal Framework Annual Report.
- MoF (2025). Green Fiscal Policy Strategy 2025–2030.
- MEMR (2025). Energy Transition Outlook 2025.
- MoHA (2024). Guidance for Regional Development Planning (Permendagri 90/2019).
- JETP Secretariat (2024). Indonesia Just Energy Transition Partnership (JETP) Comprehensive Investment and Policy Plan.
### Academic and Policy References
- Booth, A. (2016). Economic Change in Modern Indonesia: Colonial and Postcolonial Comparisons.
- Robison, R., & Hadiz, V. (2004). Reorganising Power in Indonesia: The Politics of Oligarchy in an Age of Markets.
- Unruh, G. (2000). Understanding Carbon Lock-in. Energy Policy, 28(12).
- World Bank (2022). Indonesia Climate Change and Development Report (CCDR).
- DFID (2018). Political Economy Analysis How-To Note.
- Hudson, D. & Leftwich, A. (2014). From Political Economy to Political Analysis. Developmental Leadership Programme.
- UNDP Indonesia (2023). Youth and Climate Perceptions Survey

# Annex 10: EQUALs criteria checklist
Table 42 provides an overview of the EQUALs criteria and how this has been addressed in the report.
Table 42 EQUALs criteria checklist to demonstrate how each criteria has been considered with the report
1 Structure and clarity		How the criteria has been addressed
1.1	The product is accessible to the intended audience (e.g. free of jargon, written in plain English, logical use of chapters, appropriate use of tables, graphs and diagrams).	The evaluation report structure is detailed in section 1. All acronyms are defined and included within the acronyms summary table.
1.2	It is clear who has carried out the evaluation. The roles and responsibilities of the evaluation team are clearly defined.	The evaluation team is described in section 2.3.1 and in Annex 3.
1.3	An executive summary is included, and it can stand alone as an accurate summary of the main product.	The Executive summary is included on page viii.
1.4	The annexes contain – at the least – the original ToRs, the evaluation framework, the use and influence plan, a bibliography, and a list of consultees. Annexes increase the usefulness of the product.	The ToR is provided in Annex 1. Annex 4 provides the evaluation matrix. The use and influence plan is detailed in Annex 5. The evaluation consultees are detailed in the methodology in Annex 3 and a bibliography is provided in Annex 12.
1.5	The product is of publishable quality (e.g., it is well written, clear, and robust).	The EMU has conducted internal quality assurance processes to ensure the quality of this report. The process for quality assurance is detailed on page 99.
2 Context, purpose, scope and objectives
2.1	The product provides or references/links to a relevant and sufficient description of the intervention that has been evaluated. At the least, this should include detail on the intervention’s anticipated impact, outcomes and outputs, target groups, timescale, geographical coverage.	An overview of LCDI2 delivery is included the Introduction in section 1.
2.2	Where relevant and/or funded by ODA, the overview presents gender equality, equity, poverty, and inclusion dimensions of the intervention that has been evaluated.	The inclusion of cross cutting issues has been discussed in section 1.4.2.
2.3	The product describes the intervention logic and/or theory of change.	The Theory of Change is included in Annex 2.
2.4	The product provides a relevant and sufficient description of the local, national and/or international development context within which the intervention was operating. There is an assessment of the policy context for the intervention.	An overview of the context is provided in section 1.3. The political economy analysis provided in Annex 9.
2.5	Where relevant and/or funded by ODA, the ER provides a relevant description of the policy context in relation to poverty reduction, gender equality, environmental protection, and human rights.	Where this is relevant it is included in section 1.4.2.
2.6	The purpose and objectives of the evaluation are clearly articulated. Any divergence from the purpose, objectives and scope set out in the ToR or agreed during the inception phase are identified and justified. Accountability and learning have been considered and it is clear to the reader why the evaluation has been undertaken, how the findings of the evaluation will be utilised, who the target audience are as well as key stakeholders for the evaluation.	The Evaluation objectives and scope are set out in 1.4. Deviations from the TOR are discussed in section 2 and Annex 3.
2.7	The influence and communication plan presented in the Inception Report is summarised with a description of how this has been implemented during the evaluation.	Annex 5 provides the use and influence plan.
2.8	The product explains the timing of the evaluation and clearly acknowledges how the timing of evaluation outputs relate to strengthening the utility of the evaluation.	This is discussed in section 1 and in the learning, use and influence plan.
2.9	The scope of the evaluation is defined as is what aspects of the intervention were and were not covered by the evaluation.	The scope is discussed in 1.4.1.
3 Design and Methods
3.1	The evaluation design, methods and limitations set out in the inception report are agreed and adequately summarised. Where appropriate a fuller description of the intended evaluation design and methods is annexed.	A summary of the design, methods and limitations is provided in section 2 and a more detailed description is provided in Annex 3.
3.2	Any divergence in what was done from what was planned (ToR or IR) are clearly identified and their implications for the credibility and robustness of findings and conclusions clearly explained.	Section 2 provides a summary compared to the ToR and Approach Paper. Further detail is provided in Annex 3.
3.3	Where relevant, the evaluation framework/matrix is clearly articulated indicating the evaluation criteria, evaluation questions, evaluation indicators, data sources and methods. The evaluation framework/matrix is fit for purpose.	The evaluation matrix is provided in Annex 4.
3.4	The evaluation methods are described and justified, and limitations discussed alongside strategies undertaken to mitigate risks. The analytical methods and framework employed are relevant to the methodology and evaluation purpose and questions.	A full description of the evaluation methods is provided in Annex 3. The evaluation matrix in Annex 4 sets out how specific methodologies will be used to answer ELQs.
3.5	Primary and secondary data sources are clearly distinguished, reliable/valid and sampling strategies are explained and justified including sample sizes. The approaches to data disaggregation and triangulation are explained and appropriate for the evaluation.	This information is provided in Annex 3.
3.6	Where applicable access to data sources is provided.	The EMU has provided a list of programme documents that were reviewed in Annex 11. A Bibliography is provided in Annex 12.
3.7	The product discusses any inherent imbalances or biases that interviews, and other data collection may have created, and how these were overcome.	A description of management of bias in interviews is provided in the risk management section on page 97. Any limitations are discussed in section 2 and Annex 3.
3.8	Instruments were tested and validated (e.g., pre-testing of questionnaires).	No questionnaires have been used for this evaluation.
3.9	The participation of stakeholders in the evaluation (design, implementation, feedback, dissemination, and use) is clearly explained. Where stakeholders were not able to participate, secondary data sources were identified and referred to.	A summary of stakeholder participation is provided in section 1.4, with a fuller description provided in Annex 3.
3.10	The evaluation demonstrates alignment with other partners, stakeholders of government in country and demonstrates that efforts have been made to minimise duplication.	Section 2, 1.4 and Annex 3 highlight how the evaluation has made efforts to reduce duplication through aligning to the FCDO annual review timeline, conducting a thorough document review to reduce duplication and minimise stakeholder burden through KIIs.
4 Ethics and safeguarding
4.1	The report describes how the approach adhered to international best practice and standards of ethical conduct in evaluation in sufficient detail, and drew on relevant aspects of FCDO’s Ethical Guidance for Research, Evaluation and Monitoring Activities; the report that demonstrates ethical considerations were implemented throughout the process and the principle of “do no harm” delivered, referencing gender and/or power dynamic considerations, privacy and confidentiality of evaluation participants etc. The principle of “do no harm” is cited.	A summary of ethics and safeguarding is provided in 1.4.4 and more fully described in Annex 3.
4.2	Where vulnerable community members participated, or highly sensitive geographic or thematic areas were covered, the report explains how formal approval from an Ethical or Institutional Review Board were obtained. Safeguarding considerations in terms of data protection and access to personal data and managing data integrity are fully described.	This is provided in Annex 3.
4.3	If there was a reward or compensation structure for participants, or risk of participant burden, there is a discussion and explanation of the effects on results (and biases to results).	This is not relevant for this evaluation.
4.4	The report explains how stakeholders affected by the intervention were and/or will be provided with appropriate access to evaluation-related information in forms that respect confidentiality (beneficiary feedback).	This is provided in Annex 3
4.5	If any digital tools are developed that influenced the delivery of activities or were used for data collection, the report explains how the implementation reflected the Principles for Digital Development (see FCDO Digital Strategy 2018 to 2020: doing development in a digital world) and explains the application of ethical considerations in design and deployment. This includes the approach to managing data integrity and responsible data practices including privacy, confidentiality, and consent.	This is provided in Annex 3
5 Analysis, findings and conclusions
5.1	Information is presented, analysed, and interpreted systematically and logically, and against the evaluation questions and criteria. Where findings are missing against evaluation questions or criteria this is clearly addressed.	The findings in section 3 present each finding and the summary of evidence used. Each sections links to the relevant ELQs.
5.2	The evaluation is transparent about the sources and quality of information, and references or sources are provided. Evidence is clearly and sufficiently triangulated. (Please include comments in the report against specific findings where evidence is considered weak or where evidence and analysis was strong).	At the start of sections 3.1, 3.2, 3.3 and 3.4 a summary of the evidence sources has been provided. Any limitations or gaps in evidence have been highlighted throughout the report.
5.3	Evidence can be traced through the analysis and into findings, conclusions, and recommendations. There is sufficient cross-referencing.	The lessons learned and recommendations link to the relevant findings. Cross referencing has been added throughout the report. Detailed analysis has been added to the findings, and cross referenced to Annexes that contain the full analysis.
5.4	An assessment of the strength of evidence supporting significant findings is included.	An assessment of the evidence used for each section within the findings is provided.
5.5	The analysis includes an appropriate reflection of the views of different stakeholders (reflecting diverse interests). It is disaggregated to show impact and outcomes on the different stakeholder groups.	The Findings includes views of different stakeholders and disaggregation of outcomes.
5.6	Differences of opinion (within the evaluation team, or amongst stakeholders consulted) are fully acknowledged in the findings and conclusions.	Differences of opinion amongst stakeholders has been included where relevant in the Findings.
5.7	Where appropriate the analysis and findings address the cross-cutting issues of gender, poverty, human rights, HIV/AIDS, environment, anti-corruption, capacity building, and power relations.	Gender, capacity building and power relations and discussed within the Findings.
5.8	The relevance of the context (e.g., developmental, policy, institutional) is considered and referenced/reflected in findings.	The EMU has included reference to the context throughout the findings. In particular, the political economy analysis in Annex 9 has been referenced where relevant throughout the findings.
5.9	Findings are useful and they are presented in ways that are accessible to different users.	The findings are presented in summary boxes. An overview of all findings is included in the Executive summary.
5.10	Positive and negative findings are presented.	The findings include positive and negative findings.
5.11	The report indicates where evidence is inconclusive and where there are limitations for gaps in the evidence.	The EMU has highlighted evidence gaps and used limitations to inform LKD products described in section 6.2.
5.12	Unintended and unexpected findings are identified and discussed.	The EMU found no unexpected results, as highlighted in section 3.
5.13	Conclusions provide reasoned judgement based on the evidence presented in the analysis and findings on the strengths and weaknesses of the intervention in delivering its intended results.	The conclusions are provided in section 4 and are based on the findings.
5.14	Conclusions do not present any new information that hasn’t been presented in the findings.	Conclusions in section 4 are based on the Findings and do not add new information.
6 Recommendations
6.1	Recommendations are clearly derived from the evaluation findings and conclusions and are aligned with the evaluation purpose.	Recommendations in section 6 link to the relevant findings, highlight the primary and secondary audience, and provide an indication of the priority.
6.2	Recommendations are relevant to the evaluation and targeted at the intended users.	The primary and secondary audience for each recommendation is provided.
6.3	They are prioritised and clearly presented, enabling individuals or departments to follow up on each specific recommendation. They are actionable and realistic for intended actors to take forward.	The recommendations are prioritised.
6.4	For ODA interventions, recommendations address gender equality, equity, and inclusion issues.	GEDSI is included within the recommendations.
7 Lessons
7.1	Lessons are presented separately with a clear logical distinction between findings, recommendations and lessons learned. OCED DAC defines Lessons as “Generalizations based on evaluation experiences with projects, programs, or policies that abstract from the specific circumstances to broader situations. Frequently, lessons highlight strengths or weaknesses in preparation, design, and implementation that affect performance, outcome, and impact.”	The lessons learned are provided in section 5 and clearly link to the learning questions and findings.
7.2	Lessons are valid (i.e., they have not been generalised from single point findings).	Lessons have been drawn from across the findings.
7.3	Lessons reflect differences between and specific considerations applying to stakeholder/target population sub-groups.	Lessons are differentiated between the national and sub-national level.
7.4	Lessons contribute to wider organisational learning and have the potential for wider application and use beyond the context of the evaluation.	Lessons apply to the delivery of LCDI2, but also for TA policy programmes more generally.
7.5	The mechanism by which lessons will be shared with key stakeholders (across FCDO and beyond FCDO) is clearly documented.	This is included in the Learning Use and Influence Plan Annex 5.
8 Management
8.1	Stakeholders and end-users have been given opportunities to comment on the draft findings, recommendations, and lessons. The evaluation report reflects those comments and acknowledges disagreements.	The process for including stakeholder feedback is discussed in section 1 and Annex 3.
8.2	The report indicates whether the evaluation team was able to work freely and without interference.	This is stated in section 2.3.1
8.3	Any conflicts of interest are openly discussed.	The EMU approach to managing conflict of interest is discussed on page 99.
8.4	Information sources and their contributions were independent of other parties with an interest in the evaluation.	The EMU’s approach to maintaining independence is discussed in Annex 3 and briefly mentioned in section 2.3.
8.5	There is a commitment within the report to understand how the evaluation outputs have been used and monitor the impact of the evaluation findings.	This is provided in the learning, use and influence plan (Annex 5).

# Annex 11: Programme documents reviewed
Table 43 provides an overview of documents reviewed by the EMU in the Process Evaluation.
Table 43 Documents reviewed by the EMU
Document Type	Document Name	Relevant year
Annual Review	AR of LCDI 2 Sept 2022-Sept 2023 AW_IS 300823V2_IS040923 + flq.docx	2022-2023
	LCDI annual review 2017-2018.docx	2017-2018
	LCDI annual review 2020-2021.docx	2020-2021
	LCDI Annual Review 2021-22.docx	2021-2022
	LCDI1 2018-2019 annual review.docx	2018-2019
	LCDI2 Annual Review 2024 _ final.pdf	2024
Business Case	LCDI2 Business Case.odt	2021
Delivery Documents	Nota Dinas Materi SC meeting 060524.docx	2024
	Absensi 7 June 2024.pdf	2024
	Daftar Peserta_Konfirmasi dan Undangan.doc	2024
	Lampiran 1 Daftar Peserta.docx	2025
	SC Meeting Attendance List 7 May 2024 .pdf	2024
	Attendance List SoftLaunching Green Academy 22 May.pdf	2024
	Attd list_TA Signing.pdf	2023
	Absensi 21 May 2024.pdf	2024
	Budget Plan_Taman Nusantara_120924.xlsx	2024
	D2_review of LCD implementation.pdf	2024
	D1_ Inception_Assessment of role of cities_districts in planning and LCD implementation (1)	2024
	CDEL Option Further Details 20240919.pptx	2024
	Communication and Outreach Strategy for LCDI Phase 2_281024.pdf	2024
	Communication and Outreach Strategy for LCDI Phase 2 - 071024.pdf	2024
	ICLEI_LCDI_to Bappenas 130624_Final.pptx	2024
	LCDI 2 Approach to Social Value and COVID-19 v2.pptx	2023
	Social Value in LCDI 2.docx	2023
	Social Value One-pager v1.docx	2024
	Concept Note Low Carbon Development in IKN_080824.docx	2024
	Speech for Pak Pri.docx	2024
	Options for CDEL recipients_DRAFT.pptx	2024
	Concept Note GE Expo Sponsorship(ENG 30May).pdf	2024
	Concept Note GE Expo(19Juni).pdf	2024
	Concept Note GEA_080524.docx	2024
	Concept Note Green Academy	2024
	Information on consortium and OPML suppliers.xlsx	2025
	OUTLINE PENYUSUNAN RPRKBI_D PROVINSI(1) ED.docx
	Photo Green Academy	2024
	TA Signing Photos	2023
	Catatan Studi Kelayakan (Draft 14 Maret 2025)_AAM.docx	2025
	240826_North Sumatera Visit Matrix_FINAL.pdf	2025
	LCDI Finance Manual V1.2 290424.docx
	007.LCDI.SK.08.2024 - SU Undangan Pertemuan Bappeda Provinsi Kepulauan Riau.pdf	2024
	240911_DRAFT_Surat Undangan_Bappeda NTB.docx	2024
	DRAFT Surat Kunjungan Sawahlunto.docx	2024
	Invttn_TA signing.pdf	2023
	Invitation_Participants	2024
	Invttn_Alessandro	2024
	Invttn_Bapak Hayu	2024
	Invttn_Bapak Sodikun	2024
	Invttn_Bapak Zainal	2024
	Invttn_Ibu Amanda	2024
	Invttn_Ibu Brigitta	2024
	Invttn_Ibu Vrilly	2024
	Keynote Speech Menteri GNW-FEB UI_eng.docx	2020
	Keynote Speech Menteri NCE_WRI_eng.docx	2020
	1. Remarks by MUI Chairman_ENG.pdf	2024
	2. Keynote Speech Dep KSDA Bappenas.docx	2024
	241125_MoM_Meeting with Deputy for Maritime and Natural Resources.docx	2024
	241119_MoM_Meeting with MoHA Regional Development.docx	2024
	IBCSD PPT - Kick Off Meeting 30th August 24.pptx	2024
	Presentation INFID LCDI II 020924_INFID.pptx.pdf	2024
	Kick-off presentation_LCDI 2_Prakarsa.pptx	2024
	240819 Presentasi Sumatera Utara.pptx	2024
	Trilateral Meeting_20240909_F2.pptx	2024
	PPT Trilateral Meeting_Carbon Trust	2024
	Trilateral Meeting_November 20241105_V2.pptx	2024
	20250121_Trilateral Meeting.pptx	2025
	20250409_Trilateral Meeting.pptx	2025
	241017_Consortium Meeting_Presentation Kick Off.pptx	2024
	GEDSI_Consortium Regular Meeting_041224	2024
	250122_Consortium Meeting_Presentation	2025
	250604_Trilateral meeting slide.pptx	2025
	1. Wignyo_Paparan Pengantar Green Academy	2024
	2. Isti_Bangkom Pro Hijau	2024
	EN Deputi KSDA_Opening Inisiasi Green Academy 220524	2024
	ENG SDG Academy Indonesia - 21 May 2024	2024
	Paparan Green Academy Setting Context 20240522_FINAL	2024
	10. SC Meeting Presentation 060524 v2.pptx	2024
	230927_MPPN TA signing.pptx	2023
	3. UK-MUI talk 20 May 2024.pptx	2024
	Kick Off Meeting - 30 Agustus 2024.docx	2024
	240909_MoM_Kick-off meeting with ICLEI.docx	2024
	240904_MoM_Kick-off meeting with INFID.docx	2024
	240902_MoM_Kick-off meeting with Prakarsa_ENG.docx	2024
	Meeting Minutes_FGD2_Integration GESI in MEL.docx	2024
	Notulensi FGD 2 - GESI dalam MEL.docx	2024
	BTOR_Informal Engagement MEMR_June 2024.docx	2024
	BTOR_Informal Engagement MoF BKF_June 2024.docx	2024
	BTOR_Informal Engagement MoHA_June 2024.docx	2024
	240820_MoM_Meeting Day 1.docx	2024
	240726_Meeting Rutong.pdf	2024
	240605_MoM_NTB.docx	2024
	240813_MOM Rapat with Bappeda Bengkulu.docx	2024
	240812_MoM_TOR Taman Nusantara.docx	2024
	Minutes of Meeting 7 June 2024_ENG.pdf	2024
	Photo	2024
	240612_Minutes FCDO Bappenas coordination meeting	2024
	240909_MoM_Trilateral Meeting_final	2024
	MoM Trilateral meeting_05112024.docx	2024
	250122_MoM_Trilateral Meeting.pdf	2025
	250410_MoM_Trilateral Meeting.pdf	2025
	250411_Trilateral Meeting 10 April 2025 Follow-up Items_DRAFT.pdf	2025
	20250122_MoM_Consortium Meeting.pdf	2025
	240716_Minutes of Trilateral Meeting_final.docx	2024
	Lampiran SK.T-08989.Dt.3.5.PR.08.06.05.2024 - Meeting Notes_1st SC Meeting.pdf	2024
	Lampiran SK.T-08989.Dt.3.5.PR.08.06.05.2024 - Meeting Notes_Post SC Meeting.pdf	2024
	250617_MoM_Trilateral Meeting.docx	2025
	240522 Peluncuran Inisiatif Green Academy (Notulensi).docx	2024
	Green Academy meeting.docx	2024
	2 Briefing Note and Q&A on LCDI.docx	2021
	240510_RCDS visit minutes meeting.docx	2024
	240515_minutes dry run.docx	2024
	RCDS Visit Photo	2024
	Naskah MoU Kemen PPN & Papua Barat 2019.pdf	2019
	EVALUASI KEBERJALANAN MOU PRK.xlsx
	Naskah MOU KemenPPN & Sumatera Utara 2023.pdf	2023
	Naskah MOU KemenPPN & Maluku 2023.pdf	2023
	Nota Kesepahaman Bersama Pemprov Riau (LCDI).pdf	2020
	RIAU-Adendum MoU PRK.pdf	2020
	10. Naskah MOU KemenPPN & NTB 2023.pdf	2023
	DRAFT Surat Komitmen NTB.docx	2024
	Bengkulu MOU	2023
	DRAFT Surat Komitmen Bengkulu.docx	2024
	Roadmap & Action Plan CE	2024
	LCDI climate governance assessment_National	2024
	Analisis GEI Nasional - Draft GDrive 20240911.xlsx	2023/2024
	Draft Tantangan dan Peluang Budget PRK_May 22.docx	2024
	LCDI climate governance assessment consolidated final 11022024.docx	2024
	Interim Report-Communication and Outreach Strategy for LCDI Phase 2 - 300824	2024
	0. Talking Points for Bappenas Deputy SC Meeting_060524.docx	2024
	Siaran Pers Peluncuran Inisiatif Pengembangan Green Economy_200524.docx	2024
	Siaran Pers Peluncuran Inisiatif Pengembangan Green Economy_200524.docx	2024
	PR IND - Visit by UK Minister Anne-Marie Trevelyan to Indonesia - 29 Sept 2023.docx	2023
	Media Coverage Report_TA signing	2023
	LCDI Procurement SOP V1.1 290124.docx
	TOC and Workplan Event 04122024.pptx	2024
	LCDI WS4 Technology and Innovation Fund_Workshop 1 Draft 04022025 (Clean).pptx	2025
	LCDI WS4 Technology and Innovation Fund_Workshop 2 Draft 07022025.pptx	2025
	6. Province Selection Note Final 150424.pdf	2024
	7. District and City Selection Note Final_290424.pdf	2024
	8. Post Mining District and City Selection Final 280424.pdf	2024
	Buku-7-Profil-Project-LCDI_REV2.pdf	2020
	CDEL Option Further Details 20240919.pptx	2024
	LCDI Factsheet_REV.pdf	2024
	LCDI ITF_Project Selection Criteria 28022025.pptx	2025
	RE_ LCDI Fund.eml	2025
	Social value - WS 4 project selection criteria mapping.xlsx	2025
	Analisis GEI Provinsi - Draft GDrive 20240911.xlsx	2023/2024
	NKB Pemprov Riau (LCDI).pdf	2020
	Nota Kesepahaman antara Bappenas & Pemprov Sulsel (II).pdf	2019
	Pergub Riau No.56 Tahun 2022 tentang PRK.pdf	2022
	RPRKD RIAU.pdf
	RPRKD SULAWESI SELATAN.pdf	2021
	RPRKD PAPUA BARAT.pdf
	LCDI Phase2 framework, 2019.pdf	2019
	4_KOMITMEN KABUPATEN SAMOSIR MENDUKUNG PEMBANGUNAN RENDAH KARBON.pdf	2025
	Stakeholder Assessment Report - Maluku Province.pdf	2024
	Stakeholder Assessment Report - North Sumatera Province.pdf	2024
	11. Agenda for LCDI SC Meeting 060524.pdf May 2024	2024
	2. Final Invite and TOR of SC meeting.pdf (May 2024)	2024
	10. LCDI Presentation SC Meeting 060524.pdf (May 2024)	2024
	SC Meeting_Presentation_FINAL 24112024.pdf (Nov 2024)	2024
	241126_MoM_SC Meeting 2_EN.pdf (Nov 2024)	2024
	2072 UND Rencana Pertemuan Tim Pengarah (SC Meeting) Proyek LCDI Fase 2, Selasa, 26 November 2024 (1)_sign.pdf	2024
	Undangan Komite Pengarah Program LCDI Fase 2.pdf	2025
	250622 Draf SK Komite Teknis LCDI 2.docx	2025
	Draft Ministerial Decree for LCDI Technical Committee.docx	2025
	Suppliers.xlsx
	FW_ Broadening our supplier base.msg	2025
	LCDI2 Implementation ToR.pdf
	LCDI2 MEL ToR.pdf
	ToR GI LCDI_final Inception_New_V2.docx
	Invtn field visit sumut.pdf	2024
	Invtn workshop sumut.pdf	2024
	240911_DRAFT_TOR Kunjungan Provinsi NTB.docx	2024
	TOR Kunjungan Provinsi Bengkulu.docx	2024
	Rundown Sawahlunto.xlsx	2024
	TOR Kunjungan Kota Sawahlunto.docx	2024
	1.[ENG] KLHS_integration_into_RPJMD_review_edited (6).docx	2024
	240813_Terms of Reference_Taman Nusantara_DRAFT_with Bappenas Template.docx	2024
	Terms of Reference_Taman Nusantara_240912.docx	2024
	KAK Narasumber Talkshow Green Investments_GE expo_IDN.pdf	2024
	ToR Green Economy Expo_Circular Talks _Green Financing.docx	2024
	Terms of Reference for Speakers_final	2024
	TOR Workshop NTB 20241120.docx	2024
	Letter of commitment from Samosir District Government to contribute to solar PV pilot	2025
GEDSI	[FINAL 220424] LCDI 2 - GESI Action Plan Development Report.docx
	[FINAL-081223] LCDI2 Desk Review - Gender (Response to comments).docx	2024
	Final Report onf Social Impacts Mentari Central Sumba .pdf	2023
	Mentari-Project-Decentralized-Energy-Access-Presentation.pdf	2025
	150125 GEDSI in LCDI 2_FINAL.pptx	2025
	Draft Social Value One-pager v1.docx	2025
	[250724] LCDI2 GESI Action Plans for Outcome and Output.docx	2024
	GEDSI Assessment & Action Plan_FINAL-for share.pdf	2024
	[DNReview-131224] Draft_Grand Design_GE.docx
	[100225] Pedoman Integrasi GEDSI dalam RPRKBI Provinsi (1).docx	2024
	(250724) GESI Logframe LCDI2.xlsx
	GESI Logframe LCDI2 20240825 v1.xlsx	2024
	[Gender Inputs-161024] OUTLINE PENYUSUNAN RPRKBID PROVINSI_Draft 2 Dewi .docx	2024
	[091224-NGO Women] PPT NTB LCDI.pptx	2024
	[091224-Pemerintah] PPT NTB LCDI.pptx	2024
	[091224-Privat] PPT NTB LCDI.pptx	2024
	[191224] FGD GEDSI NTB Report_FINAL.docx	2024
	GEDSI Strategy_FINAL-for share.pdf	2024
	[180225] GEDSI in LCDI 2_summary.pptx	2025
	[GEDSI-240624] LCDI Theory of Change_300424-formatted.pptx
	FGD_GEDSI pada RPRKBI NTB_11-12 Desember 2024_161224.docx	2024
MEL Documents	17 June meeting.pdf	2025
	20250617 change descriptions as per meeting on 17 June.xlsx	2025
	20250625 WS2 02 06 10.xlsx	2025
	Emerging narratives on WS2.docx	2025
	20250724 old and new numbering change descriptions pathway codes types of evidence.xlsx	2025
	LCDI Draft V.2 Exit Plan May 2025.docx	2024
	240529 LCDI Glossary.xlsx	2024
	LCDI Contract KPIs Q1 FINAL.xlsx	2024
	LCDI Contract KPIs Q2 FINAL.xlsx	2024
	LCDI Contract KPIs Q3 FINAL.xlsx	2024
	LCDI logframe, Oct 2022.xlsx	2022
	LCDI interim phase logframe.xlsx
	LCDI 2 Logframe Restructure 130325.xlsx	2025
	010524_LCDI 2 Logframe Restructure-clean.xlsx	2025
	LCDI 2 FCDO Logframe_March 2024.xlsx	2024
	GESI Logframe LCDI2 20240825 v1.xlsx	2024
	LCDI 2 Logframe Restructure-clean_Baseline_Update_sp_010524.xlsx	2024
	20250414 LCDI 2 Logframe Restructure.xlsx	2025
	20250709 LCDI 2_FCDO MEL presentation.pptx	2025
	OPML - NIRAS meeting discussion around the MEL system-20250812_100418-Meeting Recording.mp4	2025
	20240222 MEL Framework.docx	2024
	19032024_Niras_OPML Meeting_0.1.pptx	2024
	MEL_Plan_161024.docx	2024
	List of contacts for NIRAS.xlsx	2025
	LCDI Organogram with names and title.pdf	2025
	PIRS_121024.docx	2024
	PIRS_040924_v7.docx	2024
	Project Risk Register - A5043 Client 090724.xlsx	2024
	04. Project Risk Register - A5043 Client 101024_final - Copy.xlsx	2024
	250225_Project Risk Register - A5043 updated.xlsx	2025
	Fund Implementation Phase Timeline (Updated 10th Sept).xlsx	2024
	20240223 LCDI TOC framework.docx	2024
	LCDI Theory of Change_300424-formatted.pptx	2024
	NIRAS_0.2_LCDI Workstream Overview Theory of Change_update April 25.docx	2025
	20250430 0.3_LCDI Workstream Overview Theory of Change - FCDO_resp track.docx	2025
	[GEDSI-240624] LCDI Theory of Change_300424-formatted.pptx	2024
	LCDI TA draft VfM framework _ February 2025.docx	2025
	VfM Workplan Data_for NIRAS.xlsx	2025
	4. 4 Year Workplan 300424_24 25.pdf	2024
	5. 4 Year Workplan 300424 25 onwards.pdf	2024
	Copy of Draft workplan for 2025.xlsx	2025
	Workplan Tracker_2024_v4.xlsx	2024
	Workplan for 2025_ FCDO and Bappenas 20250523.xlsx	2025
	LCDI OPML - IBCSD Activities.pdf	2024
	LCDI-INDEF Activities for 2024.pptx	2024
	240826_Maluku Visit Matrix_DRAFT.docx	2024
	120724 NTB_MATRIKS PRKBI_2024.xlsx	2024
	120724 BENGKULU_MATRIKS_PRKBI_2024.xlsx	2024
	120724 SAWAHLUNTO_MATRIKS PRKBI_2024.xlsx	2024
	Workplan Tracker_2024_ Q1.xlsx	2024
	Workplan Tracker_2024_ Q2.xlsx	2024
	Workplan Tracker_2024_ Q3.xlsx	2024
	Workplan Tracker_2024_Q4 Mar.xlsx	2024
	Workplan Y1 24-25_approved SC meeting.xlsx	2024-2025
Delivery Reports	Feasibility Study Report_DRAFT 1.docx	2025
	240826_North Sumatera Visit Matrix_DRAFT.docx	2024
	BTOR of North Sumatera_FINAL_04 Sept 2024.pdf	2024
	BTOR of Maluku_FINAL.pdf	2024
	Back to Office Report Bengkulu 24 Oct 23.docx	2023
	9. LCDI Inception Report Final - Steering Committee Version_ToC for print.pdf	2024
	[041224] GEDSI in Inception Report RPJMN.docx
	20250117_LCDI progress report.pptx	2025
	Monthly progress report July 2024.pptx	2024
	Monthly progress report_October 2024.pdf	2024
	Monthly progress report_November 2024.pdf	2024
	Monthly progress report_January 2025.pdf	2025
	Monthly progress report_January 2025.pptx	2025
	Monthly progress report_February 2025.pdf	2025
	Monthly progress report_March 2025 (1).pdf	2025
	Monthly progress report_April 2025.pdf	2025
	May 2025_monthly progress report (1).pdf	2025
	June 2025_monthly progress report.pdf	2025
	July 2025_monthly progress report (1).pdf	2025
	August 2025_monthly progress report.pdf	2025
	DALA_U~1.PDF	2024
	IBCSD_~1	2024
	ICLEI_~1	2024
	INDEF_~1.PDF	2024
	INFID_~1	2024
	THEPRA~1	2024
	Riau - Provincial Context Assessment Report.pdf	2025
	Final Report_Rapid Assessment of Provincial Election_Maluku.pdf	2025
	Final Report_Rapid Asessment of Provincial Election_Sumatera Utara.pdf	2025
	LCDI Quarterly Report Q1 (Mar-June 24) Redacted.docx	2024
	LCDI Quarterly Report Q3 (Oct-Dec 24) - No costs.docx	2024
	LCDI Quarterly Report Q2 (July-Sep 24) Final_clear.docx	2024
	LCDI Quarterly Report Q4 (Jan-Mar 25) CLEAN DRAFT.pdf	2025
	LCDI Quarterly Report Q1 (Apr-June 25) - Final.pdf	2025
	LCDI1 full report.pdf	2019
	PEA - New Clean_v4.2.pdf	2021
	[260424] PPT LCDI 2 - GESI Action Plan Development Report.pptx	2024
	LCDI - Green Economy Expo - Coverage Report-6.pdf	2024
	Final Report (Draft 1)_Maluku.docx	2024
	Draft 1--Kota Sawahlunto.docx	2024
	Draft_Report LCDI_PSA IPB_Sumut.docx	2024
	Laporan LCDI Provinsi Riau PSA.pdf	2024
	Laporan LCDI Riau_18 Desember 2024.docx	2024
	Draft Tantangan dan Peluang LCDI_12 Des 2024.docx	2024
	LCDI_Draft_Inception Report_Design of the Technology and Innovation Fund_July 2024_BAPPENAS.docx	2024
	LCDI_Fund Design Activities 05 Mar 2024.docx	2024
	LCDI2 Progress Report_Technology & Innovation Fund_21122023.docx	2024
	20250102_LCDI Phase 2 progress and lessons learned_FINAL.pptx	2024
	1. [WCWD LINGUAL] IND-ENG_Final Report Maluku - Rapid Assessment of Implications of Provincial Election Results for Low Carbon Development Initiative.pdf	2025
	1. [WCWD LINGUAL] IND-ENG_Final Report Maluku - Conduct Province-level Context Assessments.pdf	2025
	4. [WCWD LINGUAL] IND-ENG_Final Report Sumatera Utara - Conduct Province-level Context Assessments.pdf	2025
	4. [WCWD LINGUAL] IND-ENG_Final Report Sumatera Utara - Rapid assessment of implications of provincial election resu.pdf	2025
	2. [WCWD LINGUAL] IND-ENG_Final Report Riau - Conduct Province-level Context Assessments.pdf	2025
	2. [WCWD LINGUAL] IND-ENG_Final Report Riau - Rapid assessment of implications of provincial election results for LCDI.pdf	2025
	3. [WCWD LINGUAL] IND-ENG_Final Report Sawahlunto - Conduct Province-level Context Assessments.pdf	2025
	3. [WCWD LINGUAL] IND-ENG_Final Report Sawahlunto - Rapid assessment of implications of provincial election results for LCDI .pdf	2025
	Final Draft - Political Mapping.pdf	2025
	2. Reviu Integrasi PRKBI dan GEDSI di dalam Dokumen RPJMD Sumut 2025-2029.docx	2025
	LCDI2 Change Harvesting October 2023-July 2025.pdf	2025
	LCDI2 Final Scoping Study Report.pdf	2022

# Annex 12: Bibliography
Below is a summary of other literature the EMU has reviewed in the development of this report.
- HM Treasury’s Magenta Book: Central Government guidance on evaluation (2020)
- Indonesia Overview: Development news, research, data | World Bank.
- Leaving No One Behind: Our Promise (2019).
- Low Carbon Development: A Paradigm Shift Towards a Green Economy in Indonesia, 2019.
- Safeguarding Against Sexual Exploitation and Abuse and Sexual Harassment within the Aid Sector (2020)
- UK International Development (Gender Equality) Act 2014
- Women and Girls Strategy 2023-2030, Disability Discrimination Act (2005)
- Perpres Nomor 18 Tahun 2020 - RPJMN (National mid-term planning)
- Perpres No 12 Tahun 2025 - RPJMN (National mid-term planning)
- UU Nomor 59 Tahun 2024 - RPJPN (National long-term planning)
- UU Nomor 17 Tahun 2007 - RPJPN (National long-term planning)
- UU Nomor 25 Tahun 2004 - Sistem Perencanaan Pembangunan Nasional (National development planning system)
- Perpres Nomor 98 Tahun 2021 - NEK (Implementation of carbon economic value)
- Permen LHK Nomor 21 Tahun 2022 - Tata Laksana Penerapan Nilai Ekonomi Karbon NEK (Carbon economic value management)
- UU Nomor 16 Tahun 2016 - Ratifies Paris Agreement
- Laporan Implementasi RAN GRK (Implementation Report of Low-carbon National Action Plan)
- RAN GRK - National Action Plan on GHG Emission Reduction
- RAN API - National Action Plan on Climate Change Adaptation
- RAN API Review - Atmospheric Climate
- RAN API Review - Oceanic Climate
- RAN API Review - Climate Change Hazard
- Permen LHK Nomor 12 Tahun 2024 - PENYELENGGARAAN KONTRIBUSI YANG DITETAPKAN SECARA NASIONAL DALAM PENANGANAN PERUBAHAN IKLIM (Implementation of NDC in climate change)
- UU Nomor 30 Tahun 2007 - Energi
- Permendagri Nomor 86 Tahun 2017 - Tatacara perencanaan pembangunan daerah (Procedure for regional development planning)\
- UU Nomor 23 Tahun 2014 - Pemerintah daerah (Regional Gov)
- Pedoman Pendanaan Anggaran Perubahan Iklim by Ministry of Finance 2021
- Green-Economy-Index-A-Step-Forward-to-Measure-the-Progress-of-Low-Carbon-and-Green-Economy-in-Indonesia.pdf
- Low-Carbon-Development-A-Paradigm-Shift-Towards-a-Green-Economy-in-Indonesia-Policymakers-Summary-2019.pdf
- low-carbon-transitions-in-west-sumatra-indonesia.pdf
- WOW UKaid supply-chain-decarbonisation-with-a-gender-lens.pdf
- UU Nomor 6 Tahun 2023 - Omnibus Law
- Perpu Nomor 2 Tahun 2022 - Cipta Kerja Law revision
- UU Nomor 6 Tahun 2023 - Ratification of Cipta Kerja Law revision
- Permen PPN/Bappenas No 1 Tahun 2024 - Implementation guidelines of SDGs
- UU Nomor 8 Tahun 2016 - People with Disabilities
- Permen PPPA No 13 Tahun 2021 - Community Participation on Women's empowerment and child protection
- Guidelines for Mainstreaming Gender and Social Inclusion in Climate Change Projects - For GCF Project Proponents
- Inpres Nomor 9 Tahun 2000 - Pengarusutamaan Gender (President Instruction on Gender Mainstreaming)
- Perpres Nomor 59 Tahun 2017 - SDGs Implementation Coordination
- Pergub NTB Nomor 43 Tahun 2024 - Roadmap NZE Energy sector
- Pergub DKI Jakarta Nomor 90 Tahun 2021 - RKRPD (LCD and Climate Resilience Planning)
- Pergub Bali Nomor 45 Tahun 2019 - Bali Clean Energy
- RAD GRK Sumsel 2010-2030
- Rencana Perlindungan Dan Pengelolaan Ekosistem Gambut (RPPEG) Provinsi Riau Tahun 2021 - 2050
- Perdasus Papua Barat Nomor 10 Tahun 2019 - Sustainable Development
- 4. Pedoman Penyelarasan Indikator REV2a.pdf
- Bahan Pegangan Studi PRKBI-OPML.pdf
- [251124] Entry Points Draft RPJMN.docx
- [261124] Gender Entry Points - Lampiran I RPJMN.pptx
- Gender in political economy analysis.pdf
- GIPP-Toolkit-Part-One-Guide-June-2021.pdf
- GIPP-Toolkit-Part-Two-Toolkit-June-2021.pdf
- DOKUMEN RENCANA PRKBI NTB 2025 - 2045
- 1. RPRKBID North Sumatera.pdf
- 20250922_Dokumen RPJMD Final_NTB.docx