Programme Completion Review

Title: Yemen Independent Monitoring, Evaluation and Data Analysis (IMEDA)
Final Programme Spend £ (full life): / £13,600,000.00	Review Date:	30 June 2025
Programme Code: 300680	Start Date: 20/07/2018	End Date: 31/03/2025

Summary of Programme Performance

Year	2019	2020	2021	2022	2023	2024	2025
Programme Score	A	A	A	A+	A+	A+	A+
Residual Risk Exposure Rating	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/45839270.odt - Original / https://iati.fcdo.gov.uk/iati_documents/D0005096.odt - Addendum January 2024 / https://iati.fcdo.gov.uk/iati_documents/D0007495.odt - Addendum September 2024 / https://iati.fcdo.gov.uk/iati_documents/D0007496.odt - Addendum December 2024
DevTracker Links to all Log Frames used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/D0005951.xlsx

A. Summary and Overview

This is the Project Completion Review (PCR) of the Yemen Independent Monitoring, Evaluation and Data Analysis (IMEDA). The IMEDA programme set out to provide FCDO’s Yemen Office Network (YON) with third party oversight of its programme portfolio (£87m in FY 23/24, £139m in FY 24/25). The IMEDA programme verified whether results had been delivered at scale by our partners, that delivery met quality standards, and that programmes targeted those most in need. IMEDA also supported YON policy development, generating evidence and analysis to support decision making and advocacy efforts. Monitoring, Evaluation, Research and Learning for Yemen (MERLY), the successor programme to IMEDA, is currently in the inception phase and due to commence implementation in July 2025.

In its lifetime, IMEDA had four components across four partners:
1. Independent Monitoring: In depth data assessments, fieldwork studies and beneficiary interviews for assurance, accountability, and lesson learning. The lead partner was Cowater, supported by Dara and APEX, the latter a Yemeni-based organisation. Following consultation with YON team members, including country-based staff, this component of IMEDA was named ‘Tahseen’, which in Arabic means to enhance, improve, or enrich, recognising the aim of this component to help foster understanding and engagement with partners and beneficiaries.
2. Data Analysis: A range of detailed analysis and presentations of the latest data and thematic analysis on the changing context in Yemen. The partner was ACAPS.
3. Satellite Imagery: High resolution satellite images and use of other advanced technologies to monitor and assess humanitarian and development risks and issues in Yemen. The partner was Satellite Applications Catapult (Catapult).
4. REACH: Support to the Humanitarian cluster system within Yemen to improve the evidence base and analytical capabilities in Yemen, to allow informed strategic planning and decision making. The partner was REACH.

The IMEDA programme commenced in July 2018 and was initially planned to operate for 4 years until July 2022 with a total budget of £9,900,000. Over the lifetime of IMEDA, the Business Case underwent 4 amendments, ultimately extending the end date to 31 March 2025 and increasing the total programme budget to £13,600,000.

In the last financial year, the IMEDA Business Case was amended twice. It was agreed that these final extensions should ensure that YON was provided with the minimum acceptable level of risk assurance and verification of expenditure and results until MERLY could begin operation. Therefore, the independent monitoring output delivered by Tahseen was deemed essential and the only output that continued into FY 24/25. The contract with Tahseen was amended in line with the Business Case amendments. The accountable grant agreements with ACAPS and Catapult concluded on 31 March 2024. The accountable grant with REACH was terminated early on 25th August 2021 due to budgetary constraints.

Major lessons learned and recommendations:
IMEDA logframe impact, outcome and output indicators were predominantly quantitative and measure inputs rather than outputs, which limited how meaningful they were. When designing the logframe for MERLY, indicators should be qualitative as well as quantitative to ensure that FCDO can measure the timeliness, quality and utilisation of activities, as well as the change that they have directly informed.

MEL programmes must be flexible in their design to appropriately respond to contextual changes, FCDO budgetary changes and evolving needs to ensure their work remains targeted and fit-for-purpose. The supplier must be able to quickly reorganise resources to reflect changing priorities and employ an adaptable workplan process. This was a great success of Tahseen under IMEDA.

Individual TPM reports should not be delivered in a vacuum and without considering the overall programmatic vision. In order to implement change as a result of TPM, it is important to have an overall plan/objective at programme-level, trends and recurring issues across different partners should be monitored and the implementation of recommendations should be tracked.

The YON Humanitarian Team (HART) often found TPM concept notes and reports to be lengthy and methodology-heavy, which made it difficult to pinpoint the key aspects of the report that required their attention and follow up. Under MERLY, it is recommended that there is an annual TPM plan for each programme which outlines the general methodology and purpose for TPM. Thereafter, individual TPM reports are focused on the findings and actions, with a clear executive summary for quick reviewing.

Under MERLY, a recommendations tracker should be developed by the supplier to monitor recommendations from TPM reporting to ensure they are followed up on. At a minimum this should track the recommendation, the latest progress made towards the recommendation, and the person responsible for it.

It is essential that monitoring activities for YON cover both the North and South of Yemen as far as possible to reflect the wide coverage of programme operations. During the inception phase of MERLY, FCDO should agree a workplan for TPM with the MERLY supplier, which includes plans for North/South coverage so approvals can be scheduled far in advance, whilst taking into account security measures required for collecting data in the North.

Despite Catapult offering up various suggestions for potential analysis (in addition to the IMEDA SRO requesting ideas from programme teams), there was limited demand for imagery/analysis. Future programming should ensure that YON programme teams fully understand the remote monitoring and data analysis capability available in the Yemen context, in order to make informed decisions regarding what would be useful for their programme.

How this report was conducted:
This PCR was drafted by the IMEDA Senior Responsible Owner (SRO) and programme support officer and has been signed off by YON’s Development Director. The conclusions of this review have been made with reference to formal quarterly reports from IMEDA partners, partner discussions on progress and performance, as well as feedback from HART. The PCR covers performance against the IMEDA logframe across the lifetime of the programme. Output 1 (Tahseen) was the only output still operating in the last year (FY 24/25) and therefore the output 1 section has a particular focus on last year’s performance which has not previously been covered by an Annual Review. Scoring has been calculated based on the final year of operation for each output against the logframe.

Actions following approval of this report:
Once approved, this PCR should be uploaded to DevTracker and stored appropriately on Microsoft Teams. The lessons learned and recommendations should be considered as part of the MERLY inception phase to ensure that MERLY builds on the effectiveness achieved by IMEDA and does not perpetuate the same inefficiencies.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£9,900,000.00	£13,600,000.00
Timeframe	20/07/2018	31/03/2025
Outcomes	Increased use of robust needs analysis by FCDO Yemen and other humanitarian actors to enable evidence-based decision making to inform strategic planning and operational response as well as supporting independent monitoring and strengthening accountability.	In the final year of implementation, 115 key humanitarian meetings, forums or products referenced ACAPS-produced analysis, which in turn enhanced situational and thematic understanding by humanitarian actors and informed strategic planning and response. Humanitarian actors included; USAID, IOM, the US Congressional Research Service, the World Bank and the UNOCHA Resident Coordinator's office.
	FCDO and FCDO-funded partners utilise evidence, findings and recommendations produced by Tahseen TPM activities to enable evidence based programmatic decision making and inform and improve project delivery and M+E capacity.	Tahseen was instrumental in developing key FCDO Yemen logframes, providing direct support to partners to develop their individual logframes and theory of change and aligning this with FCDO approaches. All TPM reports included recommendations which were discussed and agreed with partners in Action Based Learning Workshops to ensure they were appropriate and actionable.
	Increased use of satellite derived information by FCDO Yemen, FCDO Yemen programme partners and across HMG to enable evidence-based decision making to inform strategic planning and operational response as well as supporting independent monitoring and strengthening accountability.	In the final year of implementation, 21 key FCDO Yemen, FCDO Yemen programme partner and HMG meetings, forums or products referenced Catapult-produced satellite derived information.
	Improved evidence base and increased analytical capabilities in Yemen, enabling better decision making and informing strategic planning, programming and response monitoring efforts’	This indicator was closed after FY 21/22 when the REACH programme component was terminated.

Overall assessment of programme outcomes, sustainability and VfM:

The IMEDA outcome indicators have been achieved. However, the extent to which they were meaningful was limited. The majority of indicators were focused on the number of meetings/forums held by the various implementing partners which referenced IMEDA products, measuring inputs rather than outputs. This does not measure the quality or usability of the products, or to what extent they have led to appropriate change, which is essential in determining if the impact of strengthening portfolio delivery has been achieved. When designing the logframe for MERLY, the impact and outcome indicators should be qualitative as well as quantitative to ensure that FCDO can measure the timeliness, quality and utilisation of activities, as well as the change that they have directly informed.

Milestones for outcome indicators 1 and 3 continued to be met or exceeded as products from ACAPS and Catapult were continually cited in meetings, forums and products from a range of humanitarian actors. The usefulness of this outcomes data could be improved by identifying what decisions were made as a result of this increased evidence base. Outcome indicator 2 relates to output 1 (Tahseen). Tahseen was instrumental in developing key FCDO Yemen logframes, providing direct support to partners to develop their individual logframes and theory of change and aligning this with FCDO approaches. An example of this capacity building was their support of SFD’s outcome data collection through facilitating a joint monitoring visit where they were successful in upskilling SFD staff and improving their M&E processes. In addition, all TPM reports included recommendations which were discussed and agreed with partners in Action Based Learning Workshops to ensure they were appropriate and actionable. However, the process for monitoring the completion of these was not formalised. Under MERLY, a recommendations tracker should be developed by the supplier to monitor recommendations from TPM reporting to ensure they are followed up on and that accountability is clear.
The IMEDA programme delivered against all of the VfM indicators outlined in the Business Case, as covered later in this PCR. IMEDA provided independent oversight of programme delivery and programme results, acting as a crucial oversight, assurance, and risk management function for YON, which does not have a permanent presence in Yemen. IMEDA helped to improve the effectiveness, quality, and value for money of our programmes and policies, particularly vital at a time of competing global pressures on resource. Tahseen monitoring visits were successful in providing assurance and accountability of YON programme activities. They have reported cases of fraud, outlined food security trends in targeted regions, discovered examples of good practice by partners that YON were unaware of, and compared practices of different partners. Additionally, IMEDA-generated analysis was referenced in numerous media outlets and by FCDO Ministers, other donors, and the UN.

Summarise the programmes theory of change and results framework, including any changes to outcome indicators:

The IMEDA programme Theory of Change (ToC) is shown below:

The IMEDA ToC was not updated during the lifetime of the programme and remains the same as the ToC detailed in the initial Business Case. The expected impact of the programme was to strengthen portfolio and programme delivery and performance. Improvements in the quality of YON’s programming should result in improved development outcomes. This in turn was expected to strengthen public and ministerial confidence in YON programming.

There were also no updates made to the logframe impact or outcome indicators over the lifetime of the programme. The overall impact and outcome statements remained relevant. However, to ensure that the indicators within these were meaningful, they should have been more thoroughly reviewed and updated where necessary. This process would benefit from the support of a MEL advisor to ensure that revisions are appropriate. YON has not had a permanent MEL advisor in post for over a year but could engage wider MENA capacity. The main reason for the impact and outcome indicators not undergoing an in-depth review during implementation was the delay in the commencing of MERLY. As MERLY inception was pushed back gradually, it was believed that a refresh of the indicators would not be worthwhile at that late stage of the programme and therefore, only the outputs were updated. However, MERLY was ultimately delayed quite significantly that, in hindsight, perhaps a refresh could have been useful.

## C: Detailed Output Assessment

Output Number and Title	Assessment and verification of the results of FCDO projects, assessment of partner’s monitoring and evaluation (M&E) systems, and development of thematic reports aligned to FCDO Yemen priorities (Independent Monitoring – Tahseen)
Output Score	A
Impact weighting (%)	40%		Impact weighting revised since last AR?	N/a

Output Indicator		Starting Target	Final Logframe Target – March 2025	Final Result / Achieved
1.1 – Number of light touch reports (LTRs) completed to agreed standards, specifications, timeframes and signed off by FCDO		5 points	23 points	Met: 26 points
1.2 – Number of in-depth reports (IDRs) completed to agreed standards, specifications, timeframes and signed off by FCDO		3 points	21 points	Met: 24 points
1.3 – Number of sector-specific reports delivered to agreed standards, specifications, timeframes and signed off by FCDO		This indicator was merged with indicator 1.6
1.4 – Number of IP and DP monitoring and evaluation data follow up assessments completed to agreed standards, specifications, timeframes and signed off by FCDO		1 assessment	0 assessments	N/A: 0 assessments
1.5 – Number of IP and DP monitoring and evaluation data assessments completed to agreed standards, specifications, timeframes and signed off by FCDO		0 assessments	2 assessments	Met: 2 assessments
1.6 - Number of reviews / evaluations / thematic reports completed to agreed standards, specifications, timeframes and signed off by FCDO.		0 points	11 points	Moderately exceeded: 19 points
1.7 - Number of dashboard briefs based on call centre data delivered to FCDO / **Added to Logframe following 2022 AR		20 briefs	0 briefs	N/A: 0 briefs

Tahseen scores an A as part of this Programme Completion Review as all final milestone targets were met, and one was moderately exceeded. The reporting period that Tahseen has been scored against in this review is April 2024 – March 2025. However, the entirety of the Tasheen contract period (2019-2025) will be summarised below.

Indicators 1.1 and 1.2: In the last year, third-party monitoring (TPM) activities were completed for all appropriate Food Security Safety Net (FSSN) and Women & Children (W&C) programme partners at least once. Tahseen delivered two reports each for the Social Fund for Development (SFD) and the BRIGHTLY consortium, collecting data in both the North and South Yemen. Three activities were completed for World Food Programme (WFP) over the year, focused solely on the South to correspond with FCDO funding locations. In addition, the first TPM activities for the W&C programme were completed in the last year in South Yemen. Tahseen delivered a monitoring activity to assess the services, data management and reporting, and facility conditions amongst both UNICEF and RISE consortium supported health facilities. Tahseen also completed a monitoring activity for IOM, which assessed the access, quality, and coordination of healthcare and protection services for migrants in one migrant response point and three health facilities in South Yemen. This was a significant increase in the number of TPM reports produced compared to the previous year and provided YON crucial insight into how our programmes were delivering. In addition, it was a great success that three monitoring activities were completed in North Yemen during a year with a particularly volatile security situation. One additional TPM report on WFP was completed compared to the target in the initial logframe, however, the logframe was not updated multiple times during the year to reflect the workplan updates. FCDO feel like we received exactly what was asked for regarding the number TPM reports delivered and therefore indicators 1.1 and 1.2 are considered as ‘met’.

Indicator 1.5: In terms of capacity building, Tahseen delivered workshops with FSSN partners BRIGHTLY and SFD regarding how to measure outcomes for Village Savings and Loan Associations (VSLA). The purpose of the workshops was to agree upon a common outcome indicator for the VSLA and livelihoods activities, including how to align and maximise analysis and reporting. The result of this was agreed outcome indicator language, with considerations built in to account for the differing complexities of the two partners, which is outlined in Tahseen’s post-workshop report. In addition, Tahseen was asked to work closely with SFD to produce a draft Theory of Change (ToC) and ensure that SFD had the capacity to take this over going forward. Alongside the draft ToC which was produced cooperatively with SFD, Tahseen produced a report which documented their thinking behind this.

Indicator 1.6: Tahseen also delivered a number of other products in the last year. The FSSN geo-mapping tool was updated twice to ensure that the data was kept up to date and Tahseen responded to an urgent request for a Due Diligence Assessment to be completed for a new Integrated Security Fund (ISF) partner. Tahseen also delivered two focused reports on themes requested by HART, one looking at Muhamasheen in Yemen and the other was a review of Women’s Rights Organisations vs Women Led Organisations. In the year, Tahseen also delivered two synthesis reports for FSSN which analysed the trends and issues that they identified through their monitoring across all three FSSN partners. HART is keen for the monitoring of trends to continue under the new MERLY programme as it’s essential that TPM reports are not delivered in a vacuum and without considering the overall programmatic vision.

Over the lifetime of IMEDA, Tahseen remained flexible and tailored their activities and reporting to reflect FCDO’s evolving needs to ensure their work was targeted and fit-for-purpose. An annual workplan was agreed between Tahseen and YON teams at the beginning of each financial year, however, this was updated on a regular basis to respond to changing priorities. Tahseen was able to reorganise resources efficiently to support the timely delivery of the newly agreed activities whilst maintaining consistent fee rates and activity unit rates and keeping within the annual budget allocation. Tahseen also responded professionally to a number of contract amendments (three in 2024 alone, due to delays in MERLY mobilisation) which required a quick turnaround in proposing and agreeing workplans before implementation. As there was continued uncertainty regarding when MERLY would commence, in 24/25 Tahseen was forced to operate under a reduced 3–6-month workplan model rather than the usual annual workplan which made the forward planning of activities more difficult, particularly for TPM in the North which required permit approval from Yemeni authorities. In 22/23, Tahseen combined Light Touch Reviews (LTRs) and In-Depth Reports (IDRs) to achieve better value. These consolidated monitoring activities represented a much broader scope from previous assessments, combining the number of site visits and the number of people surveyed to correspond with at least 3 IDRs and 3 LTRs and combined both field and call centre activities. However, the logframe was not updated to consequently combine indicators 1.1 and 1.2.

Over time, Tahseen increased overall engagement with YON stakeholders and built strong relationships with programme partners who welcomed Tahseen’s capacity building support and openly shared data and information with them. This was a gradual process which was aided by Tahseen’s involvement in FSSN Governance Meetings and the facilitation of post-monitoring activity Action Based Learning Workshops with partners where findings were discussed, and actions agreed prior to submitting a final report to FCDO. Monthly update calls between Tahseen and HART were set up to allow Q&A and the sharing of findings ahead of report submission. These trailed off towards the end of the contract but were useful when they happened.
Although communication between Tahseen and YON programme team’s improved over time, it was not perfect. HART felt that concept notes often went through multiple rounds of revisions in addition to a call to discuss objectives. This resulted in a rather cumbersome inception process, adding time to both Tahseen and FCDO’s schedules, which could have been prevented through clearer communication from the start. This process should be looked at under MERLY to identify efficiencies.

Lessons learned through this output:
MEL programmes must be flexible in their design to appropriately respond to contextual changes, FCDO budgetary changes and evolving needs to ensure their work remains targeted and fit-for-purpose. The supplier must be able to quickly reorganise resources to reflect changing priorities and employ an adaptable workplan process. This was a great success of Tahseen under IMEDA.

Individual TPM reports should not be delivered in a vacuum and without considering the overall programmatic vision. In order to implement change as a result of TPM, it is important to have an overall plan/objective at programme-level, trends and recurring issues across different partners should be monitored and the implementation of recommendations should be tracked.

Recommendations:
HART often found TPM concept notes and reports to be lengthy and methodology-heavy, which made it difficult to pinpoint the key aspects of the report that required their attention and follow up. Under MERLY, it is recommended that there is an annual TPM plan for each programme which outlines the general methodology and purpose for TPM. Thereafter, individual TPM reports are focused on the findings and actions, with a clear executive summary for quick reviewing.

Under MERLY, a recommendations tracker should be developed by the supplier to monitor recommendations from TPM reporting to ensure they are followed up on. At a minimum this should track the recommendation, the latest progress made towards the recommendation, and the person responsible for it.

It is essential that monitoring activities for YON cover both the North and South of Yemen as far as possible to reflect the wide coverage of programme operations. During the inception phase of MERLY, FCDO should agree a workplan for TPM with the MERLY supplier, which includes plans for North/South coverage so approvals can be scheduled far in advance, whilst taking into account security measures required for collecting data in the North.

Output Number and Title	Regular independent contextual and humanitarian analysis produced for FCDO Yemen and the wider humanitarian community (ACAPS). This component ended 31/03/2024.
Output Score	A++
Impact weighting (%)	30%	Impact weighting revised since last AR?	N/a

Output Indicator	Starting Target	Final Logframe Target – March 2024	Final Result Achieved
2.1 - Number of quality and timely analytical products published on a consistent basis.	5 products	78 products	Moderately exceeded: 83 (106%)
2.2 - Number of organisations utilising Analysis Hub crisis data repository and number of humanitarian forums/meetings and products that reference/use the repository.	10 organisations	200 organisations contributing to, or utilising the data repository to enhance their understanding and build a common operational picture of the crisis in Yemen	Substantially exceeded: 1068 (534%)
2.3 - Number of scenario building exercises and scenario/outlook/forecast analytical products produced, and number of humanitarian analysis programmes held per year. (This indicator was amended during 2023 to reflect reduced funding)	1x workshop / 1x analysis products / 1x training programme	10 organisations reaching out to ACAPS for additional information and analysis	Substantially exceeded: 17 (170%)
2.4 - Number of donor organisation briefed on ACAPS methodologies, and identified potential collaboration for future initiatives	3 donor organisations briefed	10 donor organisations are briefed on ACAPS methodology and identified potential collaboration for future initiatives.	Substantially exceeded: 16 (160%)

The ACAPS agreement under the IMEDA programme concluded on 31/03/2024. Therefore, no activities were completed in FY 24/25 for this output.

The ACAPS Yemen Analysis Hub informed evidence-based decision making and response planning in Yemen through timely, quality, cross sectoral and gender sensitive thematic and risk products. It achieved this through:
1. Producing regular independent humanitarian analysis products on Yemen, including trends and thematic deep dive reports, as well as regular Crisis Insight outputs.
2. Developing forward-looking analysis to help humanitarian decision makers plan ahead, including scenario workshops, ad hoc anticipatory analysis and risk reports.
3. Providing training and technical advice to partners and key stakeholders working on Yemen, including humanitarian clusters.
4. Identifying, accessing, storing and publicising key data sets in a usable format for humanitarian actors and researchers working on Yemen.
ACAPS consistently delivered high-quality analysis for FCDO during the IMEDA programme agreement. This analysis informed our policy and advocacy efforts. The key outputs included:

Social Impact Monitoring reports (SIMP): Quarterly SIMP reports. These reports identified events and themes which were most likely to have a social impact and covered such aspects as challenges and barriers to health care, the impact of social media disinformation campaigns against international humanitarian organisations. These reports aimed to enrich the understanding of the different social groups within Yemen, and those most vulnerable to protection concerns. ACAPS presented the key findings from their SIMP reports back to YON and facilitated Q&A sessions.

Food Supply chain report: This analysis provided updates on the nature and structure of Yemen's food market and the role that various factors (responders, policies, global dynamics, etc.) play in determining food prices. The report updated on the main food supply chains and cost drivers in the country and highlighted any changes that occurred at the international and local levels between January 2021 and June 2023. The report also used data analysis and modelling of wheat and fuel cost drivers using the YETI cost driver monitoring tool (CDMT) initiative. This report also analysed the costs of bulk wheat imports to Yemen from loading ports in major exporting countries to Yemen. In addition, the report added extra value by demonstrating how ACAPS analysis could integrate data from the YETI project (under the FCDO AFFY business case and currently being transferred to MERLY) and the SDG joint research project under the UN consortium.

Flash Analysis – A number of flash analysis reports were delivered, the most recent being; (i) analysis of the Marib gas sales ban, (ii) existing practices of the traditional, cultural practice of Mahram, (iii) the Increased DFA intervention in the Private sector, and (iv) the causes of low vaccination rates. This latter analysis investigated the causes, challenges and impacts of low vaccination coverage on various population groups within Yemen, with the aim of guiding decision making and programme development. The report was shared across the donor community, including ECHO, BHA and SDC. Topics for the Flash Analysis reports were chosen following discussions with YON colleagues and were based on topics where FCDO had an information gap and ACAPS were capable of providing such information.

ACAPS analysis, produced under the IMEDA programme, was used to support other projects that enhance the humanitarian response in Yemen, including projects funded by BHA & ECHO. Analysis on Gender and Protection, Food Security and the Economy of Yemen were all referenced by external organisations such as the World Bank, The Sana’a Centre, UNOCHA and USAID.

Demand for ACAPS products remained high throughout the agreement. More than 10,000 visitors to the website and over 4,000 products downloads during the 2023/24 reporting period. Product forwarding from the website occurred almost 5,000 times during the same period. ACAPS were referenced 10 times per quarter, on average, in media forums. ACAPS reports were also mirrored in local media in Yemen several times.

Lessons learned through this output:
Milestone targets were increased following each Annual Review. However, the targets were increased in relation to the previous targets, rather than against the actual results achieved, which often meant that the new targets were not as challenging as they could have been.

Recommendations for future programming:
Future programming should take actual results into account at each Annual Review, when setting new targets, to ensure they provide the partner with an increased level of stretch and challenge.

Output Number and Title	Satellite Imagery (Catapult) - Standard and advanced satellite derived information produced for FCDO Yemen and the humanitarian community within agreed timeframes. This component ended 31/03/2024.
Output Score	A+
Impact weighting (%)	20%		Impact weighting revised since last AR?	N/a

Output Indicator		Starting Target	Final Logframe Target - March 2024	Final Result Achieved
3.1 - % of satellite derived imagery and analysis produced for FCDO Yemen within agreed timescale and to specification/requirements. Timeframes and specification/requirements will be agreed between FCDO Yemen and Catapult at the time of the work order and assessed per work order.		90%	95%	Moderately exceeded: 100%
3.2 - Number of activities (e.g., workshops, key publications) delivered to disseminate programme information. / **Indicator added during 2022/23 to ensure groundwater project results reflected.		4 activities	15 activities	Moderately exceeded: 21 activities (140%)

The Catapult agreement under the IMEDA programme concluded on 31/03/2024. Therefore, no activities were completed in FY 24/25 for this output.

The Satellite Applications Catapult provided satellite derived information for use by YON and the Humanitarian community. The intended outcome was the increased use of satellite derived information by YON, HMG and other Humanitarian actors, to enable evidence-based decision making to inform strategic planning and operational response as well as supporting independent monitoring and accountability.

Groundwater resources in Yemen are being utilised faster than natural replenishment in many areas. Monitoring and management of water resources is limited by the on-going conflict. Catapult’s downstream partner, HR Wallingford, developed a map-based website, utilising both historical and Earth Observation geospatial data to provide data and information on water resources within Yemen. Through IMEDA this tool was further developed and vigorous stakeholder engagement in the tool undertaken.

Key outputs included:
- The development of a Geo-mapping Tool (GMT) for the FSSN Programme in collaboration with Tahseen. This tool consisted of two interrelated interfaces, namely the Programme Map and the Activity Map. The Programme Map enabled users to track FSSN recipient/participant numbers on a dynamic map whilst the Activity Map provided the geo-localisation of project activities and site-level recipient/participant count, with relevant contextual indicators. Data visualisation features allowed disaggregation by geographic area, time, partner, activity type and recipient/participant gender. This Geo-mapping Tool, along with all datasets, is currently in the process of being transferred to the MERLY programme, the successor of IMEDA.
- Yemen Groundwater Phase 3: Catapult supported HR Wallingford in delivering several updates and enhancements to the Yemen Groundwater website, including adding a risk metric and website translation. The agreement was taken over by the MENA climate programme PHENOMENAL through which the ongoing management and oversight of this site is being funded. Additionally, in the final year, the website was translated into Arabic and local actors were trained in maintenance of the website to ensure on-going continuity. Workshops, promoting the Groundwater website were delivered to a number of stakeholders during the programme, including the World Bank, UNICEF and internal FCDO climate and environment advisors. Catapult additionally provided satellite derived data to HR Wallingford on the extent of surface water in wadis. This data helped infer whether groundwater recharge may occur or how much irrigation may be taking place.
- Yemen Ports & Borders Analysis: An analysis report was completed utilising the EMDYN Geospatial Intelligence Fusion Platform, which provides fusion capability between data sets such as mobility data and Satellite imagery. This report analysed activity at ports and borders over a 12-month period to assess cargo routes into and through Yemen.
- Catapult supported ACAPS to produce a Flash Analysis on vaccination rates in Yemen. Catapult provided mapping data to highlight the location of health facilities and the distances that the population must travel to reach them.

Catapult maximised value for money by utilising the geospatial software, a Digital Globe SecureWatch product that provided data at approximately a tenth cheaper than purchasing archived data. This product also provided faster delivery of accurate, high-resolution imagery, thus providing efficiency savings.

Lessons learned through this output:
In order to accurately record ICF results across the lifetime of the groundwater project, it was essential that an appropriate baseline was identified as early as possible. Without a baseline, it was difficult to determine appropriate targets thereafter.

Recommendations for future programming:
Despite Catapult offering up various suggestions for potential analysis (in addition to the IMEDA SRO requesting ideas from programme teams), there was limited demand for imagery/analysis. Future programming should ensure that YON programme teams fully understand the remote monitoring and data analysis capability available in the Yemen context, in order to make informed decisions regarding what would be useful for their programme.

Output Number and Title	Delivery of high quality and timely information products and data analysis, technical support and capacity building to the humanitarian cluster system in Yemen (REACH). This component ended July 2021.
Output Score	A+
Impact weighting (%)	10%		Impact weighting revised since last AR?	N/a

Output Indicator		Starting Target	Final Logframe Target – July 2021	Final Result Achieved
4.1 - Number of information products (factsheets, situation overviews, maps) generated or supported by REACH.		381 products	381 products	1634 products Significantly exceeded:
4.2 - Number of inter-sectoral and/or sectoral secondary data reviews produced by REACH.		11 reviews	11 reviews	7 reviews
4.3 - Number of REACH-supported monitoring systems set up with partners.		3 systems	3 systems	4 systems
4.4 - Number of inter-sectoral and/or sectoral assessment exercises supported by REACH.		7 exercises	7 exercises	5 exercises
4.5 - Number of instances of REACH supporting calculation of severity scores and PiN in collaboration with partners.		7 instances	7 instances	10 instances
4.6 - Number of trainings conducted for partners by REACH.		20 trainings	20 trainings	33 trainings

The reduction in FCDO’s ODA budget for the financial year 21/22 meant a decrease in the portfolio-level budget for Yemen. Due to these resource constraints, it was agreed in March 2021 to reduce IMEDA’s programme budget. Following this decision, a comprehensive review process was undertaken across IMEDA partners, assessing partner value for money, finances, risks and delivery against FCDO strategic objectives. This process included extensive consultation with FCDO staff and external actors.

Following the review, it was determined that the REACH component of IMEDA, valued at £801,493 across 2020-2022, would be closed early. This decision was based on two core factors. Firstly, that REACH, unlike the other IMEDA partners, had historically received support from other donors. It was understood that REACH would receive continued support from other donors, covering gaps associated with FCDO ending its support and enabling it to carry on its activities. ACAPS, Catapult and Tahseen were solely reliant on FCDO funding and without continued support would likely have had to end their operations in support of the Yemen response. Secondly, ACAPS, Catapult and Tahseen provided internal services for FCDO that were in direct support of IMEDA’s strategic objective of strengthening FCDO portfolio and policy delivery. REACH was distinct from the other IMEDA partners, primarily providing services in support of the humanitarian system in Yemen, rather than FCDO itself. Due to the cuts, we had to prioritise the internal services that the other IMEDA partners offer to ensure progress towards FCOD objectives and value for money.

REACH provided a core set of data and analytical services for the humanitarian system in Yemen through 2020/2021, supporting evidence-based decision making and enabling a more effective response. Key external users of REACH’s services provided positive feedback on their performance, stating that they are an important service provider. While REACH provided direct support to FCDO (see Famine Risk Dashboard below), it should be noted that many of its other outputs were not widely used by FCDO and were instead focused on supporting external actors within the humanitarian response. This was distinct from other IMEDA partners, who's primary user base was staff within FCDO. REACH’s key outputs included:

- Joint Market Monitoring Initiative (JMMI). REACH provided direct support to the Cash Market Working Group (CMWG) through 2020/2021, collecting and analysing food, fuel and WASH price data as well as conducting interviews with vendors. REACH produced JMMI dashboards, factsheets, situation overviews and maps for the CMWG on a monthly basis. REACH also conducted COVID-19 specific data collection and analysis to understand the impact on consumers and vendors. The JMMI was utilised by a number of actors, including the IMF, ACAPS and the Government of Yemen, to inform humanitarian and economic policy and programme development.
- WASH Cluster. REACH delivered data management, analysis, and visualisation services for the WASH cluster. This included factsheets, situation overviews and maps. REACH also supported the establishment of the WASH Needs Tracking System (WANTS), helping the WASH Cluster to better target assistance and prioritise resources.
- Shelter Cluster: REACH collaborated with the Shelter Cluster and Inter-Cluster Coordination Mechanism (ICCM) in 2020/2021, assessing flood susceptibility across IDP sites in Yemen. This work was used by key humanitarian actors to inform preparedness and response efforts.
- FCDO Famine Risk Dashboard: At the request of FCDO, REACH established key indicators and collated relevant data for food insecurity in Yemen, building an online dashboard, internal to FCDO, to present trend analysis and identify key geographical hotspots. The dashboard was established and provided FCDO with an important data repository and enhanced monitoring of famine risks. The dashboard was housed within FCDO to support internal decision-making once support to REACH ended in August 2021. It should be noted that the dashboard required significant time and staff capacity, both within FCDO and REACH, to develop.
- Support to the humanitarian system: REACH also provided extensive support to OCHA and IOM in preparing tools and processes for the Multi-Cluster Location Assessment, a key set of evidence for Yemen’s Humanitarian Needs Overview. REACH also provided data collection, monitoring, and analysis support to the Camp Coordination Camp Management (CCCM) and Education Clusters.
- Training: REACH delivered training on data collection and analytical tools across the humanitarian system, helping to build capacity and enable response efforts.

Lessons learned through this output, and recommendations for future programming:
Any future engagement on a Dashboard-type product should carefully consider the management required in the set up process to reduce the human resource burden. It should also ensure early consideration is given to where such a product will be hosted at the conclusion of the programme, along with a strategy for maintenance and updating of the tool and associated data.

D: Value for Money

Key cost drivers and performance:

  - Economy
- Tahseen maintained competitive fee rates for team members and consultants hired to conduct work throughout the length of the programme. Tahseen agreed to fixed maximum rates with all its partners, which ensured that over the course of the programme rates did not increase, allowing them to deliver quality outputs without exposure to inflation or market fluctuation risks.
- ACAPS moved to a more regional structure which allowed more flexibility in staff resources. They also closely monitored consultant time to meet programmatic budget requirements.
- Catapult utilised the Digital Globe SecureWatch product to acquire data, which was approximately ten times cheaper than buying archived data.
  - Efficiency
- Tahseen used mobile data collection for work under all indicators wherever possible.
- Tahseen provided in-house programme support services to FCDO through their existing team, enabling FCDO to avoid needing to hire external consultants. When external consultants were hired, carefully selected staff were quickly onboarded, enabling them to dive into the work without delay.
- ACAPS continuously used the cost-per-product framework to ensure the maximisation of resources and to maintain a consistent product stream within a more constrained budget environment.
  - Effectiveness
- Tahseen finalised standard templates for concept notes, reports, and other deliverables. This standardised approach facilitated quicker and less laborious reviews by FCDO. These serve as FCDO intellectual property to be used in any future programme iteration.
- ACAPS products were referenced in IOM, USAID, World Bank and UNOCHA and Congressional Research Service reports.
- Catapult activities under IMEDA resulted in an increase of humanitarian and International Development interest in satellite-based analysis. This included work with the UN’s IOM team to analysis COVID-19 impacts on migration and engagements with the wider humanitarian community and future potential MERLY partners.
  - Equity
- Tahseen ensured that all field and remote data collection included everyone, regardless of gender, age, socio-economic status, or any other differentiating factors. Vulnerable people in Tahseen surveys included women headed households, pregnant or lactating women, households with children under five, people living with a disability, and people over 65 years old. The demographic data from these surveys was reported to FCDO and FCDO partners. In addition, accessibility, safety, and dignity in humanitarian delivery were consistently assessed and reported.
- ACAPS achieved its planned target of 50% of staff being women, and 77% of staff being from the MENA region also against a target of 50%.
- The Catapult team consisted of 5 colleagues of which 40% were women and 40% were from ethnic minority backgrounds.

  - Cost Effectiveness
- The cost effectiveness of Tahseen activities was based on their capacity to verify partner results, provide overall accountability to HMG, and to enable FCDO and partners to identify issues that impeded performance. The last issue was particularly relevant to cost effectiveness as it implied that inputs/resources were maximised towards expected results with problems identified and addressed early.
- ACAPS were able to use the methodologies developed in Yemen to support other ACAPS projects and proposals, including in Afghanistan, Ukraine and elsewhere to make these projects more economical. The methodologies of the Yemen hub have been utilized by other ACAPS hubs and ACAPS successfully used these foundational initiatives developed under IMEDA to secure funding for these products from other donors, including BHA, ECHO, and the World Bank.

VfM performance compared to the original VfM proposition in the business case:

The IMEDA Business Case outlined the following possible indicators to measure the value for money achieved by the programme:
- Average consultancy salary rates and expenses.
- Supplier management fee (%) of total contract value.
- Indicators of pooling efficiencies – number of field trips relative to the number of proportions of project verifications.
- Indicators of use of analysis and images generated in decision making.
- Citation of analysis in reports.
- Partner scores of the relevance and usefulness of monitoring reports.
- Diversity of contracting staff.
Tahseen maintained competitive fee rates for team members and any consultants hired to conduct work under indicator 1.6. Salary rates and expenses were monitored by the FCDO SRO when reviewing and processing partner payments. Additional indicators were added under the ACAPS and Catapult outputs to track requests from organisations related to analysis produced, potential collaboration for future initiatives, and activities delivered to disseminate programme information to UK Government and beyond. Partners reported references to IMEDA-produced analysis and other deliverables made by other organisations. Diversity of partner staff and contracted staff was recorded by partners and reported to FCDO on request.

E: Risk

The risk appetites for the IMEDA programme aligned with the overall YON risk appetites across the programme portfolio. The risk profile of the programme remained consistently at “Major” throughout the duration of the programme.

Risk Category	Programme Appetite
Reputational	Eager
Financial & Fiduciary	Receptive
Safeguarding	Receptive
Policy & Programme Delivery	Eager
Strategy & Context	Eager
Public Service Delivery & Operations	Cautious
People	Cautious

Yemen is one of the most challenging operating environments for humanitarian workers. As a result of the conflict and the security situation, FCDO have no staff in country and are unable to visit the North of the country and have limited access to areas in the South. The Yemen context has been fluid for the duration of the programme. The most significant risks, throughout the life of the programme are noted below (this is not an exhaustive list of risks that have been tracked on the AMP system through the programme, but rather those risks with a high residual rating)

Risk description	Mitigation	Residual rating
Access to TPM restricted by conflict or undue bureaucratic processes from authorities in the North	Use of local (Yemeni) field workers who were more able to access areas at less risk than foreign nationals. Back up sampling areas were identified in case selected areas became inaccessible during scheduled field visits. Use of lighter touch studies that completed in shorter time frames and conducted regularly to maintain the integrity of the review. Use of call centre technology to reach the most difficult areas to check with beneficiaries. Security training was provided to all field team members. Open communication took place with governorate and local political leaders to present the humanitarian purpose of the field visit. No international staff were active in the local implementation of this programme; all field work was undertaken by a carefully selected Yemeni NGO.	Severe, decreasing to Major
Authorities prevent Third Party Monitoring	FCDO Yemen worked closely with wider humanitarian response, including implementing partners to ensure access for third party monitors and all humanitarian response staff. FCDO Yemen and partner Tahseen monitored the situation closely and revisited our collective strategy on a consistent basis to identify necessary solutions to barriers.	Major
Fraud, corruption or aid diversion	All partner staff undertook fraud training, and each partner was assessed to ensure they had anti-corruption and fraud policies in place and had clear oversight of their downstream partners. Regular letters were issued by FCDO Yemen to our partners, reminding them of their responsibilities in this area. Fraud was also a consistent agenda item for Programme / Partner meetings,	Severe decreasing to Major throughout the lifecycle.
Beneficiary safeguarding	All partners were assessed on a regular basis to ensure they had strict safeguarding and data protection policies in place which FCDO Yemen monitored regularly. All known safeguarding issues raised by beneficiaries, were, to the best of FCDO knowledge, reported to FCDO and investigated by the partner, with resultant outcomes communicated and lessons learnt. Safeguarding was also included as a standard agenda item on programme governance meetings with implementing partners.	Major
COVID-19 impact	All partners limited unnecessary travel where possible and independent monitoring staff all followed WHO safety guidance during field visits. Call surveys were used where the risk to staff and beneficiaries was considered unacceptable	Originally Severe, moving to minor throughout the lifecycle.

During the final year of IMEDA (FY24/25), a number of additional risks were identified due to regional events. These include ongoing Houthi activity against shipping in the Red Sea, the FTO designation of the Houthis by the US administration, increasing military action against the Houthis by the US and Israel and the reduction in humanitarian funding by donors. These risks were evaluated and mitigated through other programmes within YON rather than the IMEDA programme.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues:
IMEDA programme partners consistently delivered against their commercial and non-commercial agreements. The contracting functions for IMEDA consisted of a commercial contract with Tahseen and accountable grants with ACAPS, Catapult and REACH. Procurement of MERLY, the successor programme to IMEDA, took longer than expected and programme inception could not commence in April 2024 as initially planned. Therefore, the IMEDA Business Case was amended in January, September and December 2024 to ultimately extend the end date to 31 March 2025 and increase the total IMEDA budget to £13,600,000. It was agreed that these final extensions should ensure that YON was provided with the minimum acceptable level of risk assurance and verification of expenditure and results until MERLY could begin operation. Therefore, the independent monitoring output delivered by Tahseen was deemed essential and the only output that would continue into FY 24/25. The contract with Tahseen was amended in line with the Business Case amendments. The accountable grant agreements with ACAPS and Catapult concluded as planned on 31 March 2024. The accountable grant agreement with REACH was terminated early on 25th August 2021 due to budgetary constraints.

Throughout the lifetime of IMEDA, FCDO was kept well-informed of progress through a mixture of formal and informal reporting. All programme partners provided quarterly narrative progress and financial reports, which were largely on time and to a very high standard. The SRO held quarterly progress meetings with each partner, which were done in-person whenever possible. Communication with all partners remained strong, regular catch ups were held with each partner to discuss progress, risks and issues on either a weekly, bi-weekly or ad-hoc basis, as needed.

The total IMEDA expenditure for the 24/25 financial year was £1,542,945.26 against an allocation of £1,545,512.18 and only includes delivery against output 1, by Tahseen. This means that there was a very minimal underspend of £2,566.92 this year and against the Tahseen contract overall. When updates to the workplan were required due to changing YON priorities, Tahseen was able to reorganise resources efficiently to support the timely delivery of the newly agreed activities whilst maintaining consistent fee rates and activity unit rates and keeping within the annual budget allocation.

Programme-level approach to monitoring and evaluation:
FCDO used a mixture of formal and ad hoc methods of monitoring the IMEDA programme. As the biggest output, the IMEDA SRO met with Tahseen weekly to discuss the workplan, finances and risks to delivery. Regular meetings with ACAPS and Catapult were held on a bi-weekly and monthly basis respectively. In addition to regular catch-up meetings, more formal quarterly meetings were set up with each partner aligned to payment schedules. The IMEDA SRO had the opportunity to travel to Amman around twice a year on average to meet with partners in person, in addition to hosting Tahseen in East Kilbride and visiting them in Brussels.

As part of the Annual Review and PCR processes, the IMEDA SRO collected feedback from the HART team to gain insights into the impact Tahseen activities had and what did/didn’t work. This feedback has been integrated into the narrative for output 1 of this report and was essential considering the HART team is one of the key users and direct beneficiaries of Tahseen deliverables.

Tahseen delivered a number of learning workshops over the last few years, predominantly aimed at HART and their partners. One of which was a workshop for FCDO and FSSN partners, with the aim to agree common indicators for the Food Consumption Score (FCS) and reduced Coping Strategy Index (rCSI), including how to align and maximise analysis and reporting for these food security outcome level proxy indicators. These learning workshops often corresponded with the recurring FSSN governance meeting. The FSSN team incorporated Tahseen into their governance meetings and quarterly review meetings with all partners. Therefore, Tahseen reviewed and commented on partner reports and attended meetings to present the monitoring findings and key learning and discussed agreed upon actions from previous monitoring activities.

As part of the review process for independent monitoring reporting, Tahseen began conducting action-based learning workshops with the programme partner ahead of draft report submission to FCDO. This resulted in much better validation of findings and agreement of corrective actions and gave FCDO confidence that the proposed recommendations were appropriate and actionable.

Date of last narrative financial report	27/05/2025	Date of last audited annual statement