## AfDB 2023 GCI VII Annual Review
Title: The Seventh General Capital Increase for the African Development Bank (AfDB GCI-VII)
Programme Value £ (full life): Up to £110 million paid in capital and up to £1.7 billion in callable capital (contingent liability)		Review date: / June 2025
Programme Code: 300694	AMP start date: Dec 2020	AMP end date: July 2028

Summary of Programme Performance
Year	2020	2021	2022	2023	2024
Overall Output Score	B	B	B	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/90000434.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/90000436.xlsx

A. SUMMARY AND OVERVIEW
Description of programme
This Annual Review is the fourth assessment of the seventh general capital increase (GCI-VII) of the non-concessional arm of the African Development Bank Group (AfDB). The review covers the Bank’s operations in calendar year 2023. The GCI-VII was negotiated alongside the 15th Replenishment of the Bank’s concessional window, the African Development Fund (ADF-15) in 2020. The non-concessional window (to which the GCI relates) uses its shareholders’ capital, leveraged on global capital markets at preferential interest rates due to its AAA credit rating, to lend to credit-worthy middle-income countries (this includes lower middle-income countries) at near-market rates, including countries transitioning from ADF to AfDB. It also lends to the private sector and provides loans for regional operations in Fund and Bank countries. The larger economies account for most of the loans made, with Ivory Coast ($726 million), followed by Morocco ($695 million) and Egypt ($668 million) the top three countries for approvals in 2023.
[note] Main sources: Annual Development Effectiveness Review 2024 and Annual Report 2023

1. The AfDB was established in 1964 and is a significant source of multilateral funding for economic, social and institutional development on the continent. The AfDB’s mandate is to promote sustainable economic development, social progress, and inclusive green growth in its regional member countries, thus contributing to poverty reduction and improving living conditions. The UK is one of the Bank’s 81 total shareholders and 27 non-regional members.
2. In 2019 the Bank’s shareholders agreed to a 125% general capital increase to more than double shareholder equity in the bank. GCI-VII was intended to boost the AfDB’s lending capacity from nearly $8 billion per year in 2020 to over $11 billion by 2030. However, following the COVID-19 pandemic, weakening of shareholders’ exchange rates to the dollar means current lending expectations are likely to be more modest. The pandemic forced the Bank to reduce its lending to maintain its AAA credit rating and to seek additional temporary callable capital from AAA shareholders. Capital receipts under the GCI have helped stabilise the outlook; and with easing of pressures from the pandemic, Bank approvals increased to US$8.16 billion, getting closer to pre-pandemic levels of US$9.66 billion. In 2022 the UK agreed to provide paid-in capital and callable capital between 2020-2027, which included purchasing new shares in the AfDB increasing our shareholding from 1.755% to 1.878% as of 31 January 2024. This cost £110m and an undertaking to make available up to £1.7bn in callable capital in extreme circumstances.
  [note] AFDB uses Unit of Account (UA) as its official currency. 1 UA = 1.32405 USD as per April 2024 exchange rates. Figures in the text were UA 6.16 billion in 2022 (= US$8.16 billion) and UA 7.3 billion in 2023 (= US$ 9.66 billion).
  [note] Callable capital is capital subscribed to by shareholders that has not been paid in but may be called if a multilateral development bank cannot meet its bond and guarantee obligations under extreme circumstances. None of the multilateral development banks have ever called it.
  [note] The final shareholding will vary as other shareholders make their paid-in capital and any additional callable capital contributions.
3. The African Development Bank Group achieves its economic and development objectives by mobilising and allocating resources for investment in regional member countries; and providing policy advice and technical assistance to support development efforts. President Adesina launched the ‘High 5’ Agenda (2015-2025) to sharpen the Bank’s objectives around five pillars: 1) Feed Africa, 2) Light up and Power Africa, 3) Integrate Africa, 4) Industrialise Africa and 5) Improve the quality of life in Africa, with particular attention paid to the cross-cutting themes of climate change, gender equality and empowerment fragility and resilience; youth empowerment and employment, and finally, economic governance and institutional capacity building.
4. The UK is able to deliver a development agenda through the AfDB that could not be achieved bilaterally because of 1) the Bank’s wider geographical coverage through country and regional base 2) its relationships, technical expertise and institutional capacity through sector specialists, managing large scale, cross-country project design, implementation and monitoring systems and 3) risk sharing and fiduciary standards, where shareholders jointly share risks and the multilateral development bank provides risk mitigation in political and economically unstable environments. African countries feel a high degree of ownership and trust in the Bank. This offers strong potential to address sensitive local and regional challenges and promote transformation across the continent.
Summary supporting narrative for the overall score in this review
This review, with an output rating of A after two successive B scores reflects some improvement in achievement of development results, as tracked under output one, albeit further progress is still necessary. The approach to the review placed more emphasis on in-year delivery of results, recognising that the gap that had developed over the pandemic period with cumulative milestones had grown too large to allow a fair assessment of in-year performance. This annual review, for the first time, explicitly takes account, in a new output five, of the positive progress on delivering the policy commitments made to Governors when the GCI was agreed, and which were intended to improve the Bank’s institutional effectiveness and facilitate delivery of its mandate. They were excluded from the initial version of the logframe as not forming part of the extant results management framework (RMF). In practice we have identified proxy indicators from the RMF for some policy areas included. Other outputs remain largely unchanged from 2022, although it is worth noting the improvement in administration costs and the ongoing work on decentralisation discussed further below. This A rating is in line with consistent A output ratings for ADF annual reviews. ADF countries are a substantial sub-set of AfDB borrowers and many benefit from some non-concessional AfDB funding. Moreover, ADF uses AfDB staff and operations systems and processes as well as falling under AfDB policies and guidance.
Major lessons and recommendations for the year ahead
A number of the previous recommendations remain relevant for the forthcoming year. Overall, the recommendations for the year ahead are focused once again on improving the measurement of results/progress; implementation of the policy commitments agreed under GCI-VII; staff decentralisation; and administrative costs. Below is a summary of the specific recommendations:

Recommendation I - FCDO should clarify with AfDB Staff plans for reporting on GCI-VII 2025 targets and discuss implications for 2024 targets. Discussions should include alignment with the approved 2024 RMF and implications for the logframe.
Recommendation II - (carried over) For the project completion review, FCDO should consider doing a deep dive on one or more specific countries to provide a fuller assessment of progress made by the Bank, especially around gender, climate and environmental and social issues.
Recommendation III - FCDO to consider indicators and milestones against which to assess continuing institutional reform efforts, aligning with reform commitments in ADF17 negotiations.

Recommendation IV - Review reporting lines and press for adequate staffing and budgets for AfDB compliance functions and for improved follow up of audit and evaluation recommendations.
Recommendation V - (carried over) FCDO should continue to press the Bank on decentralisation of professional staff, in line with FCDO organisational reform priorities, and track work on the decentralisation framework as part of the strategic staffing review. FCDO should also continue to engage with the Bank to ensure that it has the right staff with the right capabilities in place.

Recommendation VI – FCDO to monitor closely the administrative costs, including proposed amendment of the administrative cost-sharing formula, and ensuring that the control measures put in place by the Bank have been effective in preventing further increases.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The following Theory of Change (ToC) is based on the premise that the AfDB serves as an effective channel for the UK to achieve large-scale development outcomes across Africa—both through its direct contributions and by mobilising additional resources. It also assumes that the ADF is an effective instrument for deploying concessional finance.

The ToC was developed by drawing on the Bank’s strategic priorities outlined in the High 5 Agenda, along with broader institutional reforms. Financial contributions and policy engagement—both during the capital increase negotiations and throughout the GCI-VII period—are expected to lead to the adoption of robust policies and reform initiatives, ultimately generating measurable development outcomes and impact.

The ToC sets out the steps by which this process should take place. FCDO’s inputs (alongside resources and dialogue from other shareholders and the Bank’s own inputs) of finance and policy engagement during the replenishment negotiations and throughout implementation are centred around the policy issues described above and should lead to outputs on two levels:

- Institutional reforms which improve the efficiency and effectiveness of Bank and Fund operations; and
- Outputs on the ground because of efficient and effective operations.

1. The ToC diagram in Figure 1 also recognises that there is a lag time regarding when inputs contribute to outputs and outcomes.
2. It is assumed that if designed effectively, the outputs on the ground will contribute positively to the outcomes in the areas of the Sustainable Development Goals. In turn, these will have a positive impact on economic growth and contribute to a reduction of poverty in Africa.
Figure 1: GCI-VII Theory of Change

Updating the logframe has been a recommendation in 2020-2022 annual reviews to account for the impact of COVID19, Russia’s invasion of Ukraine and global inflation rise on AfDB’s operational delivery. Following the recommendation of two previous annual reviews, the GCI VII logframe has been revised prior to this Annual Review’s completion. These revisions include revisions such as 1) changing the logframe indicator targets from cumulative to annual figures; 2) the inclusion of a policy commitment on debt, climate, and private sector included as separate output; and 3) the removal of the outcome relayed to the ‘Cost of trading across borders.’ This was a World Bank indicator and AfDB was no longer reporting its results.  There have been changes at the outcome level in the logframe to reflect changes in indicators used in the Bank’s Annual Development Effectiveness Review (ADER). These in turn may have reflected the independent evaluation team (IDEV) recommendation, mentioned in the previous annual review covering 2022, to review Results Management Framework (RMF) targets in light of available resources to ensure they were realistic. The logframe should be reviewed once again for the next report to ensure it aligns with the Bank’s new 2024-2033 RMF.

For consistency with the approach agreed by shareholders and the Bank on its RMF and the Bank’s published RMF results and ADER, progress against the logframe outputs are considered ‘met’ if they achieved +/-10% of the target in the programme’s annual reviews.

1. The ADER 2024, which covers 2023 findings, highlighted the impact of external shocks on the Bank’s clients and its own operations. This has been a theme in previous annual reviews, with the decrease in number of shareholders rated by the credit rating agencies as AAA along with decline in borrower credit ratings due to economic shocks before and after the COVID pandemic, and increasing non-performing private sector loans, all combining to constrain lending well below levels anticipated when the GCI was agreed. Assumptions around shareholder quality and support and those related to global and regional economic growth should be more clearly highlighted in the theory of change. There was a recovery in lending levels over 2023, with approvals rising from around $8.3bn in 2022 to $10.8bn, and disbursements from $4.7bn in 2022 to $5.9bn. AfDB more than doubled co-financing mobilised from $1.3bn to $2.9bn over the same period. Substantial increases in revenue and net income enabled it to build up capital buffers. It also began discussions on a general increase in callable capital that was agreed by Governors in 2024 and so has shored up its AAA credit rating. This increased the Bank’s capital from $188bn to $331bn.
2. Moreover, despite a challenging global environment, Africa remained the world’s second-fastest-growing region in 2023, even if economic growth slowed due to various global and domestic factors. While inflation increased and debt concerns persisted, positive trends emerged. Fifteen countries managed to achieve growth rates exceeding 5%, while others made significant progress in debt management.

Figure 2: Outcome results
Outcome indicators	Baseline 2019	Milestone 2023	Achieved 2023
Share of population with access to electricity (% population)	54	81	58
Prevalence of moderate or severe food insecurity (%)	N/A	51	61
Access to finance (% population)	56	53	49
Intra-African trade as a proportion of total goods trade (%)	N/A	14	13
Employment to population (%)	N/A	58.2	58.6

This more positive outlook is reflected in better performance against outcome indicators, with three of five being met, a significant improvement over 2022 even allowing for the change in indicators. It should be noted that the Bank decided following a review of its RMF in 2022 not to report on level one targets, which are largely outside its control to deliver, and has not reported targets in its ADERs for several years.

The Bank’s plans to publish its new Ten-year Strategy and RMF in 2023 were postponed because the new strategy was delayed and later published in Q2 2024. The annual review for 2022 noted that the RMF was being updated to reflect the AfDB’s new ten year strategy and that it would follow a new approach. The new RMF, covering 2024-2033, was published late last year. It is uncertain whether the Bank will continue to publish data on the GCI-VII results commitments. This has implications for the FCDO logframe and will need to be discussed with the Bank. The previous annual review also proposed reflecting GCI-VII policy commitments, related to reforms referenced in the theory of change, into the logframe. This is reflected in this year’s review.
[note] The AfDB Group’s Ten Year Strategy Results Management Framework (2024-33): 94878_rmf_2024-2033_en_v7.pdf

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme remains off-track in terms of cumulative development results originally anticipated and on delivery, but on track for on cross-cutting issues underpinning operational delivery, organisational efficiency and on the institutional reform commitments made at the time of the capital increase. The impact of COVID-19, the war between Russia and Ukraine and the secondary financial and economic shocks as a result of inflation continued to affect the Bank, which continued to demonstrate pragmatism by adjusting its approaches, finding new innovative instruments to mobilise resources. There was an improvement in delivery of development results assessed on an annualised basis, however. Achievement is not solely in AfDB’s control. For example, fertiliser supply chain shocks caused by Russia’s invasion of Ukraine, climate and conflict affected agricultural production. The Bank’s response included credit guarantees through the Africa Fertiliser Financing Mechanism, promoting adoption of drought resistant seed varieties, with its Technologies for African Agricultural Transformation (TAAT) programme supporting increased cereal production, farmer incomes and jobs. African Development Fund financing is important also, with $165 million through a food security programme in the Sahel increasing grain, vegetable and animal production and doubling household incomes.
Recommendations for the year ahead
Recommendation I: FCDO should clarify with AfDB Staff plans for reporting on GCI-VII 2025 targets and discuss implications for 2024 targets. Discussions should include alignment with the approved 2024 RMF and implications for the logframe.

Recommendation II (carried over from previous annual review): For the project completion review, FCDO should consider doing a deep dive on one or more specific countries to provide a fuller assessment of progress made by the Bank, especially around gender, climate and environmental and social issues.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The review finds that the rationale for FCDO support to the AfDB GCI-VII set out in the business case remains, that the UK shareholding continues to offer value for money, and that lending and performance are recovering after the shocks of the COVID pandemic and broader global economic shocks including from Russia’s invasion of Ukraine. On that basis the investment should continue.
C. DETAILED OUTPUT SCORING

Output 1	GCI delivers economic and social development results in AfDB countries. This output will score an A if 3 out of 5 milestones in a given year are met.
Output number:	No. 1		Output Score:			B
Impact weighting (%):	35 %		Weighting revised since last AR?			Yes, the weighting has been revised down due to additional output.

Indicator(s)	Milestone(s) for this review				Progress
1.1 People provided with access to electricity (number) (of whom women)	6300 (3000)				6300 (2883) – Met expectations
1.2 MSMEs effect (turnover from investments) ($ million)	8410				Data not provided
1.3 Roads constructed (km)	2896				2852 – output met expectations
1.4 Direct jobs created (millions) / (of which women)	2.90 (1.31)				2.74 (1.22) – output did not meet the expectations
1.5 Farmers using improved inputs (number) (of whom women) New	40,647 / (20,332)				11,076 / (3,488) / output substantially did not meet expectations

Briefly describe the output’s activities and provide supporting narrative for the score.
This output assesses whether AfDB’s GCI VII progress delivers economic and social development results in AfDB countries. The indicators were taken from the Bank’s Results Management Framework for its High 5 Agenda although there have been changes to results reporting over time. Given the extent by which cumulative progress had fallen behind that originally envisaged, indicator milestones were reset to reflect progress from actual achievement as of 2022 using the expected annual trajectory used in setting the original milestones. In the event, two of its five indicator milestones under this output were met, albeit in one case data was not reported. Hence the output scored B. This represents an improvement on the previous year, for which only one of five milestones were met.

Amending the performance indicators to reflect a more realistic assessment of annual progress over 2023 made a difference for output 1.1, where prior underperformance meant the original target was unrealistic, but the annual level of performance was broadly in line with what had originally been anticipated. This is the first year since the COVID-19 pandemic that this indicator has been met. There is a question about whether this indicator is sufficiently ambitious given the Desert to Power Initiative alone, launched in 2018, envisaged bringing renewable energy to 250 million people by 2030. The revision did mean that the indicator for output 1.2 was far more ambitious than the original targets if still comfortably within the increases in micro-, small and medium-enterprise turnover achieved in previous years. Unfortunately, failure to report on this indicator means we could not assess this indicator, which would have been expected to enable an overall A rating.

This is the third year in a row that the Bank has not delivered the expected annual construction of roads even if the scale of reduced ambition in 2023 meant the milestone was technically met on a cumulative basis. This highlights one of the continent’s critical challenges: a significant road infrastructure deficit leads to increased transaction costs and low levels of intra- African trade, which currently accounts for only 13% of total goods exchanged on the continent. Operational delays due to capacity, road construction staffing constraints, lengthy resettlement and compensation procedures, alongside procurement and sovereign counterpart funding, continue to be an issue.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
1. Regarding the lack of data for indicator 1.2, the Bank decided to discontinue collection of this data during the design of the new results management framework: due to data from AfDB projects’ underlying investees having been inconsistent and incomplete due to data availability, confidentiality and aggregation issues. The indicator has been replaced by a new indicator: Enterprises supported with access to finance (number), which was exceeded in 2023, with 443,510 enterprises supported of which 232,955 were women owned, against milestones of 111,209 and 76,948 respectively. Use of this indicator should be considered as part of the discussions proposed under recommendation I above.
2. In addition to the amendment of 2023 milestone targets described in paragraph 23 above, farmers using improved inputs was used for output indicator 1.5 to replace people benefiting from improvements in agriculture. Whilst the latter was reported on in narrative reporting in the AfDB’s Annual Development Effectiveness Report (ADER) in previous years, it was not a formal indicator. Indicator 1.5 is primarily intended to be met under the Technologies for Agricultural Transformation (TAAT) programme, which in its first phase has focused primarily on building a regional technology delivery infrastructure involving research and extension services and farmers associations. TAAT still hopes to meet the 40 million target in its second phase.
3. It is worth noting that previously, for indicator 1.3, the logframe assumed 2,900km of annual road construction, which was reflected in previous ADER milestones. For 2023 the Bank had a much reduced annual target. Whilst the reason for this is unclear, the 2023 ADER had noted findings of a cluster evaluation of transport projects between 2012 and 2019 that, whilst construction work was managed well overall, transport operations were delayed by capacity constraints within executing agencies, resettlement and compensation processes and challenges in procurement and mobilisation of counterpart funding. Similarly, for indicator 1.4 the logframe assumed 1.06 million annual increase in direct jobs supported. The Bank reduced the annual targets for 2023 to 701,300 direct jobs supported, of which 311,765 were women. Achievement was 77% of the annual target (70% of that for women), below expectations. This underlines the need for clarity on future milestones.
4. A discussion on milestones should cover access to electricity given Desert to Power has been followed by the Mission 300 initiative with the World Bank to reach 300 million people by 2030, under which the AfDB has committed to adding 50 million new connections. There have been external calls to revise access targets to reflect regional realities. It is unclear how these initiatives relate to one another.
  [note] Desert to Power: A Reality Check on the AfDB’s Electrification Ambitions in the Sahel - Energy for Growth Hub 6 August 2025
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
1. Revision of the logframe is in line with the recommendation for the previous annual review to review output one indicators given how far cumulative progress had fallen behind the milestones originally envisaged. The previous review’s recommendation to consider a deep dive into particular countries in conjunction with a project completion review still stands.
2. The previous annual review also recognised the importance of aligning the logframe targets with the new results management framework. This was made more difficult by delays in finalising the latter. Unfortunately, there was a failure of communication between the FCDO programme team and AfDB on how planned changes to the results management framework would impact specifically on logframe indicators. Whilst the Bank did provide updates to the Board on changes these did not prove sufficient for the programme team to pick up the implications. Monitoring of progress will be further complicated by the intent to revise the results management framework in line with the development of the new ten-year strategy, approved in 2024.

Output Title 2	AfDB improves the performance of its operations portfolio / [Bank wide]
Output number:	No. 2			Output Score:			C
Impact weighting (%):	15%			Weighting revised since last AR?			Yes, due to additional output

Indicator(s)		Milestone(s) for this review				Progress
2.1 Time from concept note to first disbursement (months)		21				25 – moderately did not meet expectations
2.2 Operations that achieved planned development outcomes (%)		80				71 – moderately did not meet expectations
2.3 Share of NSOs (Non-Sovereign Operations) investments in low-income countries (%)		40				9 – substantially did not meet expectations

Briefly describe the output’s activities and provide supporting narrative for the score.
The indicators under output two encompass efficiency, effectiveness and equity measures. Failure to meet any of the indicators have resulted in the ‘C’ output rating.

1. Both indicators’ targets were revised downwards by the Bank to be more realistic: output 2.1 after 2021 (see previous annual review) and output 2.2 after 2022. The targets were taken from the 2024 ADER. Despite the change both were missed. Delay in first disbursement was ascribed as primarily due to factors including gaps in project preparation, the volatile political and security context, and safeguarding requirements. Commercial viability and long-term financial sustainability affected private sector operations. Time from concept note to first disbursement was at least better than the 27.4 months in 2021 if slightly up on the 22.5 months reported for 2022. The 2024 ADER reported that targets for time taken to procure goods and works and for operations at risk were substantially exceeded, whilst the proportion of operations eligible for cancellation at 30% was twice the 2023 target of 15%.
2. There was, however, a modest improvement on achievement of development outcomes from 2022’s 68%, even if lower than achieved during the pandemic and failing to meet the target for 2023.
3. Notwithstanding the low share of non-sovereign operation investments in low-income countries (LICs) reported under indicator 2.3 the Bank has been working to address this, recognising that LICs, particularly in fragile contexts, face challenges that constrain private sector development, such as weak macro-economic climate, poor investment climate and security risks. The Bank is working to address this at different levels, including upstream building institutional capacity; midstream such as project preparation capacity and supporting feasibility studies; and downstream including blended finance and guarantees. This has started to deliver results.
4. 30% of the Bank’s ongoing operations faced implementation challenges and delays, mirroring levels reported in 2022, with contributing factors including ratification processes, political instability and technical design gaps. Nevertheless, the Bank remains committed to ensuring high-quality project design to enhance its results and impact on Africa’s development.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The future targets will need to take account of the new long-term strategy agreed in 2024. The associated revised RMF may affect monitoring for future years.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
1. Discussions with management during the 2024 annual meetings along with a visit to the Bank’s headquarters in Abidjan in November 2024 in conjunction with this review provided an opportunity to raise portfolio delivery with the Bank. The 2024 ADER notes initiatives to improve results measurement and support project management units and executing agencies in countries with limited capacity. AfDB also introduced new training for country programme officers and country managers under its Operational Academy Programme.
2. An evaluation of its economic sector work also highlighted the need for flexibility to respond to demand from clients to ensure relevance of knowledge products, better engagement of local stakeholders and strong results monitoring. In response, the Bank is developing a Quality, Results and Learning action plan that should drive better quality, faster delivery and continuous learning for greater development effectiveness.
3. The FCDO continues to press the bank to increase capacity, particularly in country offices, on climate change, private sector and fragility. As described in paragraph 33 above, there has been some improvement on delivery, but this is very much a work in progress. It is worth noting that the 2024 ADER reported that the proportion of operations independently rated as satisfactory and above at completion slightly exceeded the 79% target for 2023. The December 2022 IDEV evaluation of the Ten-Year Strategy 2013-2022 reported project completion reports showing the share of operations rated as satisfactory and above had risen from 69% in 2016 to 86% in 2021, so overall a positive trend. It rated performance and quality of delivery over the strategy period as satisfactory overall. Ensuring proper funding and staffing of audit and evaluation functions including follow up in recommendations will be important. This is further discussed in section D below.
  [note] TYS Evaluation-(En)-V7.1.pdf

	Output 3	Cross-cutting and strategic issues appropriately reflect Bank's strategies and programming
	Output number:	No. 3		Output Score:			A+
	Impact weighting (%):	20%		Weighting revised since last AR?			No

Indicator(s)		Milestone(s) for this review				Progress
3.1 New operations with gender-informed design (%)		91				100 – exceeded expectations
3.2 Operations with satisfactory ESS (Environmental and Social Safeguards) mitigation measures (%)		94				100 – exceeded expectations
3.3 Approvals classified as climate finance (%)		40				55 – significantly exceeded expectations

Briefly describe the output’s activities and provide supporting narrative for the score.
1. Output 3 measures the Bank’s cross-cutting objectives, focusing on gender, Environmental Social Safeguards and its project approvals classified as climate finance. These reflect equity and effectiveness considerations. This is AfDB’s best performing output, as it has exceeded all targets and scored A+ for the 3rd consecutive year.
2. AfDB recently rolled out a Gender Marker System (GMS) to non-sovereign operations, reaching 70% in 2023, with the objective of reaching 100% by 2025. Also, in early 2023, the Bank obtained Economic Dividend for Gender Equality (EDGE) certification, which demonstrates the institution’s commitment to an inclusive approach to people and talent management in its policies and actions.
3. The Bank has significantly exceeded the expectations on climate finance. In 2023, 97% of Bank approved projects were developed with climate-informed design considerations. More specifically, climate finance project approvals amounted to some USD 5.8 billion and 55% of total approvals, of which 47% was for mitigation projects and 53% for adaptation projects.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes during the past year and none planned for next year although the RMF revision in 2024 may impact on reporting.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
As for output one, the recommendation to consider a deep dive into particular countries in conjunction with a project completion review still stands.

Output 4	Bank improves its organisational efficiency
Output number:		No.4		Output Score:		A
Impact weighting (%):		15 %		Weighting revised since last AR?		Yes, due to additional output

Indicator(s)			Milestone(s) for this review		Progress
4.1 Share of operations staff based in country offices and regional hubs (%)			76		55 – Output substantially below expectations
4.2 Projects managed from country offices (%)			83		75 – Output met expectations (within 10% of target rate)
4.3 Share of women in professional staff (%)			37		32 – Output moderately did not meet expectations
4.4 Net vacancy rate - professional staff (%)			10		7.7 – substantially exceeded expectations
4.5 - Operations professional staff (%)			69		68 – met expectations (within 10% of target rate)
4.6 Administrative costs per UA 1 million disbursed (UA ’000) - Bankwide			89		90.9 – met expectations (within 10% of target rate)

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 4 measures the Bank’s organisational efficiency and effectiveness. It is important that the Bank runs well as an organisation and continues to improve its operational performance so that it increases and maintains its capacity to deliver development outcomes. This year, only three of six indicators were met.

It has been a longstanding UK priority for the bank to decentralise more staff to country offices and increase capacity particularly in climate, private sector and conflict. Notwithstanding the marginal increase in the proportion of Bank operations staff based in country offices and regional hubs from the 54% in 2022 and 52% in 2021 this remained significantly below the 76% target. Moreover, the proportion of projects managed from country offices decreased from 78% in 2022 to 75% in 2023, if technically barely meeting the target. As at the time of writing the Bank has indicated that it will be developing a new strategic staffing plan, which will include a decentralisation framework and associated three-year action plan, operationalisation of which will be underpinned by an impact measurement framework with indicators to assess its impact on the business. The strategic staffing plan should address a shortage of Task Managers, which alongside expected decentralisation of sector managers, should increase the proportion of projects managed from country offices.

In 2023, the representation of women among professional staff remained at the same level as in 2022 at 32%, below the logframe target, while women in management roles also remained the same at 27%. These are below the 2023 targets in the ADER of 40% and 35%, respectively. It will be important to ensure that ambition is retained on gender diversity among the Bank’s staff at senior and professional grades in the new strategic staffing plan. The Bank has noted that it is actively pursuing EDGE gender certification, a globally recognised assessment methodology, which entails the implementation of an action plan focused on four pillars: representation, pay, policies and practices and fostering an inclusive culture.
[note] It is calculated as the ratio of vacant professional positions, excluding those for which recruitment is ongoing, candidates have been interviewed and selected, and offers have been made and accepted and candidates are preparing to assume their duties, to all the budgeted professional positions.

There is a more positive story to tell on the net vacancy rate, despite a recruitment freeze for part of 2023, more than reversing the increases seen during the pandemic from the 9.9% baseline (2019) and 12.8% in 2022. It is also good to see that the number of days to fill vacancies has also fallen significantly below its target figure of 117 days for 2023, dropping from 152 days in 2022 to just 75 days.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes for this output within the year. The indicators will, however, need to be reviewed in light of the new results management framework.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead.
1. The past two annual reviews (2021 and 2022) have recommended that FCDO should continue to press the Bank to make progress on decentralising staff to align with organisational reform priorities, whilst the 2022 review noted the importance of controlling administration costs. This is all the more important given that the African Development Fund meets over half of AfDB administration costs. Action will include tracking the strategic staffing work referred to in paragraph 46.
2. Whilst still valid, it is also clear that inflation has substantially exceeded the 1.1% assumed in 2020 that informed the 2.9% administrative budget annual increase mandated by the Bank’s cost containment framework. The Bank will be reviewing this over the next few months.

	Output 5	GCI VII Policy Reforms (new output)
	Output number:	No. 5			Output Score:		A
	Impact weighting (%):	15%			Weighting revised since last AR?		New assigned output

Indicator(s)				Milestone(s) for this review				Progress
5.1 Policy reform: Debt / Public sector officials with improved skills in Public Financial Management (number) (of whom women)				140 (46)				110 (44) – not met
5.2 Policy reform: Climate and green growth / Paris Alignment				Full alignment of all new Bank operations and sector strategies with mitigation, adaptation and climate finance.				Met expectations
5.3 Increasing share of private sector operations in overall financing (% approval volume). Data on allocation to priorities sectors.				Significant increase in private sector operations as a proportion of approvals. Data on allocations.				Private sector operations increased from 11% in 2020 to 16% in 2023. Agriculture, energy, industry and transport sectors exceeded 58% of portfolio balance. Met

Briefly describe the output’s activities and provide supporting narrative for the score.
1. Output 5 is a new output, reviewing progress against key policy commitments made by Bank management at the time of the GCI related to FCDO priorities. Indicators needed to be those that could be tracked over multiple years as many success indicators involved individual tasks or policy products for completion in a particular year.
2. African countries were hit hard by the COVID pandemic and its economic aftermath, with median public debt-to-GDP rising from 54.5% in 2019 to 64% in 2020. 21 countries were classified as in debt distress or high risk by the end of 2023. The composition of debt was also moving towards non-concessional commercial debt. Whilst this indicator was moderately not met, its target of seven Bank-supported countries registering improved macroeconomic policy management was met and three countries of the target of four improved their governance scores.
3. On climate change the AfDB is implementing its Climate and Green Growth Strategic Framework: Projecting Africa’s Voice – Strategy 2021-2030 that aims to mainstream climate change and green growth across all of the Bank’s operations. Under this strategy the Bank committed to aligning by 2023 with principles of Paris alignment for MDBs building blocks covering: mitigation goals, adaptation and climate-resilient operations and accelerated contribution to just energy transition through climate finance. It committed to full alignment by 2025 of operations with the remaining three building blocks: strategy, engagement and policy development; reporting; and alignment of internal activities. In this case, the Bank has done reasonably well having fully aligned all of its new operations and sector strategies with mitigation, adaptation and climate finance.
  [note] Climate and Green Growth Strategic Framework: Projecting Africa’s Voice - Strategy 2021–2030 | African Development Bank Group
4. Private investment will be critical for meeting the SDGs and climate targets, as demand for finance far exceeds available public funding. Whilst the policy reforms did not include targets for private sector financing there were actions on improving the quality, additionality and impact of private sector operations. For this review evidence of increased ambition on private sector operations and reporting on allocation to priority areas is deemed sufficient for an initial indicator. Private sector approvals rose from $0.6bn in 2020 to 1.7bn in 2023. This was slightly down on the $1.9bn of private sector approvals in 2022, over 20% of the total.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This is a new output. Further discussion is needed on future reporting plans and appropriateness of indicators for 2024 and 2025.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
Recommendation III: FCDO to consider indicators and milestones against which to assess continuing institutional reform efforts, aligning with reform commitments in ADF17 negotiations.

## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

1. The original business case for the GCI-VII noted strong alignment of the Bank’s investment portfolio with UK objectives and the strong results expected through the GCI. It referenced a strong track record of productive investment. Despite the mixed record on development results recorded under output one there is evidence that in some areas at least the Bank is returning to annual levels of progress anticipated at the time of the GCI following the disruption caused by the pandemic and the decline in some shareholder credit ratings that constrained lending. In 2023 the Bank’s investments reached $9.7bn, the second highest total in its history after 2019. The importance of the Bank for Africa was recognised by the UK in bringing forward its capital payments and the decision to purchase additional shares. It remains a good value way to deliver development results in countries where the UK has a limited presence.
2. The 2023 Multilateral Organisations Performance Assessment Network (MOPAN) survey of AfDB stated: “The Bank is a robust organisation with a set of norms, standards, and procedures that by and large mirror those of peer organisations and support a highly relevant delivery programme in line with the organisation’s mandate [and it] is fit for the purpose of continuing to be a significant source of funding for Africa’s development, and an important provider of policy advice and intellectual leadership on a number of issues.”
3. The business case also noted the significant leverage offered by the high proportion of callable capital, which ensures the Bank can retain its AAA credit rating and thus raise cheap funding for onlending on terms better than its borrowers can obtain on the capital markets. The decision to pursue a general callable capital increase is a reflection of the Bank’s willingness to innovate.
4. The previous annual review included a detailed assessment of the four dimensions of value for money: economy, efficiency, effectiveness and equity:
  1. Economy: as noted in the previous annual review, the AfDB scored well against its peers in a Centre for Global Development study and that review found it to remain a lean operation relative to the IBRD. The cost containment framework has succeeded in controlling the rise in administration costs, capped at 2.9% annually, and reduced the proportion of costs met from African Development Fund donor grant contributions, even if that remains high. The cost containment framework is likely to be reviewed later this year with an increase in the annual cap expected to be proposed.

  1. Efficiency: The Bank scored as “satisfactory” for cost efficiency in the 2023 MOPAN survey, and “unsatisfactory” for timeliness (reflected also in output 2 above). It also noted scope to improve the efficiency of partnerships to better allocate resources across the partnership system and to improve the information system to provide detailed reporting on partnerships. It noted that delays in implementation and disbursement reflect “general problems with quality-at-entry reviews, unrealistic planning and targets, over-rated implementation capacity, and procurement delays … particularly … for complex projects and those in fragile contexts.” From the 2024 ADER the Bank has made progress on decentralising operations and staff, albeit with room for improvement, particularly on the latter (see also paragraph 46 under output 4 above). It has exceeded targets on financial mobilisation for public ($2.1bn mobilised) and private sector ($710 million mobilised) operations and climate financing and scored strongly on staff engagement and reducing vacancy rates. There has been no real movement on staff gender diversity indicators, however, and this should continue to be pressed in the Board.

  1. Effectiveness: the AfDB scored as “highly satisfactory” on responsiveness and “satisfactory” across indicators on achievement of results in the 2023 MOPAN survey. This also assessed mobilisation of private investors as a strength. It was third highest in the Publish What You Fund 2025 Development Finance Institutions Transparency Index for both sovereign and non-sovereign (private sector) operations, scoring maximum on impact management results for sovereign operations and third highest in non-sovereign. As discussed in section B, there has been an improvement in delivery of outcomes even if the picture on delivery of development results under output one is mixed, and it missed the target on delivery of planned development outcomes (output two) Against the High Fives. The 2024 ADER reported particularly strong performance against planned progress on Light up and Power Africa, Improve the Quality of Life (progress in Africa), Industrialise Africa and Integrate Africa with planned achievements in access to electricity, water, sanitation, education, transport and access to finance comfortably exceeded. The picture was more mixed on Feed Africa, with provision of agricultural inputs more problematic.
  2. Equity: There has been good progress on rollout of the gender marker system as reported under output three and the 2023 MOPAN report assessed AfDB as satisfactory on gender equality. The context is difficult; the 2024 ADER noted minor improvement in the Africa Gender Index score from 48.6 at baseline to (provisional) 50.3 in 2023 on a scale of 0-100. The Bank has a number of projects supporting women’s entrepreneurship and employment. The MOPAN report did, however, note scope for improvement on prevention of and response to sexual exploitation and harassment and in one country case there has been a failure adequately and promptly to respond to harassment of civil society organisations opposing relocation around an infrastructure project. There are questions around whether staffing and budgeting of compliance functions is adequate and poor follow up of audit and evaluation recommendations. These are being addressed at the Board.

Assessment of whether the programme continues to represent value for money

1. Based on the above analysis we believe that investment in AfDB capital continues to represent good value for money.
2. Recommendation IV: Review reporting lines and press for adequate staffing and budgets for AfDB compliance functions and for improved follow up of audit and evaluation recommendations.
3. Recommendation V: (carried over from previous annual review): FCDO should continue to press the Bank on decentralisation of professional staff, in line with FCDO organisational reform priorities, and track work on the decentralisation framework as part of the strategic staffing review. FCDO should also continue to engage with the Bank to ensure that it has the right staff with the right capabilities in place.
4. Recommendation VI: FCDO to monitor closely the administrative costs, including proposed amendment of the administrative cost-sharing formula, and ensuring that the control measures put in place by the Bank have been effective in preventing further increases.

E: RISK

Overview of risk management
1. There was no change in risk appetite over the year. There were, however, several key developments in the year affecting risk management.
2. Programme management capacity was strengthened with vacant posts filled and a new Deputy Team Leader position created within FCDO with a remit to support strengthened programme manage across the department.
3. The start of work to pursue a general callable capital increase, albeit finally agreed by governors in 2024, assured the bank’s AAA credit rating. This ensured it could continue with planned lending. Indeed, its capital position strengthened over the course of the year and lending volumes increased.
4. A major incident of fraud was escalated involving a loan repayment due to AfDB being sent to Latin American fraudsters. Senior Bank staff were arrested and mistreated by country authorities when investigating, albeit released after intervention of the Bank President. The funds have not been recovered. Measures have been put in place to prevent a recurrence.
5. Whilst safeguarding policies are considered robust the Bank was reported in November 2023 as off-track on some aspects of its Strengthening Safeguards Action Plan. This was raised at the AfDB Board. The April 2024 progress report on progress against GCI-VII policy commitments noted also that only 49% of audit recommendations were implemented within the agreed timeframe. Management did recognise that implementation of evaluation recommendations needed to improve also. These too, have been followed up at the Board. On the other hand, 100% of the Bank’s operations were fully appraised for environmental and social safeguard mitigation measures in 2023, exceeding its target of 93%.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

1. In 2024 Aid Transparency Index, AfDB’s sovereign portfolio ranked 1st amongst 50 development institutions, scoring 98.8 out of 100 for its performance. This was ahead of the Inter-American Development Bank, the United Nations Millenium Cooperation and the World Bank’s International Development Association, who ranked 2nd, 3rd and 4th respectively. The AfDB’s non-sovereign portfolio ranked 13th out of 50.
  [note] The Aid Transparency Index is the only independent measure of aid transparency among the world’s major development agencies. It is researched and produced by Publish What You Fund. See the 2024 here: 2024 Index - Publish What You Fund
2. AfDB delivery performance has been covered in Section D and output two above, whilst the 2022 annual review discussed findings from the Multilateral Organisations Assessment Network review. Further measures taken during 2023 include strengthening project preparation, new internal corporate key performance indicators, including two independently verified by IDEV and more support to client country project management units. Work was done to improve baseline data on quality at entry that can be used to track progress. Policy commitments.
3. There has been good progress on reform commitments to appraise all operations for environmental and social impacts, with 63% of relevant high and medium environmental and social risk operations having received at least one supervision mission, on track for complete coverage by 2025, only 49% of audit recommendations and 84% of evaluation recommendations were closed within agreed timeframes. A large audit backlog has compounded the delay. It is unclear this has received sufficient priority by operations staff.
4. Work on a review of the independence of key oversight, compliance and accountability functions of the AfDB continued over 2023 with a first progress report put to Governors at the Bank’s May 2023 Annual Meetings. A second progress report was provided at the 2024 Annual Meetings and a third at the 2025 Meetings. The Consultant submitted a final report in early 2025, to be evaluated by the Board of Directors.
5. The AfDB continues to be recognised by the major global credit rating agencies (S&P Global, Moody’s, Fitch Ratings and Japan Credit Rating Agency) with a AAA credit rating. The rating reflects that AfDB has:
- a strong capital base, conservative financial politics and liquidity;
- preferred creditor status, meaning member countries support the Bank; and
- robust institutional backing including from highly rated non-regional governments like Japan, Germany, Canada, the US and France.

In 2023, recognising the role that the Bank could play in supporting the continent’s continued response to global and regional shocks, the UK accelerated and completed its payment for its GCI VII subscriptions and the purchase of additional shares, totalling its shareholding to 1.868%.

1. The protection afforded by the Special Temporary Callable Capital Increase against a downgrade by the credit rating agency Fitch ended in December 2023. Governors agreed at the AfDB Annual Meetings in May 2024 to a General Callable Capital Increase (GCCI), which is expected to increase the authorised capital stock of the Bank to US$320bn. This should avoid the Bank having to come back shareholders ahead of the next General Capital Increase, anticipated around 2029.
2. Governors have been invited to subscribe for their allocated callable shares. The process will go through shareholder parliaments for approval. The UK has been allocated 157,548 callable shares created under the GCCI Resolution. All shareholders will be required to submit their Instruments of Subscription by the Bank’s final deadline of 31 December 2026.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

This review was completed by the FCDO’s core AfDB Programme team. Key sources of information used in parallel with the logframe for this this annual review were:
- AfDB’s 2023 Annual Report
- The Fifth Progress Report on the Implementation of GCI-VII
- The Annual Development Effectiveness Review (ADER) 2024
- The ADER 2023
- Consultations with the Bank’s management and wider bank staff
- Broader sources of information including external assessment of the Bank’s performance and effectiveness
- Consultations with FCDO colleagues who have direct experience working with the Bank.

As noted in the previous Annual Review (2022) it will be important to continue to engage with AfDB on implementing the recommendations in the annual reviews. Stakeholder interviews with regional and country teams in additional bank management will be an important factor to add to the Project Completion Review.

Date of last narrative financial report	May 2024 (covering the year to end-December 2023)	Date of last audited annual statement	May 2024 (covering the year to end-December 2023)