## Annual Review Template

Title: Accelerating Ethiopia’s Economic Transformation
Programme Value £ (full life): £45 million		Review date: June 2025
Programme Code : 300702	AMP start date: March 2020	AMP end date: October 2027

Summary of Programme Performance
Year	2020/21	2021/22	2022/23	2023/24	2024/25
Overall Output Score	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0002686.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006905.xlsx

Abbreviations
ACCELERATE - Accelerating Ethiopia’s Economic Transformation
AGOA - African Growth and Opportunity Act
BE - British Embassy
BMZ - German Federal Ministry for Economic Cooperation and Development (Bundesministerium für wirtschaftliche Zusammenarbeit und Entwicklung)
DDA - Due Diligence Assessment
EIC - Ethiopian Investment Commission
EIH - Ethiopian Investment Holdings
EPA - Environmental Protection Authority
ESA - Efficiency Saving Approach
FACT - Finance, Admin and Contracting Team
FCDO - Foreign, Commonwealth & Development Office
FDIs - Foreign Direct Investments
GIZ - Deutsche Gesellschaft für Internationale Zusammenarbeit GmbH
GoE - Government of Ethiopia
GRNI - Goods Received Not Invoiced
HIPIA - Hawassa Industrial Park Investors Association
ICF – International Climate Finance
IPDC - Industrial Parks Development Corporation
IPs - Industrial Parks
ITC - International Trade Centre
JICA - Japanese International Cooperation Agency
MOLSA - Ministry of Labor and Social Affairs
MoU - Memorandum of Understanding
NCE - No-Cost Extension
ODA - Official Development Assistance
OHS - Occupational Health and Safety
PPD(s) - Public-Private Dialogue(s)
PRO - Programme Responsible Officer
RRR - Retrospective-Refine-Redefine
SDA - Social Development Advisor
SEAH - Sexual Exploitation, Abuse and Harassment
SEZ(s) - Special Economic Zone(s)
SIC - Sustainable Industrial Cluster
SOEs - State-Owned Enterprises
SRO - Senior Responsible Owner
TAG – Textile and Garment Sector
ToC - Theory of Change
UKTP - UK Trade Partnership
VfM - Value for Money

A. SUMMARY AND OVERVIEW

Description of programme

The ACCELERATE programme (Accelerating Ethiopia’s Economic Transformation) was launched in 2020 with the objective of supporting the manufacturing sector to drive economic transformation in Ethiopia. It identified industrialisation as a pathway to transformational growth in Ethiopia and aims to address fundamental constraints in the sector, such as macroeconomic imbalances, red tape, weak capacity of the public sector, an untrained labour force and poor logistics. Since then, due to a reduction in the UK’s ODA budget, the programme has downsized to only one of the three original pillars. This remaining pillar is working with a reduced budget (from £22 million to £15.2 million). To adapt to this new budget, the programme has focused resources on supporting inclusive and sustainable operations in Industrial Parks (IPs). It is co-financed by the German Federal Ministry for Economic Cooperation and Development (BMZ) who provide an additional €12.5 million of budget. It is implemented by Deutsche Gesellschaft für Internationale Zusammenarbeit GmbH (GIZ).

The programme provides technical assistance in and around the Government of Ethiopia’s (GoE) Industrial Parks (IPs), and with government institutions. It aims to strengthen the resilience of firms in IPs and the surrounding clusters, and to enable the continued economic transformation of the sector, by:
1. Improving worker support systems within the IPs and surrounding clusters.
2. Supporting businesses in and around IPs to adapt their business practices to improve resilience.
3. Addressing business environment constraints faced by manufacturers in and around IPs.

In early 2024, the programme secured a 3-year extension until September 2027, with no additional cost implications. The programme logframe and theory of change (ToC) were adapted to reflect recommendations from the previous year’s annual review, wider macroeconomic challenges and the need to focus on making manufacturing companies in Ethiopia resilient. Since then, the UK and other donors, notably the US, announced further reductions in its ODA budget. The impact on the programme budget is yet to be confirmed but the reduction in development assistance highlights the need for Ethiopia to accelerate the shift towards a private sector led model of growth.

This annual review assesses the performance of the programme against the new reporting framework, covering the period April 2024 to March 2025. As the updated theory of change and logframe were implemented from October onwards, the revised/new indicators will only report from this period onwards. Where applicable, this is highlighted in Sections B and C.

Over the reporting period, the operating environment within Ethiopia has continued to change, with both positive and negative implications. These include:

Macroeconomic reforms: the Ethiopian Government agreed on far-reaching economic reforms aimed at stabilising the macroeconomic environment and spurring private-sector growth. In July 2024, the government floated the exchange rate for Ethiopian Birr (ETB), a bold move that aimed to address forex shortages and attract investment among other benefits. As a result, the gap between the exchange rates offered by commercial banks and the parallel market has narrowed, and the availability of foreign currency has improved significantly. At the same time, the government has enacted a strict fiscal policy with tight budget restrictions, banned Franco Valuta import scheme, which previously allowed importers with their own forex to bring in essential goods, and implemented a more transparent governance system that aims to improve efficiency and stability. These changes have helped stabilize the economy and decrease the rate of inflation to 15.5% in January 2025. However, there are concerns about the accuracy of the official inflation figures. The exchange rate gap between banks and the parallel market has risen in recent months, reaching 20%. This poses a significant risk to maintaining the positive impact of the economic reforms.

Transforming Industrial Parks to Special Economic Zones (SEZs): 10 IPs (out of 13) were transformed to SEZs. Amongst other changes, this allows investors to retain 100% of foreign exchange earnings, creates new banking and customs instruments to support the SEZs to become trading hubs, and offers greater flexibility by allowing businesses to operate across various sectors, including manufacturing, trade, logistics, ICT, finance, and services.

Structural Changes to IPDC: as part of the restructuring of several State-Owned Enterprises (SOEs), the IPDC was incorporated under the Ethiopian Investment Holdings (EIH) in late 2024, which is the Government of Ethiopia’s sovereign investment arm. This is expected to improve the management of the corporation and could lead to a more private-sector model of management. IPDC has also secured new licenses to engage in new sectors like construction, transport, manufacturing and other services.

Change in leadership: there has been a change in leadership within the Ethiopian Investment Commission (EIC) and the Industrial Parks Development Corporation (IPDC). The new leaders have expressed an increased commitment to economic transformation (incl. the manufacturing sector) and have significant political sway withing the government. This could improve the effectiveness of programme activities. However, this follows several changes in leadership over the last three years, which also creates risks in terms of continuity and change management.

Regional and local instability: the volatile security situation within Ethiopia and instability within the Red Sea has implications for key logistic corridors, production lead times and cost, and supply chain reliability. Coupled with Ethiopia’s reliance on the Djibouti corridor for more than 95% of its import/export and wider infrastructure issues this has raised the cost of logistics and lead time for producing goods.

International trade: Ethiopia was suspended from AGOA (the US African Growth and Opportunity Act) in late 2020, which cut duty-free benefits. This led to a reduction in orders from the US and exports and employment in IPs fell. More recently, the announcement of new tariffs imposed by the USA has led to a renewed interest from US buyers as Ethiopia will face the lowest level of tariffs (10%) compared to other textiles and garments exporters.

Donor landscape: the pulling of funding by USAID, and announcements of reducing ODA by the UK, France and Germany will have implications for funding available to support development and growth in Ethiopia.

Summary supporting narrative for the overall score in this review

The programme has scored an A for the review period.

All output and outcome indicators have been met or exceeded. The new outcome and output targets for this financial year, specified in the updated logframe, were set for the second half of the financial year. They cover the period October 2024 - March 2025, given the implementation of the new phase or the No-Cost Extension (NCE) started in October 2024. The logframe set several milestones for this financial year at zero recognising that some programme inputs will translate into outcomes over a longer time frame. This approach ensures flexibility to provide patient capacity building support in a challenging context. Where outputs targets have been exceeded, this is predominantly the continuation of previous outputs (incl. buyer linkages and worker support).

Two of the impact indicators, regarding export growth and job creation, were met. One impact indicator missed its target (regarding the share of textile and garment exports in total exports). This was predominantly due to the rise of coffee exports rather than a decrease in value of textiles – shown by annual exports value maintaining its value. The impact indicators remain dependent on the wider political economy of Ethiopia and the global market, which are beyond the sphere of influence of the programme. As part of the no cost extension to the programme, the theory of change and indicators have been revised for the remaining period. The links between outputs, outcomes and impacts have been strengthened, and the ambition for the programme is more aligned with the funding available, the economic realities of the manufacturing sector and the programme’s scope.

The programme has achieved or moderately exceeded all outcome and output targets for the reporting period, with 6 out of 6 outcome indicators and 7 out of 7 output indicators met or surpassed. This strong performance demonstrates effective delivery at the output and outcome levels, providing a solid foundation for progress towards the programme’s intended impact, despite external challenges affecting the impact indicators

The implementing partner, GIZ, continues to deliver the programme successfully, building on strong relationships with the individual companies, as well as key stakeholders across the Ethiopian government. They have shown flexibility in adapting to the revised ToC and logframe, as well as recommendations provided in last year’s annual review. The stakeholders met during this review had a positive perception of GIZ’s delivery, including a collaborative approach to designing interventions, high quality and independence of advice provided, and responsive communication style. GIZ maintains a strong reputation with key senior stakeholders within the Ethiopian government, especially as other development partners withdraw due to budget cuts. Issues reported often stemmed from insufficient funding for all companies to attend international trade events (given the demand), and occasional delays in the provision of technical assistance or deployment of expertise.

This annual review was led by an external reviewer in partnership with the FCDO programme team. The recommendations listed in the annual review on behalf of the reviewer have been agreed with the FCDO programme team.

Summary of Last year’s (2024) Annual Review Recommendations and Progress

Recommendation: The reviewer recommended that the revision of the theory of change and logframe as part of the no-cost extension should build in links to adjacent programming and investment portfolios. More detail are provided in Section B.
Progress: (Completed). The theory of change and logframe have been adapted for the follow-on project, with a review planned for summer 2025.

Recommendation: The reviewer recommended that the programme continuously assess trade-offs between addressing multiple barriers and focusing on fewer, more holistic activities during implementation. More detail are provided in Section B.
Progress: (Completed). This was considered in the design of the second phase and will continue to be assessed.

Recommendation: The reviewer recommended that the programme continue to explore the case for a national minimum (living) wage, involving all relevant stakeholders, despite political sensitivities and external challenges. More detail are provided in Section C.
Progress: (Ongoing). The minimum wage discussion lost political backing due to macroeconomic reforms and birr devaluation. SIC continues conversations with stakeholders and plans a minimum wage study, aligning with partners such as ILO and CETU.

Recommendation: The reviewer recommended that GIZ conduct an assessment on the drivers of high staff turnover in IPs and identify possible interventions to mitigate the issue, beyond minimum wage. More detail are provided in Section C.
Progress: (Ongoing). Wage and benefits are confirmed as key determinants of turnover. Advisory and activities on increasing wages are part of the project design. Further follow-up with GIZ on prior and new assessments is planned.

Recommendation: The reviewer recommended that GIZ conduct an assessment on safeguarding (SEAH of workers) and whether worker welfare has improved or deteriorated as a result of interventions and gather robust evidence. More details are provided in Section C.
Progress: (Completed/ Continuous). A worker survey was conducted in March 2025 and showed most workers experienced improved living and working conditions. Targeted interventions such as the STOP programme and anti-sexual harassment committees continue to be implemented to reduce safeguarding risks and promote worker welfare, following the discontinuation of the call centre and some welfare services. Ongoing monitoring and future surveys will continue to assess progress.

Recommendation: The reviewer recommended that the programme consider the impact of handouts to beneficiaries and explore more sustainable models to limit market distortion. More detail is provided in Section C.
Progress: (Completed). This has been addressed in the new phase.

Recommendation: The reviewer recommended that training in standards and certifications continue to be leveraged in park operations and informed by company feedback. More details are provided in Section C.
Progress: (Ongoing).  Ongoing follow-up with IPDC and stakeholders to ensure ownership and sustainability; continuous feedback from companies is needed.

Recommendation: The reviewer recommended that new measures to improve IP operations should take into consideration the UK’s relevant standards. More detail provided in Section C.
Progress: (Completed). This has been addressed in the design of the new phase.

Recommendation: The reviewer recommended that the programme consider how to ensure sustainability of measures introduced to improve IP operations after the programme ends. More detail is provided in Section C.
Progress: (Ongoing). Ongoing follow-up with IPDC to ensure ownership and sustainability; requires continuous monitoring.

Recommendation: The reviewer recommended that the co-investment arrangement and demand-driven model for certification and standards be maintained to ensure sustainability. More detail provided in Section C.
Progress: (Ongoing). SIC follows a market-led upgrading strategy; co-investment is a key criterion. Certifications are only supported where there is clear buyer demand.

Recommendation: The reviewer recommended that support for local and international orders (backward and forward linkages) remain a priority, with realistic targets and partnerships for private sector development. More details are provided in Section C.
Progress: (Completed/Continuous).  Promising companies have been identified for vertical integration. Indicators have been added to measure linkages. Further funding and cooperation are needed for full support.

Recommendation: The reviewer recommended that the programme continue supporting market linkages, especially towards new European and African markets, and build on collaboration with other FCDO programmes. More details are provided in Section C.
Progress: (Completed/Continuous).  Buyer matchmaking interventions are in place. FCDO linkage with other relevant programmes will be considered in the new phase.

Recommendation: The reviewer recommended that the programme keep engaging with government institutions and leverage relationships to maximise outcomes, considering constraints and opportunities. More details are provided in Section C.
Progress: (Completed/Continuous).  The follow-on project addresses key issues directly and works with relevant stakeholders in both private and public sectors.

Recommendation: The reviewer recommended that logframe indicators be disaggregated by IP/industrial cluster to better understand the spread and impact of interventions. More details are provided in Section G.
Progress: (Ongoing). To be considered in future reports. The project is reviewing how to adapt reporting formats.

Recommendation: The reviewer recommended that the breakdown by gender across logframe indicators be improved to better assess impact on women’s economic empowerment. More details are provided in Section G.
Progress: (Ongoing). Where relevant, indicators will be disaggregated by gender in future monitoring and evaluation.

Major lessons and recommendations for the year ahead

Recommendation 1: The reviewer recommends that FCDO and GIZ prioritise and strategically select activities under output 3 to maximise impact on the manufacturing sector, focusing on areas where technical assistance can drive real improvements. A more strategic approach to output 3 should be agreed by July 2025 and regularly reviewed. More details are provided in Section B.

Recommendation 2: The reviewer recommends reviewing whether the logframe targets are ambitious enough, given strong progress and government momentum. This should consider potential future UK budget reductions. FCDO and GIZ to agree an approach by December 2025; more detail in Section B.
Recommendation 3: The reviewer recommends continuing with yearly mapping of development partners operating in and around the Industrial Parks, and on related topics, to ensure efficient use of resources amid reduced funding. This will help identify duplication and opportunities for collaboration. Lessons from existing partnerships should inform future donor relationships. More detail in Section B.

Recommendation 4: The reviewer recommends developing an exit strategy with government to ensure continued worker welfare support after the programme ends, given the closure of call centres and limited EIC capacity. This is needed to prevent a gap in support once ACCELERATE closes. More detail in Section C.

Recommendation 5: The reviewer recommends that by March 2025, the programme conducts an independent, sensitive survey on SEAH prevalence in Industrial Parks to assess the impact of worker welfare activities and inform future programming. Key findings should be shareable with FCDO and government and used to support discussions on establishing a sustainable grievance mechanism. More detail in Section C.

Recommendation 6: The reviewer recommends immediately allocating a new Social Development Advisor (SDA) on the programme team to maintain adequate safeguarding oversight. If replacement is not possible due to budget constraints, the team should escalate this as a risk for discussion and mitigation or formal acceptance by August 2025. More detail in Section C.

Recommendation 7: The reviewer recommends a light touch analysis of data on manufacturers involved in buyer matchmaking to identify which businesses succeed and which need more support. This will help target services more effectively and should include lessons from the UK Trade Partnership programme. Complete this by October 2025 to inform future programming. More details in Section C.

Recommendation 8: The reviewer recommends the programme team and GIZ agree on clear criteria for when solutions are sufficiently advanced to be counted under indicator 3.2, to avoid ambiguity in reporting. This agreement should be reached before the next annual review, by October 2025. More detail in Section C.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme’s theory of change (ToC) was updated in 2021/22 to account for significant reductions in the UK’s ODA budget, and again for the no cost extension of the programme (2024/25 onwards) to respond to changes in the operating environment. The focus of the programme remains on supporting the development of Ethiopia’s manufacturing sector, through enabling decent jobs and sustainable industries.

The reviewer supports the revised ToC, noting the strengthened logic chain, improved assumptions and more achievable ambition. The updated ToC reflects the significant challenges to the operating environment (set out above). It has pivoted from pursuing an expansion in Ethiopia’s manufacturing sector, to work on maintaining the resilience of IPs, preventing job losses, and promoting safeguarding and environmental practices. It better reflects the impact that the programme can have, focusing on their ‘sphere of influence’ within the IPs.

The ToC takes on board the recommendations made from the previous year’s annual review:
1. It has strengthened the assumptions and logic chain which links the outputs, outcomes and impacts of the programme.
2. The outputs and outcomes have been adapted to better reflect what is possible through the programme, focusing on a smaller number of deeper interventions.
3. Indicators are now disaggregated by gender and by IP where relevant, to build a clearer picture on the variation of implementation.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

In the year in review, the programme has achieved 2/3 impact indicators and achieved or moderately exceeded 6/6 outcomes and 7/7 outputs. The table below provides more detail:

Indicator Level	Target by end of programme (By 2027)	Period Covered	March 2025 milestone target	March 2025 actual results
Impact: / Manufacturing sector contributing to economic transformation in Ethiopia	Total labour force in selected companies inside and outside IPs is increased to 60,000 workers, of which at least 70% are female.	Oct 2024 – Mar 2025	57,000	57,335 (of which 45,106/ 78% are women)
	Annual exports of selected companies inside and outside of IPs increased by 20%.	Apr 2024 – Mar 2025	$102 million	$102.5 million
	The share of textile and garment exports in total exports is preserved at 3%.	Apr 2024 – Mar 2025	3%	2.5%
Outcome: / The resilience of firms in industrial parks and surrounding clusters is strengthened, to enable continued contribution to economic transformation of the sector	55% of 18,200 workers (of which 70% are women) in the Ethiopian manufacturing sector confirm that their working conditions have improved (Revised Indicator)	Oct 2024 – Mar 2025	1,141	1,326 cumulative workers, / 185 (of which 82% are women) for this reporting period
	Manufacturers in Ethiopia have received 20 international orders. (New Indicator)	Oct 2024 – Mar 2025	6	9
	Manufacturers in Ethiopia have received 10 local orders. (New Indicator)	Oct 2024 – Mar 2025	3	3
	15 manufacturers in Ethiopia have improved their environmental sustainability performance in line with international standards. (Revised Indicator)	Oct 2024 – Mar 2025	0	0
	150 individuals and 15 organisations informed by International Climate Finance technical assistance. (Revised Indicator)	Oct 2024 – Mar 2025	0 individuals, 0 organisations	2 individuals, 2 organisations
	3 business environment constraints faced by the Ethiopian textile and garment sector are eased based on policy advisory by the project. (New Indicator)	Oct 2024 – Mar 2025	0	0

Given the addition of new indicators in October (halfway through the reporting period), the milestones for new outcome indicators focus on maintaining the baseline and/or recognise that groundwork is needed before results are seen – for example, it can take 1-2 years for activities that link Ethiopian manufacturers to international buyers to lead to new orders. The milestones for outcomes increase from the next reporting onwards to reflect this, and the programme seems on track to meet future outcome indicators.

On the other hand, ongoing challenges from the business environment is causing some international buyers to either reduce or stop production in Ethiopia. These decisions are not snap decisions but are often based on the experience of several years. A major European buyer recently decided to stop sourcing from Ethiopia, citing the country’s security challenges. This will impact annual exports. Despite the success in securing new international orders, it will take significant time and effort to replace this level of export volume. Furthermore, even if export volumes from the TAG sector increase, exports from other sectors like agriculture or mining could show significantly higher rate of growth either in volume or USD earning which at the end could lower the share of the TAG sector from the overall sector. As a result, there is the possibility that the programme will not meet its impact indicators on the value and share of exports in future years.

Overall, we assess the critical assumptions in the Theory of Change broadly still hold true. These are:
- Industrialisation and structural and transformation remain important objectives for GoE.
- Key barriers to industrialisation are beyond the scope of the programme to change (e.g. macroeconomic reform, conflict resolution)
- Despite this, programme interventions can improve the resilience of firms and industrial parks to secure new orders with buyers.
- Firms and industrial park management are willing to adapt their practices to align with buyer requirements.
- Project implementation is possible amid a fragile security context.
These assumptions recognise that key barriers to the growth of the manufacturing sector are outside the programme’s control but note that programme activities can nevertheless build the resilience of the sector in this context. This informed the design of indicator milestones. The Theory of Change also implicitly recognises that positive shocks that are outside the control of the programme (e.g. further efforts by government to liberalise economic sectors or an abatement of the Red Sea crisis) could improve export performance. In other words, shocks could be positive or negative and the programme aims to build the resilience of firms to such shocks. No significant change to the VfM of the programme is predicted, given the core assumptions in the Theory of Change hold true. Given the significant work done to update the theory of change and the limited time remaining for the programming (there is uncertainty regarding budgets after this financial year, i.e. between April 2026 and September 2027) no major reassessment of the theory of change is proposed. However, the programme team will continue to monitor whether key assumptions still hold through its biannual assessments of the theory of change and the logframe (as per recommendation 2 below).

In addition, the performance and resilience of individual Investment Parks varies significantly. For example, Bole Lemi IP is operating at full capacity and is moving into Phase 2 of its expansion through leasing land for manufacturers to build new sheds – its popularity stems from its proximity to Addis Ababa and the political stability of the area. In comparison, Hawassa SEZ has seen the departure of buyers and in Dire Dawa SEZ a company laid off all but 6 workers due to delayed orders as a result of the Red Sea Crisis. The ability to support the resilience of IPs will vary based on the individual circumstance of each IP – breaking down the impact indicator into performance by IP shows a very mixed picture.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against recommendations from last year’s annual review

Recommendation: The revision of the theory of change and logframe as part of the no-cost extension should build in links to adjacent programming in the BE Addis’ programme and investment portfolio where possible to strengthen assumptions and mitigate risks.
Progress: (Completed). The theory of change and logframe has been adapted to fit the follow-on project with the understanding to review in the summer of 2025. In this timeframe, the results of the macroeconomic reforms and effect of the birr devaluation should be known.

Recommendation: It will be key in the selection of priorities activities in the 3-month remaining implementation period of the programme, and the 3-year no-cost extension, to continuously assess trade-offs between more limited contributions addressing multiple barriers to the development of the sector against fewer activities delivering more holistic results with tangible results on outcome level.
Progress: (Completed). It will be key in the selection of priorities activities in the 3-month remaining implementation period of the programme, and the 3-year no-cost extension, to continuously assess trade-offs between more limited contributions addressing multiple barriers to the development of the sector against fewer activities delivering more holistic results with tangible results on outcome level.

Key lessons and recommendations for the year ahead
Key lessons

Lessons learned this year highlight the persistent challenge of converting strong delivery at the output and outcome levels into lasting impact, particularly given the volatile operating environment and ongoing budgetary constraints. The program’s experience has shown that while targeted interventions can enhance firm resilience and secure new orders, broader economic and policy barriers such as inconsistent reforms and external shocks continue to limit progress towards impact-level objectives. These barriers are often driven by complex political decisions which are difficult (but not impossible) to influence through the programme. This has reinforced the need to creatively identify activities that can impact business environment constraints. Furthermore, the importance of a nuanced understanding of worker welfare has become clear, with a need to disaggregate survey findings to better inform interventions. Finally, as funding has reduced and the donor landscape has shifted, it is increasingly critical to map and coordinate with other development partners to maximize the efficiency and effectiveness of available resources. These lessons have directly informed this year’s recommendations, which call for a more strategic focus, enhanced monitoring and evaluation, and strengthened collaboration within the sector.

Recommendations for the year ahead

Recommendation 1: While the outputs and outcomes of the programme have been met comfortably, the ability to translate that into achievement at the impact level continues to be challenging. The reviewer recommends that the FCDO and GIZ teams think more carefully about how to prioritise activities under output 3, which aims to address business environment barriers that impact the manufacturing sector. The team should agree a more strategic approach to output 3 by July 2025 and continue to monitor and test this approach regularly over the remainder of the programme. Programme activities under output 3 should be selected carefully and strategically with a clear path to impact. Support to government should focus on impact rather than supporting government processes. Engagement with EIC and other government stakeholders should identify areas where technical assistance can credibly drive an improvement in key issues such as logistics or access to finance. The reviewer also recommends coordinating across stakeholders to present a united picture on the importance of addressing these issues. This could include drawing on BE Addis Ababa and FCDO Seniors/Ministers, European buyers and the German Embassy.

Recommendation 2: The support that the programme provided this year, e.g. on buyer linkages, and meeting international standards, will deliver results over future reporting years. At the same time, the uncertain operating environment and potential future budget reductions from the UK create risks. Therefore, the reviewer recommends that the programme team review whether the ambition set out in the logframe is appropriate for the rest of the programme’s duration by December 2025.

Recommendation 3: the reviewer recommends continuous mapping of all development partners who are operating in and around the Industrial Parks, as well as on topics that are related (e.g. on working conditions, logistics, business environment). As the amount of funding for the programme has reduced, and USAID have cut funding to the IPs, it has become increasingly important to use development resources efficiently and effectively. Understanding the wider donor landscape could help to identify areas of duplication or where collaboration would be useful, e.g. through consistent messaging on issues that need to be addressed. GIZ have already successfully established links to other programmes that they deliver as well as other active partners such as the ILO and IDH. Lessons learned should be drawn from this and applied to other donor relationships.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue to operate for the remainder of the no cost extension.

Delivery against the outputs and outcomes is strong and shows potential to expand to meet the milestones for future reporting years and delivers good value for money. The programme has built good momentum in delivering business environment easing with the government and has a good track record of delivery for individual companies and each Industrial Park. Discontinuing the programme would cut this momentum short, just as it is increasing its level of impact. While the impact indicators remain vulnerable to the wider operating context, the programme will continue to support the resilience and performance of the Industrial Parks even if this context is challenging.

Further, this programme is an important part of BE Addis Ababa’s support for economic development and growth in Ethiopia (with most other funding focused on humanitarian, resilience, human capital and governance issues).

## C. DETAILED OUTPUT SCORING

Output Title	Worker support systems in the selected industrial clusters are improved.
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	Up from 25%

Indicator(s) by programme end (September 2027)	Milestone for March 2025	Progress against milestone (Oct 2024 – Mar 2025)
1.1 - 3,000 female workers in the Ethiopian manufacturing industry have used support services to improve their working conditions (from baseline of 886).	1030	1,288 (Exceeded) – during this reporting period 402 female workers used support services to improve their working conditions.
1.2 - Workers in the Ethiopian manufacturing sector have developed 10 approaches to improve their working and living conditions in collaboration with relevant stakeholders (from a baseline of 5).	5	5 (Met) – no new approach to improve working and living conditions has been developed during this reporting period. The baseline target for new approaches was set at five, which had already been met prior to this period and remains unchanged at five, with no additional approaches introduced.

NB: Where possible, indicators are measured cumulatively and have been designed with a baseline figure for September 2024 that corresponds to actual results achieved at the end of the first phase of the programme (i.e. for the period until September 2024). This is to enable cumulative tracking of results over the entire length of the programme (2020-2027) where indicators have stayed the same.

Briefly describe the output’s activities and provide supporting narrative for the score.

High quality working and living conditions for workers are essential for worker welfare and are often the driver behind high turnover for companies within the Industrial Parks. Further, due to the reduction in orders from the USA, companies are increasingly seeking European buyers who typically have higher social compliance requirements for manufacturers. Therefore, improvements in conditions are essential both for worker welfare and the resilience of companies in the IPs.

While no new approaches to improve conditions were developed during the shortened reporting period, significant activities continued to be implemented and expanded. New approaches refer specifically to innovative or previously untested methods introduced to improve working conditions; during this period, the focus was on scaling up and deepening the impact of existing interventions rather than introducing additional new methods.

In total, 1,288 female workers have used support services to improve their working conditions, exceeding the milestone target. During this period, 697 workers (568 women) participated in Accelerate-provided trainings. Of these, we count only 402 female workers towards the indicator, as 295 participated in a one-off nutrition training which does not fit our definition of support. Key developments include the expansion of the STOP programme (aimed at creating a harassment-free workplace by embedding policies, complaint mechanisms and awareness initiatives) to 20 new factories; the Hawassa-based worker’s café expanded its reach, and a new café will be launched in a different IP. Following the adoption of the anti-sexual harassment policy by the Hawassa Industrial Park Investors Association (HIPIA), the project shared the policy with the Bole Lemi and Hawassa SEZ for adoption at the park level.

The companies who received trainings through the programme provided significant positive feedback. The trainings provided included on anti-sexual harassment (for both managers and workers), human resources (HR) policies, occupational health and safety (OHS), and support for workers moving from rural areas to the IPs. Due to high turnover in the IPs, companies who have received one-off trainings voiced their intention to seek out follow-up trainings when appropriate. During the meetings with management of selected companies it was noticed that some of them lacked an understanding of what SEAH and mental health issues included and did not seem to appreciate the importance of their responsibilities around that. This is an indication that the programme could consider what further actions it can take to ensure top level managers take part in trainings and give proper attention to workers’ welfare. However, this is not fully within the programme’s control.

A worker survey conducted in March 2025 across supported IPs showed that 82% of workers reported improved living and working conditions, 72% of female respondents indicated trade union membership, and 87% of respondents received a salary increase in the past year, though wages remain low relative to inflation. The survey also noted reduced access to support services following the discontinuation of some other donor welfare programmes.

Despite this, challenges to workers’ conditions remain. Salaries were cited as the largest driver of staff turnover for companies, even when complemented with additional incentives (e.g. free meals, free healthcare). This is in part driven by inflation following the floating of Ethiopia’s currency, which has increased the cost of living (especially around Addis Ababa). The programme has initiated work to support the development of a minimum wage, including drafting a methodological approach for a wage study in Hawassa and Bole Lemi IPs to be commissioned this summer. However, official government plans to institute a minimum wage have not progressed given the general complexity of instituting a nationwide minimum wage (currently non-existent) and falling political backing by the Ministry of Labour Standards following the macroeconomic reforms. Many of the textile companies within the IPs have informally implemented a minimum wage, especially in reaction to social compliance requirements from new buyers.

During this reporting period, the workers’ grievance handling mechanism, and specifically the call centre operations in Hawassa and Bole Lemi IPs was stopped due to EIC being unable to replace (re hire) call centre staffs that mostly left as their contracts were not extended. This is discussed further in section E. Data collected through the GIZ annual survey shows that over the past year, a total of 698 grievances were recorded across all surveyed partner factories, with individual companies reporting between 0 and 150 cases. Of these, 73% of companies recorded grievances related to wages, and 30% related to working hours. Only one company reported grievances concerning workplace harassment and discrimination, although this contrasts with SEAH reports from two other companies discussed in the following paragraph. Notably, 96% of all grievances received were noted to have been resolved internally. There were no significant differences in grievance patterns between companies inside and outside industrial parks.

The programme is on track to meet future targets for this output.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The overall objective of the output remained the same as the previous year, but the two indicators were updated to reflect recommendations from last year’s annual review relating to the ability to monitor the impact of activities to improve worker welfare. These were implemented from October 2024 onwards and allow more effective tracking of progress.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against recommendations from last year’s annual review

Recommendation: The reviewer is supportive of the programme exploring the case for the development of a national minimum (living) wage, despite the challenging external environment and the low wages being one of Ethiopia’s key USPs (unique selling points). With new German legislation (German Supply Chain Act) requiring manufacturers or those in buyer supply chains to pay an adequate wage (which meets the national minimum wage or goes beyond that) there is the potential to find a solution which maximises outcomes for government, workers, local businesses and investors. Additionally, many buyers from the UK and across the EU also require a national minimum wage to source from a country (e.g. Primark). Therefore, the programme should continue the support for the agenda and include all relevant stakeholders in the process, recognizing that the issue is politically sensitive and challenging to attain. Such efforts should include all stakeholders, including significant momentum noted from discussions with the Investor Association in Hawassa IP.
Progress: (Ongoing). Minimum wage discussion lost political backing by MoLS due to macroeconomic reforms and birr devaluation. SIC continues conversation with HIPIA and other relevant stakeholders for conducting planned minimum wage study, identfiying the right time for creating a renewed momentum, while also alinging with other partners active in the area (e.g. ILO, CETU, FES, etc)

Recommendation: High staff turnover amongst firms in the same IPs coupled with worker satisfaction suggest that services provided are enhancing the IPs’ ability to attract workers even if individual companies struggle to retain workers. The reviewer recommends looking more closely at what is driving staff turnover and what is in the scope of this programme to change this (beyond work to explore a minimum wage). Indicators that better capture and reflect underlying drivers of worker satisfaction could be developed to increase the impact and value for money of activities under this output.
Progress: (Ongoing). There are many studies that show wage is key determinant of turnover (see also SIC I inception report). Hence, advisory and activities on increasing wages are part of project design. Gap assessment confirmed that wage/ benefits are also main determinant of productivity.

Recommendation: While activities such as the grievance call centre and various training/capacity building on e.g. SEAH of workers/management of IPs and their companies have yielded positive results on safeguarding, it remains challenging to assess whether worker welfare has improved or deteriorated. There are some risks to continued momentum (e.g. staff shortages at grievance call centres) that will need to be kept under review to ensure the impact of measures already undertaken by the programme (e.g. developing the SOPs) are sustained. The team should also consider more systematic and robust anonymised evidence gathering to enforce existing mechanisms and how to involve government, buyers and investors in this process effectively to achieve impact.
Progress: (Completed). A worker survey was conducted in March 2025 and showed most workers experienced improved living and working conditions. Targeted interventions such as the STOP programme and anti-sexual harassment committees continue to be implemented to reduce safeguarding risks and promote worker welfare, following the discontinuation of the call centre and some welfare services. Ongoing monitoring and future surveys will continue to assess progress.

Recommendation: While many interventions under this output are designed to be sustainable and/or market-led, there are a number of cases of contributions given to beneficiaries (e.g. computers, sanitary pads, soap, or textbooks given to participants after a training). It will be important to consider the impact of such handouts and if more sustainable models could be used in the future to limit market distortion and create more local economic opportunities.
Progress: (Completed). Completed and has been taken into consideration on the new phase of SIC ll.

Key lessons and recommendations for the year ahead
Key lessons

Lessons learned this year show the vulnerability of worker welfare initiatives to shifts in government priorities and external funding, as evidenced by the closure of the call centre and the stalled progress on instituting a national minimum wage. As a result, the programme must carefully consider how to allocate its resources for the greatest and most lasting impact, particularly in areas where safeguarding risks remain unaddressed. These lessons have directly informed this year’s recommendations, which call for the development of a government-led exit strategy for worker welfare, the commissioning of an independent survey on the prevalence of SEAH to inform future programming and safeguarding mechanisms, and the urgent replacement of the Social Development Advisor to ensure continued oversight and risk management.

Recommendations for the year ahead

Recommendation 4: Call centres in Hawassa and other IPs which provide a mechanism for workers to anonymously report their grievances (including those related to SEAH) to EIC have either stopped working or are operating in a diminished capacity, partly because of the closure of Plan International’s programme that was funded by USAID. While under the jurisdiction of the EIC, they have not provided the funding or staff to reinstate the centre in the absence of donors’ support, due to an EIC-wide hiring freeze. This highlights the risk that support for worker welfare might cease once the ACCELERATE programme closes due to a lack of capacity or momentum from government. Before the end of the programme, the reviewer recommends developing an exit strategy with government on worker welfare to take over the provision of worker welfare support.

Recommendation 5: to complement recommendation 4, the reviewer recommends that by March 2026, the programme undertake an independent survey on the prevalence of SEAH instances within the Industrial Parks. This can be used to assess the impact of worker welfare activities throughout the programme and to inform future programming, whether by the UK FCDO or other development partners. This survey should be designed in a way that is sensitive and protects workers’ privacy, but key results should be sharable with the FCDO and government. It could include a survey of a sample workers across different IPs, to understand: 1) the prevalence of SEAH, 2) the reporting rate, 3) the mechanisms through which this is reported (and the implications of the call centre closing), 4) proposals for how to address safeguarding issues. Additionally, the programme could use the findings as a basis to initiate discussions with the relevant government authorities including the EIC, IPDC, and Ministry of Labor and Social Affairs (MOLSA) so that a sustainable grievance handling mechanism is put in place for workers (as part of recommendation 4).

Recommendation 6: the 2023 Annual Review and Due Diligence Assessment noted the importance of increased scrutiny from the FCDO team of the programme’s safeguarding risks, including through reinstating a Social Development Advisor (SDA) as part of the programme team. The reviewer notes that an SDA was allocated to the programme team in 2023, but this staff member left the British Embassy Addis Ababa in May 2025. The reviewer recommends immediately replacing the SDA on the team to ensure adequate programme management and advisory support. If this is not possible due to staff budget constraints, the programme team should escalate this as a risk for discussion to identify potential mitigating actions or formally accept this risk. This should be done by August 2025.

Output Title	Firms and industrial parks in Ethiopia have adapted their business practices to strengthen their resilience.
Output number:		2	Output Score:	A
Impact weighting (%):		45%	Weighting revised since last AR?	n/a

Indicator targets for 2025	Milestone for March 2025	Progress (Oct 2024 – Mar 2025)
2.1 - 15 manufacturers in Ethiopia have implemented measures to align their business practices with requirements of international markets (from a baseline of 0).	3	3 (Met) – three manufacturers implemented measures to align their business practices with international standards, incl. through obtaining internationally recognised certificates, improving productivity performance and strengthened quality control.
2.2 - 250 business linkages between companies and international buyers/ IPs have been established (from a baseline of 69).	90	102 (Exceeded) – During the reporting period, 363 encounters between manufacturers in Ethiopia and international buyers were facilitated, of which 68 resulted in price quotations and 33 in exchange of samples. Only the latter (33) is counted towards the indicator for this period, bringing the cumulative total to 102 business linkages as of March 2025, which exceeds the target. Since this indicator is cumulative, this year’s results (33) were added to last year’s results (69), resulting in a total of 102 business linkages.
2.3 - Industrial parks have implemented 14 measures to align their operations with international requirements, of which 1 measure focuses on the mitigation of GHG emissions (from a baseline of 9).	9	9 (Met) – during the reporting period, one new measure was implemented to align IP operations with international requirements, building on the eight measures established as of September 2024. The latest measure enables SEZs and companies to align with EPA’s Certificate for Green Compliance, further promoting eco-friendly operations.

Briefly describe the output’s activities and provide supporting narrative for the score.

Building resilience in the Industrial Parks has become increasingly important in the face of challenges to manufacturing in Ethiopia. With the suspension of AGOA and increase in local and international conflict, manufacturers in IPs face challenges securing and maintaining international buyers.

The programme has built on the success of Phase 1, by taking a ‘broker’ approach when facilitating links between manufacturers in Ethiopia and European buyers. This included hosting the second international buyer delegation at the Africa Sourcing Fashion Week in Addis Ababa and supporting 15 manufacturers to exhibit in the Made in Ethiopia pavilion and supporting 12 Ethiopian manufacturers to exhibit their products at TexWorld in Paris. There has been a focus on diversifying buyers away from the USA (due to the AGOA suspension), towards European buyers – including a focus on Germany and the UK.

While the diversification towards European buyers is welcomed by companies, there is also a recognition that the volume of orders from Europe is much smaller than that from the USA. While the value per piece tends to be higher in Europe, the shift away from the mass market model favoured by US buyers is a challenge for Ethiopian firms who are still growing their productivity to compete with leading exports such as Bangladesh.

European buyers also typically have higher environmental and social compliance standards. The programme has supported 3 companies (Maa Garment, Desta, and Adama Spinning) to implement changes to meet these standards. This support has been highly valued, but there is a risk of its sustainability following programme closure – many standards require annual renewing, often using external experts (currently sourced and funded by the programme).

The programme is on track to meet future milestones on Output 2, including when milestones increase significantly. Forming business linkages between companies and international buyers can have a lead time of 1-2 years, from introduction to securing the deal. Future years will benefit from the groundwork delivered in this reporting period.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output has combined elements of outputs 2-4 of the previous logframe, covering technical and structural conditions for environmental sustainability, social compliance and buyer linkages. This output was implemented from October 2024 onwards and allows more effective tracking of progress. It reflects the recommendations made from the previous year’s annual review (see below).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Changes to this output reflect the recommendations made in the previous year’s annual review, by improving the clarity of the indicators and reducing the number of areas of focus. Further, it reflects the broader refocus to building the sector’s resilience rather than significant expansion (noting the challenging operational context).

The programme has successfully implemented the recommendations to continue supporting efforts to build market linkages with UK and European buyers and implementing new measures on standards and certifications for the UK market specifically. Another FCDO programme, UKTP, has to date provided support to link companies with buyers in the UK. The Accelerate programme has therefore focused on buyers in other European countries to avoid duplication, but this may need to change in the future if the UKTP programme does not continue its support.

Progress against recommendations from last year’s annual review

Recommendation: It will be key to ensure that training in standards and certifications obtained continue to be leveraged in park operations, that they are linked to measures and that companies’ feedback continues to inform additional measures invested in and training undertaken.
Progress: (Ongoing). The project follows-up with IPDC and relevant stakeholders to ensure ownership and are implemented measures to ensure sustainability.

Recommendation: New measures that are going to be introduced to improve IP operations or improvements to existing measures with the support of the programme, should take into consideration the UK’s relevant standards since UK is one of the potential markets for manufacturers and the programme is co-funded by the UK government.
Progress: (Completed). Completed, has been addressed in the design of the new phase of SIC ll.

Recommendation: The programme (GIZ) should consider how to make sure that measures introduced to improve IP operations with the support of the programme will continue to be implemented after the programme terminates (sustainability).
Progress: (Ongoing). The project follows-up with IPDC to ensure ownership and are implemented measures to ensure sustainability.

Recommendation: Certification and adherence to national and international standards is a dynamic and expensive area for investor companies and local businesses to keep up with. To maintain the sustainability of interventions it will be key therefore to keep the co-investment arrangement as well as the demand-driven model to ensure that only critical certifications and standards are prioritised.
Progress: (Ongoing). S.I.C. follows market-led company upgrading strategy. Co-investment and cooperation were key selection criteria in gap assessment and selection process. Certifications are only supported where a buyer has voiced their clear interest in sourcing from a specify supplier and demand a new certification.

Recommendation: Regarding local and international orders(backward and forward linkages), given it is critical to the development of the Ethiopian manufacturing sector, the support should remain a priority. However, private sector development is challenging to accomplish in programmes shorter than 5-7 years and as such the design of the programme under the no-cost extension should be targeted and realistic in terms of what it can achieve. Partnering with other programmes addressing these backward linkages (including on access to finance such as supply chain financing/purchase orders as collateral in lending, also to mitigate forex challenge in production) as well as considering (in the near to medium term) whether there is scope for spend under a separate funding modality within the FCDO could be considered.
Progress: (Completed). The programme has identified most promising companies for vertical integration to build up strong textile and garment supply chain in Ethiopia and is in process to identify activities considering value for money and expected impact within given budget framework. Indicator has been added to reflect backward and forward linkages, to measure success of activities as part of SIC II. For full-fledged support of establishment of backward linkages, further funding and cooperation with other programmes would be needed. S.I.C. welcomes further input and contacts by FCDO on the topics

Recommendation: The importance of focusing on market linkages pivoting towards new European (and potentially African markets) is a recurring theme among key challenges in the programme. The programme should continue supporting such efforts and build on the strong example of collaboration with other FCDO programmes such as UK Trade Partnerships.
Progress: (Completed). The follow-on project has targeted buyer match making intervention that addresses this recommendation. In addition, it will be pivotal for FCDO to continue linking the project with other relevant programmes.

Key lessons and recommendations for the year ahead
Key lessons
Lessons learned this year highlight the importance of targeted buyer matchmaking and support for compliance with international standards in strengthening the resilience of Ethiopian firms and industrial parks. Feedback from companies and investors’ associations has shown that participation in trade fairs and direct engagement with international buyers are the most effective means for securing new business, particularly as firms diversify away from the US market towards Europe. Companies noted the importance of having a sustained presence at trade fairs, to re-build Ethiopia’s reputation following the rise in conflict. This can take years to achieve. Some companies quoted that they would want to attend more trade fairs but were unable to cover the costs (even when the programme funded the pavilion presence).

Additionally, the experience of aligning business practices with international requirements has shown that ongoing support is necessary to maintain standards, as many certifications require regular renewal and external expertise. These lessons have informed this year’s recommendations, which call for a light-touch analysis of buyer matchmaking outcomes to better target support, and for continued flexibility in supporting firms seeking to re-enter or expand in the US market as trade conditions evolve.

Recommendations for the year ahead

Recommendation 7: the programme collects information on the manufacturers who participate in the buyer matchmaking process, including the number of linkages made and conversion into actual deals. The reviewer recommends doing a light touch analysis of this information to better understand the profile of businesses who are successful in securing linkages versus those who aren’t, to inform which businesses should be prioritised for buyer matchmaking services and which require additional support (e.g. through management and operations training) to be able to take advantage of these opportunities. This would contribute to increasing the effectiveness of the service. Given some matchmaking services have been provided in conjunction with another UK FCDO programme, the UK Trade Partnership programme, this review should include lessons learned from that programme. This should be done by October 2025 to inform future programming over the remainder of the programme.

Output Title	Business environment constraints faced by manufacturers in IPs and surrounding clusters are eased.
Output number:		3	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone	Progress (Oct 2024 – Mar 2025)
3.1 - 6 PPDs, evidence-based analyses and/or other instruments addressing challenges of textile and manufacturers in Ethiopia were completed (baseline zero).	0	1 (Exceeded) – delivery of the 2024 Buyers Breakfast, a flagship public-private dialogue (PPD) platform, bringing together 24 international buyers, policymakers, and industry leaders. The potential to support this PPD was identified opportunistically in the run up to the Ethiopian government’s High Level Business Forum.
3.2 - 3 solutions addressing challenges of (textile and garment) manufactures in Ethiopia were developed (baseline 0).	0	0 (Met) – GIZ initiated negotiations with Ethiopian Airlines for an Air Freight Offer to ease logistical challenges and support exports to Europe, but this is still in process.

Briefly describe the output’s activities and provide supporting narrative for the score.

GIZ has initiated negotiations with Ethiopian Airlines to advocate for air freight discounts for Ethiopian textile exporters (from 30% to 50%), as a temporary solution to land-based logistical challenges. This would be a creative solution and negotiations are progressing well. GIZ has reported this as a solution ‘developed’, but this reviewer does not think it has sufficiently progressed to be recorded against indicator 3.2 (see recommendation below).

In addition, the programme supported a new SEZ Proclamation, modernising the regulatory framework and enhancing the business environment, and continued to support young professionals embedded within the Ministry of Industry (MOI).

When the programme commenced, there was a negative perception of the manufacturing sector and exporting within the Ethiopian government, meaning low appetite for improving the operating environment to support the sector. Attitudes within government (including in the Ministry of Industry and IPDC) have improved significantly within the most recent reporting year, and the programme is capitalising on this momentum through increased engagement, including through the Buyers’ Breakfast public-private dialogue (PPD). The programme completed preparatory policy work to inform the discussion through collecting stakeholder views from investor associations and companies, which informed the discussion on logistics delays and rising costs. The Ethiopian Investment Commission (EIC) have committed to identifying solutions to the issues raised in the PPD within three months with implementation timelines.

However, translating discussion or analysis into impact is challenging. The Ethiopian Government have been slow to react to issues faced by the sector. Often, logistical and regulatory issues require the action of multiple government entities (e.g. Customs, Ministry of Industry, Ministry of Transport, EIC, IPDC). PPDs provide an opportunity to discuss issues with all relevant stakeholders present. Where the barrier to implementing reforms stems from a lack of capacity for analysis or coordination, support through the programme could help address these through PPDs. However, many business environment barriers are held up by political decisions or inaction, and PPDs will not by themselves be able to address these. For this reason, the FCDO and GIZ teams should be very selective when identifying interventions under output 3. An assessment of the political economy dynamics will be critical for identifying a clear path to impact; this should be a prerequisite of any interventions under this output (see recommendation 1 below).

The programme is on track to meet the end of programme targets, given the momentum built to date.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In the most recent phase of the programme, there has been a shift in focus towards unlocking national level barriers to the manufacturing sector. These issues are harder to influence through the programme alone than those addressed by outputs 1 and 2. As a result, output 3 is designed to be a smaller and more flexible component that can respond to windows of opportunity for engaging government.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no specific recommendations from the previous AR given the introduction of a new output. However, the AR did recommend continued engagement with government institutions and leveraging existing relationships held by the GIZ team, seconded advisors and BE Addis Ababa. This has been fulfilled by this output.

Progress against recommendations from last year’s annual review

Recommendation: With a range of new policy to be implemented in the near to medium term (e.g. Ethiopia ‘Tamrit’ - Let Ethiopia Produce - within the wider import substitution strategy), it will be key to keep engaging with government institutions and leverage existing relationships held by the GIZ team, seconded advisors and draw on FCDO/BE support, where possible, to ensure outcomes are maximised for the programme objectives. It will be key to consider which constraints (e.g. forex, logistics, customs issues, productivity, safeguarding, CAPEX/OPEX) the programme can realistically influence and add value in relation to. It will also be key to consider which opportunities can be leveraged, including outcomes from the COP28 attendance of government officials (e.g. taking steps towards carbon intensity of production measurement at factory and/or IP level, which will become increasingly important in global carbon policy development in the medium to long term). Seconded advisors appear to be appreciated by the government institutions they are embedded in, and the programme should use this to continue enhancing government coordination and leveraging opportunities related to new policy development.
Progress: (Completed). The follow-on project is designed to address key issues it can influence directly through its respective interventions along with its key partners (both in the private and public sector). Where relevant, it is also working with other key stakeholders

Key lessons and recommendations for the year ahead
Key lessons

This years’ experience has highlighted several key lessons for effective engagement in Ethiopia’s manufacturing sector. Notably, the programme has found that strategic prioritisation and flexibility are essential, as progress is most likely when activities are closely aligned with government priorities and windows of opportunity. Addressing complex, cross-ministerial challenges such as logistical and regulatory barriers require a targeted approach informed by a strong understanding of the political economy. Furthermore, the lack of clarity around what constitutes a ‘developed’ solution has emphasized the need for more precise definitions and shared expectations with the implementing partner.

Recommendations for the year ahead

Recommendation 1: The reviewer recommends that FCDO and GIZ prioritise and strategically select activities under output 3 to maximise impact on the manufacturing sector, focusing on areas where technical assistance can drive real improvements. A more strategic approach to output 3 should be agreed by July 2025 and regularly reviewed.

Recommendation 8: under the current wording for indicator 3.2, there is ambiguity in the extent to which activities can be counted as a solution which has been developed. GIZ have reported that initiating negotiations with Ethiopian Airlines to address logistical issues has counted as 1 solution developed against this milestone. However, the reviewer doesn’t think that sufficient progress has been made to validate this claim. To avoid ambiguity, the reviewer recommends the programme team should agree with GIZ at what point solutions ‘developed’ are sufficiently advanced to be counted against the indicator. This should be done before the next annual review, by October 2025.
## D: VALUE FOR MONEY

Key cost drivers and performance

The key cost drivers of the programme are outlined in the table below. Staff costs remain the largest proportion of spend, at over 61% of total programme costs, given most interventions are in the form of technical assistance. The average cost per GIZ seconded advisor is €135,300 / year and for national staff €22,850 / year. This has increased due to a higher proportion of project leadership and management but remains below the average across GIZ (€165,000/year and €25,250 respectively). Grant and local subsidies cover the cost of CARE delivering the STOP programme, and direct/indirect costs cover the GIZ office, training and events.

As part of the macroeconomic reforms (in July 2024), the Government of Ethiopia floated the Birr, which was over valued at the time. This exchange rate volatility led to some uncertainty about spending power. While the FCDO’s contribution is made in British pounds, approximately 60% of programme costs are paid in Ethiopian Birr (ETB). This meant a potentially significant increase in the programme’s spending power. FCDO commissioned GIZ to develop a mitigation strategy to manage this. One of the main actions GIZ took in response to the devaluation was to peg local staff costs to the euro, to avoid a real terms cut. Given the substantial portion of staff costs in the budget, this reduced the proportion of funds spent in birr and therefore reduced the impact of the devaluation. However, an increase in purchasing power for other costs paid in birr (e.g. local TA contracts, conference facilities) remained. Some of this was offset by inflation.

Since this strategy was implemented, the GBP: ETB exchange rate has stabilised near market rates. As of May 1, GIZ has stopped pegging local staff salaries to the euro.

Travel costs have also increased due to the Gap Assessment conducted – the process through which GIZ selects factories for support through output 2 and identifies upgrading needs. The assessment covered 41 factories, of which 15 local factories and 18 FDIs were selected. The findings on the upgrading needs from the assessment has subsequently been used to inform the design and implementation of the second phase of the programme.

UK Budget Lines	Cost (08/2020 – 03/2025) (GBP)
Staff costs	5,039,721
Grants and local subsidies	1,005,158
Other direct costs	607,314
Indirect costs (overheads)	607,314
Travel costs	354,920
Advanced training costs	81,849
Equipment & construction contracts	43,204
VAT	1,912
Total	8,231,582

VfM performance compared to the original VfM proposition in the business case

The programme has developed and implemented a new logframe which refocuses money and effort on a smaller number of pillars. This responds to the more challenging operational context than originally expected at inception – including due to Covid, the suspension of AGOA, increased local and international conflict and a reduced programme budget. These shocks had previously reduced the overall effectiveness of the programme and resulted in a resetting of ambition to focus on supporting the resilience of the sector. In the previous reporting year, the operational context has improved due to the implementation of macroeconomic reforms, which bodes well for the continued effectiveness for the remainder of the programme. The logframe also prioritised a smaller number of activities to enable increased FCDO oversight of activities and to increase the strategic impact of activities.

The programme has a VfM strategy reported in bi-annual programme reports, including metrics for economy, efficiency, effectiveness, equity and cost effectiveness. These are summarized below:

Economy

GIZ reports on economy measures, as set out in its annual report. Most economy measures have been met for this reporting year. The percentage of total funding on international and national long-term employment (LTE, which include travel costs) was substantially higher than expected, especially in the second half of the reporting period. This was due to a large increase in travel costs during the Gap Assessment intervention – the process of selecting factories for the upgrading programme and identifying upgrading needs. Now the assessment has been completed, travel costs are expected to reduce.

Consultant costs were substantially higher than the target for the first half of the reporting period (30% vs. 18%) due to late settlement of contracts and financial agreement ahead of the project phase ending. To counterbalance, these were low in the second half of the reporting period (1%). Average fees for international consultants remain below targets (€750-778 a day vs. the target of €900 a day).

Efficiency

The programme met its efficiency requirements for all three outputs, based on the consumption rate (i.e. use of budget allocated to each output). The consumption rate was substantially higher in the first half of the reporting year (between 84-106%), due to it being the last phase of the project lifecycle (as per GIZ’s project lifecycle). In the second half of the reporting year, representing the start of the new project lifecycle (2024-27), the consumption rate was significantly lower (5-7%).This level of consumption rate is low even noting that it is in the first 6 months of the new phase of the project. The programme should ensure that GIZ are able to distribute costs for each output for the remaining years of the programme, to maximise the effectiveness of each.

The implementing partner uses an Efficiency Saving Approach (ESA) set out in the VFM strategy. This aims to improve efficiency through measures such as flexible reallocation of resources in response to changing political-economic and security conditions and reducing transaction costs for staff and external consultants. As part of GIZ’s ESA, their Finance, Admin and Contracting Team (FACT) serves multiple programmes by serving as an overarching structure. It increases the operational efficiency of administrative procedures of implementation, and shares operational costs across projects, reducing the overall cost for any individual programme.

An example of how GIZ has improved its economy over the reporting period includes its work with the Japanese Development Agency JICA. It supported JICA to implement different soft skill training modules, which enhance management skills that promote operational efficiency and install a culture of continuous improvement within the factory environment. GIZ nominated 14 companies for participation, and JICA supported the participation of a further 22. Aligning these activities presented a cost saving for the programme by supporting outputs through other funds. The reviewer has recommended a full mapping of the development partner landscape within the textiles sector and the IPs, to identify other opportunities for alignment (see Output 1).

Effectiveness

The programme met all output and outcome targets for this reporting period, suggesting it has been effective against the new indicators implemented (although noting that many indicators were set at the baseline level). The reviewer has determined that the programme is on track to meet the higher targets for the following reporting period. However, the ability for the programme to meet its impact indicator targets and ensure the resilience of the textile sector moving forward will depend primarily on the wider operational context which could limit its effectiveness, which is to a large extent outside the control of the programme.

To address this, during the revision of the theory of change and logframe, the programme has refocused efforts towards building the resilience of the sector to withstand shocks, while also supporting improvements to the business environment where possible through output 3. If achieved, addressing these challenges will likely have the largest positive effect on the programme’s impact indicators. Further, there has been an alignment of activities across all three pillars, e.g. aligning the focus on improving worker conditions and social compliance to the standards set by the European buyers facilitated through the buyer matchmaking process.

Cost effectiveness

GIZ seeks to mobilise additional private and public resources for the programme, e.g. receiving €1.18 million from another GIZ project (Decent Work for Just Transition), and €20,000 from private sources for promoting the social dialogue project. Its mobilisation ratio of mobilised resources / invested resources was 1 over both halves of the reporting period. A leverage ratio of >1 indicates good value for money.

The programme is creatively partnering with two international buyers to support the establishment of legitimate worker representation and promote effective dialogue and solution-finding processes, aimed at worker empowerment and participation. The partnership follows a cost-sharing model, whereby the companies and GIZ share the costs of conceptualization and implementation in a selected company which can be scaled up to other factories. This saves costs while increasing effectiveness, as companies are investing money in work conditions helping implement changes within factories.

Equity

The programme has a strong focus on improving the working conditions of the employees in the IPs (Output 1), of which more than 80% are women. The programme focuses heavily on implementing anti-SEAH awareness training, reporting mechanisms and prevention mechanisms. Women make up around 40% of managerial and supervisory positions.

However, there are some ongoing safeguarding risks for the women working in the IPs. To better understand the effectiveness of mainstreaming equity and gender issues within the programme, the reviewer has recommended a light touch survey of workers to gain a better sense of the prevalence of SEAH in the IPs. This will inform the final years of the programme and work to ensure that IPDC and EIH can continue support for worker welfare (see risk section for issues and recommendations). Due to cost limitations, a full survey will not be needed every year but could be followed up through existing worker welfare surveys conducted through Output 1.

Assessment of whether the programme continues to represent value for money

Based on the above, there is sufficient evidence that the programme continues to delivery good value for money. The streamlined theory of change and logframe have adapted outputs to focus on where the programme can have the most impact and reduced the number of outputs to ensure deeper interventions on each. As set out in Section B, despite strong performance against the outputs and outcomes of the programme, there is uncertainty about the ability of the programme to achieve impacts given factors outside of its control. However, the programme has demonstrated a strong ability to respond to shocks in recent years. The pivot to strengthening the resilience of the sector aims to safeguard VFM despite the uncertain operating context.

E: RISK

Overview of risk management

The reviewer proposes no changes to the overall risk rating (Major) or individual level risk appetites.

The FCDO and GIZ each have their own system for monitoring risks. GIZ has a project-level robust risk management framework split into six categories: political, ecosystem, delivery, reputational, safeguarding, commercial. Safeguarding risks can include violation of human rights, labour standards and environmental laws, as well as unintended negative consequences related to occupational accidents, and environmental pollution. Mitigation measures and change in risk ratings are also reported on. GIZ have quarterly meetings with FCDO on risk, to update on key changes to risk and mitigation methods.

FCDO’s risk register was last updated in May and the programme team have monthly internal meetings to assess risk and update mitigation measures. Significant risks under safeguarding stem from high rates of Sexual Exploitation, Abuse, and Harassment (SEAH), weaknesses in SEAH reporting structures and limited government capacity or commitment to addressing SEAH. Although the safeguarding risks have high ratings, they are currently within the risk appetite agreed with the Development Director. In the strategy and context category, political instability presents a major risk, potentially disrupting operations and long-term planning. Finally, under policy and programme delivery, conflict remains a significant threat, affecting both the safety of personnel and the successful implementation of activities.

Appropriate mitigation measures are in place to address these risks. For example, mitigation measures to address the risk related to high rates of SEAH include activities implemented under output 1, such as training factory management teams to institute policies that can reduce SEAH in the workplace. The programme remains flexible to adapt to fluctuations in the risks. For example, following the aggravation of conflict in the Amhara region in August 2023, implementation stopped in the Debre Birhan IP with very limited intervention in the Kombolcha and Mekelle IP and resources were diverted to other IPs. Further, the programme has diverted focus away from securing buyers in the USA market due to the suspension of AGOA, focusing instead on European markets. This risk has been mitigated well, although the extent to which the European market can supplement losses from the USA market is still limited. As new opportunities arise due to the implementation of US tariffs, the programme should seek to capitalise on any renewed interest from US buyers.

An important development occurred in April 2024 when the EIC closed the Hawassa worker call centre due to a nationwide government hiring freeze. The centre was available for anonymously reporting grievance issues at Hawassa Industrial Park, including issues of SEAH. Workers can still report grievances outside of their company to the IPDC, although the IPDC management note that no issues have been raised since the call centre has stopped. IP-level call centres have tended to be less effective than factory level mechanisms. Following a review of the programme’s activities on worker welfare in August 2023, the programme team decided to prioritise factory level reporting structures given most issues occur and are resolved there. Positive feedback from interventions carried out by CARE at the factory level suggests it is possible to improve factory level handling of such cases. However, IP-level call centres remain an important second line of defence for workers who wish to resolve disputes outside of their companies, and the closure of the Hawassa call centre reduces the ability to report and monitor grievances. The Accelerate programme previously supported the call centre to improve standard operating procedures for handling cases. It decided not to step in and fund the centre as the temporary nature of the programme means this is not a sustainable solution. The closure of the call centre remains an ongoing risk. As a result, the reviewer recommends agreeing a strategy with government to improve their ownership on worker welfare issues (Recommendation 5).

Understanding the rates of SEAH faced by women working across the various IPs remains challenging. Recent media reports highlighted cases of women who work in the IPs engaging in sex work to supplement their wages. In 2023, CARE completed a SEAH assessment of the Industrial Parks which found that cases of SEAH were rampant across the park, which suggests that reporting mechanisms are not being sufficiently used. FCDO have not gained access to this report due to confidentiality concerns. In response, the 2023 DDA and Annual Review recommended that the FCDO and GIZ team dedicate additional time to collect information regarding the rates of SEAH, for example through worker surveys, site visits, interviews with stakeholders such as CARE, etc. Whie this has improved the team’s general or anecdotal sense of the situation in the parks, there remains a lack of up-to-date, independent data on SEAH within the Industrial Parks. Addressing this gap is essential to inform effective safeguarding interventions and to assess the impact of current and future programme activities.

Progress against recommendations from last year’s annual review

Recommendation: The reviewer recommended that the programme keep engaging with government institutions and leverage relationships to maximise outcomes, considering constraints and opportunities.
Progress: (Ongoing) The follow-on project addresses key issues directly and works with relevant stakeholders in both private and public sectors.

Key lessons and recommendations for the year ahead
Key lessons

The closure of the call centre at Hawassa Industrial Park due to funding constraints has demonstrated the gap in government capacity or commitment to prioritising worker welfare interventions. The programme’s focus on factory-level reporting structures makes sense in this context, given there is greater scope for impact here. However, this highlights the importance of continued dialogue with government to protect the sustainability of the programme’s interventions, as set out in recommendation 5. The closing of the call centre highlights the continued difficulty of collecting indepdent, up-to-date data on the prevalence of SEAH within Industrial Parks. As a result, the reviewer recommends undertaking an independent survey to address the data gap on SEAH, ensuring future interventions are both evidence-based and sustainable.

Recommendations for the year ahead

Recommendation 5: The reviewer recommends engaging with IPDC and EIC management to develop a plan for sustaining worker welfare support, including SEAH mechanisms, after the closure of the call centre.

Recommendation 6: to address the data gap discussed above, the reviewer recommends that by March 2026, the programme undertake an independent survey on the prevalence of SEAH instances within the Industrial Parks. This can be used to assess the impact of worker welfare activities throughout the programme and to inform future programming, whether by the UK FCDO or other development partners.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Performance of Partners
Implementation of the programme has been strong over the reporting period. GIZ is the only implementing partner for programme, which is co-funded by the German Federal Ministry for Economic Cooperation and Development (BMZ). The FCDO has signed an MOU with GIZ for delivering the programme, which has received a no cost extension until October 2027.

Following this extension, an MOU was signed in August 2024 for an amount of £950,000 to cover the period from October 2024 to March 2025. Subsequently, due to underutilization of funds by other programmes within the team, an additional £400,000 was allocated to this programme. This required another MOU amendment, which was signed in November 2024, bringing the total funding for the October 2024 to March 2025 period to £1.35 million. In line with the no-cost extension, a business case addendum was also completed to reflect the updated scope and timeline of the programme.

As part of the review, partners in the Ethiopian government (including the IPDC and EIC), investors associations, companies and downstream delivery partners (including CARE) were consulted. All highly commended the performance of GIZ, and the support was clearly valued. There were some reports from companies of delays in the provision of expertise and consultants. Having cross-checked with GIZ, these are typically due to wider factors outside of their control. Companies reported wanting more support to attend trade shows and events from GIZ, although this is limited due to budgets. The IPDC management more generally noted that the programme focuses on the textile and garment industry, whereas they are increasingly focused on the entrance of higher value sectors into the IPs (such as the solar panel industry). They noted they would want to ensure that GIZ delivery and their priorities were aligned. Another FCDO programme, Manufacturing Africa, has done some analysis on the potential to scale up solar cell production in the Industrial Parks and is in discussions with the GIZ Accelerate team about how to best align efforts here.

Delivery of the Programme
The programme was delivered through a structured approach involving fortnightly meetings between the FCDO and the GIZ project implementation team. These meetings, held twice a month, provided a platform to address financial matters, project management, and technical progress, contributing to a stronger shared understanding of the programme’s operations. The project risk register was reviewed and updated on a quarterly basis while the delivery chain map was reviewed and updated every 6 months. Part of the team, including the social development advisor and the PRO of the programme, visited Hawassa IP in February 2025 where a meeting was held with several stakeholders and partners including Factory management. A readout of the visit was shared with the wider team.

Financial Management
For the current reporting period, GIZ remains the sole implementing partner for the ACCELERATE programme. Due to significant budget reductions and a shift in FCDO’s strategic priorities, the value of the Memorandum of Understanding (MoU) was revised, and the agreement’s end date was brought forward to September 2024. In 2024, a no-cost extension was approved, allowing the programme to continue until October 2027. This extension aligns with the original business case, which recognized that budget constraints had limited the programme’s ability to achieve its intended outcomes, but that these outcomes remain highly relevant to Ethiopia’s economic development. As of 2025, the programme has been granted a full revised budget of £15.2 million to support its implementation through to 2027.

The payment mechanism used is advance payment. FCDO released disbursements based on the workplan, budget forecast, financial report and justification from the partner on the need of the advance payment. The programme followed FCDO’s purchase-to-pay guidelines when processing financial payments, and secured PRO/SRO approval to ensure all advance payments were justified and not in advance of need. Payments were processed promptly upon receipt of complete supplier documentation. As a result, the programme maintained an efficient workflow with minimal GRNI (Goods Received Not Invoiced) issues during the review period.

The payment made during the Annual Review period (April 2024 – March 2025) was £3.15m, of which 25% (£787,500.00) was expected to be spent on ICF. For programme component 300702-101, the total disbursement from April 2024 until March 2025 is £2,362,500.00, with GIZ reporting a budget utilization of £2,339,616.75 (a utilization rate of 99.03%). Similarly, for programme component 300702-105, the total disbursement is £787,500.00, with a reported utilization of £779,872.25 (a 99.03% utilization rate). However, during the revision of the programme’s ToC and results framework (as part of the NCE process), it was found out that the five ICF KPIs that the project aimed to contribute to were not the right indicators (the programme’s activities were not reportable under the previously selected 5 ICF KPIs) and hence the actual spend for ICF is much lower than the targeted 25%. Accordingly, the ICF KPIs that the programme can contribute to have been reduced to one KPI and the ICF budget for future years are expected to be lower (around 7%).

The initial allocated budget for the Accelerate programme for the period of the annual review (April 2024 – March 2025) was £2.25 million. The additional funds above the original allocation (£400k) were made available through the reallocation of underspent budgets from other projects within the team, enabling the programme to scale up delivery and meet its targets effectively.

There is a noted difference between the cost and expenditure figures in the financial report from GIZ, primarily due to timing and accounting method differences. Costs are recorded when services are invoiced and posted, while expenditures reflect actual payments. Advance payments, which initially appear only as expenditures, are later adjusted upon invoice settlement, creating temporary mismatches. GIZ has explained this process and assured that reconciliation is underway. We are maintaining close follow-up and expect a finalized report upon completion.

Due Diligence Assessment
There were eight recommendations in the 2023 DDA. Most major recommendations such as improving risk management processes, agreeing on how to manage exchange rate fluctuations, strengthening safeguarding measures (including SEAH prevention), and increasing accessibility of whistleblowing channels have been implemented or are well underway. Some actions remain outstanding, mainly those requiring further decisions from GIZ HQ, such as updating contract clauses to include safeguarding commitments and finalising risk escalation procedures with partners. Ongoing work includes regular safeguarding training and continued efforts to raise awareness and monitor compliance.

In 2025, GIZ has continued to make steady progress in implementing these recommendations. Notably, they have maintained momentum on risk management by following up with the HQ Risk Management Section, and the risk policy is actively disseminated to project staff and downstream partners. On safeguarding, GIZ Ethiopia operationalized its country-specific SEAH guideline and conducted onboarding trainings in May 2024, with safeguarding now embedded in the theory of change and regular project reporting. The whistleblowing system has become more accessible, with a local grievance phone line being established and awareness raised among project participants; however, park-level call centres for anonymous reporting have been discontinued due to funding cuts. GIZ advanced its contractual practices by initiating the inclusion of anti-SEAH clauses in new agreements, pending HQ legal review. Furthermore, safeguarding training has been institutionalized, with sessions delivered in April and May 2024 and another planned for August 2025. Risk discussions with downstream partners have become more structured, with escalation trigger points under development. For more information see the DDA.

Safeguarding and Counter Aid Diversion

In 2025, GIZ continues to demonstrate strong adherence to safeguarding and counter-aid diversion standards across the programme and its delivery chain. Following the action plan agreed in March 2024, developed in response to the 2023 DDA and Annual Review findings, GIZ has made consistent progress. The SEAH guideline introduced in 2024 has been implemented with onboarding trainings, and safeguarding is now systematically integrated into programme design and the biannual Theory of Change reviews. GIZ’s code of conduct, which includes provisions on fraud prevention, anti-discrimination, and sexual harassment, is presented during onboarding and reinforced through mandatory compliance training, monitored by supervisors and the GIZ learning system.

As part of routine programme management, the FCDO team regularly reviews fraud memos before processing payments, holds fortnightly meetings with GIZ where any raised safeguarding and fraud concerns are discussed, and monitors implementation through GIZ’s annual and biannual reports. Obligations for reporting fraud and safeguarding concerns, along with available whistleblowing mechanisms, continue to be communicated to downstream partners. The Delivery Chain Map is kept up to date, and as of 2025, no incidents of fraud have been reported to FCDO. The Delivery Chain Map (see below) is updated regularly, and there is no fraud reported to FCDO.

Additionally, the FCDO team has organized a dedicated meeting with the delivery partners, including GIZ, to reinforce FCDO’s expectations around risk management, prevention of aid diversion, safeguarding, monitoring and evaluation/value for money, and financial and commercial management. A follow-up letter summarizing key discussion points was sent to suppliers, with a request to share it with their downstream partners. This letter also reiterated the reporting channels available to GIZ and others for disclosing any fraud or safeguarding incidents. These measures are aligned with biannual reporting requirements and are a condition for fund disbursement.

Asset Management:

The implementing partner shared an updated asset register in May 2025. Responsibility for asset management lies with GIZ, and the organisation actively tracks, maintains, and reports on all assets in accordance with its internal procedures. Day-to-day oversight and compliance with asset management standards remain fully within GIZ’s operational responsibility.

Audit:

The May 2024 external audit confirmed that project funds were used appropriately and in line with the Memorandum of Understanding, with no qualifications to the audit opinion. The two findings identified in the report were successfully resolved by the end of 2024, following close coordination between the FCDO programme team and the implementing partner. In 2025, no new audit issues have been raised to date. The programme team continues to monitor financial compliance through regular management meetings and remains committed to maintaining strong financial oversight and accountability mechanisms.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Project activities were chiefly monitored through biannual project-level reporting as well as fortnightly monthly meetings between the FCDO and the GIZ project implementation team. These meetings cover updates on output level activities, as well as core finance and project management and safeguarding. In addition to this core monitoring, additional monitoring took place through field visits. The social development advisor and the PRO conducted a field visit to Hawassa IP in February 2025 to look at safeguarding issues. They met with factory management and downstream partners. A readout of the visit was shared with the wider team.

As part of FCDO’s programme reporting cycle, the programme team commenced an annual review of the programme for the 2024/25 period in April 2025. The team used the support of an external reviewer to get an independent perspective on the implementation of the programme. The process included a desk review of key programme documents, meetings with key stakeholders (including the Ethiopian Investment Commission, Industrial Parks Development Corporation, Ministry of Industry, Hawassa Industrial Park Investment Association) and a field visit to companies supported in the Bole Lemi and Adama Industrial Parks.

The reviewer has recommended further evidence gathering on the safeguarding and SEAH of workers to increase evidence on the incidence of SEAH within the Industrial Parks which is less available than for other risks (see Risk section).

GIZ also has its own internal Monitoring, Evaluation, and Learning Strategy for the programme on which it reports to the German government (BMZ).

Evidence

The business case for the programme provides significant evidence on the potential for export-led industrialisation to drive economic transformation, including in particular labour-intensive light manufacturing such as textiles and garments. This body of evidence remains strong and credible. However, there is no prescriptive or one-side approach to implementing industrialisation, which is highly political in nature. Given changes in the operating environment in the last few years, the programme has pivoted to focus more on the resilience of the sector, as an important provider for high quality jobs and exports for the country.

Learning

The programme team undertakes regular meetings with GIZ, stakeholders in the public and private sector and internal staff to update the evidence base and feed into the learning process of the programme. This includes regular informal gatherings of partners working on Ethiopia’s economic reforms to exchange insights on economic issues. GIZ hold Retrospective-Refine-Redefine (RRR) workshops every 8 weeks for all programmes they deliver. These discuss results of the previous sprint phase, plan objectives for the next 8 weeks and allow for learning and adaptations to be implemented given the volatile operational context.

Lessons identified from the reporting period and follow-up actions for the no cost extension, include:

More data and evidence is needed to better understand the prevalence and nature of issues of SEAH within and surrounding the Industrial Parks, and the extent to which the reporting mechanisms implemented are being used. Consultation through this annual review has shown that while managers have a positive perspective of the SEAH training and signal that they understand the importance, they remain detached about the realities faced by the women they employ. There is a question of to what extent the training and reporting mechanisms are effective or viewed as a box ticking exercise. The review has recommended an independent study which explores this in more depth (see above).

Following the implementation of the macroeconomic reforms, which addressed some of the major issues faced by both manufacturers and buyers, the largest remaining challenge for the sector is logistics. This was raised by every private sector stakeholder interview conducted as part of the reporting process, and government stakeholders were also keenly aware. Some short-term solutions are being explored (e.g. using Ethiopian Airlines as a temporary alternative to land-based transport), but longer-term logistical issues are due to both internal and regional instability, and the inadequacy of the transport infrastructure.

The suspension of Ethiopia from AGOA had large negative impacts on the Ethiopian textile sector. However, with AGOA due to finish towards the end of the year (and unlikely to be extended) and Ethiopia facing the lowest tariffs from the USA (current applied rate plus 10%), there are opportunities for re-establishing buyer connections. There is early evidence from manufacturers that American buyers are interested in the Ethiopian market again, and some instances of small deals being made. It will be important for the programme to continue monitoring to what extent this leads to more concrete and larger deals with the USA market. While volatile, the USA market is important for the Ethiopian textile sector – there is a much larger potential for volume of sales and the standards are easier to comply with.

There has been a significant positive improvement of the perspective of Senior government stakeholders of the manufacturing sector and exporting more widely. Multiple companies, investors association and GIZ all noted that Government are more open to implementing reforms and changes to the sector to facilitate the expansion of exporting. This has been shown through the implementation of the PPD and commitment to follow up actions (which was supported through this programme). The programme should continue to capitalise on this momentum, by presenting evidence on and solutions to a small number of key issues which are the most critical to the sector (see recommendation under Output 3).

New regulation under the SEZ proclamation allows manufacturers to sell to the local market alongside international buyers. However, multiple manufacturers raised issues in doing so, due to Ethiopian standards for the products being lower than international standards – leading to Ethiopian buyers importing cheaper, lower quality products instead of Ethiopian-made products which are produced at international standards.

There is variation in the ability of companies to capitalise on the opportunities presented through the programme implementation and wider macroeconomic reforms. Reporting from GIZ suggests that larger Ethiopian manufacturers have a better understanding of what was needed from European buyers, didn’t have a language barrier, and proactively followed up with buyers following trade fairs and buyer matchmaking. In comparison, smaller manufacturers and individual designers couldn’t do the same. This was echoed by the seconded advisor in the Ministry of Industry, who highlighted that often the leadership of individual manufacturers can hold back their ability to capitalise on, e.g. the upgrading of IPs into SEZs.

Progress against recommendations from last year’s annual review

Recommendation: Though many interventions are implemented across IPs/industrial clusters, the current reporting format is more anecdotal and doesn’t allow the FCDO to fully grasp the distribution and wider impact of the interventions against the holistic approach in the theory of change. The reviewer recommends that a disaggregation of logframe indicators by IP/industrial cluster is reported, to allow a better understanding of the spread of impact of the programme interventions and assessment of links and contribution to the holistic theory of change and national level policy, political and economic context.
Progress: (Ongoing). FCDO is due to share examples of other reports prepared by other projects. The project is reviewing on how it can adapt the reports.

Recommendation: The limited breakdown by gender across logframe indicators makes it difficult to assess the programme’s real impact towards women’s economic empowerment. The reviewer recommends considering additional indicators, targets, and sub-targets to existing indicators to better allow assessment of real impact on gender equality.
Progress: (Ongoing). Where relevant, logframe indicators will be disaggregated by gender (e.g. working conditions, workers using services, ICF support)

Key lessons and recommendations for the year ahead

Key lessons
As discussed in the section on risk above, we see a need for further monitoring of rates of SEAH across the industrial parks. Other lessons learnt include the need to monitor fast moving changes in policy: the evolving trade landscape particularly the suspension of AGOA and the ongoing tariff policy of the US demands ongoing monitoring to ensure the programme can respond. Additionally, the positive shift in government attitudes towards the manufacturing sector presents a valuable window for targeted engagement and reform, which should be strategically leveraged. Finally, there is notable variation in how companies benefit from programme interventions, with larger manufacturers better positioned to capitalise on opportunities than smaller firms. These lessons underpin this year’s recommendations: to conduct an independent survey on SEAH, undertake targeted analysis of buyer matchmaking outcomes to better support underperforming businesses, and ensure more active FCDO participation in stakeholder engagement to enhance coordination and impact.

Recommendations for the year ahead

Recommendation 6: The reviewer recommends that by October 2026, the programme conducts an independent, sensitive survey on SEAH prevalence in Industrial Parks to assess the impact of worker welfare activities and inform future programming. Key findings should be shareable with FCDO and government and used to support discussions on establishing a sustainable grievance mechanism. More details in section C.

Recommendation 8: The reviewer recommends a light touch analysis of data on manufacturers involved in buyer matchmaking to identify which businesses succeed and which need more support. This will help target services more effectively and should include lessons from the UK Trade Partnership programme. Complete this by October 2025 to inform future programming. More details in section C.

Recommendation 10: As GIZ continues to lead direct engagement with key stakeholders, including government sectors, we recommend that FCDO be more actively included in these interactions (where suitable). Involvement in stakeholder engagements - such as joint meetings, workshops, or consultations - would enhance transparency, strengthen alignment on programme objectives, and support more coordinated delivery. We encourage GIZ to create opportunities for FCDO participation in these forums to ensure shared understanding and visibility across all levels of implementation.

Date of last narrative financial report	March 2025	Date of last audited annual statement	May 2024