## Annual Review Template

Title: AFRICA TECHNOLOGY AND INNOVATION PARTNERSHIP (ATIP) PROGRAMME
Programme Value £ (full life): 32,000,000		Review date: Feb 2025
Programme Code: [AMP ID#] 300704	AMP start date: 09/01/20	AMP end date: 31/03/26

Summary of Programme Performance
Year	2020/ / 2021	2021/ / 2022	2022 / /2023	2023/ 2024	2024/ / 2025
Overall Output Score	A	A	A+	A+	A+
Risk Rating	moderate	moderate	moderate	moderate	moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/52871093.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006829.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Africa Technology and Innovation Partnerships (ATIP) is a £32m funded programme aimed at strengthening enabling environments for scaling technologies and innovations with potential for poverty reduction and inclusive growth in Ethiopia, Ghana, Kenya, Nigeria, Rwanda, South Africa and Tanzania. ATIP's overarching aim is to support the creation of more effective innovation ecosystems that catalyse new technologies and innovations to scale in these countries. This is achieved by focusing on several ATIP programme-level objectives:

- Strengthen Innovation Ecosystems: enhance the capacity of innovation ecosystems in partnership with Africa partner countries to foster environments conducive to the growth of technology and innovation-driven solutions to address development challenges.
- Stimulate Inclusive Economic Growth: promote economic growth that benefits all segments of society, including marginalised and vulnerable groups.
- Scale Technology-Enabled Businesses: encourage entrepreneurship and innovation in key sectors to facilitate the scaling of technology-enabled businesses that can provide innovative solutions to local, regional and global development issues.
- Collaborative Learning and Knowledge Sharing: build knowledge and understanding of how investments in innovation systems contribute to development objectives. This is achieved by promoting collaborative and emergent learning among programme partners, beneficiaries and other stakeholders.
ATIP’s three key output areas include networking (meaningful connections and collaborative partnerships); development and use of new knowledge and skills; and work with government and other ecosystem actors to address ecosystem barriers. These outputs are delivered through several partners and funding mechanisms:

- Innovate UK Global Alliance Africa (IUK GAA) programme – co-funded with IUK to develop and empower new country-based innovation knowledge exchange networks in Nigeria, Kenya and South Africa and act as a bridge between the UK and African innovation stakeholders.
- Research and Innovation Systems for Africa (RISA) – a joint fund with FCDO`s Strengthening Research Institutions in Africa (SRIA) programme to deliver a strategic portfolio of projects that strengthen synergies between research and innovation systems in Kenya, Nigeria, South Africa, Ghana, Rwanda and Ethiopia.
- Funguo Innovation Programme - managed by UNDP and co-funded by the European Union to strengthen the Tanzanian innovation ecosystem and support innovative startups and MSMEs.
- ATIP Flexible Funds – demand responsive funding managed by FCDO’s Research and Innovation Hubs in Nigeria, Kenya and South Africa. These are aimed at supporting innovation systems in partnership with country posts, responding to country business plan priorities and partner country and regional demand. Over the past year, ATIP’s flexible funds focused on work with the British Council to strengthen the Kenyan higher education sector’s capacity for entrepreneurship. It is anticipated that flexible funds will be used towards trilateral partnership initiatives between the UK, India, East and South Africa, as well as other demand-driven projects in 2025/26.

ATIP partners collectively contribute to the programme-level objectives through various complementary activities:

  - Capacity Building: Providing training, mentoring and technical support through innovation hubs, technology incubators and other institutions within the innovation ecosystem to enhance the capabilities of entrepreneurs, innovators and other stakeholders.
- Funding and Investment: Facilitating financial support to technology-enabled businesses and innovation projects through grants and other funding mechanisms. Where possible, mobilising additional resources from private sector investors and other development partners.
- Policy and Advocacy: Engaging with policymakers to promote an enabling environment for innovation and technology development.
  - Partnerships and Collaboration: Fostering partnerships between African and international organisations, including universities, research institutions and private sector partners. Promoting cross-border collaboration to address regional and global development challenges.
- Monitoring, Evaluation and Learning (MEL) and Knowledge Dissemination: implementing robust M&E frameworks to assess the impact of the programme and to facilitate the synthesis and dissemination of lessons learned and best practices.

ATIP is now in its penultimate year of implementation, having commenced a five-year cycle in 2020, and received a one-year extension (denoted the ‘bridge year’) to continue implementation until 2026. This is intended to ensure a more sustainable transition to potential future research and innovation system strengthening programming in FCDO in the next Spending Review.

A key addition to the ATIP portfolio in 2025/26 is Sankore, a bespoke demand-responsive project focused on the needs and opportunities for innovation system strengthening in Nigeria and Ghana. It will support research commercialisation, and innovation policy and innovation system projects that align with national and regional priorities for science, technology and innovation. Named after a historical place of learning in West Africa, Sankore will be delivered under the ATIP programme.

Summary supporting narrative for the overall score in this review

ATIP continues to perform well in delivering on its outputs and outcomes, making excellent progress in the past year, as demonstrated by its over-achievement on many of the output indicator milestones and by the case examples of system level change. These show how the individual activities supported are starting to deliver lasting change in the ecosystems where it works, driving new partnerships and collaboration, leveraging more investment and contributing to a more facilitative policy environment for technology and innovation.

This year, ATIP has focused on consolidating existing initiatives, strengthening partnerships and prioritising the most promising projects as it transitions towards programme closure in 2026. Significant progress has been made in building impactful partnerships that have bolstered local, national and regional innovation ecosystems. These efforts have contributed to positive development outcomes, including improved food security, enhanced climate resilience, job creation and the promotion of inclusive growth, gender equality and social inclusion across various regions. In food security, projects like INES Farm to Fork in Rwanda and the University of Gondar's agricultural technologies in Ethiopia have led to increased crop yields and revenue for farmers, with notable improvements in potato and rice production. The University of Ghana Business School's Investor Case Matching event and Impact Investing Ghana's support for Wami Agro Limited have enhanced market access and financial support for rural innovators and smallholder farmers in Ghana. In climate resilience, Katapult Africa supported 73 angel investors and 80 startups, resulting in a 32% increase in annual sales for climate tech companies across its cohort. Job creation efforts have generated 117 new jobs through innovation scaling in countries like Kenya, Rwanda, Ethiopia, Ghana, and Nigeria. Gender equity and social inclusion have been advanced by initiatives such as Viktoria Solutions' engagement of 1,928 girls in STEM courses in Kenya, Katapult Africa's promotion of female leadership in Rwanda's Angel Investment Ecosystem, and Impact Investing Ghana's Scale Quality Improvement Program, which improved the inclusivity of entrepreneurial support in Ghana.

ATIP has successfully leveraged nearly £4.7 million in additional funding and investments across six projects, enhancing the sustainability and impact of its initiatives. Furthermore, ATIP has made substantial strides in influencing positive policy and regulatory changes, contributing to a more enabling environment for innovation and commercialisation. This includes the development of new policies, strategies and plans in Kenya, Tanzania, Rwanda and Ghana, as well as institutional strengthening and capacity building for government and key stakeholders.

These achievements, the quality of the collaboration partnerships formed and the progress made in MEL and programme management justify the A+ overall score for ATIP in 2024/25.

Major lessons and recommendations for the year ahead

There are several key lessons learned from this year that are pivotal for driving more impactful and sustainable innovation together with Africa partners. ATIP’s success hinges on fostering cross-country learning, maintaining flexibility, aiming for systemic change, exploring innovative financing, prioritising gender equality and social inclusion, and improving climate finance tracking.

Strengthening cross-country peer learning has been essential. By leveraging cross-regional and cross-sectoral opportunities, ATIP has facilitated greater coordination among its delivery partners and downstream actors, enhancing the effectiveness of its different components and contributing to the strengthening of the overall innovation ecosystem. The onboarding of a dedicated Monitoring, Evaluation, Reflection and Learning (MELR) partner (the Institute of Development Studies (IDS) in this final year will be critical to support this process.

Maintaining agility and flexibility has been a cornerstone of ATIP’s success. The programme’s ability to adapt to budgetary changes, to seize new opportunities and to scale initiatives displaying most potential has been crucial. Proactive budget forecasting and management by both FCDO and implementing partners are recommended to sustain this adaptive approach and mitigate risks in the final year of implementation.

A significant shift from a ‘project’ focus to system-level change is necessary and will be a priority for this final year of programming. An independent review of ATIP and SRIA (with a focus on RISA) was concluded in late 2024. The review highlighted the need for the programme to aim higher, identifying actions that can catalyse long-term systemic change rather than short-term project outcomes.

Exploring innovative financing models for scaling and sustainability is another critical recommendation. Initiatives like Impact Investing Ghana (IIGh) Fund of Funds in Ghana and Katapult’s Angel Fund in Rwanda, which have mobilised over US$119 million, demonstrate the potential of leveraging alternative financing models to sustain innovation ecosystem change.

Deepening the focus on gender equality and social inclusion is imperative. While progress has been made in improving inclusion criteria and the participation of women and other marginalised groups in both research and innovation, more work is needed to drive transformative change in structures, systems and processes to ensure no one is left behind.

Improved tracking of spend attributed to International Climate Finance (ICF) is essential. Although ATIP was not initially configured to track ICF attributions, projects like RISA’s INES Farm to Fork, Funguo’s ECOACT Tanzania, and IUK’s Space Global Innovation Network (GIN) have demonstrated some climate change mitigation and adaptation impact opportunities. These projects have contributed to improved harvests, increased revenue streams and enhanced resilience to climate change. Moving forward, the ATIP programme team will continue to work towards better awareness and reporting on ICF contributions.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

ATIP’s Theory of Change (ToC) revolves around delivering system level change to enable innovation and technology to drive inclusive economic growth and development. It seeks to achieve this by addressing key innovation ecosystem enablers and facilitating partnerships and collaboration that can lead to improved policies, enhanced investments, stronger skills and knowledge and better access to markets for innovation. Through a range of delivery partners and initiatives, ATIP fosters collaboration between UK and African stakeholders, builds institutional capacities, supports the commercialisation of research and innovations, and promotes gender equality and social inclusion. By focusing on the strengthening of sustainable and inclusive innovation ecosystems, ATIP aims to empower key stakeholders (whether innovators, researchers, policymakers or implementers), enhance economic opportunities, and contribute to sustainable development goals and shared prosperity.

In 2024/25, no changes were made to the ToC, but output milestones were adjusted upwards to reflect increased programme ambition (including the output on partnerships and initiatives formed, the learning outputs documented and stakeholders addressing key ecosystem barriers). Each ATIP delivery partner programme has its own ToC, which complement one another in terms of their focus areas and relate closely to the overall ATIP ToC:

1. RISA: Updated in late 2024 to focus on behaviour change, collaborative and inclusive partnerships, capacity-building and developing effective structures and policies for locally driven research and innovation to grow and scale while addressing social and economic development challenges.
2. IUK GAA: Focuses on building UK-African partnerships to enhance market access, funding, and investment opportunities through innovation knowledge transfer. It is structured around three main outcomes: high-quality collaboration between UK-African ecosystem players; increased knowledge and capacity to leverage innovation, funding and investment opportunities; and enhanced access to network building and market opportunities for local innovation ecosystem players.
3. Funguo: Aims to increase and scale innovation impact ventures in Tanzania by promoting an empowering environment for innovators and entrepreneurs, focusing on innovation financing, service delivery, and an enabling environment.
Progress in 2024/25 includes increased ambition in partnerships, documented learning outputs, and stakeholders addressing key ecosystem barriers.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

ATIP is on track to achieve its anticipated outcomes and impact within the planned time and budget. An independent evaluation of ATIP and SRIA (focused on RISA), concluded by Technopolis in late 2024, highlighted that short-term outcomes and impacts are already observable among beneficiaries, including individual researchers, students and institutions. The groundwork laid by ATIP is expected to yield long-term benefits, although the complete transformation of complex innovation ecosystems that are geographically dispersed with differing innovation capabilities will require sustained effort and continued support. It is important therefore that any future programme builds on ATIP’s foundations continuing to drive the long-term transformation of local, national and regional innovation ecosystems.

Through RISA, ATIP has catalysed 324 innovations (defined as products, services or business models, that can transform the impact of solving complex problems) across six countries (Ethiopia (44), Ghana (35), Kenya (39), Nigeria (67), Rwanda (91), and South Africa (48), contributing to inclusive growth and the creation of over 100 new jobs. The programme has also contributed to significant policy advancements, such as the development of the Kenya Research and Development (KR&D) Policy, which is now being integrated into the ST&I Policy, and the formulation of a single bill in Ghana to consolidate similar policies and secure commitment towards the development of the National Research Fund (NRF) and the Ghana Innovation Agency (GIA). RISA work with the University of Rwanda and the National Council of Science and Technology (NCST) is contributing to the development of the Rwanda Technology Transfer and Commercialisation Strategy 2025-2029. In Tanzania, Funguo has contributed to National Guidelines on Establishing Spin-Off Companies, across six higher learning institutions, leading to the identification and patenting of technologies for commercialisation.

ATIP has also leveraged substantial additional financing for innovation, including US$5 million follow-on investment for Hinckley Recycling in Nigeria and the US$0.4 million investment for the WEEE Centre in Kenya (through IUK GAA). ATIP has also made significant progress in promoting gender equality and social inclusion (GESI) in innovation ecosystems by strengthening the access of women and other marginalised groups (including persons with disabilities) to resources and opportunities in a way that can deliver positive social change and more equitable and inclusive development outcomes. Some of the examples of success include RISA’s work promoting female researchers across Africa through its partnership with Mawazo, with Jimma University and the #EmpowerHer Initiative to target female innovators, with the University of Gondar's agricultural innovation projects, which have successful integrated and trained 200 female and disabled farmers in Ethiopia, and with Impact Investing Ghana (IIGH) which has enabled five female-led or founded businesses for investment readiness and connected them with seven impact funds. In Tanzania, Funguo’s #YouthIgnite Student Founders Fellowship has provided technical assistance and seed funding to student businesses, with 45% of the winning businesses led by women. Additionally, with Funguo’s support, the Tanzania Hubs Network (THN) engaged 110 hubs, with 54% of new members being women-led organisations. IUK GAA’s #MoreThanAWoman initiative expanded this year to support female entrepreneurs in Kenya, Nigeria, and South Africa, offering them mentorship and business support.

As ATIP enters this final bridge year, the focus will be on system change, sustainability and lesson-learning. Given the progress made and the strategic focus on building strong foundations, ATIP is on track to achieve its anticipated outcomes and impact within the planned time and budget. However, the complexity of transforming the innovation ecosystem underscores the need for continued support and adaptive management to ensure long-term success.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme is now in its sixth and final year, having successfully secured additional funding for a bridge year that is focused on pulling together the learning on what works to strengthen innovation ecosystems based on its activities over the past five years, and building the sustainability of its interventions for the future. An independent review of ATIP (and SRIA) assessed that the programme offered good value for money, allocating resources efficiently and delivering benefits that are highly relevant for the focus countries when it comes to research and innovation ecosystems’ gaps and needs. This final year offers good VFM by prioritising actions and focusing on those interventions that have strong outcomes for sustainability and system change, as well as putting an emphasis on learning and laying the foundation for future work in the field of technology and innovation. The dedicated ATIP MERL partner in this final year will be critical for pulling together lessons on what has worked (and what has failed) over the past five years and where focus should be for future programming on research and innovation.

## C. DETAILED OUTPUT SCORING

Output Title	Diverse, active networks support meaningful connections and collaborative partnerships
Output number:		1	Output Score:	A+
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 ATIP supported networks are effective, diverse and active Network health indicators - size & scope and diversity (member type, geography, sector, GESI)	0.7 (out of 1)	Innovate UK Global Alliance Africa (IUK GAA): 0.83 / RISA: 0.76 / A score of 1 signifies scores closest to an effective network health characterised by the scope, membership, participation and sustainability of the network relative to the purposes for which it was formed (e.g. for information sharing, training, technical assistance, and/or formalised innovation collaborations inclusive of joint technology development or transfer initiatives etc).
1.2 Networks support the formation of effective partnerships # and case examples of partnerships formed and initiatives arising from these	50 (cumulative milestone – up from 40 last year)	Total: 42 new partnership case examples during the year in review / Innovate UK Global Alliance Africa (IUK GAA): 30 new case examples / RISA: 12 new case examples

Briefly describe the output’s activities and provide supporting narrative for the score.

ATIP has made significant progress meeting its output 1 targets. In 2023/24, Indicator 1.1 was introduced to include a new measurement tool, commissioned by FCDO and co-created by evaluation experts from EQUALS (Evaluation Quality Assurance and Learning Service (EQuALS) in consultation with ATIP implementation partners to enable more standardised definitions and reporting around networking activities across the programme. The tool[1] captures ‘network health’, by evaluating both the scope (network size, sector, geography, and GESI) and effectiveness (outcomes relative to purposes) of networks. It uses a 10-point scale to assess network performance, with a perfect score of 1 indicating an active, diverse, and effective network. The score is calculated against a set of ranked criteria with three headline criteria for building a network specific health score: 1) Partnership action/outcomes, 2) membership, and 3) participation, communication and dissemination. This method tracks progress in key areas of network health, supplemented by case examples.
[1] The Network Health Score is an aggregate score that is reached through a quantified assessment against a 10-point scale of network performance, that include a range of factors contributing to network health and performance, guided by a shared framework of definitions and agreed criteria, based upon the scope and objective of the network and whether its purpose is around brokering partnerships, exchanging knowledge, creating innovation outcomes or bringing members together. A perfect score of 1 indicates a network that is active, diverse, functioning and leading to positive outcomes. The intention is to create a process to track progress in the key areas of network health, which are then illustrated and enriched by case examples and can form a data source for reviews, evaluations or other forms of research into the role of networks in project and programme outcomes.

This year IUK GAA improved its network health score, having facilitated 163 new introductions (target: 179), brokered 102 collaborations (target: 70), and achieved 59 positive outcomes (target: 74). Entrepreneurs (29%) and for-profit businesses (24%) formed the majority of new stakeholders, followed by R&D organisations (14%) and universities/research institutes (9%). Micro (51%) and small organisations (25%) were predominant, with larger organisations (15%) being the minority. Women-led (51%) and youth-led (34%) organisations were significantly represented among new stakeholders. Key successes include the launch of six new Global Innovation Networks (GINs) and pilot projects addressing socioeconomic challenges, generating over £1.5 million in project value.

RISA also met its network health target, demonstrating significant growth in the scope, diversity, regional focus and scale of its supported networks. In the year under review, 6 of the 8 networks analysed have expanded in size, engagement and new outcomes, including the Multi-stakeholder Innovative Platform by the University of Gondar (27 members), the Ghana Research and Industry Collaborative (GRIC) (over 400 members from 50 organisations), and the Enterprise Support Organisation (ESO) by Impact Investing Ghana (over 180 members). Notably, the Coalition Network of Stakeholders in Agricultural Mechanisation (CONESAM) by Adam Smith International has grown to nearly 2,000 members across eight states in Nigeria. Additionally, networks such as the University of Ghana Business School Collaborative Community of Practice (Rural Innovation Network Ghana) and the Kenya Space Sector Community of Practice, highlight the importance of cross-sectoral partnerships and leveraging collaborations to enhance project outcomes and strengthen the broader ecosystem. These networks bring together diverse stakeholders focused on areas like rural enterprises and space technology, contributing to regional innovation and development.

Indicator 1.2 highlights 30 impactful new partnerships/collaborations facilitated by IUK GAA, of which 25 have received seed funding. This includes 18 partnerships funded under the GIN Lead Customer Programme (of which 12 are highlighted in the 30 case examples identified in this AR); four funded under the Open Innovation challenges; and three funded under the Tembisa challenge run by Place-based Innovation in South Africa. High impact success projects include the collaboration between the WEEE Centre and Quinnovations' Urban Mining Centre in Kenya, and Hinckley Recycling's new lithium-ion battery recycling plant in Nigeria, which has partnered with UK Start-Up, Enverse, and secured a $5 million investment from the State Government of Ogun.

RISA has fostered 306 partnerships over four years, with 98 recorded in 2024/25 alone. Successful partnerships are defined as having at least two to three key actors working together on a specific, time-bound goal or project and producing concrete results that enhance project objectives or sustain effort. Typically, such collaboration results in development of new products or guidance documents, co-funding initiatives, or creating value through building of larger and more effective collaborative networks. In the year in review RISA has recorded 12 case examples of successful partnerships (Ethiopia (2), Ghana (3), Kenya (1), Nigeria (1), Rwanda (2), South Africa (2) and cross-country Ethiopia/Kenya (1). These partnerships have led to valuable initiatives, such as the commercialisation of research findings in Ghana, the dissemination of solar-powered irrigation technology in Ethiopia, and the expansion of the CONESAM network in Nigeria. The ESO Collaborative in Ghana reported substantial improvements in governance and business growth, while RIIS piloted the Innovation for Space Tech Acceleration in Rwanda (iSTAR) programme.

Overall, ATIP achieved its output 1 targets this reporting period, with progress in network health and impactful partnerships.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The output indicator 1.2 milestone was revised upwards from 18 in 2023/24 to 50 in 2024/25. This was because of a significant over achievement (i.e. 40) of the target in 2023/24. This is also aligned with the recommendations of the independent RISA review to reflect more ambitious targets.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s Annual Review made recommendations around the refinement of the network health tool to assess its efficacy for any future programmes, and the creation of more stretching milestone targets to reflect the high achievement in this area of the programme to date. Both have been achieved and this year, both IUK GAA and RISA have effectively incorporated the network health assessment tool into their reporting and learning. RISA has confirmed that the tool has effectively enabled self-evaluation, tracking and reporting partnership, collaboration and networks outcomes. It has also enabled understanding of the composition of the networks and has been critical in assessing sustainability of awardee initiatives beyond the funding period. Further engagement on this is planned at a holistic ATIP programme-level learning session in April 2025 to enable all ATIP delivery partners to share learning and encourage sustainability of the programme’s outcomes.

It is recommended that in 2025/26 IUK GAA should focus its activities, and consolidate and strengthen its approach, including maximising learning and synergies with other ATIP delivery partners (e.g. RISA in space related work in Kenya). Next year GAA will also launch a new intervention, the Business Innovation Fund, that will create a pipeline to support later stage technology development (TRL 6-8) and pathways to commercialisation. This will complement projects supported under the OI and GIN interventions, where the focus is primarily on early-stage technology development and piloting, providing GAA with the scope to support successful projects and partnerships from proof of concept through to commercialisation.

Output Title	Ecosystem actors develop, use and value new knowledge, systems/infrastructure and skills
Output number:		2	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 # Learning outputs documented, disseminated and utilised by a range of actors in the ecosystem	15	18 New Learning Outputs: / RISA: 12 / IUK GAA: 1 / Funguo: 5
2.2 # Case examples of new or strengthened knowledge/skills being put into use	18	18 New Case Examples: / RISA: 12 / IUK GAA: 3 / Funguo: 3

Briefly describe the output’s activities and provide supporting narrative for the score.

ATIP has exceeded its targets for indicator 2.1 generating and sharing learning outputs and demonstrating the application of new knowledge and skills within the innovation ecosystem. In the past year, ATIP partners produced 18 new learning outputs, including an investment guidebook, learning and exchange platforms, news media articles, policy papers and research reports. These outputs have had widespread reach, such as a RISA funded research report on climate tech and investment in Rwanda, which has been widely disseminated with 1,800 downloads and 20,000 views, and the Growth Africa Insight Report, which examines the characteristics of high-growth potential company founders in Kenya, Ethiopia, and Rwanda. This report has generated interest at global level, including from the Canadian Forum for Impact Investment and Development, promoting collaboration with other donors. The report raises awareness about GESI in growth firms, an area that has been deeply under-explored.

IUK GAA grantees developed one new learning output (with two more in the pipeline) which is the Ekiti Investment Guide - delivered in partnership with Briter Bridges, a UK based SME, and the Ekiti State Government – which aims to facilitate investors’ access to the innovation ecosystem. Pipeline learning outputs include the reports on their innovative pilots like the solar dryer in Eldoret, Kenya and the black soldier fly project in Nigeria, which have both introduced innovative technologies into new markets to support agricultural value addition and waste treatment respectively. Additionally, a knowledge exchange tour last year brought together four African space agencies and the UK Space Agency, fostering collaborative efforts and the creation of action plans. This initiative has contributed to the body of knowledge in niche areas, highlighting the economic value of space research in Africa and addressing sustainability challenges.

The Funguo programme contributed five learning outputs, including (i) the Tanzania Innovation and Entrepreneurship Support Pipeline Guidelines, developed by Ndoto Hub, providing standards and best practices for innovation hubs, (ii) the Tanzanian Innovation Ecosystem Report, which was carried out by Deloitte to provide an overview of the innovation landscape, (iii) Beyond the Hurdles Documentary, a short film on female founders and innovators, sharing lessons learned and inspiring stories, (iv) the Zanzibar Startup Ecosystem Scoping Study, which was co-funded with the Embassy of the Netherlands, providing insights and recommendations for the startup ecosystem in Zanzibar, and (v) National Guidelines on Establishing Spin-Off Companies, which was developed in collaboration with COSTECH and piloted across six higher learning institutions in Tanzania.

ATIP also met its target for Indicator 2.2, with 18 examples of new or strengthened knowledge and skills being put into use within the ecosystem. The RISA programme delivered 12 examples, such as the Africa Research Connect platform by WITS University in South Africa, and the Training of Trainers (ToT) model used by the Mawazo Institute in Kenya. IUK GAA's initiatives included the NextGen 2.0 Challenge and the Young Innovators Programme (YIP), which supported young innovators in the space sector and increased the reach of the #MoreThanAWoman initiative. The Funguo programme demonstrated improvements in ecosystem coordination, influenced policy discussions through a scoping study of the Zanzibar start-up system, and enhanced university curricula with tailored case studies relevant to local contexts.

Overall, ATIP has made significant progress in knowledge transfer, capacity building, and the practical application of new skills, contributing to strengthening innovation ecosystems across Africa.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The milestone for indicator 2.1 was revised upwards to 15 learning outputs for 2024/25 following the overachievement of last year’s target of 8 (and achieving 13). Indicator 2.2’s milestone was also revised upwards to 18 case examples from 4, as the indicator was significantly exceeded (15) in 2023/24.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s recommendation for this output was to develop more ambitious milestone targets to reflect the high achievement in this area. Efforts to promote greater co-creation with partners have resulted in enhanced partnerships and collaborative projects. RISA has increased efforts to disseminate learning outputs widely through various channels, including publications, workshops, webinars and digital platforms, ensuring that knowledge is accessible and actionable to maximise its impact.
As the ATIP programme enters its bridge year, it is recommended that the programme partners devise a comprehensive transition plan to ensure a smooth handover to local partners and stakeholders. This plan should focus on documenting processes, lessons learned and best practices to support sustainability efforts and guide future innovation systems work.
It is recommended IUK GAA focus on dissemination of recommendations from supported activities to relevant ministries and other policy actors, such as supporting the enabling policy environment for investments in Ekiti, Nigeria, and implementing recommendations from the Space in Africa report.

Output Title	Government and other ecosystem actors are informed, willing, able and take action to address ecosystem barriers
Output number:		3	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 # Innovation ecosystem actors with analysis and knowledge to influence evidence-based innovation policy	20 (cumulative target – up from 10 last year)	11 new ecosystem actors empowered to influence innovation policy in the period in review / RISA: 8 / IUK GAA: 3
3.2 # and case examples of key stakeholder actions addressing key ecosystem barriers, including policy & regulation	10	12 actions taken to address ecosystem barriers including policy in the period in review / RISA: 7 / IUK GAA: 5

Briefly describe the output’s activities and provide supporting narrative for the score.

ATIP has made progress in driving policy change and addressing ecosystem barriers, particularly in the areas of GESI.

Indicator 3.1: A cohort of eight RISA grantees has successfully driven and informed government actions and policy change through early engagement with governmental institutions. This participatory approach has fostered shared ownership of initiatives addressing development and economic challenges, leading to increased uptake at national and policy levels. For instance, the South African Research Institute for Innovation and Sustainability (RIIS) collaborated with the Kenya Space Agency to develop a national space roadmap for Kenya. This roadmap identified growth opportunities in Kenya’s space economy and provided actionable pathways for achieving growth, which the Kenya Space Agency has agreed to implement.

IUK GAA has influenced actions, policies and strategies of three new partners – the national space agencies of Kenya, Rwanda and South Africa as well as continuing to build the value of its strategic partnerships with the South African Technology and Innovation Agency (TIA); the Kenya National Innovation Agency (KeNIA); the Ekiti State Ministry of Innovation Science and Digital Economy (MISDE). In addition to these strategic partnerships, GAA activities have engaged 22 stakeholders representing government and other public bodies this reporting year, bringing the total number of stakeholders from government and public bodies within the wider GAA network to 194 since the start of the project.

Indicator 3.2: RISA awardees have made significant strides in embedding GESI and addressing ecosystem barriers around social inclusion. For example, the Impact Investing Ghana (IIGh) SCALE quality improvement programme has effectively addressed inclusion barriers by providing tailored business development support and financial assistance to women, youth, and persons with disabilities (PWDs) in rural Ghana. One notable example is Noni Hub, which implemented a GESI quota ensuring at least 30% of participants were women and 10% were PWDs. This initiative led to a 30% increase in female participation and 10% PWD inclusion, fostering a diverse entrepreneurial ecosystem. Additionally, Agrico Hub identified geographic and economic barriers and introduced a GHS 500 fee for their Digital Media Masterclass, partnered with Jobberman Ghana for tailored soft skills training, and provided transport stipends and remote learning options. As a result, over 384 participants, mainly rural women and youth, gained essential skills, improving their employability and business acumen. These efforts have significantly enhanced access to critical resources and support for marginalised groups, promoting gender equality, disability inclusion, and social inclusion in entrepreneurial programmes.

Additionally, through sustained engagement with the Ekiti State Ministry of Innovation Science and Digital Economy (MISDE), the IUK GAA team co-hosted the second Ekiti Innovation Summit and collaborated on innovation and funding models, such as the co-delivery and co-funding of the Young Innovations Programme.

These projects highlight ATIP's role in driving policy change and promoting inclusive growth.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The milestone target for indicator 3.1 was revised downwards this year (from 40 to 20) following challenges in achieving the target last year. Indicator 3.2 was revised upwards this year (from 8 to 10) to reflect the over-achievement from last year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

As the programme enters its final year, a key recommendation for ATIP partners is to focus on ensuring sustainability of the interventions and lasting system level change. Recommendations include taking participatory approaches and establishing early buy-in from national level actors. This has supported awardees in overcoming delays in bureaucratic processes that would previously hinder effective implementation.

Policy development work needs to be flexible and adaptive and should ensure that relevant government institutions are identified and formally engaged through MoUs or other binding agreements to mitigate challenges such as those experienced in the work of ISAAA in Kenya and THENSA in South Africa, which experienced significant delays and bottlenecks. Flexible approaches are critical, as seen in RISA’s support to the development of the R&D policy in Kenya which has had to go beyond its initial partnership with NACOSTI, to engage parent Ministries to secure support for policy development.
## D: VALUE FOR MONEY

Key cost drivers and performance

Across the different programme components, the key cost drivers were personnel – including grant related personnel and capacity building.

Economy
ATIP has effectively managed costs and leveraged external resources to complement available funding. RISA utilised Chemonics resources, including labour from head-office pools and specialised procurement support from Connexi in Ethiopia, ensuring cost savings and quality supply chain management. Competitive procurement practices, such as comparing quotations from multiple vendors, resulted in savings on venue costs and efficient procurement of legal and technical services. ASI's co-creation approach with stakeholders maximised the use of state-owned institutions for expert facilitation, reducing costs while maintaining quality. UNDP's procurement and travel policies ensured the best price for stipulated quality for all goods and services.

Efficiency
ATIP partners and institutions have demonstrated high productivity in converting inputs into outputs. ASI collaborated with the Federal Institute of Industrial Research to host workshops in Lagos at no cost, significantly reducing operational expenses. CONESAM utilised free spaces provided by SMEDAN in six Nigerian states for workshops and ecosystem gatherings. Mawazo Institute repurposed data collected during the Fellow onboarding process for multiple outputs, including the "Status of African Women in Research" report. The University of the Witwatersrand (Wits) expanded the maternal health innovation hub’s capacity using already mobilised technical skills and resources, achieving more without additional costs. The trilateral project activities under FUNGUO effectively used joint project resources (such as staff, office space, ICT equipment), preventing duplication of costs.

Effectiveness
ATIP interventions have achieved intended outcomes, including influencing policy, and adopting new technology for development outcomes and programmatic decision-making. RISA demonstrated strong effectiveness by generating tangible outcomes aligned with national priorities and ensuring adaptive and evidence-based management through rigorous MEL practices. RISA has documented progress in strengthening R&I ecosystems, overcoming key barriers and aligning with national priorities and SDGs. Ongoing MEL practices ensure evidence collection and analysis to measure impact, with structures in place for adaptive management and continuous improvement. Funguo's #YouthIgnite initiative provided TZS 600 million in grants to 10 HLIs and seed funding worth TZS 78 million to 20 student-led businesses, along with six months of coaching and mentorship. This demonstrates effectiveness of the Youthignite initiative to attract further funding from other entities, it also ignited coaching and mentorship offers.

Equity
ATIP has addressed equity by ensuring both the inclusion of women, marginalised groups and wider geographies in its activities, and by promoting more equitable distribution of the programme’s benefits – whether innovations, investment, networks or knowledge. RISA’s project with University of Gondar (UoG) has promoted socially inclusive technology and targeted female and disabled farmers in adopting improved agricultural practices, ensuring that marginalized groups were included in the innovation ecosystem. Its work with IIGh and DealSource through the SHEBA programme has promoted access to investment for female-led businesses. Work with Wits University has enabled creation of a data analytics platform to target marginalized populations with limited access to healthcare. ASI and CONESAM have developed guidelines to promote youth and women’s participation in research and innovation in Nigeria, while Jimma University in Ethiopia has addressed financial barriers for low-income innovators through direct equipment support. The IUK GAA project launched its Lead Customer Programmes (LCPs) across various sectors in a way that promotes equitable partnerships and participation. Funguo’s work with the Tanzanian Hub Network (THN) has expanded its membership, engaging 110 hubs across 10 regions and over 40 innovation ecosystem stakeholders from five African countries, with systematic sex and age-disaggregated data gathered for all interventions, with 54% of the new members being women-led organizations. It Youth Ignite programme has also aimed for a 50-50 gender split and ensuring 40% of funding for women-owned and led ventures.

Assessment of whether the programme continues to represent value for money

The programme continues to represent VfM. Based on the assessment of outcome and output attainment, theory of change, VfM, and evidence analysis, there is sufficient justification for the continuation of the project. The approval of the bridge year ensures continuation of priority projects, with some initiatives like the Agrifest Deal Room showing potential for self-funding through paid services. KTN has improved forecasting and expenditure management and the implementation of Open Innovation (OI) and Global Innovation Networks (GINs), including Lead Customer Programmes (LCPs) has expanded the project's scope, depth and impact. The Tanzania ecosystem has grown significantly, with active innovative ventures and enterprise support organisations. Overall ATIP collaborations with ecosystem stakeholders are effectively aligning objectives, pooling resources, and scaling impact.

E: RISK

The overall risk rating for the year under review was maintained at Moderate, and this rating is expected to continue as the programme enters its final year, focusing on closing out activities and learning from the successes and failures of ATIP programme-level interventions.

In 2024/25, implementation partners reported an improved ability to deliver outputs and contribute to outcome-level changes. This improvement is attributed to strengthened and trusted partner relationships built over time through continuous engagement. For example, in Nigeria, IUK GAA’s collaboration with Ekiti State’s MISDE has delivered significant impacts, such as the launch of the Ekiti State Investment Guide, and support for the Ekiti Innovation Summit and the Young Innovators Programme (YIP).

Financial and fiduciary risks to programme delivery were moderate. Some downstream delivery partners reported delays in fund disbursement, affecting project delivery. The programme team will follow up to prevent this from affecting delivery in the final year. Financial sustainability beyond ATIP remains a concern for partners. However, there are positive indications of partners exploring alternative funding sources. Funguo has initiated conversations with new partners to identify other funding streams, and embedding activities under existing UNDP programming is one option under consideration.

Financial risks from downstream partners were mitigated effectively. Funguo leveraged UNDP systems, including centralised procurement and payment processes, to mitigate financial risks. UNDP’s robust due diligence process helped navigate delivery risks from mismatched project partners. RISA implemented financial controls, including internal and external audits, regular spot checks, and processing payments only upon verification of deliverables.

IUK GAA maintained oversight of risks through monthly and quarterly updates to the risk register. Effective relationships with in-country stakeholders and FCDO (HQ and post) facilitated navigation of changes with minimal impact on delivery. RISA addressed safeguarding risks through increased involvement of a GESI Advisor and emphasised GESI considerations, including GESI-focused assessments of grantee reports. Climate and environmental risks were not identified as risks to delivery.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The ATIP delivery model highlights a strategic approach to programme implementation by leveraging a diverse array of partners, which includes government agencies, multilaterals, civil society organisations, non-governmental partners and commercial entities. This collaborative framework not only enhances the effectiveness of programme delivery but also ensures that ATIP can benefit from various perspectives and expertise. For example, and as noted in the 2024 independent review of ATIP, effective partnerships and collaborations reported have allowed resources optimisation and reduction of overhead costs. Viktoria Ventures and Mawazo institutes were providing their knowledge and expertise (staff time) and other in-kind support to Technical University of Kenya (TUK) during their activities at no or reduced cost and vice versa. The timely approval of the no-cost extension has allowed for continued delivery, thereby preventing disruptions and ensuring that critical activities remain on track, plus fostering alignment with the proposed successor programme.

On financial management, ATIP has managed forecasting variances to within 1% during the review period, although noting that HERA challenges in some instances have affected forecasting accuracy. Due to global FCDO fiscal pressures, it will remain unlikely that the full ATIP allocation of £32M will be disbursed, however, current projections suggest that the programme is well-positioned to spend at least 85.5% or £27.34M against the business case amount. The slower spend as noted in the independent review, is attributable to a significant budget pause in the early phases of the programme, which slowed down the pace and scale of the original delivery plans, including for MEL. Proactive and collaborative financial monitoring will remain important in ensuring that the programme can achieve its intended spend and delivery outcomes. Compliance efforts have been maintained and, in some instances, enhanced. For example, the establishment of quarterly cross-hub meetings underscores ATIP's expansive delivery model across Africa, necessitating routine check-ins to monitor progress. The onboarding of additional components during the bridge year (Sankore, ATIP MERL partner and OECD) signals the importance of effective coordination and governance mechanisms that allow for routine engagement to ensure continued alignment. Efforts are underway to also develop and refine programme specific ICF indicators and a methodology note.

RISA, under the management of Chemonics, has introduced a weekly disbursement tracker that offers FCDO real-time insights into fund commitments. This tool enhances transparency and accountability in fund management. Additionally, the RISA programme team and FCDO held a series of Investment Committee meetings for the East, West and South Africa portfolios in December 2024 where the team collectively reviewed and agreed on activities for the planned bridge year, ensuring that the grants pool will be fully committed early in the fiscal year 2025/26. Two pause and reflect (PnR) sessions as well as two thematic workshops (on Outcome Harvesting and Research to Commercialisation (R2C)) were held which will inform and improve future decision-making processes.

The Funguo initiative, managed by UNDP Tanzania, works with 13 downstream partners across different sectors, from government, public and private sector – touching on a diverse range of thematic areas from technology and innovation to logistical support. An updated delivery chain map is in place. Quarterly informal updates on both narrative and financial progress are shared with FCDO. An appreciation was received from the Funguo team on the quality of technical expertise and support received from the wider FCDO team, which goes beyond what other funders provide. A suggested area of improvement made by downstream partners was for increased support for hub-led initiatives to maximise grassroots impact and ensure that local needs are adequately addressed. The research, innovation and entrepreneurial pilot also referred to as trilateral project, which focuses on fostering research and innovation collaboration among India, East Africa and the UK, has made significant progress, as an agile, adaptive pilot in response to context specific implementation realities. The onboarding of additional personnel has been crucial in maintaining momentum and the establishment of weekly and bi-weekly meetings has ensured alignment among stakeholders including from other RED regional hubs and the timely delivery of project activities.

IUK GAA has placed strong emphasis on cultivating robust relationships with FCDO counterparts to enhance oversight of financial performance and project delivery. Effective management of forecasts and monthly budgets has been a top priority while also implementing strategies to mitigate risks associated with staff turnover through targeted recruitment efforts. The MoU extension provided assurances on project continuity to stem further departures. IUK are set to onboard a MEL partner to support project specific MEL activities. Field visits have also taken place throughout the year to ensure the country teams are supported and monitored in line with project activities and expectations, build connections and collaboration opportunities with stakeholders, and enhance the profile of the project in-situ.

The partnership between the British Council (BC), FCDO and the Kenya National Innovation Agency (KeNIA) built upon previous support to KeNIA and has helped the development of a National Entrepreneurial Institutions’ Maturity Framework, which aims to foster innovation within higher learning institutions. Personnel changes within BC have led to delivery delays, however, significant progress has been achieved against outlined activities, with new BC staff recruited to support delivery. Additional engagements have been held with stakeholders to wrap up pending deliverables and to explore how to streamline and coordinate UK’s support to KeNIA in future, reflecting a growing recognition of the UK-Kenya partnership's importance.

No assets have been disposed during the review period. However, a written submission for consideration and approval will soon be presented for the transfer of an asset under IUK GAA. Additionally, RISA has submitted an asset disposal plan that is under review.

Overall, the delivery workstreams reflect a commitment to effective programme delivery, financial management, and collaboration across various sectors, ensuring that objectives are met and impacts are maximised.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring, Evaluation and Learning (MEL) of ATIP’s progress has been prioritised this year, with additional focus on learning and mapping of results, tracking of outcomes and enhanced communication around what is working, particularly regarding system level change. Monitoring activities have included a review of partners’ ToCs, MEL plans and logframes to ensure alignment of their metrics to ATIP outcomes. Implementing partners have also carried out tailored capacity building sessions with their grantees to improve their ability for technical reporting and capturing of key metrics and case studies. IUK GAA focused on the development of case studies that showcase the programme’s progress towards its outcomes. It has also prioritised quality engagement with stakeholders, both formally through surveys and interviews, and informally through contact via core team members responsible for project delivery through on-site fields visits and stakeholder meetings.

RISA has continued to use its Aktek platform for tracking partners’ progress, as well as exploring the use of outcome harvesting methodologies, provided guided training and workshops for its partners to identify and capture outcome level changes and to map the shifts in the ecosystem that they are seeing as a result of their initiatives, whether in terms of improved job creation, increased revenues or contribution to policies developed. This methodology has enabled RISA grantees to go beyond measuring individual and institutional level results, and to start to intentionally track and report change at ecosystem-level. In the final year, RISA will focus on consolidating and communicating the results of its outcome harvesting and generating evidence and insights on what works for innovation ecosystem strengthening.

IUK GAA onboarded a new Strategic Learning Partner, MC Saatchi, and the M&E activity continued to be delivered by an external consultant, Hazel Tree Research, which works closely with the GAA programme team to ensure that relevant M&E data is captured and used to inform ongoing programme delivery. Quarterly M&E reports have facilitated regular review of progress with the wider GAA team. The RAG system allows for progress towards annual targets to be assessed on a quarterly basis, the results of which have been shared and discussed with team members at regular intervals to ensure that any ‘at risk’ performance targets have been addresses as needed. A more detailed monitoring tool has also been created this year to set targets and track progress per specific work packages to provide the team with additional insights and support in working towards achievement of overall annual targets.

Concerted efforts were made by all ATIP partners to improve programme communication this year. RISA has developed a comprehensive communication plan and a range of useful products (including slide decks and more visual reports) and there has also been an improvement in quarterly reporting through adoption of improved methods and capturing of stories of change to illustrate impact.

Evidence

Over the course of FY2024/25, RISA generated valuable evidence on different aspects of innovation system strengthening through four deep-dive studies in the following thematic areas: i) GESI; ii) Ecosystem Approach to Programming; iii) R2C and (iv) R&I Partnerships and Networks. These studies explored how RISA interventions are contributing to change at the ecosystem level and draw out learning around what works, why and how to drive scale and sustainability. These were utilised to support investment decision-making for 2025, to communicate the programme's impact to various target audiences and to provide actionable insights for better decision-making and resource allocation.

RISA’s Aktek platform has been a key source of evidence for reporting and generating evidence for decision-making especially on awardee and fund-level progress against ecosystem strengthening goals (ESGs). The dashboards have been key sources of information for both country and fund-level Pause and Reflect (PnR) sessions, providing insights on where more results have been realised and the interlinkages between the ESGs informing RISA objectives.

Ongoing products that will be key sources of evidence in 2025 include: country-level deep dives, research quality uptake and utilisation (SOAS), and access to finance (SOAS). RISA also plans to commission other evidence sources that include: a deep dive into the RISA-funded R&I endeavours to mitigate climate change, update APEAs/needs assessments in each country, enhance country-level ecosystem stakeholder mapping, explore successes in VfM at the grantee level, and produce a final consolidated learning document with case studies.

Learning

This year RISA organised a series of PnR and thematic learning sessions, which have contributed to a stronger emphasis on sharing and learning, as well as, strengthening of the quality of reporting and improving the capacity of partners to articulate the outcomes of their activities. The R2C PnR enabled the identification of critical areas of focus to promote research commercialisation and this learning has been used to develop a Research Commercialisation playbook (currently at the draft stage) which will act as a useful guide to institutions and start-ups to commercialise their research and innovation outputs.

This year RISA actively sought out seven major engagements to disseminate learning: i) Afrilabs Annual Gathering 2024 in South Africa (where DM hosted an inaugural “Makerspace” Track), ii) CEIL Summit Kenya (which coincided with PnR session in Kenya and VSL researchers actively participated), iii) the Kenya Innovation Week, iv) Ghana Digital Innovation Week (where IIGh is a key organiser), v) The 2024 Africa Impact Summit (where IIGh held a Deal Room that saw participation of 53 businesses and 13 Impact Funds), vi) Africa Evidence Summit where the Mawazo Team curated a GESI panel, and vi) the National Research Festival in Kenya (where ATIP partners shared learning on RCS and "Status of Women in Research"

IUK GAA has continued to build a valuable dataset through IUK’s internal CRM Workbooks data management systems which includes information on:
The type and progress of partnerships facilitated (introductions, collaborations and outcomes)
Geographical location including underserved innovation communities
Sector, size and other core organisational data
GESI data focused on women-led and youth-led organisations

The IUK GAA team has used cross-team learning to inform its activities, including the scaling up of initiatives such as Young Innovator, More Than A Woman and NextGen 2.0. It has also drawn on lessons from the successes of PBI pilots in Eldoret to inform the development and delivery of the Lead Customer Programme and Pilot Demonstration projects within the Global Innovation Networks (GIN) intervention. A IUK GAA PnR is also planned for the bridge year to enable a deeper dive reflection learning into the portfolio of interventions in Nigeria, Kenya and South Africa together with FCDO’s Research and Innovation Hubs.

This year ATIP will be recruiting a Monitoring, Evaluation Reflection and Learning (MERL) partner to work with all of the delivery partners and build a rich evidence base that brings together ATIP programme-level insights and feedback from the programmes complex, diverse sectors and geographical locations.

Lessons for the programme and FCDO

Given ATIP partners’ common areas of interests and shared objectives around driving lasting system change for technology and innovation, more opportunities need to be made to draw out lessons from across the various projects and to harmonise metrics and ways of measuring effectiveness. The engagement of the new ATIP MERL partner, as well as the planned ATIP-wide PnR workshop in April 2025 should contribute to these aspirations for joint analysis and learning. A new partnership with the OECD’s Innovation Development Facility (INDEF) will also be valuable for mapping out different approaches to innovation system strengthening and facilitating technical exchanges on indicators and measurement frameworks, for assessing the effectiveness of different efforts to strengthen innovation and research ecosystems.

In this final year of ATIP, a key focus for FCDO should be on supporting long-term sustainability of the programme’s efforts. With the wealth of networks, expertise and evidence that ATIP has generated over the past five years, it will be critical that this bridge year capitalises on progress so far, and works with its partners to co-create sustainability plans which enable them to maintain and expand the excellent work that has been catalysed by ATIP so far.

While ATIP’s partners’ interventions have delivered significant impact at the institutional level and in some cases, have also contributed towards promising changes in the way that research and innovation are conducted and scaled in the target countries, it is recommended that the programme should be more ambitious in this final year in terms of engaging governments and high-level stakeholders in its work to push for lasting system level change.

Date of last narrative financial report	RISA: 31/01/2025 / Funguo (informal reports/ progress report: 2/12/2024. Formal progress report for year ended 31 Dec 2024 – by end March 2025) / KTN GAA: Formal Q3 progress report received 04.02.2025	Date of last audited annual statement	RISA: February 2025 / UNDP Tz (Funguo): 2021 (NB: there is an ongoing audit for the Tz office). UNDP (globally – 2022).