BUSINESS CASE ADDENDUM

PROGRAMME TITLE
Directorate/ Post	Global Tech Directorate	Contact name
Original programme budget	£32,000,000	Country or region targeted	Kenya, Nigeria, South Africa and adjacent African countries.
Cost extension value (if applicable)	N/A	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	Research and Evidence (RED) Director
New increased or reduced programme budget (if applicable)	N/A	Original programme start and end dates	Start: 04/12/2019 / End: 31/03/2024
Latest AR programme score	A+	New programme end date (if applicable)	31 March 2027
		Programme ID	300704

Detailed information
Programme summary	(250 words maximum) / The Africa Technology and Innovation Partnerships (ATIP) Programme, signed off in 2019 with a £32 million budget, operates in Kenya, Nigeria, South Africa and adjacent countries to catalyse inclusive innovation ecosystems, foster UK-Africa S&T partnerships and drive sustainable economic growth through knowledge transfer, capacity building and policy engagement. Over six years, ATIP has supported over 200 start-ups and SMEs, facilitated more than 50 UK-Africa R&I collaborations and contributed to the UK’s strategic objectives in Africa through multiple workstreams. In its final extension (until March 2027), ATIP will support the UK’s Technology Community of Expertise (TCoE) pilots, established in response to the ODA reduction to 0.3% to enable posts and policy teams to access tailored technical assistance, deepen strategic partnerships and support country partners to drive technological transformation responsibly, including mitigating risks such as tech dependency and exclusion. / Lessons learnt (informed by the latest ATIP Annual Review): / Lesson 1 – Emerging lessons indicate that targeted interventions can address systemic challenges in African innovation systems, including fragmented policies, weak university-industry linkages and underinvestment in R&I infrastructure. ATIP has shown that fostering commercial partnerships and promoting collaborative cultures can lay the groundwork for more integrated technology innovation ecosystems. / Lesson 2 – ATIP’s use of alternative metrics, including its bespoke network health measurement tool, has been critical in providing insights into what is required to build and sustain effective partnerships. Monitoring progress in human capital and institutional readiness—including budget allocations, staff hires and incubator performance—has enabled partners to track R&I commercialisation and understand programme impact on national R&I infrastructure. / Lesson 3 – ATIP has demonstrated that sustained system strengthening requires tailored follow-on funding. Matching support to ecosystem maturity—from small grants to larger investments—helps maintain momentum, attract resources and create clearer pathways for scaling innovation.
Changes	(300 words maximum) / While the ATIP BC outcomes and impacts have not previously been amended, three No Cost Extensions (NCEs) were approved (in July 2021, September 2024 and December 2025), to align with spending reviews, budget revisions and ODA cuts. The proposed BC Addendum now seeks to broaden ATIP’s scope, enabling it to serve as a platform for piloting the new TCoE and extending Helpdesk enquiries to other global regions beyond Africa in 2026/27. This approach responds to the UK’s reduction of ODA from 0.5% to 0.3%, requiring a shift towards greater reliance on UK expertise to maximise impact and efficiency, and to ensure high-quality, sustainable outcomes aligned with UK priorities in key geographies despite tighter budgets. / To this end the addendum does represent a material change from the original business case, allowing for the geographic expansion of TCoE pilots beyond Africa to include select countries in Asia and Latin America. It also broadens the programme’s spend type to include Non-ODA funds, recognising that some TCoE priority posts may not be ODA eligible. This change facilitates new partnerships oportunities with ODA and non-ODA countries and the private sector. Importantly, this material change will not affect other aspects of ATIP, as all ATIP components except the TCoE Helpdesk will conclude in March 2026. / An updated Theory of Change (ToC) is being developed to reflect the intended outcomes of the TCoE, which remain closely aligned with ATIP’s original impact areas, albeit with wider geographic scope and the vision of longer term sustainablilty through blending ODA and NON-ODA financing and UK growth. The focus continues to be on leveraging UK expertise to enhance capacity and capability at country level, advancing mutually beneficial and strategic science, technology, and innovation objectives.
Implementation	(100 words maximum) / TCoE pilots will be delivered via an Accountable Grant with R4D, using a helpdesk model to triage requests and provide expert support for Layer 1 pilots and select Layer 2 interventions. The ATIP SRO will retain accountability, ensuring delivery aligns with ATIP’s objectives and wider UK Strategy on ST&I. The FCDO TCoE technical and in country teams will manage pilot delivery, supported by R4D’s MEL system to assess effectiveness. An external partner will also provide oversight to ensure strong alignment with the wider ATIP objectives and the overall TCoE framework. Bi-weekly meetings with R4D will ensure alignment and progress towards objectives.
Budget	(100 words maximum) / The overall BC budget for ATIP is not being amended. The budget headroom remaining in ATIP’s business case is up to £3.7M in support of the TCoE Helpdesk pilots. The budget and expansion of activities for outer years will be finalised in Q4 in coordination with the implementing partner (R4D) and is currently projected at up to £1M.
Impact	Impact of cost/time extensions on VfM (check relevant box): / ☒ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☐ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition.
Risk	(100 words maximum) / Below is limited to risks with a ‘major’ risk rating, although these remain within ATIP’s risk appetite of moderate. / Risk Mitigation / TCoE Helpdesk requests received for countries where we do not have in-country expertise to provide appropriate contextual response. Build and expand a Specialist Network, prioritising institutions and experts in focus countries; continue partnering with UK and context specific specialists. / Specialist Network performance is unsatisfactory, therefore delaying milestones. Hold fortnightly check-ins with R4D. Helpdesk Managers monitor consultant progress with oversight from the R4D Programme Manager. / Contracting and procurement delays for setting up institutional partnerships and recruitment of experts limits progress against workplan. Engage a dedicated Procurement Manager experienced in helpdesk contracting to ensure timely onboarding and compliance.
Results/Monitoring and Evaluation	(100 words maximum) / The proposed changes will enhance ATIP’s scope and ability to deliver results strengthening ST&I systems beyond core African focus countries to geographies in Asia and Latin America, drawing on six years of programming. Up to 50 Helpdesk requests are expected, at least half from Africa. The original ToC remains valid, but a revised TCoE ToC will reflect broadened scope and new outcomes, particularly partner shipbuilding and leveraging UK expertise. The amendment will enable piloting of the TCoE model, crucial to adding to the UK’s learning on delivery models. Monitoring and evaluation required, with a MEL framework codeveloped by R4D and FCDO.