Programme Completion Review

Title: Reproductive Health Supplies
Final Programme Spend £ (full life): / £312,564,686.00	Review Date:	30/06/2025
Programme Code: 300713	Start Date: 10/12/2019	End Date: 31/03/2025

Summary of Programme Performance

Year	2020	2021	2022	2023	2024/5
Programme Score	A	A	A+	A	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/57881309.odt
DevTracker Links to all logframes used during programme lifetime:	DevTracker Programme GB-GOV-1-300713 Documents

Acronyms

SRH	Sexual and Reproductive Health
SRHR	Sexual and Reproductive Health and Rights

AMP	Aid Management Platform
AOP	Apnoea of Prematurity
CAC	Comprehensive Abortion Care
CHAI	Clinton Health Access Initiative
CIFF	Children’s Investment Fund Foundation
COF	Catalytic Opportunities Fund
CYPs	Couple-years of Protection
DRM	Domestic Resource Mobilisation
EWENE	Every Woman, Every Newborn, Everywhere
FP	Family Planning
GFF	Global Financing Facility
HSS	Health Systems Strengthening
IM	Implementing Mechanism
IPPF	International Planned Parenthood Federation
LMA	Last Mile Assurance
LMIC	Low and Middle Income Country
MA	Medical Abortion
mCPR	Modern Contraceptive Prevalence Rate
MHS	Maternal Health Supplies
MMS	Multiple Micronutrient Supplements
MnHS	Menstrual Health Supplies
MoH	Ministry of Health
NLUM	New and Lesser-Used Medicines
NURHT	New and Underused Reproductive Health Technologies
ODA	Overseas Development Assistance
PATH	Program for Appropriate Technology in Health
PPH	Postpartum Haemorrhage
PQ	Prequalification
(P)SEAH	(Prevention of) Sexual Exploitation, Abuse and Harassment
RHSC	Reproductive Health Supplies Coalition
SDP	Service Delivery Point
SEMA	Shaping Equitable Market Access
SRA	Stringent Regulatory Authority
SRMNH	Sexual, Reproductive, Maternal, Newborn Health
STG	Standard Treatment Guidelines
ToC	Theory of Change
UNFPA	United Nations Population Fund
UNICEF	United Nations Children’s Fund
USAID	United States Agency for International Development
VfM	Value for Money
WHO	World Health Organisation

A. Summary and Overview

Description of the programme and what it has achieved

221 million women and girls around the world have unintended pregnancies, with over 60% ending in abortion and 45% of these being carried out using unsafe methods. Persistent market failures and a lack of domestic financing for Sexual and Reproductive Health (SRH) commodities continue to undermine access to comprehensive SRHR supplies and services worldwide. The Reproductive Health (RH) Supplies programme worked to support expanded access to RH commodities – including contraceptives, maternal health medicines and safe abortion supplies – in over 54 of the world’s poorest countries.
[note] SWP Report 2022: Impacts | United Nations Population Fund (unfpa.org); Guttmacher Institute (2019), “Adding It Up: Investing in Sexual and Reproductive Health 2019”, available online at: https://www.guttmacher.org/report/adding-it-up-investing-in-sexual-reproductive-health-2019

Limited commodity availability remains a barrier to universal SRHR, alongside a range of other obstacles preventing women and girls from accessing RH services. These include weak health systems, restrictive policies, misinformation, geographic barriers, poor counselling and social stigma. Donor funding of essential health commodities delivers exceptional VfM. By pooling donor funding, aggregating demand and purchasing health commodities globally, we are able to capture economies of scale, create attractive markets for manufacturers, secure affordable prices and dramatically increase commodity availability, choice and quality in LMICs.

However, we need to do more than simply purchase commodities if we want to secure sustainable commodity availability in LMICs. RH commodity markets are fragile and complex and currently do not function as effectively as they could. This is because the journey from the product manufacturer to end user is fraught with challenges and risks. Low and uncertain demand for RH commodities due to social norms, fluctuations in financing and political priorities can deter suppliers from beginning long and costly registration processes, investing in research and development (R&D) and scaling up manufacturing capacity. As a result, RH commodity markets in LMICs are often stuck in ‘market traps’ characterised by few quality-assured suppliers, high prices, low demand and lack of innovation. These market traps ultimately constrain access to essential medicines in low-income countries, worsening health outcomes and reducing the VfM derived from donor funding.

RH Supplies programming was structured around two complementary investment tracks designed to be mutually reinforcing to address these issues. Track 1 was the UK’s anchor investment in UNFPA Supplies Partnership - the world’s largest provider of RH commodities for low- and middle-income countries (LMICs). The UNFPA Supplies Partnership aggregates demand for RH products at the global level and delivers supplies to 54 LMICs. Track 2 consisted of complementary investments in the Clinton Health Access Initiative (CHAI) and Reproductive Health Supplies Coalition (RHSC) to strengthen the RH commodity ecosystem so that it is better equipped to build and strengthen markets, ensure adequate supply, and roll out game-changing new products in the long term. Track 2 added to the Value for Money (VfM) of Track 1 funding and worked to increase sustainability of access as donors progressively begin to share the funding burden with partner governments.

RH Supplies helped to accelerate sustainable progress towards universal access to SRHR by 2030 (Sustainable Development Goal 3), supporting the UK’s commitment to defend and promote universal and comprehensive SRHR. In September 2024, the Government signed the She Decides Champion Statement on Safe Abortion Day alongside 9 other countries to commit to supporting comprehensive SRHR, including safe abortion; and in June 2025 Baroness Harman, the UK Special Envoy for Women and Girls, addressed leaders on SRHR, expressing her commitment to standing with and alongside women and girls demanding their rights.
[note] Joint statement at the 58th Session of the UN Commission on Population and Development - GOV.UK; 7 April 2025
[note] Champion Statement | SheDecides

The success of this programme is reflected in the decision to continue funding UNFPA Supplies and CHAI from 2025 through CHOICES for Reproductive Health [GB-GOV-1-400123], which will continue to drive forward progress on the UK’s SRHR commitments.

Key achievements:
- Provided a potential cumulative 43.2 million couple-years of protection (CYPs) through the procurement of contraceptives and condoms, giving greater protection and autonomy to women around the world.
- Delivered major strides in domestic resource mobilisation (DRM) progress for SRHR, with domestic financing quadrupling between 2020 and 2023. Countries allocated a record $45.1 million to commodities in 2024.
- 50% increase in the number of LMICs with at least one quality-assured supplier of key safe abortion commodities (medical abortion (MA) combipack) and a 103% increase in the availability of long-acting contraceptives (Hormonal IUD).
- Progressive reform and strengthening of the UNFPA Supplies governance system, with increased representation of country perspectives, resulting in decisions grounded in country realities and informed by the needs of governments and on-ground partners.

Major lessons learned, evidence generated and recommendations

This section summarises the key lessons and recommendations from the programme, drawing together findings from across different outputs. More detailed and specific findings and lessons relating to each output are captured in later sections of the report.

SRH commodity financing:
Uncertain and fluctuating UK ODA funding availability over the life of the programme has curtailed programme impact and significantly limited the ability for sustainable long-term planning with partners and national governments. Significant and sudden budget cuts to the programme of over 85% in 2020 and 2021 were estimated by UNFPA to have impacted the ability to prevent around 250,000 maternal and child deaths, 14.6 million unintended pregnancies and 4.3 million unsafe abortions. Major reductions to budgets for CHAI and RHSC over this time also undermined trusted partnerships with national governments, restricted both partners’ ability to plan effectively and risked undermining value for money. As the UK moves towards ODA at 0.3% of GNI by 2027, a clear funding picture and early communication of budget changes will be critical to protect the integrity of rebuilt partnerships and safeguard the value for money of UK ODA. The ability to make multi-year commitments will also be an important part of realising UK future priorities for global access to comprehensive SRHR and women and girls’ empowerment, ensuring that long-term planning is possible.

UNFPA Supplies co-financing mechanisms have demonstrated that domestic resource mobilisation for SRH commodities is possible and realistic. Whilst UNFPA Supplies is now pivoting its model towards mechanisms that can support pathways for accelerated transition in the next 5-7 years, donor financing remains a critical element of the financing mix for the medium term. Domestic financing progress within the UNFPA Supplies Partnership has exceeded expectations in the initial years of implementation – proving that co-financing incentives can work to secure funding lines in national budgets for SRH commodities. Feedback from implementing countries has consistently demonstrated the value of the UNFPA Supplies domestic resource mobilisation toolkit as an incentive for securing domestic funding. Prompted by the global shocks in ODA financing and following the withdrawal of USAID funding across global health, UNFPA Supplies is now rapidly pivoting to adapt its co-financing mechanisms towards modalities that can support accelerated transition of countries out of UNFPA Supplies support in the coming years. In the new ODA environment, it will be critical that this includes developing transition strategies that work closely in coordination with other SRHR financing channels including the Global Financing Facility and bilateral investments in SRH commodities. Political economy realities and limited fiscal space mean that the transition to a greater burden share of domestic financing will nevertheless continue to be a medium to long-term process, especially given the political sensitivities around SRHR and growing risk of rollback in many settings.

Programme lessons:
The Best Practices Grant, delivered by CHAI, has illustrated the feasibility, importance and value of taking a health systems approach to SRH product introduction through delivering cross-cutting market functions that build a durable ecosystem and support country capacity. The grant provided flexible funding for new SRH product introduction and coordinating global action around specific products. By only working with one provider (CHAI) on our market shaping work under CHOICES we will reduce programme management burden and progress towards a single strategic framework to reduce fragmentation and drive coherence.
l
The programme has sharpened its focus on equity and access, and future programme evaluation approaches should seek to build on this including by tracking reach to users, particularly those in underserved groups. UNFPA Supplies has scaled up efforts to strengthen supply chains and improve data visibility in hard-to-reach areas, directs life-saving support to women and girls in a range of humanitarian settings and is expanding access to products that are well suited to low-resource settings and meet the needs of underserved groups. Best Practices includes work to target underserved groups (adolescents, people with disabilities), this should be expanded and equity mainstreamed in future programming.

Improved coordination and alignment between programme partners has grown over the life of the programme, but further opportunities remain to strengthen and institutionalise partnership between UNFPA Supplies and CHAI going forward. A collaboration MOU between UNFPA Supplies and CHAI signed in early 2025 has identified specific areas of joint working and coordination in particular around domestic resource mobilisation, product introduction and scale-up. A recent evaluation of the Best Practices Grant identified strong complementarity across the two strands but recognised variation in join up at country level, with scope to do more.
Comprehensive SRHR approach:
Expanding the focus of SRH commodity access beyond siloed efforts on family planning, towards a more holistic approach on safe abortion, maternal and newborn health commodities, has proven critical to advancing comprehensive SRHR and responding to country priorities. Future programming should build on this and explore additional opportunities, including on integration with HIV services and supplies as relevant. Through multilateral and bilateral engagement the UK has championed a comprehensive approach to support integration of FP, comprehensive abortion care (CAC) and maternal and newborn health (MNH) supply access – including working with UNFPA Supplies to explore alignment and integration opportunities between FP and Maternal and Newborn Health (MNH). Work under the Best Practices Grant through CHAI has demonstrated the value of a systems focused and integrated approach to market shaping for SRH commodities at country level. The impressive progress made under Best Practices since expanding to MNH commodities has demonstrated government appetite and leadership on taking a more comprehensive approach. Targeted efforts with partners towards advancing access to safe abortion have accelerated progress on access, however challenges remain in the face of increasing risk of SRHR rollback which threatens future backsliding.

FCDO engagement:
Despite challenging budget cuts, UK leadership on SRHR within the sector has played an important role in driving progress on access to SRH supplies and influencing the wider ecosystem. Looking ahead to CHOICES, sustained advocacy, strong partnership and staff capability and experience is required to make progress on UK priorities including safe abortion, maternal and newborn health and the successful implementation of domestic financing initiatives. A well-staffed programme team is critical to also support targeted engagement across FCDO Posts that can deliver on joint priorities at country and regional level.

FCDO’s programme-funded secondee into UNFPA Supplies has been widely recognised as adding significant value to the UNFPA Supplies partnership, supporting implementation and delivery of the operational model and reinforcing FCDO’s strong partnership with UNFPA. The post has been particularly critical in advancing the SRHR domestic resource mobilisation agenda globally, delivering on a key UK and wider partner priority. More broadly the role has provided an important link between UNFPA and FCDO, supported partnership building across the programme, and added invaluable insight and expertise to the programme team. Further secondments should be prioritised in future programming given the high value for money and benefits to FCDO.

Investment in RHSC has supported positive results in convening and advocacy for reproductive health commodities across the sector, however the need to streamline FCDO interventions in line with comparative leadership on market shaping and SRH commodity availability has emerged as an important priority. An in-depth assessment of FCDO’s comparative strengths in reproductive health supplies investments as part of the CHOICES business case development concluded that FCDO’s focus in market shaping and country level health systems strengthening for product introduction was a key added value to the SRHR ecosystem. Streamlining future complementary investments through a single CHOICES Accelerator model via CHAI was also a key priority to ensure FCDO has sufficient programme management capacity to deliver the programme effectively, leading to a decision to step back from direct investment in RHSC and our role on the Executive Committee in future programming.
Market shaping:
The programme has demonstrated the high strategic value of complementary market shaping interventions under Best Practices to improve the value for money of the UK investment in UNFPA Supplies. The Best Practices external evaluation found a high degree of complementarity between UNFPA Supplies and CHAI investments, but recognised scope for more strategic alignment. This is planned under CHOICES, including a programme level steering board to drive coherence. Key achievements of the programme reflect the mutually reinforcing nature of market shaping and procurement interventions, for example, work by CHAI to realise a 40-80%+ price reduction for two quality-assured hormonal IUD (HIUD) products through the hormonal IUD market access strategy (see further detail in Outcome 3 narrative); and collaborative efforts to support accelerated rollout.

Fragmented donor priorities in commodity market shaping, in particular within the Maternal and Newborn Health space, have limited the potential for a global approach and therefore faster progress to advance access to lifesaving interventions. A lack of alignment between donors was a key contributing factor in the collapse of the planned Market Access Initiative, SEMA (Shaping Equitable Market Access for Reproductive Health), which aimed to establish a shared mechanism with other partners for investment and coordination of market shaping intervention for advancing access to Reproductive Health commodities. Challenges in coordination have persisted, in particular in the MNH commodity sphere, despite efforts to drive alignment by the Every Woman, Every Newborn, Everywhere (EWENE) coalition of partners led by WHO, UNICEF and UNFPA. Coordination efforts have instead relied on individual partnerships and instances of collaboration. Future programming should explore options for systematic engagement across the sector on market shaping that is realistic and practical given historic challenges.

How this report was conducted

This report is based on an internal FCDO review by the programme PRO and SRO of:
- the activities and outcomes of the programme over its lifetime;
- previous annual reviews which have included independent FCDO reviewers outside SRHR team;
- external evaluation of the CHAI Best Practices Grant conducted by Hera;
- UNFPA Supplies Annual Report for 2024; and
- engagement with UNFPA Supplies, CHAI and RHSC, including previous programme and site visits.

In addition to specific reporting commissioned for this PCR, the final score includes a review of regular data-based reporting provided by programme partners to FCDO.

Actions following approval of this report

N/A. As of 30/06/2025, all final programme payments had been processed and audited financial statements had been received. No funds were unspent.
## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£600,000,000	£312,564,686
Timeframe	5 years	5 years
Outcomes	Equitable access to safe, effective and affordable SRHR commodities, including in hard to reach areas and fragile settings, and enhanced country commitment and capability to fund, procure and supply commodities.	Improved access to safe, effective and affordable SRHR commodities in 54 LMICs including in hard to reach areas and fragile settings; introduction of new and quality-assured commodities providing women and girls with a greater degree of choice; increased focus on maternal and newborn health (MNH) supplies; and enhanced country commitment and capability to fund, procure and supply commodities including increased DRM through UNFPA Supplies’ match fund.

Overall assessment of programme outcomes, sustainability and VfM

UK ODA budget cuts over the life of the programme have reduced the total funding available for implementation by around 50%. Whilst the programme has still performed well, these significant budget reductions have led to inevitable knock-on impacts on the programme’s ability to deliver to its full envisaged scope and impact. Particular acute pressure was felt on implementation in 2020 and 2021, given the dramatic and sudden nature of cuts during the height of the COVID-19 pandemic. UNFPA estimated that the budget cuts in 2020 and 2021 of over 85% to FCDO’s contribution to the UNFPA Supplies Partnership meant the loss of funding for essential supplies with the potential to prevent around 250,000 maternal and child deaths, 14.6 million unintended pregnancies and 4.3 million unsafe abortions. Plans to develop and scale up the Best Practices Grant with CHAI also had to be significantly curtailed during this period, slowing progress in support to country-led market shaping and stewardship efforts. Funding to the Reproductive Health Supplies Coalition (RHSC) was also significantly impacted, limiting its ability to deliver on the full breadth of its strategic plan.

However, despite budget reductions, the UK’s continued investment, close collaboration and trusted relationships with implementing partners have successfully advanced key UK priorities on global SRHR commodity access and availability. This includes driving forward governance reform of the UNFPA Supplies partnership to support improved decision-making, strengthening Last Mile Assurance (LMA) processes and policies to ensure commodities reach service delivery points, and spearheading the development of an innovative and ambitious approach on DRM led by the FCDO’s secondee to UNFPA Supplies. Over the course of the RH Supplies programme, the FCDO’s grant with the Clinton Health Access Initiative (CHAI) has successfully developed a new partnership model with 10 priority countries on market shaping and market stewardship for SRH commodities, building on an initial concept to share best practices for product introduction and evolving this into sustainable mechanisms that are government-owned and set up to support ongoing access to new and transformative SRH commodities as they become available. The UK’s investment in RHSC has supported global visibility of SRH commodities and advanced global efforts towards a more comprehensive approach to reproductive health supplies that including menstrual hygiene, safe abortion and maternal and newborn health.

Programme investments have continually demonstrated high VfM. Investing in Family Planning remains a development ‘best-buy’, returning up to $120 per dollar invested. The programme’s outcomes in expanding access and choice of reproductive health options for women and girls, has continued to play a crucial role in empowering women, adolescents and girls – supporting them to unlock their social, economic and political agency as full members of society. The evidence shows that this in turn unlocks economic growth at the national level – supporting the emergence of strong economies and societies in predominantly LMICs.
[note] Kohler, H. and Behrman, J. (2014), “Post-2015 Consensus: Population and Demography Assessment”, available online at: https://www.copenhagenconsensus.com/publication/post-2015-consensus-population-and-demography-assessment-kohler-behrman

Market shaping investments through CHAI have proven their VfM and impact potential, alongside procurement interventions. A wide set of market barriers continue to plague access to RH commodities, with high prices and limited supply limiting the availability of key products like the hormonal IUD (HIUD). These market failures could not have been solved through procurement alone – they required a variety of demand- and side-supply interventions, including price negotiations, demand forecasting and national capacity-building. Interventions delivered by CHAI through the Best Practices Grant have significantly scaled up access to innovative reproductive health supplies such as the HIUD and medical abortion combipack (MA combipack) previously limited by high prices and uncoordinated demand.

Progress against logframe impact and outcome indicators

The below results are derived from the 2024 programme implementation year, for which comprehensive data are available. Since programme commencement, targets have undergone two revisions. In 2021, targets were revised in response to FCDO funding reductions. In 2023, UNFPA Supplies’ scope expanded from 48 to 54 countries, necessitating corresponding target adjustments. Data in this report after 2023, including the final targets, encompass information for all 54 programme countries.

Overall progress trajectory:
Initial strong progress in the first year of the programme slowed or reversed across several indicators between 2020 and 2021, in large part due to the significant cut in ODA funding and to the challenges of the COVID-19 pandemic. However, the programme adaptions made to increase domestic resource mobilisation, diversify the number of donors to UNFPA Supplies, and adapt our Best Practices approach with CHAI to respond to the changing context, enabled sustainable progress to be delivered over the following years. As a result, the programme has been rated as achieving the original outcomes, despite an overall almost 50% cut to funding.

Indicator	Baseline (2019)	Starting Target	2020	2021	2022	2023	Final Target	2024
Impact Indicators
Impact Indicator 1: Average modern contraceptive prevalence rate (mCPR) (%) in priority countries disaggregated by age, residence and wealth quintile	24.5%	25%	25.1%	24%	24.3%	23.3%	24.8%	23.8%
Impact Indicator 2: Average demand for FP satisfied with modern methods in priority countries	49.1%	50%	49.4%	54.6%	55.1%	55.5%	56.8%	56.4%
Impact Indicator 3: Contraceptive method mix (including information on method mix score and method skew) *The lower the score, the better the availability of a variety of different contraceptive methods	7.5	7	8.1	9.3	8.2	6.7	7.3	6.8
Impact Indicator 4: Number of unintended pregnancies averted due to modern contraceptive use per year.	23.9m	25.3m	25.3m	26m	28.6m	35.7m	28.8m	36.5m
Impact Indicator 5: Number of maternal deaths averted due to modern contraceptive use	14,000	77,500	77,470	74,340	87,950	95,700	84,000	97,600
Outcome Indicators
Outcome Indicator 1: Percentage of countries with 85 per cent of secondary and tertiary service delivery points (SDPs) that have at least 5 modern FP methods available on the day of visit or assessment (disaggregated for urban-rural and SDP type)	57%	77%	61%	51.5%	60%	65%	57%	68%
Outcome Indicator 2: Percentage of countries reporting no contraceptive stockout in at least 60% of Service Delivery Points (SDPs) on the day of the survey (disaggregated for urban-rural and SDP type)	36%	57%	27%	44.1%	67%	61%	47.2%	45%
Outcome Indicator 3: Number of countries where governments sustain or increase the amounts allocated for procurement of contraceptives and who spend more than 80% of the allocated amount for the year	N/A	8	8	4	11	14	14	15
[note] In 2021 the number of countries reporting to UNFPA Supplies through facility surveys was 34 countries. In 2022 this was 27 countries; as a result the percentages are not directly comparable across the two years.

Impact

Impact Indicator 1: The average mCPR for 54 UNFPA Supplies Partnership countries for 2024 is 23.8: an increase from 23.3 in 2023. Although this represents a slight decrease from the baseline, the figures are not directly comparable as the number of partnership countries increased from 48 in 2020-2022 to 54 in 2023-24. Only two of the eight countries added in 2022 had starting mCPR figures higher than the 2019 baseline. Notable disparities exist among age cohorts, underscoring the sustained necessity for service provision to prioritise the requirements of adolescent and marginalised demographics. In 2024, the median Contraceptive Prevalence Rate (mCPR) among females aged 15-19 was 19.4%, in contrast to 33.3% among women aged 30-34. Furthermore, mean values for the lowest wealth quintile were 24.1%, as opposed to 35.0% within the highest wealth quintile.

Impact Indicator 2: Across the 54 UNFPA Supplies Partnership programme countries, the average demand for FP satisfied with modern methods increased from 49.4% in 2020 to 56.4% in 2024.

Impact Indicator 3: Across the 54 UNFPA Supplies Partnership programme countries, the contraceptive method mix score in 2024 was 6.8 out of 10 (showing a moderate concentration of users on a limited number of methods); a decrease from 8.1 in 2020 – as a lower score indicates a higher availability of a variety of contraceptive methods, this represents successful progress. With respect to method skew, in 2024, a single modern method was dominant (accounting for more than 50% of all modern contraceptive users in 19 (35%) of the 54 UNFPA Supplies countries for which data were available). This remains unchanged from 2023.

Impact Indicator 4: In 2024, 36.5 million unintended pregnancies were averted due to modern contraceptive use in the 54 UNFPA Supplies programme partner countries. This was an increase from 25.3 million in 2020 and 35.7 million in 2023.

Impact Indicator 5: For the 54 UNFPA Supplies Partnership programme countries, 97,600 maternal deaths were averted due to modern contraceptive use in 2024; a significant increase from 77,470 in 2020 and from 95,700 in 2023.

Outcomes

Outcome 1: In 2024, among the 40 countries with survey data, 27 (68%) had at least five modern contraceptive methods available at 85% or more of their secondary and tertiary-level service delivery points (SDPs); a significant increase from 61% in 2020 and surpassing the 2024 target of 57%. On average, contraceptive availability was higher in urban SDPs (77%) than in rural SDPs (67%) and slightly higher in secondary-level SDPs (81%) compared to tertiary-level SDPs (76%).

Outcome 2: In 2024, 45% of countries (15 out of 33 UNFPA Supplies Partnership programme countries with survey data) reported that at least 60% of their service delivery points (SDPs) had no contraceptive stock-outs on the day of the survey. This represents an improvement from 27% in 2020, but remains slightly below the 2024 target of 47.2%. On average, 55% of countries reported no contraceptive stock-out in at least 60 per cent of urban SDPs on the day of survey and 45% in rural SDPs.

Outcome 3: In 2024, 15 countries made allocations in their national budgets that were either the same or more than the previous year for family planning; they went on to spend more than 80% of their allocated amount. The number of countries has significantly increased from just 8 in 2020 to 15 in 2024, indicating more government allocating and spending resources for the purchase of family planning contraceptives.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The Theory of Change (ToC) for RH supplies (at Annex A) set out how the programme would support the establishment of a more coordinated RH commodity ecosystem enabling women and girls to access a range of affordable and quality RH commodities (contraceptives, safe abortion, maternal health, menstrual health and newborn health products) from the public and private sector, including the young, poor and those living in rural areas.

The original input into the ToC was the provision of up to £600m over 5 years to the UNFPA Supplies Partnership programme for the procurement of RH commodities; core and programmatic funding to the Market Access Initiative (which evolved into Shaping Equitable Market Access (SEMA) ) to improve global and country level data analysis and to design and execute market strategies including introducing several innovative RH technologies and transforming access in the private sector; funding to the ‘Best Practices’ grant to build government capacity for routine product introduction; and funding to RHSC to advance priority RH commodity issues and to provide critical community tools.

The intended impact of the programme was the realisation of rights for all women and girls, improved public health, and poverty reduction. Specifically, the programme was expected to meet the contraceptive needs of over 20 million women per year; to reduce unintended pregnancies and maternal deaths; to improve maternal, newborn and child health; to advance universal access to RH commodities; to increase the likelihood that girls stay in education; to increase household financial resilience; and to increase the fiscal space for public service provision.

The intended outcome of the programme was improved market functioning, increased country capacity and expanded and equitable commodity availability. At the global level, the programme was expected to deliver healthy and responsive markets for RH products including a reduction in market failures, global VfM savings and shortened time to scale for the strong pipeline of new and lesser-used RH technologies. At the country level, it was to strengthen country systems for sustainably and effectively manage RH commodity needs. At the user level, it was to enable access to a range of affordable and quality RH commodities from the public and private sector.

The intended output of the programme was a coordinated RH commodity ecosystem that carries out core functions, meeting demand, ensuring quality and taking products from innovation to scale in a sustainable way:
- efficient and timely procurement and delivery of RH commodities;
- a sustainable and coherent approach to co-financing;
- informed and coordinated global market strategy;
- coordinated execution of market strategy including price negotiations;
- country market stewardship including for public and private sectors;
- government-led, well sequenced product introduction and scale up;
- improved supply chain visibility at the global and country levels.

The programme’s ToC was built on several key assumptions. Most notably, the programme team assumed the provision of up to £600m ODA funding and national economic growth, but neither of these key assumptions held. This was due in large part to the COVID-19 pandemic; and additionally to the 2023 reduction in ODA spending. Additionally, the ToC assumed that the Market Access Initiative would be designed in a way that secured buy-in from the sector and aligned donor funding, which also did not happen (in large part due to reduced funding). In 2022/23, the FCDO decided not to proceed with our planned investment in the partnership Shaping Equitable Market Access (SEMA) for Reproductive Health; due to a combination of a reduction in other donor funding and a lack of alignment in strategic objectives. The intended impact and outcomes of this programme were impacted by these changes.

## C: Detailed Output Assessment

When considering programme performance against targets under each Output, it should be noted that we are reporting on progress made over a five-year period with final results referenced as at December 2024. Some starting targets were qualitative and could not be tracked directly year-on-year. Some were achieved mid-programme and subsequently retired or replaced. Quantitative targets could be better tracked and were often updated or made more ambitious during the programme lifespan, to reflect strong progress before that point.

Output Number 1		UNFPA Supplies Partnership programme transitions smoothly to Phase III and is underpinned by a robust operational and governance model.
Output Score		A
Impact weighting (%)		34%		Impact weighting revised since last AR?		No

Output Indicator	Starting Target		Final Logframe Target		Final Result Achieved
1.1 UNFPA Supplies is underpinned by a robust governance model which drives better performance and provides donors with stronger oversight and assurance.	Phase III governance model is up and running. Constituency-based Steering Committee was operationalised in November 2020 and specialised sub-committees were set up in March 2020. / The Programme Leader and Independent Chair had not been appointed by the 19 November deadline, but both recruitment processes are underway.		Action plan based on the UNFPA accepted recommendations of the review is produced. Agreed key actions to be implemented by the UNFPA Supplies programme by end of Q3 2024.		Met (A): / UNFPA developed an action plan for the implementation of the recommendations of the / programme review, commissioned by the Netherlands and conducted by Hera, an independent consultancy firm. The actions taken to implement the recommendations in each of the three areas are outlined in the narrative section below.
1.2 UNFPA Supplies Partnership programme is managed by a strong, multidisciplinary team at the global, regional and country levels	Organogram for the UNFPA Supplies global team finalised and shared with the Steering Committee following a recommendation by the relevant subcommittee as per the guidelines set out in the new governance model		Sustain HR base for all 54 UNFPA Supplies Partnership country offices. Launch e-learning courses to strengthen capacity in financing for health, expanding contraceptive method mix and choices, knowledge management and advocacy as per recommendations from the capacity building plan.		Met (A): / UNFPA Supplies partnership provided HR support for 54 countries to support a minimum national officer position. 49 countries have hired dedicated staff, whereas five countries relied on consultants to carry out the tasks. / A course on Family Planning, FP101, has been developed and is expected to be rolled out by the end of this year (2025). / The programme developed and launched a course on health financing in coordination with UNFPA’s Asia Pacific Regional Office. With the leadership of UNFPA’s Western and Central Africa Regional Office, the course is being further expanded and refined to meet evolving needs. / An Advocacy and Communications Toolkit for DRM finalised in 2024 will be rolled out in 2025. The toolkit provides clear programmatic guidance to country offices on how to engage in public financing management (PFM) processes and effectively advocate for domestic resources mobilisation applying the SMART approach. It includes a set of PFM tools and guidance documents to assist countries with these efforts.
1.3 UNFPA Supplies Partnership programme has strong controls in place to mitigate risks facing the programme and provide donors with assurance	Programme risk framework finalised and adopted by the Steering Committee.		The milestone in the UNFPA Supplies M&E Results Framework, OP2.2.2 on fraud, is achieved.		Met (A): / A new indicator has been developed and incorporated in the UNFPA Supplies M&E framework. The replacement was to ensure programmatic actions are in line with the current guidance from the UNFPA Office of Audit and Investigation Services (OAIS): A finding can only be referred to as a “known fraud case” when OAIS has conducted an investigation and confirmed a case to be “fraud”.
	Guidelines on Last Mile Assurance adopted by the Steering Committee and included in the Programme Document		32 in-country assessments are completed by the LMA Team in UNFPA Supplies countries (2024 LMA cycle), and all recommendations from the in-country assessments are taken forward in a timely manner.		In 2024, LMA in-country assessment (ICA) team completed on-site visits in 37 countries, 36 of which were UNFPA Supplies Partnership countries.
1.4 Robust results framework and reporting procedures are in place to ensure strong accountability, transparency and assurance over programme performance	Phase III results framework finalised and agreed by the Steering Committee.		75% of milestones within the UNFPA Supplies Partnership M&E Results Framework are achieved.		Exceeded (A+): / 86% (30 out of 35) of the UNFPA Supplies Partnership M&E framework milestones were successfully achieved.
1.5 UNFPA Supplies Partnership programme is underpinned by a robust operating model which delivers stronger VfM and impact and provides donors with greater assurance.	Guidelines on country eligibility, country categorisation and domestic financing adopted by the Steering Committee and included in the Programme Document.		By 15 November 2024, Compact agreements, including mandatory domestic financing contributions for 2024 and a valid Annex A, have been signed in 37 Partnership countries.		Exceeded (A+): / Compact agreements (including mandatory domestic financing contributions) have been signed in all 44 UNFPA Supplies Partnership countries that were expected to do so. / For 2024, 41 out of 42 countries re-signed Annex A commitments.
[note] 10 countries were exempt or not required to sign compact agreements. 6 countries were not required to sign Annex A, while another 6 were exempt.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Over the lifetime of the programme, the UNFPA Supplies Partnership programme has successfully transitioned to Phase III of its model, supported by a resilient operational and governance framework. The programme’s formal mid-term evaluation is currently ongoing, with the final evaluation report expected to be delivered in July 2025. Whilst the report is yet to be finalised at the time of writing, early findings indicate that Phase III of UNFPA Supplies introduced a transformative shift to a partnership model with stronger mutual accountability, a new focus on sustainable financing and improved transparency.

Key achievements:
- Achieved 86% of performance measurement milestones (30 of 35) against a target of 75% in 2024.
- Facilitated multi-year Country Compact negotiations and re-signed Annex A documents in 41 countries in 2024 to increase DRM in 2024.
- Supported 34 of 44 countries to meet their minimum domestic financing obligations in 2023.
- Implemented Strategic Readiness Assessment Tool (SRAT) in 47 countries in 2024 to inform Health Systems Strengthening (HSS) applications, aligning funding with critical needs.
- Reconfigured the Steering Committee to increase participation of programme-implementing countries.
- Conducted in-country assessment visits in 36 countries and provided support to all 54 countries to enhance supply chains and minimise the likelihood of product wastage.

(1.1) Improved governance over the life of the programme has supported more robust decision-making and oversight of implementation. Notably, a number of key improvements were initiated based on findings from an independent programme review, commissioned by the Netherlands and presented at the Steering Committee meeting in London in October 2023. This included increased emphasis on country compacts, refinement of the SRAT and HSS applications, and enhancement of the functionality of core governance model components.

Broader efforts to strengthen and mature the governance and decision-making of the partnership have continued to be a priority in 2024 with clearer materials and a stronger approach to advance consensus-building emerging in early 2025. This was reflected in robust and well-evidenced Steering Committee discussions at the April 2025 meeting in London, Most recently, Steering Committee membership has also been reconfigured in 2024 to promote broader country participation with the addition of two government seats from programme-implementing countries, Chad and Zambia (in addition to the two existing government representatives from Lao PDR and Sierra Leone).

(1.2) UNFPA Supplies staffing has continued to be a key focus area over the course of the programme. The approach to human resource fund-leveraging was revised, adopting an objective, needs-based model for staffing support to UNFPA Country Offices to provide a national officer in each country to support reproductive health commodity management and HSS. In 2024, funds were allocated to support a national officer in each of the 54 countries, with 49 currently utilising this opportunity; while countries with complex supply chain contexts received support for international positions. To enhance staff capacity, a suite of tools was developed including learning and toolkits on health financing, “FP 101”, and Advocacy and Communications for DRM.

Opportunities to strengthen UNFPA Supplies team capacity at global level remain, with additional pressure faced due to the ongoing relocation of the UNFPA Programme Division (including the UNFPA Supplies team) to Nairobi. Risk mitigation planning by UNFPA and improved visibility of the programme organogram over the past year has provided valuable assurance.

(1.3) UNFPA Supplies’ Last Mile Assurance processes have matured significantly over the life of the programme, with routine policies and processes now well-established for monitoring and assurance. Regulatory challenges, in combination with constraints to and inconsistent levels of health system readiness and preparedness, remain barriers to widespread adoption, requiring enhanced advocacy and policy engagement to expedite regulatory approvals and ensure readiness for new product introduction. In 2024, UNFPA supplies conducted in-country assessment (ICA) on-site visits in 36 partnership countries, with findings integrated into countries’ Health Systems Strengthening (HSS) applications to help enhance in-country supply chains and minimise the likelihood of product wastage. In 2024, all 54 UNFPA Partnership countries also received support for the implementation of supply chain strengthening interventions.

Reporting on the specific fraud-related metric for 2024 was not feasible in light of current guidelines from the UNFPA Office of Audit and Investigation Services (OAIS) on the designation of a “known fraud case”. FCDO and UNFPA will jointly agree revised metrics going forward to support future reporting under the next programme.

(1.4) UNFPA Supplies has established a rigorous results framework for Phase III, developed through consultation with staff across all organisational levels (Headquarters, Supply Chain Management Unit, regions, and countries), to support transparency and promote accountability at both global and regional levels. Data for performance monitoring within the UNFPA Supplies Partnership are collected from both primary (directly from country offices, facility and other surveys when available) and secondary sources (FP2030 and other global partner reporting).

The UNFPA Supplies Performance Measurement Framework currently comprises 35 milestones, of which 30 (86%) were fully achieved in 2024. Milestones not achieved – most of these marginally – were on 1) number of users (99.5m vs 100.9m target), 2) modern contraceptive prevalence rate (23.8% vs 24.6% target), 3) demand satisfied (56.4% vs 57.1% target), 4) service delivery point reporting no stockouts (45% vs 58% target) and 5) budget needs met (72.4% of budget mobilised against a target of 94%). Missed targets are largely attributable to factors outside of UNFPA Supplies’ control, with weak health systems and cultural and religious barriers playing a notable role in limiting progress. Supply chain and distribution challenges played a key role in levels of stockouts reported.

(1.5) Significant progress on domestic resource mobilisation efforts over the course of the programme have been achieved with the development and rollout of a comprehensive DRM toolkit, encompassing a suite of incentives including country compacts, match funding and minimum DRM requirements to receive programmatic funding. In 2024, 41 of the 42 countries required to re-sign their minimum co-financing agreements (Compact “Annex A”) did so and 32 countries fulfilled the programme's domestic financing requirements, collectively realising a record $45.1 million of domestic financing for SRH commodities.
[note] Notwithstanding the effectiveness of Compact agreements and Annex A commitments in securing government financial contributions to reproductive health commodity procurement, exceptions were necessitated for countries experiencing specific challenges, including political instability and humanitarian crises. Of the remaining 12 countries, six were granted exemptions due to humanitarian crises, and six were deemed ineligible to receive routine commodities through the programme and thus not required to execute Compacts.

Lessons learned through this output, and recommendations for future programming

Interdependencies at global and country level: progress towards impact indicators depends on multiple factors, from the strength of individual countries’ family planning approaches to levels of donor funding to UNFPA Supplies. While there have been good results across various indicators – particularly on meeting demand and diversifying the contraceptive commodities available – progress in increasing the use of contraceptives (the modern contraceptive prevalence rate, mCPR) and then mitigating the negative impact of stockouts remains inconsistent. Strong collaboration between governments, stakeholders and programme countries to improve service delivery is essential to advance progress, which otherwise cannot be maintained.

Domestic resource mobilisation: significant strides over the life of the programme in advancing domestic resource levels for SRH have demonstrated that mobilising country co-financing for SRH commodities is possible and realistic. Whilst initial domestic funding levels are not sufficient to support immediate transition, progress so far has laid essential groundwork for future pathways out of donor support.

Compact contingency measures: initial data indicates that current compact contingency measures are working effectively to support countries to increase their contributions and finance greater proportions of domestic demand. These should go hand-in-hand with additional advocacy interventions on DRM.

Supply chain challenges: failures and weaknesses in the supply chain pose a consistent risk to the accessibility of RH commodities. Ongoing efforts to address and mitigate these will be essential in the next phase of programming.

Recommendations
Future programming should continue to prioritise domestic resource mobilisation and pivot efforts to the next phase, seeking to develop agreed transition pathways and a vision for long-term sustainability of SRH commodity financing via countries’ domestic health budgets.
Output Number 2	UNFPA Supplies Partnership programme procurement and technical assistance increases the availability of RH commodities in LMICs and represents strong VfM.
Output Score	A+
Impact weighting (%)	34%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
2.1 2020 – 2025: Total Couple Years Protection provided for the year through the procurement of contraceptives and condoms by UNFPA Supplies	40 million	38 million	Exceeded (A+): / 43.2 million
2.2 2021 – 2025: Number of countries where 75% of UNFPA Supplies Partnership programme commodity orders are delivered on time in country	Introduced in 2021 with an initial milestone of 30 countries.	42	Exceeded (A+): / 48
2.3 2021 – 2025: UNFPA Supplies Partnership programme implementing countries implement strategies to strengthen humanitarian preparedness and resilience	Introduced in 2021 with an initial milestone of 20%, following the discontinuation of output indicator 2.5 below.	80%	Met (A): / 81%
Old 2.3 2020 – 2021: 75% of UNFPA Supplies expenditure is dedicated to the procurement and supply of reproductive health commodities	Starting target was 75% in 2020. Once this was achieved, this indicator was discontinued and institutionalised into the programme	N/A – discontinued in 2021	N/A
2.4 2020 – 2025: Number of countries where new and lesser-used RH products are procured for their use in the public sector in line with government introduction plans	2	16	Exceeded (A+): / 34
Old 2.4 2020 – 2021: Average number of days between the time when requisition is budget checked and when the commodities (contraceptives) are handed over to the first carrier (Atlas financial receipt date).	Original target in 2020 was 107 days. The programme achieved 148 days. / This indicator was discontinued in 2021.	N/A – discontinued in 2021	N/A
Old 2.5 2020 – 2021: Percentage of countries in humanitarian and fragile contexts, where implementing partners did not experience stock outs of RH kits during the year	Original target in 2020 was 90 countries. / This was achieved and indicator was wrapped into an overarching humanitarian indicator in 2021 and subsequently discontinued.	N/A – discontinued in 2021	N/A

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Key achievements:
- Consistently exceeded Couple Years Protection (CYPs) targets. Achieved 43.2 million CYPs in 2024 against a target of 38 million.
- The number of countries achieving at least 75% on-time delivery of commodity orders increased from 30 in 2021 to 41 in 2023.
- 81% of countries in humanitarian and fragile contexts integrated preparedness interventions by 2024, up from 26% in 2021.
- Provided technical assistance to countries to introduce new and lesser-used products (including hormonal IUDs (HIUD), tranexamic acid (TXA) injections, heat-stable carbetocin injections (HSC) among others) in 34 countries in 2024, up from 7 in 2020.
- Increased procurement of comprehensive abortion care (CAC) supplies: 13 countries procured the medical abortion (MA) combipack in 2024, up from 9 in 2023. MVA kits were procured by 14 countries, up from 7 in 2023. 28 countries included CAC-related activities in their Health Systems Strengthening (HSS) applications for 2025, up from 8 in 2023.

(2.1) UNFPA Supplies has consistently exceeded its targets on CYPs. In 2024, the contraceptives distributed via the programme yielded a cumulative 43.2 million couple-years of protection CYPs, exceeding the final logframe target of 38 million CYPs. A comprehensive analysis of potential CYPs provided by each contraceptive modality in 2024 is also detailed in Annex C. The cost per CYP in 2024 amounted to $2.68, a marginal decrease from the $2.71 reported in 2023.

(2.2) This indicator on timely delivery of commodities was introduced in 2021 and has consistently performed above target, though practical challenges have persisted. The number of countries where at least 75% of UNFPA Supplies Partnership programme commodity orders were delivered on time in 2021 was 45 countries, surpassing the annual milestone of 30 countries. In 2022, the milestone was established at 33 countries, with 39 countries meeting the criteria. The year 2023 saw 41 countries attain at least 75% on-time delivery of UNFPA Supplies Partnership programme commodity orders, exceeding the milestone of 36 countries. Despite the predominant timely delivery of orders, persistent challenges were observed. These challenges were manufacturer delays stemming from protracted lead times for products with limited availability, in-country security concerns and issues related to warehouse quality assurance.

(2.3) UNFPA Supplies Partnership programme implementing countries have successfully implemented strategies to strengthen humanitarian preparedness and resilience. By the end of the programme, 81% (21/26) of countries in humanitarian and fragile contexts had integrated humanitarian preparedness interventions within their HSS applications. A range of strategies were adopted by countries to develop humanitarian preparedness and resilience actions, including capacity building and reinforcing the provision of Minimum Initial Service Package (MISP) for SRH in crisis situations within the broader context of health response strategies, enhancing community capacity in preparedness and emergency response, strengthening reporting and surveillance capabilities, integrating family planning services in humanitarian and crisis settings, and mainstreaming sexual and reproductive health and rights into national preparedness and response processes and plans for humanitarian responses. Additionally, an increased number of countries prioritised humanitarian interventions via the UNFPA Supplies Partnership, concurrently pursuing alternative funding mechanisms to implement and reinforce humanitarian and preparedness initiatives. This trend underscores the critical importance of diversifying funding streams and cultivating robust partnerships to effectively confront humanitarian challenges and enhance resilience during periods of crisis.

(2.4) UNFPA has worked with other FCDO-funded programmes to provide technical assistance to countries to introduce new and lesser-used products in 34 countries in 2024, up from 7 in 2020. Interventions included guidance on developing and implementing country-specific strategies for advocacy and policy dialogue, addressing regulatory frameworks, capacity building and strengthening supply chain systems. This approach led to the successful introduction of the HIUD, TXA, HSC, Mifepristone and misoprostol (MA combipack), Non-Scalpel Vasectomy Kits + Bilateral Tubal Ligation Kits, MVA kits, and DMPA-SC.

Lessons learned through this output, and recommendations for future programming

Unpredictable funding availability: while the programme successfully met its final targets, unprecedented fluctuations in funding, particularly in 2022, impacted overall CYP delivery, highlighting the vulnerability of achievement to financial disruptions. Ensuring the continuous provision of contraceptive supplies, avoiding over-reliance on politically-vulnerable funding and reducing the risk of stock-outs requires robust financial risk mitigation strategies, with diversified donor engagement and alternative funding mechanisms (e.g. DRM, innovative financing) at their core.

Supporting access to new and lesser used products: the introduction of new and lesser-used reproductive health products has significantly expanded contraceptive choices. Technical assistance and training are crucial to support countries to introduce new products into national supply chains and health services. The timeline for introducing new and lesser-used products into the procurement and implementation stages can also be extensive, often spanning 12 to 18 months – effective implementation is highly contingent upon meticulous strategic planning, coordinated action and sustained engagement with a wide range of stakeholders.

Recommendations
Maximise opportunities in future programming to support consistent and predictable funding to safeguard sustained delivery of commodities and minimise cliff edges in provision of supplies for those who need them most.

Future FCDO programming for SRH commodity access should seek to further collaboration between UNFPA Supplies, CHAI, key partners like the Global Financing Facility for women, children and adolescents (GFF) and wider partners to support effective product introduction and leverage the UNFPA Supplies new and lesser used product fund to maximum impact.

Output Number 3	Coordinated strategies and interventions for RH commodities to support access, affordability, innovation rollout, supply security, country capability and availability through the public sector.
Output Score	A
Impact weighting (%)	22%	Impact weighting revised since last AR?	No

Starting Target	Final Logframe Target	Final Result Achieved
3.1 The hormonal IUD is widely available to women and girls in focus countries and underpinned by a commercially sustainable market. Overall Met (A)
4 countries completed initial meetings with Ministries of Health (MOH) to discuss hormonal IUD (HIUD) introduction 2 countries developed national strategies for product introduction Catalytic Opportunity Fund (COF) designed and linked to HIUD governance structure	8 countries total with annual supply needs quantified and met	Partially met: 7 countries (DRC, Kenya, Nigeria, Malawi, Rwanda, Uganda, Zambia) quantified and met supply needs for hormonal IUD in 2024. 4 additional countries (Cameroon, Eswatini, Senegal and Sierra Leone) are developing costed introduction plans. Sierra Leone placed its first HIUD order in Q1 2025.
	8 countries are progressing or have completed introduction of HIUD	Partially met: 7 countries (DRC, Kenya, Nigeria, Malawi, Rwanda, Uganda, Zambia) are progressing or have completed introduction. 2 countries have made progress in developing their CIPs (Senegal and Sierra Leone) and 2 countries (Cameroon and Eswatini) have begun coordination of introduction activities leveraging COF awards.
	3 countries with HIUD introduction preparation activities underway	Exceeded: 4 countries (Cameroon, Eswatini, Senegal and Sierra Leone) are completing preparation activities with CHAI support.
	75% annual increase in total facilities providing HIUDs across 7 countries	Exceeded: Between Q3 2023 and Q1 2025, the total number of facilities providing HIUDs across actively introducing countries where CHAI is supporting increased by 99% (from 1,206 to 2,403).
	1 country with HIUD integrated into systems and graduated from technical assistance for HIUD introduction	Met: Rwanda has graduated from technical assistance for HIUD introduction.
	Targeted mapping of near-term new market opportunities for HIUD introduction completed through HIUD Access Group	Met: CHAI developed a resource package and led a targeted mapping of near-term market opportunities through the HIUD Access Group. Ten new countries have indicated preparation to introduce the method.
	Continued global level coordination and market monitoring for Hormonal IUD strategy, including facilitating and managing the HIUD Access Group priority agenda, refreshing the global public sector demand forecast, drafting a TMA strategy and engaging regularly with two quality assured suppliers	Met: CHAI facilitated and managed the HIUD Access Group priority agenda and engaged regularly with both quality assured suppliers. CHAI refreshed the global public sector demand forecast and shared outputs with HIUD Access Group (including suppliers) in Q3 2024. CHAI completed an initial HIUD TMA landscaping exercise and presented it at the in-person hormonal IUD meeting in October 2024. In Q1 2025, CHAI facilitated a Market Stewardship Group meeting which was used to discuss and align upon key priorities for 2025, and CHAI also engaged 1:1 several times with the HIUD suppliers (e.g., to provide market visibility and discuss potential impact from the USAID Stop Work Order).
3.2 Quality-assured medical abortion combipack (MA combipack) for safe medical abortion are widely available to women and girls in focus countries and underpinned by a commercially sustainable market. Overall Met (A)
Access group governance structure set up and Catalytic Opportunity Fund adopted as core activity of group to increase access to MA combipacks / 1 country completed initial meetings with MOH to discuss combipack introduction	5 countries with annual MA combipack supply needs quantified and met	Met: 5 countries (Cambodia, DRC, Liberia, Uganda and Zambia) had their quantified supply needs for 2024 met. Rwanda had their needs quantified but only 87% of the orders were met by the available stock and procurements.
	6 countries are progressing or have completed introduction of MA combipack	Exceeded: Rwanda and Zambia have completed introduction of MA combipack and are bolstering provision and uptake. Cambodia, DRC, Ghana, Liberia, and Uganda are progressing with introduction activities.
	Increased country registration of quality-assured (QA) combipack product	Met: As of 2024, LMICs with at least one QA supplier registered increased by 50% from 2021. QA suppliers are also pursuing or planning registrations in a number of LMICs.
	Increased procurement of QA combipack	Met: QA MA combipack procurement grew by 19% from 2022 to 2023 and by a more modest 11% from 2023 to 2024 (note: 2024 figures are estimates pending a full MA dashboard update.)
	Non-QA suppliers supported to make progress against achieving World Health Organisation (WHO) prequalification and/or Stringent Regulatory Authority (SRA) approval and offer QA product at affordable price points; target SRA/WHO PQ regulatory filings by Q1 2025	Not met: Despite support provided, non-QA suppliers did not make anticipated progress toward achieving WHO prequalification and/or SRA approval; however, current QA supplier pricing has come down to affordable targets.
	Global MA community including partners and donors are engaged on key MA priorities including historical MA combipack market shaping work via WHO consultation and finalisation of MA action plan	Partially met: Donors and partners have improved coordination and sharing information through forums including the WHO MA Global Action Plan, RHSC Safe Abortion Supplies group, and WHO’s Preventing Unsafe Abortion group. However, limited progress has been made on a shared strategy.
	Landscape of opportunities to increase near-term demand for QA MA combipacks completed and action mapped out for future interventions for 2025 onwards	Met: CHAI completed a landscaping of near-term demand opportunities in key markets in Q1 2024. In Q2 and Q3 2024, CHAI utilised these landscape findings to inform near-term focus areas/plans in key countries, including activities funded by FCDO.
3.3 Governments build domestic capacity to routinise RH product introduction and lead government-owned introduction processes across a range of RH products, Overall Met (A)
4 countries with MOH champion identified to lead mechanism / 2 countries with country-level kick-off meetings completed, led by MOH and attended by partners and donors to ensure strong coordination and alignment / Initial version of RH product landscape completed to support product introduction decision-making	6 countries with active government-led market stewardship groups	Met: 6 countries have established market stewardship groups (Kenya, Nigeria, Zambia, Malawi, Uganda, and Senegal).
	9 market health assessments conducted by government-led market stewardship groups / Government-led market stewardship groups in 6 countries conduct scoping for potential new products (including 3 new countries)	Partially met: 8 market health assessments were conducted, including seven by state market stewardship groups in Nigeria and one in Zambia. Kenya initiated a national level market stewardship assessment with plans to complete in Q2 2025.
	36 new product introductions underway across 10 countries (includes 25 new introductions and 3 new countries)	Exceeded: 42 product introductions are currently underway across 11 countries (DRC, Ethiopia, Ghana, Kenya, Lesotho, Malawi, Nigeria, Rwanda, Senegal, Uganda, Zambia). An additional 3 introductions can be considered complete (HIUD and MA combipack in Rwanda, and combipack in Zambia).
	The Catalytic Opportunity Fund (COF) catalyses introduction of new products based on government demand, supports government ownership of product introduction plans, and supports coordination and sequencing of product introduction activities.	Met: CHAI approved 143 awards covering HIUD, MA combipack, DMPA-SC, and post-partum haemorrhage (PPH) across 27 countries that align to COF requirements and government priorities, supporting catalytic, high-impact funding for 59 distinct product introductions. 93 final reports, 36 during the final grant year, were completed by COF awardees. These reports demonstrate, and impact analyses affirmed, achievement of critical government priorities and progress to scale-up access to key new and underutilized SRH products.
3.4 2020 - 2025: Best practices and lessons learned are documented and shared to inform future RH product introduction activities. Overall Met (A) / FCDO asked CHAI not to report on this for 2021, 2022 and 2023 Annual Reviews to consolidate reporting. We returned to this indicator after providing an uplift in 2023/4.
Agreement from 4 countries' MOH champions to share product introduction progress, and share lessons learned on best practices with wider RH community	Global access coordination in place for Multiple Micronutrient Suppements (MMS) and wider maternal and newborn health (MNH) commodities, leveraging best practices from HIUD	Met: CHAI supported global partners to take steps towards establishing an effective global coordination structure for MMS introduction, with a positive shift towards country-driven planning reflected in the latest structure. There continues to be an important role for CHAI in ensuring connectivity across the coordination groups, particularly in ensuring that government priorities are reflected in supply planning, which will be critical for a sustainable transition to domestic budget. For MNH, CHAI also supported progress toward establishing the EWENE Commodities group including development of the theory of change for the group and beginning to socialise it and get feedback from members.
	6 international disseminations of best practices through conference participation; 4 international webinars; 1 package of resources developed for sharing with countries; by December 2024 share lessons learned with 10 countries	Exceeded: CHAI completed 16 international disseminations of best practices through conference participation; and 4 international webinars. CHAI facilitated an internal global SRMNH learning summit in Nairobi attended by 10 country teams and numerous global teams, where teams presented and engaged on learnings from the grant.
	FCDO is supported to socialise best practices work within the organisation	Met: CHAI routinely responded to requests from FCDO to socialise best practices work within the organisation.
3.5 2024 – 2025: Improved early detection, management, and treatment of PPH through updated guidelines, strengthened service delivery and reliable access to key commodities. Overall Met (A)
N/A – added in 2024	6 countries have updated their Standard Treatment Guidelines reflecting inclusion of revised clinical care bundle (E-MOTIVE) for early and accurate PPH detection and treatment	Partially met: E-MOTIVE introduction is underway in 8 countries. 4 countries (Ethiopia, Kenya, Nigeria, and Zambia) have updated their Standard Treatment Guidelines (STGs) to include the latest clinical guidelines.
	6 countries incorporate drapes and tranexamic acid (TXA) into forecasting and quantification for maternal health supplies	Exceeded: All 10 countries have integrated TXA into their quantification processes (Ethiopia, Ghana, Kenya, Lesotho, Malawi, Nigeria, Rwanda, Senegal, Uganda, and Zambia. / Additionally, 7 countries – Ethiopia, Kenya, Malawi, Nigeria, Rwanda, Senegal, and Uganda – have included drapes in their quantification process. / Two other countries – Lesotho and Zambia – are currently working towards including drapes in their F&Q.
	6 countries have initiated introduction of calibrated drapes for early PPH detection.	Exceeded: 10 countries – Ethiopia, Ghana, Kenya, Lesotho, Malawi, Nigeria, Uganda, Senegal, Rwanda, and Zambia – have initiated introduction of calibrated drapes for early PPH detection.
	UNFPA and CHAI have developed collaborative approach to strengthening access to quality maternal health products	Met: CHAI supported UNFPA to convene and host the first meeting of the Every Woman Every Newborn MNH Products Working Group. CHAI and UNFPA finalised an MOU that was signed in Q2. CHAI supported UNFPA with assessing the impact of the compact requirements, contingency measures, and Match Fund approach on domestic resource mobilisation efforts. CHAI also facilitated initial discussions between UNFPA and GFF in Nigeria, Uganda, Mozambique, & Madagascar as the two institutions begin to develop a roadmap for further collaboration.
3.6 2024 – 2025: Enhanced care for small and sick newborns through the integration of caffeine citrate provision. Overall Exceeded (A+)
N/A – added in 2024	6 countries have updated their Essential Medicines Lists to incorporate caffeine citrate	Exceeded: Essential Medicines Lists have been updated in 6 countries (Lesotho, Malawi, Senegal, Uganda, Zambia, and Nigeria [6 states]). Ghana is in the process of updating its EML. In Ethiopia, the 20mg/mL formulation is on the EML, but the 10 mg/mL is not yet added. Ghana is seeking to update the EML in 2025 following finalisation of STGs. Kenya and Rwanda added caffeine citrate to their EMLs prior to the grant.
	7 countries have initiated the introduction of caffeine citrate through forecasting and/or guidelines updates	Exceeded: 8 countries (Ethiopia, Ghana, Kenya, Lesotho, Nigeria, Rwanda, Uganda and Zambia) have initiated introduction through forecasting and/or guidelines update.
	3 countries have included caffeine citrate in their newborn training package and are rolling out to strengthen quality of care	Exceeded: 7 countries (Ethiopia, Ghana, Kenya, Nigeria, Rwanda, Uganda, and Zambia) have included caffeine citrate in their newborn training package and are rolling out.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

A recent external evaluation has concluded that CHAI’s Best Practices Grant has made significant strides in expanding availability of key reproductive health commodities and strengthening health systems. The interventions were found to be effective due to strong alignment with national policies, phased and targeted roll-out strategies, and robust technical support from CHAI. Global stakeholders interviewed for the external evaluation confirmed that the Best Practices Grant has been successful in generating investments, building the market, and crowding the donor funding around the same strategy.
[note] Hera, Evaluation of CHAI Best Practices Grant p.8
[note] CHAI evaluation p. 7

Key achievements:
- Significantly improved access to hormonal IUDs (HIUD); achieving 40-80%+ price reductions, facilitating inclusion in UNFPA and USAID procurement catalogues and supporting introduction in 7 countries equating to 1.7 million CYPs.
- Through the Catalytic Opportunity Fund (COF) funded 41 grants across 13 countries implemented by 13 partners to increase access to medical abortion (MA) combipacks for safe abortion, including through country rollout of products, expansion of comprehensive abortion care (CAC) services and training for midwives. Global combipack procurement increased 52% (2020–2023).
- Strengthened health systems with the establishment of market stewardship groups in 6 countries and supported an additional 5 governments with product introduction, to support 40+ introductions and enable faster, more cost-effective rollouts (e.g., Kenya’s government-led HIUD rollout reached 32% of facilities in 2 months whereas it took 48 months for partners to reach 20% of facilities with DMPA-SC).
- Expanded focus to include maternal and newborn health, supporting introduction of PPH commodities in 10 countries and training more than 2,800 healthcare workers.
- Scaled access to caffeine citrate for management of apnoea of prematurity (AOP) in newborns, achieving a 71% price reduction and supporting procurement in 6 countries.

(3.1) & (3.2) CHAI has provided leadership of targeted access initiatives for priority products including HIUD and MA combipacks. Despite being originally developed for resource-limited settings, for many years hormonal IUD uptake grew very fast in high-income markets while remaining very limited in LMICs. This was in spite of pilot studies showing high continuation (81-95%) and satisfaction rates (80-98%), indicating strong potential user demand.

In late 2019, supported by the Best Practices Grant (BPG) and FCDO leadership, CHAI convened partners into the HIUD Access Group to develop a market access strategy and market shaping approach to expand HIUD access in LMICs. The three-pillar strategy was designed to build the supply and demand sides of the market together:

1. Improved affordability, negotiating reduced prices for Bayer’s Mirena and further enhancing access pricing for Medicines360’s Avibela, making hormonal IUDs more cost-competitive with other LARCs.
2. Competitive marketplace, ensuring multiple quality-assured suppliers to safeguard supply security and price sustainability.
3. Phased country introduction, supported by CHAI in BPG and other committed countries, to build provider capacity and availability focused on public sector channels

The clear commitment to support the demand-side of the market by global donors and procurers, underpinned by market forecasts, enabled CHAI in partnership with the Access Group to:

- Negotiate a very significantly reduced price for Mirena for use in LMIC public sector settings and secure a more affordable access price from Medicines360; achieving a 40-80%+ price reduction across the two
- Facilitate the inclusion of hormonal IUDs on UNFPA and USAID’s global procurement catalogues, and secure commodity funding through the UNFPA Supplies New and Lesser-Used Commodity Fund
- Support grants for hormonal IUD introduction in 14 countries through the Catalytic Opportunities Fund (COF)
- Support 7 countries to introduce and procure more than 400,000 units since 2021, with uptake of 363,000 to date representing 1.7m CYP. In Rwanda, this growth has been complemented by an increase in uptake of copper IUDs.
  [note] DRC, Malawi, Uganda, Cameroon, Eswatini, Senegal and Sierra Leone

A comprehensive approach to strengthen access to quality assured affordable MA combipacks has also been delivered. CHAI’s efforts, with support from other donors, to commercialise products at a lower price point have resulted in a fall of 33-53% for quality-assured combipacks, reaching the target price point, although delays caused by COVID-19 has meant no additional quality assured products have entered the market. Global MA combipack procurement for public and social marketing sectors increased 52% between 2020 and 2023. CHAI also worked to increase access to CAC in 7 countries (DRC, Ghana, Lesotho, Rwanda, Uganda and Zambia), through a variety of mechanisms including training of midwives and other healthcare providers, combipack procurement and rollout, supply chain integration, advocacy efforts including civil society and social engagement, and development of legislation. For these countries, there has been an estimated increase of 99% in the number of facilities providing HIUD in Q1 2025 compared to Q3 2023, and an estimated increase of 103% in total quarterly HIUD insertions in Q1 2025 compared to Q3 2023. In Uganda, combipacks were procured for the first time for provision through the public sector and in Rwanda the percentage of eligible facilities providing combipacks rose from 71% in 2022 to 98% in 2023. CHAI also progressed HIUD introduction preparations in Senegal, Sierra Leone, Eswatini, and Cameroon, e.g., by supporting initial planning discussions with governments/partners and supporting initial quantification discussions. The World Health Organisation (WHO), supported by CHAI, have convened partners on MA combipacks, developing a global action plan, but a coordinated global strategy for expanding access has not yet been developed.

(3.3) CHAI has further supported health system strengthening in six countries (Kenya, Malawi, Nigeria, Uganda, Senegal, Zambia) by establishing government-led reproductive health market stewardship groups to make product adoption decisions, coordinate new product introductions, and identify and solve market challenges for existing reproductive health products. The external evaluation deep dives in Rwanda, Kenya and Zambia recognised the success of these mechanisms in providing a structured, systematic and sustainable approach to integrating new and lesser used products. In Kenya, several other MoH departments (including oncology and non-communicable diseases) are keen to adopt the model based on the success with SRH. These groups have since expanded their remit to include maternal and newborn health. In an additional five countries (DRC, Rwanda, Ghana, Lesotho, Ethiopia), CHAI supported governments to lead introduction of new products without formalising new structures or mechanisms. In total, 42 product introductions across 11 countries have been supported through the project.
[note] BPG evaluation Kenya Deep Dive p.24

The Catalytic Opportunity Fund’s innovative global financing mechanism was also found to have played a significant role in improving the effectiveness and efficiency of product introductions and scale-up in the recent external evaluation. Over the course of the programme the COF committed $19m to provide rapid, flexible grants to partners to implement activities that will catalyse greater access to RH commodities, and has expanded to support introduction of H-IUD, MA combipack and PPH medicines. The evaluation concluded that COF's requirement for projects to align with national plans and ensure government buy-in has also enhanced the effectiveness of product introductions, strengthened integration with broader health systems and thereby provide a higher chance of sustained impact. The evaluation also found that the COF’s flexible and nimble approach has allowed for efficient use of resources and this agility has been particularly valuable in the face of challenges, such as the COVID-19 pandemic.
[note] BPG evaluation p.28
[note] BPG evaluation p.7

(3.4) CHAI has also worked to strengthen the wider commodity ecosystem by sharing best practices and lessons learned on market shaping. This has focused on sharing lessons learned between governments who were establishing product introduction mechanisms and lessons emerging from COF grants with the wider community. In the initial years of the programme CHAI was also using learning to support the design of SEMA initially but after SEMA failed, CHAI shifted to influencing wider stakeholders. Best practices and lessons learned have been shared through webinars, journal publications, learning exchange visits, workshops, knowledge products and tools, including market shaping resources and market analysis. Global stakeholders interviewed for the external evaluation confirmed that CHAI’s work on global market assessments and sharing these was a “major contribution” to the sector – highlighting the H-IUD and MA commodities groups in particular.
[note] BPG evaluation p.28

(3.5) Best Practices has made impressive progress on expanding its focus to include maternal and newborn health (MNH) products since late 2023 following a funding uplift, including progress across ten countries in supporting PPH commodity access – initiating introduction of calibrated drapes and tranexamic acid (TXA). CHAI supported countries to update treatment guidelines and implement the clinical care bundle E-MOTIVE for early and accurate PPH detection and treatment; and provided training to thousands of healthcare workers across Ethiopia, Kenya, Malawi, Nigeria, Rwanda, Senegal, Uganda, and Zambia. These interventions have had a real and immediate impact, with the Kenyan county of Homa Bay reporting a 39% reduction in maternal mortality following the introduction of CHAI-supported weekly meetings on maternal and perinatal death surveillance and response. CHAI has also supported the introduction and rollout of MMS in several countries, drawing on lessons from the HIUD access group to shape discussions on market management, to ensure a coordinated and country-driven introduction process with a coherent rollout strategy. Global partners have taken steps towards establishing an effective coordination structure, including the development of an MMS supply dashboard housed at UNICEF and alignment of partners around country-driven product introduction plans.

(3.6). CHAI began working with governments to scale access to caffeine citrate for management of apnoea of prematurity (AOP) in newborns; supporting a 71% price reduction for caffeine citrate through supplier engagement and increased visibility into market potential, and influencing and supporting WHO to launch an Expression of Interest for product evaluation, which can reduce regulatory requirements across countries and attract new donor funding. At the country level, CHAI supported initial procurement of caffeine citrate in six countries (Kenya, Ghana, Uganda, Zambia, Rwanda, and Nigeria) alongside health system strengthening to ensure quality rollout of caffeine citrate in newborn care services in these countries alongside Ethiopia and Senegal. The external evaluation reflects the success of this work to prime national health systems and support governments to take over, including in Kenya where, after an initial catalytic procurement of 20,000 ampoules of caffeine citrate (with 10,000 matched by the manufacturer Etypharm) MoH has now taken over and is currently tendering for the procurement of 37,500 ampoules.
[note] Kenya deep dive p.22

Lessons learned through this output, and recommendations for future programming

Health systems strengthening for SRH commodities: the Best Practices Grant scaled up over the life of the programme from initially an incubator/proof-of-concept vehicle that would then transition activities across to SEMA, to a respected centre of expertise building government-led systems and processes to introduce new products and shape reproductive health markets to deliver greater efficiency and impact. The external evaluation has confirmed that the programme delivered results in a cost-effective and timely manner, leveraging existing systems, donors and partnerships to maximise impact while reducing duplication and fragmentation of efforts.

Government ownership and DRM: the external evaluation recognises that the focus on government ownership and strong alignment with national systems has been critical to the programme’s success. It recognises challenges remain and will likely intensify with wider ODA cuts – CHOICES will need to build on progress to date including ramping up efforts on DRM.

Equity: there is scope to build on country programming targeting underserved groups (e.g. training healthcare providers in sign language in Uganda and a mobile application aiming to increase awareness of medical abortion and family planning services amongst youth in DRC) to mainstream and track equity.

Demand generation: the external evaluation recognised progress made on generating demand alongside challenges with using short term COF funding to deliver complex and long term behaviour change. Within the sector funding for demand side activities for safe abortion remains particularly limited and fragmented.

Opposition to SRHR and stigma: The external evaluation recognised that navigating political barriers and stigma amongst healthcare workers and users has been a challenge, particularly for MA combipacks. As we expect to see intensified efforts to rollback SRHR at country level it is important to join up FCDO’s wider work on rollback and supplies to mitigate these risks.

Recommendations
Build upon success of Best Practices to develop an approach that is systems-oriented – delivering critical cross-cutting market functions that build a durable ecosystem. At the heart of this approach should be the building of national capacity to establish and systematise product introduction processes and market access activities.

Include an explicit focus on how to strengthen equity and inclusion; mainstreaming equity in market interventions and access strategies within countries; and reflecting equity considerations in product choice. Programme evaluation should include tracking on reach to users, particularly those in underserved groups.

Deepen and create more formal mechanisms for collaboration between CHAI and UNFPA to maximise synergies between the programmes – including a programme level steering board.

Output Number 4	Reproductive Health Supplies Coalition (RHSC) activities help to strengthen supply chain performance, data visibility and collaboration within the RH commodity ecosystem.
Output Score	A
Impact weighting (%)	10%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
4.1 2021 – 2025 RHSC is well governed, is fit for its purpose, and develops a clear strategy to support a healthier RH supplies ecosystem	1 sub-agreement in place to drive public-sector advocacy initiatives in 2 to 3 countries	Strategy refresh is finalised and endorsed by the Executive Committee (EC) by March 2024 and recommendations implemented shortly after.	Exceeded (A+): / An extensive Strategy redesign process was completed in March 2024, and RHSC Strategy 25/35 was endorsed by the EC in September and launched in November 2024.
	1 RHSC initiative underway to document efforts to grow private sector financing for commodity procurement	Executive Committee Chair appointed by March 2024 in a robust process with implementation of the Diversity, Equity and Inclusion paper at its core	RHSC’s Chair, Beth Fredrick, began her term on April 24, 2024.
		New RHSC core funding secured from existing and new donors in support of the next core workplan, by March 2025.	$15.5 million secured from 6 donors, including the Gates Foundation, the David and Lucile Packard Foundation, CIFF (ex-Amref/SEMA funds), UNFPA, UNOPS-SHF, and a Washington, DC-based philanthropic donor. Funds initially committed by the USAID Office of Population and Reproductive Health for FY2025, were cancelled in 2025, due to USG policy shifts.
		5 instances of demonstrable initiatives on market management are achieved in collaboration with FCDO programme partners	11 instances of demonstrable initiatives on market management (summarised in narrative below).
Old 4.1 2020 – 2021: RHSC expands the resource base for RH supplies	1 RHSC initiative to mobilise support for private sector engagement in RH supplies procurement and management	N/A (discontinued in 2021)	N/A
4.2 2021 – 2025: RHSC develops diagnostics or landscaping analyses with partners on RH market dynamics to support global - and country level actors to make procurement and supply chain decisions	2 diagnostic or landscaping exercise elucidates RH market dynamics / 10 applications of tools are applied to estimate demand, improve forecasting, and/or coordinate procurement / 2 RHSC-convened meetings successfully address market challenges	8 diagnostics/ landscaping analyses are produced: / - 2 x CHAI/ RHSC Family Planning Market Reports / - 2024 Landscape and Projection of RH Supply Needs / - 2 x Global Family Planning Visibility and Analytics Network (VAN) Consensus Planning Group country funding gap analysis / - Cross-product forecast developed with SEMA and CHAI, using jointly developed forecast methodology / -2 further analyses are conducted in response to needs in the RH supplies community	Met (A): / 8 diagnostics/ landscaping analyses produced: / 2x CHAI/RHSC Family Planning Market Reports (Dec 2023; Nov 2024). / USP/RHSC Manufacturing Landscape for Maternal Health Supplies in Sub-Saharan Africa. (Mar 2024) / 2024 LEAP Report. (May 2024) / 2023 Contraceptive Social Marketing Statistics Report. (Jun 2024) / VAN Procurement Funding Gap Analysis (August 2024) / Analysis, Exploring the Potential for Joint Supply Planning in West Africa (May 2024) / Landscape Review, Volatility, Resilience, and Transformation in the Reproductive Health Supplies Ecosystem (Dec 2024)
Old 4.2 2020 – 2021: RHSC supports healthier markets for RH supplies	2 diagnostic or landscaping exercise elucidates RH market dynamics / 10 applications of tools are applied to estimate demand, improve forecasting, and/or coordinate procurement	N/A (discontinued in 2021)	N/A
4.3 2021 – 2025: RHSC coordinates and facilitates global and RH thematic meetings to address market and product challenges	2 additional countries submit country supply plan data to the VAN / 2 new members sign the VAN ToU	RHSC jointly with SEMA launch a Market Committee meeting by Autumn 2024, developing and distributing a consensus statement on longer term market solutions.	In early 2024 SEMA closed after two years in operation. [See below section on FCDO funding to SEMA].
		Implementing Mechanisms (IMs) advance high priority RH Supplies issues in 6 areas	Met (A): RHSC IMs advance high priority RH Supplies issues in 6 areas: / Menstrual Health Supplies (MnHS) Workstream heightened visibility of menstrual health supply access and market development in conversations throughout the World Economic Forum (Jan 2024) / MnHS Workstream, the Sanitation and Hygiene Fund and International Trade Center called on the World Customs Organisation (WCO) to split the harmonised system (HS) codes for menstrual health and contraceptive products / Maternal Health Supplies (MHS) Caucus’s small grant mechanism to support rapid scale up of Heat Stable Carbetocin Injection (HSC) and tranexamic acid (TXA), supported 10 NGOs in 6 African countries to integrate national HSC and TXA in pre-service education and in-service provider trainings, broadening access for women including refugee populations accessing services in the public and the faith-based sectors. / Advocacy and Accountability Working Group (A&AWG) and MHS Caucus co-implementing advocacy activities around the World Health Organisation (WHO) Post-Partum Haemorrhage (PPH) Roadmap. / Market Development Approaches Working Group (MDAWG) and New and Underused Reproductive Health Technologies (NURHT) Caucus learning series on BPs in support of market-based approaches for equitable access to menstrual health supplies. / Systems Strengthening Working Group (SSWG), A&AWG, and ForoLAC’s Climate Change group survey on priorities for advancing action within the intersection of climate and RH supplies.
Old 4.3 2020 – 2021: RHSC increases visibility and control of RH supply chains	2 additional countries submit country supply plan data to the VAN / 2 new members sign the VAN ToU	N/A (discontinued in 2021)	N/A
4.4 2023 – 2025: RHSC increases visibility and control of RH supply chains through the Global Family Planning Visibility and Analytics Network (VAN)	4 new members sign the VAN Terms of Use	6 new members sign the VAN Terms of Use	Exceeded (A+): / 19 new members signed the VAN Terms of Use.
	18% of the VAN costs are covered by membership subscription revenue	20% of the VAN costs are covered by membership subscription revenue	30% of the VAN cost are covered by membership subscription revenue.
	New Demand Planning Module leads to at least one product-specific forecast	New Demand Planning Module leads to at least two product-specific forecasts	8 product-specific forecasts were developed: / Levoplant for Shanghai Dahua (3); Sayana Press for Pfizer (3); and MPA-IM for Pfizer (2).
	VAN platform used by an average of 110 unique users every month to track shipments and orders and make supply chain decisions	VAN platform used by an average of 140 unique users every month to track shipments and orders and make supply chain decisions	VAN platform used by an average of 137 unique users every month to track shipments and orders and make supply chain decisions.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Key achievements:
- Published the RHSC Strategy for 2025-35.
- Expanded the use and impact of the Global Family Planning Visibility and Analytics Network (VAN), tracking over 13,000 shipments of family planning products across 154 countries.
- Through the Global Family Planning Visibility and Analytics Network (VAN) Procurement Funding Gap Analysis identified a $157 million funding gap for family planning products for 2024-25, allowing UNFPA to mobilise $25.3 million targeted at urgent gaps.

(4.1) RHSC worked with its Executive Committee and partners to develop a new strategy for 2025-35 and raised $15.5m in core funding to deliver their workplan (although US government funding since cancelled in light of policy shifts). RHSC has continued to deliver market management activities in close collaboration with UNFPA Supplies and CHAI to strengthen coherence across the programme. Key examples include RHSC coordination on hormonal IUD and DMPA-SC, bringing together CHAI, UNFPA and manufacturers to ensure better forecasting and supply planning of these commodities. RHSC is supporting UNFPA Supplies work on domestic resource mobilisation at the country level in Benin, Uganda, and Congo-Brazzaville by strengthening local advocacy capacity. RHSC and UNFPA also partnered on the SEPREMI initiative – the first virtual price tracking platform for SRH specific to Latin America – to help 14 Latin American governments to maximise resources for RH security and raise awareness about UNFPA’s third party procurement mechanism. RHSC and CHAI are working together to accelerate the scale-up of Heat Stable Carbetocin Injection (HSC) and tranexamic acid (TXA) in national markets in 6 African countries. RHSC are also hosting the MA combipack Catalytic Opportunity Fund on behalf of CHAI to support scale-up of access to MA commodities.

(4.2) RHSC has worked with partners to undertake several diagnostic reports and landscape analyses to help strengthen procurement and supply chain decisions at the global and country level. Key examples include the annual FP Market Report in collaboration with CHAI covering 80+ LMICs and work to assess the current state and opportunities to expand quality-assured regional manufacturing of maternal health (MH) supplies in sub-Saharan Africa. RHSC’s LEAP 2024 analysis estimated the future use and cost of RH supply needs to 2035 and filled an important gap on private sector spending for RH supplies. This analysis is even more important at a time when insufficient financing, natural and human-induced disasters and political unrest will put increasing pressure on weak and under-resourced health systems.

(4.3) RHSC plays an important coordination role to address market and product challenges by facilitating global and thematic meetings through its caucuses and working groups. Key successes include RHSC’s collaboration with IPPF to update the Medical Abortion Commodities Database with country level data on the availability of varied brands of abortion pills. RHSC has also heightened the visibility of menstrual health supplies on the global stage through participation at the World Economic Forum in Davos. RHSC is also increasing access to new and lesser-used medicines for postpartum haemorrhage (NLUM-PPH) in 6 countries through the MHS Caucus supported small grants mechanism.

(4.4) Over the life of the programme, RHSC has expanded the use and impact of the VAN to ensure more efficient allocation of supplies. More than 140 member organisations now rely on the VAN to track in real time over 13,000 shipments of 87 Family Planning products across 154 countries. Additionally, VAN Consensus Planning Group members used VAN data to analyse the procurement funding gap for family planning products, identifying a $157 million funding gap in 2024. This enabled UNFPA to mobilise/allocate more than $25.3m to urgent gaps. Overall, an estimated 9m CYPs have been provided and 2.5m pregnancies averted as a result of this analysis. UNFPA Supplies leadership is represented on the VAN Steering Committee to support join up.

Lessons learned through this output, and recommendations for future programming

Funding predictability and diversification: donor government budget cuts (particularly FCDO and USAID) highlighted that global financing flows for RH supplies security are precarious and that alternative strategies to ensure the resource base for RH supplies are of huge importance. Specifically for RHSC, a diversified revenue stream has helped mitigate the risk of losing any single source of money and enable RHSC the flexibility to respond to issues such as funding cuts and policy shifts as these arise, continuing to deliver on its workplan while addressing members’ shifting needs. In recent months, the unpredictable funding landscape motivated RHSC to invest in business development. RHSC’s new fundraising strategy offers a starting point for identifying additional funding prospects.

RHSC membership: The dramatic shifts in the RH supplies financing landscape have highlighted the specific position that RHSC occupies, as a neutral convener and data steward. RHSC demonstrated its ability to quickly pull together the main data players and begin to answer larger questions being asked, for example creating a forum for discussion by partners on how to respond to budget cuts and supply funding gaps, and opening up the discussion to new partners such as the Global Financing Facility (GFF).

FCDO engagement: as the RH Supplies programme has evolved and grown, FCDO’s comparative leadership in the SRHR sector has emerged as firmly based in market shaping and sustainable SRH commodity availability. In parallel, RHSC’s strategy development process has demonstrated the organisation’s clear strengths in driving convening, advocacy and transparency across the SRH commodity sector. A review of FCDO’s role and engagement in as part of the development of the next programme identified value in taking a more streamlined approach to investments that strategically leverages FCDO leadership and expertise.

Recommendations
It will be critical moving forward to approach RH supplies financing within the broader context of global health priorities, to build towards a new, more sustainable and more resilient financing architecture in the long-term. This represents a step change from the current approach to RH supplies financing within the SRH commodities partner landscape.

Future programming will streamline FCDO SRH commodity investments into two streams: UNFPA Supplies and a bilateral CHOICES Accelerator delivered by CHAI. Opportunities to continue engagement and possible partnership with RHSC should be considered as part of the CHOICES Accelerator approach, where this may be relevant to support market shaping and sustainability activities.

Planned Programme Investment in SEMA

In 2022-23, the FCDO Deputy Director for the Human Development Department agreed with the programme team’s recommendation that the FCDO should not proceed with our planned investment in the partnership Shaping Equitable Market Access (SEMA) for Reproductive Health.

Launched in 2021, SEMA was a new organisation designed as a new market access partnership with the aim of strengthening commodity markets for reproductive health. Following the significant budget cuts made to the RH Supplies programme in 2020 and 2021, the UK’s planned contribution to SEMA was put on hold in order to maintain the delivery of existing programme components. In 2022 RHSC signed a partnership agreement with AMREF as host of SEMA, that laid the foundation for proactive collaboration and alignment between SEMA and RHSC on RH market issues. SEMA became a member of the RHSC and, in March 2023, a paying network player of the Global Family Planning Visibility and Analytics Network (VAN), making it possible for SEMA to contribute to the VAN’s Steering Committee.

While the FCDO’s funding for reproductive health improved in 2022 and 2023, reduced funding from other donors to SEMA, and then a lack of alignment in strategic objectives, meant that a UK investment was deemed to be outside of risk appetite. To ensure programme outcomes were not compromised, budget was reallocated to the CHAI Best Practices grant – a highly successful programme component that was able to advance some of the market shaping activities initially envisaged under SEMA. Meanwhile RHSC worked across FCDO partners including SEMA to wind down activities responsibly, streamline, and clarify forecasting datasets and methodologies (including defining the data sharing and analysis value proposition for social marketing organisations).

D: Value for Money

VfM performance compared to the original VfM proposition in the business case

This programme represented high VfM. By pooling donor funding, aggregating demand and purchasing health commodities globally through mechanisms such as UNFPA Supplies, we were able to capture economies of scale, create attractive markets for manufacturers, secure affordable prices, and dramatically increase commodity availability, choice and quality in LMICs.

Economy	UNFPA Supplies has maintained prices that are comparable or better than other large procurers such as USAID or MSF. / In 2024, UNFPA initiated a tender for male and female condoms – new negotiated prices are more competitive than those previously held by USAID. / CHAI helped to realise cost savings throughout product introduction process by reducing input costs for training and rollout, by reducing wastage of resources through improved sequencing of product introduction activities and by supporting commodity price reductions. / In Kenya, CHAI supported the government-led rollout out hormonal IUD (HIUD) to 32% of facilities in 2 months, compared with 48 months to train 20% of targeted facilities under an earlier partner-driven roll out of DMPA-SC. As the government chose to combine trainings for both products into one shorter training it also represented a $278 saving per health worker trained. / CHAI realised a 40-80%+ price reduction for two quality-assured (QA) HIUDs, a 70% price reduction for caffeine citrate, and a 33% discount on calibrated trays for pilot introductions.
Efficiency	UNFPA demonstrates continued progress in shortening lead times for reproductive health commodities, facilitating the prompt delivery of products and accurate quantities to approximately 80% of Partnership countries. / CHAI: / The recent Best Practices evaluation concluded that coordination mechanisms and cost-effective training approaches contributed to efficient use of resources. / It also found the Catalytic Opportunity Fund (COF) has played a significant role in improving the effectiveness and efficiency of product introductions and scale-up by targeting FCDO funding towards the most critical introduction activities, in line with national priorities and scale-up plans – avoiding duplication and fragmentation of efforts.
Effective / ness	UNFPA Supplies leverages its extensive country presence and global procurement capabilities to enhance the availability of reproductive health commodities. / In 2024, the programme delivered over 43.2 million CYPs. In 2024 the average cost per CYP fell to US$ 2.68 in 2024 from US$ 2.71 in 2023. / Strong progress made on expanding access to high-quality, affordable new and lesser-used products. The HIUD, tranexamic acid (TXA) and Heat Stable Carbetocin Injection (HSC) have been added to the UNFPA product catalogue and are being made available to countries through the public sector. / CHAI: / Leveraging global groups to actively monitor supply and demand for new and lesser-used RH products helps to mitigate global supply shortages and ensure product availability. / Strengthening health systems and ensuring that government is in the lead of new product introduction improves the timeliness and cost-effectiveness of commodity delivery, amplifying this impact through overall increase in access. / Sustainability: the evaluation concluded that the net benefits are likely to continue, particularly where there has been strong integration into government systems and capacity building. / RHSC: Data platforms such as SEPREMI and the Global Family Planning Visibility and Analytics Network (VAN) are being used by governments to support the prioritisation of RH supplies, improve the timeliness of commodity delivery by enhancing coordination among supply chain actors at the country level and helped partners ensure shipments reach their destinations.
Equity	UNFPA Supplies: / In 2024, almost 72% of the programme’s countries experienced a humanitarian crisis such as a conflict, natural disaster or public health emergency. / The programme continues to play a crucial role in delivering emergency RH kits – providing women and girls with life-saving supplies at the onset of a humanitarian crisis. / CHAI: / Country activities supporting equity include training healthcare providers in sign language in Uganda and ongoing development of a mobile application to increase awareness of medical abortion and family planning services amongst youth in DRC.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

FCDO developed and maintained a comprehensive risk matrix and register on AMP throughout the programme lifespan. This included both risks related to programme partners, and risks specific to FCDO delivery. The programme team reviewed the risk with each partner at quarterly programme meetings and reviewed the aggregate risk quarterly. UNFPA Supplies, CHAI and RHSC also provided comprehensive assessments of potential risk, with UNFPA developing a risk matrix aligned to the FCDO model which was shared regularly with the Finance and Risk Committee. RHSC maintained quarterly risk registers for the Global Family Planning Visibility and Analytics Network (VAN) and for its programme activities, shared quarterly with FCDO.

Over the life of the programme, external factors presented varying and substantial risks to delivery; many of which will continue to present a risk to the future programme CHOICES. The Covid-19 pandemic had both an immediate impact on programme delivery, causing manufacturing and distribution challenges or bottlenecks, and in the longer-term demonstrated how vulnerable supply chains are to external pressures (political, economic/trade or health-related). The vulnerability of programme activities (particularly for CHAI) to inflation, donor financing, consumer demand, and other manufacturing-related issues also presented a risk to delivery.

Financial/fiduciary risk was closely monitored throughout the programme. The UNFPA Supplies Partnership faces substantial fiduciary risk and maintains a low tolerance for such risk. Operational complexities in various countries constitute a considerable risk factor, potentially exacerbating fiduciary risks by hindering efficient resource monitoring and oversight; as well as certain instances of fraud and/or corruption. To address these vulnerabilities, UNFPA employs financial policies encompassing inventory control procedures designed to mitigate fraudulent activities: routine in-country inventory evaluations, spot audits and last-mile assurance protocols.

CHAI also had strong protocols in place to mitigate fiduciary risk, with any suspected, detected or reported cases of fraud, corruption or conflict of interest reviewed. For all concerns of wrongdoing, including fraud, CHAI staff and the public have multiple mechanisms available to report concerns. Further, CHAI finance staff are responsible for upholding financial controls, including active engagement in oversight for payment processing. The global Accounting Department also comprises a check on ensuring the responsible use of CHAI funds and resources, conducting sample validation on a regular basis. Internal Audit regularly reviews teams’ finances, testing for financial irregularities including misallocation and the possible diversion of donor funding.

Finally, RHSC was subject to PATH’s rigorous financial management and accounting processes and related systems of internal control. In addition, PATH has a detailed policy in place for reporting fraud, bribery and corruption communicated to downstream partners through funding agreements, with contract conditions setting out clear obligations. Funding partners are informed as soon as RHSC/PATH become aware of any potential incidence of fraud.

The programme operated within a challenging operational landscape impacting programme execution. In 2024, a significant majority, 75% (40 of 54), of UNFPA Supplies Partnership countries, encountered considerable external risks (including corruption, limited governmental commitment, and complex operational environments). Despite these barriers, mitigation strategies, such as intensified spot checks and audits, capacity building for warehouse personnel through the Health System Strengthening fund, and the development of preparedness plans, are employed. To enhance domestic resource mobilisation and ensure sustainable commodity financing within participating countries, the UNFPA Supplies Partnership employs the Compact and Match Fund models. These programmatic approaches serve as supplementary measures to mitigate operational risks, particularly in bolstering national systems for resource mobilisation and encouraging governmental procurement of Reproductive Health Commodities (RHCs) through domestic funds. Risks associated with the relocation of personnel from New York to Nairobi were addressed through the formulation of a comprehensive relocation strategy, designed to guarantee business continuity and minimise disruption to programme operations.

For CHAI, operational risks included the lack of sufficient funding for product introduction plans which could lead to delays in introduction in hormonal IUD and/or medical abortion introductions. Again, a lack of sufficient funding particularly from country donors for new products risked delays in the approval of Catalytic Opportunity Fund (COF) grants for country introduction activities.

The UNFPA Supplies Partnership maintained a high appetite for delivery risk. The programme operated in challenging environments with limited partners to deliver reproductive health commodities. In the majority of UNFPA Supplies Partnership countries, a significant portion of in-country deliveries of reproductive health commodities are undertaken by the government, with limited infrastructure. To mitigate the risk of stock-outs in healthcare facilities, the UNFPA Supplies Partnership provided support for the enhancement of electronic logistics management information systems (eLMIS) to facilitate the acquisition of real-time commodity data. Last mile assurance (LMA) processes are in place to mitigate delivery risks and to bolster capacity building in supply chain management.

RH Supplies operated with medium reputational risk, associated with the sensitivity of SRHR and potential for backlash from opposition groups. To address these risks, FCDO continues to advocate for the importance of investing in SRHR as a “development best-buy” and as part of our commitment to supporting women and girls. UNFPA maintains robust programme and communications teams that actively work to mitigate and manage potential reputational issues.

There was a low risk that the RH Supplies programme caused unintended harm to people and the environment. The programme team managed this safeguarding risk robustly, with a particular focus on sexual exploitation, abuse and sexual harassment (SEAH). This included communicating FCDO’s zero tolerance approach for inaction and mishandling and expectation that all partners follow robust safeguarding and reporting measures through their own processes, including prompt reporting to FCDO of SEAH allegations relating to FCDO funding, or where there was a significant impact on the partnership. FCDO continues to ensure all programme partners maintain full compliance with respective safeguarding policies and ensure full transparency on reporting with FCDO.

UNFPA maintains a policy of zero tolerance for SEAH. Implementing partners of UNFPA undergo capacity assessments in the protection against sexual exploitation and abuse. FCDO is actively engaged in UNFPA's initiatives to prevent and address sexual exploitation and abuse and sexual harassment through the UNFPA Executive Board. These encompass clear leadership and communication of zero tolerance, mandatory training and awareness campaigns, the establishment of a SEAH network including focal points in country offices, and clearly indicated reporting mechanisms. UNFPA Supplies collaborates with national counterparts and governmental bodies to enhance national protocols and guidelines pertaining to the disposal of medical waste and contraceptives. In conjunction with the WHO and regulatory bodies, UNFPA ensures that all supported products adhere to stringent standards of safety, efficacy and quality.

Looking ahead to CHOICES, future pressures – particularly the global rollback on women’ and girls’ rights and opposition to comprehensive SRHR which was another key programme risk – could impact the supply of commodities and the delivery of SRHR services, restricting access to safe, effective, high quality and affordable RH commodities for women and girls. Recent donor financing cuts, particularly the U.S., are expected to cause significant disruptions to supply chain management due to the contributions previously made by the U.S. to strengthening supply chain functions, such as eLMIS and distribution and warehouse management, within the broader ecosystem. This will likely place additional pressure on the already limited resources available to UNFPA Supplies for supporting these vital functions. To mitigate these risks as much as possible, FCDO and its likeminded partners continue to promote diverse funding mechanisms such as DRM; and strategise and advocate for the protection and progress of SRHR primarily in the multilateral space, but also at the country level, particularly through the International Women and Girls’ Strategy.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.
[note] A full assessment of VfM of each component is at Annex C.

UNFPA Supplies
Throughout the programme's duration, the UNFPA Supplies Partnership has been subject to stringent internal and external monitoring procedures. In accordance with the UNFPA Evaluation Policy, independent Mid-Term Evaluations (MTEs) are conducted for the program. The official mid-term evaluation is currently underway, overseen by the UNFPA Independent Evaluation Office, with the finalised evaluation report projected for submission in July 2025. Furthermore, the programme's performance is evaluated annually against the UNFPA Supplies Partnership Results Framework.

CHAI
Through the Catalytic Opportunity Fund (COF), CHAI (working with other stakeholders) identifies and undertakes due diligence on partners to receive funding to support RH product introduction and scale up. CHAI maintains a proactive dialogue on risks and delivery chain mapping. CHAI has worked hard to address its grant accounting processes for the COF (a key cost driver) in order to better align with FCDO financial forecasting expectations to manage uncertainties around FCDO funding. CHAI successfully spent down 100% of its budget in the 2024/2025 fiscal year, even while absorbing an additional £14m to the planned budget in June.

RHSC
Unexpected FCDO in-year funding cuts in 2024 forced PATH/RHSC to pivot and draw on other funds to cover planned programme expenditure. Though mitigated, this created potential risk around the delivery of agreed activities. Substantial modifications to RHSC’s programme logframe and indicators mid-programme also created some challenges. These changes required substantial investments on the part of RHSC to track and report on a new set of indicators, distinct from the core set of indicators initially agreed upon by RHSC’s main donors at the beginning of the programme.

Programme-level approach to monitoring and evaluation

UNFPA Supplies
- The UNFPA Supplies Partnership employs a rigorous results framework to ensure transparency and promote accountability at both global and regional levels. In 2022, the UNFPA Supplies Partnership initiated an independent review, undertaken by Hera, a cooperative consultancy firm.
- UNFPA has undertaken regular facility-based surveys to evaluate advancements towards programme objectives. These surveys yield critical data concerning the accessibility of diverse contraceptive methods and have been instrumental in tracking stock-out rates and gauging progress on a global scale. The UNFPA Supplies Partnership has been subjected to numerous FCDO reviews, audits and monitoring visits.
- Each programme implementing unit is required to submit quarterly and annual reports detailing progress against agreed-upon milestones. From 2021 onwards, quarterly reporting on Key Performance Indicators (KPIs) has been an essential monitoring mechanism, allowing FCDO and other donors to observe programme implementation and advancement in relation to quarterly targets and other relevant indicators. Quarterly reports are submitted to the Strategy and Planning sub-Committee (SPC) and the Finance & Risk Committee (FRC), detailing programmatic and financial performance, and biannual Steering Committee meetings are conducted to present key programme outcomes and solicit strategic direction and guidance.
- A consolidated UNFPA Supplies Partnership Annual Report provides a comprehensive overview of performance, risk and financial implementation across all programme areas. This report is submitted to all donors and made publicly available.

CHAI
- CHAI reports quarterly against the agreed milestones while also systematically tracking a longer list of KPIs on a monthly basis across all countries. CHAI delivered comprehensive quarterly monitoring reports, providing status updates across all milestones, highlighting risks, detailing narrative updates on the program, and reporting data on key performance indicators related to product access.
- The Hormonal IUD Access Group, co-led by CHAI and FHI360, is an effective oversight committee for understanding progress and challenges in increasing access to this underutilised product.
- CHAI facilitated lessons sharing through a number of fora throughout the grant:
  - Cross-country convenings of Ministry of Health officials from different countries to share lessons and best practices related to new product introductions and market stewardship
  - Country learning exchange visits, for example between Kenya and Uganda, on maternal and newborn health best practices
  - Publication of results and learnings in journals
  - Webinars to share best practices and lessons learned on the COF and on market stewardship
- An external evaluation of CHAI’s performance was conducted in the final year of the programme and concluded that the investment was successful in improving access to RH commodities and strengthening health systems in supported countries.

RHSC
- RHSC delivered comprehensive quarterly progress reports that provided status updates on objectives, key milestones, and performance indicators. FCDO and RHSC met quarterly to discuss these quarterly progress reports and results achieved against RHSC’s logframe.
- RHSC supported the dissemination of results and learnings to its members and to the broader RH community through its digital platforms, webinars and fact sheets.
- In 2023-2024, the RHSC conducted an independent landscape review of the RH ecosystem as well as a forward-looking qualitative assessment of RHSC’s future possibilities and potential that relied on key informant interviews of selected RHSC members and staff, and an online survey sent to all individuals with Coalition affiliations. The findings and recommendations of this landscape review and assessment shaped the contents of the RHSC’s new 2025-2035 Strategy and four-year workplan (2025-2028).
- FCDO was also a member of RHSC’s Executive Committee, meeting at least twice annually.

Date of last narrative financial report	May 2025 (various, covering 3 partners)	Date of last audited annual statement	May 2025 (various, covering 3 partners)