## Economic Development Investment Programme – Annual Review December 2022

Title: Economic Development Investment Programme (EDIP) – St Helena
Programme Value £ (full life): £30m		Review date: 03/04/23
Programme Code: 300714	AMP start date: 30/07/18	AMP end date: 31/07/26

Summary of Programme Performance
Year	2020	2021	2022
Overall Output Score	A	B	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300714/documents
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300714/documents

A. SUMMARY AND OVERVIEW

Description of programme

The St Helena Economic Development Investment Programme (EDIP) was approved in March 2019 and currently runs until July 2026, although a no-cost programme extension is currently under consideration to allow for full achievement at a deliverable pace. The programme’s purpose is to support economic development in St Helena by establishing sustainable and resilient small capital investments and physical infrastructure, and improving the enabling environment for economic activity. The FCDO is providing assistance to St Helena Government (SHG) of up to £30m, split into two phases of £15m each, with Phase 1 spread over the first four years, followed by a break point to establish the basis for approval of Phase 2 for the following years. Phase 1 is currently drawing to a close, and an independent breakpoint review has been conducted; its recommendations informing Phase 2.

The implementing partner is SHG, managing the programme through a Project Management Unit (PMU) on the island. This annual review was initially intended to take place in July 2022, but given the commission of the independent break point review, it was decided to postpone the annual review to a later date to avoid concurrent duplication of effort. The break point review issued a series of recommendations to address emergent issues and ‘course-correct’ where necessary, to ensure that the programme effectively achieves the intended impacts.

St Helena is one of the world’s most remote inhabited islands with limited capacity to support self-sustaining economic growth. This has meant its economic development remains highly constrained by barriers like economy of scale, high unit costs, and insufficient resources (physical, human, business, and financial), resulting in a low capacity to drive sustainable growth. The enduring impacts of the COVID-19 pandemic are still materialising, further constraining opportunities for development.

UK ODA is the main source of funding for St Helena through Financial and Capital assistance. The total funding envelope for EDIP remains valid, although the breakpoint review of summer 2022 has recommended a no-cost extension to the programme to allow SHG sufficient time to make full use of the allocation.

Summary supporting narrative for the overall score in this review

It is important to note that the milestones reviewed in this document were initially set for review in June 2022, but given the commissioning of the Break Point Review this annual review has been based on results achieved by December 2022.

The project has been reviewed as an A score. The third year of the programme has progressed well, although continued governance and capacity strengthening are required in order for EDIP to deliver on its ambitions at the intended pace. The focus this year has been on the reform of governance processes, establishment of a pipeline of major projects for phase two, and continued infrastructure works, including rehabilitation of Side Path and the construction of new port facilities in Ruperts Valley. A number of microprojects have also been completed, including construction of a car park by the hospital in Jamestown to reduce congestion, the construction of bus shelters to improve public transport access, and the rehabilitation of Bishops Bridge. Strong initial efforts have been made in institutionalising the Project Management Office (PMO), championed by EDIP as the largest capital programme on the island. A strong, empowered PMO will ensure that the skills and expertise generated through the delivery of EDIP are retained in SHG beyond EDIP’s lifetime.

The pace at which the programme is able to deliver is limited by domestic construction sector capacity (reducing ability to deliver multiple projects in parallel), by irregular shipping schedules and, despite a dedicated and skilled core team, by capacity shortages within SHG. More needs to be done to ensure SHG has adequate capacity and expertise to deliver on EDIP, and to mitigate external factors. More also needs to be done to ensure the implications of capital investment (e.g. operations and maintenance costs) on recurrent budgets are adequately factored into SHG’s budgets.

Major lessons and recommendations for the year ahead

Lessons:
- EDIP struggles to deliver at pace, due to limited contractor base and low capacity in SHG. Friction in EDIP decision processes should be minimised, and opportunities for parallel project implementation sought out.
- Lengthy procurement times and a lack of ‘shovel ready’ projects limits the ability of EDIP to adapt or flex to utilise available budget in full.
- EDIP’s Programme Review Group lacks the authority (or the willingness to wield authority) to function optimally, deferring responsibility to the High Level Panel, which in turn becomes too operational, thereby limiting space for strategic conversations.
Recommendations:
- An indicatively costed pipeline (and timeline) of projects for the remainder of EDIP, with ministerial endorsement from SHG, must be in place before the approval of Phase 2 of the programme.
- Monitoring and evaluation of EDIP projects should be supported by the recruitment of an M&E specialist. The EDIP logframe should be refreshed to better reflect the ambition and achievements of the programme.
- The High Level Panel should be elevated to a strategic body, with oversight of all capital investment projects on the island, and the Programme board (previously PRG) should be empowered to make effective and timely decisions.
- In parallel with the approval of the initiation of Phase 2 of EDIP, a two year no cost extension should be sought to extend the programme’s lifetime from 2026 to 2028, to allow EDIP to utilise the full funding envelope available.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The overall logic of the programme sets out that the outputs which are primarily social and economic infrastructure investments (with some enhanced dialogue, policy reforms and capacity development), in order to lead to a stated outcome of “Adequate resilient well maintained social economic infrastructure and utilities.”

(Image 1. EDIP ToC)

This infrastructure outcome is then intended to lead to an impact of “Increased attractiveness and economic development opportunities for Sustainable Development in St Helena”. The programme has assumed that improved quality of decision making and strengthened investment design and business case development alongside a targeted set of investment will enhance the benefits to economic development as compared to previous capital programmes.

The Logframe was finalised and agreed relatively late during the first year of delivery (2019/2020). The break point review criticises the narrative of the current logical framework for monitoring EDIPs progress towards the outcomes and impacts stated in the theory of change. As a result, this annual review will indicate where changes to the logframe will be made ahead of the approval of EDIP Phase 2, taking into account the comments made by the break point review.

By design, the programme will indirectly benefit every person on the island due to the range of projects prioritised. The direct benefits are yet to be fully planned and monitored, as is the full monitoring and evaluation plan for the programme. This presents a risk to the programme going forward and to correctly assessing the ToC.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme broadly remains on track to contribute to the expected outcomes and impact. The corrective steps outlined in this review will need to be implemented in the coming year in order to ensure the programme provides VfM and remains on course.

The ability of the programme to impact the island’s economic development has been constrained by the global effects of the pandemic, by a limited contractor base on island, and by the pressing need for small and/or remedial projects on St Helena, that are necessary for continued provision of critical services but do not explicitly contribute to the theory of change of the project.

Global tourism demand continues to be dramatically affected by the lingering effects of the pandemic, and a sustainable long-term recovery path remains uncertain, particularly for many African states, including South Africa which remains a key partner and originator of a high proportion of visitors to St Helena. The success of the programme, measured against the original theory of change, is intimately connected to the broader fiscal environment. A large exogenous shock (the pandemic) has hampered broader economic outcomes and by extension has limited the economic growth (which was promising, prior to the pandemic) that EDIP is predicated on amplifying.

The independent break point review stated that the core programme logic remains valid, although it also remarks that the prospects for short term economic growth are diminished relative to that predicted in EDIP’s business case. This is due to the fact that the business case was prepared with the consideration of an independent economic analysis (2018) that has since proven to be optimistic, in that it overestimated the economic gains associated with the opening of the airport, underestimated the timescales for the reticulation of the submarine telecommunications cable, and of course it did not (and could not) account for the significant impacts of COVID-19 on St Helena’s tourism sector.

The theory of change’s output 2 was discussed in the breakpoint review, which argued that EDIP is perhaps not the appropriate vehicle to undertake policy dialogue or to support policy reform, but also noted that effective capital investment programmes also require commensurate investment in governance and project management systems. This aligns with a recommendation in the previous annual review, which stated that the ‘Compact’ should be removed as an EDIP output, and programme management reform should instead be progressed by a country board to enable more strategic discussion between SHG and UKG. EDIP does not work in isolation, complementing (and being complemented by) the Financial Aid programme, which continues to champion this work. Instead, EDIP has pivoted to focus on supporting SHG’s Project Management Office (PMO) to better develop, manage and evaluate a pipeline of priority investments.

Given delays to projects, due to the impacts of travel restrictions necessitated by COVID-19 as well as capacity constraints and a dearth of ‘shovel ready’ projects, a no-cost extension to EDIP Phase 2 will be required to allow for the full allocation of UKG funds to be utilised effectively as noted in the break point review. The case for this extension will be submitted for approval in early 2023, in parallel with the case for initiating EDIP Phase 2, pending the recommendations made in this review.

In the coming year, major projects include; continuation of the Rupert’s Bay development, progressing the new prison project from design to construction, project development for an eco-business park, the telecommunications project (which intends to roll out connection to the submarine cable across the island), development of a new renewable energy strategy, continuation of the improved agricultural productivity project, and further flexible support to emerging needs through EDIP microprojects.

Residents are included in extensive public engagements driven by the PMU across all districts of the island and subsequently through their elected representatives who are involved at the planning permission stage, sometimes earlier. The PMU’s outreach programme via radio, online and through the local newspaper is effectively communicating the programmes progress to the public.

Gender, mental wellbeing, minority groups, and visible and invisible disabilities are recognised, acknowledged, and supported in the programme teams. Women are well represented at all levels in the programme team and governance structure. Further work is needed to ensure that the needs of marginalised groups are fully embedded into EDIP processes, for example the explicit discussion of universal design principles at the business case stage for infrastructure projects.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The programme has made good progress in some areas during its third year, and should be continued. This review has given due consideration to the unique global and internal challenges the programme has faced in the past few years (namely the lasting impact of the pandemic, and the creation of the FCDO). Improvements need to be made to the programme as detailed and recommended in this review. With these changes implemented, the programme is very likely to make a lasting contribution to the island’s economic and social development.

The programme continues to effectively support SHG’s long term sustainable development objectives, and to promote closer alignment between SHG and UKG priorities.

## C. DETAILED OUTPUT SCORING

Output Title	Social and economic development infrastructure investments and utilities delivered to meet short term and medium term needs with a justifiable return on investment
Output number:		1	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of prioritised social and capital infrastructure investments under the pipeline developed and approved by the HLP (High Level Panel)	Draft Pipeline of Future Projects for EDIP funding presented to HLP	Score: A. Achieved / As of June 2022: draft Pipeline of Future Projects for EDIP funding presented and discussed at the June 2022 meeting. / As of November 2022: Since then, the HLP has approved strategic priorities for Phase 2 at October 2022 meeting.
1.2 Share of new and resilient infrastructure spending planned and executed.	60% Spend target met (in financial year 2021/2022)	Score: A. Achieved / As of June 2022: 72% of allocated funds had been disbursed (Allocated £3.98m and disbursed £2.896m) / As of November 2022: 20% of the £4.5m allocation for financial year 2022/2023 has been disbursed
1.3 Ruperts Bay development constructed against a high quality business case with justifiable benefits.	50% of Ruperts Port Masterplan phase 1 completed.	Score: A. Achieved / As of June 2022: CFS yard complete / PCB yard commenced / Steel Frame erection contract awarded / Transformer purchased and received / Lighting purchased and received / Footpath (phase 1) complete / Sewerage plant installed / Fencing Contract awarded / Landscaping phase 1 completed / As of November 2022: Concrete pads for the PCB building have been poured. / By spend, of the project’s allocation of £4.794m, £2.427m has been disbursed, which is approx. 50.6% of the project’s allocated budget.
1.4 Water security, solid waste and wastewater feasible solutions being implemented	Strategic Case for separate systems in Half Tree Hollow (HTH) & Jamestown approved by HLP. / TOR to appoint a design engineer completed.	Score: A. Achieved / As of June 2022: Strategic case for separate systems in HTH & Jamestown approved by HLP / TOR to appoint a design engineer completed. / As of November 2022: TOR's for the consultancy have been approved by Project Board. Considerations of form of contracting underway.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output Area 1 measures EDIP’s success in mobilising investment for key social and economic infrastructure projects on St. Helena, meeting stated short and medium term priorities of the Government of St. Helena (SHG).

Indicator 1.1: In order to ensure that Phase 2 of EDIP has a pipeline of strategic priorities, planned and approved in preparation for investment, a prioritised list of infrastructure projects has been drafted, presented and discussed both by programme governance bodies (i.e. the Project Review Group and the High Level Panel) and SHG political decision makers. The indicator’s milestone has been met, and progress on gaining political endorsement of the priority projects continues in advance of Phase 2’s initiation. As such, Indicator 1.1 scores an A.

Indicator 1.2: This indicator measure’s EDIP’s ability to disburse allocated funds for infrastructure projects in St. Helena. Given significant delays to projects over the course of the pandemic, exacerbated by St. Helena’s remoteness, the milestone for the 2021-2022 financial year was set at 60% of allocated funds. EDIP exceeded that target, disbursing 72% of the financial allocation. Financial management and planning of the programme has improved since the previous annual review, but further work is required to identify and mitigate risks to delivery schedules at an earlier stage. Indicator 1.2 scores an A.

Indicator 1.3: Rupert’s Bay port was constructed as a means of offloading the material and heavy equipment required in the construction of the St Helena Airport. Historically, the wharf at Jamestown has been used for cargo loading and offloading, where cargo and passengers were ferried from the wharf to ocean-going vessels anchored in James Bay. The mixed use of Jamestown’s wharf (i.e. cargo, passengers, fishing and recreation) limited the benefits to all stakeholders. To capitalise on the economic potential of the Rupert’s Bay port, the Rupert’s Bay development plan was initiated in 2020, aiming to relocate cargo handling from Jamestown wharf to Ruperts, reducing health and safety risks and freeing up use of the Jamestown wharf for non-cargo activities. This indicator measures progress against the planned activities for development of Ruperts. The indicator scores an A, given that the target of 50% completion against the plan has been achieved, based on the ratio of spend vs budget allocation.

Indicator 1.4: This indicator measures the progress made by EDIP in supporting development of St. Helena’s water (supply, storage, and treatment) and sanitation infrastructure. The strategic case for separate water systems for Jamestown and Half Tree Hollow has been approved by the High Level Panel, with the Terms of Reference for a design engineer for these systems compete with contractual considerations underway. EDIP is also facilitating FCDO support to Connect and SHG’s implementation plan for St. Helena’s Water Resource Management Strategy, which will ensure secure and sustainable water resource utilisation on the island. This process may indicate further water and sanitation priority investments in the coming year. Given the progress made in this area, Indicator 1.4 scores an A.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No significant changes have been made to this output over the review period. The logframe indicators were mutually agreed based on ambitious but achievable expectations.

Indicator 1.1 should be revised to assess the completeness of the priority projects pipeline, including indicative costs and timelines, to allow for practical budgets to be allocated each year.

It is recommended that a revision of Indicator 1.2 is considered, to include consideration of the quality of investments and the ability of the allocated funds to be prioritised to projects with the greatest social and economic returns. Logframe targets for the next review period will be mutually agreed by FCDO and SHG following this annual review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations from the previous Annual Review for this output area were:

1. Prioritised list of year-on-year projects to support in-parallel development of business cases, to significantly improve future planning and prioritisation by HLP;
2. Update and monitor log frame indicators through PRG, to ensure milestones are current, practical, and ambitious;
3. EDIP should allow current economic development infrastructure projects to establish themselves before any further projects of this kind are agreed;
4. EDIP should reset pipeline programmes for Phase 2 to pivot towards social/critical infrastructure projects, revisiting the John Cox Report to inform this process.

Recommendations 2 and 3 and 4 have been adopted, and recommendation 1 has partially been adopted, although a deeper pipeline of prioritised projects would be beneficial to the smooth operation of EDIP, not least allowing EDIP activities to flex with variable budget allocations.

Recommendations for the coming year include;

1. A clear, indicatively costed pipeline of priority activities for the remainder of the EDIP programme, including indicative timelines
2. Refresh logframe for Phase 2 to more accurately showcase EDIP objectives and achievements
3. Develop an asset management system to catalogue EDIP funded infrastructure, including recommended maintenance schedule and indicative maintenance costs as part of the standard business case

Output Title	Robust and effective project/programme governance to maximise the chance of project success and ensure time, cost and delivery objectives are met.
Output number:		2	Output Score:	A+
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Project/programme management embedded within the public service at a strategic level.	Project management framework drafted. Strategy for developing PMO agreed.	Score: A. Achieved / Project Management Framework has been drafted in consultation with Programme and Project Managers. Its use is being trialled by the Technical Section, before being rolled out across the Public Services. / SHG Senior Leadership Team has agreed in principle for SHG's strategy to be delivered through the PMO. Discussions with Portfolios Senior Management Team planned for January 2023.
2.2 EDIP projects governance arrangements are periodically reviewed.	New process for project onboarding tried and tested to 2 projects.	Score: A+. Milestone exceeded / Process applied to 4 projects with successful outcome / BPR proposes a change in project onboarding and approval process.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output Area 2 measures the success of EDIP in contributing to improvements in infrastructure project governance in St. Helena’s public sector, considering how improvements made through EDIP programme governance can serve as a tent-pole for improvements across project/programme management in SHG.

Output 2.1: FCDO has facilitated the partnership between SHG and the Government of Montserrat to support SHG’s establishment of Project Management Office (PMO), to be responsible for capital project preparation, evaluation and procurement. As this initiative has led to improvements in project governance (and project delivery) in Montserrat, FCDO has encouraged the adoption of a similar body within SHG. This Output measures the success of EDIP in facilitating and supporting the implementation of such a body. To date, a Project Management Framework has been drafted and is currently being trialled ahead of wider adoption, and the delivery of SHG priorities through a PMO has been agreed in principle by SHG’s senior leadership team. This indicator scores an A.

Output 2.2: To ensure that project governance arrangements are held to a high standard, and improved upon where necessary, periodic evaluation is required. This indicator measures the trialling of new project onboarding processes intended to improve outcomes. Against a target of trialling the onboarding process in two projects, the PMU successfully applied the progress to four projects, therefore this indicator scores an A+.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The original intent of the Output, in respect of the Compact, was to develop and design the architecture for a new style of relationship between SHG and UKG, for long term engagement on the management of capital funding to the island, beyond the scope of EDIP. The purpose was to create a partnership fit for the future, which is not based on the legacy model of a recurrent ODA allocation and separate capital fund programmes. Whilst progress has been made, the output area has since been changed – based on recommendations made in the previous Annual Review, the output now focuses on improvements to project management and governance rather than a ‘compact’ between SHG and UKG.

Further changes, based on recommendations made in the break point review, are planned for the next review period, including; increased responsibility and resourcing of the PMO, improvements to the onboarding process, and renewed focus on institutionalising MEL processes. Following this annual review, new milestones will be agreed for existing indicators, and additional indicators will be considered to measure reporting and MEL expectations.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations from the previous annual review were:

1. A decision should be made about whether it is appropriate for the Compact to remain in EDIP, or to be moved to an FCDO country level plan.
2. A governance review should be conducted to review the composition and terms of reference of both HLP and the Programme Review Group;
3. HLP makes a concerted effort to discuss the long-term vision for the economic development of the island, and avoid focusing on updates and progress reports on individual projects within EDIP;
4. The Logframe, in its entirety, needs to be monitored by the Programme Review Group. Milestone indicators need to be reviewed to ensure they are relevant and achievable. It is unacceptable that these activities are only done once a year at the time of the AR.
Recommendations 1 and 2 have been adopted and actioned; the ‘compact’ is no longer to be delivered under EDIP; a review of the terms of reference and composition of the HLP and PRG is underway, including directing the HLP towards more long-term, strategic discussions rather than operational matters (thus contributing to the partial actioning of Recommendation 3). Recommendation 4 remains a concern that will be addressed as a priority in the period following this annual review, as milestones and indicators are discussed and mutually agreed.

Recommendations under this area for the coming year are:

1. Review and refresh EDIP Governance boards, ensuring that there is an appropriate cross-SHG portfolio level forum
2. Clearly define the proposed responsibilities of the PMO, seek ministerial endorsement for mandate
3. Drive forward the upskilling of the PMO to enable the fulfilment of its mandate
4. Use the refreshed logframe, once agreed, as the foundation for quarterly updates in the Programme Delivery Group

Output Title	Well prioritised, high quality, well justified high return social and economic development investments developed
Output number:		3	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of Business Cases with realistic options and quantifiable benefits considered - submitted and approved.	A formal benefits monitoring framework for EDIP investment linked to quantified benefits drafted for approval	Score: A. Achieved / Benefits monitoring framework drafted.
3.2 Reduction in size of investments as a result of improved quality of project development processes	600k savings from first and final business case with comparable scope.	Score: C. Not achieved. / £30k increased in budget for IAP, as a result of change of scope.
3.3 Number of changes made to project proposals as a result of public consultations, to reflect an improvement in the project development processes.	15 changes made from original proposals to finalised and approved versions	Score: A+. Milestone exceeded / 18 changes made in total / IAP - 4 changes / Micro Projects - 5 / R2 - 3 / Ruperts - 3 / Judicial Relocation - 3

Briefly describe the output’s activities and provide supporting narrative for the score.

Output Area 3 is predicated on measuring EDIP’s success in ensuring that investments made under the programme are sufficiently prioritised, and maximise social and economic benefits for the people of St. Helena.

Output 3.1: measures the extent to which benefits are monitored and quantified at a project level, allowing for improved prioritisation and decision making in future strategies. The milestone this year was for a formal benefits monitoring framework to be drafted for approval by SHG and EDIP’s High Level Panel. This framework has been drafted and is ready for review and approval, meeting expectations, therefore the indicator scores an A.

Output 3.2: measures the ability of EDIP, through improvements to project development and management processes, to reduce the size of investments without compromising on scope or quality of investment. The stated ambition of £600k of savings between project proposals and final business case has not been achieved, and instead an increase of £30k has been incurred by expansion of scope in the Increased Agricultural Productivity project. As such, the indicator scores a C. This, in part, may be due to an absence of reported successes in comparing initial and final business cases rather than a reflection on the quality of the development process.

Output 3.3: measures the efforts made by the PMU to ensure that EDIP projects are fully consultative and in the interest of the St Helenian public. The stated ambition was, through public consultations, to facilitate 15 amendments to project proposals. The ambition was exceeded, with a total of 18 amendments made between initial and final proposals for EDIP projects, and as a result the indicator scores an A+

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No significant changes were made to this output over the review period. The PMU continues to ensure that EDIP projects are subject to public scrutiny and consultation, and progress has been made in formalising benefits monitoring for EDIP investments.

The wording of Indicator 3.1 should be revised to indicate EDIP’s achievement of robust evaluation of benefits and costs at the business case stage.

For Indicator 3.2, greater attention needs to be paid to recording and reporting initial and final business case figures in order to fairly gauge success. Milestones and revisions to indicators will be mutually agreed following this annual review.

Indicator 3.3 should be revised to better reflect the extent to which EDIP is consultative, rather than the number of revisions needed in business case development.

An additional indicator should be included to reflect EDIP’s ambition to ensure the recurrent costs necessitated by capital investments on St Helena are understood and accounted for, including maintenance and replacement budgets and timelines.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations made in the previous Annual Review were:

1. Greater emphasis should be placed on the importance of social infrastructure projects as a driver of economic development, addressing the current imbalance which favours economic infrastructure projects would benefit future investment decisions;
2. Education infrastructure investment should be considered central to economic development as recognised in the original EDIP BC;
3. PMU to ensure all changes made to BCs as a result of public consultations are thoroughly recorded, in line with the programme Logframe;
4. Programme Logframe output indicators need to be monitored more regularly and effectively, and if unfit for practical purposes, must be changed accordingly.
5. This AR strongly recommends that social and environmental impact assessments are correctly resourced and reflected within programme business cases to ensure unintended and non-desirable outcomes can be identified and where possible mitigated against.
Recommendations 1, 2 and 4 have not been sufficiently progressed. Recommendations 1 and 2 are strategic directions that will be need considered in building the project pipeline for phase 2 of EDIP.

Recommendation 3 has been partly actioned, but a change-log of changes prompted by consultations should be implemented for each business case to evidence the attention paid to these consultations.

Recommendation 4 has not been progressed and, as noted in output area 2, is an immediate concern that will be addressed in the period following this annual review, as the logframe is revised to include mutually agreed indicators and milestones, more frequent reporting against the logframe will be expected, including regular in-year review of indicator validity.

Recommendation 5 has been addressed and impact assessments are routinely included within project proposals.

Recommendations for the coming year:

1. Ensure economic appraisal of proposals for EDIP projects include a robust consideration of recurrent costs, and that these costs are accounted for in SHG recurrent budgets
2. Ensure a change-log is kept for project Business Cases, indicating changes prompted by public consultation and indicating changes to costs (and reasoning)

Output Title	Increased local capacity through enhanced prog management, assets management, procurement capabilities, systematic stakeholder involvement and climate and environment opportunities.
Output number:		4	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Assets and facilities management system setup and incorporated into O&M plan.	Policy and Strategy for Asset Maintenance endorsed by St H Ministers.	Score: B. Partially Achieved / Building Maintenance Policy and Strategy approved by Minister in May 2022. / Locally producing asset management software as the next step.
4.2 % of project forecasts being achieved and timely completion of EDIP projects within budget and to specification	90 percent of project forecasts hold true within 10 percent allowance of initial estimate. VfM Assessments of proposed investments opportunities undertaken.	Score: B. Partially Achieved / 2021-2022 Financial Year forecast for R2 and Ruperts projects within 87% / R2 forecast/spend - £967k/ £733k / Ruperts forecast/ spend - £1.676m/ £1.592m
4.3 Programme management capacity strengthened.	EDIP specialised expertise needs met within 3 months. / 21 number of SHG employees pass an APM Fundamentals course	Score: B. Partially Achieved. / Recruitment into vacant positions, commences within 3 months after positions become vacant, but does not prove successful. / Resources strategy on improving EDIPs resource approved in June 2022. / 21 employees completed an APM fundamentals course, out of which 15 achieved pass marks

Briefly describe the output’s activities and provide supporting narrative for the score.

Output Area 4 measures the efforts of EDIP to enhance the St Helena Government’s domestic capacity for effectively managing capital investment and infrastructure projects.

Output 4.1: measures the extent to which asset and facilities management systems have been established and incorporated into standard operations and maintenance practices within the St Helena Government. The ambition in the review period was to have a policy and strategy for asset maintenance endorsed by SHG ministers; this was achieved in May 2022 with the approval of the Building Maintenance Policy and Strategy, meeting the milestone and scoring an A.

Output 4.2: this indicator measures the accuracy of SHG infrastructure project finance forecasts, and routine the evaluation of the value for money of projects. The ambition for the review period was to have 90% of projects reporting an expenditure within 10% of their initial forecasts, and for value for money assessments to be undertaken for proposed investment opportunities. The forecast for the 2021-2022 financial year was within 87% of the forecasted figure, narrowly missing the milestone, and achieving a score of B.

Output 4.3: measures the success of EDIP at driving capacity strengthening in the St Helena Government with regards to project management. The milestone for the year was for EDIP specialist expertise needs to be met within three months of the need arising, and for 21 SHG employees to have passed an APM (Association of Project Management) fundamentals training course. Whilst recruitment for specialist expertise has taken place within three months of the need arising, in this review period the recruitment has not proved successful. 21 SHG employees have undertaken the APM fundamentals training course, but only 15 scored a passing grade, and so the indicator achieves a score of B.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes to the output have been made during the past year.

In the coming year this output area needs to be revised to better reflect upskilling and capacity development initiatives at the programme and project level, including (but not limited to) EDIP support to the Programme Management Office. Indicator 4.1 should be moved into output area 3, as the intent of this is to ensure sufficient consideration of the costs and benefits of each intervention, rather than to build capacity as such.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations made in the previous annual review were:

1. SHG to establish and own PMO function to support programme governance;
2. SHG to improve timeliness of financial reporting to PMU to support effective decision-making by project governance groups;
3. SHG to develop a robust AMP within the next year;
4. SHG to appoint a dedicated M&E specialist to support EDIP (as part of wider responsibilities);
5. PMU to assess if recruitment of full time Quantity Surveyor is necessary.
Recommendation 1 is in progress; SHG have committed to establishing the PMO, which is being championed by the Chief Secretary (SHG’s most senior civil servant). Discussions continue regarding how this PMO will be resourced and how it will interface with EDIP (and other) capital investment projects.

Recommendations 2, 3 and 4 have not progressed and will be carried forward to the next year.

Recommendation 5 has progressed, with the decision that a full time Quantity Surveyor is not necessary for EDIP projects.

Recommendations for the year ahead:
1. EDIP to support the establishment of SHG owned PMO, with defined roles and responsibilities, with staffing needs identified.
2. Appointment of dedicated SHG M&E specialist to support EDIP, as part of PMO
3. SHG to improve timeliness of financial reporting to support effective decision making by project governance groups, supported by a costed timeline of priority projects
## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

Achieving value for money on large scale infrastructure investments in the Overseas Territories, or any Small Island Developing States, is difficult, as their small size leads to diseconomies of scale. Challenges include, long supply chains and lead times for international procurement which increase costs and extend project timelines, as well as a limited supplier base on the island which reduces the competitiveness of tenders and capacity to implement projects in parallel.

Large infrastructure projects, such as a port, cost a similar amount regardless of the number of people able to utilise them. In St Helena, where the population is less than 5,000, this inevitably means projects will have a high per-capita cost and lower potential returns on investment. Furthermore, the large projects funded by EDIP (eg Rupert’s wharf and R2) are not ones which will necessarily generate immediate direct economic returns.

However, these projects generate substantial spill over effects and are essential for all forms of economic activity on island, thus facilitating and amplifying the impact of complementary investments which can generate returns. For example, without investment to operationalise Rupert’s Wharf, the benefits of previous investment to construct the wharf will not be realised. Similarly, investment to improve roads networks are essential for maximising the impact of the investment into Rupert’s Wharf. Such positive spill over effects on the broader economic environment are difficult to quantify and attribute but their magnitude is sufficiently large to justify the investment costs.

The breakpoint review recognises the difficulty of benchmarking infrastructure project costs in remote small island states such as St Helena, including between (for example) St Helena and Montserrat. A solution to this would be to collect as much disaggregated data on design, materials, shipping and labour costs for infrastructure projects in St Helena as possible, to better inform costing and bid evaluation in future projects and ultimately strengthen VfM.

VfM performance compared to the original VfM proposition in the business case

The breakpoint review indicates that the Business Case’s stated intention to verify VFM through independent quality assurance and validation has not been realised. The £300k evaluation budget has, to date, only been drawn on for funding the breakpoint review, limiting the ability to provide assurances of VFM.

The breakpoint review also notes the potential confusion between cost effectiveness and the guarantee of a rate of return – for EDIP’s purpose, cost effectiveness (that is achieving a set objective with the minimum lifetime costs) is a more appropriate ambition than ‘adequate rate of return’, as specified in the Business Case, which is difficult to evaluate and cannot be guaranteed, especially in critical infrastructure projects that enable an economic environment rather than directly generate revenue.

The breakpoint review notes, positively, that EDIP’s Chartered Engineer provides considerable reassurance on the cost-effectiveness of technical solutions and the contracts awarded to implement these. This review indicates that this should be supplemented by the work of an M&E specialist in future years.

Evaluating VFM against the Business Case’s VFM Matrix:

Level	Projects Implementation	Achievement and recommendations
Economy	Independent assessment of delivery agent’s procurement and contract management capacity / Evidence of quality indicators of operations and works / Quality factors, such as proposed approach to construction supervision, environmental and social impacts, on-going maintenance, etc. / Local procurement and transport costs where possible / Cost deviations from Budget	Conducted through Breakpoint review, no regular independent assessments / Local procurement is standard, where possible, in all EDIP projects. Some larger projects (e.g. new build prison) necessitate international competition, as exceptions. / EDIP Projects are generally delivered on budget, with the exception of instances where project scope has increased.
Efficiency	% of payments that are linked to outputs / transparent and competitive procurement / Standardization of procurement, contracts, and performance standards / Implementation time vs. original schedule	Payments are made based on delivery of milestones / Local and international procurement is transparent and competitive, although the limited size of domestic supplier base does constrain the competitiveness of any local procurement. / Procurement and contracts are standardised, with scope to flex with specific needs / Project delivery times regularly overrun, due to supply chain issues and due to labour constraints
Effectiveness	Amount of construction risk being taken on by contractor / Service Quality (e.g. households connected, outage days, etc). / Revenue collection	Little risk is taken on by contractors, ultimately resting with SHG / EDIP delivered infrastructure is generally of a high quality and receives positive public feedback. / No EDIP infrastructure built to date generates revenue directly. / EDIP funded infrastructure is generally of high quality. Post-project reviews are required for further assurance
Equity	All new build includes a professional assessment and implementation of disabled access for a range of disabilities; and includes consultation with disabled and user groups. / Access by minority groups / Gender and ethnicity targets for SME funds and other individually accrued benefits / Gender and beneficiary analysis included in prioritisation/choice of infrastructure/approval discussions	Consultations with user groups are carried out routinely, and new builds are assessed by EDIP’s chartered engineer, although explicit reports on these are not produced. / Universal access is a design consideration at business case stage of project proposals / There are no gender/ethnicity targets in place or measured / Beneficiary analysis is not explicitly considered in project prioritisation or approvals process, but remains an underlying factor. This needs to be brought out more explicitly in future years.

Assessment of whether the programme continues to represent value for money

Whilst quantifying the impact of EDIP is difficult – anecdotal and qualitative evidence suggests that EDIP investments are essential for enabling broader economic activity. Given the lack of revenue generating projects, the VfM of projects can only be quantitatively assessed through a cost-effectiveness approach, to evaluate the extent to which EDIP projects minimise costs associated with achieving specific objectives.

The Breakpoint review disputes the previous annual reviews assertion that EDIP investments do not offer good value for money, stating that:

The statement in the 2021 Annual Review that the business cases for the EDIP investments undertaken do not offer good value for money is not correct. It asserts that because the small population of St Helena means investments have high per capita costs and low returns, and that for some larger projects there will not be
immediate economic returns, it is not possible to assert that value for money is achieved. In these circumstances cost-effectiveness analysis should be deployed and could demonstrate value for money.

St Helena has a continuing need for capital investment in social and economic infrastructure, and will do so for the foreseeable future. EDIP is central to meeting this need, and ensuring value for money is essential to maximising benefits from limited resources. Further real-time and post-implementation evaluation (to be supported by the appointment of an M&E specialist) will bolster efforts to gauge and maximise VFM.

As the Breakpoint review states; a recast EDIP Phase II is both desirable and essential to St Helena, and should be approved expeditiously.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The St Helena Government programme risk appetite for EDIP is Moderate and is overall in line with FCDO’s EDIP risk register, which is also Moderate.

As of January 2023, SHG’s main emerging EDIP risk areas are:
1. Project costs increase as a result of global crises, resulting in less production at a high costs
2. Unable to spend budget allocated for this Financial Year
3. Contractors uncertain of freight and delivery of materials to St Helena following announcement that SHG awards new contract to provide cargo freight to St Helena, resulting in increased costs and delays to project implementation
4. Growing (and poorly defined) maintenance needs limiting funds available for new investments.

Mitigating measures are in place, and FCDO are supporting with these. Elements of these risks (high materials and shipping costs, irregular shipping schedules) are external to SHG and whilst the impacts can be minimized, the risks cannot be removed entirely. The PMU continues to work to mitigate these risks with FCDO support. Within the coming year, the greatest challenge will be managing the initiation of Phase 2, including UK Treasury approval of the Phase 2 budget and SHG’s implementation of Phase 2 reforms.

The Project Management Unit submits a monthly monitoring workbook. Monthly Programme Review Group meetings discuss and scrutinise the workbook, providing the PMU with a challenge function and testing for any emerging risks. An update on health and safety incidents is also now a standing item on the PRG meeting agenda. Any emerging risks are discussed at the fortnightly EDIP planning meeting. Safeguarding concerns are routinely prompted, and where extant raised, at regular meetings. The FCDO EDIP programme risk register was last reviewed and amended in February 2022. More regular reviews and updates are required – at least quarterly. None of these risks have escalated into issues but are being regularly monitored.

The main risks for FCDO are:
1. EDIP funded interventions fail to implement proper controls, causing harm to the people or the environment of St Helena.
2. New (and existing) infrastructure does not have adequate provision for maintenance, leading to reduced operational life and exposure to health and safety and reputational issues.
3. Failures in SHG's procurement practices resulting in resources getting wasted, which in turn reduces the ability of FCDO to continue with the programmes as planned

Measures to mitigate these risks are in place in partnership with SHG.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Overall strategic decisions for the programme are made by the HLP, which is chaired by the UKG SRO. This has resulted in more cohesive and strategic approach, which has helped to strengthen SHG and UKG engagement and collaboration, and foster a greater sense of partnership. HLP also includes elected representatives from St Helena. The HLP receives Business Cases for review after they have been cleared by PRG, which sits at the technical level. There is a consensus that the existing governance processes can be improved upon, however. SHG and UKG lack a forum to discuss portfolio level strategy, the HLP often spends time on operational matters, and the PRG lacks the confidence to utilise delegated authority. This will be addressed in the coming year, in tandem with strengthening the PMO, through a governance reforms process.
Programme monitoring is conducted by the PMU and provides a programme monitoring report to its Board and to UKG on a monthly basis. Once received, a PRG meeting takes place to discuss the report. The quality of reporting is good, but the report should be received at least week before the meeting takes place to provide an opportunity for members to fully digest its contents. It includes a narrative around progress on each project including timeline, actual/projected spend, activity log, risk log, along with a financial summary for the year. The Programme Responsible Officer has recently visited St Helena, conducting site visits to historical and current EDIP projects, and holding conversations with the PMU on project management, governance and resourcing.
The total spend at the end March 22 on the project was £7,917,310 (75% of allocated budget). Last financial year (2021/22) spend was £2,748,581 - 69% of allocated budget. The below table indicates the up to date allocation and spend figures for each financial year.

Year	Allocation	Spend	Percentage of allocation spent
19/20	3,320,000	2,747,163.46	82.75
20/21	3,200,000	2,421,556.41	75.67
21/22	3,980,000	2,748,580.74	69.06
22/23	3,800,000	2,707833.53	71.26

The programme continues to struggle to spend its full allocation, due to a number of reasons, including; a lack of shovel ready projects delaying project implementation, low capacity of SHG further contributing to long lead-in times, limited supplier base on island reducing the ability to implement multiple projects in parallel, uncertain/irregular shipping schedules delays delivery of materials.
However, underspends may also have arisen from efforts by SHG to ensure value for money and reduce costs, notably by utilising local contractors and careful consideration of costs of inputs. All payment requests are submitted with a funds request signed by the Financial Secretary along with an expenditure spreadsheet.
At the end of year 3, the project to date has not fully utilised the initially agreed £15m. Phase 1 of the programme was extended by a year, and a further no-cost extension to the programme is planned, to allow for full utilisation of the allocation, whilst FCDO continues to support SHG to build capacity and mitigate project risks to improve the ability to deliver infrastructure projects at pace.

Date of last narrative financial report	March 2023	Date of last audited annual statement	FY 2022/23