## Annual Review Template

Title: Economic Development Investment Programme (EDIP) – St Helena
Programme Value £ (full life): £30m		Review date: Dec 2023
Programme Code: 300714	AMP start date: 30/07/18	AMP end date: 31/07/26

Summary of Programme Performance
Year	2020	2021	2022	2023
Overall Output Score	A	B	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300714/documents
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300714/documents

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

- The St Helena Economic Development Investment Programme (EDIP) was approved in March 2019 and currently runs until July 2026. The programme’s purpose is to support economic development in St Helena by establishing sustainable and resilient capital investments and physical infrastructure and improving the enabling environment for economic activity. The FCDO is providing assistance to St Helena Government (SHG) of up to £30m, split into two phases of £15m each, with Phase 1 spread over the first four years, followed by a break point to establish the basis for approval of Phase 2 for the following years. Phase 1 is currently ending, and an independent breakpoint review has been conducted; its recommendations are informing Phase 2.
- The implementing partner is SHG, managing the programme through a Programme Management Office (PMO) on the island. This annual review takes place 18 months after the independent break point review in summer 2022. The break point review issued a series of recommendations to address emergent issues and ‘course-correct’ where necessary, to ensure that the programme effectively achieves the intended impacts. All these recommendations have been satisfied and there is an expectation that Phase 2 this will be approved this year.
- St Helena is one of the world’s most remote inhabited islands with limited capacity to support self-sustaining economic growth. This has meant its economic development remains highly constrained by barriers like economy of scale, high unit costs, and insufficient resources (physical, human, business, and financial), resulting in a low capacity to drive sustainable growth. UK ODA is the main source of funding for St Helena through Financial and Capital assistance. The total funding envelope for EDIP remains valid, although the breakpoint review did recommend a no-cost extension to the programme to allow SHG sufficient time to make full use of the allocation.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

This annual review has been based on results achieved by December 2023.

The project has scored an A. The fifth year of the programme has progressed well, although continued governance and capacity strengthening are required for EDIP to deliver on its ambitions at the intended pace. The focus this year has been to establish a pipeline of major projects for phase two, and to continue infrastructure works, including the wastewater systems for Half Tree Hollow and James town and the widening of Field Road and the further construction of new port facilities in Ruperts Valley with the intention for operation in 2024. On the larger projects, the tender for the new prison has been issued and preparations are underway to begin design and modelling work for the new renewables project. Several microprojects have also been completed, including an extension of the prison into the tool shed and work identified to be undertaken on the Jamestown Wharf Landing steps. Strong efforts have been made in institutionalising the Programme Management Office (PMO) and a revised governance structure, championed by EDIP as the largest capital programme on the island. A strong, empowered PMO will ensure that the skills and expertise generated through the delivery of EDIP are retained in SHG beyond EDIP’s lifetime.

The pace at which the programme can deliver is limited by domestic construction sector capacity (reducing ability to deliver multiple projects in parallel), by irregular shipping schedules and, despite a dedicated and skilled core team, by capacity shortages within SHG. More needs to be done to ensure SHG has adequate capacity and expertise to deliver on EDIP, and to mitigate external factors. More also needs to be done to ensure the implications of capital investment (e.g. operations and maintenance costs) on recurrent budgets are adequately factored into SHG’s budgets.

Major lessons and recommendations for the year ahead [1/2 page]

Lessons:
- EDIP struggles to deliver at pace, due to limited contractor base and low capacity in SHG. EDIP decision processes should be efficient and effective, and opportunities for parallel project implementation sought out.
- Lengthy procurement times and a lack of ‘shovel ready’ projects limit the ability of EDIP to adapt or flex to utilise available budget in full.
- The Programme Review group transitioned to the programme board in 2023. This gave the necessary authority for it to make effective and timely decisions. It also offered the space for strategic conversations.
- The High-Level Panel transitioned to Steering Committee in 2023. This gave strategic oversight of all capital investment projects on the island and has been operating effectively.
- While the EDIP team is skilled and committed, a combination of capacity constraints and optimism bias often results in unforeseen cost and time extensions to projects, sometimes unfairly undermining credibility. FCDO and SHG should work together to mitigate these risks.
Recommendations:
- Monitoring and evaluation of EDIP projects should be enhanced now that recruitment of an M&E specialist has happened. The EDIP log frame should be refreshed to better reflect the ambition and achievements of the programme going into phase 2.
- The approval of the initiation of Phase 2 of EDIP, a two year no cost extension should be sought to extend the programme’s lifetime from 2026 to 2028, to allow EDIP to utilise the full funding envelope available.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The overall logic of the programme sets out that the outputs which are primarily social and economic infrastructure investments (with some enhanced dialogue, policy reforms and capacity development), in order to lead to a stated outcome of “Adequate resilient well maintained social economic infrastructure and utilities.”

(Image 1. EDIP ToC)

This infrastructure outcome is then intended to lead to an impact of “Increased attractiveness and economic development opportunities for Sustainable Development in St Helena”. The programme has assumed that improved quality of decision making and strengthened investment design and business case development alongside a targeted set of investment will enhance the benefits to economic development as compared to previous capital programmes.

The Logframe was finalised and agreed relatively late during the first year of delivery (2019/2020).

By design, the programme will indirectly benefit every person on the island due to the range of projects prioritised. The direct benefits are yet to be fully planned and monitored, as is the full monitoring and evaluation plan for the programme. This presents a risk to the programme going forward and to correctly assessing the ToC. However, an officer has taken up the SHG MELO role in January 2024

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme broadly remains on track to contribute to the expected outcomes and impact. The corrective steps outlined in this review will need to be implemented in the coming year to ensure the programme provides VfM and remains on course.

The ability of the programme to impact the island’s economic development has been constrained by project and shipping delays, by a limited contractor base on island, and by the pressing need for small and/or remedial projects on St Helena, that are necessary for continued provision of critical services but do not explicitly contribute to the theory of change of the project e.g. funding a new prison from EDIP

Global tourism demand has begun to recover, and the subsea telecommunication cable is now connected. A sustainable path forward however is unclear, particularly with instability in South Africa which remains a key partner and originator of a high proportion of visitors, material, and goods to St Helena. The success of the programme, measured against the original theory of change, is intimately connected to the broader fiscal environment. Exogenous shocks like the rise in cost of living and internal shocks like the decline in the working age population has hampered broader economic outcomes and by extension has limited the economic growth that EDIP is predicated on amplifying.

The independent break point review stated that the core programme logic remains valid, although it also remarks that the prospects for short term economic growth are diminished relative to that predicted in EDIP’s business case. This is due to the fact that the business case was prepared with the consideration of an independent economic analysis (2018) that has since proven to be optimistic, in that it overestimated the economic gains associated with the opening of the airport, underestimated the timescales for the reticulation of the submarine telecommunications cable, and of course it did not (and could not) account for the significant impacts of COVID-19 on St Helena’s tourism sector.

The theory of change’s output 2 was discussed in the breakpoint review, which argued that EDIP is perhaps not the appropriate vehicle to undertake policy dialogue or to support policy reform, but also noted that effective capital investment programmes also require commensurate investment in governance and project management systems. EDIP has pivoted well to focus on supporting SHG’s Project Management Office (PMO) to better develop, manage and evaluate a pipeline of priority investments. EDIP in this regard has provided an effective vehicle to deliver an updated project and programme governance approach which feeds into the new steering committee.

A no-cost extension to EDIP Phase 2 will need to be in place to allow for the full allocation of UKG funds to be utilised effectively as noted in the break point review.

In the coming year, major projects include the continuation of the R2 road project, Rupert’s Bay development, progressing the new prison project from design to construction, project development for a new renewable energy system, and further flexible support to emerging needs through EDIP microprojects.

Residents are included in extensive public engagements driven by the PMO across all districts of the island and subsequently through their elected representatives who are involved at the planning permission stage, sometimes earlier.

Gender, mental wellbeing, minority groups, and visible and invisible disabilities are recognised, acknowledged, and supported in the programme teams. Women are well represented at all levels in the programme team and governance structure. Further work is needed to ensure that the needs of marginalised groups are fully embedded into EDIP processes, for example the explicit discussion of universal design principles at the business case stage for infrastructure projects.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme has made fair progress in some areas during its fifth year and should be continued into Phase 2. This review has given due consideration to the unique global and internal challenges the programme has faced throughout the course of operation. Improvements can be made to the programme as detailed and recommended in this review. With these changes implemented, the programme is very likely to make a lasting contribution to the island’s economic and social development.

The programme continues to effectively support SHG’s long term sustainable development objectives, and to promote closer alignment between SHG and UKG priorities.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Social and economic development infrastructure investments and utilities delivered to meet short term and medium-term needs with a justifiable return on investment
Output number:		1	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of prioritised social and capital infrastructure investments under the pipeline developed and approved by the Steering Committee	Outer Year Pipeline prioritised and endorsed by EDIP's Programme Board and Steering Committee, indicating priority use of EDIP resources for Phase 2, including consideration of capacity implications	Score: A. Achieved / For Nov 22: HLP has approved strategic priorities for Phase 2 at October 2022 meeting. Political approval will be sought in January 2023. / For Dec 23: EDIP Phase 2 Pipeline approved by Steering Committee in September 2023 and subsequently endorsed by Executive Council in October 2023.
1.2 Share of new and resilient infrastructure spending planned and executed.	Phase 1 funds fully committed. 50% of yearly allocation spent by December 2023	Score: A. Achieved / For Nov 22: Budget allocated for 2022/23: £4.5m / Spend to October 2022: £932k - i.e 20% to date / For Dec 23: Phase 1 funds fully committed. 54% of yearly allocation (£4m) spent by December 2023 (£2.162m) / The forecast spends going forward was £4.338m, however they forecast spend is £3.178
1.3 Ruperts Bay development constructed against a high-quality business case with justifiable benefits.	Completed: CFS steel frame building, PCB yard, PCB steel frame building. Fencing and gates for PCB and CFS installed. Small buildings package contracted and underway. Contract for internal fit-out of PCB and CFS buildings agreed. Field road project contract signed and underway.	Score: B. Outputs moderately did not meet expectation / For Nov 22: CFS yard complete PCB yard commence Steel Frame erection contract awarded with the concrete pads for the PCB building already poured. Transformer purchased and received Lighting purchased and received Footpath (phase 1) complete Sewerage plant installed Fencing Contract awarded Landscaping phase 1 completed / For Dec 23: Steel frame buildings erected. Fencing and gates being manufactured with the supplier delays occurred due to late contract signature. / Field road project is underway and on track. / Internal fitout contract signed in December 2023, following 4-month delay in contract signature. No tenders received for small buildings package following 2 rounds of open procurement. Single supplier identified and negotiations finalised. Contract to be signed in January 2024.
1.4 Water security, solid waste and wastewater feasible solutions being implemented	Strategic case for Water Resource Management Plan completed and presented to the Steering Committee for consideration in phase 2. Design consultancy for Wastewater design project contracted and underway.	Score: A. Achieved / For Nov 22: TORs for the consultancy approved by Project Board. Discussions with AG's Chambers of form of contract ongoing. / For Dec 23: Business Justification Case approved by Steering Committee in October 2023.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Output Area 1 measures EDIP’s success in mobilising investment for key social and economic infrastructure projects on St. Helena, meeting stated short and medium-term priorities of the Government of St. Helena (SHG).

Indicator 1.1: In order to ensure that Phase 2 of EDIP has a pipeline of strategic priorities, planned and approved in preparation for investment, a prioritised list of infrastructure projects has been drafted, presented and approved by the portfolio Steering Committee and endorsed by Executive Council. The indicator’s milestone has been met, as the EDIP Phase 2 Pipeline approved by Steering Committee in September 2023 and subsequently endorsed by Executive Council in October 2023. As such, Indicator 1.1 scores an A.

Indicator 1.2: This indicator measure’s EDIP’s ability to disburse allocated funds for infrastructure projects in St. Helena. Given significant delays to projects over the course of the pandemic, exacerbated by St. Helena’s remoteness. Phase 1 funds fully committed stands at 54% of yearly allocation (£4m) spent by December 2023 (£2.162m). EDIP exceeded that target of 50%, accruing 54% of the financial allocation. Financial management and planning of the programme have some room improvement, the forecast spends going forward was £4.338m, however they forecast now spend is £3.178m. Quite a substantial difference. Further work is required to identify and mitigate risks to delivery schedules at an earlier stage. Indicator 1.2 scores an A.

Indicator 1.3: Rupert’s Bay port was constructed as a means of offloading the material and heavy equipment required in the construction of the St Helena Airport. Historically, the wharf at Jamestown has been used for cargo loading and offloading, where cargo and passengers were ferried from the wharf to ocean-going vessels anchored in James Bay. The mixed use of Jamestown’s wharf (i.e. cargo, passengers, fishing and recreation) limited the benefits to all stakeholders. To capitalise on the economic potential of the Rupert’s Bay port, the Rupert’s Bay development plan was initiated in 2020, aiming to relocate cargo handling from Jamestown wharf to Ruperts, reducing health and safety risks and freeing up use of the Jamestown wharf for non-cargo activities. This indicator measures progress against the planned activities for development of Ruperts. The Steel frame buildings erected. Fencing and gates are being manufactured with the Supplier due to late purchase order issued because of delays in agreeing the contract. The Field Road project is underway and making good progress in line with planned completion. The indicator scores a B, given that the target is mostly reached completed against the plan but there are delays to the fencing and gates and hold ups in the AG chambers.

Indicator 1.4: This indicator measures the progress made by EDIP in supporting development of St. Helena’s water (supply, storage, and treatment) and sanitation infrastructure. The strategic case for separate water systems for Jamestown and Half Tree Hollow has been drafted, the Business Justification Case has been approved by Steering Committee in October 2023. EDIP is also facilitating FCDO support to Connect and SHG’s implementation plan for St. Helena’s Water Resource Management Strategy, which will ensure secure and sustainable water resource utilisation on the island. Given the progress made in this area, Indicator 1.4 scores an A.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No significant changes have been made to this output over the review period. The log frame indicators were mutually agreed based on ambitious but achievable expectations.

Indicator 1.1 was revised to reflect the new governance systems and should be revised to assess the completeness of the priority projects pipeline, including indicative costs and timelines for phase 2, to allow for practical budgets to be allocated each year.

It is recommended that a revision of Indicator 1.2 is considered, to include consideration of the quality of investments and the ability of the allocated funds to be prioritised to projects with the greatest social and economic returns.
Indicator 1.3 was updated to offer more granular detail on projects, perhaps it should include the operational date of the facilities considering it’s this year and perhaps indicate a target to improve strategic planning of procurement and reducing timelines for contract placement.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations from the previous Annual Review for this output area were:

1. A clear, indicatively costed pipeline of priority activities for the remainder of the EDIP programme, including indicative timelines
2. Refresh log frame for Phase 2 to more accurately showcase EDIP objectives and achievements
3. Develop an asset management system to catalogue EDIP funded infrastructure, including recommended maintenance schedule and indicative maintenance costs as part of the standard business case

Recommendations 1 and 2 and 3 have been adopted, the pipeline has a comprehensive list for prioritisation, and exceeds the funding available. Work on indicative maintenance costs and where they are placed as part of the standard business case could be improved, which would be best done as part of a strategic review of maintenance needs across SHG assets (recognising some of this will go beyond the scope of the EDIP programme).

1. As the Ruperts project, and field road project, draw to a conclusion, it is important that a plan for operationalisation and handover is agreed with key stakeholders (i.e. port authorities, customs officials and private importers).
2. Continue to develop an asset management system to catalogue EDIP funded infrastructure, including recommended maintenance schedule and indicative maintenance costs as part of the standard business case

Output Title	Robust and effective project/programme governance to maximise the chance of project success and ensure time, cost and delivery objectives are met.
Output number:		2	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Project/programme management embedded within the public service at a strategic level.	PMO established as a central SHG entity, takes ownership of capacity development and risk management, supports SHG project delivery and acts as a centre of excellence. PMO acts as secretariat for newly established Steering Committee. Information flows between Project board, Programme board and Steering Committee institutionalised.	Score: A. Achieved / PMO established and redesignated as the Programme Management Office rather than Project, reporting directly to Chief Secretary. / The PMO has started to operate as a Centre of Excellence in some areas. It’s worth highlighting that this is something that needs continuous development and can always look to better itself.
2.2 EDIP projects governance arrangements are periodically reviewed.	Breakpoint Review recommendations tracked and actioned, including new joint FCDO-SHG Programme Board and Steering Committee approach to programme/project governance implemented, with mutually agreed terms of references. Process for project approvals, monitoring, and risk escalation agreed.	Score: A. Achieved / Bi-Weekly Reform meetings on BPR action plan in place. Progress on recommendations updated. Recommendations from breakpoint review have been satisfied

Briefly describe the output’s activities and provide supporting narrative for the score.

Output Area 2 measures the success of EDIP in contributing to improvements in infrastructure project governance in St. Helena’s public sector, considering how improvements made through EDIP programme governance can serve as a tent-pole for improvements across project/programme management in SHG.

Output 2.1: FCDO has utilised lessons learnt from the Government of Montserrat to support SHG’s establishment of Programme Management Office (PMO), to be responsible for capital project preparation, evaluation and procurement. As this initiative has led to improvements in project governance (and project delivery) in Montserrat, FCDO has encouraged the adoption of a similar body within SHG. This Output measures the success of EDIP in facilitating and supporting the implementation of such a body, it’s worth recognising the PMO is SHG wide, not just EDIP and benefit are felt across the broader portfolio. To date, PMO established and redesignated as the Programme Management Office rather than Project, reporting directly to Chief Secretary. This indicator scores an A.

Output 2.2: To ensure that project governance arrangements are held to a high standard, and improved upon where necessary, periodic evaluation is required. This indicator measures the Bi-Weekly Reform meetings on BPR action plan in place and is tracked at a higher level at the steering committee level. The progress on the previous reviews recommendations has been updated. This indicator scores an A.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The original intent of the Output, in respect of the Compact, was to develop and design the architecture for a new style of relationship between SHG and UKG, for long term engagement on the management of capital funding to the island, beyond the scope of EDIP. The purpose was to create a partnership fit for the future, which is not based on the legacy model of a recurrent ODA allocation and separate capital fund programmes. Whilst progress has been made, the output area has since been changed – based on recommendations made in the previous Annual Reviews, the output now focuses on improvements to project management and governance rather than a ‘compact’ between SHG and UKG.

Further changes, based on recommendations made in the break point review, including; increased responsibility and resourcing of the PMO, improvements to the onboarding process, and renewed focus on institutionalising MEL processes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations from the previous annual review were:

1. Review and refresh EDIP Governance boards, ensuring that there is an appropriate cross-SHG portfolio level forum
2. Clearly define the proposed responsibilities of the PMO, seek ministerial endorsement for mandate
3. Drive forward the upskilling of the PMO to enable the fulfilment of its mandate
4. Use the refreshed log frame, once agreed, as the foundation for updates in the EDIP programme board
Recommendations 1,2,3 and 4 have been adopted and actioned; there is a refreshed governance board and steering committee in place. There is a Ministerial endorsed mandate, upskilling of the PMO has taken place with a new MELO officer and Oxford based LnD course completed. The refreshed Log frame has been agreed.

Recommendations under this area for the coming year are:

1. Ensure the role and authority of respective EDIP governance bodies is well understood within SHG, including how these bodies interact with Portfolios and Ministerial responsibilities, and ensure that the route for Ministerial input into EDIP governance is well understood by SHG.
2. Ensure that procurement and legal advice is sought from the procurement team and AG’s chambers well in advance, in order to inform procurement and contracting timelines.
3. Using the agreed pipeline, propose a programme of recruitment pre-emptively, in order to ensure necessary capacity is in place to deliver on the agreed ambitions of the pipeline.
4. The logframe and theory of change need to be updated, with the support of the Monitoring, Evaluation and Learning Officer, in improve the relevance and usefulness of these key documents for the programme’s second phase.

Output Title	Well prioritised, high quality, well justified high return social and economic development investments developed
Output number:		3	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of Business Cases with realistic options and quantifiable benefits considered - submitted and approved.	Business Case development and approvals process reviewed and updated, to include greater consideration of potential social and economic benefits. Monitoring, Evaluation and Learning role recruited for, with responsibility for supporting business case development and benefits monitoring. 3 Strategic cases progressed through new process by December 2023	Score: A. Achieved / Business Case process re-defined and agreed with EDIP Programme Board and Steering Committee in September 2023. / Process adopted and applied to projects for Renewable Energy, Water development and EDIP Pipeline. / MELO recruited and on-island from January 2024.
3.2 Reduction in size of investments as a result of improved quality of project development processes	N/A	Score: B. Outputs moderately did not meet expectation / There is no stated ambition and a notable uptick in investments has been noticed. This should point to tighter budget control, better VfM from investments etc. But appreciate it is difficult to measure
3.3 Number of changes made to project proposals as a result of public consultations, to reflect an improvement in the project development processes.	Every project proposal subject to consultation with relevant SHG ministry/portfolio or non-SHG organisation. Microproject proposal process clarified for ministries. EDIP projects are well received by the St Helenian public, and the EDIP 'brand' is clear for all EDIP funded projects.	Score: B. Outputs moderately did not meet expectation / Micro-Project process redefined and aligned against EDIP objectives. Process applied in 2023/24. New projects will be subject to relevant stakeholder consultation. The EDIP/UK branding isn’t always consistently applied in press releases or to the public and could be communicated better.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output Area 3 is predicated on measuring EDIP’s success in ensuring that investments made under the programme are sufficiently prioritised and maximise social and economic benefits for the people of St. Helena.

Output 3.1: measures the extent to which benefits are monitored and quantified at a project level, allowing for improved prioritisation and decision making in future strategies. The milestone this year was for the Business Case process to be re-defined and agreed with EDIP Programme Board and the Steering Committee which happened in September 2023.
The new process was adopted and applied to projects for Renewable Energy, Water development. Additionally, the MELO has been recruited and has been on-island since January 2024. Therefore, the indicator scores an A.

Output 3.2: measures the ability of EDIP, through improvements to project development and management processes, to reduce the size of investments without compromising on scope or quality of investment. There is no stated ambition and a notable uptick in investments has been noticed. As such, the indicator scores a B. This, in part, may be due to an absence of reported successes in comparing initial and final business cases rather than a reflection on the quality of the development process. The scrutiny and use of a tight tender process and competition to drive down prices is key to this Output.

Output 3.3: measures the efforts made by the PMU to ensure that EDIP projects are fully consultative and in the interest of the St Helenian public. The Micro-Project process was redefined and aligned against EDIP objectives. The Process was applied in 2023/24. New projects will be subject to relevant stakeholder consultation, and as a result the indicator scores an B

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No significant changes were made to this output over the review period. The PMO continues to ensure that EDIP projects are subject to public scrutiny and consultation, and progress has been made in formalising benefits monitoring for EDIP investments.

The wording of Indicator 3.1 was changed to indicate the new MELO officer (dues to start in January 2024), the wording should be revised to indicate the benefits and costs at the business case stage of monitoring and evaluating the work.

For Indicator 3.2, greater attention needs to be paid to recording and reporting initial and final business case figures, this is a hard one to measure and perhaps requires changing to better reflect something that can be measured easier.

Indicator 3.3 was revised to better reflect the extent to which EDIP is consultative, rather than the number of revisions needed in business case development. An additional indicator should be included to reflect EDIP’s ambition to ensure the recurrent costs necessitated by capital investments on St Helena are understood and accounted for, including maintenance and replacement budgets and timelines.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations made in the previous Annual Review were:

1. Ensure economic appraisal of proposals for EDIP projects include a robust consideration of recurrent costs, and that these costs are accounted for in SHG recurrent budgets
2. Ensure a changelog is kept for project Business Cases, indicating changes prompted by public consultation and indicating changes to costs (and reasoning)
On recommendation 1 evidence has been seen that recurrent costs are considered. There haven't been evidence that these have been built into recurrent budgets (i.e. for prison extension, R2 roads, Ruperts). On recommendation 2 this has been sufficiently progressed. Recommendations 1 and 2 are strategic directions that will be need considered in building the project pipeline for phase 2 of EDIP.

Recommendations for the coming year:
Further work is needed to ensure that recurrent implications of capital investment projects are accounted for and understood, both by teams responsible for EDIP project delivery and client portfolios within SHG, who will be responsible for maintenance and operations expenses. These should be reflected fully in ‘handover’ documentation, and considered at the business case stage of project development.

Output Title	Increased local capacity through enhanced prog management, assets management, procurement capabilities, systematic stakeholder involvement and climate and environment opportunities.
Output number:		4	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Assets and facilities management system setup and incorporated into O&M plan.	Asset Management Process agreed and institutionalised across relevant ministries in SHG. Central asset register compiles project level registers to inform financial requirements and forecasting	Score: B. Partially Achieved / There is good work taking place and an asset management setup, there are some examples of this being done well but still more to be progress to be desired here
4.2 % of project forecasts being achieved and timely completion of EDIP projects within budget and to specification	Forecasts include a level of risk against spending items to communicate likelihood of spend, and key dependencies. Forecasts updated and presented on a monthly basis at Programme Board meetings. Completed projects come in within 10% tolerance of initial forecast. Cost Effectiveness and/or VfM considerations explicitly included in Business Case templates.	Score: B. Partially Achieved / Forecast now includes a RAG status. Forecasts included with monthly monitoring reports
4.3 Programme management capacity strengthened.	EDIP Programme Team vacant roles recruited for. Capacity/capability gaps identified proactively. EDIP provides training opportunities for SHG senior leadership team on project management and delivery. PMO identifies capacity gaps in programme delivery and implements plan to address these.	Score: B. Partially Achieved. / Recruitment for PM not successful during first round. Re-advertising will commence in January 2024. / FCDO also offering potential support through the CCS framework. / Design Manager recruitment was positive with a candidate identified. / EDIP funded Oxford Leading Strategic Projects Programme, with 7 Officers obtaining pass mark. A further cohort to commence the course in February 2024.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output Area 4 measures the efforts of EDIP to enhance the St Helena Government’s domestic capacity for effectively managing capital investment and infrastructure projects.

Output 4.1: measures the extent to which asset and facilities management systems have been established and incorporated into standard operations and maintenance practices within the St Helena Government. The was no progress reported in the review period scoring an C. This, in part, may be due to an absence of reported successes rather than a reflection on the quality of the development process.

Output 4.2: this indicator measures the accuracy of SHG infrastructure project finance forecasts, and routine the evaluation of the value for money of projects. The ambition for the review period was for forecasts to include a level of risk against spending items to communicate likelihood of spend monthly. The forecast now includes a RAG status. Forecasts are included with monthly monitoring reports achieving a score of A.

Output 4.3: measures the success of EDIP at driving capacity strengthening in the St Helena Government with regards to project management. The milestone for the year was for the EDIP Programme Team vacant roles to be recruited for and any Capacity/capability gaps identified proactively. Recruitment for PM not successful during first round, but the EDIP funded Oxford Leading Strategic Projects Programme concluded with 7 Officers obtaining pass mark. The indicator achieves a score of B.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output area has been revised to better reflect upskilling and capacity development initiatives at the programme and project level, including (but not limited to) EDIP support to the Programme Management Office.

Indicator 4.1 should be reformed more

Indicator 4.2 has removed the percentage of forecasts correct, would be good to restore this figure

Indicator 4.3 has been updated to reflect vacancies, would benefit from connecting the vacancy to the capacity building

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations made in the previous annual review were:

1. EDIP to support the establishment of SHG owned PMO, with defined roles and responsibilities, with staffing needs identified.
2. Appointment of dedicated SHG M&E specialist to support EDIP, as part of PMO
3. SHG to improve timeliness of financial reporting to support effective decision making by project governance groups, supported by a costed timeline of priority projects
Recommendation 1 is in progress; SHG have established the PMO, which is being championed by the Chief Secretary (SHG’s most senior civil servant). Discussions continue regarding how this PMO will be resourced and how it will interface with EDIP (and other) capital investment projects.

Recommendations 2, 3 have progressed well A M&E specialist has been appointed and financial reporting has improved enabling the newly formed governance systems to make effective decisions.

Recommendations for the coming year:

1. EDIP should continue to support capacity, resourcing and learning and development in the PMO, to ensure that it becomes the centre of excellence for project delivery in SHG, and is capable of delivering on SHG’s ambitions.
2. There is a need to agree at an earlier stage the ‘owner/client’ responsible for project operationalisation and benefits realisation, to facilitate a more gradual handover between the EDIP team at the latter stages of project delivery.

## D: VALUE FOR MONEY (1 page)

Achieving value for money on large scale infrastructure investments in the Overseas Territories, or any Small Island Developing States, is difficult, as their small size leads to diseconomies of scale. Challenges include, long supply chains and lead times for international procurement which increase costs and extend project timelines, as well as a limited supplier base on the island which reduces the competitiveness of tenders and capacity to implement projects in parallel.

Large infrastructure projects, such as a port, cost a similar amount regardless of the number of people able to utilise them. In St Helena, where the population is less than 5,000, this inevitably means projects will have a high per-capita cost and lower potential returns on investment. Furthermore, the large projects funded by EDIP (eg Rupert’s wharf and R2) are not ones which will necessarily generate immediate direct economic returns.

However, these projects generate substantial spill over effects and are essential for all forms of economic activity on island, thus facilitating and amplifying the impact of complementary investments which can generate returns. For example, without investment to operationalise Rupert’s Wharf, the benefits of previous investment to construct the wharf will not be realised. Similarly, investment to improve roads networks are essential for maximising the impact of the investment into Rupert’s Wharf. Such positive spill over effects on the broader economic environment are difficult to quantify and attribute but their magnitude is sufficiently large to justify the investment costs.

It is difficult to benchmark infrastructure project costs in remote small island states such as St Helena, including between (for example) St Helena and Montserrat. A solution to this would be to collect as much disaggregated data on design, materials, shipping and labour costs for infrastructure projects in St Helena as possible, to better inform costing and bid evaluation in future projects and ultimately strengthen VfM.

VfM performance compared to the original VfM proposition in the business case

A breakpoint review was undertaken by a team of consultants in September 2022. (link report). The Breakpoint Review indicated that the Business Case’s stated intention to verify VFM through independent quality assurance and validation has not been realised. The £300k evaluation budget has, to date, only been drawn on for funding the breakpoint review, limiting the ability to provide assurances of VFM.

The breakpoint review also noted the potential confusion between cost effectiveness and the guarantee of a rate of return – for EDIP’s purpose, cost effectiveness (that is achieving a set objective with the minimum lifetime costs) is a more appropriate ambition than ‘adequate rate of return’, as specified in the Business Case, which is difficult to evaluate and cannot be guaranteed, especially in critical infrastructure projects that enable an economic environment rather than directly generate revenue.

The breakpoint review positively indicated that EDIP’s Chartered Engineer provided considerable reassurance on the cost-effectiveness of technical solutions and the contracts awarded to implement these. The review also recommended that this should be supplemented by the work of an M&E specialist in future. In January 2024 an M&E specialist was recruited by SHG and has started Work on EDIP.

Evaluating VFM against the Business Case’s VFM Matrix:

Level	Projects Implementation	Achievement and recommendations
Economy	Independent assessment of delivery agent’s procurement and contract management capacity / Evidence of quality indicators of operations and works / Quality factors, such as proposed approach to construction supervision, environmental and social impacts, on-going maintenance, etc. / Local procurement and transport costs where possible / Cost deviations from Budget	Conducted through Breakpoint review, no regular independent assessments / Local procurement is standard, where possible, in all EDIP projects. Some larger projects (e.g. new build prison) necessitate international competition, as exceptions. / The OTPD Infrastructure Adviser is working with EDIP to improve their maintenance plans. A visit is being arranged in March 2024 to specifically work on improving Maintenance and Asset management plans / EDIP Projects are generally delivered on budget, with the exception of instances where project scope has increased.
Efficiency	% of payments that are linked to outputs / transparent and competitive procurement / Standardization of procurement, contracts, and performance standards / Implementation time vs. original schedule	Payments are made based on delivery of milestones / Local and international procurement is transparent and competitive, although the limited size of domestic supplier base does constrain the competitiveness of any local procurement. / Procurement and contracts are standardised, with scope to flex with specific needs / Project delivery times regularly overrun, due to supply chain issues and due to labour constraints
Effectiveness	Amount of construction risk being taken on by contractor / Service Quality (e.g. households connected, outage days, etc). / Revenue collection	Little risk is taken on by contractors, ultimately resting with SHG / EDIP delivered infrastructure is generally of a high quality and receives positive public feedback. / No EDIP infrastructure built to date generates revenue directly. / EDIP funded infrastructure is generally of high quality. Post-project reviews are required for further assurance
Equity	All new build includes a professional assessment and implementation of disabled access for a range of disabilities; and includes consultation with disabled and user groups. / Access by minority groups / Gender and ethnicity targets for SME funds and other individually accrued benefits / Gender and beneficiary analysis included in prioritisation/choice of infrastructure/approval discussions	Consultations with user groups are carried out routinely, and new builds are assessed by EDIP’s chartered engineer, although explicit reports on these are not produced. / Universal access is a design consideration at business case stage of project proposals / There are no gender/ethnicity targets in place or measured / Beneficiary analysis is not explicitly considered in project prioritisation or approvals process,but remains an underlying factor. This needs to be brought out more explicitly in future years. / To ensure the Programme Board was up to date on safeguarding, a safeguarding note was produced for the EDIP Programme Board with two guidance documents for FCDO implementation partners regarding approach to safeguarding and expectations with regard to safeguarding in project implementation. The note also detailed where safeguarding concerning should be reported.

Assessment of whether the programme continues to represent value for money

Quantifying the impact of EDIP is difficult, anecdotal and qualitative evidence suggests that EDIP investments are essential for enabling broader economic activity. Given the lack of revenue generating projects, the VfM of projects can only be quantitatively assessed through a cost-effectiveness approach, to evaluate the extent to which EDIP projects minimise costs associated with achieving specific objectives. In January 2024 an M&E specialist was recruited by SHG. He has started work on options for benefits monitoring and to deliver a road map. This will feed into the evidence to show value for money

 :

E: RISK [½ to 1 page]

The St Helena Government programme risk appetite for EDIP is Moderate and is overall in line with FCDO’s EDIP risk register, which is also Moderate.

As of January 2024, SHG’s main emerging EDIP risk areas are:
1. Project costs increase because of global crises, resulting in less production at high costs
2. Unable to spend budget allocated for this Financial Year
3. The Project Management Office (PMO) fails to sustainably build project management and delivery capability in SHG. EDIP fails to contribute to capacity building, resulting work falling on a small number of SHG officials.
4. Growing (and poorly defined) maintenance needs and limited funds available for new investments.
SHG have mitigating measures that are in place for these risks and are supported by FCDO. Elements of these risks (high materials and shipping costs, irregular shipping schedules) are external to SHG and whilst the impacts can be minimized, the risks cannot be removed entirely. The PMU (Project Management Unit) continues to work to mitigate these risks with FCDO support.

The Project Management Unit submits a monthly monitoring workbook, which includes a tab for risks. The Monthly Programme Review Group, which has now been replaced with a monthly EDIP Programme Board discuss and scrutinise the workbook, providing the PMU with a challenge function and testing for any emerging risks. It has been recently agreed by the Programme Board to add Risk as a standing item on the agenda, to ensure all emerging risks are fully discussed and to decide whether they should be escalated to the Steering Board. Safeguarding is discussed regularly at the Programme Board. To enhance the Programme Board’s understanding of Safeguarding issues a guidance note will be provided to them followed by a visit by OTPD Safeguarding adviser. The FCDO EDIP programme risk register is reviewed quarterly. It was last reviewed and amended in November 2023. None of these risks have escalated into issues but are being regularly monitored.

The main risks for FCDO are:
1. EDIP funded interventions fail to implement proper controls, causing harm to the people or the environment of St Helena.
2. The Project Management Office (PMO) fails to sustainably build project management and delivery capability in SHG, EDIP fails to contribute to capacity building, dependence on small numbers of SHG officials risks loss of institutional memory
3. New (and existing) infrastructure does not have adequate provision for maintenance, leading to reduced operational life and exposure to health and safety and reputational issues.
4. Failures in SHG's procurement practices resulting in resources getting wasted, which in turn reduces the ability of FCDO to continue with the programmes as planned

Measures to mitigate these risks are in place in partnership with SHG.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

All projects under EDIP fall under authority and oversight of the joint FCDO-SHG governance structure, comprised of an EDIP Programme Board and a strategic level Steering Committee. This has resulted in more cohesive and strategic approach, which has helped to strengthen SHG and UKG engagement and collaboration to foster a greater sense of partnership. The steering committee receives Business Cases for review after they have been cleared by the Programme Board, which sits at the technical level.

Programme monitoring is conducted by the PMO and provides a monthly programme monitoring report to its Board and UKG. Once received, a Programme Board meeting takes place to discuss the report. The quality of reporting is generally good and includes a narrative around progress on each project including timeline, actual/projected spend, activity log, risk log, along with a financial summary for the year. In addition to this, the PMO and FCDO programme team meet fortnightly to discuss in more detail, any issues arising with projects, delays, forecasting/budgeting etc.

The SRO has visited St Helena several times, conducting site visits to historical and current EDIP projects, and holding conversations with the PMO on project management, governance and resourcing.

The programme was allocated a budget of £4m for 2023/24. The total expenditure 2023/24 reached 78% of the allocated budget. The below table indicates the up-to-date allocation and spend figures for each financial year.

	Year	Budget	Spend	Percentage of allocation spent
FY19	2018/19	39,188.29	39,188.29
FY20	2019/20	3,500,000.00	2,751,114.92	79%
FY21	2020/21	3,200,000.00	2,244,786.24	70%
FY22	2021/22	3,980,000.00	2,867,013.95	72%
FY23	2022/23	3,800,000.00	2,582,732.98	68%
FY24	2023/24	4,000,000.00	3,136531.08	78%
		18,519,188.29	13,621,367.46	74%

The programme continues to struggle to spend its full allocation, year on year, this is due to several factors. One key constraint is the lack of resources in the PMO and SHG procurement departments. The other purchasing goods - the small population and access constraints mean there are few economies of scale in providing infrastructure improvements. SHG relies on importing all materials and equipment required for construction and maintenance. This inevitably leads to higher costs and affects the speed of construction. Despite these challenges, achieving VFM remains a priority and mitigating actions to minimise risks will continue to be put in place to improve the ability to deliver infrastructure projects at pace.

Over the last year the EDIP team have made notable improvements in early forecasting, indicating items at risk and where spend is confirmed, enabling FCDO to reallocate to other priorities across the portfolio at an earlier stage. The team should be commended for the collegiate spirit with which this is approached, and on the improvements made to reporting.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

The programme is governed by monthly programme boards, into which monitoring information is fed by individual project boards. FCDO staff attend the programme boards and many of the project boards. Project and programmatic decisions are made in these boards, on the basis of value for money, risk, and alignment with programme objectives, with evidence provided through business cases and formal project proposals.

During the implementation of specific projects (i.e. those with significant direct impact on local communities), quarterly beneficiary feedback sessions are held by SHG’s EDIP team, in order to understand the impacts of ongoing works, and to address any issues that may arise.

This annual review has been conducted jointly by FCDO staff based on St Helena, in the Governors office, and UK based staff, with inputs from the EDIP project team on Logframe achievements. The review has been shared with SHG prior to finalisation to ensure accuracy and fairness.

In the past year, and based on recommendations made previously, a Monitoring, Evaluation and Learning Officer (MELO) has been recruited, and is already making progress on further formalising and institutionalising good practice on MEL within the programme, and more widely across SHG’s capital programme teams.

Date of last narrative financial report	February 2024	Date of last audited annual statement	Jan 2024 (2022/23 AAS)