## Annual Review Template – July 2021

Title: Economic Development Investment Programme (EDIP) – St Helena
Programme Value £ (full life): £30m		Review date: 30/08/2021
Programme Code: 300714	AMP start date: 30/07/18	AMP end date: 31/07/26

Summary of Programme Performance
Year	2020	2021
Overall Output Score	A	B
Risk Rating	Mod	Mod

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300714/documents
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300714/documents

A. SUMMARY AND OVERVIEW

Description of programme

The St Helena Economic Development Investment Programme (EDIP) was approved in March 2019 and runs until July 2026. The programme’s purpose is to support economic development in St Helena through enhanced dialogue on policy reforms, infrastructure development, and through harnessing investment opportunities through Public Private Partnerships. The FCDO is providing assistance to St Helena Government (SHG) of up to £30m, split into two phases of £15m each with Phase-1 spread over the first four years, followed by a break point to establish the basis for approval of Phase-2 £15m for the following three years. The implementing partner is SHG, managing the programme through a Project Management Unit (PMU) on the island.

St Helena is one of the world’s most remote inhabited islands with limited capacity to support self-sustaining economic growth. This has meant its economic development remains highly constrained by barriers like economy of scale and high unit costs, insufficient resources (physical, human, business, and financial), resulting in a low capacity to drive forward change effectively. The enduring impacts of the COVID-19 pandemic (St Helena had restricted access to the island for 18 months) are only likely to be known in the years ahead once the global economy and international tourism recovers to pre-pandemic levels. Despite the island being closed to tourism for 6 months during 2020, its domestic economy and consumer spending continued as normal. Apart from a few Covid 19 cases (i.e. individuals tested positive on arrival and subsequently quarantined), the island has remained COVID-19 free.

The pandemic has had a major impact on UK economy, forcing the UK government to take tough but necessary decisions. It was announced in November 2020 that the UK moves to a target of spending 0.5% from 0.7% of its GNI as Official Development Assistance (ODA) in 2021 - which is the main source of funding for St Helena through Financial and Capital assistance.

The UK remains a world leader in international development, not only through the impact of these financial allocations but also through the creation of the FCDO (merging the FCO and DFID), integrating diplomacy and development to deliver greater impact. We will return to our commitment to spend 0.7% of gross national income on ODA when the fiscal situation allows.

Summary supporting narrative for the overall score in this review:

The programme scored a B this year overall. It is partially meeting its pre-agreed milestones, and while it continues to achieve good results, the programme needs to adapt and plan better for it to achieve its full potential.

The programme has to provide greater value for money (VfM). However, given the social and economic changes caused by global behavioural shifts resulting from the global pandemic, i.e. reduction and limitations on Tourism numbers and ability to travel and trade with the Island, with the growing concerns to gaps within social and critical infrastructure, it is recommended that a pivot to address key critical infrastructure projects would help to maximise the impact of further capital investments on St Helena.

Other remedial steps this review recommends include a governance review of programme structure, and consideration of how monitoring and evaluation (M&E) expertise can be brought in to enhance the programme.

The absence of regular monitoring of Logframe outputs and yearly indicators was a common issue this review identified across the programme, and is an area that must be improved upon in the coming year for further funding to be guaranteed.

As well as assessing milestones achieved, this review has taken into account the extraordinary effort and work ethic of the core programme delivery team within SHG, the Programme Management Unit (PMU). EDIP is not the only capital fund programme managed by the two-person PMU + the four-person contracted technical team. Their achievements in the context of the confluence of a unique set of global (ongoing and developing C-19 restrictions) and internal (change of modal of island government and major public service institutional reforms) challenges should be emphasised, and are recognised at the start of this review. It should also be noted the dramatic impact

On the output relating to ensuring social and economic development infrastructure investments meet needs and deliver a justifiable return on investment (30% weighting), one of the four sub-indicators was achieved and two were partially met. The final sub-indicator, relating to the approval of business case for wastewater treatment in Half-Tree Hollow and Jamestown, was not achieved, but this was a result of discrepancies in the ordinance relating to sewerage.

On the output relating to the implementation of economic development reforms consistently with the long-term programme vision (15% weighting), neither of the two sub-indicators were met. Some useful reforms have been made, but the high level of ambition of the indicator milestones, when combined with the impact of the FCDO merger, meant that neither could be progressed.

On the output relating to well prioritised, high quality, justifiable high returns on social and economic development investments (30% weighting), one indicator exceeded expectations, one was achieved, and one was partially met. The concerted effort made by the PMU to increase the number of public consultations, and increase public engagement with EDIP’s projects overall, are a notable achievement of the programme this year.

On the final output relating to increasing local capacity through (inter alia) enhanced programme and asset management (25% weighting), one indicator was achieved, one was partially met, and one was not achieved.

This year’s Annual Review has been light touch, carried out by a small internal team. In addition, the lack of Social Development and Governance advisory support within OTD has been noticed. The current constraints on international travel have further limited the review team’s ability to engage and support the lead reviewer on island. A Quality Assurer has been appointed, to ensure the process was carried out in a balanced way and to sense check the review’s findings.

Overall value for money

Achieving value for money on large scale infrastructure investments in the Overseas Territories, or any Small Island Developing States, is difficult, as their size makes it almost impossible to achieve economies of scale.

Large infrastructure projects, such as a port, cost a similar amount regardless of the number of people able to utilise them. In St Helena, where the population is less than 5,000, this inevitably means projects will have a high per-capita cost and lower potential returns on investment. Furthermore, the large projects funded by EDIP (eg Rupert’s wharf and R2) are not ones which will necessarily generate immediate direct economic returns. Therefore, at face value, the business cases do not offer good value for money.

However, these projects are arguably necessary for past and future investments to generate returns. For example, without investment to operationalise Rupert’s Wharf, the benefits of previous investment to construct the wharf will not be realised. Similarly, investment to improve the road may not generate significant direct economic returns, but if the road between Rupert’s and Jamestown were to degrade and become unusable, this would severely limit the returns from the Rupert’s investment.

Therefore, the investments are arguably justifiable despite having lower direct returns on the grounds that they are essential to enable the wider economic development of the island. Increased data collection on immediate impacts of investments would be beneficial in justifying value for money, however, it is also recognised that monitoring of benefits can be time-consuming and resource intensive.
Major lessons and recommendations for the year ahead:

Lessons Learned
Comprehensive lessons learned for each Output are detailed in Section C below. The principal and strategic lessons this review has highlighted are:
1. As noted above, and in last year’s review, regular monitoring of performance against Logframe Indicators by PMU has been challenging and progress against a number of Output Indicators missed. Delays in confirmation from UKG of budget allocations made it difficult for PMU to prioritise and progress agreed projects. This has had a knock-on effect on PMU’s ability to deliver in year 2. Logframe indicators should have been revisited and revised at the quarterly or mid-year point to make sure programme progress could be adequately captured by this review. The Logframe has not been revisited since the last annual review, and this review therefore finds that progress has been difficult to measure against Output Indicators previously stipulated in the Logframe. Priority action within the next quarter should be to update the Logframe and agree a new / revised set of indicators against the various milestones.
2. Throughout the last year, agenda setting and decision-making by the three key governance review groups - High Level Panel (HLP), Programme Review Group (PRG), and the programme planning group - remained mostly reactive. This has been exacerbated by greater demands on the PMU than its resources can meet. This is in part due to quick turnaround of both meetings prior to decisions being required. A shift needs to be made towards a more proactive and strategic approach to business through the establishment of a central Programme Management Office. It may well be that the current three tiers of governance in place could benefit from some restructuring for a programme of EDIPs unique nature and to incorporate the new PMO setup
3. Reactive decision-making around investment decisions has not aided the long-term, strategic vision of the programme. There is clear duplication of effort and membership across the programme’s key governance groups, with a lack of clarity around division of roles and responsibilities of these forums. For example, HLP, which is the upper tier group with responsibility for articulating a strategic vision for the programme and monitoring overall performance, is regularly drawn into operational and working level decisions. The ToRs of each of the governance tiers would benefit from a redrafted with clear roles, responsibilities and interconnection detailed.
4. The programme has placed greater emphasis on economic development projects. EDIP was approved to deliver economic development investments, and over the last two years the investments that have been approved largely relating to infrastructure base for the island. The economic case for the programme has subsequently altered due to the effects of the global pandemic, which has severely limited the levels of tourism, travel, and trade to the Island. As a result, the programme will unlikely see its desired impact realised in the short-term. To help counterbalance the programme’s desired impacts, growing concerns regarding gaps in St Helena’s social and critical infrastructure must be addressed as a priority. EDIP must pivot towards social and critical infrastructure investments for the remainder of the programme’s life.
5. The relationship between SHG as delivery agent and beneficiary, and the FCDO as sponsor has over the past year encountered challenges, which have in themselves hindered specific action on certain deliverables. This is partly a feature of the relationship with FCDO in OTs. The combination of self-determination and self-governance of the OTs and the assurances the construct surrounding the ODA management system requirements. These have been largely addressed in the last six months by the Development Attaché on island, but it is key that similar discrepancies of overarching direction and objectives do not re-emerge as progress is made and teams and individuals change.
6. This review concludes that the Compact, specified in Output 2, which is designed to establish a model for a new style of relationship between SHG and UKG, cannot be sufficiently addressed or delivered by EDIP alone, this was acknowledge by last year’s AR recommendations. The Compact is undoubtedly a fundamental part of the success of long-term economic investment in St Helena, but it can only be properly progressed through further higher-level discussions between SHG and UKG in the coming years before its outline could be defined. It is the opinion of this review that the compact be removed in its current formation, [or should be reviewed entering into the next year.]
7. Finally, the lack of in-person UKG visits to St Helena continues to be a limitation on gathering the full assurances required for EDIP. As the effects of the pandemic continue to be felt across financial years, delivery and fiduciary risks may rise. EDIP is designed to provide a greater level of autonomy for the PMU, government officials, and political leaders, but this needs to be supplemented with the right level of oversight. This has been somewhat mitigated having FCDO’s Development Attaché in post for the last 6 months.
Recommendations:
Specific recommendations for each Output are outlined in detail in Section C.
The principal, strategic recommendations this review wishes to make are:
1. Within the next year, Logframe Output indicators and milestones need to be comprehensively reviewed by FCDO and PMU and endorsed at the HLP. Once reviewed and agreed, the PMU should regularly (preferably quarterly) monitor and report progress of programme Logframe outputs to Programme Review Group (PRG);
2. PMU is enabled to engage an M&E specialist for setting up an Impact Monitoring System and secure the necessary administrative support to monitoring the Logframe indicators and Output milestones;
3. PMU should establish and own a Programme Management Office function to make the shift away from reactive agenda setting and decision-making, towards a proactive and strategic style of business by the programme’s three governance groups;
4. Within the next year, a governance review should be conducted (jointly by PMU and FCDO) to establish a clear division of responsibilities between HLP, PRG, and the programme planning group;
5. Further investment in economic development infrastructure should be delayed to allow existing projects to establish themselves so their impact can be properly determined in the unique context of the pandemic;
6. EDIP should pivot to investing in social and critical infrastructure projects (e.g. education and health infrastructure) for the remainder of the programme’s life, drawing on resources like the John Cox Report to ensure prioritised pipeline projects are aligned to St Helena’s long term sustainable development goals;
7. The Compact should be removed as an EDIP Output and instead progressed by a country board, to enable a more strategic discussion about the future SHG/UKG relationship;
8. As soon as global conditions safely allow annual visits to St Helena by UKG should be resumed;
9. Within the next year, a review of EDIP risk reporting processes should be conducted (jointly by PMU and UKG) to provide clarity for governance groups on the level project and programme risk each is able to accept, ignore, or mitigate. EDIP would benefit from empowering PRG and Planning Meeting to deal with certain risks and issues, escalating them to the next governance group only when appropriate. This would ensure ownership of programme delivery by technical and programme teams, while supporting HLP in addressing only the highest rated/emerging risks and issues.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case:

The overall logic of the programme sets out that the outputs which are primarily social and economic infrastructure investments (with some enhanced dialogue, policy reforms and capacity development), in order to lead to a stated outcome of “Adequate resilient well maintained social economic infrastructure and utilities.”

(Image 1. EDIP ToC)

This infrastructure outcome is then intended to lead to an impact that “Increased attractiveness and economic development opportunities for Sustainable Development in St Helena”. The programme has assumed that improved quality of decision making and strengthened investment design and business case development alongside a targeted set of investment will enhance the benefits to economic development as compared to previous capital programmes.

The Logframe was finalised and agreed relativity late during the first year of delivery (2019/2020). Since agreed, there have been no changes to output, outcome, or impact indicators. This has limited the ability to show the successes of the programme, which has adapted and flexed to the uncertainty created by the global pandemic.

The pandemic continues to generate ambiguity around some key assumptions in the theory of change, for example limitations on travel and trade have impacted the current long-term vision for the island as an attractive island with strong economic development opportunities. The impact of EDIP and the pandemic on the growth of the island, prevents the programme from being able to making a clear statement on the economic viability of the island at this time.

St Helena has reopened its borders. However, regular commercial flights to the island will not start before April 2022, and it remains uncertain when they will return to pre-pandemic levels of operation. SHG has continued to enable a flight corridor to the UK. This arrangement has been revised due to the recent demand, and the schedule is to move to a more regular service (3-4 weeks) beginning September 2021 until the end of March 2022. This will support required resourcing and expertise being able to reach and conduct activity on island once again.

By design, the programme will indirectly benefit every person on the island due to the range of projects prioritised. The direct benefits are yet to be fully planned and monitored, as is the full monitoring and evaluation plan for the programme. This presents a risk to the programme going forward and to correctly assessing the ToC.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme broadly remains on track to contribute to the expected outcomes and impact. The corrective steps outlined in this review will need to be implemented in the coming year in order to ensure the programme provides VfM and remains on course.

The ability of the programme to impact the island’s economic development has been constrained by the global effects of the pandemic. Global tourism demand continues to be dramatically affected, and a sustainable long-term recovery path remains uncertain, particularly for many African states, including South Africa which remains a key partner and originator of a high proportion of visitors to St Helena. The economic returns of the programme will be lower if visitor numbers to St Helena do not return to the pre-pandemic level and the growth path assumed in the business case. The current outlook suggests it is extremely unlikely that this assumption will be borne out in the short term.

The programme will likely see less than expected returns and the programme team should continue to monitor tourism demand on reopening services in island and note the risk that return on investment in terms of additional tourism revenue may be lower (either through delayed return to previous growth levels or a lower growth rate). The programme may need to pivot to more social infrastructure development requirements in the coming years, as the underpinning economic assumptions aren’t as strong as when the initial business case/ToC was developed.

The projects to be implemented this year (R2, Rupert’s Bay) will continue to have a stimulating effect on the local economy which will promote job retention in the local labour market. However, this is unlikely to have a tangible effect on GDP in the short term. Over the coming financial year, the economic impact of EDIP projects will not have as significant an impact as the full return of the tourism industry on island. However, the improvements to infrastructure base, reduce health and safety risks to the island through R2, Rockfall, and Rupert’s projects will contribute greatly to the social/human development then solely economic. Even so EDIP has continued to promote professionalisation and capacity building of local industry. And improve the infrastructure base, reduce health and safety risks to the island – R2 and Rockfall, and Rupert’s all contribute more to that then to economic development. To capture this Logframe indicators and milestones should incorporate the PMU and FCDO team’s efforts and consequences upon professionalisation in local industry to date.

Residents are included in extensive public engagements driven by the PMU across all districts of the island and subsequently through their elected representatives who are involved at the planning permission stage, sometimes earlier. The PMU’s outreach programme via radio, online and through the local newspaper is effectively tying to communicate the programme progress to the public,

Gender, mental wellbeing, minority groups, and visible and invisible disabilities are recognised, acknowledged, and supported in the programme teams. Women are well represented at all levels in the programme team and governance structure.

In the past year it has been agreed that phase 1 of the programme will be spread across four years, instead of three, extending the life of EDIP by one year. Phase 2 of the programme will remain over three years, concluding ultimately in 2026.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio:

The programme has made good progress in some areas during an extremely challenging second year, and should be continued. This review has given due consideration to the unique global and internal challenges the programme has faced in the past year (namely the lasting impact of the pandemic, and the creation of the FCDO). Improvements need to be made to the programme as detailed and recommended in this review. With these changes implemented, the programme is very likely to make a lasting contribution to the island’s economic and social development.

The issues around the governance of the programme identified by this review should be addressed in order to strengthen EDIP efficiency – these are detailed in the sections and recommendations below. However, the current structure has not had a significant impact on the programme’s ability to deliver effectively in many areas, improvements are advised.

The programme continues to effectively support SHG’s long term sustainable development objectives, and to promote closer alignment between SHG and UKG priorities.

## C. DETAILED OUTPUT SCORING

## C. DETAILED OUTPUT 1 SCORING

Output Title	Social and economic development infrastructure investments and utilities delivered to meet short and medium term needs with a justifiable return on investment.
Output number:		1	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of prioritised social and capital infrastructure investments under the pipeline developed and approved by the HLP	Business cases for prioritised investments for year 2 in plan 75% approved by HLP	Score: A. Achieved: Two presented and two recommended by HLP for approval by Executive Council.
1.2 Share of new and resilient infrastructure spending planned and executed.	Spend target met	Score: B. Partially Achieved: £3.2m allocated (FY 20/21). Actual spend - £2.42m (FY 20/21
1.3 Ruperts Bay development constructed against a high-quality business case with justifiable benefits.	Rupert's master plan approved. Phase 1 of operationalising wharf 75% complete.	Score: B. Partially Achieved: Masterplan for Rupert’s has been approved for 2021
1.4 Water security, solid waste and wastewater feasible solutions being implemented	Half-Tree-Hollow and Jamestown wastewater treatment BC approved by HLP	Score C. Not Achieved:: Business Case not approved as it was not ready for presentation to HLP.

Briefly describe the output’s activities, and provide supporting narrative for the score:

Output 1.1: There has not been a formalised list of year-on-year projects, which has made year 2’s expected milestone indicator 1.1 (75% of pipelined projects would receive HLP approval by July 2021) difficult to assess.

Due to EDIP’s first year low spend [19/20], it was agreed that the programme will be delivered across 4 years instead of 3, with no funding extension. In practical terms, this means the £15 million in phase 1 will be spread across the 4 years [19/20 to 22/23]. This required HLP, with PMU and FCDO, to reprioritise those projects that could be progressed within this financial year’s funding allocation. A new prioritised list was created May 2021, which featured and recommended two projects: the Rupert’s wharf project and R2 (Field Road and Side Path Road Rehabilitation Project). Work has commenced and is scheduled to be completed 22/23.

According to programme governance, this year the Rupert’s and R2 projects were presented to High Level Panel (HLP) and recommended for political approval, granted in September and December 2020 respectively. A previously prioritised list of projects covering phase 1, which have been progressed during year 2 of this programme are presented in the table below with corresponding final spend amounts.

Projects Progressed in Year 2 / [Jul 20 – Jul 21]	Expenditure / [April 20 – March 21]
Programme Development Support	£316,995.60
Rockfall Protection	£1,342,716.90
Judicial Services Relocation – Phase 1	£63,563.49
Judicial Services Relocation – Phase 2	£11,033.37
Ruperts Cargo Handling Development	£474,852.93
Water	£71,181.05
R2 – Field Road & Side Path Road	£19,022.32
Micro Projects	£122,103.12
Jamestown Development	£97.71
£2,421,566.49

Output 1.2: SHG PMU advised FCDO on 9 March 2021 that they would not spend £400k of the original £3.2m allocation, leaving £2.8m as a revised budget for 2020-21. This notification, in the last month of the financial year, came too late for funds to be reallocated and properly processed by FCDO. Furthermore, at year end, there was an underspend of £500k as a result of the impact of Covid-19 on suppliers. This left a total combined underspend of £900k.

The impacts of the pandemic on international suppliers, and residual effects on programme delivery, are clearly significant. However, very late updates to financial information is not adequate financial management for a programme of this size. Further support for the PMU is required to avoid a recurrence of this error, and work is being done to address this (with the arrival of a new chartered engineer to support more accurate monthly and quarterly reporting). A clear deadline must be established in future years by which funds should be returned to FCDO.

Output 1.3: Given land constraints within Rupert’s Bay (a deep, narrow rock valley with limited useable space), the development of a comprehensive master plan for Rupert’s valley project and the operationalising of 75% of the wharf has not been progressed to the expected milestone (July 2021). So far, the master plan has been approved for 2021, and is scheduled to be married into the land control plan, which is owned by the Chief Planning Officer. This will be complete alongside EDIP activity within 2021-22. The significant slippage on this indicator originates in challenges relating to land swapping agreements between SHG and private owners. This process is beyond EDIP’s control, being driven instead by SHG’s Land Division. A success within the context of this indicator has been the team’s ongoing engagement with the Rupert’s Bay community, continuing to provide information and guidance, and to assuage fears and opposition to the planned development. This Review has seen the impact of this investment, and believes it will be an asset to programme delivery in the years to come.

Output 1.4: The milestone of an approved business case with HLP endorsement was not achieved in full this year. This milestone was not possible due to factors outside of EDIP’s control, specifically the Connect SH proposal for a combined water system which received planning permission in 2016, and which has since lapsed. SHG PMU explored options for separating the stormwater from wastewater in Jamestown and Half Tree Hollow, but found amendments to the water ordnance were necessary to reflect Connect SH’s responsibilities for waste and surface water. An ordnance change is being processed by the Attorney General’s chambers, following ENRC approval. Connect and SHG are not in agreement on this change. PMU have investigated a deep bore drilling exploration to support the required water security needs of Jamestown and Half Tree Hollow. This work will continue in 2021-22.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year:

Economy: The cost of the port will be less than originally budgeted, partially due to changes in the scope and design options, but also due to efforts taken to ensure good value contracts. Predominately local contractors are being proposed for the port construction: which will generate direct savings and would be beneficial for local employment and the wider economy.

Efficiency: Splitting the Rupert’s development into two phases ensures that the aspect of the project which will confer the largest benefit, operationalising the port, is prioritised over other aspects. The process of undertaking consultations and doing due-diligence slowed down the project. This was largely unavoidable, particularly as St Helena planning authorities are not used to approving projects of this size, although it could be worth examining whether this process could be made more efficient in the future.

Effectiveness: Both Rupert’s and R2 are essential capital projects: without these necessary infrastructure improvements, further capital projects to enhance St Helena’s development either cannot take place or will not be as beneficial. Therefore, these projects have significant indirect economic benefit and are consistent with the aims of EDIP and wider economic development plans for the island. The return on investment is justifiable and they represent value for money.

Equity: Although extensive consultations with the community have slowed down the process, these are essential to ensuring views of effected groups are considered.

Describe any changes to this output during the past year, and any planned changes as a result of this review:

The log frame output indicators and milestones have not reflected significant changes to the workplan as a result of reprioritisation, funding restructuring, water ordnance blockage, and Rupert’s land allocation issues. Significant progress has been made this year on a new business case model. This has gained support across the board, and allowed for projects to be presented on their strategic case first, followed by economic, and financial/project management cases. This has allowed SHG PMU to develop business cases in conjunction with FCDO advisory support, helping to avoid surprise issues arising at late stages, and has helped to strengthen working relationships between the teams.

Progress has been made to date. However, there are significant and growing concerns about gaps in St Helena’s social and critical infrastructure. The economic case for the programme has altered due to the effects of the global pandemic, which has limited the levels of tourism, travel, and trade to the Island, reducing the anticipated returns of the programme’s activities. It is likely the programme will not see its desired impact realised in the short-term.

Therefore, it is recommended that EDIP allows the current economic development programmes to establish themselves and monitors their effects, while revisiting the John Cox Report to reset the prioritised social and critical infrastructure investments currently in the pipeline for the remainder of Phase 1; and subsequently EDIP should pivot to social and critical infrastructure programmes for Phase 2.

Further resource support for the PMU is required in order to enhance accurate and timely financial reporting, which will help to avoid a recurrence of late reporting of underspends and the return of funds (output 1.2).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead:

Key lessons from last year’s AR have been learned and implemented:
1. Revisions to the business case model and process;
2. Understanding of the Programme Review Group (PRG) and HLP roles and approval structure continues to strengthen and develop.
Key lessons to take from this year’s AR are:
1. Not having a clear, prioritised list of year-on-year projects delays implementation significantly;
2. Late returning of funds in the month of the end of the financial year does not offer assurance that public money is being spent correctly and responsibly. FCDO requires 3-6 months’ notice of anticipated underspends to allow funds to be reallocated to other priorities;
3. Absence of monitoring of log frame indicators results in out-of-date milestones, presenting challenges to ability of AR to accurately benchmark programme success.
Recommendations from this AR are:

1. Prioritised list of year-on-year projects to support in-parallel development of business cases, to significantly improve future planning and prioritisation by HLP;
2. Update and monitor log frame indicators through PRG, to ensure milestones are current, practical, and ambitious;
3. EDIP should allow current economic development infrastructure projects to establish themselves before any further projects of this kind are agreed;
4. EDIP should reset pipeline programmes for Phase 2 to pivot towards social/critical infrastructure projects, revisiting the John Cox Report to inform this process.
## C. DETAILED OUTPUT 2 SCORING

Output Title	Key reforms for economic development implemented consistent with new long-term vision.
Output number:		2	Output Score:	C
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Compact set up and implemented.	Compact agreed, and is agreed as the platform for high level dialogue between UKG and SHG.	Score: C. Not Achieved:
2.2 Number of reforms meeting their target milestones as set out in Compact agreement	4 critical reform areas have new policies changed and implemented: financial management; political reform; policy environment; growth.	Score: C. Not Achieved:

Briefly describe the output’s activities, and provide supporting narrative for the score:

The original intent of the Output, in respect of the Compact, was to develop and design the architecture for a new style of relationship between SHG and UKG, for long term engagement on the management of capital funding to the island, beyond the scope of EDIP. The purpose was to create a partnership fit for the future, which is not based on the legacy model of a recurrent ODA allocation and separate capital fund programmes.

Last year’s AR noted that year 2 milestones were notably more ambitious in its intent to agree the Compact, particularly given the influence had on discussions by the merger of the FCO and DFID, the impact of the pandemic on capacity, and SHG restructuring. Consequently, the Output indicators 2.1 and 2.2 have not been progressed over the past year, and no attempt to amend or correct the indicator milestones or wider output has been made. This Output has not been achieved.

It is worth noting, however, that a series of reforms have been implemented. SHG has conducted a substantial administrative restructure (Fit for the Future Programme), which ensures the government administration is aligned to the new Ministerial system. Further steps will be taken following the outcome of the October 2021 election, which will ensure further alignment of policy with long term vision.

With regards to EDIP, constructive progress has been made. Regular HLP meetings are an established part of the programme’s governance, and have been successful in strengthening programme management and oversight. They have added impetus, providing momentum on decisions. Some concerns have been raised as to whether the pace of business case development and approvals is putting undue pressure on SHG and UKG teams. The re-establishment of a development focused FCDO presence on the island, in the Development Attaché, has helped to mitigate this pressure by enabling closer engagement between the teams, prior to HLP. This has enabled a more constructive flow of information, supporting, and refining the business case development process. This AR makes recommendations for further work in this area.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year:

No significant immediate value for money considerations on the sub-indicators as they were not achieved. However, the infrastructure projects do appear to be widely consistent with the long term economic development of the island, as discussed in other sections.

Describe any changes to this output during the past year, and any planned changes as a result of this review:

Furthering the Compact at a high level has not been a priority for UKG due to structural changes involved in the creation of the FCDO and shortage of Governance Advisory support within OTD. When combined with Covid-19’s impact on SHG operations and budgetary constraints across UKG, the Output has not been progressed effectively .

There has been no change to Output indicators during the past year. The indicators and milestones have not been monitored or amended. In several interviews for this AR, it was commented that the Logframe is only reviewed during the process of an Annual Review, which is not an effective way to manage programme progression.

This AR concludes that EDIP is not an appropriate or effective place for this Output to be monitored or carried forward, and recommends it is either substantially amended in the year ahead, or removed from EDIP entirely.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead:

Substantial progress has been made on last year’s lessons and recommendations:
1. The creation of the FCDO has supported the development of a more cohesive, strategic view of development work on island.
2. Currently three FCDO observers/representatives, and an FCDO chair (the Programme SRO), attend regular meetings of HLP, which set clear direction for the programme and use of FCDO funds.
Recommendations from this AR are:

1. A decision should be made about whether it is appropriate for the Compact to remain in EDIP, or to be moved to an FCDO country level plan. This was a recommendation from last year’s AR, which has not been considered;
2. A governance review should be conducted to review the composition and terms of reference of both HLP and the Programme Review Group;
3. HLP makes a concerted effort to discuss the long-term vision for the economic development of the island, and avoid focusing on updates and progress reports on individual projects within EDIP;
4. The Logframe, in its entirety, needs to be monitored by the Programme Review Group. Milestone indicators need to be reviewed to ensure they are relevant and achievable. It is unacceptable that these activities are only done once a year at the time of the AR.

## C. DETAILED OUTPUT 3 SCORING

Output Title	Well prioritised, high quality, well justified high return social and economic development investments developed
Output number:		3	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of Business Cases with realistic options and quantifiable benefits considered - submitted and approved.	A formal benefit monitoring framework established for approved EDIP investment linked to quantified benefits	Score: B. Partially Achieved: Spreadsheet capturing benefits as outlined in BC’s developed
3.2 Reduction in size of investments as a result of improved quality of project development processes	500k savings from first and final business case	Score: A++. Exceeded Expectations: We have between £940,000 - £5.8 million in savings between the preferred options and the other short-listed options considered for: / Rupert’s (3 options short-listed) / R2 business cases (2 options short-listed) / These were the only two business cases from Year 2.
3.3 Number of changes made to project proposals as a result of public consultations, to reflect an improvement in the project development processes.	10 changes	Score A. Achieved: 9, (6 based on 2 complex BC and the remainder being related to Micro Projects)

Briefly describe the output’s activities, and provide supporting narrative for the score:

The overarching conclusion of this AR is that there is an insufficient balance between projects with an economic versus a social development focus. Far more emphasis is placed on a high return from economic projects, while projects with a purely social focus seem to be considered comparatively less worthwhile or fundamental. However, good social investment is crucial to the long-term success of economic development. In particular, this AR identifies investment in education infrastructure as an area where social programming is noticeably lacking. Investment in education infrastructure (e.g. school buildings, IT facilities) should be considered a key component of furthering the economic development of the island. This reality was recognised in the original business case, but has not been carried forward in practice.

Output 3.1: A formal framework for monitoring quantified benefits of approved EDIP investments has not been established. Some steps have been taken towards establishing this formal framework – a spreadsheet is being used by PMU to begin to capture benefits – but further work is needed to enhance and build on initial steps so that these can be incorporated into a formal process. This has only partially been achieved.

Output 3.2: Greater scrutiny is being applied to tendered options/bids by the PMU, who have adapted locally unsuitable and cost options put forward by international consultants to fit the local context and available resources. This has only been achievable by having a dedicated SHG EDIP team with consultants (e.g. architect, structural engineer), which has allowed the PMU to identify savings, from the first to last business case, of between £940,000 and £5.8 million. The PMU favour using a number of locally engaged contractors over one or two international firms. Although this method extends the delivery timeline, it has ensured that investments can be maintained on island over a longer period, has avoided investment leakage off-island, and maximised opportunities to build skills and capability within the local workforce.

Output 3.3: The expected milestone of 10 changes as a result of public consultation reflect improvements in project development processes from a number of interviews and conversations with stakeholders . The number of engagement sessions run by the PMU with members of the public have not been recorded fully, but the team have actively engaged throughout the year, seeking comments from the public on the designs, which have been reflected in the final BCs presented to HLP.

A number changes following public consultations that were implemented were efforts to keep Rupert’s pleasure beach open throughout the build phase (including access to picnic huts). Amendments throughout R2 were also numerous (including social mitigation and water pipe integration). However, the PMU did not consider it necessary to document the majority of these changes. Going forward it is recommended that the PMU should ensure that all its public consultations, and changes made as a result, are comprehensively recorded. This finding again emphasises the importance of rigorously monitoring the Logframe so there is clarity on which data needs to be captured.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year:

Efficiency: Reducing scope of projects from original business cases has improved efficiency. An example is Rupert’s wharf: the previous consultants produced solutions that were theoretically optimal, yet expensive and didn’t fit St Helena’s needs. Therefore, the scope was redefined, and the project split into two phases, with phase one being the minimum needed for operationalising the port in the short term and phase two, addressing the subsequent demands of an operational port. This reduced the expected cost and ensured that the aspect of the project with the highest benefit, making the port operational, is prioritised.

Effectiveness: Projects were prioritised with essential infrastructure projects being ranked first along with smaller “shovel ready” projects, as opposed to conducting a cost benefit analysis for all projects and ranking them by net benefits. Although the latter methodology would have been preferable, it was deemed highly likely that the ranking would be the same. This approach is logical as without essential infrastructure improvements, other projects either cannot go ahead or will not be as beneficial. For example, improving the road connection from Rupert’s to Jamestown (R2) is essential to transporting goods from the port and therefore realising its full economic benefit. Therefore, the indirect economic benefits are significant, and these projects are consistent with EDIP’s overarching aim of enhancing St Helena’s economic development. The full benefit of these projects are not being captured in the formal monitoring frameworks – quantifying indirect benefits requires time-consuming analysis which SHG does not have the resource for at the moment.

Equity: Public consultations on Rupert’s helped ensure views of different groups were taken into account. The micro-projects included infrastructure improvements such as making the courthouse more accessible. Any benefits framework should ensure social benefits to marginalized groups are captured.

Describe any changes to this output during the past year, and any planned changes as a result of this review:

SHG’s Programme Manager and her team within the PMU have made great strides towards investing widely in consultation and engagement with those principally affected by developments under EDIP. This has resulted in a more informed, engaged, and receptive local community when it comes to major developments. This was a significant development, given the impact major projects will have in the coming years on the lives of islanders. It has resulted in positive community interest in EDIP, in both major and micro projects.

The PMU should continue to monitor Logframe output indicator milestones, to ensure relevant information is captured properly and reported to the next AR.

This review suggests an improved methodology for quantifying savings made from initial to final versions of business cases so as to ensure a true reflection of the work undertaken by PMU in scrutinising the use of (and safeguarding) public money.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead:

All business cases now incorporate an environment and social impact assessment. However, a number of these have been “light touch”. One interviewee commented that these assessments could not be conducted locally without technical support, noting the current approach was more “pragmatic”. This AR strongly recommends these assessments are given more detailed consideration in the early stages of project design in future.

Recommendations from this year’s AR are:

1. Greater emphasis should be placed on the importance of social infrastructure projects as a driver of economic development, addressing the current imbalance which favours economic infrastructure projects would benefit future investment decisions;
2. Education infrastructure investment should be considered central to economic development as recognised in the original EDIP BC;
3. PMU to ensure all changes made to BCs as a result of public consultations are thoroughly recorded, in line with the programme Logframe;
4. Programme Logframe output indicators need to be monitored more regularly and effectively, and if unfit for practical purposes, must be changed accordingly.
5. This AR strongly recommends that social and environmental impact assessments are correctly resourced and reflected within programme business cases to ensure unintended and non-desirable outcomes can be identified and where possible mitigated against.

## C. DETAILED OUTPUT 4 SCORING

Output Title	Increased local capacity through enhanced prog management, assets management, procurement capabilities, systematic stakeholder involvement and climate and environment opportunities.
Output number:		4	Output Score:	B
Impact weighting (%):		25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Assets and facilities management system setup and incorporated into O&M plan.	Asset condition updated, O&M Planned and budgeted under Financial Aid for 30% of Infrastructure O&M needs met through FA.	Score: C. Not Achieved:
4.2 % of project forecasts being achieved and timely completion of EDIP projects within budget and to specification	85 percent of project forecasts hold true within 10 percent allowance of initial estimate. VfM assessments of proposed investments opportunities undertaken	Score: B. Partially Achieved: 75% achieved based on £3.225 million budget. 85% achieved based on £2.825 million budget.
4.3 Programme management capacity strengthened.	PMU fully staffed. Specialist staff for M&E, resilience and specialist infrastructure contracted	Score: A. Achieved: 75% met - three out of four posts have been recruited. 90-95% of the fourth, unrecruited post (Quantity Surveyor) has been delivered through local contracts.

Briefly describe the output’s activities, and provide supporting narrative for the score:

Output 4.1: Other competing priorities (COVID-19 and the FCO/DFID merger) have meant SHG staff have not been able to progress the activity for this output indicator. The indicator was based on proposals initially drafted by the Infrastructure Adviser who was in post in 2019. Some progress has been made. Draft terms of reference for an Asset Management Fund (AMF) have been prepared and discussed this year, but no further updates have been made to the ToRs at the time of this AR. An Asset Management policy and strategy are under development: the policy was produced by July end, and at the time of this AR is being taken through the policy development process; the strategy was still under construction by July end.

However, this activity has not met the expected milestone for year 2. This AR recognises the constraints on financial aid in the past year, and additional pressures on SHG financing across other priority sectors. More emphasis needs to be placed on making island investments sustainable, and it would be remiss to continue to implement infrastructure projects without an AMP or funding source to guarantee EDIP’s long term impact. This again highlights the importance of strategic planning and monitoring Logframe output indicators, in order to maximise VfM and impact of UKG investments.

Output 4.2: The total funding available for spend in 20-21 was £3.23 million (including a contribution from Connect SH of £25k for a water exploration project). A total spend of £2.4 million was achieved: this followed a return to UKG of £400k, as PMU forecast during the year that activities would not be delivered and a budget revision was necessary (giving a budget of £2.83 million); in addition, at the end of this year, a further £400k was not spent as a result of contracting issues with an implementing partner, and these funds were subsequently also returned to UKG (and could not be rolled over). On the basis of the original budget of £3.23 million, the 85% milestone was not met; however, if the revised budget of £2.83 million is considered as the baseline, this milestone arguably was achieved.

There are concerns about the rigour of financial systems and reporting processes within SHG, and subsequent reporting to PRG/UKG. SHG finance teams provide the PMU with monthly forecasts/financial reports 7-10 days into any given month. This means PRG/UKG are routinely asked to make decisions on the basis of out of date and inaccurate financial information, which prohibits PRG from fulfilling its duties as a review group, and prevents good programme governance. Reforms to this process and systems must be implemented by SHG.

Output 4.3: Three out of four PMU posts have been successfully recruited: a Chartered Engineer, a Constructions Project Manager, and an Architect. A graduate Projects Engineer has also been seconded to the PMU. The fourth PMU post, for a Quantity Surveyor, has not been filled due to constraints brought on by the global pandemic. It is, however, important to note that 90-95% of quantity surveyance tasks for EDIP have been delivered through local contractors instead. Therefore, as the fourth PMU post has largely been delivered, even if not through the recruitment of a full-time staff member, this AR concludes that this milestone has been achieved.

The milestone for this indicator suggests that an M&E specialist should also have been recruited to work on EDIP. However, following interviews conducted for this AR, it is clear that having an M&E specialist working full time for EDIP, and funded by the project, would not be a prudent use for public money and limited programme funds. While EDIP and the PMU would benefit significantly from the input of an M&E specialist, there would be insufficient work to justify a full-time EDIP post. Instead, SHG should prioritise the recruitment of a wider M&E specialist who could, as part of their role, provide support to the PMU on EDIP.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year:

Economy: Use of local contractors to undertake quantity surveyance tasks generates savings compared to employing external companies.

Efficiency: Management of EDIP by a local team has so far been a successful approach. An on-island team is better placed to understand conditions on the ground and engage with local stakeholders than external consultants would be, bringing efficiency gains to the process. It has reduced costs and logistical difficulties associated with travel, particularly during Covid-19.

Describe any changes to this output during the past year, and any planned changes as a result of this review:

A major change is an almost fully staffed project, with 75% of posts filled and additional resource brought in through secondment. This is a significant achievement in the context of severe constraints on the movement of people globally in the past year. The remaining post that the PMU were not able to recruit has instead been almost entirely filled through local, call-down contracts, which is also a laudable effort.

It would be remiss to continue to implement infrastructure projects without a robust Asset Management Plan (AMP). In conjunction with wider SHG asset recovery policy, the PMU should develop an AMP in the next year.

A Programme Management Office, within SHG, should be established to provide a dedicated secretariat function for the various governance groups (weekly EDIP planning, PRG, and HLP), to give Chairs of each group more latitude to set direction and prioritise conversations strategically throughout the year. This is important to move away from the current, entirely reactive approach to agenda setting and decision-making, and towards a more proactive and strategic style of business. This AR recommends agenda items should be set on a yearly basis to create opportunities for mid-year prioritisation, quarterly milestone monitoring, and monthly financial reporting.

Efforts towards a more proactive approach have been enabled by the reintroduction of a development focused role in the form of the UKG Development Attaché, who has promoted a more proactive stance to programme governance.

SHG should appoint a dedicated M&E specialist to support EDIP in developing an M&E framework. This will ensure programme activity and data are sufficiently captured, to promote learning of lessons across the future of EDIP.

The PMU should also reassess if a full-time Quantity Surveyor is still required, or if local call-down contracts may prove to be a cost-effective, sustainable, and efficient way to deliver.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead:

Work has been progressed by SHG to establish an Asset Replacement policy and strategy. However, as outlined above, this work still needs to be progressed and should be prioritised after the October 2021 elections.

Recommendations for this year’s AR are:

1. SHG to establish and own PMO function to support programme governance;
2. SHG to improve timeliness of financial reporting to PMU to support effective decision-making by project governance groups;
3. SHG to develop a robust AMP within the next year;
4. SHG to appoint a dedicated M&E specialist to support EDIP (as part of wider responsibilities);
5. PMU to assess if recruitment of full time Quantity Surveyor is necessary.

D: RISK

Overview of risk management:

The St Helena Government programme risk appetite for EDIP is Moderate and is overall in line with FCDO’s EDIP risk register, which is also Moderate.

As of July 2021, SHG’s main EDIP risk areas are:
1. Projects developed are not supported with a O&M strategy and recurrent directorate budget constraints not able to meet additional O&M demands resulting in assets falling into derelict quickly
2. Delays from stakeholders (e.g. Planning/AG’s chambers) jeopardising the programme and funding allocation for the year
3. Financial reductions as a result of UKG Budget cuts
4. Weather impedes delivery

None of these risks have been escalated into issues, due to mitigation processes in place within PMU and due to the involvement and support of FCDO’s engagement . Within the coming year the biggest challenge will be the forthcoming spending review that will look at a three-year programme allocation for EDIP.

The Project Management Unit submits a monthly monitoring workbook which includes a risk register that has been improved since the last Annual Review. The EDIP FCDO team held a meeting with PMU to help improve the risk register. The improved EDIP Risk Register is now more akin to the FCDO risk register. It now has the same risk categories, along with mitigation measures rather than Mitigations (outcome/consequences). It also includes new columns for likelihood of occurrence, post mitigation, severity of impact of post mitigation, total score and residual risk rating post mitigation.

Safeguarding remained high on the agenda, with FCDO support from the Social Development Adviser (until their departure in February 2021). Although there are no safeguarding risks logged in the SHG EDIP risk register, there is a risk logged on the FCDO EDIP risk register.  Any emerging risks are discussed at the weekly EDIP planning meeting. The FCDO EDIP programme risk register was reviewed and amended in late 2020 and again in May 2021 followed by a further review in August 2021. None of these risks have escalated into issues but are being regularly monitored.

The main risks for FCDO are:
1. Risk of Management / Treasury approval for Programme continuation beyond break-point review not secured in time.
2. New (and existing infrastructure), does not have adequate provision for maintenance, leading to reduced operational life and exposure to health and safety and reputational issues.
3. EDIP funded interventions fail to implement proper controls, causing harm to the people or the environment of St Helena.

Recommendations for this year’s AR are:

EDIP risk reporting structure requires review to ensure clear understanding of dealing and escalation of project and programme risk. Teams and governance groups throughout the 3 tiers are not clear on the level of risk they are able to accept, ignore or mitigated. EDIP would benefit from empowering PRG and Planning Meeting to deal with certain risks and issues, only escalating upwards when deemed appropriate. This would ensure greater ownership of programme delivery by technical and programme teams, while supporting HLP in addressing only the highest rated/emerging risks and issues.
E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency:

Overall strategic decisions for the programme are made by the HLP, which is chaired by the UKG SRO. This has resulted in more cohesive and strategic approach, which has helped to strengthen SHG and UKG engagement and collaboration, and foster a greater sense of partnership. HLP also includes elected representatives from St Helena. The HLP receives Business Cases for review after they have been cleared by PRG, which sits at the technical level. Concerns were again raised this year that there are representational/membership overlaps between HLP and PRG, which hampered progress on some projects. This review has recommended (above) that this issue is addressed through a governance review.
Programme monitoring is conducted by the PMU and provides a programme monitoring report to its Board and to UKG on a monthly basis. Once received, a PRG meeting takes place to discuss the report. The quality of reporting is good, but the report should be received a week before the meeting takes place to provide an opportunity for members to fully digest its contents. It includes a narrative around progress on each project including timeline, actual/projected spend, activity log, risk log, along with a financial summary for the year. The UKG Development Attaché also conducts ad-hoc field monitoring visits.
Overall financial management is good. Over the last year PMU has tweaked the financial reports and included a new monthly forecasting report, which includes all contractual commitments on each project.
The total spend at the end March 21 on the project was £5,168,729 (85% of allocated budget). Last financial year (2020/21) spend was £2,417,615 - 76% of allocated budget. One of the reasons for underspend in this financial year was due to appropriate guarantees not being in place prior to contract signing, specifically on the R2 and Rupert’s projects.
However, underspends may also have arisen from efforts by SHG to ensure value for money and reduce costs, notably by utilising local contractors and careful consideration of costs of inputs. All payment requests are submitted with a funds request signed by the Financial Secretary along with an expenditure spreadsheet. To date 8 payments have been made to the project (see below). The most recent payment made was 17 August 2021 for spend from 1st April 2021 to 30 June 2021 for £266,846.59.

At the end of year 2, the project to date has only spent £5.169m of the agreed £15m in the first 3 years. This has been slow starting due to a number of reasons:
  1. Time taken to set up PMU unit and put key technical staff in place.
  2. Establishing financial procedures and governance structures, with newly onboarded staff.
  3. Covid-19 restrictions and its industrial impact affecting materials.
Due to these conditions and the nature of the circumstance, the FCDO in partnership with SHG have agreed to extend the 1st phase of the project from 3 years to 4 years, with a view to proposing a no-cost extension for one year at the end of phase 2.
Recommendations for this year’s AR are:

Timely and accurate financial reporting must be strengthened by monthly and quarterly monitoring of project spend, to flag yearly underspends to FCDO in good time.

Date of last narrative financial report	July 2021	Date of last audited annual statement	June 2021 for financial year 19/20