## Annual Review

Title: Transforming Access to WASH and Nutrition Services in Mozambique - T-WASH II
Programme Value (full life): £70 million		Review date: June 2024
Programme code : 300725	AMP start date: 04/09/2020	AMP end date: 30/09/2026

Summary of Programme Performance
Year	2021	2022	2023	2024
Overall Output Score	A	A	A	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/90000499.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0003453.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Transforming Access to Water, Sanitation, Hygiene and Nutrition Services in Mozambique (T-WASH II) programme was approved by Ministers in July 2019, with a budget of up to £70 million, to be implemented from September 2019 to September 2026. The objective of the programme is to improve sustainable access to WASH (Water, Sanitation and Hygiene) services and improve sanitation and hygiene behaviours at the sub-national level for around 2 million people, in particular women, young girls, and children. Due to delays in budget confirmations (in part due to COVID-19 and Official Development Assistance (ODA) reductions), the programme did not begin full implementation until September 2021.

T-WASH II is delivered through four components:

- Component 1 supports the Government of Mozambique’s (GoM) Rural Water and Sanitation Programme (PRONASAR) under the National Directorate of Water Supply and Sanitation (DNAAS). PRONASAR is funded by GoM and through a multi-donor Joint Fund mechanism. UK funds are channelled through a Fund Manager.
- Component 2 funds a Capacity Building Agent (CBA) which enhances government capacity at the central, provincial and district levels. The CBA supports multi-sectoral planning, improved budgeting, procurement and monitoring through targeted training and mentoring, as well as managing pilot interventions to test new and innovative approaches in WASH. SNV fulfils the role of both Fund Manager and Capacity Building Agent under T-WASH II.
- Component 3 is for an Independent Monitoring Partner (IMP). The IMP, contracted in February 2024, will assess progress against performance-based funding elements of the programme, provide independent verification of results and strengthen GoM monitoring and information management systems.

Component 4 comprises policy, monitoring, evaluation, and learning (MEL) work across the programme and uses MEL products to support evidence-based policy initiatives. A programme-funded adviser (PFA), based in the DNAAS, works closely with the CBA and PRONASAR Joint Fund to enhance the uptake and use of evidence in the programmes to improve implementation and policy making. A second programme-funded adviser, starting in July 2024, will provide technical support and strategic guidance for policy influencing.

Summary supporting narrative for the overall score in this review

T-WASH II scored an A+ rating in this annual review. During the review period (April 2023 to March 2024), the programme provided new water and sanitation services to approximately 272,830 people with the construction of 24 water systems, 9 of which were inaugurated by the President of Mozambique. In addition, 94 boreholes and 11 toilet blocks were constructed. Sensitisation and community mobilisation through social enterprise companies, contracted by the GoM, reached more than 190,000 people with access to safe sanitation through the construction of around 38,000 improved latrines in 14 districts. More than 311,000 people have benefited from hygiene messages, contributing to behavioural change.

The programme also introduced and conducted climate resilience assessments of WASH infrastructure using the assessment tool developed by the programme. This emphasised the importance of “resilient infrastructures” (that can withstand natural disasters) within the sector. The use of clean energy has been a focus of the WASH sector, with T-WASH II adhering to this approach, contributing 323kV of clean energy through the installation of solar panels in water systems.

Three outputs (outputs 1, 2 and 4) are on track to achieve their targets, while one output (output 3) faced some challenges associated with decentralisation and the difficulties in allocating a greater percentage of WASH funds to decentralised levels (province and district levels). This was due to weak technical capacity at these levels and the complexity of some activities, particularly around the construction of resilient infrastructures. Good progress has been made towards outcome indicators with some having already exceeded the programme’s end targets.

One of the most significant challenges in the past year was the annual budget being depleted by December 2023, which meant the Fund Manager was unable to process new invoices from ongoing PRONASAR WASH activities. This was due to the lack of a commonly agreed Delivery Plan between stakeholders, outlining all activities and forecasts for the year, which caused confusion and tension between partners. As a result, an additional £2.0m was disbursed to the programme during this reporting period, which was fully utilised and allowed for additional results. Throughout the annual review, revised results targets are included where the additional funds were used.

Major lessons and recommendations for the year ahead

The main lessons from the last year of implementation have been captured in the below table:

Main Lessons Learned
#	Lesson
1	Coordination with Education sector: The programme has invested in WASH facilities in schools to ensure that girls do not miss school during menstruation. However, it was found that some of these facilities were underutilised. This issue largely stems from a lack of coordination between the Ministry of Public Works, which provides the infrastructure, and the Ministry of Education, the end users of the facilities. This lack of coordination has negatively impacted girls’ ability to use the facilities, thereby undermining value for money of the investments.
2	Socialising change: Bringing together the various components/stakeholders of the programme whenever changes occur - whether from the implementing partner, service provider or the donor - adds value to the programme. This practice fosters strong relationships, trust, and effective coordination among programme components, positively impacting programme performance. This was seen recently when the programme organised a meeting between stakeholders, with positive feedback received that the approach helped in improving working relationships between partners.
3	Under-reporting beneficiaries from water systems: The programme has performed well in terms of number of beneficiaries receiving new water services. However, it is likely that the programme’s monitoring framework and current GoM systems do not account for all beneficiaries: / Unreported Water System Expansions: PRONASAR does not systematically record the additional beneficiaries from water system expansions. Private Operators of the water systems expand their services by adding new household connections each year, but these are not reported through the standard reporting systems. / Multiuse Systems in Drought-Prone Areas: The programme is implementing new multiuse systems in areas prone to droughts, allowing livestock herders and farmers to access water during periods of scarcity. These additional beneficiaries are currently not being counted or reported. / Undercounted Household Connections: Anecdotal information suggests that some household connections serve multiple families. Currently, the beneficiaries are calculated based on 5 people per household connection, which may underestimate the actual reach of water investments. More evidence may be needed to support this assumption.

Main Recommendations
#	Recommendation	Responsible	Timeline
1	To drive decentralisation of the WASH sector, the programme should allocate more funds to provinces and districts. / FCDO will stipulate that new contracts should mainly be allocated to decentralised levels, with appropriate training and capacity-building, and only be managed centrally by DNAAS in exceptional circumstances. / Further, the CBA should work with districts to identify priorities and plans for activities to be implemented in 2025, to which funds can be allocated under the performance-based funding approach.	UK with SNV (CBA)	By December 2024
2	SNV should review the survey methodology to assess level of satisfaction of beneficiaries of WASH infrastructure to ensure all aspects related to “satisfaction” (e.g. number of hours of water supply, cost of water per cubic meter) are considered.	SNV	By November 2024
3	DNAAS should coordinate with stakeholders involved with WASH in schools, in particular the Ministry of Education, to ensure inclusive WASH infrastructures in schools are used, maintained, and provide added value to schools, particularly for girls.	DNAAS with UK support	By February 2025
4	The programme should work with DNAAS to identify a system for better recording and reporting of additional beneficiaries, such as livestock herders at multiuse systems or from expansion of water supply systems.	UK with SNV (CBA) and DNAAS	By November 2024
5	Through the Independent Monitoring Partner, the programme should support a case study to better understand the impact of improved WASH services on women and girls in Mozambique. The Terms of Reference should be shared with DNAAS and key stakeholders to ensure buy-in from a wider range of actors.	IMP (C4ED)	By November 2024
6	The UK should discuss with DNAAS the possibility of providing additional technical assistance to the National Water and Sanitation Information System (SINAS).	UK	By December 2024
7	A more thorough value for money assessment of the water systems should be conducted, including analysing the bills of quantity to improve understanding of cost drivers and develop baselines for average costs. The findings should be presented to DNAAS and provinces responsible for contracting services.	UK with SNV	By December 2025
8	The programme logframe (indicators and targets) should be reviewed to ensure they are pragmatic and realistic given the changing context.	UK	By September 2024
9	The programme team should work with SNV to improve on financial reporting, adopting a simpler template suggested by FCDO and ensure they work towards more effective provision of capacity building support	UK with SNV (CBA) and DNAAS	By July 2024

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The 2021 FCDO Mozambique Business Plan set out a shift away from large direct support for public service delivery to a more targeted portfolio of smaller human development programmes (including T-WASH II) focused on systems building, coordinating investments with other development partners, improving the value for money of our sizeable share of multilateral spend, and testing innovative approaches. The Theory of Change (ToC) for T-WASH II already envisioned an approach centred on system strengthening and targeting disadvantaged groups (including women and girls). T-WASH II also supports objectives on climate change, helping to build Mozambique's resilience to climate and humanitarian shocks.

Following significant reductions to the budget in 2021 and in line with centrally mandated handrails, three major changes were agreed to the T-WASH II ToC and outcome-level indicators. Two new outcomes were designed to increase focus and funding for climate change and emergency response. A new Output was developed to provide support to rural communities to adapt to the effects of climate change and to improve resilience. While the emergency response was a timebound intervention that has since ended, the programme has maintained flexibility to respond to new emergencies and climactic events. Lastly, the overall ambition of the programme was reduced in line with the budget reductions.

The overall assumption of the programme is that increased access to WASH infrastructure, together with improved practices and behaviours, along with sufficient means and as part of a wider package of health interventions, will lead to a reduction of diarrheal disease and stunting among children under-5 and improve the general wellbeing of the rural population, in particular women and girls. This assumption and the ToC still hold true.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

At the Outcome-level, the programme is performing well against indicators and, in some cases, exceeding the final targets. Planned milestones for indicators 2 and 3 were revised as more activities were implemented through additional funding (£2 million) provided in February 2024. Targets for outer years will need to be revised in the coming months as part of the logframe review. The below table shows the results that were achieved in the past year.

Outcome Indicator		Target (March 2024)
Number of people in rural areas with access to new water supply services (disaggregated by gender)	Planned	66,000
	Achieved	82,240 / (42,765 female / 39,475 male)
Number of people in rural areas with access to new sanitation services, of which % live in open defecation free (ODF) communities	Planned	35,000 (original) / 109,350 (revised)
	Achieved	190,590 / (99,107 female / 91,483 male) / 100% in ODF
Number of people in rural areas with improved nutrition-sensitive hygiene practices (disaggregated by gender)	Planned	40,500 (original) / 109,350 (revised)
	Achieved	190,590 / (99,107 female / 91483 male)
% of funds that are decentralised for implementation by the provinces and districts	Planned	70%
	Achieved	69%
Number of people with improved climate resilience as a result of International Climate Finance (ICF) WASH investments	Planned	52,800
	Achieved	272,830 / (141,872 female / 130,958 male)
Number of people gaining access to safe water through emergency water supply interventions (emergency support planned for Year 1 only, but available for flexible funding when needed)	Planned	N/A (respond to needs and specific emergency)
	Achieved	9,300 / (3 emergency interventions in Maputo)

Outcome Indicator 1, people with access to new water services, exceeded expectations by reaching 82,240 beneficiaries (against a target of 66,000). The was achieved through the construction of 24 new water supply systems and 94 boreholes/community handpumps (see Output 1). A large number of existing infrastructure contracts, and some water systems were concluded before the planned date. This result was driven by a strong push from the government for provinces and contractors to deliver. As beneficiary results are only counted when infrastructure is completed, this led to a significant overachievement for this target.

Outcome indicators 2 and 3, people with access to new sanitation services and improved hygiene practices, exceed expectations, reaching 190,590 people (against a target of 109,350). Sanitation-focused behaviour change campaigns led to the construction of over 38,000 household (resilient) latrines. These two indicators share the same target beneficiaries for sanitation and hygiene messaging and access to sanitation is a requirement in the methodology for the improved nutrition indicator. The overachievement in results can be attributed to conservative targets set (due to fewer sanitation contracts concluded in the previous year) and a change in the government’s sanitation strategy. Previously, social enterprise companies, contracted to run sanitation & hygiene awareness campaigns, targeted specific numbers of people within provinces. The government has changed this approach and now requires these companies to deliver area-based campaigns targeting whole communities within a district, so they can achieve ODF status, thereby reaching more people. As a result, more people were sensitised which led to more sanitation infrastructure being constructed.

Outcome Indicator 4, which measures the % of funds planned and managed by decentralised government was 69% against a target of 70%. At the start of T-WASH II, due to the delays in initiating the programme, it was assessed that DNAAS (at central level) could implement and disburse funds faster than decentralised institutions. This resulted in most contracts tendered in 2021 being managed by DNAAS. DNAAS executed 16 water system contracts during the reporting period compared to 8 contracts executed by the 10 provinces.

Outcome Indicator 5, people with improved climate resilience, is measured by the programmes’ ability to enhance communities’ capacities to anticipate, absorb and adapt (3 As) to climate shocks and stresses. The indicator exceeded expectations with 247,280 people supported to better absorb climate shocks through the delivery of safe and reliable water or sanitation services (including climate resilient infrastructure). A further 25,550 people, gained access to multiuse and desalinisation water systems, helping them to better adapt to areas prone to drought and saline water sources. There are two reasons for the significant difference in relation to the target (52,800 people). The first is that when setting the target, the highest number of beneficiaries expected from either access to resilient water or sanitation is used to avoid double-counting of beneficiaries. However, when reporting results, the government can verify exactly who the beneficiaries are and eliminate the risk of double counting, using the sum of people receiving access to resilient water and sanitation is used. The second reason is that more results were achieved both in terms of providing water and sanitation due to the push from government to deliver.

Outcome Indicator 6, people supported with emergency water supply interventions, reached 9,300 beneficiaries through the repair of three water systems that had been damaged due to heavy flooding in Maputo Province. This is a good example of the programme’s ability to flex and quickly adapt to emerging priorities and challenges.

At the Impact-level, the 2022-23 Demographic Health Survey (DHS) reported improved rates for both indicators - diarrheal rates in children under 5 years is at 8.7%, a significant decrease from the 11% baseline, and stunting levels have decreased from 38% to 37%. While results are positive, it is not possible to fully understand attribution to UK interventions without deeper, more targeted geographical analysis. This is currently not within the scope of the programmes monitoring framework.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

T-WASH II continues to be relevant to UK priorities, is valued by the GoM, has increased our ability to gain political access and engage, and is making good progress towards outcome-level indicators. The programme has demonstrated the ability to flex to the changing priorities of the FCDO, pivoting to a larger focus on climate resilience and supporting emergency WASH interventions as needed. T-WASH II contributes to the British High Commission Mozambique Country Plan and the Africa Strategy by providing a significant contribution to strengthening service delivery systems, improving the wellbeing of women and girls (including girls education), and enhancing resilience to climate change. The programme also continues to provide a strong value for money case.

## C. DETAILED OUTPUT SCORING

Output Title	Central, provincial and district government respond to demand for improved and inclusive WASH services, in target rural communities, by delivering agreed WASH infrastructure and services.
Output number:	1	Output Score:			A++
Impact weighting:	40%	Weighting revised since last AR?			No

Indicator(s)			Milestone	Progress
1.1 Number of water and sanitation infrastructures constructed or rehabilitated (disaggregated by type), as agreed annually in the PRONASAR procurement plan (PIA)			35 (original) / 64 (revised)	129 / (24 water systems, 94 boreholes, 11 sanitation blocks) / [Substantially Exceeded]
1.2 % household satisfaction with new piped water supply systems achieved in pilot locations in targeted districts.			70%	99% / [Substantially Exceeded]
1.3 % of women surveyed reporting improved access to water services in pilot locations in targeted districts.			80%	98% / [Substantially Exceeded]
1.4 Number of girls gaining access to inclusive menstrual hygiene management (MHM) WASH facilities in schools			3,995 (original) / 6,000 (revised)	6,961 / [Moderately Exceeded]

Briefly describe the output’s activities and provide supporting narrative for the score.

This output monitors progress on the UK investments to provide basic services for water, sanitation and hygiene. All indicator targets have been exceeded, with more water systems and boreholes than planned concluded in the reporting period. Initial milestones for the year for indicators 1 and 4 were revised as an additional £2 million was provided to the programme in February/March 2024. The output has scored an A++ (substantially exceeded expectation).

Output Indicator 1.1: Substantially Exceeded. The number of water and sanitation infrastructures constructed/rehabilitated substantially exceeded what was planned. 129 infrastructures were completed by government-contracted service providers, including 24 water systems, 94 boreholes and 11 sanitation blocks. The overachievement in this target was driven by a government push to expedite delivery, resulting in contracts being finalised before the planned date. For example, the programme normally completes between 15 and 18 water systems each year.

The government’s capacity to deliver water infrastructures and manage these contracts has also improved considerably. Almost all provinces have been able to carry out their planned activities, with some, such as Cabo Delgado, Gaza and Nampula, still needing technical support from the central government level (DNAAS). The construction of water supply systems, along with good relations with DNAAS, has served to influence the government politically and strategically in other areas and at different levels. For example, the programme will be piloting a new approach to sanitation that combines WASH infrastructure with improved technologies. This approach is new for the sector and the Government is willing to learn from it to further scale it up. We hope that this approach will raise the profile of sanitation in rural areas of the country.

Output Indicator 1.2: Substantially exceeded. As part of delivering new piped water systems, a sample survey was carried out to assess the satisfaction of beneficiaries with the services provided. Overall, 99% of households reported being satisfied (against a target of 70%). However, when looking at more specific questions such as satisfaction with the cost of water, the scores are lower. Users believe that water should be cheaper because it is a public service. Additionally, they would like to have more hours of water supply than the current 4 hours a day.

Output Indicator 1.3: Substantially exceeded. Similar to the indicator above, 98% of women interviewed reported improvement in water services (against a target of 80%). Most women previously had to fetch water from a borehole or river stream. A small proportion (2%) stated that they were not satisfied with the number of hours of water supply, with the cost of water and the lack of advance notice of interruptions in supply, whether due to lack of electricity or other reasons.

Output Indicator 1.4: Moderately exceeded. 2,926 girls gained access to new WASH services with Menstrual Hygiene Management (MHM) facilities in schools, and 4,035 girls received MHM dignity kits through the BeGirl (social enterprise company) MHM campaign on safe menstruation. The programme will continue working with DNAAS and the Ministry of Education and Human Development (MINEDH) to ensure that more girls have inclusive WASH infrastructure in schools, thus, not missing school during menstruation. One area that needs improvement is the coordination between DNAAS and MINEDH to maximize the effort being made (see lesson 1 under section A).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Targets for indicators 1.1 and 1.4 were changed as a result of additional activities executed with the £2 million provided in February 2024. Following the Annual Review and based on the PRONASAR Annual Implementation Plan (PIA), the logframe targets for outer years will be revised.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendations from previous year: These included a recommendation that the programme should seek opportunities to support collaboration between DNAAS and AURA (Water Regulating Authority), mainstream the four WASH sustainability pillars, and finalise the sustainability framework. This activity is ongoing. DNAAS and AURA have met to agree on a framework for private operators of water delivery systems, but the process is not finalised, and currently only 2 rural water system operators are reporting to AURA. Another recommendation was to scale up the work done by Be-Girl, a social enterprise company, in using local influencers to promote better Menstrual Hygiene Management (MHM). This activity is also ongoing. Discussions to scale up the programme have taken place but are currently stalled due to limited budget.

Recommendations for the year ahead: The programme aims to allocate most of its funds at the decentralised level, for planning and management by provinces and districts, but this is at odds with the how the funding is currently allocated. Of the 24 water systems completed in the past year, 16 (or 66%) were managed centrally by DNAAS. Many of these were initiated in late 2021 at the start of T-WASH II implementation. To ensure better decentralisation of the WASH sector, the programme should consider a top-down and bottom-up approach: The FCDO should not approve any new contracts to be managed centrally by DNAAS (except in genuinely extraordinary circumstances) and should ensure annual plans allocate sufficient funds for decentralised levels. Additionally, the CBA should work with districts to identify priorities and plans for activities to be implementing in 2025.

SNV should review the survey methodology to assess level of satisfaction of beneficiaries with WASH infrastructure to ensure all aspects related to “satisfaction” (e.g. number of hours of water supply, cost of water per cubic meter) are considered.

It is important for the programme to better capture the impact of improved WASH services on women and girls in Mozambique. This can be done through a case study with results disseminated to a wide range of stakeholders.

Output Title	Improved and coordinated availability of nutrition-sensitive hygiene delivered through social behaviour change (SBC) interventions
Output number:	2	Output Score:			A++
Impact weighting:	20%	Weighting revised since last AR?			No

Indicator(s)			Milestone	Progress
2.1 Number of people reached through targeted hygiene behaviour messages			81,000 (original) / 109,350 / (revised)	312,218 / (162,353 female / 149,865 male) / [Substantially Exceeded]
2.2 Number of new sanitation activities and Community Participation and Education (PEC) contracts approved in the Procurement Plan.			15	23 / [Substantially Exceeded]
2.3 Number of communities that maintain Open Defecation Free (ODF) status for one year following verification			Target not set for year	Not measured

Briefly describe the output’s activities and provide supporting narrative for the score.

This output performed well in the past year, with results substantially exceeding the targets, achieving an A++ score (substantially exceeded expectation). The aim of the output is to monitor efforts to raise awareness and encourage communities to adopt good hygiene practices through behaviour change campaigns. Community mobilisation is carried out by social enterprise companies contracted by the government. A strong push from government on delivery of planned activities (compared to previous years) as well as change in government sanitation approach led to more people being reached - companies were required to deliver activities to all communities within a district rather than a specific number of beneficiaries. As a result, families and entire communities have stopped practising open defecation and have started building and maintaining their latrines.

Output Indicator 2.1: Exceeded. The implementation of community awareness-raising initiatives for access to adequate sanitation and hygiene through the T-WASH II programme has successfully reached a cumulative number of over 500,000 people reached. Last year, 312,218 people were reached, against a milestone of 109,350, of which over 160,000 were women. This was achieved through 14 active contracts with Participatory Community Education (PEC) contracts - 5 in Maputo, 5 in Tete, 2 in Sofala, 1 in Gaza and 1 in Inhambane. The initial target set for this period was conservative, considering the limited number of PEC contracts concluded in the previous year. Overachievement was also driven by the change in government sanitation approach as explained above.

Output Indicator 2.2: Exceeded. 23 sanitation activities and PEC contracts were approved in the 2023 Procurement Plan, against a milestone of 15. These are multi-year contracts. 14 PEC contracts were active, performing community mobilisation activities on the ground, while others are still being mobilised.

Output Indicator 2.3: Not measured. This indicator measures the number of communities that maintain the ODF status one year after achieving it. It was not measured in 2023/24 since contracts to support communities to reach ODF status started only in August 2023. It takes at least 3 quarters to deliver the work and assess these communities as open-defecation free. Tete was the only province that carried out an assessment for open defecation - 165 new communities were declared Open Defecation Free. Some provinces, such as Niassa, Gaza and Inhambane, were unable to conduct the assessment due to lack of a multisectoral team (a local technical team comprised by technicians from the WASH, education, health, and environment sector). We will measure the number of communities that maintain their ODF status after they have completed at least one year in the next annual review.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The target for indicator 2.1 was changed as a result of additional activities paid with the extra £2 million towards capital costs provided in February/March 2024. Output indicator 2.2 “Number of people with access to new nutrition-sensitive services” was no longer feasible due to budget reductions (on non-capital). To shift focus and investments to the sanitation sector, a new indicator was proposed and approved in November 2023: “Number of new sanitation activities and PEC contracts approved in the Procurement Plan”. Following this Annual Review, indicators and milestones will be reviewed to ensure they are still relevant and practical for the purpose of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from previous AR: Last year’s review recommended the programme work with government to ensure provinces and districts have ownership of interventions and report results aligned with government systems. This has been completed. Provinces reported the results of UK-funded interventions into the Government Annual Report and suggested new sanitation activities to be included in the 2024 Annual Implementation Plan (PIA).

Output Title	Central government supports improved sub-national delivery and monitoring systems through effective decentralisation of WASH service delivery
Output number:	3	Output Score:			C
Impact weighting:	20%	Weighting revised since last AR?			No

Indicator(s)			Milestone	Progress
3.1 % of WASH services developed with FCDO funds that are annually and accurately updated on SINAS against agreed performance indicators			90%	27% / [Substantially not met]
3.2 Number of pilot target districts that have advisory WASH and nutrition commissions participating in PESOD planning process.			15	16 / [Met]
3.3 % of contracts procured by districts that are approved by the tribunal court at first submission.			60%	0% / [Substantially not met]

Briefly describe the output’s activities and provide supporting narrative for the score.

This output monitors the success of interventions to improve WASH service delivery at decentralised level. Weak institutional and staff capacity at province and district levels has affected allocation of funds to decentralised levels, thus affecting the performance of this output (C score – substantially did not meet expectations). This is evidenced by a lack of qualified personnel, insufficient training for public sector personnel involved in the provision of services, limited access to investment funds, low involvement of the private sector in the provision of services and inconsistent standards for water quality control in rural areas. Consequently, the central government level (DNAAS) has reduced the allocation of funds to the decentralised levels, which contradicts the decentralisation principle. The ideal approach would involve increasing capacity of local governments to ensure sector budgets are effectively used at decentralised levels. The capacity building agent provides this support in Nampula and Zambezia provinces.

Output Indicator 3.1: Substantially not met. 90% of WASH services provided were expected to be registered in the National Information System for Water and Sanitation (SINAS). While this was achieved in Nampula and Zambezia where the CBA has a presence (a 100% registration rate), only 27% of new infrastructures were registered on the system across all provinces where the UK is providing support. This was due to lack of equipment, such as smartphones, to register infrastructures, as well as a shortage of trained technicians.

Nevertheless, the programme undertook other activities, including the development of a monitoring and evaluation (M&E) platform to aggregate all major achievements and indicators of the programme. In addition, the Climate Resilience assessment tool is now operational, having been tested in two districts and used in three water systems (Pussolane, Vila Franca and Pambara).

The programme is also supporting field data collection using the m-SINAS platform. The aim is to establish a system to quickly update SINAS data using SMS/SSD technology and support follow-up action where needed. Unfortunately, DNAAS is facing challenges in maintaining a dedicated team for SINAS management. To ensure a more effective SINAS, there is a need for: i) decentralisation of the management process along with the reinforcement of provincial teams; and ii) introduction of simplified management processes and the use of other technological options, potentially involving participation of beneficiaries to report on the quality of WASH services provided. The programme will continue discussing these points with the Department for Planning and Projects at DNAAS.

Output Indicator 3.2: Met. 16 districts, 8 in Nampula and 8 in Zambezia are actively participating in the preparation of PESOD (District Economic and Social Plan). This is a successful legacy of the T-WASH I programme which has been implemented in the T-WASH II programme at a decentralized government level.

Output Indicator 3.3: Substantially not met. This indicator measures the % of contracts procured by districts that are approved by the tribunal court at first submission (target of 60% for reporting period). Last year, UK funds were not allocated to districts which meant that no results were achieved. The Disbursement-Linked Indicators (DLIs) for the performance-based funding component of the programme, which incentivise decentralised WASH service delivery, were only approved in April 2024. Consequently, districts were not technically prepared as they did not have WASH technical staff or training to implement this indicator. With the approval of the DLIs, it is now urgent to prioritise the WASH activities that the districts will implement, so that funds are allocated and managed by the districts. The CBA will work directly with the targeted districts, and results will be verified by the independent monitoring partner (IMP).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this Output in the past year. Following this Annual Review, and given the challenges faced in achieving Output 3 targets, the programme will review and amend the indicators to ensure they a) better reflect the realities of the operating environment and b) they are aligned with existing programme activities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendations from previous AR: The recommendation for the CBA to provide full support to districts to establish multisector teams and support them in completing the planning process to inform the PESOD at district and province levels was completed.

Recommendations for the year ahead: The DNAAS Department which is responsible for managing the WASH Information Management System (SINAS) is facing serious capacity issues due to the withdrawal of funding for technical assistance from other donor partners. This reduced capacity is affecting several work streams, including the registration of new infrastructures on SINAS, the progress on scaling up the SMS-update, and initiating the SMS early warning systems. The programme should discuss with DNAAS the possibility of providing additional technical assistance to SINAS.

The CBA should continue working with targeted districts to ensure that during the preparation of PESOD 2025, district-level activities (sanitation activities and construction of boreholes) are prioritized, to which funds can be allocated under the performance-based funding approach.

Output Title	Targeted communities supported to better adapt to the effects of climate change through resilient water and sanitation services
Output number:	4	Output Score:			A+
Impact weighting:	20%	Weighting revised since last AR?			No

Indicator(s)			Milestone	Progress
4.1 Number of people supported to better adapt to the effects of climate change			81,000 (original) / 109,350 / (revised)	272,830 / (141,872 female / 130,958 male) / [Substantially Exceeded]
4.2 % of new WASH infrastructure with a completed resilience assessment			75%	75% / [Met]
4.3 New SMS early warning system established to provide alert texts to WASH infrastructure managers and operators in advance of severe weather incidents.			Terms of reference for new SMS system agreed	Terms of reference prepared, awaiting final agreement with DNAAS / [Moderately Not Met]
4.4 Number of Megawatts of clean energy installed			150kw	323kw / [Substantially Exceeded]

Briefly describe the output’s activities and provide supporting narrative for the score.

The T-WASH II programme has focused on construction of climate-resilient WASH infrastructure to minimize the effects of climate change and to build anticipatory, absorptive, and adaptive capacities in rural communities since 2021. In 2023, the programme supported construction of 7 water systems with desalination units and 5 multi-use water systems in remote areas of rural Mozambique where water is scarce or is too saline to drink safely. Out of the 12 water systems, 11 are equipped with solar panels, providing reliable and continuous water supply. This approach helps to mitigate the effects of climate change and minimises the project’s impact on the environment by using green energy to generate and store electricity. The output has met 3 out of 4 indicator targets, with 2 targets substantially exceeded, scoring an A+ (moderately exceeded expectation).

Output indicator 4.1: Substantially exceeded. 272,830 people were supported to adapt to the effects of climate change, against a target of 109,350. Of these, 56,690 people had access to reliable and safe improved water services, while 190,590 had access to new resilient sanitation services. In addition, 25,550 people had access to multi-use and desalinisation water systems, which will provide them with ability to adapt to multiple, long-term, and future climate change risks, and to learn and adjust after a disaster. When setting the target, the highest number of beneficiaries expected from either access to resilient water or sanitation is used to avoid double-counting of beneficiaries who may receive both water and sanitation access. However, when results are reported, the government can verify exactly who the beneficiaries are and eliminate the risk of double-counting. As such, a sum of people receiving access to resilient water and sanitation has been used to indicate people reached. The programme also delivered resilient water systems that are solar-powered, including 6 water systems with desalinization facilities.

Output indicator 4.2: Met. A climate resilience assessment was carried out in 9 out of the 12 (75%) selected water systems. WASH and environmental technicians from the provinces were trained by the Capacity Building Agent to carry out the assessment. These trained technicians are now responsible for developing the resilience assessment monitoring plan which the programme will support for further implementation. This is a key success of T-WASH II programme.

Output indicator 4.3: Moderately not met. The programme partially met the target of developing terms of reference (ToRs) for the SMS early warning alert system for cyclones and other extreme climatic events. The ToRs, where prepared, but are awaiting approval from DNAAS. DNAAS is coordinating with other key stakeholders with similar initiatives to ensure coherence and maximise synergies. A dedicated technician at central level will be required to manage the platform.

Output indicator 4.4: Substantially exceeded. As part of the construction of resilient water infrastructures, the government has embarked on the construction of solar powered water systems. In some drought prone areas, boreholes constructed are equipped with solar powered handpumps. This indicator (the number of megawatts of clean energy installed) was measured for the first time and exceeded its target (323kW against a target of 150kW).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The target for indicator 4.1 was increased as a result of additional activities implemented with the extra £2 million provided in February/March 2024. Output indicator 4.3 was changed and approved in November 2023. The original indicator measured the “Number of new WASH infrastructure included in Local Adaptation Plans”. However, the programme faced challenges to engage with the Local Adaptation Plans and couldn’t update them annually to include new WASH infrastructures. As such, a new indicator was proposed: “New SMS early warning system established” with the aim of developing an early warning system to warn WASH infrastructure managers and operators in advance of severe weather changes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendations from previous AR: The last AR recommended for T-WASH II to set targets for megawatts of clean energy installed in infrastructures. This has been completed.

## D: VALUE FOR MONEY

Key cost drivers and performance

An important success of the programme this year has been the design and monitoring of a set of value for money (VfM) indicators. This provided clear markers with which to better assess VfM and to set benchmarks. It has also had a positive impact in changing the perspective of partners on activities and monitoring.

A total of £9,000,000 was disbursed between April 2023 and March 2024 for capacity building and PRONASAR WASH activities. Of this amount, £3,144,966 (35%) came from USAID funds (managed by the UK under a partnership agreement) and £5,855,034.00 (65%) from UK funds. Roughly 97% of all disbursed funds were executed within the reporting timeframe.

Economy

The key cost driver of the programme continues to be the WASH infrastructure constructions (water systems, school sanitation blocks and boreholes), which account for £6.8m (or 75%) of the total annual budget. In comparison, last year, WASH infrastructure cost accounted for 71% of the budget.

The second and third biggest cost drivers are the Capacity Building Agent (SNV) staff costs (including travel) which account for £1.2m, and SNV operating cost of £0.76m (13% and 6% of the budget respectively). These costs have been the source of much discussion this year as the infrastructure funding component of the programme (through PRONASAR) has been increasing. Last year, operating costs accounted for 12% of the total budget compared to 13% this year.

It is worth noting that SNV’s non-programme associated costs (NPAC) are set at 13.6%, and a management fee of 6.5% is charged for transactions managed by the Fund Manager on behalf of PRONASAR (for example, payments to contractors of WASH services procured by DNAAS). In 2023/34, the programme spent £614,451 on NPAC and Management Fees. In contrast, SNV (in their role as CBA) could only allocate £262,700 to programme capacity-building activities (such as training of Government officials). This is extremely low and largely due to ongoing limitations on UK resource budget.

Although the SNV operating costs remain the second highest cost driver, having a single supplier as FM and CBA represents greater value for money as fees are paid to just one organisation instead of two. The SNV team is comprised of mostly local staff who not only have local expertise but also have lower rates compared to international consultants.

Budget line / Cost driver	Cost 2023/24	% of Budget
PRONASAR WASH activities
PRONASAR WASH infrastructure (water systems and boreholes)	£6,801,616	75%
Community mobilizing, sanitation & hygiene campaigns	£142,360	1.5%
Government operating costs (i.e. travel for monitoring visits)	£82,581	1%
WASH in schools	£58,853	0.5%
Operational costs
SNV project staff costs including travel	£1,175,763	13%
SNV operating costs (including NPAC and programme delivery)	£759,921	6%
CBA programme activities	£262,700	3%

Efficiency

A significant improvement has been seen on the Fund Management by SNV in terms of efficiency of making payments. On average, the Fund Manager (FM) takes 3-5 days from when they receive a payment request, to review and process the payments, if all the paperwork is in order. This is a contrast from last year where they took up to 15 days to process payments. Delays in payments in previous year have resulted in suppliers contacting FCDO directly complaining of non-payment. Although the FM has been more efficient in processing payments, communication and tracking of the Procurement Plan (which includes all approved PRONASAR WASH activities) need to improve to avoid going over budget.

The programme has also implemented other approaches to achieve better efficiency, for example, contracting inspectors to review multiple construction projects, as opposed to assigning one per project as previously done.

Effectiveness

Through the agreed VfM indicators, the programme now systematically collects costs per beneficiary for the different investments made. The below table shows the cost per beneficiary for investments concluded in the past year:

Activity	Cost per beneficiary
Water Supply System (person with immediate access to new water services from piped system)	121.07
Borehole (person with access to new community hand pump)	20.56
School WASH (student with access to new school sanitation block)	439.35
Sanitation Campaign (person with access to a new household latrine)	1.20

A total of 24 water systems and 94 boreholes with handpumps were completed in the past year (12 water systems and 125 boreholes were constructed in the previous year). The average cost of a water system is £306,175, however, there is a large variance between the costs of individual systems. For example, the system in Jangamo, Inhambane, inaugurated in July 2023, cost £1,345,195, while the one in Hapacue, Nampula cost only £101,517. This is due to various factors such as location, terrain, difficulty in accessing water, rising costs of building material and procurement. There appear to be no direct economies of scale to be found by investing in larger systems as costs will be influenced by the factors mentioned above. Jangamo (by far the most expensive system) also has the highest cost per beneficiary return (£315 per beneficiary). A more thorough value for money assessment of the water systems will improve our understanding of cost drivers and develop baselines for average costs.

In relation to boreholes, the average cost was of £7,346, with a cost per beneficiary of £20.56. This was significantly higher than the average cost of boreholes last year which cost an average of £6,462. The increase can be attributed to rising costs of materials. At first glance, boreholes seem to offer much better value for money than the water systems. However, the numbers alone fail to consider other important factors. Providing household connections (through the Water Supply Systems) reduces time spent by beneficiaries collecting water, which can be onerous and sometimes even dangerous. Time saved from collecting water enables beneficiaries to participate in other productive activities, such as livelihoods or attending school) and provides better longevity.

Similarly, the cost per beneficiary of providing school sanitation blocks with menstrual hygiene management facilities appears expensive (at £439 per person), but the infrastructures enable girls to attend school year-round and provide opportunity for a better and more consistent education.

The average cost of community mobilizing, sanitation & hygiene campaigns is £51,300. A total of 312,218 people benefited from targeted hygiene behaviour methods and 190,590 people gained access to new improved household latrines. This provides the most cost-effective return with the cost per beneficiary at £1.20 showing an improvement from the previous year’s £2.54 cost per beneficiary. In 2022/23, awareness raising was implemented through the Namiruku behaviour change campaign via radio, community leaders, local activists, and authorities. Although this was a success, it was very costly. In 2023/24, much of the work was done though local NGOs and costs were much less.

The T-WASH II programme also support some government operation costs, such as travel for monitoring, as government funding to the sector is still low. Monitoring visits are essential to the programme approach the Government must verify that activities met the required standard before approving the invoice which is sent to the Fund Manager for payment.

A final point on the programme’s effectiveness is the flexibility and responsiveness to changes in context. T-WASH II added the facility to fund Government operational costs for monitoring visits, which are vital to ensure progress on implementation. The programme also supported the refurbishment of three water systems that had been damaged by heavy flooding in Maputo Province demonstrating the ability to respond to emerging needs and challenges in the WASH sector.

Equity

A total of 11 inclusive sanitation blocks were constructed, providing 6,961 girls with access to adequate facilities for menstrual hygiene – an increase from 3,629 girls reached last year. The availability of these facilities can have a long-term positive impact in the lives of girls. Many girls choose not to attend school during their menstrual cycle because they feel ashamed or lack proper facilities to manage their hygiene. Missing large periods of school affects girls’ education levels and may result in many abandoning school altogether. This can lead to early marriage, early motherhood, and a cycle of poverty. The sanitation blocks are also constructed to enable people with disabilities to use them – including ramps to enable wheelchair access and specially design latrines

The below maps show A) UK-funding on WASH activities (water system construction, sanitation campaigns, etc) and B) the latest data on percentage of the population with access to basic water services in Mozambique, as reported in the 2023 Demographic Health Survey. Tete, Nampula and Maputo are the provinces with highest investments, while Niassa and Cabo Delgado, have the fewest. While poverty is less prevalent in Maputo Province, the size of the population has determined the large number of activities. In terms of access to water, Manica, Tete, Niassa, Nampula and Zambézia are the Provinces with 50% or lower access rates. This information will allow us to better analyse and plan to direct future funding where the need is greatest.

Map A: UK-funded WASH activities	Map B: Access to basic water services

Assessment of whether the programme continues to represent value for money.

Overall, based on the analysis above, the T-WASH II programme continues to deliver good value for money (VfM). It provides water for the most vulnerable, positively impacting entire communities by providing them with clean water and reducing the time needed to collect water, thereby allowing them to focus on other priorities. The programme has also supported more resilient latrines and promoted hand hygiene resulting in fewer hygiene related diseases. Although some costs (particularly for water systems in remote areas, or difficult terrain) are high, the impact the programme continues to have in people’s lives is significant. We will continue to work with the Mozambican government to help improve procurement and try to find ways to bring down costs. The approval of value for money indicators will also allow us to compare metrics across years.

E: RISK

Overview of risk management

Overall, the programme risk rating has remained ‘Moderate’ with no change since the last annual review.

One of the main risks remains the ongoing conflict in Cabo Delgado. This has resulted in displaced people migrating to neighbouring districts and provinces, which has put pressure on existing water systems, made construction in critical areas difficult, and slowed down progress in areas of sanitation and hygiene, such as open defecation levels. The limited resources available to decentralised government levels for WASH interventions are prioritised to focus on the displaced people’s needs. The conflict also puts at risk the government staff and partners who operate in these areas, and leads to either partially or completely destroyed infrastructure, or infrastructure with no people to use it. To mitigate this risk, the programme remains flexible to support humanitarian WASH interventions as well as capacity building activities in areas such as Nampula which hosts many displaced civilians.

The past and current year are election years - last year saw the municipal elections and this year the country will have a general election in which a new president will be elected. There are many associated risks, such as the WASH programme being used for political gain, staff working in election campaigns instead of their day-to-day activities, public works slowing down as well as uncertainty regarding the incoming government. The UK will mitigate risks by avoiding participation at high-level inaugurations during campaign time as well as maintaining a needs-based approach for decisions on locations for PRONASAR water system constructions.

Another risk, although moderate, is safeguarding. Downstream partners (community campaigners) and building contractors operate in communities and schools for long periods of time and a risk exists of exploitative or abusive behaviour towards beneficiaries (in particular women, children, and adolescent girls). The recent due diligence assessment for SNV (FM and CBA) found that the partner has adequate safeguarding policies in place and has regular discussions with downstream partners, including contractors. However, safeguarding discussions with the government remain a challenge as the issue extends beyond the WASH sector. Nonetheless, we were pleased to see that contracts include an immediate termination clause in the event of any safeguarding (as well as fraud) allegations that are proven. The UK team has conducted various field visits and so far, have not yet received concern reports from beneficiaries. We will continue to monitor this closely in the coming year.

The government’s reliance on UK funds for the WASH sector poses a risk as the programme enters its final years of implementation. Early communication with the Government, identifying alternative sources of revenue or funding and ensuring sustainably of existing investments will be important. With both UK and Mozambique elections this year, changing priorities, funding availability, or leadership may significantly impact the stability and continuity of WASH programming.

The programme team will continue to update the programme risk matrix and engage with partners early and as risks evolve.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The programme has benefited from regular meetings with partners, including quarterly meetings and high-level discussions throughout the year. This has ensured transparency, open communication, and real-time progress. SNV has been very responsive to requests for information, meetings, and participation in events (such as the BHC Maputo Partners’ Day, for which they prepared a presentation), as well as external discussions (such as IMP discussions). There is a clear improvement in communication.

In terms of financial performance, the vast majority of funds that were disbursed in the past year were executed. However, a few issues arose. In December 2023, the Fund Manager ran out of funds to make payments for PRONASAR activities, as the allocated budget for the year was spent early. This was due to miscommunication, lack of a government delivery plan as well as political pressure to complete works quickly. As a result, the FCDO agreed a disbursement of an extra funds (£2 million) to cover the deficit. Discussions were held with both government and the Fund Manager to improve budget tracking and communication between the partners. For future years, disbursements are conditioned to an approved Delivery Plan which sets out the timelines for the implementation of approved PRONASAR activities.

The SNV due diligence assessment was refreshed in August 2023, focusing on governance & internal control, financial management as well as safeguards. The assessment noted that SNV has good financial systems in place and exceptional safeguarding policies which all staff and downstream partners must adhere to. However, financial reporting has remained a challenge, with reports not always easy to interpret. FCDO has been working with SNV to make improvements in this area including a new finance template to be used going forward.

The programme has successfully procured an Independent Monitoring Partner (IMP) whose primary objective is to provide independent verification of the results of the PRONASAR programme, with a focus on verifying performance against key performance and disbursement-linked indicators (DLIs) for decentralised WASH service delivery. The IMP has recently submitted a draft Inception Report with is being reviewed by the team.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The CBA has developed a Monitoring and Evaluation (M&E) platform to strengthen the evaluation and review of monitoring data from the programme. This has allowed Independent Verifying Agents, hired by SNV, to update data directly on the platform to confirm service providers’ activities and deliverables.

The Independent Monitoring Partner (C4ED) was contracted in February 2024. The first verification exercise will be carried out in July 2024. Additionally, they will conduct sector specific case studies which will enhance evidence of what works in the WASH sector in Mozambique.

Evidence

The programme commissioned a desk study through the UK-funded Knowledge for Development (K4D) facility to better understand factors which impact the sustainability of rural water systems. Key findings from the study included i) the importance of institutional capacity to support WASH service providers, ii) the need for adequate arrangements for operational and maintenance (O&M) costs and capital replacement to augment investments in WASH infrastructure and iii) that the private sector service delivery model (as employed by PRONASAR) performs well.

Learning

The programme has learned many lessons in the past year, as highlighted under Section 1 of this annual review. Learning was collected through: 3 field visits by the WASH team with DNAAS to Tete, Inhambane and Nampula provinces to assess progress in implementation of T-WASH II, constraints and recommendations; 1 joint field visit organised by DNAAS with all sector partners to Maputo province to assess progress on water and sanitation in Matutuine, Manhiça and Marracuene districts; a scoping visit by the Independent Monitoring Partner during their inception phase; quarterly meetings with SNV; and the international learning event on Climate Resilient WASH “professionalising management and accountability in rural water supply”, event that was held in Nampula between the 6-9 May 2024.

Date of last narrative financial report	7 May 2024
Date of last audited annual statement	30 November 2023