## Annual Review 2024/25

Title: Tackling global plant and animal health risks which threaten global food systems and health – in partnership with the Gates Foundation
Programme Value £ (full life): £38m		Review date: January 2025
Programme Code: 300728	AMP start date: 23 October 2019	AMP end date: 31 Dec 2026 (NCE approved in 2024)

Summary of Programme Performance

Year	2020	2021	2022	2023	2024
Overall Output Score	A	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.FCDO.gov.uk/projects/GB-GOV-1-300728/documents
DevTracker Link to results framework:	https://devtracker.FCDO.gov.uk/projects/GB-GOV-1-300728/documents

A. SUMMARY AND OVERVIEW

The challenge
Plant pests and diseases are estimated to account for 25-40% of direct yield losses in global agricultural production. Meanwhile, in sub-Saharan Africa alone, livestock mortality and morbidity cost well over USD $6 billion per year in production losses. Zoonotic diseases – the category of animal diseases which can transfer to humans – pose a significant threat to human health. Over 60% of emerging infectious diseases in humans have an animal origin. The Covid-19 pandemic, likely of zoonotic origin, illustrates the significant risks to human health, prosperity and global economic stability posed by emerging infectious zoonotic diseases.
[note] Myers (2017) ‘Climate Change and Global Food Systems: Potential Impacts on Food Security and Undernutrition’, Annual Review of Public Health 38, pp.259-77
[note] http://www.emro.who.int/about-who/rc61/zoonotic-diseases.html

Several factors are increasing the scale of the risks posed by animal and plant diseases: (i) climate change is increasing the geographical spread and lifespan of several pests and diseases; (ii) pests and diseases are being moved more rapidly between countries as a result of increased international trade combined with weak bio-security; (iii) poorly regulated and poorly managed agricultural intensification and wildlife farming are facilitating the emergence and establishment of diseases and pests in previously unaffected areas; and (iv) agricultural expansion is, in some areas, increasing human-wildlife contact, creating new risks of zoonotic disease transfer to humans.

There is an urgent need for scientific innovation to tackle and mitigate emerging plant and animal diseases. Without new agricultural technologies, localised outbreaks can quickly become epidemics, causing income losses and ill-health, creating food insecurity across countries and regions, and hindering international trade opportunities. Climate change exacerbates risks by altering evolution of disease threats and facilitating the emergence of new diseases, as well as impacting the geographic spread of disease threats.

Design and background to this programme
This programme responds to the need for a significant expansion in the availability and adoption of agricultural technologies that can (1) increase the productivity and climate-resilience of global agriculture, and (2) control plant and animal diseases and pests, which pose a significant, and growing, supply-side risk to global agricultural production and food systems.

This programme is a portfolio of agricultural technology investments, co-funded with and directly managed by the Gates Foundation. The investments are designed to protect global food systems from the risks posed by plant and animal diseases and pests, and to increase global agricultural productivity and climate-resilience. FCDO’s funding of £38 million leverages co-funding from BMGF of approximately three times this size. The programme builds on the significant achievements delivered through FCDO’s agricultural research partnership with BMGF since 2010, summarised in the business case and in the Project Completion Review (August 2020) of DFID project 205273.

Project list and reporting
The active projects under this programme and where they will be reported upon are as follows:

Output	Live project	Lifetime budget	Project dates	Reporting: 24/25 Annual Review	Payment in FY 24/25
1.1	Disease Early Warning Advisory System (DEWAS)	BMGF: $ 4,899,973 / FCDO: $ 1,400,000	Jan 23 – Jan 26	301328	Yes
1.2	Next WAVE (follow on to West and Central African Virus Epidemiology for Roots and Tubers (WAVE))	BMGF: $ 3,135,240 / FCDO: $ 3,810,702	Oct 23 – Nov 25	301328	Yes
2.1	Accelerating bovine tuberculosis control in LMICs – Phase 2 (Bovine Tb)	BMGF: $ 4,995,876 / FCDO: $ 1,660,000	Nov 23 – Mar 26	301328	Yes
2.1	Centre for Tropical Livestock Genetics and Health (CTLGH) - Phase 2	BMGF: $ 14,019,094 / FCDO: $ 3,400,000	Aug 22 – Aug 27	301328	Yes
2.1	Global Burden of Animal Diseases (GBAD) Phase II completion	BMGF: $ 1,498,298 / FCDO: $ 1,311,797	Feb 23 – Apr 24	301328	No
2.2	Cassava Horizons (follow on to ENSA – these figures include ENSA funding as it is a single grant)	BMGF: $ 23,485,053 / FCDO: $ 8,297,000	Oct 17 – Jun 25	300728	No
2.2	Combining Algal and Plant Photosynthesis (CAPP)	BMGF: $ 1,710,266 / FCDO: $ 753,123	Oct 23 – Sep 25	300728	Yes
2.2	Legume Technology	BMGF: $ 1,620,669 / FCDO: $ 1,100,000	Jan 24 – Feb 27	301554	No
3	Agricultural Technology Adoption Initiative (ATAI) – Phase II	BMGF: $ 4,593,784 / FCDO: $ 4,500,000	Nov 18 – Dec 24	300728	No

Closed projects that have been funded under this business case are:
- African Crop Epidemiology System (ACES)
- Next Gen Cassava
- Realising Increased Photosynthetic Efficiency (RIPE)
- West and Central African Virus Epidemiology for Roots and Tubers (WAVE)
- Global Burden of Animal Disease (GBADS)

Summary supporting narrative for the overall score in this review

Scoring
The portfolio overall has made good progress over the reporting period meeting output milestones for this review. The majority of projects are multi-year initiatives, some of which began receiving FCDO support during the previous phase of FCDO’s agriculture research partnership with the Bill & Melinda Gates Foundation (project 205273, 2016-2020). As a result, most projects were already well-established (ENSA, WAVE, CTLGH, ATAI, GBAD), and have made significant scientific progress. Others have built on the success of the partnership and have been launched in recent years (DEWAS, Legume Technology, CAPP).

This programme has received an ‘A’ grading for this year, with all projects on track and meeting (or exceeding) milestones. This is primarily a technology and innovation portfolio with a range of investments with different technology readiness levels, some of which are delivering solutions which are feeding in directly to uptake (e.g. wheat rust early warning and surveillance, new evidence on digital agriculture advisory services), others are further from application (e.g. improvements in photosynthetic efficiency in crops, alternative fertilisers or improvements in livestock genetics and health).

This scoring is based on four projects having interim reporting and three having full reporting in this annual review (see above). In this reporting period, in line with the recommendation in the last AR, a No-Cost Extension was approved to December 2026, in order to manage a smooth transition to the new business cases and close out the outstanding projects that will not transition.

Explanation for this annual review’s reporting and scoring
As noted in the last annual review, some of the projects in this programme are now aligned to the new APHID (301328) programme which integrates FCDO research investments in this thematic programme into one larger and agile programme platform, and will be transitioning to this business case. These projects will be reported against in full detail in the APHID annual review in June 2025 in order to provide a portfolio overview on plant and animal health and track wider lessons, recommendations and outcomes. However, payments have been made to these projects from this business case, and we have therefore included interim reporting in this annual review. Similarly, one other project, Legume Technology, will be reported in detail under the Delivering the Agriculture Breakthrough (301554) annual review in January 2025. The interim reporting for these projects in this annual review will therefore be light touch.

Key highlights
- WAVE: An example of recent success has been that WAVE Sierra Leone, WAVE Gabon and WAVE-Côte d’Ivoire have been selected to lead the plant health component in their respective One Health cross government coordinating units.
- New data and research to support bovine tuberculosis control in India and other LMICs, contributing to building a model for bovine TB control in developing countries
- Good early progress in two new programmes exploring novel approaches for creating higher-yielding crops that are robust in the face of climate change. These look at crop improvements via improvements in photosynthesis (CAPP), and improvements in cassava crops by exploiting soil microbes that enhance nutrient uptake in West Africa (Cassava Horizons).
- Several new policy briefs and insights from JPAL’s Agriculture Technology Adoption initiative include new policy insight on building farmers' resilience to climate change, which were shared in a variety of different media including a Voxdev podcast. There is some evidence of uptake of research in Niger (on approaches to promoting soil and water conservation techniques), in Kenya (on using mobile platforms to improve access to market information) and in India (on benefits of providing farmers with long-range, seasonal monsoon forecasts through SMS messages). ATAI continues to demonstrate success through the publication and sharing of policy briefs and in the uptake and scaling of findings from randomised controlled trials by governments, including in India and Niger. As the programme closes, the team is focusing on sharing lessons, data and findings, so further impact will be reported in the programme completion review.

Lessons learned
- Management approach: The transition to this new FCDO reporting structure via an integrated platform has some challenges, however it ultimately provides an opportunity to learn a broader set of lessons, better aggregate results, and ultimately demonstrate impact from this thematic portfolio. We intend to learn and improve this approach as we go in order to make the transition to these platform programmes successful.
- Cassava Horizons: This follow-on programme, building on years of discovery science through ENSA, shows the value of working with in-country partners and networks to apply potentially transformative science in specific and complex contexts. As this phase draws to an end in 2025, we will work with the Gates Foundation to maximise how we can learn from this approach and replicate in future, and build stronger southern partnerships.
- J-PAL ATAI: As J-PAL ATAI Phase II closes, we have reflected on the successes and challenges from this phase. In particular, we have noted the challenge of getting consistent policy uptake. Successes have been greatest around topics where there has been a concentration of RCTs. A potential future phase will aim to tighten the scope and align better with emerging FCDO and Gates Foundation priorities, so that the evidence can be integrated more quickly into programmes and policy advocacy. We would also encourage earlier publication of interim results and early findings.

Recommendations for the year ahead

- Recommendation 1: Work with the Gates Foundation to renew the secondment past June 2025.
- Recommendation 2: Use the Strategic Dialogue in February 2025 and related engagement to understand the emerging strategy for the Foundation in food and agriculture, including the shift towards more ambitious programmes. This provides an opportunity to align with FCDO priorities for translational research, proximate partnerships and drawing on expert science, including UK research expertise.

.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The theory of change for this programme is presented visually on page 26 of the business case (October 2019). The theory of change is supplemented by detailed results frameworks, developed by co-funded grantees. Grantees submit annual progress reports against these results frameworks to BMGF and FCDO. There has been no material change to the evidence base or to the assumptions underpinning the programme’s theory of change during this year of the programme.

This portfolio comprises a wide range of investments, all co-funded and directly managed by the Gates Foundation. These range from piloting and establishing a new systematic approach to plant health monitoring in sub-Saharan Africa, to development of new crop and livestock breeding technologies, to animal health control mechanisms, to the generation of policy-relevant, randomised control trial evidence on what works to promote agricultural technology adoption by smallholder farmers in sub-Saharan Africa and South Asia.

To capture this, the theory of change is pitched at a relatively high level. The three targeted outcomes, as described in the business case, remain:
1. Improved surveillance and control systems and prevention mechanisms developed to track plant pest and disease outbreaks, reducing risks faced by farmers, increasing agricultural outputs and catalysing rural markets
2. Tools and technologies in place to identify and respond to plant and animal health threats and mechanisms established to ensure uptake, reducing vulnerability and sparking economic growth in developing countries
3. Underpinning institutions developed, such as agricultural risk surveillance data-sharing arrangements, increased African research capacity, and establishment of policies to improve agricultural productivity, informed by evidence from this programme
The programme aims to contribute to the following impact: Sustainable global food systems in the face of plant and animal pest and disease threats, climate change, and the increasing scarcity of natural resources; increased agricultural productivity for smallholder farmers in sub-Saharan Africa and South Asia.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track – the no-cost extension will allow the programme to fully deliver expected outcomes and transition to new business cases.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The investments in this portfolio were co-selected by FCDO and BMGF based on their high potential for commercialisation and scaling, and/or for transformative impact for global agriculture. The tools and technologies supported through this programme continue to represent strong value for money for the FCDO. They are also aligned with FCDO priorities, particularly around climate and nature, as well as prevention and resilience to crises.

C: DETAILED OUTPUT SCORING

Output Title	A systematic approach to plant pest and disease control in sub-Saharan Africa
Output number:		1	Output Score:	A
Impact weighting:		40%	Weighting revised since last AR?	N/A
Indicator(s)			Milestone(s) for this review	Progress
Develop a scalable and sustainable monitoring and early warning advisory system for key wheat diseases in East Africa and South Asia			DEWAS on track with milestones in BMGF results tracker	On track
In 10 West and Central African countries, development of improved early detection and containment of cassava viral diseases			WAVE on track with milestones in BMGF results tracker	On track

Output 1 scores an A: / Both projects are contributing to building systematic approaches for plant health management in Africa and South Asia. Both projects will be reported against in detail in the APHID annual review. Interim updates can be found below.

Output 1.1: Monitoring and early warning advisory system for wheat diseases

Disease Early Warning Advisory System (DEWAS)
Brief description: A scalable and sustainable monitoring and early warning advisory system for key wheat diseases in East Africa and South Asia; for better preparedness, contingency planning, and control.
Focus countries: Ethiopia, Kenya, Zambia, Tanzania, Bangladesh, Bhutan, Nepal, Pakistan, India
Progress update: The DEWAS project is making good progress towards delivering against its milestones. Systems are being put in place, collaborations are being built and surveillance is underway. One particular highlight has been the stakeholder engagement with national agricultural research systems (NARS). One area to monitor will be the options for sustainability beyond the life of this project - the solution is valuable and impactful but its current model is reliant on donor funding and is not owned by an institution that would maintain this work. This will continue to be a focus for FCDO and the Gates Foundation, and will be reported against in the APHID Annual Review.

Output 1.2: Improved early detection and containment of cassava viral diseases in West and Central Africa

West and Central African Virus Epidemiology for Roots and Tubers (WAVE)
Brief description: A regional research initiative in Central and West Africa (CWA) which aims to improve viral disease diagnostics and the management and control of cassava brown streak and cassava mosaic disease in the region. Awareness raising and training of cassava value chain actors (farmers, producers' associations, seed multipliers, agricultural advisors, policy makers and plant protection agents) on cassava diseases, their impact and on agricultural productivity and management best practices to prevent the diseases and their spread.
Focus countries: Benin, Burkina Faso, Cameroon, Côte d’Ivoire, DRC, Gabon, Ghana, Nigeria, Sierra Leone and Togo
Progress update: In this final phase of work, WAVE is focusing on two main areas of work:
- WAVE is working to advance the response plans of two pilot countries by developing and testing a Functional Rapid Responses to Plant Infectious Diseases (RAPID) prototype system. RAPID relies on dynamic models for epidemic spread and management developed in collaboration with the University of Cambridge.
- WAVE is also focusing on the future sustainability of the project beyond this phase of funding. A key milestone, building on work in the last year, will be the upcoming convening of key plant health partners in Abidjan in February 2025 that aims to strategically review plant health activities in Central and West Africa, identify existing competencies and reach, establish partnerships for a collaborative Plant Health Alliance in Central and West Africa. Further updates will be provided in the APHID AR in June once we have engaged with key partners and reviewed outcomes of this convening.
- An example of recent success has been that WAVE Sierra Leone, WAVE Gabon and WAVE-Côte d’Ivoire have been selected to lead the plant health component in their respective One Health cross government coordinating units.
- This is based on WAVE’s contribution to community disease monitoring and reporting, as well as requisite laboratory testing, leading to the detection and molecular confirmation by WAVE of the East African Cassava Mosaic Virus Uganda strain (EACMV-Ug) in Guinea and Sierra Leone since August 2023. EACMV-Ug was responsible for the devastating Cassava Mosaic Disease (CMD) epidemic that broke out in Uganda and other East African countries in the 1990s but had previously not been established in West Africa. WAVE has been supporting the response since 2023.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes.

Recommendations for the year ahead
Recommendations will be made in the APHID annual review.
Output Title	New agricultural tools and technologies which increase productivity and build resilience to climate change, developed and adopted by smallholder farmers in sub-Saharan Africa and South Asia
Output number:		2	Output Score:	A
Impact weighting:		40%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 Scientific progress and development of improved livestock tools and technologies, including dissemination to, and adoption by, smallholder farmers in target countries	3 projects (Bovine TB, Centre for Tropical Livestock Genetics and Health and the Global Burden of Animal Diseases) on track with milestones in BMGF results tracker, including at least 2 examples of impact from scientific advances	On track: / Bovine Tb Phase II is on track / CTLGH is on track / GBAD II Completion is now closed
2.2 Scientific progress and development of improved crop tools and technologies, including dissemination to, and adoption by, smallholder farmers in target countries	2 projects (Engineering Nitrogen Symbiosis for Africa, Combining Algal and Plant Photosynthesis) on track with milestones in BMGF results tracker, including at least 2 examples of impact from scientific advances / 1 project (Legume Technology) on track, with full reporting and detail to be provided in the 301554 Annual Review.	On track: / Cassava Horizons and CAPP: Good progress on both projects. Impact examples below. / Legume Technology: On track, progress to be reported in 301554 AR.

Output 2 scores an A: / Output 2.1: Interim update – The projects remain on track and GBAD II is now completed. They will be reported against under the 301328 AR. / Output 2.2: Full update for two projects that have progressed well in this reporting period and remain on track. One project with an interim update, this new project will be reported fully under the 301554 AR. / The six projects under Output 2 remain on track during the reporting period.

Output 2.1: Improved livestock tools and technologies

Accelerating bovine tuberculosis control in LMICs – Phase 2
Brief description: A research initiative to accelerate progress on bovine tuberculosis control in India and other LMICs, as a model for bovine TB control in developing countries.
Focus countries: Ethiopia and India
Progress update: The project has made good progress, with at least 8 new peer-reviewed publications in this reporting period, and another 8 in progress for 2025. There were some delays in subcontracting in this first year, but these have now been resolved. Further detailed reporting will be presented in the June APHID AR, once the progress report has been reviewed.

Centre for Tropical Livestock Genetics and Health (CTLGH) - Phase 2:
Brief description: A global research alliance established and supported by FCDO and the Gates Foundation which aims to improve livestock-dependent livelihoods in the tropics, by improving the health and productivity of livestock in the tropical regions of Africa and South-East Asia.
Focus countries: Sub-Saharan Africa (new technologies in development and not yet deployed, but sub-Saharan Africa is target region)
Progress update: CTLGH Phase II aims to contribute to increased animal productivity and income for small-scale producers with livestock in tropical conditions. The Phase 2 investment will deliver new tools and technologies needed for effective dairy and poultry breeding platforms to deliver genetic inputs that are optimally adapted for varying local conditions in Sub-Sharan Africa (SSA) and Southern Africa (SA). A new Director was appointed in April 2024. There has been strong collaboration with related farmer-facing projects and animal breeding networks. Key results include:
- Key results in chicken:
  - Genomic referencing to improve bird responses to environmental challenges is on track
  - Successful culturing of enteroids as an in-vitro tool to select for resilience to gut health challenges
  - New candidate genes identified for environmental adaptation, based on Sequence Variance analysis
  - New gene edited surrogate host developed for biobanking; biobanking of indigenous chicken in Kenya, Uganda and Burkina Faso
- Key results for cattle:
  - Completion of CTLGH panel of African-wide cattle genome, published in Nature. This panel will be used to find candidate genes for parasitic diseases tolerance and climatic adaptation.
  - Optimised in-vitro assay is being developed for East Cost Fever tolerance.

Global Burden of Animal Diseases II (GBAD):
Brief description: A data initiative which aims to document, for the first time, a global evidence base on the health and economic impacts of animal health issues. This evidence base will underpin the optimisation of investments in animal health and welfare at global, national, sector and farm levels.
Focus countries: Global public good evidence targeted at policy and programming in Sub-Saharan Africa and South Asia. The main case study in this phase has been in Ethiopia.
Progress update: The GBADs programme has demonstrated progress in assessing the economic burden of animal diseases during Phase II and this completion phase. By systematically integrating data-driven methodologies into practical tools and enhancing scientific validation, the programme has contributed to how animal health burdens are understood and managed, both nationally and internationally. The donors have supported the ongoing development of the knowledge engine to maintain continuity as this phase of funding closes. The capacity building initiatives, particularly in Ethiopia, have empowered local stakeholders through targeted training and the development of essential resources like the living technical guides. As GBADs moves beyond Phase II, issues around continuity, governance, and the scalability of the work given data limitations will need to be addressed. This project has now closed.

Output 2.2: Improved crop tools and technologies

Cassava Horizons (spin-off to ENSA project)
Brief description: ENSA is an international research project that is engineering crops to be able to achieve biological nitrogen fixation using naturally occurring nitrogen. The Cassava Horizons project is a spin-off phase of the project which focuses on cassava crop improvement in West Africa by exploiting soil microbes that enhance nutrient uptake. The nutrient-scavenging arbuscular mycorrhizal (AM) fungi penetrate the plant root to exchange nutrients such as phosphates and nitrates for carbohydrates. AM fungi colonised roots are often associated with other bacteria that can enhance nutrient availability to the plant due to their nitrogen-fixing and/or phosphate-solubilising capacities. The Cassava Horizons project aims to dissect the AM-fungal responsiveness of West African cassava accessions genetically and to study the relevance of nutrient-providing root-associated bacteria in this interaction. To enhance the impact of the research, they focus on cassava accessions local to West Africa, for which relevant experimental protocols will be developed, enabling studies in laboratory and field conditions.
Focus countries: Sub-Saharan Africa (new technologies in development and not yet deployed, but sub-Saharan Africa is target region)
Progress update: This is the first annual review to report in detail on this phase of the project and it reports against four main achievement (below). In these early stages of work, Cassava Horizon’s main external impact has been on dissemination of the science through workshops, masterclass and presentations at conferences.

1. Culture collection of West African soil bacteria isolated from cassava roots: They established a cassava culture collection comprising more than 200 unique bacterial strains of distinct agricultural zones in Côte d'Ivoire. This collection represents a rich source for discovering strains with relevant plant growth-promoting traits and the characterised culture collection of cassava rhizosphere bacteria will be available through a public repository.
2. Yield increase and genetic diversity in mycorrhizal responsiveness of West African cassava cultivars: A screen house experiment in Côte d’Ivoire uncovered significant yield increase effects upon mycorrhizal inoculation of plants. Comparing 10 West African cassava accessions also found significant variation in AM responsiveness. Four accessions showed more than a 20% yield increase under the given growth conditions. These findings provide a unique entry to genetically dissect the AM responsiveness trait and develop markers that can be implemented in breeding programs.
3. Mycorrhizal responsiveness fast screening assay: They developed an experimental growth assay under laboratory conditions, which enables much faster measurement of root formation within 8 weeks post-planting .This assay allows a significantly higher throughput, and which will be used in Cote d’Ivoire and Nigeria. Additionally, the assay can be used for discovery research, like the in-depth characterisation of the AM-cassava symbiosis, the development of molecular markers associated with AM infectiveness, and/or to compare different inoculums. Using this assay, they uncovered variation in the onset of storage root formation upon AM inoculation. These data will be integrated with screen house and field experiments in Cote d’Ivoire and Nigeria to increase the screening throughput.
4. Protocols for the regeneration of African cassava accessions: To quantify the relevance of AM symbiosis in cassava cultivation, mutants in this trait are indispensable. Such mutants can be generated by CRISPR-Cas9 gene editing technology. However, this technology is available only for very few cassava accessions. They have developed a robust testing protocol for cassava in vitro culturing and regeneration, which has been implemented in four participating laboratories, three of which are in West Africa.

In these early stages of work, Cassava Horizon’s main external impact has been on dissemination of the science through workshops, masterclass and presentations. Although data obtained in the Cassava Horizons project have not yet been published, oral dissemination resulted in at least two new collaborative initiatives amongst international researchers.

Combining Algal and Plant Photosynthesis (CAPP)
Brief description: Meeting future global food demands will require novel approaches for creating higher-yielding crops that are robust in the face of climate change. A major opportunity for increasing the yields and resilience of crops lies in enhancing their ability to assimilate CO2, from which plants make sugars and starch for growth. The Combining Algal and Plant Photosynthesis (CAPP) consortium seeks to enhance CO2 assimilation in crops by endowing them with a specialised cellular compartment called the pyrenoid that has naturally evolved in eukaryotic algae and one lineage of land plants but is not present in crops. In addition to enhanced yields, it is expected that engineered crops will require less nitrogen and water, and may have improved high-temperature tolerance, reducing farmer inputs and making the crops more robust to climate change. Target crops that could benefit from a synthetic pyrenoid include wheat, rice and cassava. Wheat and rice are staple crops for large parts of South Asia and the Indo-Pacific, and cassava is a major carbohydrate source in sub-Saharan Africa.
Focus countries: Sub-Saharan Africa (new technologies in development and not yet deployed, but sub-Saharan Africa is target region)
Progress update: This phase of support focuses exclusively on Arabidopsis in order to prototype the process. The key milestone that the project seeks to achieve in this two-year grant is enhancement of CO2 uptake in the model plant Arabidopsis via a synthetic pyrenoid. The project is making good progress toward the aims to engineer a functional pyrenoid-based CO2 concentrating mechanism (CCM) into land plants. The team is well organized and focused on delivery of a prototype that increases confidence of the feasibility of engineering CCM into higher plants by the end of the investment. They are managing risk appropriately and have made several adjustments to the project to respond to technical challenges. The team has made good progress toward a prototype on two of the essential elements.

Legume Technology
Brief description: The project aims to develop techniques to measure biological nitrogen fixation in non-legumes so that potential inoculant products for maize can be evaluated, and if effective, to produce such inoculants in large volumes at high quality for small holder farmers in Sub-Saharan Africa. Second, the Project will scale up the rapid manufacturing of legume inoculants for use in small packs to supply the smallholder sector.
Focus countries: Sub-Saharan Africa (new technologies in development and not yet deployed, but sub-Saharan Africa is target region)
Progress update: After some initial delays in recruitment for key roles in the project, it is now on track and has made good progress in its first year. This project will be fully reported against in the Agriculture Breakthrough annual review.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
- Legume Technology was added to Output 2.2
- RIPE and Next Gen Cassava have now closed and are no longer included in Output 2.2.

Output Title	Enabling environment for agricultural innovation
Output number:		3	Output Score:	A
Impact weighting:		20%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of high-quality randomised control trials and pilot projects commissioned (ATAI Phases 1 and 2 – cumulative) to address high-priority agricultural evidence gaps	78 high-quality studies to be commissioned from ATAI Phase 2	Exceeded: Since 2009, ATAI has supported 85 research investments across 18 countries. ATAI has funded 45 full randomised controlled trials, 30 pilot projects, and 10 proposal development grants.
Number of projects producing at least one working paper, publicly available results report, or peer-reviewed publication (ATAI Phases 1 and 2 – cumulative)	29 projects (ATAI Phases 1 and 2 – cumulative)	Exceeded: To date, ATAI-funded research has resulted in 38 peer-reviewed publications and 25 working papers, with some projects generating multiple peer-reviewed publications. Thirty-five randomised controlled trials and 16 pilot studies have produced at least one working paper, publicly available results report, and/or peer-reviewed publication. There are 8 randomised controlled trials that are in the final stages of research implementation and/or analysis and due to submit preliminary results in 2025.
Number of new, publicly available policy briefs which synthesise multiple studies	2	Met: In 2024, ATAI produced two new policy briefs that synthesize evidence and policy lessons across multiple studies and geographic contexts.
Impact of high-quality evidence on policies and programmes	At least 1 illustrative example of adoption/impact of ATAI evidence on policies or programmes	Met: see below

Output 3 scores an A as achievements have been met or exceeded and the project has continued to deliver strong progress in this final year.

Agricultural Technology Adoption Initiative (ATAI) – Phase II

Brief description: This output area encompasses a rigorous evidence initiative – the JPAL Agricultural Technology Adoption Initiative (ATAI) – co-funded by FCDO and BMGF since 2011. JPAL ATAI has developed a portfolio of rigorous evidence from J-PAL and the Centre for Effective Global Action (UC Berkeley) which aims to inform policies and programmes to enable higher take-up of beneficial agricultural technologies leading to improved lives for the poor, and to define how specific microeconomic-level mechanisms can catalyse agricultural transformation in sub-Saharan Africa and South Asia. FCDO began co-funding ATAI Phase 2 with BMGF in 2018.
Focus countries: Sub-Saharan Africa and South Asia
Progress update: ATAI II was due to end in December 2024. The Gates Foundation is in the process of approving a short extension to ensure dissemination of results and to close out the studies. Discussions are also ongoing about supporting a follow-on phase of work that will focus on key FCDO and Gates Foundation priorities.
- Policy briefs: In 2024, ATAI produced two new policy briefs that synthesize evidence and policy lessons across multiple studies and geographic contexts.
  - Building farmers' resilience to climate change (September 2024): The policy insight incorporates evidence from ten randomised controlled trials (of which three are ATAI-funded studies) and three quasi-experimental evaluations.
  - Increasing small-scale farmers’ access to agricultural markets (December 2024): The policy insight incorporates evidence from sixteen randomised control trials (of which nine are ATAI-funded) and thirteen quasi-experimental evaluations.
- Evidence uptake:
  - In Niger, ATAI-funded researchers are collaborating with the Ministry of the Environment to fine-tune and scale farmer training on simple water catchment techniques like demi-lunes. This ongoing effort has reached around 15,000 households and builds upon an ATAI-funded randomised controlled trial that found that training alone increased the adoption of demi-lunes by 90 percentage points relative to villages that did not receive training, whereas financial transfers had little effect on adoption.
  - In Kenya, ATAI-funded researchers are partnering with Sauti East Africa, a social enterprise that empowers over 138,000 rural, women-led MSMEs to evaluate the impact of providing trade and market information through a mobile platform. This study builds on a randomised controlled trial funded by ATAI demonstrating that access to market information through Sauti’s platform led to an increase in cross-border trading, increased women traders profits, and reduced prices faced by consumers of these traded goods.
  - In India, ATAI-funded researchers are working with the Indian Ministry of Agriculture & Farmers’ Welfare to test and scale providing farmers with long-range, seasonal monsoon forecasts through SMS messages. This effort builds upon their randomised controlled trial that found that having access to relatively high-accuracy forecast information about the onset of the summer monsoons enabled farmers to make informed decisions, adjusting land under cultivation, input expenditures, and crop choice to improve outcomes.
- Major dissemination activities
  - ATAI at the Paris Peace Forum 2024: “The Future of African Agriculture" (November 2024). ATAI co-chair Tavneet Suri presented evidence from a newly published policy insight and moderated a panel that featured the researcher and implementing partner from an ATAI-funded study and FCDO representative.
  - Food Quality and Safety Workshop in Senegal (October 2024): In collaboration with the Interdisciplinary Policy-Oriented Research on Africa (IPORA) network, ATAI organised a two-day workshop in Dakar, Senegal.
  - Science Summit at UNGA79 (September 2024): ATAI co-organised a full-day event at the UNGA Science Summit in New York City with the Innovation Commission for Climate Change, Food Security, and Agriculture that attracted over 100 participants from government, philanthropic, and implementing organisations.
- Media Coverage:
  - Over the last year, ATAI researchers and staff released eleven blogs or written dissemination on seven different platforms. They have disseminated the new policy insight on building farmers' resilience to climate change, including via a Voxdev podcast (November 2024). ATAI staff also released a video summarizing the takeaways from the insight.
- Plans for close out of ATAI II: In 2025, we expect results from 8 randomised controlled trials and 7 pilots, which are currently in the final stages of research implementation or analysis. ATAI will continue to promote evidence uptake and use, with a focus on synthesizing evidence as themes emerge from the broader impact evaluation research ecosystem and ATAI portfolio, potentially including new policy insights on agricultural labor markets and groundwater management. In January, ATAI will launch an outreach campaign to spotlight a new policy insight, increasing small-scale farmers’ access to agricultural markets, and conduct evidence sharing sessions with policy partners such as the Word Food Programme (WFP). Discussions on any potential future phases of ATAI are ongoing.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes.

D: VALUE FOR MONEY

Key cost drivers and performance

For all projects within this portfolio, FCDO funding is channelled through the Gates Foundation to grantees. This funding arrangement is governed by the Gates Foundation-FCDO Collaboration Framework (2016-2026). The Gates Foundation directly manages all grantees in the portfolio. the Gates Foundation issues grant agreements on behalf of both the Gates Foundation and FCDO, manages the reporting and payment schedules, and shares progress reports, financial reports and annual audited statements received from grantees with FCDO. This represents significant value for money for FCDO, as it leverages the technical and programmatic capacity of the Foundation, as well as project co-investments.

FCDO and the Gates Foundation are large funders of agricultural research for development globally. By working in partnership, the two funders can target joint resources and expertise to address the most pressing needs in global agriculture. FCDO is able to harness the Gates Foundation’s capacity and expertise in agricultural technology prospecting and development, significantly reducing the inherent risks associated with R&D investments. Meanwhile, FCDO’s strategy of prioritising technologies with near-term pathways to impact focuses both funders on the identification of projects for co-funding with high potential for commercialisation and scaling. FCDO’s support to this portfolio of projects thus expedites the progress of promising technologies and innovations, with a very high success rate for an R&D portfolio.

The Gates Foundation covers the significant administrative and overhead costs of running these projects, without charging any management fee or overhead to FCDO. From an economy of inputs perspective, this partnership represents extremely high value for money. FCDO co-funds and steers the direction of a broad portfolio of R&D projects with strong potential for development impact, while maintaining very low transaction costs of managing the research.

Since May 2018, FCDO has seconded a staff member into the Gates Foundation to coordinate and support the partnership, with a new secondee taking over the role in March 2021 until June 2025. This role has significantly strengthened the efficiency, effectiveness and success of the partnership and discussions are ongoing about renewing this role beyond 2025. This post is funded through this programme.

VfM performance compared to the original VfM proposition in the business case

5 Es	Summary of performance
Economy	The Gates Foundation manages the grant portfolio directly and does not charge any management fee or overhead to FCDO. This is a key component of this programme’s VFM proposition. This is in addition to the significant monetary and in-kind contribution made by the Gates Foundation through their co-funding and direct management of the procurement process and handling all grant management.
Efficiency	The partnership between FCDO and the Gates Foundation has become increasingly efficient, in part because the two funders have now been working together on research in the agriculture sector for a number of years. The establishment of the FCDO secondment significantly strengthened the partnership between the two funders and facilitated closer involvement from FCDO in this portfolio. A review of the partnership is currently underway and recommendations will be reported against in the next annual review.
Effectiveness	Overall, the programme is on track to produce a stream of highly relevant agricultural technologies, scientific advances and evidence.
Equity	Gendered dimensions of agriculture are addressed by multiple projects under this portfolio, with some particularly strong examples of integrating gendered considerations – for example, ATAI and WAVE.
Cost effectiveness	This programme represented strong value for money over the reporting period, with co-funding from the Gates Foundation, and a significant in-kind contribution through their direct handling of all the grants and procurement, on behalf of both funders. There are also important returns for the levelling up agenda, with UK partners in Edinburgh and York.

Assessment of whether the programme continues to represent value for money

The programme continues to represent value for money. By harnessing the Gates Foundation’s considerable technical expertise and grant management capacity, FCDO is able to co-fund a diverse portfolio of highly relevant research projects, which it would struggle to identify and manage through any other delivery route. There is significant value for money in this type of collaboration between two of the major funders of research in agriculture. The overarching partnership with the Foundation leverages significant R&D resources into the UK. The transition of some projects to two new business cases demonstrates the continued relevance of this work to FCDO priorities.

E: RISK

Risk category	Gross risk description	Mitigation strategy	Residual risk rating	Risk rating changed from business case?	Likely trajectory of risk severity (to Jan 25)
Delivery	Managing budget uncertainty	The FCDO programme teams are working closely with the Gates Foundation counterparts to successfully mitigate uncertainty. However, there remains a risk of the pipeline of jointly funded research slowing for new investments and this should be prioritised in the year to come.	Moderate	Yes
Innovation / Intellectual	The CAPP and Cassava Horizons projects are particularly innovative initiatives, attempting advances at the forefront of crop science. If successful, these projects could have transformative effects for global agriculture. However, the cutting-edge nature of the scientific objectives pursued means they are high-risk projects, with inherent potential for failure.	The Gates Foundation provided the initial funding to ENSA for several years before FCDO co-funding commenced, developing both initiatives from early concept. CAPP is a pilot project that aims to test viability before scaling takes place. FCDO’s involvement by selecting both projects for co-funding is key to expedite progress. Before proceeding to funding, FCDO agreed a robust process for stage-gating and a set of go/no-go decision points, to enable rapid course-corrections if particular lines of scientific enquiry do not prove to be fruitful. / While this risk remains moderate, it is within the FCDO Agriculture Research team’s risk appetite. Particularly in the context of climate change, there is a need for agricultural research to deliver transformative solutions which can increase agricultural productivity. FCDO’s investments in these types of technologies are part of a broader portfolio of agricultural R&D investments and FCDO balances risk against the potential for transformative impact for global agriculture.	Moderate	No change
Context	Strategy could change within the Gates Foundation, affecting the priority given to working in partnership with FCDO on the development of agricultural technologies for smallholder farmers.	The priorities of the Gates Foundation Agricultural Development team are evolving. There is still appetite within the Gates Foundation for continuation of the strategic agricultural technology development partnership with FCDO, but close engagement as the strategy refresh takes places will be crucial to ensure future alignment. The secondment role is key to delivering this.	Moderate	Yes
Safeguarding	There is a risk that, across a portfolio of projects working to develop new diagnostic tools and technologies, issues around gender and social inclusion are not sufficiently well integrated. This would mean the end-products would not be suitable for all intended beneficiaries.	FCDO’s safeguarding standards and requirements are incorporated in the grant terms of all the Gates Foundation/FCDO co-funded grants.	Minor	No change
Fiduciary	The Gates Foundation supports the oversight of the grant management. Risk that this is not done in alignment with FCDO’s compliance and assurance requirements.	FCDO is updating the due diligence and is confident that the Gates Foundation has robust due diligence, whistleblowing, fraud and corruption policies and procedures. The FCDO also has a secondee in place who supports the Gates Foundation with the grant management and who has close oversight of the projects.	Minor	No change

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

For all projects within this portfolio, FCDO funding is channelled through the Gates Foundation to grantees. This funding arrangement is governed by the Gates Foundation-FCDO Collaboration Framework (2016-2026). The Gates Foundation directly manages all grantees in the portfolio. The Gates Foundation issues grant agreements on behalf of both the Gates Foundation and FCDO, manages the reporting and payment schedules, and shares progress reports, financial reports and annual audited statements received from grantees with FCDO. The grant agreements between the Gates Foundation and grantees include all of FCDO’s core requirements – including, for example, the requirement for an annual audited statement from co-funded grantees – and has been reviewed and approved by FCDO’s assurance teams.

Progress reports, financial reports and annual audited statements have been submitted on time (per the Gates Foundation reporting schedules) by all grantees during the reporting period. FCDO SRO/Lead Adviser approval of grantees progress reports and their annual audited statement is required before payment is released. Payment is then made in US Dollars to the Gates Foundation for onward transmission to the grantees. Throughout the reporting period, FCDO engaged closely with the Gates Foundation Programme Officers to track progress on the grants, particularly through the FCDO secondee role.

Monitoring
The Gates Foundation maintains regular contact with FCDO on grantee progress and emerging issues. Additionally, the FCDO seconded staff member to the Gates Foundation from March 2021 continues to coordinate and support the partnership building with frequent visits to both the Foundation and overseas to the jointly funded projects. This role is supported by a FCDO Programme Manager. Both roles are strengthening the efficiency, effectiveness, and success of the FCDO-the Gates Foundation partnership. Going forward, some projects will be integrated into the APHID and Ag Breakthrough annual reviews. Our technical consultant on animal health will support this review.

Compliance with FCDO requirements
- This programme is compliant with the 2014 Gender Equality Act. The portfolio of research projects works to deliver new agricultural technologies and research products which will increase agricultural productivity and improve both men and women smallholders’ resilience to climate change, diseases and pests in sub-Saharan Africa and South Asia. Gender issues are considered at the design stage of each grant.
- The portfolio’s compliance with the International Aid Transparency Initiative (IATI) is under review as part of the Due Diligence process.
- Asset and risk registers: Assets and risks are reviewed in the progress reports and the annual reviews. Both of these processes will be reviewed through the Due Diligence process and updated if needed.

Approach to the Annual Review
This Review was conducted by the Lead Adviser. The Review draws on annual reports from grantees to the Gates Foundation, additional supplementary information provided by the Gates Foundation, and discussions with the Gates Foundation Programme Officers.

Key Documentation:
- Programme logframe
- Programme business case
- Progress reports from all grants, submitted to the Gates Foundation

Date of last narrative financial report	Grantees each submit financial reports and audited accounts at different points during the year, depending on the reporting schedule in their grant agreement with the Gates Foundation. All audited accounts requirements are up to date.
Date of last audited annual statement