## Annual Review Template

Title: The Global Polio Eradication Initiative (GPEI)
Programme Value £ (full life): UK £125m (reduced from £400m)		Review date: April 2025
Programme Code: 300739	AMP start date: 19/10/20	AMP end date:

Summary of Programme Performance
Year	2021	2022	2023	2024
Overall Output Score	A	A	B	B
Risk Rating	Major	Major	Major	Major

DevTracker Link to Business Case:
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

Since its establishment in 1988, the Global Polio Eradication Initiative (GPEI) has successfully led global efforts that have reduced Wild Polio Virus (WPV) cases by over 99%.  From 350,000 cases in 125 countries in 1988, to 99 cases in 2024 with only two countries considered endemic - Afghanistan and Pakistan. Between 1988 and 2020, USD $17 billion has been provided by public and private donors, with the UK contributing £1.4 billion in total since 1995.

Investing in GPEI enhances global health security; GPEI improves global health surveillance and response capability, contributing to stronger health systems, and reducing the risk of future global health threats.

UK funding to GPEI in the initial Business Case for this programme has been reduced from a £400m commitment for April 2021 – March 2024 to a current £125m commitment from April 2021 - March 2025 due to UK Overseas Development Aid (ODA) reprioritisation (c70% reduction). This review reflects the ongoing prioritisation and refocusing of resources.

An Acronym list has been included at Annex A

Summary supporting narrative for the overall score in this review

In 2024 the programme moderately did not meet expectations, scoring a B.  Although overall each output did not meet expectations and eradication targets are off track, there has been progress across outputs with many indicators meeting expectations or showing improvements from 2023.

The score reflects the situation in the endemic countries, Pakistan and Afghanistan, where there has unfortunately been a setback in the programme. Throughout 2024 there has been an increase in cases and environmental positive samples (which show the virus continues to circulate), including from the seemingly cleared historical reservoirs. This means GPEI are now off target to meet the interruption of transmission of WPV1 by the end of 2025.

The Polio Programme has been through an incredibly difficult year in 2024. GPEI Director Aidan O’Leary died unexpectedly on 6 August. His leadership and commitment to Polio Eradication, which are universally recognised, have been a huge loss to the programme and to broader international development efforts.

GPEI has rallied and continued its efforts to make the key tactical shifts needed to reach eradication and have remarkably facilitated two high risk and complex poliovirus campaigns in Gaza in 2024. A new Director for Polio Eradication has now been recruited and been in post since March 2025; Dr Jamal Ahmed brings strong experience at both the AFRO and global level of collaboration towards polio eradication.

Output	Score
Polio campaigns yield a high population immunity	B
High poliovirus detection capacity	B
Integrated service delivery expedites eradication progress	B
Political will secured and coordinated transition planning in place	B

GPEI’s two goals:

Goal 1: Interrupt All Poliovirus Transmission in Endemic Countries
Goal 2: Stop Transmission of Variant Poliovirus and Prevent Outbreaks in Non-endemic countries.

In October 2024, the Polio Oversight Board (POB) officially extended the GPEI’s 2022 – 2026 Strategy to the end of 2029 extending the timeline for certifying the eradication of wild poliovirus type 1 (WPV1) to the end of 2027 and certifying the elimination of type 2 variant poliovirus (cVDPV2 to the end of 2029, as shown below). GPEI extended their strategy with a Strategy Extension Document to outline their planned tactical shifts to reach the new targets.[1]
[1] polioeradication.org/wp-content/uploads/2024/11/GPEI-Strategy-extension-20241113.pdf

Goal 1

Goal 1 has faced a setback, with WPV1 cases rising to 99 in 2024 (74 in Pakistan and 25 in Afghanistan) compared to 12 in 2023. This increase, along with wastewater detections, signals widespread transmission in Pakistan and an intense outbreak in southern Afghanistan. Challenges include insecurity, political transitions in Pakistan, less effective site-to-site campaigns in Southern Afghanistan, vaccine hesitancy, logistical difficulties in remote areas, and misinformation affecting vaccination efforts.

Both programmes are revising their national emergency plans to improve vaccination coverage, reduce transmission, and enhance early detection and response to outbreaks. Despite aiming to stop transmission by the end of 2025, this goal appears increasingly unlikely as of April 2025.

Pakistan Overview:
- 74 cases in 2024, up from six in 2023
- 628 environmental samples for WPV1 reported in 2024.
- Most cases and environmental samples are reported from Balochistan Province, Sind and Khyber Pakhtunkhwa provinces.
- The epidemiology indicates intense transmission in the Southern Corridor (Kandahar-Helmand-Quetta); a downward but continuing trend of transmission in the Northern Corridor (Peshawar-Nangarhar-Kunar) and Karachi; and continued endemic transmission in South Khyber Pakhtunkhwa (Central Corridor).

In Pakistan, political transitions (to a caretaker administration at the end of 2023, before elections in February 2024 where the previous Prime Minister was returned to power but through a coalition government) have had a negative impact on the Polio Programme. Gains made in 2023 were not able to be maintained and the pre-election period was a key factor in triggering the wild poliovirus resurgence during 2024. Security concerns, particularly in south Khyber Pakhtunkhwa Province where there have also been boycotts of the polio vaccination campaigns, have continued to be a challenge to the programme and have meant that a number of campaigns have had to be shortened which is sub-optimal. With the new coalition Government, the programme in Pakistan has developed a new strategy focusing on management and accountability to address the setback. Work to address these challenges includes:
- An aggressive Supplementary Immunisation Activities (SIAs) schedule, including four synchronized SIAs before June 2025.
- Working in collaboration with Gavi, on the implementation of Big Catch Up (BCU) and improving Routine Immunisation (RI) coverage in core reservoir areas to increasing the vaccination of zero dose children. The programme has sustained strong political commitment in country.
- Increased security protection for vaccination teams in key areas
- Strengthened efforts to build trust within communities in key areas to combat vaccine hesitancy and misinformation.
- Better distribution of resources to ensure effective vaccination efforts in remote and high-risk areas.
- Enhanced coordination between health organizations and improved training for vaccination teams to increase the effectiveness of campaigns

Afghanistan Overview:
- 25 cases in 2024 up from six in 2023.
- 113 environmental samples for WPV1 reported in 2024.
- Most cases and environmental samples are reported from the Southern region with just two cases reported from Eastern region of Afghanistan.
- Vaccine campaign modality in the Southern region remains site to site rather than house to house, resulting in sub-optimal coverage for more than two years, which has left a substantial pool of under or unimmunized children.

In Afghanistan, the shift from house-to-house to site-to-site vaccination campaigns after the Government prohibited house-to-house campaigns in August 2024 has had a significantly detrimental impact on the programme. During the first two quarters of 2024, when house-to-house campaigns were still in place, the number of missed children was approximately 150,000. However, when the programme moved to site-to-site campaigns the number of missed children rose sharply to around 706,613

In response to this rise in missed children the programme revised its strategy increasing the number of vaccination sites to a ratio of one site per every three to five houses, aiming to mimic the effectiveness of house-to-house campaigns as closely as possible. This new modality showed promising results, with the number of missed children beginning to decrease significantly. For example, by the end of 2024, the revised site-to-site campaigns in Kandahar and Helmand had reduced the number of missed children to approximately 300,000

This improvement was largely attributed to the increased accessibility of vaccination sites and the strong support from community influentials, including religious leaders, Shuras, and tribal elders. For example, religious leaders in Kandahar have been organizing community meetings to educate families about the importance of vaccination, while Shuras in Helmand have been coordinating with local health workers to ensure vaccination sites are accessible. Tribal elders in remote areas are also helping to identify suitable locations for vaccination sites and assisting in the transportation of vaccines

Goal 2 Overview

Overall cases of vaccine derived polio (cVDPVs) are lower than in 2023, with cVDPV2 cases reported down to 295 in 2024 from 395 in 2023, and cVDPV1 cases down to 17 in 2024 from 133 in 2023. While huge progress is being seen in the Democratic Republic of the Congo (DRC) and Somalia towards ending transition, the cVDPV2 transmission continues in Northern Nigeria, adjoining areas of the Lake Chad Basin countries, Algeria and Ethiopia. In Yemen a total of 35 cases are reported in 2024 but due to insecurity the sample shipments are currently stopped so numbers could be higher.

- In 2024 95 vaccination campaigns were implemented using 506m doses of novel oral polio vaccine type 2 (nOPV2) across 35 different countries. And 15 campaigns using 106 million doses of bivalent oral polio vaccine (bOPV).
- A global outbreak response plan for African countries was finalised for 2024, focussing on stopping the transmission in North-West Nigeria; Eastern DRC; South-Central Somalia and Northern Yemen.
- Huge progress was seen in DRC, with only 15 cases of cVDPV2 reported in 2024 compared to 120 in 2023.
- cVDPV2 was reported from the wastewater samples collected from Gaza. The programme was able to mount two rounds of novel OPV2 (nOPV2) responses in Gaza under very difficult political and security situation in close collaboration with key stakeholders. Despite extremely difficult circumstances 556,774 children under the age of 10 were vaccinated with two doses of polio vaccine achieving 94% coverage of the target population. There has been an additional round in 2025.
- cVDPV2 reported in the wastewater in Europe (Spain, Poland, Finland, Germany and UK)
- No cVDPV1 reported from any source from Madagascar since over last 18 months and program plans to undertake an assessment to ultimately declare this outbreak as over.
- No cVDPV1 is reported from Southeastern African block (Mozambique, Malawi) since May 2024

The 2024 outbreak response was hindered by nOPV2 vaccine supply disruption, preventing full implementation of plans. WHO granted prequalification for a second supplier in July 2024, ensuring sufficient stockpile since Q4 2024. Despite these challenges, evidence shows that the nOPV2 vaccine maintains enhanced genetic stability, reducing the risk of causing paralysis in low immunity settings compared to monovalent oral polio vaccine type 2.

Conflict, insecurity, and difficulties in accessing children for vaccination remain a significant challenge in parts of North Nigeria, Eastern DRC, North Yemen, and South-Central Somalia. The programme continues to assess area-specific issues and formulate and implement tailored action plans to address these challenges. These revisions include negotiating access, adapting SIA schedules and operations, sampling older age groups, and increasing target populations.

DRC case-study: The decrease in cVDPV2 cases in DRC from 120 cases in 2023 to 15 cases in 2024 demonstrates the effectiveness of international outbreak response guidelines when fully implemented. The reduction is attributed to increased vaccination efforts for children in high-risk areas, the use of nOPV2, enhanced surveillance to identify and respond to new cases and outbreaks, greater involvement of local community influencers in promoting vaccination and addressing vaccine hesitancy, and geographic targeting focused on provinces with the highest incidence of cVDPV2.

Gaza: GPEI in collaboration with partner agencies, led an impressive response in Gaza under exceptionally difficult security conditions, following environmental samples of cVDPV2. Key factors for success included strong community engagement with community leaders helping to build trust and encourage families to participate in the vaccination campaigns, negotiating coordinated humanitarian pauses to allow vaccination teams to access areas previously unreachable due to security, and robust surveillance systems which allowed early detection and response. These factors – community involvement, coordination with local authorities to facilitate access to high-risk conflict zones, enhanced surveillance and flexibility can be adopted in other geographies.

Programmatic Progress

As outlined above, GPEI has made varied progress against its amended 2022-2026 strategy. There have been notable efforts and advancements in certain areas. There has been a consistent emphasis on campaign quality in endemic regions and rapid outbreak response. The prohibition of house-to-house campaigns in Afghanistan has been a significant challenge for the programme; however, GPEI has maintained an advocacy plan with Afghanistan, who participated in the Independent Monitoring Board (IMB) meeting in July.

Surveillance in endemic countries remains robust. In the AFRO region, logistical challenges continue to cause delays as samples often need to travel internationally to two destinations for sequencing. GPEI’s Global Surveillance Action Plan work in this region is expected to take effect in 2025 when new laboratories become operational. However, recent budget changes have put this at risk beyond 2025. GPEI is working with WHO Regional Offices and Finance Team on prioritising surveillance and laboratory functions, contributing to a prioritisation exercise led by the Strategy Committee (SC).

Regarding integration, GPEI has made progress, and there has been an increase in the number of campaigns implemented with another antigen or polio plusses (where another service is provided alongside the polio vaccine). 45% of all outbreak country campaigns in 2024 were integrated, and 75% in the endemics. However, there is more work required to systemise and record this integration—a joint Gavi Board and POB meeting is scheduled for 2025 to enhance collaboration between the two organisations.

GPEI continued to operate under significant financial constraints in 2024, although all prioritised activities were funded. They succeeded in attracting new donors and optimising their funds with dynamic budgeting. The US Government's withdrawal from WHO will have significant impacts on funding GPEI’s programmes beyond 2025, necessitating further prioritisation.

Progress on 2023 recommendations:

Recommendation	Progress made
As GPEI make an addendum to their strategy to include extended targets for eradication they will need to provide a full analysis on why targets were not met, and how they will change their operations to make corrections and ensure that the revised targets are achieved. GPEI will need to be realistic about what is feasible for the remainder of the strategy, incorporate lessons from the t >b OPV switch, and provide milestones to be met for eradication to be successful.	GPEI strategy addendum was agreed at the POB in October 2024 and included key tactical shifts needed for eradication of Poliovirus. This addendum included lessons from the t >b OPV switch.
GPEI focus on integration should be enhanced over 2024, particularly in light of Gavi’s 6.0 strategy being finalised. The importance of integration is understood well across GPEI but they need to move to more intentional focus, leveraging the extensive experience of GPEI front line workers in reaching unreached communities and working in partnership with Gavi to develop clear accountability for IPV coverage, and country level changes in how routine immunisation and polio teams share data to strengthen routine immunisation.	GPEI has been working to increase the priority given to IPV coverage by its relevant partners. Although accountability for IPV lies with country governments, Gavi, IVB and their associated governance mechanisms GPEI has been making the case for the huge impact this has on polio eradication efforts. / The GPEI Integration function intends to increase efforts in 2025 to further develop its RI strengthening approach – in particular on the “post-campaign handover” between GPEI and EPI and the steps that can be taken to maintain population immunity once GPEI campaigns stop.
GPEI must retain their focus on accountability and monitoring structures for polio transition (as presented to the POB in Oct 2023). Significant progress has been made over 2023 on clarity of how different parts of WHO will be responsible. GPEI should carefully consider how to increase country capacity and willingness to self-finance and develop -with partners and implementing countries- global accountability mechanisms for the delivery of polio transition.	Discussions on transition have continued over 2024 with the Polio Cessation Strategy in Phase 1. There will be a discussion on GPEI dissolution in October 2025.
GPEI must work to ensure they have the data for all Key Performance Indicators (KPIs) to enable them to make informed strategic decisions. There has been mixed progress on data for gender, age disaggregated data is still missing for endemic countries, and integration reporting is patchy. Where data is not possible GPEI must look into alternative accountability measures or adapt KPIs.	With the Strategy Extension in 2024 new KPIs have been agreed. Data availability was a key consideration when selecting these indicators. The new KPI framework includes indicators to track progress in reporting sex disaggregated data and more comprehensive reporting on Integration. / For the Annual Review indicators have been adapted and all but one have been reported on.
GPEI should consider reporting to donors, through the Strategy Committee, a high-level summary of GPEI sexual exploitation, abuse, and harassment (SEAH) cases and action to address them, on a 6 monthly/annual basis.	The UN prepares a summary of cases across the UN system in the annual report “Special measures for protection from sexual exploitation and abuse: Report of the Secretary-General" and the WHO Sexual Misconduct and Abusive Conduct Investigations Dashboard documents cases and action taken on a quarterly basis.

Recommendations for the year ahead

Accountability Framework: To ensure revisions to the programme are implemented with an accountability framework clearly setting out tactical shifts, responsibilities and check points to revise actions where needed. This process should draw on the risk and performance review and the recommendations from the 2019 and 2025 Governance reviews and include actions from IMB recommendations.

Integration: GPEI’s joint meeting with Gavi scheduled in June 2025 must be the catalyst for institutionalised collaboration to strengthen coverage and measurement of polio-containing vaccines (IPV and Hexa) in eligible countries; improving integration of GPEI and Gavi-financed campaigns and enhancing health systems cooperation including zero dose identification and targeting, data and gender. GPEI and Gavi must developing a joint workplan to achieve these shifts with an agreed measurement framework and accountability processes.

Gender: To build on progress in this area GPEI must strengthen leadership accountability on gender mainstreaming efforts and demonstrate commitment to how pivotal female workers across organisational structures are to polio eradication. The IMB report recommends that gender should be a mandatory and core part of the discussions on planning and delivery of the Polio Programmes, and that more women in supervisor and senior roles could enhance the most critical layer of the programme: performance and oversight.

Risk management: GPEI should clarify and clearly communicate how risk is managed within each of the partners and how partnership-wide risks are escalated and managed through its governance structures. GPEI should take accountability for safeguarding and fraud risks across the programme and incorporate these into the risk and performance report.

PCS: Through the member state consultation on the Polio Certification Strategy (PCS) GPEI partners, specifically the WHO, should ensure that endemic countries and consequential geographies are supported in fully engaging in the opportunities and risks of the strategy ahead of endorsement at the 2026 WHA.

Safeguarding: Given the high risk of SEAH in the Polio Programme there should be a mechanism for the Polio Programme to have disaggregated information on allegations, still maintaining confidentiality. This would allow targeted mitigation activities, and provide assurance that any efforts which are being made by the programme are having a positive effect.

The FCDO will require a quarterly check-in to review actions on recommendations from the Annual review and DDA.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme's theory of change outlines that financial, political, and governance assistance from the UK will support GPEI to function as an effective partnership providing immunisation and surveillance services needed to achieve polio eradication. The steps needed to reach these outcomes and impacts remain valid, and the underlying assumptions are consistent with implementation experience. However, due to broader ODA reductions in 2020, the spending review adjusted UK funding for 2022-2025 to a considerably lower level (£125m) than initially proposed in the original Business Case (£400m). To manage this reduction, GPEI has partially relied on early contributions from the Gates Foundation and introduced a dynamic budgeting and risk-based prioritisation framework.

Recent funding cuts to GPEI, including the US withdrawal from WHO, present additional challenges. While funding for 2025 is secured, GPEI is currently undertaking a prioritisation exercise for subsequent years, where funding is expected to be significantly reduced compared to previous years.

Despite the reduction in UK funding, the UK has maintained substantial influence within the programme. Until December 2023, the UK represented all sovereign donors on the Strategy Committee (SC). Although Canada has now taken this position, the UK remains actively supportive of Canada's efforts and continues to advance its priorities through the donor consortium seat for the SC and the POB, as well as directly engaging with the GPEI secretariat and WHO, including through the UK's Core Voluntary Contribution to WHO.

There have been several iterations of GPEI's Key Performance Indicators (KPIs) since the inception of the programme, and the POB approved a new set of KPIs with the 2024 Strategy Extension. FCDO has endeavoured to monitor progress using GPEI indicators as much as possible to reduce the burden on GPEI and ensure appropriate measures are in place to assess progress and make necessary adjustments. Additionally, as highlighted in the 2023 A/R, GPEI was unable to report on certain indicators, prompting a recommendation to address this issue. Consequently, further changes to A/R indicators have been implemented in 2024. These changes are detailed in each output table for clarity.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Despite setbacks in 2024 it remains possible – and highly desirable – to eradicate polio. GPEI has proven its effectiveness as a programme by reducing WPV cases over 99% since 1988 and reducing endemic countries to just Afghanistan and Pakistan. Twenty million people would have been paralysed without GPEI's efforts, saving over $27 billion in healthcare costs and productivity losses since 1988[2]. The last mile is always the most difficult and the operating environment in the affected regions in Afghanistan and Pakistan is very challenging. However, the programme is adapting lessons-learned from the resurgence of cases in Afghanistan and Pakistan in 2024, including opportunities to reach Afghani returnees from Pakistan. Ending eradication efforts could lead to a global resurgence of polio, with the cost of managing a perpetual polio epidemic likely exceed the costs of the current eradication effort. It is estimated that controlling polio and treating survivors would cost over $1 billion per year for years to come[3].
[2] https://www.weforum.org/stories/2017/01/6-key-numbers-in-the-fight-to-end-polio/
[3] Zimmermann M, Hagedorn B, Lyons H. Projection of Costs of Polio Eradication Compared to Permanent Control. J. Infect. Dis. 2019;221(4):561–5. doi:10.1093/infdis/jiz488.

Given the UK has invested £1.4bn so far, withdrawing from the programme before eradication is achieved would be poor value for money. The UK is GPEI’s only fully flexible funder. Flexible funding allows GPEI to allocate funds to outbreaks of cVDPV quickly, which is crucial in preventing spread and has supported GPEI’s response in Gaza.

Investment in polio contributes to strengthening global health security, as demonstrated during the COVID-19 pandemic when polio surveillance systems and infrastructure were extensively leveraged in the global response. GPEI continues to provide foundational support in many fragile and humanitarian settings, such as in South Sudan, where they provide foundational support for vaccine preventable disease surveillance. This is increasingly important with upcoming budget gaps across global health.

Poliovirus has recently been detected in sewage samples in London and other European countries. While there have been no confirmed cases of polio-related paralysis in the UK, the detection highlights the active spread of the virus and the risks of a global resurgence.

Taken together these are all good reasons for the UK to continue investing in GPEI. However, given the UK Government’s decision to reduce the UK’s ODA spend to 0.3% GNI difficult decisions will need to be made regarding where UK ODA will have the most development impact and deliver on UK priorities. Future funding to GPEI will be decided within this broader context.

## C. DETAILED OUTPUT SCORING

Output Title	Polio Campaigns yield a High Population Immunity
Output number:		1	Output Score:
Impact weighting (%):		25	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1: % of all Supplementary Immunisation Activities (SIAs) achieving LQAS pass rate (measurement: compliant SIAs/total SIAs) / (scope limited to NID and SNID. For endemics and outbreaks) =>The data may not be exhaustive. EMU report to the SC mentioned ~100 SIAs implemented in 2024. May need to anticipate them cross-checking info	80%	88% (PAK), / 33% (AFG) / 48% (OBR) / B: Moderately did not meet expectations / * Note that this indicator is revised. 2023 A/R indicator was ‘% of supplementary immunisation activities (SIAs) where awareness was >80% of all households.
1.2: % of female front-line workers per SIA nationwide in endemic countries.	70% Pakistan / 50% Afghanistan	Pakistan: 66% (average of 4 quarters' data) / Afghanistan: 27% (average of 4 quarters' data) – increased to 33% by Q4 / B: Moderately did not meet expectations / * Note that this indicator is revised to measure nationwide rather than priority subnational areas in endemic countries.
1.3: % of missed children nationwide in endemic countries / Note: include outbreak countries in narrative and look to incorporate in future.	2% Pakistan / 2% Afghanistan	Pakistan: 2.6% (median) / Afghanistan: 8% (median) / B: Moderately did not meet expectations / * Note that this indicator is revised to measure nationwide rather than priority subnational areas in endemic countries.
1.4: % of outbreaks stopped within 120 days of outbreak confirmation (scope of outbreak countries)	70%	93% / A++: Outputs exceed expectations / * Note that this indicator is revised. 2023 indicator measured % of countries implementing outbreak response (OBR) round 1 within 28 days of confirmed outbreak.
1.5: % Funds for outbreak campaigns allocated to countries within 48h of receiving the budget request Include challenges encountered in narrative	90%	85% / B: Moderately did not meet expectations / * Note that this indicator is revised. 2023 indicator measured % of districts that have funds available at least 72hrs prior to SIA start.

B: Moderately did not meet expectations

The indicators for this output have all been adapted for 2024 year to align with GPEI KPIs and to ensure the data was available. It is therefore difficult to make comparisons with 2023.

Insecurity and political instability remain a persistent challenge to this output: in southern Khyber Pakhtunkhwa province in Pakistan, in East and Northeast DRC, North Yemen, Sudan, Gaza, South-Central Somalia and Afghanistan. For each of these geographies very specific strategies tailored according to context are in place. In Afghanistan, the main challenge was campaign modality with house-to-house rather site to site campaigns prohibited since August 2024. In consultation with community influencers the programme has now implemented a strategy to increase the number of sites, with a ratio of one site per 3-5 houses to ensure as close to the houses as possible but supported by religious and community leaders.

The Lot Quality Assurance Sampling (LQAS, which accesses the quality of campaigns), pass-rate was exceeded in Pakistan in 2024. Although missed overall in Afghanistan, this was due to the change in campaign modality rather than poor overall programmatic performance. In 2024 80% of those campaigns which were able to be completed on a house-to-house basis did reach the pass rate, compared to less than 20% in areas using site-to-site or mosque-to-mosque approaches. Unfortunately, due to the restrictions of the Taliban, all three campaigns in Q4 of 2024 were implemented through site-to-site.

Over 2024 there has been a significant improvement in the ratio of female front-line workers in both countries. GPEI’s gender programme is robust, and it is recognised that in Pakistan female frontline health workers are the backbone of the Programme. Each team has at least one woman, ensuring access to mothers and children. In Islamabad and Sindh provinces there is a high percentage of female front-line health workers (71% and 68% respectively).

Tellingly the provinces where it is the hardest to increase the number of female front-line health workers - Balochistan Province (35%) and Khyber Pakhtunkhwa Province (45%) are historically the two endemic provinces. These two provinces practice gender conservative norms more strictly compared to the other provinces. The security situation further adds vulnerability to the female frontline health workers for gender-based violence or character assassination as working women are perceived negatively as per local gender norm. To concentrate approaches the polio Programme has segregated priority sub national areas. The ratio of women in frontline workforce in these sub national areas indicate lowest coverage in Killa Abdullah (17%) and South Khyber Pakhtunkhwa (35%).

The Gender Mainstreaming Group’s Listening Project in Pakistan is in its second phase – ensuring that the perspectives of the female front-line health workers on the challenges are addressed by the Programme – this has included the implementation of safeguarding guidelines, issuance of identity cards, and the establishment of team support centers.

In Afghanistan sub–National Polio Priority areas, the percentage of female front-line workers has been increasing and is up from 23% in 2023 to 33%, though again there is great variation across regions. The inclusion of female front-line workers is dependent on the policies of the Taliban Government, good will of local authority and the security situation in the deployment areas. In the Eastern Region the number of female front-line workers (volunteers, supervisors and social mobilisers) has increased from 2732 in Dec 2023 to ~4826 in Dec 2024 thanks to consistent efforts to increase the level of participation including through engaging female monitors as well in urban areas. In the Southern region however, due to the local context female participation is close to zero. As a result, the percentage of WPV1 cases are higher in Southern region.

The percentage of missed children has increased since 2023 and was above target by 0.6% for Pakistan and 6% for Afghanistan. The main reasons for missed children were predominately security related issues restricting access to children, for example shortened campaign implementation; community hesitancy and refusals; and operational gaps in micro-planning. To address these in both countries GPEI has revamped its community influencer engagement system through their trainings and reward/recognition system tailored according to the specific contexts. They have also prioritised integrated ‘health camps’ for areas with higher proportions of missed children to encourage attendance.

The percentage of outbreaks stopped within 120 days of outbreak confirmation has risen from 80% to 93% in 2024. This significant improvement reflects better coordination as GPEI have put in place a number of measures to increase the speed of response. For example, a prefinancing mechanism which involves sending funding to the country within 48 hours of an outbreak being declared to allow for an immediate rapid response ahead of final approval of the budget, and decentralised surge recruitment to enhance speed and effectiveness during outbreaks. Looking forward, GPEI are assessing the feasibility of pre-positioning vaccines and funds in countries to save time during the response process. GPEI has process in place to ensure value for money, cost effectiveness and to mitigate against misuse of these funds and the remaining balance is only released once budgets are officially approved. Despite progress challenges remain in the most difficult regions and despite high level advocacy GPEI has not been able to implement outbreak response in countries affected by humanitarian emergencies such as North Yemen and Sudan.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Specific changes to each indicator’s milestones, or the use of alternative indicators, are described in the outputs table.

Output Title	High Poliovirus Detection Capacity
Output number:		2	Output Score:
Impact weighting (%):		25	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1: % of districts with population under 15 years >=100,000 in priority countries achieving npAFP rate of 2/100,000	90%	94% / A+: Outputs moderately exceed expectations
2.2: % of ES sites in priority countries meeting sensitivity threshold of at least 50% samples positive for enterovirus	90%	77% / B: Moderately did not meet expectations / Improvement from 68% in 2023 and up from 48% in 2022.
2.3: % of priority countries achieving stool adequacy targets overall and disaggregated by sex	90%	92% (92% females and 92% males) / A: Met expectations / Improvement from 79% in 2023
2.4: % of AFP cases and ES samples in priority countries with final positive results reported within 35 days of onset for AFP cases or ES sample collection (within 49 days for countries without sequencing capacity)	80%	WPV: 92% (<35 days), 88% (<49 days) / cVDPV: 7% (<35 days), 30% (<49 days) / B: Moderately did not meet expectations / WPV: slight decrease from 99% (<35 days) in 2023 / cVDPV: improvement from 1.7% (<35 days) in 2023

B: Moderately did not meet expectations

Overall, there has been good progress across indicators on this output indicating a well-functioning surveillance system. Indicators which did not meet expectations, nevertheless showed marked improvement from last year.

In endemic countries all surveillance indicators meet the globally required standards, though a number of orphan viruses reported from the bordering districts of the two countries may indicate potential gaps in reach of surveillance system in these areas. Efforts are being made to enhance surveillance sensitivity and coverage in these areas, for example by increasing the frequency of environmental sampling, and by identifying and targeting specific sampling sites in locations at highest risk for poliovirus transmission. They are also working to and improve coordination and data sharing between the countries, and to engage the local communities and leaders to raise awareness about the importance of the vaccination thereby improving participation and coverage.

In Afghanistan the surveillance quality in 2024 met the benchmarks at the national and provincial levels, and internal review mechanisms are in place to continuously monitor the quality. The number of active surveillance sites was increased from 1958 in 2023 to 2079 in 2024, and community reporting volunteers from 50,409 to 62,268. The number of environmental surveillance sites increased from 38 in 2023 to 43 in 2024. As recommended by the IMB an external audit was conducted by a team of 19 independent reviewers in the East region of Afghanistan in April 2024. On Surveillance, the team concluded that: generally, the surveillance system for polioviruses (AFP – facility & community-based, and Environmental) exists and is functioning. There is a need to enhance surveillance in migrant mobile populations and border areas and WHO teams continue to support on implementations of the audit recommendation.

For outbreak countries, most surveillance indicators meet the required standards at the national level, but GPEI’s in-depth analysis shows gaps at sub-national level. Particularly in some of the high priority countries in Central and West Africa the AFP detection rate and stool adequacy rates are sub-optimal. Many outbreak countries lack the necessary laboratory facilities and equipment to perform sequencing locally, requiring specimens to be sent to international reference laboratories. Though there has been a small improvement in sequencing timeliness in outbreak countries, this is still much behind targets with only 7% of cases with final positive results reported within the 35 days target (or 49 days for countries without sequencing capacity). The ongoing challenges related to inter-country shipment of specimens (sometimes internationally shipped twice for compete lab processing), and regulatory requirements often leads to delays.

On stool adequacy targets, although the data shows overall and equal percentage for males and female stool adequacy targets met, aggregated analysis of data by the Gender team shows there are wide variations by country in female and male children. 33% of 42 countries indicate a 5 to 19% discrepancy between male and female children and only 14 countries have no sex-based discrepancies. This suggests that this indicator needs to be reconsidered to allow these discrepancies to be further understood.

To address these issues the GPEI launched a new Global Polio Surveillance Action Plan (GPSAP 2025-2026) to systematically improve timeliness while maintaining a focus on preserving or enhancing the surveillance sensitivity (to pick up AFP cases early), case investigation and specimen collection and shipment. GPEI had plans to expand sequencing capacity especially in the African region to reduce the need for international shipments and therefore improving timeliness. Labs are being set up in Uganda, Nigeria, DRC, Cameroon Senegal and Kenya. Oman has also been trained to do sequencing for Pakistan and Afghanistan. If timeliness can be improved in Nigeria, DR Congo and Madagascar, this will have a significant impact due to the high number of cVDPV positive isolated in these three countries.

Funding gaps from 2026 onwards will have significant implications for surveillance, including the Global Polio Surveillance Action Plan. Prioritisation discussions are ongoing for the programme from 2026 -onwards.

Output Title	Integrated Service Delivery Expedites Eradication Progress
Output number:		3	Output Score:
Impact weighting (%):		25	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1: % reduction of zero dose children (KPI 3.1.1) / IA2030 call for all countries to reduce the number of zero dose children (ZDC) by half,	Pakistan: to reduce by half from 11% to 6% / Afghanistan: to reduce by half (62,000)	Pakistan: 6% / (With a linear trajectory, Pakistan should have ZDC reduced by 91k, managed to reduce by 175k) / Afghanistan: 34% / (unreported in 2023 but number of ZDC went up 70,000 in 2024) / B: Moderately did not meet expectations
3.2: % of countries receiving supplementary BCU funding from GPEI that have implemented SIAs.	90%	46% / C: Significantly did not meet expectations
3.3: % of planned SIAs that co-deliver another antigen and/or one of the polio plusses (Vit A, Sprinkles, Soap bar, hygiene kit).	75% (Endemics) / 50 % Outbreak countries)	75% in Endemics / 46% in Outbreak countries / A: Met expectations

B: Moderately did not meet expectations

There has been moderate progress on integration in 2024, with an increase in SIAs co-delivering another antigen or one of the polio plusses. However, integration should be more systematic and GPEI will need to enhance efforts rapidly in 2025 in order to reach eradication targets.

23 of 50 campaigns in the first half of the year were integrated, including all but one in the endemics. These campaigns effectively combined RI antigens with other essential health interventions, including Vitamin A supplementation, albendazole, lymphatic filariasis treatments (ALB, DEC, IVM), malnutrition screening, and vital public health messaging such as WASH (Water, Sanitation, and Hygiene). A standout example was DRC, where nearly two-thirds of outbreak response activities had an integrated approach, illustrating a model of efficiency and impact in multi-faceted health interventions during critical outbreak periods.

Gavi’s BCU initiative follows the drop in immunisation coverage as a result of the COVID-19 pandemic. GPEI have supplied bOPV for 24 countries to be administered as part of this initiative. Though this indicator looks like it hasn’t been reached a delay in reporting could account for some of the shortfall – preliminary data from several countries indicates high vaccine coverage rates:
- Nigeria: The integration of bOPV with routine immunisation campaigns has led to significant improvements in vaccination coverage. For instance, the BCU initiative helped vaccinate over 2 million children with bOPV, reaching high-risk areas and vulnerable populations. As a result, Nigeria saw an increase in vaccination coverage from 44% in 2021 to approximately 60% in 2024.
- Madagascar: The collaboration between GPEI and Gavi facilitated the integration of bOPV with other routine immunizations, such as measles and Vitamin A supplementation. This integrated approach helped improve overall immunisation coverage. Madagascar achieved a vaccination rate of 92% for the first dose of the pentavalent vaccine (Penta1), 85% for the second dose (Penta2), and 86% for the third dose (Penta3) in 2023, representing a significant increase from previous years.
- Kenya: The initiative helped vaccinate over 1.5 million children with bOPV, significantly improving vaccination coverage. Kenya saw an increase in vaccination coverage from 70% in 2021 to approximately 85% in 2024.
An assessment in 2024 which was discussed at the IMB meeting held in July 2024 found the major challenges on integration to include: a lack of programme leadership and management at the global level; weak coordination processes between Global HQ and regions and countries; inadequate communication to partners and donors (underreporting of integration activities); and siloed tendencies of individual immunisation programmes. Key aspects of GPEI’s 2024 work plan on integration to address the issues included;

- Integration activities to directly support interruption
- A differentiated approach to integration in the Endemics, Consequential Geographies, Ongoing Outbreaks & New Outbreaks
- Active engagement in partner initiatives notably the BCU, and Gavi FPP and annual Joint appraisal processes at country level to support improvements in population immunity due to poor coverage of routine immunization.
- Development and maintenance of a network of integration focal points at global, regional and country level, within and outside of GPEI.
- Improved documentation, reporting and communication on integration
- A shift in focus in future years as GPEI nears sunset to ensure continuity of key functions, notably IPV, Stockpiles of novel OPV, and Surveillance.

GPEI have recently stepped up their engagement with Gavi and are planning a joint Board meeting between the POB and the Gavi Board to discuss how they can better work together for the benefit of both programmes. A joint Action Plan will then be agreed by the organisations to enhance integration.

Output Title	Political will and funding secured, Legacy plan in place
Output number:		4	Output Score:
Impact weighting (%):		25	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1: % of outbreak countries that activate an Emergency Ops Centre within 3 days upon outbreak confirmation / ORPG	90%	No data / 93% of countries have set up an EOC, but there is no data on the timeliness of this. This 93% is an improvement on 2023 where 57% of countries set up an EOC.
4.2: Meetings of the national task force on polio eradication (chaired by the head of government or Prime Minister) convened each year to review progress and address challenges	PAK:2 PM chaired / AFG: 2 Health Minister or more senior.	Pakistan: 5 / Afghanistan: 0 / B: Met expectations
4.3: % of LMIC outbreak countries making financial contribution to outbreak response	LMIC: 100% / LIC: 10%	LMIC: 42% / LIC: 6% / C: Outputs substantially did not meet expectation
All agreed milestones are achieved for the updating of the Post-Certification Strategy in preparation for submission for approval in WHA 2025, including strong engagement with other partners (FCDO)		On schedule for WHA sign off in 2026. / A: Met expectations

B: Moderately did not meet expectations

Overall, the political commitment at the highest levels remains high in the endemic countries, and in a number of outbreak countries, particularly DRC, Nigeria, Sudan, OPT, Egypt, Malawi, Mozambique and Ethiopia. However, maintaining a high level of political commitment for a prolonged period of time has proven difficult, particularly as many countries are dealing with multiple crises. There are also challenges at regional levels where tailoring approaches to the specific local context is vital.

In Pakistan, the Prime Minister chairs the meetings of the National Taskforce for Polio Eradication on a quarterly basis. The PM also regularly held in-depth review meetings with the Core Polio Management Team, including the WHO, UNICEF and partners in June, July, August and October 2024.

In Afghanistan, the Minister of Public Health, under the Minister of Health, chairs National Task Force Polio meetings and updates the Prime Minister and relevant ministries as relevant. The Executive Director WHO Health Emergencies visited Afghanistan in December 2024. During the visit he met the Afghan Minister of Health and other high-level officials to advocate for their continued oversight for the Polio programme and maintaining coordination with Pakistan’s Polio Programme.

GPEI has a comprehensive advocacy plan to maintain countries commitment to Polio. The POB regularly visits Pakistan, Afghanistan and Nigeria. WHO and UNICEF Regional Directors actively co-ordinate with Ministers of Health of their respective member states. For the epidemics GPEI has established a Sub-Committee of Ministers of UAE-Saudi Arabia and Qatar to support advocacy with endemics and outbreak countries.

Although Pakistan and Afghanistan are considered as one epidemiological block, the political, operational and security dimensions are different, and this is a challenge for cross-border coordination. To support this WHO are hoping to hold a health dialogue between the two countries in Doha in 2025. GPEI’s Afghanistan advocacy plan engages other member states to advocate for house-to-house vaccination in south Afghanistan.

Strategies tailored to the local security context are pivotal in reaching children in a number of difficult to access areas, particularly in North Nigeria, East DRC, Central Somalia and parts of South part of Khyber Pakhtunkhwa province of Pakistan. The role of provincial Chief Secretaries in Pakistan is critical in ensuring accountability and ownership of SIAs in Pakistan, and all provincial CSs or Additional Chief Secretaries attended the IMB in July 2024. The IMB had a closed session with the Pakistan team including Chief Secretaries to ensure key challenges by province and their potential solutions were discussed in detail.

In Northern Yemen, with very complex security and health emergency situation and anti-vaccine sentiments within Northern government governments, the program has not been able to vaccinate since the start of the outbreak. There was some recent negotiation on integrated multi-antigen campaigns with relevant authorities, but this is again on hold given the current situation in country.

GPEI’s Polio Certification Strategy (PCS) defines the standards that will be required for essential functions to sustain a polio-free world after the certification of eradication. The Strategy is now in its second draft (in Phase 1) and now being shared with Member States for consultation. Timelines for the report have changed since the indicator was created and it will now be submitted to the WHO Executive Board in January 2026 followed by submission to the WHA for endorsement of Member States in May 2026. Through the member state consultation on the PCS GPEI partners, specifically the WHO, should ensure that endemic countries and consequential geographies are supported in fully engaging in the opportunities and risks of the strategy ahead of endorsement at the 2026 WHA.
## D: VALUE FOR MONEY

GPEI’s value for money rests on the two eradication goals being achieved. 2024 has been a difficult year for GPEI marked by an increase in wild poliovirus transmission in the two endemic countries and new, high-profile outbreaks including in Gaza, and detection of poliovirus in wastewater in five European countries. It is looking increasingly unlikely that GPEI will meet their extended deadlines, and therefore 2025 will be a pivotal time for the Programme.

From an effectiveness perspective GPEI has maintained high quality of surveillance and delivery of campaigns particularly in the endemic countries and despite setbacks in house-to-house campaigns in Afghanistan, GPEI are now mitigating this with site-to-site campaigns every three houses. The strong engagement of senior political leaders ensures better value for money by supporting more coordination and community engagement. The ongoing lower level of political will and access in the consequential geographies remains a challenge for the efficiency and effectiveness of GPEI’s work, although progress has been made, particularly in Nigeria which is a critical area for Goal 2.

GPEI have continued to strengthen financial management systems. Following the successful implementation of dynamic budgeting in 2022, the Financial Management Group under the guidance of SC, continued to use this approach.  This dynamic budgeting guided the Programme through challenging financial decisions – and was used in mid-2024 when a revision of endemic and outbreak budgets was needed as the cost per campaigns increased in Pakistan, and there was an increase in outbreak response countries compelling an overall increase of USD$ 100m in the 2024 approved budget. GPEI was able to identify and transfer ‘unusable’ budget space such as savings, cancelled activities or vacant positions.

Looking ahead, and given the uncertainty around funding beyond 2025, requirements will continue to exceed the projected resources. GPEI are currently going through a prioritisation activity given the depth of projected budget gaps. Improvements in value for money could be achieved by GPEI through more concrete collaboration in delivery on routine immunisation strengthening through the partnership with Gavi, through increased domestic financing and ownership from affected countries and better coordination for integrated service delivery.

E: RISK

FCDO funds to GPEI are dispersed under an accountable grant to WHO. This section, and section F focus on WHO’s financial, risk and commercial management processes, but draw on wider GPEI partnership aspects where relevant. The FCDO has recently refreshed it’s Central Assurance Assessment (CAA) of WHO and a Due Diligence Assessment (DDA) on the WHO Polio Programme is underway.

The DDA highlights the programme as high risk, reflecting key risks in areas such as the external context (outbreaks continuing), resource mobilisation and addressing SEAH. The FCDO’s DDA of the WHO Polio Programme from April 2025 assessed funding to the WHO Polio Programme as being a major risk to the FCDO. Major risks identified are sexual exploitation, abuse and harassment (SEAH), resource mobilisation, cVDPV outbreaks, and WPV in south-east Africa. Resource mobilisation and SEAH are discussed here, the external context was discussed in Output 1. The UK monitors GPEI risks on a quarterly basis through internal FCDO processes and review our risk appetite annually. The UK will continue to use our position of influence to ensure robust risk management and development of comprehensive risk mitigation strategies.

The WHO Polio Programme depends on central WHO processes. There have been several positive developments on WHO processes, around safeguarding where they have made real progress in strengthening their approach to sexual misconduct and put in place refreshed policies, and around risk management and risk appetite, however in both these areas there is still much to do to fully implement and embed these initiatives, particularly at country level and in the highest risk contexts including emergency response where regional differences are apparent.

GPEI should clarify and clearly communicate how risk is managed within each of the partners and how partnership-wide risks are escalated and managed through its governance structures. GPEI should take accountability for safeguarding and fraud risks across the programme and incorporate these into the risk and performance report.

Sexual exploitation, abuse and harassment (SEAH)

As a WHO programme, the Polio Programme is subject to the WHO Policy on Preventing and Addressing Sexual Misconduct. WHO’s Three-Year Strategy 2023-2025: Preventing and Responding to Sexual Misconduct has made significant progress, but implementation particularly at country level is variable. There is a high risk of SEAH within the Polio Programme, particularly in fragile and conflict settings where GPEI’s work increasingly is focused.

The Polio Programme does not have a separate policy or strategy for preventing sexual misconduct from the wider WHO but efforts are made to amplify and strengthen policy awareness:
- References to the Sexual Misconduct policy are included in GPEI technical guidelines, such as the outbreak Standard Operating Procedures.
- Administrative staff at HQ have been trained on the inclusion of the Sexual Misconduct policy.
- All surge staff complete online training, often complemented by face-to-face training.
In order to strengthen technical capacity at country level in SEAH, WHO has appointed PRSEAH technical officers in 11 high risk countries. GPEI provides cofounding for these officers in Pakistan, Afghanistan and Nigeria. These technical officers work across all WHO programmes but given the size of the polio programme in the three countries a large proportion of their time is dedicated to polio operations.

WHO has confidential reporting systems on SEAH and while aggregates of reports received are made available publicly on the WHO sexual misconduct dashboard to maintain confidentiality, this information is not disaggregated by programme. The WHO Polio Programme does not have sight of reports received or numbers of allegations within the Polio Programme.

Given the high risk of SEAH in the Polio Programme there should be a mechanism for the Polio Programme to have disaggregated information on allegations, still maintaining confidentiality. This would allow targeted mitigation activities and provide assurance that any efforts which are being made by the programme are having a positive effect.

WHO report any SEAH allegations that would impact the GPEI partnership to FCDO through their confidential mechanism. On a broader WHO level, FCDO continue to closely monitor WHO’s efforts to improve how it prevents and responds to SEAH.

Resource Mobilisation

Resource mobilisation remains a significant risk due to the increasingly challenging global financial landscape. Nevertheless, the Global Polio Eradication Initiative (GPEI) has made notable progress, utilising innovative budgeting mechanisms and securing new donors.
In 2024, the Kingdom of Saudi Arabia rejoined the global eradication effort with a pledge of US$ 500 million over the next five years to support polio vaccinations and other health-saving interventions. Additionally, the Government of Canada has announced a contribution of CAN $151 million over the next three years to aid the GPEI's efforts. Contributions from the innovative financing partnership between the European Investment Bank, European Commission, and Gates Foundation have proven effective in addressing outbreaks in several countries. Extraordinary funding from Austria, Switzerland, and the United Arab Emirates facilitated the Gaza outbreak response, enabling the programme to serve highly fragile and underserved populations. These contributions, along with support from other donors and partners, represent a substantial increase in funding for the global polio eradication initiative.

In October 2024, the Polio Oversight Board (POB) determined that the total funding needs for the extended 2022-2029 strategic period amount to US$ 6.9 billion, an increase from the US$ 4.8 billion projected for the 2022-2026 strategic period. In light of the highly challenging and rapidly evolving global health funding landscape, the Resource Mobilisation Group (RMG) is prioritising the identification of innovative financing solutions, diversifying its donor base, enhancing donor flexibility, and potentially advancing long-term commitments.
In response to US funding cuts to WHO, GPEI has developed a prioritised plan to ensure that key activities in 2025 are funded. However, significant risks remain regarding funding for the programme beyond this period.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

GPEI’s Financial Management Group continue to implement their dynamic budgeting with the budget prioritisation framework to guide difficult programmatic decisions.

Dynamic budgeting has continued to help in reducing under-spend and flexibly reallocating programme funds. Having been first implemented in 2022 most countries are now aware of this process and implement accordingly readjusting future quarters if needed based on an annual budget ceiling.

This budget prioritisation approach does mean that some GPEI priorities are unfunded. Deprioritised activities and vacant roles bring significant strategic risks to the overall eradication effort. While GPEI’s focus on prioritising the most consequential geographies to interrupt the sources of transmission is sensible, ultimately to achieve eradication GPEI will need to interrupt transmission simultaneously everywhere. This means that a preventative focus is also required.

Fraud and mismanagement are reported and managed through several central WHO mechanisms including internal and external audit, delegation of authority, segregation of duties, WHO ombudsman and whistle blowing. Each staff member with delegated authority must sign a Declaration of Conflict of Interest on an annual basis. The department also prepares a self-assessment on how it applies internal controls each year and reports back to the Director-General’s office on its delegated authority and any waivers from norms, financial rules and regulations.

Governance

Changes to POB membership Terms of Reference in October 2024 have instigated an independent governance review of GPEI. This is currently underway and is due to be completed in Q3 2025. A Governance Review was previously completed in July 2020 however due to the COVID-10 pandemic progress on implementing the recommendations stalled. A number of recommendations supported by the FCDO were not implemented therefore we are supportive of these being reconsidered, including membership of the POB and SC to broaden their membership to include implementing countries.

The FCDO would also like to improve the accountability of GPEI actors. Operational and managerial functions are left to central WHO and it would be of benefit to the programme for GPEI’s Executive Management Unit to be more involved in these areas which have a direct impact on the programme.

To ensure revisions to the programme are implemented systematically GPEI should adopt an accountability framework clearly setting out tactical shifts, responsibilities and check points to revise actions where needed.

At the end of 2023 the UK handed over sovereign donor representation on the SC, after five years of service, to Canada, who in turn handed over representation on the POB to GPEI’s newest donor the European Commission. The UK has continued to feed in through the donor constituencies and engaged to influence in GPEI through the constituency, and bilaterally including through our Annual Reviews.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

There are a number of levels of Monitoring and Evaluation in GPEI’s programme. The most significant is the annual external review by the Polio IMB, to the POB. This annual report is generated after an in-person conference with stakeholders across the Polio world including academic experts, CSOs, implementing countries, donor countries. The report includes recommendations for the programme on technical and operational areas. GPEI’s process to respond to these recommendations could be communicated more clearly, with review points to monitor progress on each area.

At a more local level there are a number of mechanisms to evaluate and improve eradication efforts:
- Outbreak Response Assessments (OBRAs) and reviews which evaluate campaigns during outbreaks. Five OBRAs were completed between July and December 2024.
- Nigeria’s Expert Review Committee (ERC) who independently review outbreak responses and provide recommendations.
- Technical Advisory Groups (TAGs) who offer strategic guidance on outbreak responses in Pakistan and Afghanistan.
- SIA Independent Monitoring by third parties who evaluate SIA campaigns to ensure accurate data and unbiased reporting allowing for real-time adjustments to improve campaign coverage.

Gender

As one of the first major programmes to have a Gender Equality strategy (developed in 2010) GPEI is a leader in its approach to Gender. The Strategy, extended to 2029, provides guidelines for gender-responsive programming, institutional structures, and environments. There are seven key performance indicators in which four of these indicators—percentage of women in the National Emergency Operation Centre (NEOC), percentage of women working as frontline health workers, sex-disaggregated percentage of missed children, and percentage of SIAs showing sex-disaggregated coverage—are specifically for the two endemic countries, Pakistan and Afghanistan. One indicator, concerning stool adequacy targets, applies to both endemic and outbreak countries. In 2024, the SC endorsed two additional indicators which are applicable to outbreak countries and are about the percentage of women in International/National GPEI surge deployments and the percentage of countries implementing gender-specific actions as per the 'Standard Operating Procedures for Outbreak Response'. Although the overall performance is on track, there are some variations in Pakistan and Afghanistan due to ongoing security challenges and political instability. Key activity in 2024 included:

1. Strategic Capacity Building: GPEI hosted trainings, webinars, and an annual retreat to enhance GPEI staff's ability to address gender-related barriers.
2. Expanded Engagement: Increased participation from regions and countries, disbursed grants to 17 countries for gender-responsive initiatives, and provided technical support for gender mainstreaming in polio eradication efforts.
3. Community Engagement: Promoted male engagement and local leadership through programs like Nigeria’s “Fathers for Good Health” and partnerships with religious leaders in Burundi.
4. High-Level Advocacy: 11 Gender Champions amplified support for gender equality in health, with Dr. Hanan Blakey becoming the first Gender Champion from a Middle-Income Country.
5. Improved Data Practices: Integrated sex-disaggregated data into the Polio Information System (POLIS) for evidence-based decision-making.
6. Evaluated GPEI Gender Equality Strategy for capturing the level of success and challenges in its implementation for a robust way forward.
7. IMB and transition monitoring board included importance of gender integration in its findings as a missed opportunity for the polio programme and made concrete recommendations for the success of the polio programme.
8. SC made a decision that sex disaggregated data of missed and zero dose children would be mandatory requirement for two endemic (Afghanistan and Pakistan) and two outbreak countries (DRC and Nigeria).

Despite this impressive work from GPEI’s Gender Mainstreaming Group challenges remain in perception biases in gender integration in the programme. There remains work to get the leadership fully on board to how pivotal female workers are to Polio eradication. The IMB report recommends that gender should be a mandatory and core part of the discussions on planning and delivery of the Polio Programmes, and that more women in supervisor and senior roles could enhance the most critical layer of the programme: performance and oversight. GPEI should prioritise strengthening leadership accountability.

Date of last narrative financial report		Date of last audited annual statement

Annex A: Acronym List

AFP	Acute Flaccid Paralysis
AFRO	WHO African Region
BMGF	Bill and Melinda Gates Foundation
CAA	Central Assurance Assessment
CVC	Core Voluntary Contribution
cVDPV	Circulating Vaccine-derived Poliovirus
cVDPV1	Circulating Vaccine-derived Poliovirus Type 1
cVDPV2	Circulating Vaccine-derived poliovirus Type 2
DDA	Due Diligence Assessment
DFC	Direct Financial Cooperation
EIB	European Investment Bank
eJRF	Electronic Joint Reporting Form
EMRO	WHO Eastern Mediterranean Region
EPI	Expanded Programme for Immunisation
ES	Environmental Surveillance
EU	European Union
FAC	Financial Accountability Committee
FDA	French Development Agency
FLW	Front Line Worker
FMG	Financial Management Group
GLOWACON	Global Consortium for Wastewater and Environmental Surveillance for Public Health
GPEI	Global Polio Eradication Initiative
GPSAP	Global Polio Surveillance Action Plan
HEER	Health Emergency Extension Response
IA2030	Immunisation Agenda 2030
IPV	Inactivated Polio Vaccine
KPI	Key Performance Indicators
NEOC	National Emergency Operation Centre
NID	National Immunisation Days
nOPV2	Novel Oral Poliomyelitis Vaccine Type 2
npAFP	Non-Polio Acute Flaccid Paralysis
OBR	Outbreak Response
ODA	Overseas Development Aid
OPV2	Oral Poliomyelitis Vaccine Type 2
PCS	Post Certification Strategy
PEI-EPI	Polio Eradication Initiative and Expanded Programme for Immunisation
POB	Polio Oversight Board
PSEAH	Protection from Sexual Exploitation, Abuse, and Harassment
RMG	Resource Mobilisation Group
SEAH	Sexual Exploitation, Abuse, and Harassment
SIA	Supplementary Immunization Activities
SNID	Sub National Immunisation Days
UNICEF	United Nations Children's Fund
USCDC	US Centre for Disease Control and Prevention
VPD	Vaccine Preventable Disease
WHO	World Health Organisation
WPV	Wild Polio Virus
WPV1	Wild Poliovirus Type 1