## Annual Review Template

Title: Child Wasting Innovation Programme (CWIP), formerly PARSNIP
Programme Value £ (full life): £61.4m		Review date:
Programme Code: 300750	AMP start date: 20 May 2020	AMP end date: 31 March 2030

Summary of Programme Performance
Year	20/21	21/22	22/23	23/24	24/25
Overall Output Score	A	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/58006857.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/58037381.xlsx

A. SUMMARY AND OVERVIEW

Description of programme
The Child Wasting and Innovation Programme (CWIP), previously known as the Progressing Action on Resilient systems for Nutrition through Innovation and Partnership (PARSNIP) programme, is a 9-year, £61.4 million partnership between the Foreign, Commonwealth, & Development Office (FCDO) and UNICEF. The programme contributes to the Sustainable Development Goal of ending malnutrition in all its forms by 2030 by strengthening the resilience of services to treat and prevent child wasting (acute malnutrition) in the face of climate change.

The programme focuses on countries in Africa and South Asia where child wasting remains persistently high and climate change is an increasing risk. It builds on FCDO’s wider investments to strengthen quality and coverage of services to treat child wasting. The programme will promote reform in the way the UN agencies and other multilaterals address child wasting and how governments and donors finance prevention and treatment.

The intended objectives set out in the Business Case are to: (1) reduce mortality associated with child wasting, (2) reduce the prevalence of child wasting in target countries; and (3) avoid permanent damage to the growth and development of young children that results in them doing less well at school, being less economically productive as adults and less resilient to the effects of climate change. This will be achieved by:
- Integrating treatment and prevention of child wasting into health systems as part of Universal Health Coverage.
- Optimising treatment and prevention services to reduce cost, improve coverage and enable services to be scaled up to deal with climate shocks and other crises effectively.
- Generating evidence of how government services can more effectively prevent child wasting, including where climate change is increasing risk.
The programme seeks to accomplish this through:
1. The creation of financing solutions to improve predictability and value for money of prevention and treatment of wasting (Output 1).
2. Addressing weaknesses in the supply chain and information systems for wasting and to strengthen value for money (Output 2).
3. Adapting programming and policy globally and in target countries to strengthen treatment and prevention of wasting (Output 3).
4. Improved coordination and strategic leadership to promote reform in how wasting is addressed (Output 4)
5. Strengthening the evidence base and investment case for effective action on wasting (output 5).
In April 2020, a £0.75 million cost extension was approved for the overall programme to enable UNICEF to take forward strategic research relating to the prevention and treatment of acute malnutrition in the face of COVID-19. In November 2023 a further cost and time extension of £30.7m and 5 years (for a total of £61.5m until March 2030) was approved to build and expand on the successes and lessons learned over the first three years of the CWIP programme around improving the sustainability of financing for wasting through the Child Nutrition Fund and strengthening the global evidence base for better prevention of wasting.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]
The CWIP programme, now in its 5th year, has continued to deliver meaningful results despite a challenging context. This year saw the official launch of the Joint UN Initiative on the Prevention of wasting (JUNIPr), one of the components under the cost-extension as well as a significant increase in our support to the Child Nutrition Fund (CNF). Overall, the programme is assessed as continuing to meet expectations.

This review covers the reporting period between January 1st to December 31st, 2024, and is based on a combination of official UNICEF progress reports, the CWIP Feedback Survey results, participation in WHO guideline Technical Advisory Group meetings, regular catch-up calls with the UNICEF team as well as a field visit to Nigeria (to monitor progress of the CNF contribution) as the basis for the scores and narrative provided. Given this review is written in May 2025, where further progress has been made since the end of the reporting period, this is referred to in the narrative but progress against milestones remains based on the agreed reporting period.

Major lessons and recommendations for the year ahead
Progress in 2024 shows gains made on treatment coverage have largely been able to be maintained and progress on indicators such as average cost of RUTF is starting to recover from the shocks to the global market caused by Covid-19 showing the positive impact of sustained focus and strategic funding.

Unfortunately, the progress against a number of the outcomes and outputs is likely to backslide in 2025 given the ongoing shocks to the international financing system by global reductions to Overseas Development Assistance (ODA). While these ongoing shocks are expected to adversely affect some of the achievements under CWIP (particularly under output 1 and 2), it is not expected that these impacts are likely to compromise the programme’s ability to meet its overall objectives. This is because, for the most part, the programme is projected to deliver substantial results relative to a counterfactual scenario in which the programme had not been implemented. This underscores the programme’s added value and its role in mitigating the impact of these shocks.

Therefore, due to the change to the external context, and in line with the recommendation from FCDO’s Internal Audit Department (IAD), this review recommends that logframe targets for this programme be reviewed and adjusted as needed.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The theory of change for the programme is that by: (1) improving the value for money of investments to treat and prevent child wasting; (2) strengthening the capacity of government services to treat and prevent wasting; and (3) enhancing coordination and collaboration by the UN and other external actors, it should be possible to more effectively prevent child wasting and treat those who slip through the net more cost effectively. This should ultimately result in: (a) fewer child deaths; (b) improved growth and development of children living in contexts where climate change presents a threat; and (c) benefits to long term resilience that come from reducing the likelihood that people get trapped in a cycle of poverty and malnutrition.

As a result of the cost and time extension of CWIP which was approved in 2023, over the last year the logframe has undergone a review with the addition of four new outcome indicators (5-8). Three outcome indicators were removed (previous indicators 5-7) as these were either completed or now captured under the new output level indicators. Impact indicator 3 was changed to track number of countries integrating nutrition into their emergency response plans to better reflects the programme’s focus on integrating the management of child wasting into systems/plans. Milestones and targets for this indictor have yet to be agreed but will be discussed as part of the logframe review recommended by this annual review. Outcome indicator 1 and 2 will be reported on in the next annual review and will then be retired as this component of CWIP will then be completed. Outcome indicators 3 and 4 will be reported against in the next annual review but will then be retired and replaced by indicators from the agreed Child Nutrition Fund strategic results framework.

As set out below there is evidence at the end of the fifth year of the programme that this theory of change still holds. There continues to be an increased recognition among the UN and other donors of the relevance of the actions being taken through this programme to help shift how child wasting is addressed. Despite the backdrop several consecutive global shocks since the programme’s inception in 2020, it is delivering significant results and the rationale and value for money proposition set out in the Business Case still hold.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Indicators	Milestones (Dec 2024)	Progress (As per Dec 2024) (**)
Impact: fewer child deaths and a reduction in child wasting and other forms of malnutrition
Impact 1: Prevalence of wasting among children in target countries	No milestone agreed for 2024. / Target for 2025: <5%	Off track: 10% / Prevalence reported directly by countries – to be confirmed in the 2025 Joint Malnutrition Estimate Report.
Impact 2: Proportion of children with wasting who recover after receiving treatment	>90%	On track: 93%
Impact Indicator 3: Number of countries integrating nutrition in their emergency and resilience response to mitigate the impact of climate change	TBC	4 countries (Afghanistan, Bangladesh, Nepal and the Philippines).
Outcome indicators
Outcome 1: Number of children receiving essential nutrition actions for the prevention of child wasting in target countries	2.4 million	On track: 138,772,851 children
Outcome 2: Proportion of children with severe wasting receiving treatment in target countries	>35%	On track: 42% of children with severe wasting were reached with lifesaving treatment in CWIP countries
Outcome 3: Number of countries allocating national health / nutrition budgets to commodities to treat child wasting	5	On track: 8 countries
Outcome 4: Proportion of total RUTF costs covered by national health budgets	7%	On track: 16%
[note] Milestones for this impact indicator is to be determined as part of the logframe review recommended in this annual review.
[note] Milestones for this impact indicator will need to be readjusted/increased in 2025.

Most impact and outcome indicators remain on track. Impact indicator 1 has seen a backsliding since last annual review (7.32% as reported in 2024 annual review) however given these are only tentative results based on reported prevalence from country level reports rather than on the officially agreed source (the Joint Malnutrition Estimate Report) the accuracy of this figure remains questionable and subject to change when JME report is released (planned for mid-May 2025). The significant achievement against Outcome Indicator 1 can be attributed to its recent inclusion in UNICEF’s global Strategic Plan indicator framework, which mandates country-level reporting. This integration reflects a heightened institutional focus on the prevention of wasting, representing a positive and strategic outcome of the programme’s influence. The milestone and targets for this indicator are in this context set much too low and will need to be readjusted upwards in 2025.

For next year’s review the below new outcome indicators will be added:

Outcome 5: National governments and stakeholders demonstrate improved capacity to use, and integrate new research evidence on the prevention of wasting into national policies and programs	Milestone to be determined	This is new outcome indicator which relates to JUNIPr which was only launched in October 2024.
Outcome 6: Number of Global Action Plan on child wasting initiatives related to increased advocacy for the prevention of wasting including in food insecure contexts (global and national)	Milestone to be determined	This is a new outcome indicator which relates to JUNIPr which was only launched in October 2024.
Outcome 7: Percentage of children under 5 years of age who benefit from programmes to prevent malnutrition	Milestone to be determined	This is new outcome indicator which will draw its results from the CNF Annual Report which will be published in July 2025
Outcome 8: Percentage of children under 5 years of age with wasting who are admitted for treatment	Milestone to be determined	This is new outcome indicator which will draw its results from the CNF Annual Report which will be published in July 2025.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Taking into consideration the evidence provided in this Annual Review, the programme should continue as it is on track to achieve its outcomes and mitigate the wider impacts of conflict, climate change and decreasing ODA financing. Against the backdrop of global cutbacks on financing for international development, the focus of the programme is even more relevant now than ever before. The initiative strongly aligns with UK objectives to strengthen health systems and improve effectiveness of humanitarian response.

## C. DETAILED OUTPUT SCORING

Output Title	Effective financing and pre-positioning
Output number:		1	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Trend since last annual review
1.1 Total equivalent number of RUTF cartons procured with VII Nutrition Window and Nutrition Match Funds (cumulative)	135,833	Milestone significantly exceeded: 1,224,218	Increase of 370,849 cartons since last AR (853,369 cartons in last AR)
1.2 Number of partner governments integrating wasting treatment into GFF investment cases (cumulative)	5	Milestone exceeded: 8	Stable (8 countries in last AR)
1.3 Landed costs ($) per RUTF carton in West & Central African Region (annual)	$48	Milestone not met: $51.60	Improving ($55.20 in last AR)
1.4 Number of days to complete delivery of RUTF in West & Central African Region (Coastal Countries/Landlocked Countries) (annual)	50/70 days	Milestone significantly exceeded: 10/51 days	Improving (16/70 in last AR)
1.5 $ value (in millions) of domestic resources matched through the CNF (cumulative)	70	Milestone not met: 13	This is a new indicator which relates to the CNF strategic results framework
1.6 Number of countries with multi-year partnership frameworks with the CNF (cumulative)	3	Milestone not met: 0	This is a new indicator which relates to the CNF strategic results framework
1.8 Percentage of nutrition commodities procured through the match window (annual)	25%	Milestone exceeded: 32%	This is a new indicator which relates to the CNF strategic results framework
1.9 Number of individual donors contributing to the CNF (cumulative)	7	Milestone exceeded: 10	This is a new indicator which relates to the CNF strategic results framework.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output has had mixed results over the past year but overall has been assessed as continuing to meet expectations. The output is showing significant progress compared to targets against five out of seven indicators and despite indicator 1.3 not meeting target for the second year in a row, progress against this indicator is showing improvement since last year, reversing a previously deteriorating trend.

Failures to meet the milestones on indicators 1.5 and 1.6 reflect a slower than expected progress in establishing key operational procedures under the Child Nutrition Fund (CNF). Much work this year has focused on formalising these processes and procedures through the work of the Steering Committee. This has included work to finalise and agree key documents such as the Governance Basis, Allocation Criteria and Strategic Results Framework but also involved discussions and decisions on expanding country eligibility to include countries with high or very high levels of stunting as well as aligning the service package and costings with the World Bank Investment framework as much as possible. Positively, this year has seen the addition of several new donors to the CNF (indicator 1.9) including a substantial contribution from the Bezos family as well as other bilateral donors such as Ireland and Canada showing a growing confidence among the wider donor community to engage with and contribute to the CNF.

This critical work to formalise key aspects of the CNF has meant that much of CNF staff time has been taken up with driving forward these processes. This has meant less time to dedicate to advancing discussions with national governments on multi-year matched deals as evidenced by the disappointing performance against indicators 1.5 and 1.6. However, with the onboarding of several new staff to the CNF Management Unit progress has now picked up with the SC being presented with two proposed multi-year investments at the last SC meeting.

FCDO has also contributed to a new £7.5 million match deal for SQ-LNS (a commodity used for the prevention of wasting) in Nigeria (indicator 1.7) which was disbursed to UNICEF for procurement in the latter half of 2024. This was done as a separate agreement, rather than through the match-window, to allow the government of Nigeria to procure RUTF (the commodity used to treat wasting) using its own systems for its half of the match. Due to some delays in agreeing the terms of Nigeria’s World Bank IDA loan, the matched deal is facing some delays, but we expect distribution of commodities to commence in 2025.

The landed cost per carton of RUTF in West and Central Africa (indicator 1.3) remains above the target however has seen a reduction of around 2 USD from its peak last year. This was primarily due to a stabilisation of key cost drivers associated with production of allowing suppliers to offer more competitive prices. Transport cost remained stable with the average spending on international freight decreasing due to significant progress made on regional production of RUTF (see output 2). This has further contributed to significant progress on reducing lead time to complete delivery of RUTF in this region (indicator 1.4) largely due to large volumes being able to be produced in Nigeria and Burkina Faso.

On a more concerning note, much of the progress against this output is at significant risk due to ongoing shocks to the international financing landscape and decisions to reduce overseas development assistance taken by several key donors. The trend within the new US administration to require a larger proportion of its funding for RUTF be procured from American producers will lead to challenges for the financial viability of local producers with knock-on impacts on increased average costs as well as lead times to complete delivery.

The CWIP feedback mechanism annual perception survey confirms a high level of awareness of ongoing action to identify sustainable sources of funding for wasting (73%) and governments having financed programmes to address child wasting from their national health/nutrition budget (70%). There was also a steady increase of participants responding ‘yes’ to government partners having managed to procure RUTF from sustainable financing. When asked about their perception of change (direction of travel) against these same indicators there was, however, a deteriorating trend across all, likely reflecting a concern amongst respondents relating to the current decline in international development funding and the implications this will have on availability of funding for nutrition.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Following last year’s annual review and the formalisation of agreements for the cost and time extension of the CWIP programme, the decision was taken to update the logframe leading to the addition of several new indicators for this output (indicators 1.5 – 1.9). Indicators 1.1 - 1.4 will be reported against for the next annual review but will then be retired as these components of the programme either come to an end (1.3 and 1.4) or have been replaced (1.1 and 1.2) by the formally agreed strategic results framework indicators for the CNF (1.5, 1.6, 1.8 and 1.9). In addition, the following indicator will be added to this output:

1.7 Number of children under 5 years of age who benefit from programmes to prevent malnutrition (this indicator will measure the reach specifically for FCDO's contribution to SQ-LNS in Nigeria)	Milestone to be determined		This is a new indicator which relates to the FCDO contribution to the CNF commodities match with Nigeria (programme window 1A).

Progress on recommendations from the previous AR:
Recommendation set out in last Annual Review	Update on progress made	Next steps (if any)
Given the impact of the increased lead time for RUTF in east DRC and its impact on overall lead-time for landlocked countries, specific focus should be paid to addressing the issues in DRC.	Regional procurement in Kenya is now the most used sourcing option for East DRC; but the indicator for landlocked country is still impacted by the Niger crisis, and the closing of previously used corridors.	To keep exploring alternative routes and corridors to use as the situation is still very volatile in the region and flexibility is required to ensure optimal lead time.
Given the successful fundraising for the Match Window, the CNF should set out a plan to build up demand from eligible GAP country governments including by setting up a domestic resource allocation tracking system and country engagement strategy.	The CNF is actively increasing demand for the Match Window by engaging in multi-year partnership discussions with strategic countries including Bangladesh and Nigeria, ensuring close alignment of domestic resources with investments from multilateral development banks. Additionally, the CNF is upgrading the Match Window dashboard to offer more detailed demand forecasts by product. To further support these efforts, UNICEF has recruited an additional staff member to focus on facilitating country engagement discussions.
The CNF should prioritise setting out its process for the allocation of unearmarked funding.	The CNF is finalising the Operating Basis, Allocation Criteria, and Allocation Plan, which includes the process for the allocation of unearmarked funding.

Recommendations for the year ahead:
- Given the risks to progress due to ongoing shocks in the financing landscape and in-line with the recommendation from FCDO Internal Audit Department (IAD), it is recommended that logframe targets for this output be reviewed to determine if targets are achievable.
- Milestones and target to be agreed for new indicator 1.7.

Output Title	Strong and resilient supply chains and information systems
Output number:		2	Output Score:	A++
Impact weighting (%):		10%	Weighting revised since last AR?	Yes (-5%)

Indicator(s)	Milestone(s) for this review	Progress	Trend since last annual review
2.1 Proportion of RUTF procured for West & Central African Region from suppliers from within the region (annual)	35%	Milestone significantly exceeded: 78%	Significantly increasing (49% in last AR)
2.2 Number of countries that have developed and are prioritising actions to integrate RUTF into national supply chain systems (cumulative)	8	Milestone exceeded: 11	Increasing (10 in last AR)

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall progress against this output has been significant. The proportion of RUTF which is being procured from suppliers in the region (indicator 2.1) has performed above expectations and this output is given a score of A++. In 2024, out of a total of approximately 1.4 million cartons procured by UNICEF for the West and Central African region, approximately 1.1 million cartons were produced locally by three suppliers – two in Nigeria and one in Burkina Faso. An additional 108,000 cartons (8%) were purchased from suppliers on the African continent (Kenya and South Africa) meaning only 14% if the total demand was procured from outside the African continent.

This indicator is measured annually, capturing only the results achieved within each year rather than cumulatively. While performance has exceeded expectations for two consecutive years, the milestone for this year was not increased solely based on last year’s results. The original target was set based on delivery capacity and contextual considerations. The strong performance remains significant, particularly given the baseline of 26% at programme inception, which had dropped to 15% by 2021, and reflects sustained progress within a consistent results framework

Unfortunately, this progress is likely to be undone in the year ahead given the increase in the proportion of US funding which will be required to be procured from American producers (so called ‘Title II funding’) combined with a reduction in funding overall. This review recommends that the final milestone for this indicator be reviewed to ensure it remains realistic in the current economic climate.

Progress on Indicator 2.2—tracking the number of countries prioritising the integration of RUTF into national supply chain systems—continues to exceed expectations. Having already reached 10 countries last year (over and above the total expected over the original programme timeframe), the programme has now expanded to 11 countries. Despite having reached the target for the programme already last year, the milestones for this indicator have not been adjusted upwards given challenging global context and declining global ODA. Given this indicator will be retired at the end of 2025 as this component of the programme wraps up, we are also not recommending revising the final target for the same reason. Progress in 2024 was in line with the originally planned trajectory of one additional country and hence represents good progress. The sustained progress in 2024 reflects both the relevance of the intervention especially in light of declining ODA finance available to support in country health systems, and the strong engagement of national stakeholders, building on the programme’s original strategic ambition. This year UNICEF’s Supply Chain Strengthening Centre (SCSC) emphasised the importance of utilising data collected from assessments to support countries in achieving better integration of nutrition into health systems. The UNICEF team provided significant technical assistance to Djibouti, where an Assessment Coverage and Evaluation was conducted. This collaboration enabled the identification of gaps within the nutrition supply chain, leading to targeted interventions. The final report from this assessment has been disseminated by the government, and improvements are currently underway to address the identified issues. Additionally, efforts were focused on developing national supply chain strengthening activity plans for Lebanon, Yemen, and Iraq, fostering a more coordinated approach to nutrition initiatives in these countries as well as developing Standard Operating Procedures (SOPs) for supply chain management for the government of Liberia. Progress against this indicator is consistent with the results from the CWIP feedback mechanism perceptions survey (figure 1 above) which shows a consistently high proportion of respondents confirming awareness of ongoing to support to government with regards to integration of RUTF within government supply systems. When answering the question related to perception of change however, responses again seemed to suggest a deteriorating situation similar to under output 1 above.

The agreement between UNICEF and FCDO for JUNIPr was signed in August and the first tranche of funding was disbursed in October. Therefore, the period between August to December 2024 has focused primarily on setting up and socialising the programme in the three focus countries (Bangladesh, Ethiopia and Mali) as well as formalising agreements for downstream partners. As such, there is no progress to report against any of the output indicators.
Figure 1: Results from CWIP feedback mechanism perceptions survey

When it comes to the overall perception of the consistency and reliability of the supply chains the CWIP feedback mechanism annual perception survey shows a mostly consistent trend in terms of positive responses (46% in 2025) but as above, when it comes to perceptions of trend the positive responses are reducing compared to previous years (see figure 2 below). Again, this is likely related largely to concerns over the ongoing shocks to the funding landscape.

Figure 2: Results from CWIP feedback mechanism perceptions survey

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following last year’s annual review and the formalisation of agreements for the cost and time extension of the CWIP programme, the decision was taken to update the logframe leading to the addition of two new indicators for this output (see below outputs 2.3 and 2.4) which relate to the JUNIPr component. Two indicators which were previously reported on under this output have been moved to output 5 below (5.1 and 5.2). Indicators 2.1 and 2.2 will be reported on in the next annual review but will then be retired as this component of CWIP wraps up. Because of these changes, the impact weighting of this output has been reduced by 5% so is now 10%. The new indicators for next year are:

2.3 Interoperable multisectoral nutrition monitoring system is in place (cumulative)	Milestones to be determined		This is a new indicator which relates to JUNIPr
2.4 Number of countries that have developed early warning thresholds in monitoring systems and plans to trigger interventions to prevent wasting (cumulative)	Milestones to be determined		This is new indicator which relates to JUNIPr

Progress on recommendations from the previous AR:
Recommendation set out in last FCDO Annual Review	Update on progress made	Next steps (if any)
FCDO to consider options for raising concerns through diplomatic channels regarding impacts of large-scale in-kind contributions of RUTF on the market for local suppliers and the risk this poses to gains made under this programme.	Done.
An urgent meeting should take place between UNICEF supply division and FCDO to discuss upcoming risks (in particular to 2.1) and ways to mitigate these risks on the overall targets for the programme	Done.

Recommendations for the year ahead:
- Given the risk articulated above of backsliding on progress due to ongoing shocks in the financing landscape and in-line with the recommendation from FCDO Internal Audit Department (IAD), it is recommended that logframe targets for this output be reviewed to determine if targets are realistically achievable.
- Milestones for new indicators 2.3 and 2.4 to be determined.

Output Title	Optimised policies and programmes
Output number:		3	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	Yes (-10)

Indicator(s)	Milestone(s) for this review	Progress	Trend since last annual review
3.1 Status of evidence-based global guidelines on treatment and prevention of wasting	At least 2 joint policy briefs on the prevention and treatment of wasting developed, and support given to countries to update their policies and protocols based on the new evidence-based guidelines on wasting; and support implementation research based on the gaps identified	Milestone met: / - 4 briefing notes finalised / - Operational tools still being drafted / -Country level workshops held to support operationalisation / -Paper on research gaps finalised and will be published in 2025	Progressing
3.2 Proportion of targets for the integration of treatment of child wasting across health systems building blocks in selected countries (Governance, financing, workforce, supplies, information, service delivery)	60%	Milestone met: 67% (6 countries)	Progressing (40% in last AR)
3.3 Increased proportion of health budget allocated to the prevention of child wasting in selected countries	Re-alignment of services completed in 60% of target countries	Milestone not met: 20% (2 countries)	Stagnant (20% in last AR)

Briefly describe the output’s activities and provide supporting narrative for the score. Overall, progress against this output has met expectations over the last year.

The progress on the WHO operational guidelines (output 3.1) has been slow likely in part due to key staffing gaps in WHO which have now been filled. Despite this however, progress still meets the milestone for this year. The annual CWIP perceptions survey confirms a high level of awareness of the new WHO guidelines (90%) and 68% of respondents also indicated awareness of work having begun at the national level to update guidelines indicating that even without operational guidelines and tools, work to operationalise the guidelines at the national level has begun. A joint WHO/UNICEF regional workshop for the operationalisation took place in Nairobi in November and involved representatives from Ethiopia, Kenya, Malawi, Namibia, Nigeria, South Sudan, Uganda, Zambia, Zimbabwe, Somalia, and Sudan. Similar workshops were conducted in francophone Africa and the middle east (Jordan, Egypt, Lebanon).

6 out of the 9 CWIP focus countries report wasting treatment being partly or fully integrated into health systems building blocks, indicating good progress against this output (indicator 3.2). Progress in relation to increasing the health budget allocation for the prevention of wasting has, however, been slower, with only two countries (Nigeria and Philippines) reporting an increase in domestic budget allocated to this (indicator 3.3). The lack of progress against this indicator highlights clearly the need for more action to strengthen the investment case for the prevention of wasting as is currently being planned under JUNIPr.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Following last year’s annual review and the formalisation of agreements for the cost and time extension of the CWIP programme, the decision was taken to update the logframe leading to the addition of three new indicators for this output (see below 3.4 – 3.6) which relate to the JUNIPr component. Indicator 3.2 will be reported on in the next annual review but will then be retired as this component of CWIP wraps up. Indicators 3.1 and 3.3 will continue but will only measure progress in the three JUNIPr countries post 2025.

Next year the following indicators will be added to this output:

3.4 Enabling environment and platforms for the prevention of wasting in food insecure settings assessed and conducive for implementation	Milestones to be determined		This is new indicator which relates to JUNIPr
3.5 Management of infants at risk of poor growth and development is part of the prevention package of wasting in food insecure settings	Milestones to be determined		This is a new indictor which relates to JUNIPr
3.6 Global advocacy/policy briefs developed and disseminated calling for increased funding allocation for the prevention of wasting in food insecure contexts	Milestones to be determined		This is a new indicator which relates to JUNIPr

Progress on recommendations from the previous AR;
Recommendation set out in last FCDO Annual Review	Update on progress made	Next steps (if any)
The UNICEF/WHO should consider sharing a timeline with the TAG for its work to ensure progress is made on the operational guidance	A tentative timeline for finalisation of the remaining sections of the operational guidelines has been shared with the Technical Advisory Group. The full guidelines are planned to be published in Q4 of 2025.
UNICEF and FCDO to discuss how best to track operationalisation of the guidelines at the national level to ensure this output stays on track to meet end-of-programme targets	It has been agreed that UNICEF and WHO will monitor national guidelines’ update process through ROs and COs, and keep that mapping updated. UNICEF to report on the number of countries adopting WHO 2023 recommendations / JUNIPr also includes an indicator to monitor progress up to 2030 / CWIP feedback mechanism annual perception survey has also incorporated two questions in relation to the roll out within its questionnaire.
FCDO and UNICEF to continue discussions with WHO and WFP on a Joint UN Initiative on the Prevention of Wasting.	JUNIPr agreement finalised and launched

Recommendations for the year ahead:
- WHO and UNICEF to work to urgently finalise operational guidelines and tools.
- Milestones and target for new indicators 3.4, 3.5 and 3.6 to be determined.

Output Title	Improved coordination and collaboration of the UN agencies leading to strengthened governance of the GAP
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Trend since last annual review
4.1 Number of meetings of the High-Level Panel on Child Wasting involving external stakeholders convened annually by UNICEF	1	Milestone met: 1	Progressing

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall progress against this output is assessed as meeting expectations.

The fourth annual meeting of the High-Level Action Review Panel (ARP) took place on June 20th, 2024, co-chaired by UNICEF ED Catherine Russell; USAID Administrator Samantha Power; and UK FCDO permanent undersecretary Nick Dyer standing in for the minister for development due to general election guidance for ministers. 18 participants joined the meeting, including new members such as the Governments of Ireland, UNHCR, FAO and 4 GAP frontrunner countries: Cambodia, Kenya, Nigeria and Pakistan. The meeting focused on two main topics: Sustainable Financing for Wasting; with a special intervention from the World Bank; and the Implications of the new WHO Guidelines. The minutes of the meeting are available on the GAP website: https://www.childwasting.org/action-review-panel-child-wasting.

The convening of the Action Review Panel on Child Wasting is a significant marker of success for this programme, not merely as a procedural milestone, but as evidence of strengthened global coordination, accountability, and momentum in addressing child wasting. The inclusion of new governments this year and, in particular, the GAP frontrunners, is important progress. As a high-level, multi-stakeholder mechanism, the Panel plays a critical role in translating strategic commitments into coordinated action, advocating for sustainable financing, and ensuring the delivery of effective, country-led solutions. Its activation reflects the programme’s influence in catalysing the governance structures necessary to drive systemic change.

The taskforce (the working level group underneath the ARP) continues to meet at least monthly and now also includes representatives from at least three of the four GAP countries and the two new UN agency members (FAO and UNHCR). The taskforce continues to see good levels of engagement from key stakeholders and provides a platform to discuss and agree messaging around key issues and take forward actions from the high-level ARP meetings to ensure progress is being made between meetings.

The changes in US government since the last ARP meeting and the dismantling of USAID has created several uncertainties with regards to the future co-chair roles of both the panel itself and taskforce. Whilst there has been no official communication from US counterparts about withdrawing its co-chair role there has been no engagement from any US officials since the start of the new administration. Adapting the ARP to the new post-USAID context will be a challenge for 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Following last year’s annual review and the formalisation of agreements for the cost and time extension of the CWIP programme, the decision was taken update the logframe leading to the addition of two new indicators for this output (see below indicators 4.2 – 4.3) which relate to the JUNIPr component. Two previous indicators under this output have been removed due to not adding additional value in terms of measuring progress against this indicator. Next year the following indicators will be added to this output:

4.2 National bodies involved in JUNIPr receive targeted training, technical assistance, or briefing sessions to engage with the new research evidence related to preventing wasting.	Milestones to be determined		This is a new indicator which relates to JUNIPr
4.3 National bodies involved in JUNIPr receive targeted training, technical assistance, or briefing sessions to engage with the new research evidence related to preventing wasting.	Milestones to be determined		This is a new indicator which relates to JUNIPr

Recommendations for the year ahead:
- FCDO to consider raising the ARP co-chair role in any upcoming engagement with US counterparts.
- FCDO and UNICEF to continue co-chairing the ARP taskforce (the working level group underneath the ARP panel) and lead planning for next ARP meeting.

Output Title	Strengthened evidence base and investment case for wasting
Output number:		5	Output Score:	B
Impact weighting (%):		15	Weighting revised since last AR?	This is a new output

Indicator(s)	Milestone(s) for this review	Progress	Trend since last annual review
5.1 Number of sources / varieties of alternative RUTF formulations assessed by UNICEF that are safe, meet UNICEF QA standards and represent value for money with a final outcome	8	Milestone exceeded: 11	Increasing (9 in last AR)
5.2 Number of countries where trials on alternative RUTF formulations have been conducted	1 RCT (ongoing) 5 acceptability trial (completed)	Milestone not met: 1 RCT (ongoing) / 1 acceptability trial (ongoing)	Progressing but delayed

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output is scored as a B meaning it has not met expectations this year.

Progress continues to be made on identifying alternative RUTF formulations (indicator 5.1). In 2024 UNICEF worked with two suppliers to develop additional soy and chickpea products. These products will be used in the planned acceptability trials and also the ongoing clinical efficacy trial (RCT). In 2024 UNICEF initiated collaborating with a supplier in Ethiopia to enable the use of local chickpea flour in an alternative RUTF. The facility has recently renovated their site and installed an extrusion machine to enable processing of chickpeas for use as an ingredient that can be incorporated into finished products such as RUTF. Despite this however, the annual CWIP perceptions survey showed a significant drop in respondents being aware of any work to identify alternative formulations of RUTF (see figure 3).
Figure 3: Results from CWIP feedback mechanism perceptions survey

Unfortunately, the results reported in last year’s annal review against indicator 5.2 (then output indicator 2.2) were incorrect. Due to an unintentional error/misunderstanding in the reporting provided to FCDO, it was understood that acceptability trials had been completed in 4 countries. However, this was incorrect as it has since transpired that it was only the initial feasibility assessments (a critical first step prior to commencing acceptability trials) which had been completed. Progress on the studies was delayed due to the initial lack of clear guidance on the type of evidence required. Following consultations, UNICEF experts recommended controlled trials that could assess the risk of reduced consumption and appropriately measure adverse events. In response, UNICEF’s legal and research ethics departments developed new policy and regulatory guidance to address gaps in the organisation’s research framework. Conceptual frameworks for clinical trials now include specific clauses to manage risks associated with research involving children and vulnerable populations. These strengthened legal, ethical, and methodological requirements have increased both the cost and complexity of the trials, necessitating additional staff, enhanced ethical oversight, and rigorous quality assurance measures, all of which have contributed to delays in trial commencement.

To address the funding shortfall as a result of the additional costs noted above, UNICEF had identified funding from USAID to complement the allocated CWIP funding. However, due to the change in US administration, this funding has now been terminated. This has resulted in a decision to reduce the ambition on number and type of evidence generated for alternative RUTF. The revised evidence generation milestone is to conduct two RCTs evaluating alterative RUTF formulations: one efficacy study and acceptability trial on a soy-based RUTF and one comparative consumption trial on a chickpea-based RUTF variant.

A no-cost extension will need to be agreed as the completion of these trials require additional time compared with the current agreement which is due to wrap up 31 March 2026.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Following last year’s annual review and the formalisation of agreements for the cost and time extension of the CWIP programme, the decision was taken update the logframe leading to the addition of this output. Two indicators (5.1 and 5.2) were moved down from output 2.

Next year the following indicators will be added to this output which relate to the work under the new JUNIPr programme component:

5.3 High-quality new body of evidence related to the prevention of wasting in food insecure contexts is disseminated and used at country and global level	Milestones to be determined		This is a new indicator which relates to JUNIPr
5.4 Contextualised decision framework to design specific interventions for prevention of wasting in food insecure settings is available and disseminated	Milestones to be determined		This is a new indicator which relates to JUNIPr
5.5 Global investment case to support increased government and donors' allocation towards the prevention of wasting in food insecure contexts disseminated	Milestones to be determined		This is a new indicator which relates to JUNIPr
5.6 Contextualised decision framework to design specific interventions for prevention of wasting in food insecure settings is available and disseminated	Milestones to be determined		This is a new indicator which relates to JUNIPr
5.7 National investment case including costed plan developed and disseminated in target countries	Milestones to be determined		This is a new indicator which relates to JUNIPr

Progress on recommendations from the previous AR:

Recommendation set out in last FCDO Annual Review	Update on progress made	Next steps (if any)
An urgent meeting should take place between UNICEF supply division and FCDO to discuss upcoming risks (in particular to output 5.2) and ways to mitigate these risks on the overall targets for the programme	Done. Number of trials reduced as explained above.

Recommendations for the year ahead:
- FCDO and UNICEF to agree a new timeline and milestones/target for completion of ongoing trials (indicator 5.2) including a no-cost extension and a milestone/target review.
- Milestones and targets for new indicators 5.3 – 5.7 to be determined.
## VALUE FOR MONEY

Key cost drivers and performance

The underlying parameters and VfM assessment that were presented in the Business Case continue to hold.

Economy- (key cost drivers)
- Key cost drivers for the production of RUTF (e.g. raw materials), have stabilised leading to costs coming down slightly but still remaining higher than in 2020. For example, for Western and Central African Region (WCAR), the landed costs per carton of RUTF have decreased by 6.5% (c. $3.60) in 2024 compared to 2023.
- Due to an increase in regional sourcing of RUTF, average spending on international freight per mobilised carton in the region also decreased.
- Travel and expenses continued to be low this year due to many meetings taking place online. Where travel has been necessary, SRO and PRO have taken it in turns to represent.
- The agreed JUNIPr programme will support better evidence and a strengthened investment case for the prevention of wasting to better be able to prevent wasting from occurring and reduce the need for treatment which would drive down costs.
- Cost overruns for RUTF Trials under Output 5 have emerged due to unexpected additional staffing, compliance and monitoring costs to ensure robust research. This has led to a reduction in milestone outputs.
Efficiency- (how well are we converting inputs into outputs?)
- Regional prepositioning and localisation of RUTF production show positive progresses despite challenges.
- The lead time and production costs of RUTF have seen significant improvements throughout Output 1 grant implementation. In 2024 the number of days to complete delivery in West and Central African region was 10 days in costal countries and 51 days in landlocked countries; a significant improvement on the 50/70 days average reported for 2023.
- There has been an increase in the number of sources / varieties of alternative RUTF formulations assessed by UNICEF from 9 in 2023 to 11 in 2024.
- Although there have been significant improvements on localisation with 78% of RUTF in West and Central African region being procured regionally, the shift in USAID position to require a larger proportion of American made products is likely to undermine some of this progress and will inevitably reduce the VfM of our investment.
- The publication of the new WHO guideline for the prevention and management of child wasting marks important progress. However, the delay in the finalisation of the operational guidelines is likely to negatively impact the efficiency with regards to the implementation at the country level.

Effectiveness- How well are the outputs of an intervention having the intended effect?
- The programme’s work to strengthen national leadership and locally produced nutrition commodities has led to an increasing number of RUTF cartons being procured by UNICEF and matched by domestic resources of 18 countries.
- The Child Nutrition Fund has gained significant momentum in 2024 attracting several new donors including both bilateral donors like Canada and Ireland as well as philanthropies, showing great impact from a modest initial UK investment.
- The number of countries that have developed and are prioritising actions to integrate RUTF into national supply chain systems has also increased, from 10 in 2023 to 11 in 2024, which is more than the milestone of 8, representing another achievement.
- The Action Review Panel in 2024 again created a unique momentum for key agencies, partners, and donors working on wasting to come together and renew their commitments towards reducing the prevalence of wasting globally.
Equity- how fairly are the benefits distributed, in particular among marginalised groups?
- The programme’s overall focus is on the poorest and most vulnerable affected by wasting as well as by specifically targeting countries that are classified as in crisis by UNICEF.
- The Child Nutrition Fund (CNF) focuses specifically on low and lower middle-income countries with high or very high levels of stunting and wasting.
- CWIP (and the CNF) specifically targets pregnant and breastfeeding women as well as children under 5 given they are known to be among the most nutritionally vulnerable.

Overall Cost Effectiveness
- While the cost of wasting treatment is still dependent on global market fluctuations, the efforts of this programme demonstrate clearly that improving the sustainability and predictability of financing along with a more localised and regionally focused production and procurement of RUTF leads to more rapid and positive impacts on children.
- The ongoing shocks in global financing for international development are likely to start to impact some of the progress and achievements made under CWIP thereby reducing the overall cost-effectiveness of the investment.
Assessment of whether the programme continues to represent value for money
The programme continues to represent value for money and should continue. The aims and outputs of CWIP are more relevant now than ever, given the recent reduction and restrictions on US financing for child wasting. Therefore, work to ensure sustainable financing for child wasting and ongoing efforts to prevent and treat wasting in the most cost-efficient way is timely and offers consistent value.

E: RISK

Overview of risk management
UNICEF have continued to manage risk throughout 2024 and continue to maintain a good mitigation plan for risks affecting CWIP. Overall, for 2024 UNICEF have employed a robust risk management approach by monitoring key risk areas, such as price of RUTF and the impact on exchange rates on how this affects CWIP VfM. Risks are discussed formally on at least a quarterly and risks are then updated on the AMP Risk Register.
In early 2025 CWIP underwent an Internal Audit Review which provided a review of our risk management process. The outcome assessed the net risk rating of CWIP as moderate due to robust controls identified across the programme.
The review noted that there is a lack of detail on the risk register reflecting specific safeguarding risks and that downstream partners had limited awareness of fraud reporting mechanisms. The SRO and PRO have taken note of these recommendations and have accordingly incorporated a specific risk on safeguarding within the CWIP risk register and have reminded all downstream partners of the appropriate procedures for reporting concerns in relation to fraud and aid diversion.

Risk Appetite
During a routine risk review, the risk appetite for CWIP was amended on AMP after an error was noticed on one of the risk categories. Public Service Delivery and Operations had an out-of-date risk appetite statement, so this was amended from minimal to cautious in line with both the GHD and FCDO wide risk appetite and reflecting a dynamic approach to risk appetite as context shifts, as outlined as best practice in Prof rule 17.

JUNIPr DDA
In 2024 a bespoke Due Diligence assessment was undertaken for the new JUNIPr component. The result of this assessment was that all 4 DDA pillars assessed were within the FCDO risk appetite. The assessment reviewed the partner’s systems, policies and processes with an aim of identifying risks associated with the provision of funds and recommending any mitigating actions required. Overall, the DDA concluded that the JUNIPr investment with UNICEF is “Low Risk” and considered the systems upon which it depends to be generally robust, placing it within FCDO’s risk appetite for CWIP. UNICEF continues to operate effectively as a host organisation of CWIP, with appropriate safeguards in place to protect donor funds. FCDO therefore proposed to support UNICEF as the lead agency of JUNIPr through a Contribution Arrangement up to March 2030.

Global shocks to financing landscape for international development
Due to ongoing shocks in the financing landscape for international development, there has been an increase in risk and volatility for the work CWIP focuses on. As a result of this, four of the risks identified in the CWIP risk matrix are now above the risk appetite threshold and have been escalated accordingly. Risk to the programme’s progress and efficiency is likely to increase as the impact of funding cuts will affect health service delivery given strong links between poor access to basic health services and increasing rates of malnutrition. These risks and mitigation strategy continues to be monitored closely, and the SRO and PRO have had regular conversations with partners and wider stakeholders about the uncertainty and some potential implications for the programme. This is also likely to be the main focus of the next global Action Review Panel meeting (see output 4) in 2025.

Conclusion
While the ongoing shocks to the financial system are expected to adversely affect some of the achievements under CWIP (particularly under output 1 and 2), for the most part the programme is nonetheless projected to deliver substantial results relative to a counterfactual scenario in which the programme had not been implemented. This underscores the programmes added value and its role in mitigating the worst potential impact of the crisis. Taking all this into account it is recommended that the overall risk rating for this programme remains at moderate.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
FCDO and UNICEF have met at least bimonthly to reflect on the programmes progress, review progress on previous recommendations, risk management, including updates to the risk register, and priorities for the coming period. Meetings were previously monthly but amended to bimonthly given the agreement to have quarterly JUNIPr meetings between FCDO, UNICEF, WFP, WHO and IFPRI. The bimonthly UNICEF/FCDO meetings are minuted for audit and reference purposes. UNICEF have provided two narrative and financial reports each year – in accordance with the FCDO-UNICEF Framework Agreement. The narrative reports include information on progress, risks, and challenges.

In 2024 the CWIP logframe was updated to reflect progress and the uplift funding with to CNF, the extension of the timeline of the overall business case until 31 March 2030 and the inception of JUNIPr. Several indicators were added and closed at the outcome and output level. This was approved by the SRO and Deputy Director of HDD and reflects the progression of CWIP into its new phase.

The CWIP feedback mechanism perceptions survey established as part of this programme has enabled wider nutrition stakeholders to provide insights and perspectives on progress under CWIP. In general, the survey results from this year show mixed results, with some improvements but also some deteriorating trends primarily reflecting concerns about the ongoing shocks to the global financing for international development. Gradual improvements can be seen on two main indicators such as awareness of government partners successfully managing to procure RUTF from sustainable financing sources (improved from 13% at baseline to 31% in 2025) and awareness of any efforts by UNICEF to support government partners to identify and establish sustainable financing for treatment of wasting (73% in 2025 compared to 56% in 2021). A number of indicators remained mostly consistent since 2021, including whether efforts had been seen regarding UNICEF supporting the government partners to integrate RUTF into the national supply chain system (‘Yes’ has ranged from 68% to 73% 2021-2025) and whether UNICEF actively supporting / promoting existing nutrition policies and protocol to prevent and/or treat child wasting effectively in their country (‘Yes) ranged from 67%-71% 2021-2025), which shows a good level of consistency. However, there was a concerning decline on whether programme(s) had sustainable funding to address wasting over the last year (34% ‘Yes’ compared to 40% in 2024. This might reflect a lack of secure and sustainable funding in wasting, perhaps due to reprioritisation in governments and a reversal to reliance on humanitarian aid.

Travel costs continue to be low. In early 2025 the PRO and nutrition team leader conducted a field visit to monitor progress on the CNF contribution. In 2025, a priority will be to visit a country under JUNIPr in order to monitor progress during the early stages of the programme.

As is standard practice with UNICEF, FCDO funds are transferred in advance on a six-month basis to enable UNICEF to take forward programme activities. At the end of 2024, FCDO has paid a total of £15,737,732 to the CNF (via components 101 and 102) and £22,412,268 to support operational activities to strengthen policy and programming – including in the nine priority countries (component 103) and £3,293,044 for JUNIPr (component 401).

Due to a change in accounting treatment for funding to UNICEF from cash accounting to resource accounting, a total underspend of £2,719,394.69 against component 103 was identified for FY 24/25 and was therefore re-profiled into FY 25/26.

In 2024 FCDO completed an agreement amendment on component 300750-103 as it was incorrect in the original agreement. This did not affect the budget of the programme. FCDO also set up a new component (401) and added funds to an existing component to channel the uplift to the programme.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
FCDO and UNICEF have met at least bi-monthly to reflect on the programmes progress, review progress on previous recommendations, risk management, including updates to the risk register, and priorities for the coming period. UNICEF continue to produce two Partner Progress Reports annually, which contains analysis of outputs and indicators, risks and VfM. The report also includes updates from the regional and country offices. These reports are used to review risks, understand emerging pressures and to monitor progress at all levels of the programme.

The feedback mechanism established as part of this programme continues to enable wider nutrition stakeholders to provide insights and perspectives on UNICEF’s performance. For 2025, while there are some notable improvements for indicators since the baseline in 2021, there has been some deterioration in progress, e.g. on RUTF procurement. As CWIP continues to 2030 we may see further progress from baselines and from one year to the next.

CWIP PRO travelled to Nigeria for the CNF SC visit to meet with key stakeholders and policy makers. This allowed for monitoring of progress at the country level of the £7.4m contribution for a commodities match deal of SQ-LNS and RUTF. There is strong demand for the CNF in Nigeria and a growing track record of successful match funded RUTF procurement at State Government level. UNICEF and the Federal Government of Nigeria are keen to work in partnership to develop future CNF matches and commitments. The field visit facilitated networking, deep dives into status of malnutrition in Nigeria and government action, the work of UNICEF Nigeria and lobbying government/key actors to continue to access the CNF.

Additionally, the SRO and PRO travelled the WHO office in Geneva in April 2024 to attend the JUNIPr partner concept workshop in person. This was a productive meeting with all key partners present to discuss the concept note and the next steps for the JUNIPr project. It allowed for networking and was very successful with lots of agreement on next steps.

JUNIPr partners including the FCDO also planned a global awareness raising event and invited speakers from all three of the JUNIPr countries to discuss challenges and progress made in the prevention of wasting in their contexts.

The Annual Review process is led by the SRO in collaboration with the PRO, using inputs from the annual feedback mechanism perception survey of all key stakeholders at the national level in the CWIP countries, field visits as well as from UNICEF reports and discussions (including in the CNF steering committee meetings) over the course of the year. The Head of the FCDO Nutrition Team and Head of the Humanitarian and Development Department provide internal quality assurance and approval.

Evidence
As illustrated by continued significant over-achievement against output indicator 1.1, the CWIP Match window continues to be successful in increasing the availability of lifesaving supplies to prevent and treat child wasting. 7 out of the 9 CWIP countries reported that national budgets were allocated to fund commodities for the treatment of child wasting, indicating huge successes for efforts in lobbying for sustainable financing. Since its inception in 2021, the Child Nutrition Fund has so far matched over $33 million in domestic resources in 18 countries.
[note] https://www.childnutritionfund.org/match-window

FCDO’s learning under CWIP is also contributing to wider international learning/review processes. This was demonstrated during at least two conferences in 2024 in St Louis and Washington DC, where learnings from the CWIP programme was presented and discussed.

Learning
Key lessons learned in 2024 include the need for flexibility to advance funding to respond to growing demand from the countries for the Match Window. The establishment of nutrition financing interventions under the CNF, initially implemented to drive sustainability efforts can also be leveraged for emergency preparedness, as both the Match Window and the pre-financing envelope have been leveraged in the context of nutrition food crises.

A key lesson from the work on alternative RUTF formulations is that multi country trials projects require more time for national level regulations, ethics approvals, and multi partner coordination than originally envisioned. This has been the main lessons learnt since the start of the programme, and flexibility in timelines continues to be required to ensure high quality for the alternative recipes, leading to greater impacts and scale up of such formulations. This has been further noticed in 2024 with more delays in the Alternative Ingredients for Malnutrition (AIM) project due to clarifications and budget constraints.

Finally, recent ODA cuts underline the urgent need for sustainable and domestic financing mechanisms in order to prevent and treat malnutrition and child wasting effectively. Therefore, the need for CWIP has been strengthened to continue global progress towards tackling malnutrition, in order to improve long term health outcomes of vulnerable women, children and babies.

Date of last narrative financial report	February 2025	Date of last audited annual statement	February 2025