## Annual Review Template

Title: Child Wasting Innovation Programme (CWIP), formerly PARSNIP
Programme Value £ (full life): £61.4m		Review date: 18 June 2026
Programme Code: 300750	AMP start date: 20 May 2020	AMP end date: 31 March 2030

Summary of Programme Performance
Year	20/21	21/22	22/23	23/24	24/25	25/26
Overall Output Score	A	A	A	A	A	A
Overall programme risk rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/58006857.odt
DevTracker Link to results framework:	D0006523.xlsx

A. SUMMARY AND OVERVIEW

Description of programme
The Child Wasting and Innovation Programme (CWIP), previously known as the Progressing Action on Resilient systems for Nutrition through Innovation and Partnership (PARSNIP) programme, is a 10-year, £61.4 million partnership between the Foreign, Commonwealth, & Development Office (FCDO) and UNICEF. The programme contributes to the Sustainable Development Goal of ending malnutrition in all its forms by 2030 by strengthening the resilience of services to treat and prevent child wasting (acute malnutrition) in the face of climate change.

The programme focuses on countries in Africa and Asia where child wasting remains persistently high and climate change is an increasing risk. It builds on FCDO’s wider investments to strengthen quality and coverage of services to treat child wasting. The programme will promote reform in the way the UN agencies and other multilaterals address child wasting and how governments and donors finance prevention and treatment.

The intended objectives set out in the Business Case are to: (1) reduce mortality associated with child wasting, (2) reduce the prevalence of child wasting in target countries; and (3) avoid permanent damage to the growth and development of young children that results in them doing less well at school, being less economically productive as adults and less resilient to the effects of climate change. This will be achieved by:
- Integrating treatment and prevention of child wasting into health systems as part of Universal Health Coverage.
- Optimising treatment and prevention services to reduce cost, improve coverage and enable services to be scaled up to deal with climate shocks and other crises effectively.
- Generating evidence of how government services can more effectively prevent child wasting, including where climate change is increasing risk.
The programme seeks to accomplish this through:
1. The creation of financing solutions to improve predictability and value for money of prevention and treatment of wasting (Output 1).
2. Addressing weaknesses in the supply chain and information systems for wasting and to strengthen value for money (Output 2).
3. Adapting programming and policy globally and in target countries to strengthen treatment and prevention of wasting (Output 3).
4. Improved coordination and strategic leadership to promote reform in how wasting is addressed (Output 4)
5. Strengthening the evidence base and investment case for effective action on wasting (output 5).
In April 2020, a £0.75 million cost extension was approved for the overall programme to enable UNICEF to take forward strategic research relating to the prevention and treatment of acute malnutrition in the face of COVID-19. The UK ODA reductions in 2021 caused some budget uncertainties for the programme however this was managed through redistribution of funding across the years rather than an absolute budget reduction. In November 2023 a further cost and time extension of £30.7m and 5 years (for a total of £61.5m until March 2030) was approved to build and expand on the successes and lessons learned over the first three years of the CWIP programme around improving the sustainability of financing for wasting through the Child Nutrition Fund (CNF) and strengthening the global evidence base for better prevention of wasting (this component has subsequently been called the Joint United Nations Initiative for the Prevention of wasting (JUNIPr)).

2025 marks the final year of implementation for several of the components under CWIP. For the ten primary countries supported since 2020—Afghanistan, Bangladesh, Ethiopia, Indonesia, Malawi, Mali, Nepal, Nigeria, Pakistan, and the Philippines—current operations are set to conclude in March 2026. This also encompasses support provided to UNICEF Supply Division’s Strengthening Supply Chain Centres and the West and Central Africa Regional Office’s supply functions. For this reason, this will be the last AR reporting against several of the indicators in the logframe.

The components set to continue include the support to the CNF and JUNIPr. A No-Cost Extension (NCE) for the Alternative Ingredient for Malnutrition (AIM) project has also been granted hence this component will continue until 31 March 2028. Additionally, some of the activities under the WHO Guideline development component will continue as part of the JUNIPr.

The reduction in ODA under the Spending Review period of April 2026 to March 2029 will also result in key changes to this programme. The findings of this Annual Review therefore reflect on a programme in transition with further deliberations needed in relation to a budget reduction of the JUNIPr component.

Summary supporting narrative for the overall score in this review
The CWIP programme, now in its 6th year, has continued to deliver meaningful results despite a challenging context. This year saw significant disruption to international development systems and decline of global ODA funding. Overall, the programme is assessed as continuing to meet expectations despite a particularly challenging global context. A key achievement of this programme has been the continued success of the Child Nutrition Fund (CNF) which has attracted almost $1bn in additional funding allowing governments to access matched funding to be able to scale up coverage of essential nutrition commodities and services.

This review covers the reporting period between January 1st to December 31st, 2025, and is based on a combination of official UNICEF progress reports, the CWIP Feedback Survey results, participation in WHO guideline Technical Advisory Group meetings and regular catch-up calls with JUNIPr partners and the UNICEF team as the basis for the scores and narrative provided. Given this review is written in April 2026, where further progress has been made since the end of the reporting period, this is referred to in the narrative but progress against milestones remains based on the agreed reporting period.

Major lessons
- National leadership and systems integration are critical for sustainability. Countries that embedded child wasting priorities within national policies, budgets, and supply chains—leveraging the UN Global Action Plan—demonstrated stronger progress and resilience, even amid funding and political transitions. Local ownership and tailored roadmaps have been key to expanding both treatment and prevention coverage.
- Regional production and supply chain localisation deliver value for money and resilience. Investments in regional and national Ready to Use Therapeutic Food (RUTF) production have reduced costs and lead times, enabling faster, more reliable treatment delivery. However, persistent bottlenecks—such as security, administrative hurdles, and corridor disruptions—highlight the need for ongoing risk management and adaptive logistics.
- Evidence and innovation drive policy and practice but require sustained investment. The development of alternative RUTF formulations and the generation of new evidence on prevention and treatment have positioned the programme as a global leader. Sustaining engagement as evidence develops and translating it into policy and scalable practice requires continued technical and financial support.
- Funding volatility and global shocks demand agility and prioritisation. The programme’s ability to adapt to a shifting funding landscape—through logframe revisions, phased implementation, and targeted advocacy—has been essential to protecting core gains and managing expectations. However, reduced resources have necessitated difficult trade-offs and reinforced the importance of domestic resource mobilisation.
- Pooled financing can diversify resources and strengthen coordinated action on nutrition. The CNF has demonstrated that a well-designed pooled financing mechanism can help mobilise a broader mix of funding for nutrition, including from philanthropies, governments and bilateral donors, while also creating a practical platform for aligning priorities, reducing fragmentation and coordinating action across partners.

Recommendations for the year ahead:
In light of reduction in UK ODA, the remaining programme components are entering a period of significant transition that requires careful and proactive adaptation. It is essential that FCDO and UNICEF work together to undertake a thorough review of the strategic direction of the JUNIPr component. This joint review should critically assess the implications of reduced funding, considering both immediate and longer-term impacts on delivery, coverage and ambition. The aim should be to ensure that programme priorities, delivery models and resource allocation are realigned to reflect the new financial reality, while safeguarding core objectives and maintaining a focus on the most critical outcomes. In parallel, FCDO and UNICEF should ensure that the CNF retains a clear strategic focus on strengthening health systems and mobilising more sustainable financing for child wasting, while clearly articulating its distinct value-add and ensuring that any adaptation to evolving humanitarian needs does not dilute its core purpose or undermine the existing humanitarian architecture.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change for the programme is that by: (1) improving the value for money of investments to treat and prevent child wasting; (2) strengthening the capacity of government services to treat and prevent wasting; and (3) enhancing coordination and collaboration by the UN and other external actors, it should be possible to more effectively prevent child wasting and treat those who slip through the net more cost effectively. This should ultimately result in: (a) fewer child deaths; (b) improved growth and development of children living in contexts where climate change presents a threat; and (c) benefits to long term resilience that come from reducing the likelihood that people get trapped in a cycle of poverty and malnutrition.

As set out below there is evidence at the end of the sixth year of the programme that this theory of change still holds. There continues to be an increased recognition among the UN and other donors of the relevance of the actions being taken through this programme to help shift how child wasting is addressed. Despite the backdrop several consecutive global shocks since the programme’s inception in 2020, it is delivering significant results and the rationale and value for money proposition set out in the Business Case still hold.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Indicators	Milestones (Dec 2025)	Baseline (2019)	Progress (As per Dec 2025)
	Impact: fewer child deaths and a reduction in child wasting and other forms of malnutrition
Impact 1: Prevalence of wasting among children in target countries	<5%	7.3%	Milestone not met but showing improvement: 8.60%
Impact 2: Proportion of children with wasting who recover after receiving treatment	>90%	85%	Milestone not met: 85.6%
Impact Indicator 3: Number of countries integrating nutrition in their emergency and resilience response to mitigate the impact of climate change			4 countries (Ethiopia, Malawi, Mali and Nepal).
	Outcome indicators
Outcome 1: Number of children receiving essential nutrition actions for the prevention of child wasting in target countries (CWIP 1)	2.5 million	1.9 million	Milestone significantly exceeded: 165,268,469
Outcome 2: Proportion of children with severe wasting receiving treatment in target countries (CWIP)	>35%	20%	62.9%. / Milestone significantly exceeded
Outcome 3: Number of countries allocating national health / nutrition budgets to commodities to treat child wasting (CNF)	5	0	12. / Milestone exceeded
Outcome 4: Proportion of total RUTF costs covered by national health budgets (CNF)	10%	0%	6%. / Milestone not met and backsliding (was 16% in 2024)
Outcome 6: Number of GAP initiatives related to increased advocacy for the prevention of wasting including in food insecure contexts (global and national) (JUNIPr)	1	0 (2024)	2. / Milestone exceeded
Outcome 7: Percentage of children under 5 years of age who benefit from programmes to prevent malnutrition (CNF)	90% (by 2030)	36%	On track: 70% (in 2024) / CNF annual report for 2025 to be published in July
Outcome 8: Percentage of children under 5 years of age with wasting who are admitted for treatment (CNF)	90% (by 2030)	41%	Off track: 46% (in 2024) / CNF annual report for 2025 to be published in July

This reporting year marks a transition point for outcome‑level measurement. It will be the final year of reporting against Outcomes 1–4, with Outcomes 1 and 2 being replaced by Outcome Indicators 7 and 8 which are aligned with the CNF Strategic Results Framework, and Outcomes 3 and 4 repositioned as outputs aligned to CNF indicators 1.6 and 1.8.

Overall, progress against impact and outcome indicators remains broadly on track, with performance at this level reflecting both the ambition of the indicators and the inherent challenges of inferring causality in complex, multi‑sectoral nutrition systems. Progress on treatment‑related outcomes remains generally positive, with treatment coverage remaining high in the contexts where CWIP has been focused and a growing number of countries integrating wasting into national systems and budgets, indicating a sustained contribution of this programme toward longer‑term impact.

While some outcome indicators have not met/appear off-track to meet their milestones—particularly those related to global treatment coverage and proportion of total treatment costs covered by domestic budgets—the overall direction of travel is positive, with several indicators showing improvement over time. Taken together, the evidence suggests the programme is making a credible contribution to higher‑level outcomes, even where attribution cannot be definitively established. Continued progress will depend on sustaining delivery momentum and navigating an increasingly challenging and resource constrained external operating environment.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Taking into consideration the evidence provided in this Annual Review, the programme should continue as it is on track to achieve its outcomes and mitigate the wider impacts of conflict, climate change and decreasing global ODA financing. Against the backdrop of global cutbacks on financing for international development, the focus of the programme is even more relevant now than ever before. The initiative strongly aligns with UK objectives to strengthen health systems and improve effectiveness of humanitarian response.

## C. DETAILED OUTPUT SCORING

Output Title	Effective financing and pre-positioning
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Trend since last annual review
1.1 Total equivalent number of RUTF cartons procured with VII Nutrition Window and Nutrition Match Funds (CWIP)	135,833	Milestone significantly exceeded: 1,543,198	Increase of 318,980 cartons since last AR
1.2 Number of partner governments integrating wasting treatment into GFF investment cases (CWIP)	6	Milestone met: 8	Continued progress (6 countries in 2025)
1.3 Landed costs ($) per RUTF carton in West & Central African Region (CWIP)	$48	Milestone not met but showing positive progress: $50.60	Improving ($51.60 in last AR)
1.4 Number of days to complete delivery of RUTF in West & Central African Region (Coastal Countries/Landlocked Countries) (CWIP)	50/70 days	Milestone significantly exceeded: 20/43 days	Slight increase for costal countries. Improving for landlocked countries.
1.5 $ value of domestic resources matched through the CNF (cumulative) (CNF)	30	Milestone significantly exceeded: 53	Increasing (13 in last AR)
1.6 Number of countries with multi-year partnership frameworks with the CNF (cumulative) (CNF)	8	Milestone not met but showing positive progress: 7	Significantly increasing (0 in last AR)
1.7 Number of children under 5 years of age who benefit from programmes to prevent malnutrition (this indicator will measure the reach specifically for FCDO's contribution to SQ-LNS in Nigeria) (CNF)	48,000	Milestone not met: 0	This is a new indicator and has not been reported against in previous AR’s
1.8 Percentage of nutrition commodities procured through the match window (CNF)	25%	Milestone exceeded: 30%	Slight reduction (32% in last AR)
1.9 Number of individual donors contributing to the CNF (cumulative) (CNF)	8	Milestone significantly exceeded: 20	Significant increase (10 in last AR)

Briefly describe the output’s activities and provide supporting narrative for the score.
This output has had mixed results over the past year but overall has been assessed as continuing to meet expectations. Apart from indicator 1.7, performance across most indicators has met or exceeded expectations; where milestones were narrowly missed (1.3 and 1.6), performance still represents significant improvement compared to the previous year and failure to meet milestones reflects justifiable, clearly articulated factors.

Performance against Output Indicators 1.1 and 1.2 is strong in volume and leverage. By end‑2025, a cumulative 1.54 million cartons of RUTF had been procured through the Child Nutrition Fund[1] (CNF), significantly exceeding the milestone for the review period and reflecting continued scale‑up. Six additional governments integrated wasting treatment into the Global Financing Facility (GFF) investment cases in 2025, bringing the cumulative total to eight. However, progress on GFF integration has plateaued since 2023, suggesting that future gains may require more targeted policy and technical engagement rather than reliance on organic uptake.
[1] More information about the CNF and its various windows can be found here: https://www.childnutritionfund.org/

Results against Indicators 1.3 and 1.4 show overall improvements in Value for Money, with landed costs per RUTF carton in West and Central Africa decreasing by around 2 percent compared to last year, and average delivery times remaining well below agreed benchmarks. These gains are primarily driven by increased regional and domestic production, which reduces international freight costs and lead times and are especially significant given a backdrop of global market fluctuations as well as geopolitical instability. However, performance is uneven: headline averages mask persistent delays and high costs for fragile, landlocked contexts, where administrative, security and seasonal access constraints continue to undermine efficiency. Regional sourcing has not yet delivered its full potential benefits across all corridors.

Progress on domestic resource mobilisation (Indicator 1.5) is strong, with US$53m matched cumulatively, largely for RUTF procurement, demonstrating sustained government buy‑in and effective use of the matching mechanism. By contrast, Indicator 1.6 slightly underperforms, with seven countries endorsed for multi‑year partnership frameworks against a milestone of eight, though additional partnership frameworks have since been agreed by the steering committee.

Performance on Indicator 1.7 is not meeting expectations, with no children yet having been reached with SQ‑LNS in Nigeria at the end of 2025 due to delays in procurement by the government. While preparatory activities were undertaken, this represents a clear underperformance however distribution to four states was initiated in January 2026 which demonstrates progress despite delays.

Indicators 1.8 and 1.9 perform well, with close to 30 percent of RUTF procurement channelled through the Match Window and a significant increase in individual donors, strengthening the sustainability and diversification of the CNF funding base. However, the growth of the CNF and the evolving global context have brought into sharper focus tensions relating to the Fund’s original purpose: strengthening health systems and reducing reliance on short-term humanitarian financing. At the same time, some stakeholders are increasingly advocating for the CNF to play a more direct humanitarian financing role.
These developments will require careful management to ensure that the CNF retains its strategic focus while demonstrating sufficient flexibility to respond to changing needs and circumstances. It will also be important to ensure that any evolution in the CNF’s role does not inadvertently undermine the existing humanitarian architecture.

Overall, this output demonstrates good aggregate performance and improving VfM, particularly through supply‑chain localisation and domestic co‑financing. However, results remain context‑dependent, with persistent delivery risks in fragile settings and slippage on prevention‑focused programming highlighting areas requiring corrective action.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
A logframe review was carried out in December 2025 as per last year’s annual review recommendation.
- Milestones for indicator 1.7 were agreed.
- Milestones against indicator 1.5 were revised downwards to align with the CNF Strategic Results Framework which was agreed by the Steering Committee. Importantly the end-of-programme target for this indicator remains the same hence the changes reflect an adjustment to a more realistic timeline rather than a lowering of ambition.
This will be the final year in which progress against Indicators 1.1–1.4 is reported. Reporting on CNF outputs (Indicator 1.1) is transitioning to the agreed Strategic Results Framework indicators (1.5, 1.6, 1.8 and 1.9), and the programme component underpinning Indicators 1.2–1.4 has now concluded.

Progress on recommendations from the previous AR:

Recommendation set out in last Annual Review	Update on progress made	Next steps (if any)
Given the risks to progress due to ongoing shocks in the financing landscape and in-line with the recommendation from FCDO Internal Audit Department (IAD), it is recommended that logframe targets for this output be reviewed to determine if targets are achievable.	Logframe review carried out end of 2025	None
Milestones and target to be agreed for new indicator 1.7.	Logframe review carried out end of 2025	None

Recommendations for the year ahead
- FCDO and UNICEF to convene a joint deep‑dive to critically assess the causes of zero delivery against Indicator 1.7 (SQ‑LNS reach in Nigeria), to agree actions with clear to ensure delivery and accountability in 2026.
- The CNF should maintain a clear strategic focus on strengthening health systems and mobilising more sustainable financing for child wasting, while articulating where the Fund adds distinct value and ensuring that any adaptation to evolving humanitarian needs does not dilute its core purpose or undermine the existing humanitarian architecture.
Output Title	Strong and resilient supply chains and information systems
Output number:		2	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Trend since last annual review
2.1 Proportion of RUTF procured for West & Central African Region from suppliers from within the region (CWIP)	80%	Milestone exceeded: 89%	Increasing (78% in last AR)
2.2 Number of countries that have developed and are prioritising actions to integrate RUTF into national supply chain systems (CWIP)	9	Milestone exceeded: 16	Increasing (11 in last AR)
2.3 Interoperable multisectoral nutrition monitoring system is in place (JUNIPr)	Monitoring systems review and analysis done in all three countries (Bangladesh, Ethiopia and Mali)	Milestone progress ongoing but not yet met	This is a new indicator and has not been reported against in previous AR’s

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output is assessed as having exceeded expectations despite some delays in the new component (JUNIPr).

Performance against Indicator 2.1 is strong and exceeds the annual milestone. In 2025, 89 percent of RUTF procured for West and Central Africa (WCAR) was sourced from within the region, continuing an upward trend since 2022 and reflecting successful investments in regional manufacturing capacity. This has contributed to improved price competitiveness and reduced reliance on overseas suppliers. However, when in‑kind donations are included, the share of overseas‑sourced RUTF increases substantially (41 percent), highlighting that overall sourcing patterns remain partially outside UNICEF’s control and that systemic dependence on external supply persists.

Progress against Indicator 2.2 has exceeded expectations, with 16 countries now developing and prioritising actions to integrate RUTF into national supply chains, significantly above the milestone of nine. Regional supply chain strategies have been drafted or finalised, providing a clearer framework for national action from 2026 onwards. While institutional engagement is strong, the extent to which these strategies translate into operationalised, budgeted and sustained system changes remains to be demonstrated.

Performance against Indicator 2.3 is ongoing. In Bangladesh and Ethiopia, substantive analytical work has been undertaken to map, review and assess readiness of existing multisectoral nutrition and social protection information systems, identifying both opportunities and limitations for integrating wasting prevention indicators. In Mali, system strengthening remains at an earlier stage, with implementation deferred to 2026 following completion of formative research. While progress is appropriate given this indicator is new, full operationalisation has not yet been achieved.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
A logframe review was carried out in December 2025 as per last year’s annual review recommendation:
- Final target for indicator 2.1 was substantially increased from 35% to 80% (this was still exceeded in this final year showing a significant overachievement compared to what was expected at the start of the programme).
- Milestones 2.3 and 2.4 were agreed.
This will be the final year for which progress will be reported against indicators 2.1 and 2.2. From next year there will instead be an additional indicator added (2.4) related to the JUNIPr component.

As a result of the difficult but necessary decision taken by the Prime Minister to reduce the ODA budget to 0.3%, the JUNIPr component of this programme is having to undergo some downsizing of budget which is likely to have an impact on the original outputs and outcomes. As a result, a logframe review will need to be carried out to adjust the milestones for all the remaining indicators under this output.

Progress on recommendations from the previous AR:
Recommendation set out in last FCDO Annual Review	Update on progress made	Next steps (if any)
Given the risk articulated above of backsliding on progress due to ongoing shocks in the financing landscape and in-line with the recommendation from FCDO Internal Audit Department (IAD), it is recommended that logframe targets for this output be reviewed to determine if targets are realistically achievable.	Logframe review carried out end of 2025	None
Milestones for new indicators 2.3 and 2.4 to be determined.	Logframe review carried out end of 2025	None

Recommendations for the year ahead:
In light of the budget downsizing of the JUNIPr component, FCDO and UNICEF should undertake a formal logframe review to revise outputs and adjust milestones for all the remaining indicators under this output ensuring expectations remain realistic and aligned with available resources.

Output Title	Optimised policies and programmes
Output number:		3	Output Score:	B
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Trend since last annual review
3.1 Status of evidence-based global guidelines on treatment and prevention of wasting (CWIP + JUNIPr)	8 Countries updated their policies and protocols based on new evidence-based guidelines on wasting; implementation research supported in 8 countries	Milestone met: 8 countries	Progressing
3.2 Proportion of targets for the integration of treatment of child wasting across health systems building blocks in selected countries (Governance, financing, workforce, supplies, information, service delivery) (CWIP)	>80%	Milestone not met: 67% (6 countries)	Stagnant (67% in last AR)
3.3 Increased proportion of health, food and social protection budget allocated to the prevention of Child wasting in selected countries (CWIP + JUNIPr)	Re-alignment of services completed in 80% of target countries	Milestone not met: 44% (4 countries)	Improving (20% in last AR)
3.4 Enabling environment and platforms for the prevention of wasting in food insecure settings assessed and conducive for implementation (JUNIPr)	3 context analysis to inform the prevention package completed	Milestone progress ongoing but not yet met	This is a new indicator and has not been reported against in previous AR’s
3.6 Global advocacy/policy briefs developed and disseminated calling for increased funding allocation for the prevention of wasting in food insecure contexts (JUNIPr)	0	Milestone exceeded: 1	This is a new indicator and has not been reported against in previous AR’s

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output is assessed as not meeting expectations this year due to three of the indicators not having been met. For indicator 3.2 this is the last year of reporting against this indicator meaning the end-of-programme target for this indicator has not been met.

Progress against Indicator 3.1 meets expectations. Eight countries have updated national guidelines in line with the 2023 WHO guideline on wasting, meeting the milestone. Supporting global public goods—such as updated policy briefs, inclusion of wasting actions in the UHC Compendium and the One Health Costing Tool, and publication of a BMJ Global Health supplement—represent credible contributions to the global evidence base. That said, most operational tools critical for implementation (including the UNICEF‑WHO implementing guide) are yet to be finalised, with delivery now expected in 2026, placing pressure on downstream uptake.

Performance against Indicator 3.2 is below target and stagnant. Only 67 percent (6 of 9) of CWIP countries report partial or full integration of wasting treatment across health‑system building blocks, unchanged from last year and below the >80 percent milestone. Reported integration is uneven and often partial: for example, financing gaps persist (Pakistan), quality and coverage remain constrained (Indonesia), and integration is limited to specific service components (Bangladesh). This indicates structural challenges in translating policy intent into system‑wide implementation.

Progress under Indicator 3.3 shows improvement but remains limited. Four countries report increased budget allocations to wasting, but evidence on scale, sustainability and allocation between prevention and treatment is weak, with incomplete budget disaggregation.

Indicator 3.4 reflects early‑stage delivery under JUNIPr. Context analyses for prevention packages are ongoing, with validation deferred to 2026. This represents a delay relative to the original timeline of the programme. By contrast, Indicator 3.6 shows progress, with the release of a global Call to Action. This was accelerated ahead of original timeline due to increasing conflict contexts worldwide and decreasing funding landscape.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
A logframe review was carried out in December 2025 as per last year’s annual review recommendation and milestones for indicators 3.4 – 3.6 were agreed and indicator 3.3 was expanded to take into account budget allocations across multiple sectors (previously only health budget was included). This will be the final year for which progress will be reported against indicator 3.2. From next year there will instead be an additional indicator added (3.5) related to the JUNIPr component.

As a result of the difficult but necessary decision taken by the Prime Minister to reduce the ODA budget to 0.3%, the JUNIPr component of this programme is having to undergo some downsizing of budget which is likely to have an impact on the original outputs and outcomes. As a result, a logframe review will need to be carried out to adjust the milestones for all of the remaining indicators under this output.

Progress on recommendations from the previous:
Recommendation set out in last FCDO Annual Review	Update on progress made	Next steps (if any)
WHO and UNICEF to work to urgently finalise operational guidelines and tools.	Implementation guidance planned to be released early 2026/currently under copy-editing	Dissemination plan for 2026 to be developed
Milestones and target for new indicators 3.4, 3.5 and 3.6 to be determined.	Logframe review carried out end of 2025.	None

 Recommendations for the year ahead

In light of the budget downsizing of the JUNIPr component, FCDO and UNICEF should undertake a formal logframe review to revise outputs and adjust milestones for all the remaining indicators under this output, ensuring expectations remain realistic and aligned with available resources.

Output Title	Improved coordination and collaboration of the UN agencies leading to strengthened governance of the Global Action Plan on child wasting
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Trend since last annual review
4.1 Number of meetings of the High-Level Panel on Child Wasting involving external stakeholders convened annually by UNICEF	1	Milestone not met: 0	No progress (1 in last AR)
4.2 National bodies involved in JUNIPr receive targeted training, technical assistance, or briefing sessions to engage with the new research evidence related to preventing wasting.	Inception workshops with national bodies engaged in GAP to brief and sensitise on research plans in 3 countries	Milestone met	This is a new indicator and has not been reported against in previous AR’s
4.3 UN Collaboration between UNICEF, WFP and WHO at global, regional and national level demonstrate positive progress and improved coordination towards the prevention of wasting	At least 1 coordination meeting per quarter held at global and national level (2 per quarter)	Milestone met	This is a new indicator and has not been reported against in previous AR’s

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall progress against this output is assessed as having met expectations.

Under performance against Indicator 4.1 reflects a joint and decision by FCDO and UNICEF, as co‑chairs of the Action Review Panel (ARP) Task Force, not to convene a high‑level panel meeting in 2025. This decision was taken in light of significant organisational restructuring and leadership transitions across participating agencies, with the shared assessment that high‑level engagement would be more effective once institutional changes had stabilised. Momentum has nonetheless been maintained through regular monthly Task Force meetings, which sustained dialogue, enabled collective prioritisation, and supported preparation for a Directors’‑level convening planned for 2026. As such, while the annual milestone was not met, this was expected and managed, with progress deferred rather than diminished.

Progress against Indicator 4.2 meets expectations. Inception workshops were successfully delivered in Bangladesh, Ethiopia and Mali, engaging national governments, UN agencies, academia and civil society to introduce JUNIPr, map existing policies and platforms, and shape emerging prevention packages. These workshops established a shared understanding and identified next steps, though engagement to date has focused on planning rather than technical implementation, which will be required in subsequent phases.

Performance against Indicator 4.3 is positive. A formal global governance structure and Steering Committee for JUNIPr have been established, and regular coordination meetings are now taking place at global, regional and country levels. Initial steps to establish national steering committees are underway in all three countries, although most remain in development rather than fully operational.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
As a result of the difficult but necessary decision taken by the Prime Minister to reduce the ODA budget to 0.3%, the JUNIPr component of this programme is having to undergo some downsizing of budget which is likely to have an impact on the original outputs and outcomes. As a result, a logframe review will need to be carried out to adjust the milestones for indicators 4.2 and 4.3 under this output.

Progress on recommendations from the previous AR:
Recommendation set out in last FCDO Annual Review	Update on progress made	Next steps (if any)
FCDO to consider raising the ARP co-chair role in any upcoming engagement with US counterparts.	Not yet possible.	To consider in 2026/27
FCDO and UNICEF to continue co-chairing the ARP taskforce (the working level group underneath the ARP panel) and lead planning for next ARP meeting.	The ARP taskforce continued to meet monthly throughout 2025 and engagement from key stakeholders remained high despite the turbulent and uncertain times.	Planning is ongoing for a 2026 ARP meeting

Recommendations for the year ahead:

In light of the downsizing of the JUNIPr component, FCDO and UNICEF should undertake a formal logframe review to revise outputs and adjust milestones for indicators 4.2 and 4.3 under this output, ensuring expectations remain realistic and aligned with available resources.

Output Title	Strengthened evidence base and investment case for wasting
Output number:		5	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	Yes (new output)

Indicator(s)	Milestone(s) for this review	Progress	Trend since last annual review
5.1 Number of sources / varieties of alternative RUTF formulations assessed by UNICEF that are safe, meet UNICEF QA standards and represent value for money with a final outcome	10	Milestone met: 10	Slight decrease (11 in last AR)
5.2 Number of countries where trials on alternative RUTF formulations have been conducted	1 Randomised Control Trial (RCT) ongoing	Milestone met: 1 RCT ongoing	Progressing
5.3 High-quality new body of evidence related to the prevention of wasting in food insecure contexts is disseminated and used at country and global level	3 formative research conducted	Progress towards milestone ongoing but not yet met (formative research in all 3 countries has started but not yet finalised)	This is a new indicator and has not been reported against in previous AR’s
5.4 Contextualised decision framework to design specific interventions for prevention of wasting in food insecure settings is available and disseminated	3 context-specific decision framework developed	Progress towards milestone ongoing but not yet met (decision frameworks proposed but not yet validated)	This is a new indicator and has not been reported against in previous AR’s
5.6 National and subnational reviews, landscape analysis, assessment, bottleneck analysis conducted in contexts of intervention on food systems, impacting prevention of wasting	1 review done in the target countries	Progress towards milestone ongoing (reviews are ongoing in all 3 countries but none are yet finalised).	This is a new indicator and has not been reported against in previous AR’s

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall, performance against this output is assessed as meeting expectations as milestones have either already been achieved or demonstrating that they are on track to achieve their milestones in early 2026.

Indicators 5.1 and 5.2 relate to the Alternative Ingredients for Malnutrition (AIM) project which is trialling new alternative formulations of RUTF. This component was granted a No-Cost Extension (NCE) until 31 March 2028. Performance against Indicator 5.1 meets expectations. UNICEF has assessed 10 alternative RUTF formulations with a final outcome, meeting the milestone, though this represents a slight decrease compared to the previous year due to one supplier no longer meeting UNICEF approval standards. Progress has been credible but incremental, reflecting the complexity of regulatory approval, quality assurance and supplier readiness. While several suppliers have expressed interest in alternative formulations, none are yet procurement‑ready, and further QA and commercial validation will be required before alternatives can meaningfully contribute to routine supply.

Progress against Indicator 5.2 is strong and on track. The randomised controlled trial in Burkina Faso reached full recruitment for both moderate and severe acute malnutrition populations and progressed into data analysis without safety concerns, with results expected in 2026. In Ethiopia, the comparative consumption trial advanced through protocol development, supplier engagement and eventual government endorsement, despite initial regulatory hesitation. While encouraging, these trials remain pre‑commercial, and any anticipated cost or supply benefits will only materialise if results are positive and can be translated into procurement decisions at scale.

Delivery against Indicators 5.3 and 5.4 is ongoing but behind planned timelines for the set milestone. Formative research, literature reviews and selection of academic partners have commenced in all three JUNIPr countries, and draft prevention packages and decision frameworks have been proposed. However, finalisation and validation remain pending and was deferred to early 2026. As such, these indicators were not met at the end of the reporting period for this annual review however both are on track to be met in the first quarter of 2026.

Indicator 5.6 remains in progress, with multiple national and sub‑national reviews and analyses completed across countries, but findings are yet to be fully synthesised and translated into programme decisions.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A logframe review was carried out in December 2025 as per last year’s annual review recommendation.
- Milestones for indicator 5.2 were revised to reflect the changes which were agreed as part of the NCE for this component reflecting a change to the type of evidence being generated and therefore a longer timeline to completion. This component will now run until 31 March 2028.
- Milestones for indicator 5.7 were revised to reflect a more realistic timeline while still maintaining the overall target for the end of the programme. This indicator will now not be reported on until the final year of the programme (2029).
- This will be the final year for which progress will be reported against indicator 5.1 as the component underpinning this indicator ends.
- New indicator 5.5 will not be reported against until end of 2028 as per the agreed milestones for this indicator.
As a result of the difficult but necessary decision taken by the Prime Minister to reduce the ODA budget to 0.3%, the JUNIPr component of this programme is having to undergo some downsizing of budget which is likely to have an impact on the original outputs and outcomes. As a result, a logframe review will need to be carried out to adjust the milestones for all of the remaining indicators under this output.

Progress on recommendations from the previous AR:
Recommendation set out in last FCDO Annual Review	Update on progress made	Next steps (if any)
FCDO and UNICEF to agree a new timeline and milestones/target for completion of ongoing trials (indicator 5.2) including a no-cost extension and a milestone/target review.	Logframe review carried out end of 2025	None
Milestones and targets for new indicators 5.3 – 5.7 to be determined.	Logframe review carried out end of 2025	None

Recommendations for the year ahead:
In light of the budget downsizing of the JUNIPr component, FCDO and UNICEF should undertake a formal logframe review to revise outputs and adjust milestones for indicators 5.3 to 5.7 this output, ensuring expectations remain realistic and aligned with available resources.

## D: VALUE FOR MONEY

Key cost drivers and performance- VfM performance compared to the original VfM proposition in the business case

The underlying parameters and VfM assessment that were presented in the Business Case continue to hold.

Economy- (key cost drivers)
- Increased regional and domestic production of RUTF has led to continued reduced landed costs and delivery times. For example, the landed cost decreased by 4.2% from 2024. However, further efficiency is constrained by administrative, security and seasonal limitations which may encourage purchasing of imported alternatives.
- CWIP’s AIM workstream continued to advance, meeting its milestone for the number of sources of alternative RUTF formulations assessed as safe. Further progress may be hampered by complexities in quality assurance and control requirements.
Partner travel and expenses remained low in 2025 as the majority of meetings took place online.
Efficiency- (how well are we converting inputs into outputs?)
- The CNF has successfully facilitated significant domestic resource mobilisation, mainly for RUTF, indicating strong and continued government buy in and fruitful engagement with the match and programme windows.
- UNICEF procured c. 30% of RUTF through the CNF match window and a total of 20 individual donors signed contribution arrangements to the CNF, enhancing and strengthening the CNF funding base.
- The Bezos Family Foundation gave a generous donation of $500 million to the CNF this year, which will allow further interventions in maternal nutrition, micronutrient supplementation and treatment of wasting.
- Increased awareness among stakeholders is a vital first step in progress towards systems change from short term humanitarian funding towards more sustainable, predictable child wasting funding sources. The feedback mechanism reported a 27% increase in awareness of sustainable financing for the prevention and treatment of wasting from the baseline year.
- Progress in the early stages of JUNIPr has continued, and the formative research stage will soon be concluding. This will enable the formative research reports to be produced for early 2026 and inform validation workshops so that the research can move onto the next stage.

Effectiveness- How well are the outputs of an intervention having the intended effect?
- The CNF has been effective in scaling up RUTF carton procurement in 2025, significantly exceeding the milestone for this period. This has led to an increase in the number of children with severe wasting receiving treatment in target countries, increasing to 62.9% from the baseline proportion of 42%.
- The number of partner governments integrating wasting treatment into GFF investment cases has also increased, showing continued strong leveraging power and leading to stronger country ownership.
- Robust JUNIPr global governance structures and communication channels developed, with structured meeting scheduled at various levels to ensure alignment and responsiveness to evolving project requirements. This has led to strong government buy in and reported protection of child wasting budgets in order to ensure continued engagement with JUNIPr.
- 16 countries are developing and prioritising actions to integrate RUTF into national supply chains, displaying strong institutional engagement.
- However, partial/full integration of wasting treatment across health-system building blocks is uneven and sometimes partial. Only 67% of CWIP countries have reported full or partial integration showing there is still further work and thinking needed to enact sustained system-wide change.
- There was no Action Review Panel in 2025 due to ongoing shocks to the international aid architecture and substantial restructuring at both FCDO and UNICEF HQ. This could potentially slow the momentum gained in previous years for key agencies, partners and donors working on wasting to come together, discuss key blockers to progress and renew their commitment towards reducing the prevalence of wasting globally. However, ARP Task Force meetings continued, maintaining dialogue and ensuring progress is not lost.

Equity- how fairly are the benefits distributed, in particular among marginalised groups?
- The programme’s overall focus is on the poorest and most vulnerable affected by wasting as well as by specifically targeting countries that are classified as in crisis by UNICEF.
- CWIP and the CNF aims to specifically improve the health and nutrition outcomes of the most nutritionally vulnerable by targeting pregnant and breastfeeding women, as well as children under 5.

Overall Cost-effectiveness- what is the interventions ultimate impact on our foreign policy objectives, relative to the inputs that we or our agents invest in it?
- While the cost of wasting treatment is still dependent on global market fluctuations, the efforts of this programme demonstrate clearly that improving the sustainability and predictability of financing along with a more localised and regionally focused production and procurement of RUTF leads to more rapid and positive impacts on children.
- The ongoing shocks in global financing for international development are likely to negatively impact some of the progress and achievements made under CWIP and may also reduce the outputs and impact of the JUNIPr component. This may in turn reduce the overall cost-effectiveness of the investment.
Assessment of whether the programme continues to represent value for money

Despite challenges, the programme continues to represent value for money and should continue. The first phase of the programme delivered clear, attributable results against its original objectives. For example, the seed funding disbursed to the CNF attracted almost $1bn in additional funding allowing governments to access to matched funding to be able to scale up coverage of essential nutrition commodities and services. CWIP supported increased treatment coverage across the 9 pilot countries and saw an increasing number of countries integrating wasting treatment into national systems and budgets. By working to ensure financing for child wasting is more sustainable and available for countries to access, as well as working to strengthen the way in which wasting is prevented from occurring, CWIP continues to improve the cost-effectiveness of the way in which child wasting is tackled in a budget-constrained global world.

E: RISK

Overview of risk management

UNICEF have continued to manage risk throughout 2025 and continue to maintain a good mitigation plan for risks affecting CWIP. The main ongoing risk in 2025 was due to continued shocks to the financing landscape for international development, leading to increased funding shortfalls and diverting attention from longer term thinking to address urgent gaps in the short term. UNICEF have led several discussions on the direct risks and developed mitigation plans. Risks are discussed formally with FCDO on at least a quarterly basis and are then updated accordingly on the AMP Risk Register.

Risk Appetite
During a routine risk review, the risk appetite for CWIP was amended on AMP after an error was noticed on one of the risk categories. Public Service Delivery and Operations had an out-of-date risk appetite statement, so this was amended from minimal to cautious in line with both the FCDO wide risk appetite and reflecting a dynamic approach to risk appetite as context shifts, as outlined as best practice in FCDO’s Prof rule 17.

In addition, the March 2025 Internal Audit Review noted that there was no risk appetite set for the People risk category for the programme. The Risk Register Appetite for People was update to cautious for people-related risks in line with the central FCDO risk appetite statement. At the end of 2025 no risks sit outside the overall appetite.

CWIP Risk Register Review
In 2025 the FCDO Programme Team for CWIP undertook a thorough review of the risk register, after noting that several of the risks were overlapping and containing out of date information and references. The PRO synthesised and combined several risks in order to streamline and update the register. Outdated language, e.g. reference to the Covid-19 pandemic, were removed, amended or updated. This ensured that the risk register remains efficient, well organised and up to date and prevented it from becoming unwieldly. This was an opportune time to conduct a deep dive and full review in light of the changing global ODA context, ensuring the programme’s risks reflected this and remained responsive to external change.

Two risks were added in line with further recommendations from the CWIP Internal Audit Review reflecting both safeguarding and fraud risks. CWIP has a low appetite (minor/moderate) for these risks, in line with FCDO’s zero tolerance stance regarding fraud, corruption or sexual exploitation, abuse and sexual harassment (SEAH).

Specific risks identified in 2025, to be monitored in 2026

CWIP AIM and JUNIPr Projects
UNICEF are currently searching for other donors for AIM and JUNIPr components of CWIP. Both FCDO and UNICEF have made proactive efforts to identify new funding sources for both components and produced summaries of the projects which have been presented to interested donors however additional funding has not yet been secured. This risk will need to be monitored as a failure to secure additional funding may reduce the overall impact of FCDO’s investment.

Nigeria SQ-LNS Reach- Output Indicator 1.7 Underperformance
The CWIP contribution to the CNF match for Nigeria has been slower than expected to become operational as no children were reached with SQ-LNS in 2025, underperforming against the set target of 48,000. As per the recommendation set out in section C of this review, a deep dive to understand the causes and identify mitigation strategies to prevent further delays.

Global shocks to financing landscape for international development
The JUNIPr project is particularly vulnerable to shocks to the global aid architecture and funding landscape due to the effectiveness of the research component relying on funding being available for the delivery of nutrition services (not included in JUNIPr budgets). This shocks to the global financing landscape in 2025 has therefore added pressure to the delivery of JUNIPr within the programme’s relevant risk appetite. The FCDO and UNICEF prioritised frank discussions on programme viability amid ongoing change and uncertainty, using quarterly JUNIPr meetings to seek assurance. While sufficient funding was maintained to support programme delivery, the short‑term and volatile nature of funding in these contexts means this risk will need to be kept under close review.

Risk of progress plateauing and/or backsliding due to shocks in the global system
Despite significant progress under CWIP, there is a risk that gains may plateau or reverse due to major global shocks and a contracting funding landscape. This has implications for areas such as treatment coverage, where programme‑driven efficiencies are unlikely to fully offset reductions in available resources. There is also a risk that attention shifts away from addressing longer‑term structural barriers towards short‑term responses to urgent gaps, and that progress in promoting prevention gives way to a renewed focus on treatment alone, driven by resource constraints and its strong life‑saving rationale. As the external landscape continues to evolve, changes in the relative influence of different actors and priorities may further shape focus and direction, with potential implications for coherence and balance across the sector. While largely beyond the control of the CWIP programme team, it will be important to monitor how these risks materialise across both ongoing and closing components, with further analysis carried forward into the Programme Completion Review.

Conclusion
The emerging reality of the ongoing shocks to the international development financial system can now be expected to adversely affect some of the achievements under CWIP (particularly under output 1 and 2). Specifically, the planned evidence generation of JUNIPr remains a key concern going into 2026. However, we have seen continued success and progress from the first phase of the programme in spite of significant challenges such as market disruptions associated with the Covid-19 pandemic, providing key lessons and learnings for the second half and showing that progress is possible even in challenging times. Despite the challenging context, for the most part the programme is nonetheless projected to deliver substantial results relative to a counterfactual scenario in which the programme had not been implemented at all. This underscores the programmes added value and its role in mitigating the worst potential impact of ongoing shocks. Taking all this into account it is recommended that the overall risk rating for this programme remains at moderate.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
FCDO and UNICEF have met at least bimonthly to reflect on the programmes progress, review progress on previous recommendations, risk management, including updates to the risk register, and priorities for the coming period. The bimonthly UNICEF/FCDO meetings are minuted for audit and reference purposes. These bimonthly UNICEF/FCDO meetings complement the quarterly JUNIPr meetings between FCDO, UNICEF, WFP, WHO and IFPRI. The Nutrition Team leader attends the quarterly CNF Steering Committee meetings to represent the UK, with the CWIP Senior Responsible Officer (SRO) acting as an alternate.

The CWIP feedback mechanism perceptions survey established as part of this programme has enabled wider nutrition stakeholders to provide insights and perspectives on progress under CWIP. This year’s feedback mechanism exercise will be the final round as the first phase of CWIP ends and aimed to capture reflections from not only the previous year but the full programme lifetime. In general, the survey results from this year show mixed results. Positive feedback was noted from high, sustained awareness of efforts to strengthen sustainable financing and RUTF supply chains. However, there continued to be concerns about slower perceived progress on budget allocation for prevention and reflecting growing concern about future financing trajectories. These concerns relate more to the global funding environment and highlights limitations in the extent to which efficiency improvements can offset global funding reductions.

Overall, the feedback mechanism indicated strong CWIP performance against country expectations, showcasing sustained credibility and influence among partners and countries. Over the six years of examining perceptions to CWIP, stakeholders reported a strong need to shift towards prevention of child wasting, which will be the ongoing focus of CWIP via JUNIPr. Overall, the learnings and reflections gathered from the feedback mechanism will inform and reinforce the second phase of the CWIP programme and strategic direction of FCDO’s child wasting work.

At the end of FY 25/26, FCDO has paid a total of £18,427,732 to the CNF and £22,412,268 to support operational activities to strengthen policy and programming – including in the nine priority countries and £7,176,980 for JUNIPr.

In July 2025 a non-cost extension agreement was completed, amending the end date from 31 March 2026 to 31 March 2028, to allow completion of the Alternative Ingredient for Malnutrition (AIM) project. The extension reflected necessary methodological upgrades following government and expert feedback, rather than performance issues, and did not require additional funding.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
UNICEF have provided two narrative and financial reports each year – in accordance with the FCDO-UNICEF Framework Agreement. This is complemented by quarterly and annual CNF reports. These reports are used to review risks, understand emerging pressures and to monitor progress at all levels of the programme as well as inform conclusions in the Annual Review.

The majority of first phase of CWIP came to an end in 2025 (with the exception of the AIM project and CNF components both of which have been extended). UNICEF and the 9 CWIP countries have identified lessons, recommendations and priorities from the first phase of CWIP, which will be used to inform future programming. The first phase has seen significant achievements unlocked at global, regional and country levels which will provide excellent learnings and lessons for the continued roll out and progression of the CNF and JUNIPr.

In early 2025 a field visit to Nigeria was conducted to monitor progress on the CNF contribution, visiting health clinics and nutrition initiatives in Abuja, Kano and Jigawa. A planned early field visit under JUNIPr did not take place due to competing priorities. A visit is therefore recommended in 2026, as the programme progresses beyond its initial phase.

Evidence

Positive evidence for the influence that CWIP has had on national policies incudes the progress on the UN Global Action Plan (GAP) on Child Wasting at country level. For example, the Indonesian Ministry of Health and UNICEF have ensured child wasting remains a national priority by aligning support with the GAP and the country’s 2025-2029 Medium-Term Development Plan. This will ensure that multi-year government investments to treat and prevent child wasting are continued to be secured, rather than relying on humanitarian aid efforts. Another example includes Mali and Nepal, which continued to rollout the GAP roadmap within the framework of CWIP, showing continued commitment to tackling child wasting in a structured way.

During the JUNIPr quarterly calls convened over the year, it became clear that there were some delays in holding the validation workshops and finalising the prevention packages to be trialled in each country. FCDO sought assurance that JUNIPr still had sufficient buy in from national governments to continue. JUNIPr partners and UNICEF country representatives were able to provide this reassurance; however, this will need to be continually monitored in 2026 as the ongoing shocks within global aid/international development continue.

Learning
Supply Chain learnings

CWIP’s achievement in increasing the amount of RUTF procured within Africa combined with lower costs and decreased lead times provide a robust body of evidence on the cost-effective benefits of localised procurement. These learnings can be scaled up and used as a roadmap for other regions to emulate, providing useful and scalable learnings for global improvements to supply chains.

Feedback mechanism learnings

The CWIP feedback mechanism has provided a valuable and structured source of learning, offering an independent, confidential and longitudinal perspective on how UNICEF’s performance under CWIP is perceived by governments, UN agencies, NGOs and other stakeholders across nine programme countries. It has ensured continued robust monitoring of progress during the first phase of the programme and the learnings will inform the second phase to bolster success based on key successes and failings in the first phase. The mechanism has allowed continued tracking of the perceptions of the programme and facilitated the programme team’s understanding of what actions are specifically having an impact, generating change at country level and having immediate effect on the treatment and prevention of child wasting.

Key lessons

2025 was a seismic year with several unpredictable changes in the global political and funding architecture for child wasting, malnutrition and development more generally. The CWIP team have had to reprioritise, reexamine and explore the feasibility of all future planned activities. CWIP needs to continue prioritising a balanced approach for 2026, ensuring decisions that are taken acknowledge, and remain realistic given the changing context.

The global reduction in ODA continues to underscore the urgent need for increased sustainable and domestic financing to prevent, detect and treat child wasting effectively. Therefore, the value of CWIP has been strengthened to continue global progress towards tackling malnutrition, in order to improve long term health outcomes of vulnerable women, children and babies worldwide.

Date of last narrative financial report	February 2026	Date of last audited annual statement	February 2026