BUSINESS CASE ADDENDUM

PROGRAMME TITLE	GLOBAL RISK FINANCE FACILITY (GRIF – PROJECT 300751)
Directorate/ Post	International Finance	Contact name	Nicola Jenns
Original programme budget	£150m	Country or region targeted	Global
Cost extension value (if applicable)	Up to £15m.	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	The then Secretary of State approved the original Business Case. / Business Case amendment in 2021 approved by the then Foreign Secretary.
New increased or reduced programme budget (if applicable)	£165m	Original programme start and end dates	August 2019 – December 2027
Latest AR programme score and outcome confidence rating	A	New programme end date (if applicable)
		Programme ID	203469

Detailed information
Programme summary	The Global Risk Finance Programme (GRIF) builds resilience to shocks such as droughts and hurricanes, and saves lives by enabling quicker, more effective and predictable responses to disasters. It does this by providing grants to establish and pay for pre-arranged finance (PAF), for example: / supporting shock-responsive social protection through the World Bank which scales up automatically after disasters to get money to affected people quickly, / subsidising premiums for drought and tropical cyclone insurance for African countries through the African Development Bank (AfDB), / pre-positioning funding for civil society response to floods, drought, tropical cyclones and extreme heat through Start Network, and / establishing new insurance for critical infrastructure and public services in the Caribbean. / The programme is FCDO’s major source of premium subsidy support for PAF and insurance. Fast payouts using pre-agreed triggers enable responses that can pre-empt damage, thereby reducing the overall costs of response, mitigating the impact of shocks on lives and livelihoods and averting secondary impacts. This can be three to five times cheaper overall, as well as faster and more dignified for recipients. / There is significant demand for this support and a track record of success. Significant payouts have been made including $62m in early 2024 for the World Food Programme, Start Network and countries to help them cope with severe drought in southern Africa.
Changes	Previous amendments: The GRIF business case was originally agreed to support projects delivered through the World Bank. It was amended in April 2021 (with an additional £60m added to the budget) to expand support to the AfDB, critical public services, infrastructure and civil society. This enabled FCDO to support locally-led action such as drought response through Start Network, humanitarian response through the World Food Programme, UNICEF and Red Cross, and hurricane protection for critical services through the new Caribbean Water Utilities Insurance Collective. / Changes proposed: The proposed £15m extension will enable FCDO to maintain momentum towards greater use of PAF. Increasing the proportion of PAF as part of crisis finance is a major UK objective for the Financing for Development conference and beyond, delivering the recommendations of the High-Level Panel on Closing the Protection Gap. / The changes proposed here will enable spend to be made against the programme’s confirmed resource budget of £12m for FY 25/26 as the programme is nearing its financial limit with only £2.82m headroom remaining. It will also allow some flexibility (up to £5.82m) if additional resources are available within IFD this year, but there will be no obligation on FCDO above the £12m confirmed budget for 2025/6. / New evidence: There is a pressing need for continued FCDO support to GRIF and for PAF. Extreme weather events have increased five-fold in the past 50 years. In the last decade alone, 1.7 billion people have been affected by sudden, extreme climate-related disasters. Country partners are increasingly interested in better managing climate risks, and there is strong demand for PAF and insurance. Without subsidies, the poorest and most vulnerable countries tend to remain underinsured (meaning payouts are inadequate to meet the needs), resulting in the need for donor appeals, which are more costly and slower. / Trade offs: If this expansion is not agreed, it will not be possible to utilise the £12m confirmed budget for this financial year. PAF is emerging as a key part of global financial system reform, and the proposed extension will enable continued progress towards partnering with the insurance industry and demonstrating the benefits of insurance in helping to mobilise private capital for climate vulnerable countries.
Implementation	The GRIF programme would continue to be delivered as it is now, supporting work through the World Bank (trust fund administrative agreement), AfDB (trust fund administrative agreement) and civil society (Start Network accountable grant agreement). / A new component is envisioned, developing a partnership with the City of London and private sector insurers in line with the Foreign Secretary’s vision. This will be funded through the expansion of an existing partnership if possible, with no new tender or contract required.
Budget	The current budget (after business case amendment 1 in 2021) is £150m. / Of this, £147.18m has been spent, with £2.82m remaining to spend. / The proposed cost extension is £15m (with £9.18m profiled alongside the existing headroom of £2.82m to enable spend against our existing allocation of £12m for 2025/6). Remaining headroom would be available if additional resources allow, subject to Spending Round allocation decisions, but there will be no financial commitment beyond our confirmed budget in 2025/26. / IFD believes this to be affordable within the 2025/26 allocation, and there are no commitments beyond this financial year.
Impact	Impact of cost/time extensions on VfM (check relevant box): / ☒ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☐ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition.
Risk	This amendment will enable FCDO to continue to support pre-arranged finance and insurance and potentially develop a new partnership with City of London insurers. The major risk would be if this support creates dependency on subsidies that cannot be sustained longer term. The programme will therefore work closely with private sector and other partners to be catalytic and develop self-sustaining initiatives, being very clear that there is no ongoing obligation on our support
Results/Monitoring and Evaluation	New results: An additional up to £15m could be expected to enable up to £39m in total risk finance (the cumulative value of the insurance policies that can be supported), protecting 4.8m people. In addition to these direct results, FCDO’s support to date has been catalytic in encouraging other donors, Foundations and private finance support into the sector. / The original Theory of Change remains valid for the programme. / A new component (a partnership with the City of London and private sector insurers) is anticipated under this amendment which would update the theory of change by broadening the pre-arranged finance options available and bring in greater private sector skills and expertise. / There are already monitoring and evaluation plans in place for GRIF, and these would be extended to cover the additional programme resources and duration and new City of London partnership.
[note] Start Network cost benefit analysis of Start Ready ,2025.