Business Case

Summary Sheet

Title: Global Risk Financing Facility (GRIF)
Programme Summary: / The Global Risk Financing Facility (GRIF) will help to save lives and reduce the impacts of shocks, like droughts, hurricanes and floods by enabling earlier and more effective response and faster recovery. It provides finance to support governments and humanitarian agencies to use disaster risk financing instruments, like insurance and contingent credit, to access more rapid finance in emergencies, and to strengthen preparedness of local systems for disaster response and recovery. It focuses on disasters but will develop to cover wider risks, including famine. DFID has partnered with the World Bank and German Government to design the GRIF, building upon a pilot facility in the UK-funded Centre for Global Disaster Protection in London. / The UK is a leader in disaster risk financing both domestically and in our international partnerships. Risk financing instruments allow governments and others to “pre-arrange” finance that can be released almost immediately in emergencies based on pre-agreed triggers. This can: / Significantly speed action in emergencies, enabling more timely and predictable crisis response and faster recovery / Strengthen public financial management and smooth the fiscal impact of the shock / Provide financial protection of key assets to ensure continuity and rapid recovery of critical public services and infrastructure, like schools, hospitals and roads. / Together this can reduce the impacts of disasters, cut the costs of response by more than half and safeguard longer-term poverty alleviation and economic development. Such instruments have been shown to work in the Caribbean, Pacific, Mexico and Africa. For example, in the Caribbean countries received $50m from the Caribbean Catastrophe Risk Insurance Facility (CCRIF) following the devastating hurricanes in 2017. / The GRIF will strengthen the options available to countries through testing new approaches and will help to scale-up the use of risk financing instruments and increase their impact. GRIF blends grant finance, World Bank lending and private sector capital to help overcome the barriers to uptake and to ensure finance is embedded within strong, well targeted systems that benefit the most vulnerable people. It provides multi-year packages of support to countries to build financial resilience but also encourage countries to invest in risk reduction and preparedness themselves. The GRIF will also work on bridging the gaps between humanitarian and development financing, including working with humanitarian agencies, particularly in fragile environments, to trial ways of improving predictability of financing for early action and promoting greater preparedness. The long-term ambition for the GRIF is to drive integration of these approaches into the multilateral system as part of a paradigm shift from a reactive to a proactive approach to managing the risks of disasters and other crises. The concept of the GRIF was supported by the G7 Finance and Development Ministers in June 2018. / The Facility complements and works with the UK-funded Centre for Global Disaster Protection in London, which provides technical assistance, analytics, innovation and knowledge. This programme will work with the Centre to provide technical support to implement GRIF projects.
Programme Value: £90m			Country/ Region: Global
Programme Code:	Start Date: January 2019		End Date: December 2025
Overall risk rating:	Moderate
Vault Number:

Intervention Summary

What support will the UK provide?
The UK will provide £90m over seven years.
Why is UK support required?
Disasters are a major impediment to poverty alleviation and economic development in many countries. Globally, 2017 was one of the costliest years on record for natural catastrophes with three major hurricanes striking the Caribbean region and many thousands of people affected by flooding in Asia. For example, in Dominica in 2017, more than 200% of GDP was wiped-out overnight. In 2018, we have seen a major tropical cyclone hit the Philippines and the deaths of thousands of people in Indonesia following two earthquakes in Lombok and Sulawesi. A recent study by the World Bank estimated that disasters force some 26 million people into poverty each year. When disasters strike, the ability of the government to access finance and direct it effectively can be a major constraining factor in response and recovery that increases the scale of the impacts. Having financial strategies and instruments in place ahead of a disaster is an important part of disaster preparedness and can lead to earlier and more reliable response and recovery, saving lives and reducing costs. In many vulnerable countries, systems and capabilities in this area are still relatively weak, increasing risks.
What are the main programme activities?
The Global Risk Financing Facility (GRIF) focusses on strengthening country systems for crisis response and recovery through enhancing preparedness and shock-responsive systems backed by financing arrangements. It was co-designed by the UK, Germany and the World Bank and builds upon an earlier DFID-funded pilot facility. It hosted by the World Bank and focusses on populations at greatest risk, including small-island states. It works mainly with Ministries of Finance, but also other line ministries, to strengthen financial strategies and the use of prearranged risk financing instruments and embed these within national systems. This can include shock-responsive social protection systems and critical public services and assets. DFID funding will be used to co-finance projects alongside World Bank lending, to expand the use of risk financing instruments and create incentives for countries to embed these into national systems and to invest more in preparedness and resilience themselves. The GRIF will also work on bridging the gaps between humanitarian and development financing, including working with humanitarian agencies, particularly in fragile and conflict affected states, to trial ways of improving predictability of financing for early action and promoting greater preparedness. This business case also supports some complementary activities, including through the Centre for Global Disaster Protection.
What are the expected results?
- Strengthened government systems and financial resilience, and more timely, reliable and cost-effective disaster response and faster recovery, with an economic benefit estimated at £580 million, or more than double the benefit of the same scale of investment in ex-post aid, and over 80 million beneficiaries globally.
- Improved options for crisis risk financing instruments and greater knowledge, evidence and learning on their application.
- Greater use of risk financing approaches within the multilateral system as part of a shift from a reactive to proactive approach to managing crisis risks.
Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan (SDP), International Development Act and the department’s Business Plan?
In line with the strategic objectives of the 2015 UK Aid Strategy, the GRIF will strengthen the resilience of countries to disasters and enable more effective response to crises. In doing so it will help protect the poorest and most vulnerable people and unlock sustainable economic development. In line with DFID’s SDP, crisis risk finance will help to deliver finance more quickly during an emergency and support efforts to adapt to climate change.
What percentage of DFID’s SDP results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?
DFID SDP results (to date) do not include quantified economic development or humanitarian indicators related to risk finance or disasters. The programme will contribute to: (1) HMG’s climate finance targets (0.5% of £5.8bn spend target for the current SR period), (2) DFID’s increased climate finance target for FY 2020/21 and beyond, (3) the Africa Strategy climate change work, and (3) the adaptation side of climate change spending balance.
Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?
The GRIF is a multilateral mechanism co-funded with the Government of Germany. The concept was supported by the G7 Finance and Development Ministers in June 2018 and responds to the need for more proactive management of risk and opportunity for greater use of risk finance and insurance identified by the G7 (2015, 2018), G20 (2017), the World Humanitarian Summit, the Global Goals, the Addis Ababa agenda on Development Finance, the Paris Agreement and the Sendai Framework. The programme has a clear exit strategy for DFID in that firstly, it aims to support countries to better manage their own risks and fund through their own fiscal budgets, and secondly, it aims to trial enhanced instruments that can over time be integrated into core multilateral development finance.
Has the programme considered working with HMG Departments/cross-HMG funds?
This programme links to and builds upon an existing £33m Prosperity Fund programme, the Centre for Global Disaster Protection (the Centre). It extends an existing Pilot Facility funded by the Centre. DFID is working x-HMG on this, particularly DIT, HMT and FCO.
How does the programme relate to other UK aid, including multilateral, bilateral and centrally managed programmes? Is there flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
GRIF complements other centrally managed programmes like African Risk Capacity, the Centre, several research programmes (MAINTAINS, SHEAR, etc.) and country-based disaster resilience programmes. The programme is structured to allow flexibility to learn and adapt and shift emphasis and be responsive to opportunities and demand from countries.
Does the proposed level of risk fit with DFID’s risk appetite for the portfolio?
The risk appetite is consistent with other programmes in the portfolio.
Is there a clear communications strategy to reinforce objectives? Will it be branded with the UK aid logo and recognise UK Government funding?
The programme will be branded with the UK aid logo and recognise UK funding in accordance with DFID guidelines and standard branding agreements with the World Bank.
Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
The GRIF has been designed in partnership with the World Bank and the German Government with significant input from HMG/DFID experts, the private sector, and civil society. It builds upon learning from previous DFID and World Bank programmes in disaster risk finance across several countries, including a DFID-funded Pilot Facility. Existing programmes give us high confidence of the capacity, resources and political will to deliver.
Does the SRO/team have the capability and resources to deliver the programme?
The SRO and team have technical expertise and experience in disaster risk financing and manage a portfolio of complementary programmes.

Strategic Case

Context
Disasters, poverty, gender inequality and economic development
1. Disasters are a major impediment to poverty alleviation. Recent work by the World bank estimated that disasters force 26 million people into poverty each year[1]. In recent years up to 100 million people have been affected by events such as earthquakes, cyclones and flooding in developing countries[2] and the poorest people suffer most due to their higher vulnerability and exposure. This can have long-term impacts on their development prospects, including permanent impacts on education and health.
  [1] Hallegatte, S. et al. (2016). Unbreakable: Building the resilience of the Poor in the Face of Natural Disasters. World Bank, Washington D.C.
  [2] IFRC (2015) World Disasters Report. IFRC: Geneva
2. Globally, 2017 was one of the costliest years on record for natural catastrophes with three major hurricanes striking the Caribbean region and many thousands of people affected by flooding in Asia. In 2018, a major tropical cyclone stuck the Philippines and thousands of people were killed in Indonesia following earthquakes. In the future, climate change will further increase the intensity of weather extremes and increases in populations in at-risk areas will place struggling systems under additional pressure.
3. As well as the immediate effects on people, disasters cause a significant fiscal and economic shock to vulnerable countries that can slow response and recovery. Economic losses to disasters are now reaching, on average, more than $60 billion each year[3]. For the poorest countries, these costs can overwhelm the capacity of government to respond. The 2017 hurricanes caused losses of 200% of GDP in Dominica[4]. This can have long-run impacts on development. In Ethiopia, recurrent droughts and flooding over the past decade are estimated to have reduced annual growth by more than one third[5].
  [3] Guha-Sapir, D., Below, R. and, Hoyois, Ph. (n.d). The CRED/OFDA International Disaster Database (available at: www.emdat.be). Université Catholique de Louvain, Brussels. DFID analyses, averages over the period 2000 – 2016.
  [4] Government of the Commonwealth of Dominica (2017) Post-Disaster Needs Assessment Hurricane Maria September 18, 2017. Government of the Commonwealth of Dominica: Roseau.
  [5] Grey, D. and C.W. Sadoff, 2006: “Water for Growth and Development”. In, Thematic Documents of the World Water Forum. Comision National del Agua, Mexico City.
4. Risk reduction and earlier action saves lives, can more than half the costs of response[6] and reduce long-run negative effects on growth and development. For example, evidence from Ethiopia shows that every $1 spent in planning (including ex ante financing based on triggers, preparedness plans, and capable systems) saves $5[7]. If governments are not able to respond quickly and effectively, the immediate losses to lives, livelihoods and assets can have amplified impacts throughout the economy.
  [6] Clarke, D. and Vargas Hill, R. (2013) Cost–benefit analysis of the African Risk Capacity Facility, IFPRI Discussion Paper 01292. Washington DC: IFPRI
  [7] Wiseman, W. and Hess, U., (2007). Reforming Humanitarian Finance in Ethiopia: A Model for Integrated Risk Financing, United Nations World Food Programme Working Paper. WFP: Geneva.
  1. Productivity and economic activity is reduced in the short-term, with knock-on effects on people’s livelihoods, sometimes forcing them to sell their assets and take children out of school, depressing household productivity for years.
  2. Investing in recovery and reconstruction, draws resources away from more productive activities and investment, like education, healthcare, or new infrastructure, creating long-run impacts on development.
  3. Fiscal sustainability is impacted in the long-term. The required increases in spending to rebuild after a disaster can put pressure on public finances. The debt-to-GDP ratio can rise, and sovereign credit ratings can be eroded[8] with knock-on effects for the ability and costs of raising capital.
    [8] Standard’s and Poor’s Rating Services. (2015). Storm Alert: Natural Disasters Can Damage Sovereign Creditworthiness. SPRS, New York.
These impacts can spread throughout the economy, affecting investment, growth, and fiscal accounts[9]. For countries suffering recurrent disasters, the periodic destruction of part of a country’s productive assets acts as an implicit tax on capital and labour, deters investment, and lowers productivity and living standards on a sustained basis[10].
[9] Srinivasan, K., Otker, I., Ramakrishnan, U., and Alleyne, T. (2017). Unleashing Growth and Strengthening Resilience in the Caribbean. IMF, Washington D.C.
[10] Note that similar processes operate at the micro-scale for individual households and businesses.
Disasters disproportionately affect women and children. Not only are women, boys and girls more than fourteen times more likely than men to die during a disaster[11], but their subsequent life expectancy is more affected by a disaster than men’s[12]. As men tend to hold title to lands and larger assets, losses associated with female livelihoods (e.g. kitchen utensils, sewing machines) are often not counted, protected or replaced, strengthening dependence on men[13]. Women and girls often experience a ‘double disaster’ as the impacts increase levels of domestic violence, childhood marriage, and reduces the numbers of girls in education[14].
[11] UNDP Bureau for Crisis Prevention and Recovery, ‘Gender and Disasters’, 2010, page 2: http://www.undp.org/content/dam/undp/library/crisis%20prevention/disaster/7Disaster%20Risk%20Reduction%20-%20Gender.pdf
[12] Neumayer, E., & Plümper, T. (2007). The Gendered Nature of Natural Disasters: The Impact of Catastrophic Events on the Gender Gap in Life Expectancy, 1981–2002. Annals of the Association of American Geographers, 97 (3), 551–566
[13] Bradshaw, S and Fordham, M (2013) Women, girls and disaster: A review for DFID. DFID: London.
[14] Bradshaw, S and Fordham, M (2013) Women, girls and disaster: A review for DFID. DFID: London.
Rationale for Risk Financing
The ability of governments to access finance reliably, cost-effectively and at the right time can be a critical factor in determining both the short-term and long-term impacts of disasters and other shocks. Table 1 presents an overview of the range of fiscal tools used to finance response, recovery, and reconstruction after a disaster. These each have different characteristic costs, reliabilities and disbursement times.

Table 1: Fiscal tools used during emergencies. Source: World Bank, 2017 [15]
[15] World Bank (2017) Sovereign and Climate Disaster Risk Pooling: World Bank Technical Contribution to G20. World Bank: Washington DC.

1. For the poorest and most vulnerable countries, access to finance in emergencies is often less-reliable, more expensive and slower and this can amplify the impacts of the disaster. Developing countries rarely hold adequate contingency budgets and raising finance on international markets is expensive and takes time. Budget reallocations take time and can have high opportunity costs, diverting resources away from other development projects. Crisis finance can be accessed in the form of emergency loans/grants from multilateral development banks (MDBs) or others but this can take 3 – 6 months. These delays can amplify impacts.
2. To fill financing gaps, countries may seek humanitarian aid, but funding this can be slow, unreliable, and creates the wrong incentives. On average, natural disasters and pandemics account for around 13% of international humanitarian aid, or $1.5 billion per year, often spiking to over $4 billion per year[16]. Humanitarian aid is vital and helps millions of people each year, but can come too little, too late – around 1 to 6 months after the event. In a particularly tragic example, in 2011 international aid to Somalia came several months after forecasts predicted a major food security crisis, leaving millions without food. In addition, the current (as at 11 October 2018) humanitarian funding gap stands at US$14 billion meaning 57% of immediate humanitarian needs have no funding[17]. This gap is growing.
  [16] DFID in-house analyses based on UNOCHA Financial Tracking Service data
[17] # UNOCHA (2018) Global Humanitarian Overview. UN: Geneva (accessed at https://interactive.unocha.org/publication/globalhumanitarianoverview/ on 11 October 2018)
3. There is evidence that an overreliance on ex-post finance and aid can lead to an underinvestment in disaster prevention and risk reduction[18]. Globally, there is still a major imbalance between spend on disaster risk management versus humanitarian response, with disaster risk reduction funding only 12.7% of total aid related to disasters[19]. Reliance on ex-post finance, creates unpredictability and reduces incentives for all stakeholders to invest in preparedness. In a world where risk and needs are increasing, a reactive approach to financing disasters will fail.
  [18] Clarke, D. and Dercon, S. (2016). Dull Disasters? How Planning Ahead Will Make a Difference. New York: OUP
  [19] Kellett and Caravani 2013 “Financing Disaster Risk Reduction: A 20 year story of international aid”.
4. Approaches to disaster financing need to change. Ideally, funding will be:
  1. Timely. Delays to immediate funds cost lives but can also mean greater impacts and more expensive response and recovery. Earlier action can halve the costs of response[20]. However, not all funding is needed at once (see Figure 1).
    [20] Clarke, D. and Vargas Hill, R. (2013) Cost–benefit analysis of the African Risk Capacity Facility, IFPRI Discussion Paper 01292. Washington DC: IFPRI
  2. Predictable and reliable. With predictable and reliable finance, preparedness and response plans can be put in place, increasing the effectiveness of response.
  3. Best value for money. Fiscal budgets are severely restricted in the poorest countries. The costs of finance include the actual cost (e.g. fees or interest rates which are generally high for developing countries) but also the opportunity costs.
Pre-arranged disaster risk financing approaches deliver these requirements.

Figure 1: Timing of disaster financing needs. Source: Ranger & Signer 2018[21]
[21] Ranger, N. and Signer, B. (2018) Even duller disasters. How earlier finance can save lives in emergencies. Voices: perspectives on development. https://blogs.worldbank.org/voices/node/5556/
1. In the last decade, there has been increasing use of ex-ante financial instruments, like insurance and contingent credit, by governments to provide timely, predictable and cost-effective liquidity in emergencies. These instruments allow governments and others to pre-arrange finance for crises with multilateral development banks, the private sector (e.g. insurance) or others. Examples include:
  1. Sovereign risk transfer, including insurance, derivatives, or catastrophe bonds. Around 25 developing country governments currently use some form of sovereign risk transfer solution to help manage the potential fiscal impacts of disasters. This includes regional risk insurance pools like the Caribbean Catastrophe Risk Insurance Facility (CCRIF), for which the UK was a leading donor at its foundation. CCRIF was set up in 2007 to provide much needed immediate liquidity after a disaster based on objective triggers (e.g. a hurricane wind speed). Since then it has provided insurance to 18 Caribbean countries with pay-outs totalling over $100m[22]. This includes over $50m paid out to countries affected by Hurricanes Irma and Maria in 2017. Used as a tool to reduce the immediate fiscal shock on government budgets, it delivers a relatively small amount of finance (compared to total losses) very quickly (within 14 days). It delivered nearly $8m to Haiti following the devastating earthquake in 2010 within 19 hours of the event[23].
    [22] GFDRR CCRIF note (2011) and more recent data from http://www.ccrif.org/content/about-us
    [23] Payout for Perils Working Group (2017). Payouts for Perils: How Insurance Can Radically Improve Emergency Aid. Center for Global Development: Washington DC.
  2. Contingent credit. This is a pre-arranged loan that is released based on a trigger. Examples include the World Bank’s catastrophe deferred draw-down option (Cat DDO) and equivalents offered by the Japanese International Cooperation Agency (JICA) and the InterAmerican Development Bank. These have ‘soft’ triggers, usually triggered by the declaration of a national emergency, and typically release around $100m – $250m within days. Contingent credit could also have a hard trigger, like a measured rainfall deficit.
  3. Public assets insurance, which provides vital reconstruction finance for public assets, like schools, roads, and hospitals. This is typically more traditional indemnity-based insurance.
2. A comprehensive risk financing strategy will use a combination of instruments (both ex-ante and ex-post instruments) that deliver finance when needed, for different scale shocks, and in a way that is most cost-effective. This is known as ‘risk layering’. The range of instruments covering the spectrum of needs are presented in Figure 2.
3. A growing body of evidence shows that if used effectively, pre-arranged disaster risk financing can significantly reduce the short-term and long-term impacts of disasters on people and the economy, through providing much needed immediate liquidity post disaster, reducing the fiscal impact of disasters and enabling more rapid, reliable and cost-effective response and recovery. Research by the IMF[24] and Standard & Poor’s[25] shows that a country’s fiscal risk management strategies for disasters, including use of insurance and other contingent financing, is a crucial determinant of the impact of disasters on fiscal sustainability and sovereign credit ratings. Disaster risk financing also has wider benefits for the economic resilience. In Mexico, evidence shows that the sovereign risk transfer system, FONDEN, has significant benefits; increasing the local gross domestic product post-disaster by 2 – 4 percent, with a benefit-cost ratio estimated conservatively between 1.52 and 2.89[26].
  [24] Srinivasan, K., Otker, I., Ramakrishnan, U. and Alleyne, T., (2017). Fiscal Challenges in the Caribbean: Coping with Natural Disasters. In ‘Unleashing Growth and Strengthening Resilience in the Caribbean’. IMF: Washington DC
  [25] Standard & Poor’s Rating Services, (2015). Storm Alert: Natural Disasters Can Damage Sovereign Creditworthiness. Standard & Poor's Financial Services: London.
  [26] de Janvry, Alain; del Valle, Alejandro; Sadoulet, Elisabeth. 2016. Insuring Growth : The Impact of Disaster Funds on Economic Reconstruction in Mexico. Policy Research Working Paper; No. 7714. World Bank, Washington, DC.
4. This programme focusses on scaling-up the use and ensuring the effectiveness of pre-arranged (ex-ante) financing for disasters. The uptake and use of these instruments is still generally low. For example, today around 25 developing countries are using some form of sovereign risk financing instrument (a large proportion being small island states in the Caribbean and Pacific), but the amount of losses covered (compared to the expected loss) is low.

Figure 2: Range of sovereign disaster risk financing tools. A financial risk management strategy can draw upon multiple tools to achieve risk layering across the range of hazard frequency and timing of financing needs. Source: World Bank, 2017 [27].
[27] World Bank (2017) Sovereign and Climate Disaster Risk Pooling: World Bank Technical Contribution to G20. World Bank: Washington DC.
Beyond finance – integration into systems
1. Risk finance by itself is not a silver bullet. To ensure it reduces the impacts of disasters, risk finance needs to be part of a broader set of activities to strengthen preparedness, build systems, and develop capabilities[28]. An example from the Caribbean in 2017 demonstrates this; when reconstruction finance arrived, countries lacked the plans, systems and human capacity to use it, delaying the recovery process. This was also a key lesson learnt from the Pacific Catastrophe Risk Assessment and Financing Initiative (PCRAFI) pilot[29].
  [28] MCII (2016). Making climate risk insurance work for the most vulnerable: seven guiding principles. MCII: Munich.
  [29] World Bank (2016), Implementation completion and results report for the Pacific Catastrophe Risk Insurance Pilot Program. World Bank: Washington DC.
2. Clarke and Dercon (2016)[30] lay out three pillars to strengthen disaster responses:
  [30] Clarke, D and Dercon, S. (2016). Dull Disasters? How Planning Ahead Will Make a Difference. OUP: New York.
  1. Pre-disaster planning, systems and capability – having credible plans in place before a disaster strikes as well as capabilities and systems to deliver in emergencies, including ‘shock-responsive’ systems and services.
  2. Pre-agreed triggers – having a pre-agreed decision-making process in place that can trigger action, including objective data-driven triggers.
  3. Pre-arranged finance – having finance on stand-by to ensure that funds are quickly available to put plans into action when a disaster strikes.
3. All three pillars are needed. For example, the Productive Safety Net Programme (PSNP) in Ethiopia is able to scale up rapidly to help around 10 million people during a drought, delivering vital food, cash and other assistance to people, however it is not fully pre-financed, so in large emergencies it has been partly funded by donors ex-post, creating some unpredictability, underfunding, and delays.
4. There has been substantial innovation and progress in this area over the past 10 years and systems are already demonstrating results. There are examples where the three pillars have been established prior to a crisis:
  1. In Mexico, FONDEN links more than a decade of investments in data, pre-agreed plans and decision-making processes to financial instruments to protect key public assets. The Mexican Government received a $150m pay-out from a catastrophe bond to support reconstruction after the earthquake in 2017.
  2. The African Risk Capacity (ARC) regional risk insurance pool, of which the UK has been a key donor since its inception, requires and assists countries to develop contingency plans to help ensure pay-outs are used effectively to deliver aid to those who most need it. Senegal, Niger and Mauritania received pay-outs from ARC totalling $26.5m after poor rains in late 2014. These were received several months before any other aid, funding cash transfers, food and fodder that benefitted 1.3 million people.
  3. The Disaster Emergency Response Facility (DREF) of the International Federation of the Red Cross (IFRC) recently launched a ‘forecast-based action’ window; a contingent finance window where finance is released to local Red Cross branches based on pre-agreed automatic triggers (a forecast) to action pre-determined contingency plans.
5. As such, this programme is focussed not only on finance, but also on ensuring that finance is linked to preparedness planning and embedded within strong local and national systems for disaster response and recovery.
6. The importance of risk finance and insurance in parallel with effective plans and capabilities is now widely recognised in global policy, including in the G7, G20 and V20 dialogues, the Sendai Framework on Disaster Risk Reduction (2015), the G7 InsuResilience initiative and the UN Framework Convention on Climate Change, the Addis Ababa Action Agenda on Finance for Development in July 2015 and the UN Secretary General’s High-Level Panel report on Humanitarian Financing[31].
  [31] UNOCHA, (2016). High-Level Panel on Humanitarian Financing Report to the Secretary-General: Too important to fail—addressing the humanitarian financing gap. UNOCHA: Geneva.

Summary: / When a disaster strikes, the ability of the government to access finance and direct it effectively is a critical factor in determining the impacts on affected people and the knock-on effects for long-term development. Countries predominantly rely on ‘ex-post’ financing, including humanitarian aid and lending. This can be slow, poorly coordinated and poor value for money. This model of disaster financing also creates poor incentives for investment in disaster preparedness, resilience and shock-responsive systems. The net result is higher risk and delays in assistance reaching affected people and slower recovery, leading higher costs and lost lives. ‘Ex-ante’ risk financing tools like insurance enable governments to access rapid finance in emergencies and if coupled with investments in preparedness and shock-responsive systems, can speed response and recovery, saving lives and cutting the costs of disasters. These ex-ante instruments are agreed on the global stage to be key to overcoming the ever-growing humanitarian need from disasters. They are increasingly used by governments but to be effective they need to be well integrated within capable national disaster risk management systems.

Rationale for the Global Risk Financing Facility (GRIF)
1. The proportion of disaster losses covered by risk financing and insurance instruments is low, and preparedness for disasters is weak. If such instruments covered a larger fraction of disaster losses, this could help to shift from a reactive to a proactive approach to crisis risk management and create incentives for preparedness. This shift would lead to faster, more reliable and more cost-effective response and recovery, thereby reducing the impacts of disasters. Over time, dependence on slower, less reliable and less cost-effective ex-post disaster financing would decline.
2. The barriers to uptake are mainly issues of demand not supply[32]:
  [32] Barriers are present for governments as well as at other scales such as sectoral specific infrastructure, such as energy or water.
  1. Awareness and capacity: Low awareness of risk and insurance and lack of institutional capacity to analyse risks and instruments/products, carry out transactions and link to local systems. Lack of trust in financial products and insurance can also be an issue. Lack of data and models to assess risks.
  2. Upfront and opportunity costs: for example, it can be difficult for a government to justify an annual budget allocation for an insurance policy for an event which may or may not happen, when under pressure to spend its limited resource in other more immediately concerning areas. There are also opportunity costs in setting aside an annual contingency budget or reserve, or setting aside part of a country IDA/IBRD lending envelope for a contingent credit instrument that may or may not be required.
  3. Political and behavioural incentives: there are well known behavioural drivers that tend to prevent people from investing up front in reducing the risks of rare, uncertain events even when it is shown to be economically rational to do so[33]. The political economy of disasters can worsen this – the political gains to waiting for a disaster then responding, can be larger than those in investing upfront in reducing risks[34]. Also, if donors are willing to pay for post-disaster relief but are unwilling to part-pay for ex-ante instruments that finances relief, then governments may prefer to rely on post-disaster relief. There are also issues around lack of clarity on who owns the risk and is responsible for it.
    [33] Clarke, D and Dercon, S., (2016). Dull Disasters? How Planning Ahead Will Make a Difference. OUP: New York.
    [34] Clarke, D and Dercon, S., (2016). Dull Disasters? How Planning Ahead Will Make a Difference. OUP: New York.
  4. Trust and risk appetite: It is risky for a government to try new approaches, particularly where there are upfront costs, and this can be a barrier.
3. Various initiatives exist to increase awareness and capacity. The majority of donor and multilateral risk finance initiatives to date have been on providing technical assistance and establishing and financing risk transfer initiatives like the Caribbean Catastrophe Risk Insurance Facility (CCRIF) and African Risk Capacity (ARC). The World Bank (particularly the Disaster Risk Financing and Insurance Programme (DRFIP) and the Global Facility for Disaster Reduction and Recovery (GFDRR)) has been a driving force in this area since the start, and is still dominant, generating most of the pipeline of projects with governments and building three out of the four regional risk insurance pools (the fourth, ARC is an African-led initiative linked to the African Union and hosted by the World Food Programme). The UK has been a major funder of all these initiatives and has played an important role in shaping this space. Recently other regional development banks have become more active. Humanitarian agencies (particularly WFP and FAO), NGOs and the IFRC are also now active though at fairly small scale.
4. The Centre for Global Disaster Protection was established by the UK, in partnership with the World Bank, in 2017 as a hub of expertise to increase awareness and capacity, catalyse innovation and to provide impartial advice to help scale-up the use of risk financing and to maximise its impact. The UK and the World Bank aimed to build a centre of technical expertise to support this growing area and to tackle the barriers around awareness and capacity highlighted above. It provides technical assistance (TA), risk data, evidence and analytics to support governments and humanitarian agencies to use financial instruments and integrate them into their national systems with the goal of strengthening financial resilience and supporting governments to deliver earlier and more cost-effective response in emergencies
5. No initiatives to-date systematically tackle the two remaining barriers to scaling the use of risk financing instruments: the upfront/opportunity costs and the political economy issues. To help address these barriers, research by the World Bank, the Government Actuary’s Department, the independent ARC evaluation[35], the Insurance Development Forum and others suggest that donors should consider providing a time-limited subsidy to reduce the upfront costs of risk financing instruments, enabling countries to test the instrument and build discipline around paying for disasters within national budgets. Research by the IMF concluded that the international community should reward preparation and risk reduction actions through reducing insurance premiums. Global insurers[36] as well as international public-private organisations like the Insurance Development Forum and NGOs have similarly called for increased investment in data, technical assistance and insurance premium financing.
  [35] https://www.opml.co.uk/projects/independent-evaluation-african-risk-capacity
  [36] For example, Inga Beale (CEO Lloyds of London) et al. (paper prepared in advance of Ministerial roundtable, July 2016)
6. Given the development and humanitarian benefits of well-designed risk finance, there is a strong case for co-financing (i.e. part-paying premiums or contingent credit) with those countries with willing and able governments to help them transition from a reliance on ex-post financing (e.g. humanitarian assistance) towards a more reliable, earlier government-led response that saves lives and cuts costs:
  1. Premium financing or subsidised contingent credit instruments reduce the upfront cost and opportunity costs of risk financing instruments, placing them on a more comparable footing with ‘free’ humanitarian aid and other concessional finance. For example, in 2016 ARC had ten countries ready to purchase insurance but the majority were unable to afford the premiums. Countries potentially missed out on payouts which could have been channelled to faster disaster response. This inability to overcome the upfront and opportunity costs has impacted on uptake and limited coverage of risk financing instruments, for example, in the Caribbean many countries have CCRIF coverage that only partially covers their disaster risks, and the same is true for PCRAFI coverage of island states in the Pacific.
  2. Well-designed financing builds trust in these new instruments and enables countries to have more ownership of their risks, as well as promoting risk management.
  3. Evidence shows that premium financing is currently the most cost-effective way to reduce the cost of insurance for many developing countries[37]. For example, donors paying part of the premiums for African countries would be around 20% more cost-effective in reducing the price of insurance than additional ARC capital injections[38].
    [37] Vivid economics; Surminski Consulting; Callund Consulting (2016). Final report: Understanding the role of publicly funded premium subsidies in disaster risk insurance in developing countries. Evidence on Demand, UK
    [38] Analysis by the Government Actuary’s Department
  4. Using premium financing (or equivalents for other instruments) will in turn drive direct investment from the private sector in new products, data analytics and risk modelling, which coupled with their vast knowledge and expertise in risk financing will result in efficiencies and improved value for money for countries.
7. Premium financing is already used in insurance schemes for developing countries, particularly in the early stages but it is ad-hoc. For example:
1. For Haiti’s membership of the CCRIF, their premium has either been paid by an IDA grant, directly by Canada, or through the Caribbean Development Bank. In 2018, the Government of Haiti, one of the world’s poorest and most vulnerable nations, announced that, for the first time, it was to pay for around 36% of their premium[39].
  [39] http://www.caribank.org/news/cdb-to-help-pay-haitis-2018-2019-catastrophe-insurance-premiums
2. The Canadian government paid the CCRIF insurance premium for Dominica in 2018 and 2019, following the devastating hurricane damage to the country in 2017.
3. The Japanese government paid the full premiums for 5 countries for the initial years of the Pacific Catastrophe Risk Assessment and Financing Initiative (PCRAFI), decreasing the amount of subsidy over two years. Since 2015, countries use a combination of IDA and national budgets to pay their premium.
4. The African Development Bank has recently developed an initiative to subsidise premiums through the Africa Disaster Risk Financing (ADRiFi) programme[40].
  [40] AfDB (2018) Multinational-Africa Disaster Risks Financing (ADRiFi) Programme Document
1. Learning from this experience has pointed toward the need for a more coherent approach to providing financial support to vulnerable countries[41] and a robust set of principles. A coherent approach is needed to promote best practice and incentives for preparedness, create greater certainty for governments, and allow donor coherence. Consultations show that the current lack of certainty for developing countries and private sector partners halts the progress in building better risk financing strategies and stalls private sector investments in data and innovation that will reduce the costs of insurance.
  [41] For example, World Bank (2017) and Clarke et al. 2016.
2. There are also lessons to be learned from these experiences on the phasing out of premium finance. If well planned for in fiscal budgets, the reduction of donor premium subsidy over time is achievable sustainably. The GRIF principles (Annex C) ensures that projects have a plan for the phasing-out of donor subsidy and clear government ownership to ensure the sustainability of GRIF projects in the medium to longer term.
3. In 2017, the UK established a Pilot Premium Financing Facility through the Centre for Global Disaster Protection, to drive progress in this area and bring other partners on board with a more scaled-up and coherent approach. This was the first attempt to establish a facility with a coherent, principles-based approach to help the poorest and most vulnerable countries to access sovereign insurance through part-paying premiums for a limited time and create incentives for countries to invest more in preparedness and resilience[42]. The Centre’s pilot facility drove learning and innovation (Box 1) and encouraged other donors to join. Germany initially allocated €25m to work with the UK and the World Bank to implement the pilot financing facility and have since committed an additional €90m toward a scale-up. The pilot led to projects in Kenya and Mozambique that will help cut the costs of disasters for hundreds of thousands of people.
  [42] World Bank (2017) Sovereign Catastrophe Risk Pools: A brief for policy makers. World Bank: Washington DC.
Box 1: Lessons from the Pilot Premium Financing Facility / In its first year, the pilot facility has commissioned analyses[43] and scoped six proposals for part-financing of insurance premiums, two of which are already moving forwards into implementation. While the pilot facility has been running for only a year, the consultations with countries and analyses have generated significant learning. Early learning outcomes include: / Development of a set of twelve principles to guide the allocation and appraisal of projects to ensure quality, impact and value for money for the client country and donors[44]. / Better understanding potential project risks and development of risk mitigation approaches. / Process mapping around operational application of these principles within a typical project cycle and appropriate governance and independent review to manage risks / Modalities of donor financing, including subsidy design and co-financing rules, to ensure sustainability, incentives for resilience and a clear exit strategy for donor. / Understanding country demand and early pipeline. / These lessons are now captured and operationalised within the GRIF Operations Manual, which is attached at Annex A.
[43] World Bank (2018) Concessional Finance for DRFI
[44] See Clarke and Ranger 2018.

Based on learning from the pilot, and in consultation with a wide range of stakeholders, the UK co-designed the Global Risk Financing Facility with Germany and the World Bank. The facility is designed not just to scale-up the use of risk financing, building on and complementing the Centre’s work, but also to build a critical mass of support that can develop and promote global standards and best practice and catalyse increased investment in preparedness and resilience. The concept of the GRIF was supported by Finance and Development Ministers at the G7 Summit in 2018[45] and launched at the World Bank/IMF Annual Meeting in 2018. At that time, DFID committed its remaining financing from the pilot facility to the GRIF. Other donors have shown interest to join. This document presents the business case for scaling up DFID financing to the Global Risk Financing Facility and appraises the options for how this finance is delivered.
[45] G7 (2018) Co-chairs’ summary: G7 joint development and finance ministers in Charlevoix, Canada. Available at: https://g7.gc.ca/en/g7-presidency/themes/investing-growth-works-everyone/g7-ministerial-meeting/co-chairs-summary-g7-joint-development-finance-ministers-meeting/

Why should DFID act?
UK comparative advantage
1. The UK is a leader on disaster risk financing agenda. The ambition to scale up the use of ex-ante risk financing instruments and shift toward a more proactive and anticipatory risk management model, is a core part of the UK’s Humanitarian Reform Policy 2017. The implementation of the Global Risk Financing Facility through the World Bank is also consistent with DFIDs push as a shareholder of the World Bank to expand its suite of ex-ante crisis financing instruments, take a risk-based approach to supporting countries to better manage risks and to find ways to leverage its balance sheet for the benefit of developing countries. GRIF is also well aligned with UK and World Bank strategy on Maximising Finance for Development, as embodied in the DFID Economic Development Strategy 2017.
2. The UK has comparative advantages in this area. DFID is recognised globally for our technical strength and experience on risk financing, disaster preparedness and shock-responsive systems, and the UK more widely is regarded as a centre of expertise across its public, private and third sectors. DFID has financed all three of the existing regional risk insurance pools and is now involved in establishing the fourth pool in South Asia. We have been founding donors in shock-responsive social protection systems, including in Kenya, Uganda and Ethiopia. This gives DFID the unique ability to connect our work on risk financing with our bilateral investments in shock-responsive social protection, as well as in disaster risk management and resilient infrastructure, to ensure risk financing is embedded in national systems. An example is our work in Kenya, where we have worked with the World Bank and the Government of Kenya to combine DFID bilateral grants and multilateral lending, with technical assistance, to enhance the Hunger Safety Net Programme (HSNP) and embed risk financing. We can also link the GRIF to DFID’s existing technical programmes like the Centre, BRACED (Building Resilience and Adaptation to Climate Extremes and Disasters), MAINTAINS (Maintaining Essential Services after Natural Disasters) and SHEAR (Science for Humanitarian Emergencies and Resilience) so the portfolio delivers impacts greater than the sum of its parts.
3. DFID has been a world leader in the global crisis risk financing agenda, including the 2019 Prime Minister’s Resilience Champion role at the UN Climate Summit. DFID’s initial seed funding of the pilot, and substantial role in the design of GRIF, has ensured it is well aligned to UK ambitions on humanitarian reform and the role of the World Bank in crises, and reflects DFID’s approaches to innovation and learning, and our strong focus on maximising short-term benefits for the most vulnerable people and a longer-term contribution to resilient economic development and poverty alleviation.
4. UK funding will strengthen the GRIF’s impact in both financial and political terms, creating more global coherence, best practice and standards, increasing the impacts of crises risk financing. Without DFID playing a strong continued role, the strategic direction would likely move away from and introduce risks to UK leadership and objectives in this area[46]. DFID brings a strong focus on strengthening preparedness and risk reduction, ensuring there are well-defined exit strategies, working with governments to increase national system capacities, and delivering sustainable change.
  [46] Poor use of premium financing, for example to finance low quality insurance products, could erode trust and undermine progress on shifting to an ex-ante approach, as well as crowd-out investment in preparedness and resilience

Box 2: Risk Financing and Kenya Hunger Safety Net Programme / DFID has worked with the Government of Kenya for almost a decade to establish the Hunger Safety Net Programme, which provides regular cash transfers to 100,000 households in four of the most drought-affected counties in Kenya, with the ability to scale to an additional 300,000 households in the event of severe drought. The third phase of HSNP (now beginning) led by the Government of Kenya, combines World Bank lending and DFID Kenya financing, to fully finance the existing HSNP households, including under the shock-responsive component of HSNP, and to expand the HSNP into four additional drought-affected counties. With technical support of the World Bank and the Centre for Global Disaster Protection, this third phase will include, for the first time, a risk financing component, allowing the scalability of HSNP to be fully-financed by the Government, ensuring greater cost-efficiency and reliability of funding in droughts. The financing (the Kenya Social and Economic Inclusion Project) was approved by the Board of the World Bank in December 2018 and is moving into implementation.

Box 3: Risk Financing in the Caribbean following the 2017 Hurricane Season / Following the devastation of the 2017 Hurricane Season, the UK pledged support to help build the financial resilience of the Caribbean region and strengthen preparedness through the World Bank London hub of the Centre for Global Disaster Protection. As a result, two countries are already exploring new financial instruments and the World Bank is in the process of preparing projects for the new Global Risk Financing Facility.

Why can’t multi-lateral development banks (MDBs) like the World Bank already do this? Why is donor funding needed to establish the GRIF?
1. Countries could already use their IDA or IBRD (or equivalent) lending envelopes to pay for risk financing instruments at concessional rates. The missing pieces (additionality) that donor grant finance within the GRIF provides are:
  1. Strengthening economic and political incentives for countries to strengthen fiscal risk management, use ex-ante instruments, reduce reliance on humanitarian aid and invest more in disaster management systems, plans and capability. The GRIF will use donor finance combined with MDB lending instruments (IDA/IBRD) to level the playing field (e.g. versus humanitarian assistance) and strengthen the incentives for governments to invest. Trust fund concessional finance is justified to help correct the under-valuation of disaster risk financing by governments, collaboration and influence on this specific issue, and efficiency[47].An analogous example is the Global Concessional Financing Facility, which used donor grants to allow middle income countries access to more concessional lending from the WB/IBRD to support refugees. In that case, donor grant finance was justified through the long-term benefits to vulnerable refugee populations, which in turn has benefits for the region through reducing the economic and social impacts of large refugee flows on surrounding countries. In this case, there is similarly a long-term benefit to people in the beneficiary countries through reducing the impacts of natural disasters, but also the global benefit of reducing strain on the international humanitarian system.
    [47] See IFID concessionality paper, November 2018
  2. Space to innovate and learn. As a donor-funded initiative, the GRIF will have more scope to work with governments to develop and test new approaches in a faster, more responsive, more agile and lower-risk way than could be achieved otherwise, e.g. through adjusting core MDB products. It will have the flexibility to build upon and enhance MDB instruments and invest in monitoring and evaluation to ensure rapid feedback loops and comprehensive learning. GRIF will also help overcome the barriers for governments to innovate, through taking some of the risk by reducing upfront costs.
  3. Incentivise preparedness, risk reduction and resilience building. The World Bank’s “Maximising Climate Finance for Climate Action 2018” strategy lays out how grant finance can provide incentives for countries to invest in preparedness and resilience activities that they would not otherwise prioritise through their allocations. The GRIF can implement this through financing of preparedness activities, by placing conditions on access to finance for premiums.
  4. A principles-based approach, coherence and shared global standards. As this area grows, we are beginning to see greater fragmentation and differing levels of quality of implementation. The GRIF provides a vehicle to improve coherence and standards, both through bringing together bilateral agencies as co-funders, or through creating a critical mass of finance and political strength.
  5. Investment in global public goods, like crisis risk data. Better information can have huge advantages for government decision making but is often difficult for countries and multi-laterals to justify investment using core funds. It also has huge advantages for countries who can use crisis risk data to manage risk. DFID funding also ensures products are open and have national and global benefits.
Fit with the UK Aid Strategy and DFID Single Departmental Plan
The GRIF contributes to the UK Aid Strategy 2015 objective on Strengthening Response and Resilience to Crises, and the UK Humanitarian Reform Policy 2017:
    1. Strengthening preparedness and financial resilience of DFID/UK priority countries to disasters and other shocks, and thereby reducing their economic and humanitarian costs.
    2. Responding faster and more effectively to humanitarian crises related to disasters by strengthening the use of ex-ante crisis risk financing instruments and using transparent, planned delivery systems to ensure that the poorest and most vulnerable are protected.
    3. Helping to reduce the reliance on humanitarian aid for disasters, by empowering countries that are ready to do so to take more ownership over their risks and create incentives for investing in preparedness and resilience.
    4. Building resilience and helping to manage the risks of climate change, by promoting stronger disaster risk management and the links to adaptation.
1. It will also contribute to the UK Aid Strategy’s third objective on Promoting Global Prosperity and the DFID Economic Development Strategy 2017, through promoting economic development and leveraging the global private sector.
2. Finally, it will contribute towards meeting our international commitments, including contributing to the Grand Bargain commitments, the Sendai Framework and several of the Sustainable Development Goals. For example, building the resilience of the poor and those in vulnerable situations (Sustainable Development Goal SDG1), building resilience of agricultural systems (SDG2), infrastructure (SDG9) and cities (SDG 11), as well as the Sendai targets and commitments on climate adaptation as part of the Paris Agreement. It will make a significant contribution toward the G7 InsuResilience target, of an additional 400 million people with access to climate insurance by 2020.
3. For the UK as a major global centre for finance and insurance, investment in the GRIF has natural win-wins (secondary benefits). The UK is the largest global hub for insurance in Europe and the third largest globally after the US and Japan. The London insurance market is the largest global hub for commercial and speciality risk. The GRIF will deliver both direct and indirect secondary benefits for UK and global prosperity. With direct benefits through both the increased demand for insurance and related professional services (e.g. risk modelling, actuarial advice, brokerage etc) generated directly by the programme, and the indirect benefits from greater awareness of risk and insurance, leading to broader increases in demand and strengthening of global insurance markets.
Compliance with Relevant Legislation
Gender Equality: International Development Act 2014
Women are disproportionately affected by natural disasters and as such are key target beneficiaries of this programme. Due to their higher vulnerability, women and children can benefit disproportionately from programmes that build resilience and reduce the social and economic impacts of disasters. Gender equality and inclusivity more broadly (including other more vulnerable groups such as those with a disability) will be a central consideration of the GRIF. The work that this programme does will actively focus on gender and inclusivity issues, to maximise benefits for women and girls and other more vulnerable groups. For example, this includes the incentivisation of preparedness plans that explicitly consider gender and inclusivity, and the strengthening of national systems that increase the benefits to women, girls and the marginalised. A gender action plan developed by experts will requested from implementing partners within a year. For more details on the way the GRIF will promote gender equality see Annex B.
Countering the Financing of Terrorism
1. This programme (like all other interventions) must comply with relevant legislation, including the Terrorism Acts 2000 & 2006, Proceeds of Crime Act 2002 (Part 7) Money Laundering Regulations 2007, Terrorist (Asset Freezing etc.) Act 2010, the Bribery Act 2010, and the Al-Qaida (Asset Freezing) Regulations 2011. This will require DFID, and its delivery partners, to: (a) identify our partners (including robust due diligence) and ensure they are aware of their responsibilities in relation to the legislation; (b) keep appropriate records; (c) establish internal procedures and controls to mitigate risks; (d) prepare guidance and training sessions to increase staff awareness; and (e) report any contra indicators to the relevant authorities.
2. While the GRIF may work with some Fragile and Conflict Affected States (FCAS), the risk of funds being misappropriated for terrorist purposes is assessed to be very low given the nature of the programme. The programme has the opportunity to work with recipient countries and domestic companies to strengthen regulatory frameworks, which will boost transparency and operational capacity. At the same time, the programme must be alive to potential unintended consequences of more robust enforcement, which can create a compliance burden so great that it deters financial institutions from serving vulnerable populations. A risk-based approach will be key. The GRIF may disburse funding through World Bank Trust Funds. The World Bank along with the IMF and UN have, over the last 20 years, been world leaders in developing approaches, tools and reducing the risk of financing ending up in the wrong hands through their Anti-Money Laundering and Combating the Funding of Terrorists programmes[48].
  [48] World Bank. 2009. Combating Money Laundering and the Financing of Terrorism - A Comprehensive Training Guide : Workbook 7. Investigating Money Laundering and Terrorist Financing. World Bank.
Impacts and Outcomes we expect to achieve
Over the next seven years, UK funding of the GRIF will achieve the following impact:
Reduced human and economic impacts of crises, contributing to more stable and resilient economic development and poverty alleviation. Around 80 million people could benefit from increased resilience to climate, disasters and other shocks.
This is achieved through the following four specific outcomes:
  1. Strengthened financial resilience to disasters, including increased use of crisis risk financing instruments. At least 15 governments will have enhanced strategies and capabilities in place for mitigating the fiscal impacts of disasters, including making strategic use of crisis risk financing instruments. The economic and social benefits of DFIDs investment could total around £580 million.
  1. More timely, reliable and cost-effective disaster response and faster reconstruction and recovery of key public services and infrastructure. Earlier action could save lives and more than halve the costs of disaster response and recovery[[1]]. We expect to see a greater proportion of disaster finance flowing through pre-arranged systems with clear plans and decision processes in place ahead of a disaster, including in at least two fragile states. Risk finance would be clearly integrated within broader risk management systems, including:
    [[1]] de Janvry, et al. 2016. Insuring Growth: The Impact of Disaster Funds on Economic Reconstruction in Mexico. Working Paper;No. 7714. World Bank, and Clarke, Daniel et al. 2016. A Methodology to Assess Indicative Costs of Risk Financing Strategies for Scaling Up Ethiopia's Productive Safety Net Programme. Working Paper;No. 7719. World Bank
    1. Shock-responsive systems and public services, including social protection.
    1. Risk finance linked to clear preparedness plans in advance of event
    1. Greater proportion of public assets protected by insurance
  1. Catalysed investment in preparedness, disaster risk reduction and building national systems and capability for response, including shock-responsive systems, though both embedding risk financing more fully into systems, and making disciplined use of grant finance to create incentives for risk management.
  1. Advance multi-lateral systems for crisis risk financing. The multilateral system is still weighed too heavily towards responding only after the disasters. The GRIF support the design and testing of an expanded set of instruments and approaches, alongside evidence on what works, and bring together a critical mass of donors and implementing partners to foster greater coherence, coordination and shared global standards around operating principles and disciplined use of grant finance. An outcome will also be to better leverage the capital of the private sector.
Appraisal Case

1. At the time of writing, the Global Risk Financing Facility (GRIF) already exists as a World Bank multi-donor trust fund (MDTF). The GRIF concept was co-designed by the UK, Germany and the World Bank. Germany has already committed to contribute a total €115m to the GRIF MDTF. The multi-donor trust fund underpinning GRIF evolved from an earlier MDTF co-financed by the UK and Germany, where UK funding supported a pilot premium financing facility (up to £8m) and analytics/innovation activities (both part of the DFID-funded Centre for Global Disaster Protection).
2. The operating modalities of the GRIF are captured in an Operations Manual approved by the Steering Committee (including DFID DG Economic Development and International), included at Annex A. The decision to work through the multilateral system, and initially with the World Bank, is explained in Box 4.

Box 4: Why work through the multilateral system, initially with the World Bank / The World Bank is the institution with the most established reputation, track record and expertise in this sector. It is unique in its global reach, the breadth of its instrument set, its technical expertise and operational capabilities and experience in sovereign risk financing. Besides the Caribbean Development Bank, no other Bank has experience in delivering premium subsidies. While other development banks are also strengthening capabilities in this area, the World Bank has a unique ability to drive the global standards and coherence needed for GRIF to be a success. Benefits include: / a global footprint and pipeline of projects - World Bank country programmes working with governments across the developing world; / ability to leverage World Bank lending operations, including to better embed activities into core budgetary processes and enhance sustainability / taking advantage of the Bank’s risk management systems, and reducing the internal administrative burden; / linkages to wider Bank work on public financial management and macro-fiscal frameworks to ensure risk finance is plumbed into systems within government that enable it to deliver impact. / access to unique technical knowledge, networks, and influence; / greatest potential to gain the critical mass (scale and buy-in); and, / necessary links to IBRD/IDA financing to drive real change in the multilateral system, ensure sustainability and to ensure risk finance is appropriately linked to investments in preparedness and resilience. / Partnering with the World Bank would also align with our wider objectives of encouraging the Bank to do more to support countries prepare for and respond to crises. The fact that the GRIF was included within the World Bank’s Global Crisis Risk Platform (GCRP) paper that was approved by the Board in July 2018 demonstrates its potential for systemic impact. Alignment of the GRIF and GCRP, and senior-level World Bank ownership of these linkages, is necessary to ensure the GRIF can drive systemic impact. / Other regional development banks (RDBs) currently have a narrower range of capabilities in this sector, however, they may offer some comparative advantage due to regional knowledge, networks, or other considerations. The World Bank is selected as the initial implementing partner as this is currently it is the only multilateral with the systems and capabilities in place to achieving the GRIF’s project and wider objectives. Options for working with other RDBs over time are considered further during the options appraisal.

Given this status, the options considered in this business case cover: (1) the size of a potential UK contribution to the GRIF, (2) the modalities of funding (i.e. whether to commit all financing through the World Bank MDTF or to leave flexibility to use other funding channels but under a GRIF ‘umbrella’), and (3) the types of activities to be funded. Types of activities are discussed below then an options appraisal conducted on size and modalities. An analysis of forecasted pipeline projects has been completed and can be found in Box 6.
Types of activities to be supported
1. The GRIF aims to increase the use of crisis-risk financing instruments and ensure these are embedded within effective national systems for disaster response whilst catalysing investment in risk reduction, preparedness and resilience building activities. It focuses on helping the most vulnerable people, and the economy, services and infrastructure they depend on, to recover more quickly when a disaster strikes. It will prioritise the strengthening of country systems for crisis response and recovery through contingent response plans and shock-responsive systems linked to and backed by financing arrangements, but it will also work with humanitarian agencies where necessary.
2. The scope of the Facility initially covers shocks from disasters but could be broadened over time to other types of crises, such as famine. The GRIF will fund scoping grants, focused TA, and investments in risk financing instruments (it does not provide insurance itself). Activities to be financed or co-financed by GRIF may include:
  1. Insurance premium financing, e.g. for catastrophe risk transfer instruments;
  2. Costs associate with contingent financing instruments, e.g. fees for grants or credit lines with hard/soft triggers, or contingent debt instruments;
  3. Start-up costs of risk financing vehicles, such as sovereign risk pools;
  4. Costs for developing and strengthening disaster preparedness, risk reduction and the implementation of risk financing linked to national delivery mechanisms; and
  5. Technical assistance for development of risk financing solutions for countries and associated global public goods (e.g. data) to support the implementation of projects by a government or agency.
3. Activities involving the creation of financial assets on DFID’s balance sheet are initially excluded. In particular, this includes the creation of national disaster funds or other contingency funds that are held by a client government on/off budget. Investment in capitalising of sovereign risk pools is initially excluded by DFID but this may be revisited if the GRIF governance modalities evolve in the future to meet DFID requirements on oversight of that financial asset and where that investment is small enough to justify grants versus development capital. Funding for the capitalisation of risk pools, either as grant or Development Capital, would require additional approvals from PSD and FCPD under Smart Rule 11. In such cases, the required approvals will be sought.
4. The GRIF works by co-financing with IFI lending operations to ensure risk finance is embedded within country systems (see Box 5). The GRIF does not act as a fund that any organisation can bid into. It aims to incentivise preparedness through a combination of direct financing of actions/systems, placing prior actions (i.e. conditions) on instruments and through requirements within the project appraisal criteria (Annex C).

Box 5: What does the GRIF MDTF actually do? / World Bank operational teams, working with a technical unit, will work with countries to develop proposals to access financing from the GRIF as part of larger project preparations with a government (see Figure 3). For example, a pilot project in an African country requested around $5m to part-pay insurance premiums as part of a larger $80m, 4-year lending operation to help the government strengthen its disaster risk management systems. GRIF can also fund standalone proposals for work on public goods or work with other implementing partners, such as humanitarian agencies, to develop proposals. It is expected that proposals will incorporate up to $4m in technical assistance support plus co-financing of instruments of up to $25m over 3 years. The full operating parameters of the GRIF MDTF are laid out in Annex A. / Figure 3: GRIF MDTF

Box 6: Forecasting Project Pipelines
The funding level of the GRIF should be aligned to the volume of projects expected to be funded. Given that this is a new initiative, it is difficult to estimate the potential pipeline of projects and the financing needs of those projects over multiple years. Here, estimates are made for financing needs over the next seven years based on extrapolating from the projects prepared for the existing Pilot Facility, from the World Bank MDTF pipeline and investment through additional channels. Given the long time to generate demand from countries and build capacity, as well as to use subsidies to deliver quality projects, it is expected that activity will increase over time and that there is an upper bound on the level of funding needed over time. Three scenarios have been prepared:
1. Baseline scenario: $125m ($55m – $190m). This scenario is based only on projects already being scoped, prepared or under implementation for the Pilot Facility.
2. Central scenario: $230m ($130m – $320m). This includes increased support for the baseline projects and includes the provision for additional countries (and humanitarian agencies) that have expressed interest.
3. High scenario: $370m ($220m - $520m). This includes scaling up for support for the centrals scenario projects and includes provision for additional projects and support for a regional initiative.
A high degree of uncertainty is due to uncertainties about how quickly the projects will develop, and the scale and lengths of the projects. Both will be partly determined by the donor preferences on projects and the levels of subsidies that are acceptable.
Appraisal of Feasible Options
Feasible Options
1. The following programme options are considered feasible and appraised to select the best way of achieving the impacts and outcomes set out in the strategic case:
  1. Option 1: Do nothing (counterfactual). The £8m already committed to the GRIF (from the Pilot Facility of the Centre for Global Disaster Protection) becomes a small part of the GRIF MDTF.
  2. Option 2: Commit £45m to the GRIF World Bank MDTF. This commitment level is set to be consistent with the low pipeline forecast pipeline volume (Box 6). The UK a smaller but not insignificant partner in the GRIF.
  3. Option 3: Commit £90m to the GRIF World Bank MDTF. This commitment level is set to be consistent with the ‘Central’ forecast pipeline volume. It makes the UK and Germany equal partners in the GRIF MDTF.
  4. Option 4: As Option 3, the UK commits £90m to the GRIF “initiative”, but with flexibility to utilise other funding channels beyond the MDTF. The GRIF design is as in Option 3, but here DFID would commit funds to the MDTF initially for an inception year but retain flexibility to use other channels in addition to the MDTF.
2. It is noted that the Centre for Global Disaster Protection is not considered a feasible option to deliver the GRIF (as set out in Box 7), though it plays a role in providing complementary technical assistance and as an incubator of more cutting-edge innovations in all options and is considered as a specific delivery channel in Option 4.

Box 7: Why can’t the Centre for Global Disaster deliver GRIF?
The Centre for Global Disaster Protection is the flagship bilateral programme in DFID’s disaster risk financing and insurance portfolio and funded the original pilot facility that led to the creation of the GRIF, so it makes sense to consider whether this existing programme could be built upon rather than investing in a new mechanism.
The Centre is a bilateral programme (see business case[49]) currently implemented mainly through a managing agent (a contracted company) and a World Bank Single Donor Trust Fund (SDTF) and with some activities directly managed and/or procured by DFID. The Centre is geared up to work on relatively small, agile and technically complex activities, including technical assistance, global public goods, and innovation. The GRIF conversely focuses on large, multi-year investments in co-financing investments with governments, e.g. premium subsidies. Therefore, delivering GRIF-type activities through the Centre would therefore require a substantial change in the Centre’s mandate, size and design and is not well aligned to its comparative advantage versus a development bank. A particular constraint is that the Centre is not set up to provide financial aid to governments; it does not have the fiduciary systems in place to manage these types of interventions and building this capability would take time and not be good value for money compared to using a development bank that already has strong systems in place. It could also not offer a wider toolkit of instruments such as contingent credit as it has no lending capability.
[49] DFID (2017) Centre for Global Disaster Protection Business Case. https://devtracker.dfid.gov.uk/projects/GB-1-205231/documents
Conceivably, the Centre could pay premiums directly to an insurer, but its comparative advantage would only be for small, agile type projects, such as small-scale pilots, so it would not be appropriate for deliver large amounts of financing. This innovation focus could fit well with the mandate of the Centre. The World Bank single-donor trust fund (SDTF) that is set up as part of the Centre is able to provide GRIF-type activities if needed. While this option would not deliver the benefits of multi-donor coordination (see Option 1, 2 and 3), it could be a useful channel where activities needed to be smaller, more agile and more targeted. The use of this channel is considered in Option 4 of the appraisal.
Under any option, it is essential to hard-code complementarity and linkages between the Centre and GRIF. The GRIF has been designed to complement the Centre. The comparative advantage of the Centre is its ability to respond quickly to demand from clients and provide impartial advice, as well as to form partnerships that would allow it to leverage the skills and expertise of the private sector, humanitarian agencies or others. Its agility, impartiality and technical expertise gives it a unique positioning and role in innovation. The GRIF is conversely a large, multi-donor facility providing long-term finance to governments. Technical assistance is provided by both the GRIF and the Centre, but in a complementary way. For example, TA from the GRIF will be focused on funding World Bank operational teams to embed finance into country programmes, whereas the Centre will fund TA to support these teams with specific expertise on risk finance. In the Operations Manual of the GRIF (Annex A), the Centre is identified as a partner initiative and plays a role in providing technical expertise and acting as an incubator for new innovations and approaches that can be scaled up by GRIF. The existence of GRIF will increase the impact of the Centre and vice versa. The complementarity between the GRIF and the Centre is given in Annex D.

	Attributes impacting ability to meet DFID objectives on maximising effectiveness and efficiency in achieving desired impacts
Effectiveness in Achieving Impact	Appropriate scale, expertise and toolkit to deliver activities and desired impact / Ability to drive global change in the multilateral system, including achieving scale, embedding approaches, critical mass of finance and partners to achieve greater coherence, learning and standards, and a sufficient change incentives globally around ex-ante versus ex-post disaster management / Ability to work with/influence other implementing partners, including regional development banks and humanitarians	Speed and agility in responding to client needs; tools are accessible and responsive and well embedded in projects / Sufficient senior level buy-in within the World Bank, alignment with GCRP and links across GPs and country/regional teams / Able to catalyse strong pipeline of projects / Agility and capacity for innovation and learning / Achieving multilateral approach - other donors / Quality and impactful investments in global public goods in alignment with GCRP / Ability to link to DFID bilateral programmes / Centre for Global Disaster Protection links / Strengthening DFID bilateral partnerships
Efficiency in Achieving Impact	Efficiency – admin/human costs/burden versus spend on actual projects / Potential to scale-up and learn	DFID administrative burden / Minimising disbursement risks
Minimising Risks in Achieving Impact	Sufficient DFID oversight and strategic direction to ensure GRIF meets DFID objectives has strong standards and maximises impact / Realisable exit strategy	Ensuring high quality projects: minimising risks associated with poor application of principles, uneven concessionality, inadequate gender sensitivity / Minimising risks of distortions, perverse incentives

Table 2: Appraisal criteria. Those in bold are most important and given higher weighting in the appraisal.
Options appraisal
Based on the desired impacts and outcomes refined in the Strategic Case, Table 2 defines the appraisal criteria for delivery options. The options are discussed below and appraised against the criteria in Table 3. We judge that there is a moderate level of evidence to support these conclusions, which comes from learning from the pilots and analogous multi-donor programmes. The remaining uncertainty stems from this being a new initiative.

	Weight	Option 1: Do Nothing	Option 2: Smaller multilateral GRIF	Option 3: Larger multilateral GRIF	Option 4: Larger multilateral GRIF with flexibility
Appraisal Criteria for achieving Impact/Outcomes		(ratings: 1= Low, 5 = High)
Appropriate scale, expertise and toolkit to deliver activities and desired impact nationally	20	1	3	3	5
Drive change in the multilateral system, including achieving scale, embedding approaches, critical mass of finance and partners to achieve greater coherence, learning and standards, and a sufficient change incentives globally around ex-ante versus ex-post disaster management	20	1	3	5	4
Speed and agility in responding to client needs; tools are accessible and responsive and well embedded in projects	15	3	4	5	5
Sufficient senior level buy-in within the World Bank, alignment with GCRP and links across GPs and country/regional teams	15	1	4	5	4
Ability to work with/influence other implementing partners, including regional development banks and humanitarians	10	1	3	4	5
Able to catalyse strong pipeline of projects	10	1	4	5	5
Agility and capacity for innovation and learning	10	2	3	5	5
Achieving multilateral approach - other donors	15	3	4	5	4
Quality projects: minimising risks associated with poor application of principles, uneven concessionality, inadequate gender sensitivity	20	3	4	4	4
Minimising risks of distortions, perverse incentives	20	3	5	4	4
Quality and impactful investments in global public goods in alignment with GCRP	15	1	3	4	5
Efficiency – admin/human costs/burden versus spend on actual projects	5	1	4	5	3
Potential to scale-up as learn	10	3	5	4	5
Sufficient DFID oversight and strategic direction to ensure GRIF meets DFID objectives, including responsiveness to DFID requests	40	2	3	4	5
Realisable exit strategy	20	3	5	4	4
Minimising disbursement risks/opportunity cost	15	3	3	2	5
DFID administrative burden	5	3	3	4	3
Ability to link to DFID bilateral programmes	10	3	3	4	5
Centre for Global Disaster Protection links	10	3	3	4	5
Strengthening DFID bilateral partnerships	5	3	3	4	5
TOTALS (weighted)		630	1140	1190	1300

Table 3: Appraisal of feasible options. The objectives shown represent assessment of the key design factors that affect the ability of the GRIF mechanism to drive efficiency and effectiveness in meeting the desired impacts and outcomes of the programme (as per Table 2).
1. Option 1 (Counterfactual): ‘Do nothing’. The current status quo largely continues, with countries relying on a combination of ex-post budget reallocations and external post-disaster assistance (humanitarian aid, lending). Some ex-ante instruments are available, but uptake is relatively low due to scale of funding and they are not implemented in a way that is comprehensive and integrated into national systems for response and recovery. Consequently, financial exposure to disasters continues to grow. The impacts increasingly erode progress against broader development objectives and lead to rising calls for humanitarian aid. The existing financial commitments to the GRIF from the Germany and the UK allows lower levels of impact and donor activity continues to fragment. Standards and interventions are heavily influenced by siloed, political decisions, the delivery of sustainable interventions suffers, the ability to crowd-in quality private sector risk capital suffers, and levels of innovation and learning are lower. DFID risks losing its leadership and comparative advantage in this field, and there is a risk that the Centre’s work is overshadowed.
2. Option 2: Commit £45m to a multilateral GRIF World Bank MDTF
1. What would it look like? GRIF operating parameters are as outlined above and in Annex A, with £45m DFID funding commitment to the World Bank multi-donor trust fund alongside Germany (who have committed €115m). This would create a GRIF MDTF of around $185m (and potentially up to $225m later with other donors).
2. Advantages:
  1. As a fully multilateral vehicle, the GRIF should be able to crowd in other donors and drive greater coordination and a more coherent approach on principles and learning, as well as generate demand from beneficiary governments and signal to the private sector to begin to develop high quality products tailored to this market. Such critical mass is also necessary to help drive forward DFID ambitions on implementation of Grand Bargain commitments around better coordination in crises response, joint needs assessment, localisation and supporting the development of government systems. A multilateral mechanism that can be apolitical, can also help to ensure crisis risk finance is reliable and effective and less subject to vested interests.
  2. Working with a development bank is essential to blend donor grants with sovereign lending at scale to offer comprehensive packages of financial support and leverage the superior fiduciary systems of development banks to manage finance flowing to client governments. Based on current GRIF pilot projects DFID grants could leverage 10 times or more of World Bank lending.
  3. The World Bank is the institution with the most established reputation, track record and expertise in this sector. It is unique in its global reach, the breadth of its instrument set, its technical expertise and operational capabilities and experience in sovereign risk financing. Besides the Caribbean Development Bank, no other Bank has experience in delivering premium subsidies. While other development banks are also strengthening capabilities in this area, the World Bank has a unique ability to drive the global standards and coherence needed for GRIF to be a success. Benefits include:
    1. a global footprint and pipeline of projects - World Bank country programmes working with governments across the developing world;
    2. taking advantage of the Bank’s risk management systems, and reducing the internal administrative burden;
    3. linkages to wider Bank work on public financial management and macro-fiscal frameworks to ensure risk finance is plumbed into systems within government that enable it to deliver impact.
    4. access to unique technical knowledge, networks, and influence;
    5. greatest potential to gain the critical mass (scale and buy-in); and,
    6. necessary links to IBRD/IDA financing to drive real change in the multilateral system, ensure sustainability and to ensure risk finance is appropriately linked to investments in preparedness and resilience.
Partnering with the World Bank would also align with our wider objectives of encouraging the Bank to do more to support countries prepare for and respond to crises. The fact that the GRIF was included within the World Bank’s Global Crisis Risk Platform (GCRP) paper that was approved by the Board in July 2018 demonstrates its potential for systemic impact. Alignment of the GRIF and GCRP, and senior-level World Bank ownership of these linkages, is necessary to ensure the GRIF can drive systemic impact.
  1. Drive consistent approaches to concessionality, reducing perverse incentives, and setting standards. For example, new initiatives like the Famine Action Mechanism (FAM) could be supported through the GRIF. Ongoing programs would be grandfathered but could be integrated into the GRIF upon renewal or receive financing from the GRIF. As these initiatives come to an end, the aim is to bring all future extensions of such initiatives or new programs on risk financing under the GRIF.
2. Disadvantages:
    1. There are risks that with this level of funding, the UK risks losing its clear leadership in this substantial and strategic agenda, losing the ability to steer and shape the pursuit of reducing the humanitarian bill.
    2. As a smaller funder, our influence may be reduced giving risks of lower value for money if donor interests are misaligned. This is somewhat mitigated by the governance arrangements of the trust fund, which have equal voting rights for all donors contributing $10m, though in practice experience suggests donor influence tends to be proportionate to scale relative to others. This could be mitigated if more donors aligned to DFID join, however there is also a risk that additional donors will further dilute DFID influence.
    3. The smaller size means a small number and/or short/smaller projects, which means the GRIF will be less likely to achieve critical mass to drive real, long-term sustainable impact, particularly in terms of strengthening country capabilities and systems, and less chance of achieving the ambition of driving significant transformation in terms of cutting the costs of disasters. The economic appraisal (Table 4) demonstrates that this option would deliver disproportionately lower impact than the higher investment options (#3 and 4).
    4. The scale is matched to the lower end of the ‘central’ forecast pipeline volume and the upper bound of the “baseline” forecast (Box 6). There is a high chance that the GRIF will require replenishment within 3 - 5 years.
    5. A multilateral vehicle means limited flexibility for DFID to move faster and in a more agile way than other donors where impactful and to link finance into DFID bilateral programmes, including the Centre for Global Disaster Protection.
    6. Having all funding flowing through the World Bank risks creating a monopoly and could prevent other actors (e.g. regional banks) from entering this space reducing choice for client governments and potentially restricting innovation. This could be mitigated through allowing ‘transfers-out’ from the World Bank to other implementing partners, but this comes with overhead costs.
Option appraisal: On balance, this option would achieve some, but not all, of the programme objectives and disproportionately lower impact and so lower levels of value for money. Some progress would be made on premium financing, however DFIDs smaller role in this option risks divergence from DFID ambitions, in particular, the ambitions to drive real systemic change including incentivising preparedness and risk reduction and achieving innovation and quality monitoring and evaluation. For these reasons, Option 2 is not a preferred option.
1. Option 3: Commit £90m to the GRIF World Bank MDTF.
  1. What would it look like? As Option 2 but with a larger financial commitment that matches Germany’s commitment of €115m, achieving higher levels of value for money and driving greater alignment with DFID ambitions, including systemic change, innovation and learning through quality monitoring and evaluation.
  2. Advantages:
    1. As Option 2, but including the potential to achieve greater scale of impact and greater chance of achieving ambition of driving real systemic change. This is reflected in the much higher economic impact and value for money of this option (Table 4), which results from the larger and longer-term investments that deliver greater sustainability and benefits for preparedness.
    2. The larger size offers greater potential for strong buy-in within the Bank at senior and operational levels, and stronger demand from countries, accelerating the pipeline and therefore the impacts.
    3. This level of funding sits well within the ‘central’ pipeline forecast volume, so will serve ambitions for scaling-up well.
    4. DFID’s clear leadership is maintained, and levels of influence are increased giving greater potential for agenda setting and increased value for money.
    5. Greater ability to develop, test and apply standards, driving greater and lasting coherence amongst donors and implementing partners.
  3. Disadvantages:
    1. There could be issues with quality of projects if other donors push the World Bank to scale up too quickly. This is mitigated by setting expectations with other donors early that there will be a gradual ramp up of activity over time.
    2. There are uncertainties within the pipeline volume projections and a chance that forecasts have been overestimated leading to undisbursed funds. This is mitigated if DFID takes a phased approach, with an initial inception year, then transferring funds to the MDTF only as they are needed (in accordance with normal DFID rules on not transferring funds in advance of need).
    3. There is some risk that a larger trust fund could create incentives for the World Bank and donors to offer higher subsidy levels to disburse funds more quickly, with greater risks in terms of creating distortions. Potentially greater risks in terms of exit strategy as beneficiary countries may become accustomed to greater subsidies. This is mitigated through the operations manual, which has clearly defined co-financing rules and project appraisal criteria.
    4. Could detract other donors if the initial funding levels are large.
    5. DFIDs ability to move in a faster, more agile, adaptive and targeted way is more limited if all funding flows through the MDTF (compared to Option 4) and subject to agreement of the MDTF steering committee.
  4. Option appraisal: This option achieves the scale to enable significant change and drive impact, innovation, and learning. It places DFID well to influence alignment of the GRIF with our objectives. However, full commitment to the MDTF creatives some poor (and less easily managed) incentives and a lack of ability to be flexible and learn and adapt results means that, on balance, Option 3 is not the preferred option.
2. Option 4: As Option 3, but with greater flexibility on funding channels (£90m DFID commitment).
  1. What would it look like? In this case, DFID would make a commitment of funding to the GRIF initiative and would direct funds through the World Bank GRIF MDTF in phases (£45m initially, then increasing according to funding flows through other channels), retaining flexibility to utilise other funding channels where these deliver impact and value for money against DFID objectives. As a key DFID objective is donor coherence and global standards it is expected that the majority of funds would still flow through the MDTF and DFID would commit to ensuring standards are adhered to across all delivery channels.
  2. Advantages:
    1. Advantages are as Options 2 and 3, but with reduced risks and increased ability to adapt the programme to ensure it delivers maximum impacts and value. For example: this option allows more direct DFID control on financing than can be achieved with Options 2 and 3, and increases flexibility to test, learn and adapt the programme over time by using different delivery channels to maximise its impact and value for money against DFID objectives. It also brings an aspect of performance-based funding and so can create a lever to increase performance of the MDTF-funded activities (as poor performance of the MDTF could result in funds being redirected to another channel).
    2. Enables DFID to also (more easily) build the capacity of other implementing partners (e.g. regional development banks) where appropriate and encourage them to adopt the GRIF’s standards and principles. This would reduce risks of creating a monopoly position for the World Bank in this space.
    3. Greater ability for DFID to move faster and in a more agile way than could normally be achieved through an MDTF, for example doing more with humanitarian actors and supporting more innovative approaches, but also link finance into DFID bilateral programmes (e.g. as in Kenya, Box 2), as well as make stronger links to the Centre for Global Disaster Protection.
    4. Economic benefit and value for money of this option is estimated to be the highest of all three options (Table 4), due to the high chance of sustainability of projects and opportunities to maximise impacts through agility and innovation.
  3. Disadvantages:
    1. Threat to objectives on driving global coherence and standards. Other donors could perceive DFID as being less committed to a coherent GRIF and to ‘playing by the rules’ of the principles, reducing our influence on the GRIF MDTF and reducing GRIF’s ability to drive global coherence and standards. This would be mitigated by making a substantial commitment to the GRIF MDTF (£45m initially) and being clear on the conditions under which other channels would be used and that any activities would still be branded as associated with the GRIF MDTF.
    2. DFIDs commitment to the MDTF could be smaller, reducing our influence.
    3. Uncertainty on the size of DFIDs contribution to the MDTF could affect its ability to generate an ambitious pipeline of projects (as the World Bank needs to know what funds are available before it can start discussions with clients).
    4. This option increases the management burden on DFID as it would require great DFID advisory and programme management time.
  4. Option appraisal: This option has trade-offs versus Option 3 in that it gives DFID greater opportunity to adapt the programme to maximise impact over time but could reduce influence on the MDTF. The multicriteria analysis in Table 3 suggests that on balance, this option should deliver the greatest impact and value for money. Any increase in management burden is outweighed by the increased flexibility, risk reduction, and opportunity to maximum value for money and impact. If risks associated with Option 4 were found to be underestimated, then DFID could switch to Option 3 at no cost. Therefore, Option 4 is the preferred option.
Economic appraisal of the options
	Estimated Economic Benefits (in terms of reduced impacts of disasters)
	Total benefit (Central estimate and uncertainty)	Percentage increase in benefit relative to counterfactual	Benefit per £ invested by DFID (central estimate)
Option 2	£250m (100 – 550m)	+85% (-25 to 305%)	2.60
Option 3	£575m (250 – 1,280m)	+115% (-20 to 375%)	3.40
Option 4	£580m (290 – 1,380m)	+135% (5 to 400%)	3.45

 Table 4: Summary results from economic appraisal (Annex E).
1. The economic appraisal found in Table 4 and Annex E shows that the greater the investment in the GRIF, the greater the economic benefits per pound invested, and that the additional flexibility from Option 4 will further increase the benefit per pound.
2. This quantitative economic analysis reinforces the qualitative options appraisal that the highlights the preferred approach is given in Option 4.
Preferred option - summary
Based on these analyses, the preferred option is option 4. This option achieves a balance between coherence and opportunity to test, learn and adapt and the economic appraisal suggests it delivers the greater economic benefit and impact for every £1.
Where it will work – allocation methodologies and expected pipeline
1. The GRIF does not have focal countries as it will respond to demand and opportunities arising from World Bank country engagement and larger project preparations. Annex F analyses criteria to highlight potential priority countries that GRIF could work in. The GRIF MDTF governance (see Annex A) process requires the WB teams to construct an annual Scoping Plan that will be endorsed by donors at the biannual/annual Steering Group meetings. Project Concept Notes with more details will then be presented for donor review prior to moving forward with funding for technical assistance and/or investment.
2. The work plan will aim to create a portfolio that balances focus on countries in greatest need (in terms of vulnerability to crises and poverty levels) and the potential for successful impact (including ease of working and government ownership and readiness). GRIF will also strive to create a balance between cutting edge, high risk projects to test innovations and to learn versus more standard but lower risk projects. Within this high-level framework, project funds will likely be evaluated on a first-come, first-serve basis. In steering the work plan and enforcing the principles (see Annex C), DFIDs priorities will be set based on DFID objectives and bilateral interest (in terms of UK humanitarian aid, geography, innovation, potential for impact, etc.).
3. Fragile and conflict-affected states (FCAS): The GRIF will work in FCAS countries. The link between disasters and conflict is well documented. Conflict increases vulnerability, meaning that if an event occurs its impacts are magnified[50]. There is also evidence (though a weaker evidence base) that disasters act as a threat multiplier of violent conflict, particularly in fragile states where governance is weak, through putting additional pressure on community relations and tension [51]. The GRIF can help to reduce the likelihood of conflict and instability through building resilience and strengthening systems for early response and recovery.
[50] # Ferris, E. (2010) Natural Disasters, Conflict, and Human Rights: Tracing the Connections. Available at: https://www.brookings.edu/on-the-record/natural-disasters-conflict-and-human-rights-tracing-the-connections/; & International alert (2015) Compounding risk: disasters, fragility and conflict. International Alert: London
[51] # Ferris, E. (2010) Natural Disasters, Conflict, and Human Rights: Tracing the Connections. Available at: # https://www.brookings.edu/on-the-record/natural-disasters-conflict-and-human-rights-tracing-the-connections/; & International alert (2015) Compounding risk: disasters, fragility and conflict. International Alert: London
4. GRIF provides a vehicle to test how risk financing instruments can: operate in fragile contexts; be used by humanitarian agencies, and; promote greater coordination, preparedness and early action. GRIF will work closely with DFID and relevant parts of the World Bank, for example the Fragility, Conflict and Violence FCV Global Practice, to test, evaluate and learn what works. This could include supporting parts of the proposed Famine Early Action Mechanism (FAM) where this aligns with the principles, or pilot work with the Red Cross Movement and NGOs (e.g. via the START Network). The approach will be developed during the inception year.
Theory of Change for the Preferred Option
1. The impacts, outcomes, outputs and activities of the GRIF are summarised in a preliminary theory of change presented in Figure 4. The GRIF’s overall impacts of reduced human and economic impacts from disasters will be achieved through outcomes which are about both the operating environment (the green circles) of the wider system and demand at country level which operates in this environment (the arrow).
2. Environmental or systemic outcomes are an improve multi-lateral system that has the right instruments and capabilities to enable global shift towards more ex-ante approaches to disaster risk. Country level outcomes are around the strengthening financial resilience, catalysed investments in preparedness and resilience, and more disaster finance flowing through pre-arranged systems.
3. These outcomes will be driven by intermediate outcomes and outputs that are detailed in Figure 4. Gender and equity is a foundational focus at each step of the theory of change.
4. The Centre for Global Disaster Protection, multilateral financing, private sector capital, the World Bank Group capability and DFID (and partners) bilateral influence are all key enablers for the programme.
5. There are a number of key assumptions that the theory of change relies on and differing levels of evidence and therefore confidence can be attached to each; this is unpacked further below. These assumptions will form a pivotal part of the design of, and outcomes from, the M&E work. Where the assumptions pose significant risks to the delivery, outcomes and impacts of the programme, these are placed in the risk register.
6. The project principles have been designed to underpin the design and approval of GRIF projects and will play a key role in ensuring the assumptions in the theory of change hold. For example, risk financing paying out according to preparedness plans is a key principle meaning that the projects will be judged and assessed on the strength of these aspects. A further example is that strong government buy-in (a project principle) increases the likelihood that grant funding will catalyse further investment.
7. The assumptions around demand are underpinned with evidence from the ARC evaluation that premium financing is a key barrier[52]. The strong pipeline of countries for the GRIF highlights the strong interest from countries for premium subsidy (one project underway, six more actively working on proposals, with nine further countries on the initial scoping plan, and under the ADRiFi initiative these is one country project underway with a further eight in the pipeline). TA programmes, such as the Centre, have been, and continue to, help countries overcome the other barriers to risk financing, leaving the financial challenges the remaining issue for many countries.
  [52] https://www.opml.co.uk/projects/independent-evaluation-african-risk-capacity
8. There is evidence[53] that strong preparedness reduces the times for response and for every $1 invested in preparedness, at least $2 are saved in the response, meaning that stronger national systems and preparedness plans should lead to reduced impacts from disasters.
  [53] Price Waterhouse Cooper and Boston Consultancy Group, 2015 and 2017, Return on Investment Analysis of the Ready to Respond programme of UNHCR, UNICEF, WFP and OCHA.
9. A strong learning plan and the development of global standards based on GRIF project learning will likely drive that the system to becomes an further advocate and implementor of disaster risk financing, financial resilience, preparedness and risk reduction.
10. This narrative around the draft theory of change and the assumptions that underpin it will be developed further in the inception year.

Figure 4: Preliminary theory of change
There is clear evidence from the literature and consultations that the GRIF design is addressing the key market and government failures, and that a financing vehicle investing in these areas can drive increases in demand and capacity to use risk financing systems effectively. However, success will depend on the willingness of governments and World Bank country/regional/global practice teams to engage and utilise the GRIF to catalyse improved pre-disaster planning and financing systems. It also depends upon opportunities to link into wider shock-responsive services and recovery planning (e.g. infrastructure). GRIF is designed to maximise impacts by:
  1. Linking to World Bank operations and working where there is strong demand and commitment from governments and other partners, as well as being able to respond quickly and flexibly to demand.
  2. Robust, evidence-based set operating principles, co-developed with DFID and other stakeholders, to guide project development and appraisal (Annex C), and investments in learning and evaluation. The WB technical unit will play a key role in implementing these principles. The trust fund management unit will provide an open and transparent review of proposals against the principles, and post-hoc evaluation of projects against them.
  3. Focus on learning: the GRIF will have the clear mandate to test and learn and will be built to be able to adapt based on learning.
  4. Drawing upon the Centre for Global Disaster Protection/WB Hub, including for technical services, data, research and as an incubator for new innovations.
  5. Evolutionary approach and investing in evaluation and learning.
Exit strategy
The programme has a clear exit strategy for DFID in that firstly, it aims to support countries to better manage their own risks and fund through their own fiscal budgets, and secondly, it aims to trial enhanced instruments that can over time be integrated into core multilateral development finance. Sustainability and exit strategy are key criteria for appraisal of GRIF project proposals by the trust fund (Annex A).
Gender, disability and inclusiveness
Gender considerations, as well as broader inclusivity of the results and impacts, will play a key role in the design and ongoing decision making of the GRIF. Particular attention will be given to the gender dimension of crises preparedness, response and recovery. The GRIF will explore the integration of a gender lens in risk financing initiatives, an area that is often missing in such initiatives. For example, activities should integrate gender and ensure inclusion of the needs of the poorest and most vulnerable people. Any solutions or strategies developed should promote, or at least not disadvantage, female beneficiaries, and deliver benefits for poverty alleviation. To ensure that gender and inclusivity is actively considered and monitored throughout, a gender action plan will be requested from implementing partners by the end of the inception year. Further details are given in Annex B.
Climate and environmental sustainability
This programme will play an important role in strengthening resilience to climate-related disasters like droughts, storms and flooding. It can also have wider benefits through integrating climate and environment considerations in technical assistance activities. For example, risk financing can build in projected climate trends in terms of frequency and intensity of events to ensure robust and appropriate solutions are found. In addition, the focus on risk financing that incentivises risk reduction will also be key to reducing the impacts and costs of climate-related events.
Value for Money
Measures to assess value for money
Value for money will be continually monitored through evaluating delivery in the following areas, based on the theory of change. Preliminary indicators are included in 5. These will be used to build the logframe for the programme.

Type	Area	Illustrative Indicator
Output	Technical Assistance	# countries receiving technical assistance to prepare and implement GRIF financing
	Financing	# countries receiving support (disaggregated by type of support, e.g. premiums only, contingent credit only, multiple instruments, etc.) / # countries, % matched funding (by IDA/IBRD and investment type) / % project proposals reviewed by external experts with review shared openly and transparency with donors and % published in public domain / # projects meeting GRIF appraisal criteria based on external review at different levels (Red, Amber, Green) / # pilots of risk financing mechanisms in fragile states and/or as part of a coordinated approach with humanitarian agencies. / # projects linking in incentives for preparedness and resilience
	Innovation and influencing	# revisions to operational principles as the GRIF evolves and learns / # new approaches trailed and learning reports published / # projects subject to full evaluation (and # partial evaluations), and % with key outcomes and learning published in public domain
Outcome		# countries with risk financing strategies/instruments in place supported by GRIF, and % of these (hard/soft) linked to contingency plans/national systems / Evidence of strengthened financial strategies and use of instruments / Evidence of strengthened pre-disaster planning, preparedness and resilience catalysed as a result of projects / Evidence of linkages of risk finance to shock-responsive systems and services, DRM strategies and or protection of critical infrastructure. / Number of ex-ante risk financing instruments/approaches available
Impacts		# people benefitting from financial protection through risk financing / $m disaster losses covered by sovereign risk finance and insurance (average annual expected, and actual absorbed if a disaster occurs). / Evidence of reduced impact from disasters and other crises (impact evaluated if event occurs)
Other	Financial	Administrative and programme management spend as a fraction of project spend, benchmarked against other similar projects. / Accurate profiling and forecasting.
	Value-add	Multilateral co-financing (e.g. IDA/IBRD/others) / Evidence of increased leveraging of the WB balance sheet / Private sector risk capital leveraged / Linkages/Collaborations with the Centre for Global Disaster Protection

Table 5: Initial vfm indicators (to be confirmed during inception phase)
Summary value for money statement
1. The return on investment for this programme is expected to be significant, even under conservative ‘central’ assumptions. For example:
  1. Around 80 million people in developing countries will benefit from strengthened preparedness and faster, more reliable response to disasters. Relatively, women and children will benefit most from GRIF programmes, as they are disproportionately vulnerable to disasters.
  2. The economic benefits of the programme, in terms of reduced impacts of disasters, are estimated to be around £580m (range of 290 – 1,380m based on a range of assumptions). This equates to over £3 benefit for every £1 invested.
  3. The economic benefits of the programme are expected to be around 135% (5 – 400%) larger than the counterfactual case, hence more than double an equivalent investment in traditional post-disaster assistance.
2. The ranges of uncertainty in these estimates stems from uncertainty in the benefit of early versus later disaster response, the costs of risk financing instruments, the chance of project success and the level of co-financing per project. The full economic analysis is shown in full in Annex E.
Commercial Case

1. As outlined in the Appraisal Case, the preferred option is to deliver the GRIF through one main delivery channel (the GRIF multi-donor trust fund (MDTF) with the World Bank) but retain the flexibility to utilise other funding channels where this can deliver greater overall impact and value for money for the programme than the MDTF alone (Appraisal Case, Option 4). Therefore, for the total funds of £90m:
  1. Majority of £90m (£45m initial commitment) will be delivered through a third party – the World Bank through either the MDTF or, if required, the Centre’s SDTF.
  2. A minority of the funds through secondary channels where appropriate:
    1. A trust fund type arrangement with a regional development bank or other implementing partner
    2. Direct procurement from DFID, via the bilateral Centre for Global Disaster Protection or suitable DFID bilateral programme.
2. The preliminary delivery chain map, including the different options for the flow of funding, is given in Figure 5.
3. The Management Case lays out the decision criteria and process for how funding will be allocated between these channels.

Figure 5: Preliminary Delivery Chain Map
I
Delivery through a third party – World Bank Group
There are different options available to deliver using this route:
  1. Utilise the existing, repurposed multi-donor trust fund (MDTF). The existing InsuResilience Climate Risk Financing and Insurance Programme trust fund that Germany and DFID co-fund has recently been repurposed for the GRIF. The Global Facility for Disaster Risk Reduction and Recovery (GFDRR) and DRFIP act as the secretariat. Redefinition of the identity, governance and scope has been completed to meet the GRIF’s requirement. This is the preferred option.
  2. Utilise the existing DFID single donor trust fund (SDTF). The existing SDTF established in December 2017 as part of the Centre for Global Disaster Protection is able to deliver GRIF projects but this would require a programme redesign with the trust fund administrators - the Disaster Risk Financing and Insurance Programme (DRFIP) of the Finance, Competitiveness and Innovation (FCI) Global Practice. Option available where appropriate (see Management Case).
  3. The design phase of GRIF also considered whether to establish a Financial Intermediary Fund (FIF). Although not immediately required, a FIF could become a suitable option if the GRIF were to reach a sufficient size (through other donor commitments) and if multiple transfer-out’ arrangements became necessary. This is not a preferred option at inception.
Why are these the right arrangements for this intervention?
1. As outlined in the Appraisal Case, the World Bank is unique in its global reach and capability, proven track record in delivering disaster risk financing and insurance projects and ability to link trust funds with IDA/IBRD lending operations.
2. For a large, special purpose, new initiative, the World Bank’s preferred method is to establish a trust fund. The trust fund provides the most efficient financial structure that can be quickly operationalised while minimising administrative costs.
3. The Multilateral Aid Review in 2016 concluded that the World Bank Group is one of the most effective multilateral institutions that DFID funds. On average, World Bank trust funds score better in Annual Reviews and PCRs than the rest of the bilateral portfolio.
4. The World Bank will act as trustee and administrator of the trust fund, responsible for delivery, appraisal, implementation review, monitoring and reporting on all performance aspects of fund-financed activities implemented through the World Bank. The Bank will administer the trust fund in accordance with fiduciary terms agreed with donors.
The capability and capacity of the World Bank to deliver the GRIF
1. The World Bank is unique in its capability and proven track record in delivering disaster risk financing and insurance projects. It has been a pioneer in the development and implementation of these types of programmes and projects globally. The Disaster Risk Financing and Insurance Programme (DRFIP) was established in 2010 as a joint initiative of the World Bank’s Finance, Competitiveness, and Innovation Global Practice and the Global Facility for Disaster Risk and Recovery (GFDRR) to work on sovereign disaster risk finance, market development, analytics and knowledge management and global partnerships. DFID has worked with both DRFIP and GFDRR on successful disaster risk financing initiatives for five years[54], including of the Pilot Premium Financing Facility that this programme builds on.
  [54] E.g. Sovereign Disaster Risk Financing and Insurance (SDRFI) research programme, Philippines Catastrophe Risk Insurance Programme and the Centre for Global Disaster Protection.
2. Based on learning from these experiences, there are some key points that will need to be (and have been) addressed in the GRIF agreements and operations manual:
  1. Ensuring that the GRIF has sufficient internal visibility, senior buy-in, appropriate internal governance and connections to relevant Global Practices and regional and country teams within the World Bank to integrate risk financing effectively into IDA/IBRD operations and be adequately embedded/aligned to effectively support the goals of the Global Crisis Risk Platform and DFIDs desired outcomes.
  2. Setting out the relationship between the GRIF and the Centre for Global Disaster Protection to ensure these two programmes mutually reinforce each other and to ensure no competition/duplication in scope or activities.
  3. Ensuring sufficient UK oversight and strategic direction, including through satisfactory governance arrangements and visibility of UKaid brand.
  4. Agreed operational processes that provide sufficient openness and transparency and quality around how standards/principles will be embedded into projects and minimum standards ensured, e.g. on issues such as open procurement of any insurance. This includes sufficient external technical review of projects (before, during and after) and appropriate governance structures and sufficient technical capacity in place within the World Bank to identify and correct issues early, as well as sufficient oversight by the Steering Committee. Agreed processes for open and transparent monitoring, evaluation and learning with external experts.
  5. For GFDRR[55] hosting the MDTF, given the scale of this initiative, DFID would need to be assured that areas for improvement identified in the 2016 Multilateral Development Review (MDR) have been addressed. If the SDTF were to be used, DFID would need to be assured that sufficient administrative capacity was built.
    [55] DFID withdrew core funding from GFDRR in 2016 based on the strategic fit. At that time, there was agreement that this would not prevent DFID from working with GFDRR. Several programmes are working well (e.g. DFID-GFDRR Challenge Fund and Strengthening Climate Services for Resilience in Asia).
  6. Clear governance arrangements that assure DFID equal say in setting the strategy with any other donor(s), and reduce risks of free riding by other donors.
  7. Assurances around open and value for money approaches to reinsurance procurement where UKaid is being used to provide subsidies for premiums, including where the WB Treasury (WBT) is acting as an intermediary. WBT provides a valuable service to clients but analyses commissioned by DFID[56] suggest that current practices for reinsurance procurement by WBT required due to credit ratings may lead to higher costs of insurance and artificially constrain market development and are not justified where a donor is paying a portion of the premium. This issue will need to be further assessed and satisfactorily addressed before UKaid is used to procure reinsurance via WBT in this way.
    [56] GAD procurement study
What are the key cost elements that affect overall price?
1. Management costs: World Bank management cost has two components: the trust fund fee (maximum of 5%, reducing to 4% for grants of between US$50 million and US$500 million) and an Indirect Rate of around 17%. These rates are determined at institutional level between DFID and the WBG. They cover all secretariat activities related to the programme, including planning, monitoring and evaluation, staff and communications. The cost is no higher than analogous competitively procured programmes.
2. Programme costs: DFID policy is that Trust Funds should not support Bank staff costs. However, exceptions can be made if those costs are additional. Any GRIF staff that were situated in the Hub in London are clearly additional and so staff costs can be funded. Currently it is anticipated that up to 2 staff may be located in the London hub. Beyond this, the World Bank will use established procurement process and norms to ensure programme costs are competitive and provide value for money.
3. Travel and subsistence: Travel and expenses of World Bank staff working on the programme will be in line with existing World Bank practices.
Form of the agreement
DFID will form Administrative Agreements for the MDTF and/or the SDTF with the World Bank. The agreements, any amendments, and associated side letters will set out the terms and conditions of trust funds including governance, management, reporting and allocation and use of funds. Payments to the trust fund(s) will be made periodically in advance in accordance with trust fund rules.
Managing delivery risk
A key risk for this delivery route is the delivery quality. Trust funds are generally less flexible compared to commercial procurement routes, and DFID will not have the same level of oversight and influence of its investments. This risk is being reduced and managed through the programme design and actions presented in the management case, including governance structures and processes, independent expert reviews, implementing project principles ensuring quality projects and levels of co-financing, and maintaining flexibility to change routes if required.
Delivery through a third party – Regional Development Bank/Other Implementing Partner
1. Other regional development banks (and some humanitarian agencies) are beginning to strengthen their capabilities in financing disaster risk finance programmes. The only initiative to date is the ADRiFi proposal by the African Development Bank to provide sovereign insurance premium subsidies in Africa. As an example, the GRIF could direct funds through the African Development Bank’s ADRiFi programme which could support a country purchasing ARC coverage if the GRIF project principles are met.
2. The GRIF initiative should support, and not crowd-out, the development of such other initiatives, as a way to promote innovation and effectiveness, and avoid creating monopolies. As such, it is recommended that an option is left open to provide appropriate financing to such an initiative if, during the course of this programme, an appropriate initiative arises. A decision to support such as initiative will be based upon full due diligence of the capability, effectiveness and efficiency of the organisation, resulting in a proposal approved by the DFID Director of Economic Development. This decision should be based upon evidence that using another implementing partner will increase the overall effectiveness and efficiency of this programme in achieving its impacts.
3. It is noted that the World Bank GRIF MDTF has a facility to “transfer-out” funds to another implementing partner, such as a regional development bank. This would be an alternative to setting up a new, direct relationship with another implementing partner and has advantages in that the Bank completes basic fiduciary due diligence. When funds are transferred out from a World Bank trust fund, although the World Bank completes due diligence on the receiver, they bare no fiduciary or other responsibility for the funds, so DFID would still need to separately appraise the capability of the other implementing agency to deliver, complete adequate due diligence, and ensure appropriate governance is in place (as with direct financing above). Transfers-out incur an administrative fee, which make it more expensive than direct financing. Decisions to allow the GRIF MDTF to transfer-out will therefore be made by the DFID Director of Economic Development[57], based on evidence, as in the case of direct financing. Our recommendation is that transfers-out not be considered during the first year of GRIF unless a clear VFM case can be made.
  [57] or the DFID representative on the World Bank GRIF Steering Committee if more senior
Direct procurement through contracted supplier/third party
1. Direct procurement of activities, or procurement through a contracted supplier, is justified in circumstances where:
  1. There is a need to move in a faster and more agile way to drive new innovations or areas than can be achieved through the MDTF/SDTF and this is achievable through direct procurement or through the DFID-funded Centre for Global Disaster Protection.
  2. There is a need to fund additional advice, analytics or capacity building work through the Centre for Global Disaster Protection to complement GRIF projects, e.g. related to DFID country offices or need for impartial advice.
  3. Opportunity to link financing directly to a DFID bilateral programme, e.g. as in the case of the Kenya Hunger Safety Net Programme (see Box 2).
  4. Evidence that direct procurement can increase the overall effectiveness and efficiency of DFID’s funding to achieve the desired impacts.
2. We envisage that only a small portion of funds will flow though this channel, if any, and only after the inception year unless a clear VFM case can be made. Three potential procurement routes are foreseen:
  1. Direct procurement, using DFID standard procurement systems and follow DFID guidelines.
  2. Scaling-up the Centre for Global Disaster Protection. This is suitable for activities to scale-up advice and analytics and to test new innovations. Such activities fit with the mandate of the Centre. At the time of writing, the Centre is delivered by a private sector managing agent[58]. Scaling up the activities of the Centre would require amending the contract with this supplier or procuring a new one. Any amendment or new contract would need to be approved by the Centre SRO, the Board and Ministers and would follow DFID standard systems and guidelines. A full appraisal of this option will be developed during the first year of GRIF. To facilitate this link, the duration of the Centre programme would need an extended costed extension.
    [58] Centre for Global Disaster Protection Business Case, 2017
  3. Scaling up/linking to existing/new DFID bilateral programme. This would similarly follow DFID departmental approval processes and standard procurement systems and guidelines.
3. The decision criteria and processes to direct funding to these channels is outlined in the Management Case

Financial Case

Who are the recipients of all the proposed payments?
1. Of the total budget of £90m:
  1. At least £45m and up to £90m to the World Bank received by the GRIF multi-donor trust fund (MDTF) and organisations/recipient governments contracted/agreed under that.
  2. The minority received via one of three potential channels, and organisations (e.g. government, NGOs, research) contracted/agreed under those:
    1. The World Bank received by the DFID-World Bank Disaster Protection Program single donor trust fund (SDTF)
    2. Organisations directly procured by DFID or through its bilateral programmes, including the Centre for Global Disaster Protection.
    3. Another implementing partner, e.g. regional development bank
  3. This does not include financial aid to governments.
A preliminary delivery chain map was given in Figure 5 (Commercial Case).

Costs to be directly incurred by DFID/HMG
1. The total cost of the programme to DFID is £90m over seven years. This amount includes all implementing activities, such as monitoring and evaluation and administrative costs. The option for a programme-funded post is maintained and will be decided upon at key decision points, for example when we begin to work with new implementation partners. The DFID Private Sector Department budget will cover administrative costs of managing the programme on a day-to-day basis. All funds are ODA eligible.
2. The financial scale of the programme was determined after a period of consultation with the World Bank, the preliminary workplan for the Pilot Premium Financing Facility, ongoing/past projects and potential beneficiary countries and other agencies (see Box 1). The size and structure were set to produce a facility of sufficient size to meet its ambitious objectives, including helping to drive a shift in how disasters are financed to a more ex-ante approach and creating sufficient demand from countries. A smaller programme would not be able to achieve scale and disproportionately reduce impact.
3. The GRIF will link to and complement the existing Centre for Global Disaster Protection programme (£30m funded by the Prosperity Fund in 2017). For example, the Centre can align its technical assistance programme and investments in research, evaluation, data and analytics to the needs of the GRIF where this can increase impact and value for money of both initiatives (decisions/work plan to be overseen by the Centre Board and SRO as outlined in the Centre business case). It is foreseen that the Centre could provide independent external reviewers for GRIF projects to ensure quality, and the GRIF share data with the Centre to support its analytics and research.
How will it be funded: capital/programme/admin?
Funding will be all programme spending (RDEL). We envisage the schedule of disbursements to go beyond the current spending round (expires March 2021) and will comply with the smart rules accordingly.
Costs incurred by third party organisations
There is strong prospect of donor and Multilateral Development Bank co-investment in GRIF and its projects. Germany has already committed €115m to the GRIF. The GRIF is designed to co-finance projects with World Bank lending operations (leveraging up to 10 times or more, based on current pilot projects), as well as alongside investments countries’ own budgets. These significantly boost the impact of UK funding and ensure strong multilateral ownership.
Profile of expected costs
DFID/HMG will provide a total budget of £90m over seven years from early 2019 to December 2025. Table 6 gives an indicative spend profile for the DFID funds. The spend is expected to start slowly as projects are developed, peaking after two years once projects are fully implemented. This is likely to be fairly lumpy given that the GRIF is demand-led, but there are various indicators to enable this be managed proactively, such as annual workplans, progress reports of ongoing projects, and key decision point timings for projects. The total costs of this project will be fixed. The allocation of funds between different components and scope of individual activities will be reviewed on an annual basis to maximise impact.
FY	18/19*	19/20	20/21	21/22	22/23	23/24	24/25	25/26*
Expected total GRIF spend (£m)	1	7	11	17	19	19	11	5

Table 6: Indicative financial profile *N.B. A partial financial year.
How will you work to ensure accurate forecasting?
Forecasting will be undertaken by DFID using its own system based on the payment schedule supplied by the implementing partners. The Administrative Agreement with the World Bank will set out a schedule of payments and requirements on forecasting; this will be reviewed regularly, and the World Bank will inform DFID at least 2 months prior to any adjustments to the payment profile. Beyond this, for all activities, accurate forecasting will be managed by ensuring payments follow an agreed schedule defined by clear and time-bounded deliverables and costs. Payments schedules will be reviewed bi-annually and are monitored monthly and can be adjusted if necessary.
Disbursement mechanism
For any World Bank administered activities, funds will be paid in GBP into the World Bank trust fund(s). Disbursements will be made against firm commitments for the following six months as identified in the call for funds. Funding calls will be assessed on the basis of need, including spending progress and forecasts of future needs. The initial disbursement of funds will take place in accordance with Trust Fund administration arrangement. For directly procured activities, funds will be disbursed against invoices based on agreed terms of reference and milestones.
What is the assessment of financial risk and fraud?
The financial risk and risk of fraud is minimal. The World Bank operates procedures to mitigate these risks and has put in place due diligence procedures and checks for financial management and fiduciary risk that meet our (DFID’s) standards and norms. All contractors will be bound by WB operating procedures and beholden to their regulations on reporting any suspicion of financial misconduct. As in all programmes, a zero-tolerance approach is taken to fraud and corruption. There will be regular review as part of DFID’s annual review process and the programme may be independently reviewed by the Internal Audit Department. Implementing partners may be subject to a formal DFID audit assessment if deemed appropriate. If trust fund channels are not used, the risk remains minimal as procurement will be controlled and guided by DFID rules and processes.
How will expenditure be monitored, reported, and accounted for?
1. World Bank MDTF and SDTF: grant activities, commitments, disbursement and reporting will be routinely monitored through the Bank’s Trust Funds Donor Centre secure website. As per standard practice of the WB; the trust funds will provide to DFID, an annual ‘single audit’ report at an institutional level. The World Bank will be responsible for the relevant due diligence, selection, supervision and execution of the activities undertaken, and will report on progress as outlined in the Administrative Agreement. Any excess funds at the end of the programme will be returned in accordance with the Administration Agreement and World Bank Trust Fund policies.
2. For directly procured contracts: in accordance with the contractual provisions, funds will be disbursed in arrears on a quarterly basis on receipt of a valid invoice supported by a breakdown of expenditure that is in line with the overall budget set aside. In accordance with DFID’s standard contractual provisions, each invoice will be supported by a breakdown of the costs being claimed against each budget line in the contract and the Programme Manager will be responsible for ensuring due diligence in the disbursement of funds, and for taking any action deemed necessary. The implementing partner will submit annual audited accounts to DFID for each of the financial years covered by the project and they will show DFID funds as a separate item of income.
Are there any accounting considerations arising from the project?
As GRIF projects are approved and funds for TA and investments are required, the World Bank will call down funds on a six-monthly advanced basis.

Management Case

Management arrangements
1. The programme will be managed from the Disaster Risk Finance Team of DFID’s Private Sector Department (PSD).
2. The Senior Responsible Owner (SRO) will be an A2 advisor (0.5 FTE) and will have overall responsibility for ensuring the delivery of the project and coherence with DFID and x-HMG priorities. They will be supported as required by an A2 Economist. They will manage the relationship with implementing partners (e.g. the World Bank DRFIP team and GFDRR) and work closely with the Centre’s SRO to maintain strong alignment.
3. The programme manager (0.25 FTE B1) will be responsible for the programme and financial management. This will include: ensuring compliance with corporate processes for establishing the programme; leading on financial management of the project; ensuring that DFID funds are used for the correct purposes; ensuring that progress and financial reports are submitted by the implementing partner(s) as set out in the contractual agreement; corporate reporting; supporting the SRO on project communications.
Decision making on delivery channels
1. As discussed in the Appraisal Case and subsequent sections, the majority of the £90m funding will support activities of the World Bank GRIF multi-donor trust fund (MDTF) and alternative delivery channels can be used in circumstances where:
  1. There is a need to move in a faster and more agile way to drive new innovations or developments than can be achieved through the MDTF
  2. There is a need to support additional advice, analytics or capacity building
  3. There is an opportunity to link financing directly to a DFID bilateral programme
  4. There is a need to support building capacity/toolkit of other implementing partners
  5. There is evidence that an alternative delivery channel can increase the overall effectiveness and efficiency of DFIDs funding to achieving impacts.
2. The GRIF programme will have clear criteria and decision processes for utilising these alternative delivery channels, which aim to maximise effectiveness and efficiency of the programme and reduce risks. Preliminary decision criteria are captured in Figure 6 below and will be finalised during the inception phase, approved by the DFID Director of Economic Development and documented in the Delivery Plan. Decisions to utilise the alternative delivery channels will be made by the DFID Director of Economic Development, based on evidence on these criteria provided by the DFID SRO.
Expected phases of operation
1. The GRIF will have three phases of operation, including a 12-month inception phase at the beginning following the final approval of the business case. The second phase will run from around May/June 2020 to May/June 2023, then the third phase to the end date in December 2026.
2. The end of the inception year will coincide with the first Annual Review. At this time, based on evidence from the Annual Review and other sources, the DFID Director of Economic Development will take a decision on the appropriate allocation of funds between delivery channels for the subsequent phase. New decisions on delivery channels can also be made within a phase if need arises.
Exit strategy
The GRIF has a natural exit strategy/wind-down strategy through projects with time-bound premium financing. In the longer-term, its mission is to develop and test new instruments and approaches that, if successful, could be integrated into core operations of the MDBs, or related organisations (e.g. global climate finance architecture). Each project funded by GRIF is assessed for sustainability and exit strategy.

Figure 6: Preliminary criteria for managing the flows of funds through the three delivery channels. Impact and value for money (vfm) here are against the Theory of Change (ToC) and indicators (Table 4).

Overall programme management/governance
1. Figure 7 gives a preliminary governance structure to be finalised during the inception year.
2. The governance of the World Bank GRIF MDTF is detailed in Annex A. Given the scale and ambition of this MDTF, a Director General/Director level Steering Committee has been established for the MDTF, with representatives from donors and the World Bank, and a secretariat provided by the GFDRR. The DFID SRO will be present at Steering Committee meetings as an observer and will brief, advise and support the DFID representative. The Steering Committee will review progress, set the strategic direction of activities and approve/make adjustments to key documents including the Scoping/Work Plan and Operations Manual. The Operations Manual (Annex A) is the key document outlining the operational procedures of the Trust Fund, including the principles and project approvals processes. The Steering Committee will meet annually but biannually in the first year. It will have responsibility for ensuring value for money, robust M&E and reporting/accountability. DFID will have rights of audit and evaluation.

Figure 7: Preliminary programme governance structure
1. Between Steering Committee meetings, the DFID SRO will be the main day-to-day manager and contact point but will escalate to the DFID Steering Committee representative where it is necessarily to do so (e.g. emerging risks).
2. In line with normal Trust Fund practices, DFID (and other donors) play a role in setting and refining the operating framework of the GRIF MDTF (laid out in the Operations Manual) and will endorse the annual scoping plan. The development and approval of individual projects that move ahead under the scoping plan will be managed by the Secretariat and Technical Manager in line with the principles and procedures laid out in the Operations Manual. Projects that move towards implementation will be presented in a Project Concept Notes to the SC for approval. Once approved the Technical Committee, led by the Technical Manager, and including donor appointed experts (1 per donor) will appraise the project against the principles, as laid out in the Operations Manual (Annex A). The Technical Committee will also include focal points from relevant WB Global Practices and Units, who will represent the collective ideas and interests of their respective group. Their role includes enhancing overall technical quality, providing advice on how the project can best meet the GRIF principles and ensuring M&E is well integrated into projects. All project proposals will be reviewed by an external reviewer nominated by DFID who will provide impartial non-binding feedback on how well the project meets the key principles laid out in the Operations Manual. This external review will be shared openly and transparently with donors as part of periodic reporting. Issues with projects will be raised and addressed at Steering Committee meetings.
3. Funding using alternative delivery channels will utilise the relevant governance arrangements. For example, any funds disbursed through the SDTF, will come under the oversight of the SDTF Steering Group/Centre Board. The SROs of GRIF and the SDTF/Centre for Global Disaster Protection will work together to ensure coherence.
4. The GRIF will become a member of the Program Alliance of the InsuResilience Global Partnership. This is a voluntary collaboration between programmes that aims to create more coherent support for countries, knowledge sharing and coordination. A condition of the GRIF being part of this group (agreed between DFID, Germany and the World Bank[59]), is that the GRIF will not have any real or perceived accountability to the Alliance, the InsuResilience Global Partnership or its High Level Consultative Group. The DFID SRO will monitor this and take actions to reduce risks as required.
  [59] Agreement detailed in the Collaboration Agreement of the Program Alliance
5. The GRIF will not establish its own Expert Advisory Group, however it will have the ability to draw upon the advisory groups/high-level consultative group of the InsuResilience Global Partnership and the Centre as required. There will be no formal reporting requirements to these groups, but advice can be sought on an ad-hoc basis. The DFID SRO will also establish/participate in a working group within DFID/HMG to ensure coordination with other related initiatives and alignment with DFID/UK policy.
What are the risks and how would these be managed?
The overall risk to the success of the programme is rated as moderate, see Table 7.

Risk	Likelihood	Impact	Mitigation Options	Residual Risk
Politics of premium financing external to GRIF causing a reduction in global standards and reduced GRIF impact	Medium-High	Medium	Utilise bilateral and multilateral relationships and forums to provide global standards	Moderate
Donor/political interference with GRIF projects	Medium	High	Ensure governance structure promotes good multilateralism	Minor
Insufficient buy-in from WB at senior and operational levels to achieve full impact (including not seen as WB mechanism/linked to GCRP)	Medium	High	Ensure good alignment between GRIF and GCRP and appropriate governance structures in place	Minor
WB insufficient technical capacity to deliver quality projects at scale	Medium	High	Push for hiring of additional technical staff and use of the Centre	Moderate
Limited agility and flexibility in responding to client needs	Low	High	Ensure adequate technical capacity and buy-in from donors	Minor
Limited learning achieved and implemented into practice	Medium	High	Push for investment in open, transparent monitoring, evaluation and learning processes	Moderate
DFID becomes a smaller donor and loses influence on strategic direction	High	High	Ensure governance provides adequate influence for DFID	Minor
Lower than expected pipeline/disbursement risks	High (particularly initially)	High	Allow for slow start in budgeting. Utilise bilateral relationships to promote	Moderate
Misaligned Steering Committee member interests lead to lower impact, and greater risks in terms of meeting DFID objectives	Medium	High	Ensure governance structure promotes good multilateralism. Develop strong bilateral relationships with other donors to align views	Minor
Reputational risks and/or reduced impact due to poor quality projects	Medium	High	Ensure good application/governance of operating principles. Promote all SC to push for quality not quantity. Use the Centre for Disaster Protection as expert reviewer of project proposals.	Moderate
Risks of creating distortions or perverse incentives through poor use of subsidies	Medium	High	Ensure good application/governance of operating principles. Promote all SC to push for quality not quantity.	Minor
Risks of crowding out the private market or other initiatives like regional pools, or conversely implicit/explicit biased or preferential access to certain market players	Low-Medium	High	Ensure principles around how to engage the private sector/pools and project risk analyses/principles to crowd-in.	Minor
DFID technical capacity to manage intervention well declines over time	Low	Medium	Role for the Centre for Global Disaster Protection in providing technical expertise. Good initial programme design.	Minor
Duplication/reducing the impact of the Centre for Global Disaster Protection	Low-Medium	Medium (on the Centre)	Monitor and proactively adjust work plans as needed.	Minor
Failure to meet objective of integrating into multilaterals	Medium-High	High	This is an ambitious objective but success more likely by using bilateral and multilateral dialogue and aligning with GCRP and other multilateral mechanisms.	Moderate
No clear exit strategy without significant loss of impact.	Medium-High	Medium	Design in exit strategy from the start and ensure clear in the narrative that GRIF about testing and learning not a permanent fixture within the system	Moderate

Table 7: Preliminary risk matrix
Partnership principles
Partnership principles are an important part of the decision-making process for DFID’s programmes where direct bilateral development assistance is provided to a priority country. As the final structure and funding flows used by the GRIF are flexible, a flexible approach is required. The SRO will review and manage the GRIF’s approach to applying and assessing the partnership principles as required.
How will progress and results be monitored, measured and evaluated?
1. The GRIF SRO has, and will continue to, work closely with the Private Sector Department’s (PSD) A1 Senior Evaluation Adviser and the A2 Evaluation Adviser to ensure that GRIF progress and results will be monitored, measured and evaluated most effectively. The advisers have fed in to this business case and will be actively involved throughout the programme.
2. Progress will be monitored against the theory of change and logframe which will both be finalised during the inception year. Results and progress will be monitored through the formal Steering Committee meetings (e.g. of GRIF MDTF and Centre’s SDTF), quarterly update meetings between the World Bank TTL and the SRO, and the annual progress reports. These will feed into the DFID annual review process (led by the DFID SRO) and the new Economic Development and International scorecard disaster risk financing indicators. The scorecard is updated biannually and reviewed and signed of at DG level.
3. Collectively, DFID’s disaster risk financing programmes have been developing a standardised set of indicators to allow aggregation, scrutiny and comparative analysis across programmes. The GRIF will align and fit with these indicators.
4. The PSD evaluation advisors are developing an evaluation strategy across the Private Sector Department. Forming part of this is an M&E strategy covering disaster risk financing programmes, including the Centre for Global Disaster Protection and the Africa Risk Capacity programmes. The strategy aims to better align learning on the processes and performance of disaster risk financing and insurance related interventions. The GRIF M&E will align with this work as the strategy is developed.
5. Early results from the PSD M&E strategy work have highlighted that there are multiple evaluations in progress or planned this space, including the 10-year ARC evaluation which is currently in Year 3, and the Centre’s Prosperity Fund led evaluation that is underway.
6. The ongoing (and currently being redesigned) ARC evaluation is expected to focus on key questions around the timeliness of risk financing payouts (vs. humanitarian aid), and the effectiveness of capacity building in influencing governments to develop and implement disaster risk financing strategies. The ongoing Centre evaluation will focus on the value for money of disaster risk financing interventions and will have a particular focus on gender issues. There are also plans for the Centre to map out a range of evaluation questions for disaster risk financing. In addition, the ARC evaluation is expected to complete a full evidence review of the area of disaster risk financing, due for completion in 2019.
7. For the GRIF, the World Bank have also committed to developing a programme of multi-stage, independent evaluations of GRIF projects (see Annex A). This work is currently being developed and will be closely monitored by the GRIF SRO.
8. Given this context of ongoing work and evolving landscapes, there are opportunities to enhance VFM and ensure clear alignment and complementarity of DFID’s M&E strategy for the GRIF. During the inception year, the DFID SRO and the PSD Evaluation Advisers will take stock of the evolving landscape and ongoing work and develop a M&E strategy to ensure that GRIF compliments the development of a robust evidence base without duplication or overlap. It is envisaged that any questions outstanding that the GRIF should address would, in the first instance, be designed into the WB GRIF team’s evaluations.