## Annual Review 2024/25

Title: Securing global wheat crops for food and nutritional security – in partnership with the Gates Foundation (GF)
Programme Value £ (full life): £15.2m (initially £16m, reduced by £800,000 in UK ODA prioritisation in 2020)		Review date: 12 March 2025
Programme Code: 300755	AMP start date: 12 December 2019	AMP end date: 30 September 2025 (a no-cost extension was approved in March 2025)

Summary of Programme Performance
Year	2020	2021	2022	2023/24	24/25
Overall Output Score	A	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.fcdo.gov.uk/iati_documents/51484648.odt
DevTracker Link to results framework:	http://iati.fcdo.gov.uk/iati_documents/58086726.xlsx

A. SUMMARY AND OVERVIEW
Description of programme

Wheat is grown in 128 countries around the world. 2.5 billion people in 89 countries depend on wheat as a staple food crop. It currently provides 20% of the protein and calories consumed worldwide. More than half of global wheat production comes from 80 million developing country wheat farmers, the majority of whom are smallholders experiencing or at risk of poverty.

This project addresses two key issues that relate to the future production of wheat. Firstly, that climate change and the evolution of increasingly virulent diseases, particularly fungal disease, represent serious threats to the future of wheat farming and specifically the increase in productivity needed to meet rising demand for cereal crops. Secondly that a lack of essential vitamins and minerals such as Vitamin A, iron and zinc, affects 2 billion people worldwide mostly in developing countries. The Accelerating Genetic Gains (AGG) project component will invest in the development of new crop varieties that are more productive and resistant to biotic and abiotic stress, the Zinc (Zn) mainstreaming component will integrate Zn biofortification with the CGIAR CIMMYT global wheat programme breeding pipelines, ensuring that by 2030 all new wheat varieties released have enhanced zinc content.
[note] International Maize and Wheat Improvement Centre

The project will deliver three Outputs:
Output 1: Improved wheat varieties delivered to meet demand sustainably in the face of climate, pest and disease risks.
Output 2: Strengthened global wheat disease surveillance
Output 3: Zinc (and by extension, iron) biofortification of CGIAR-CIMMYT wheat
[note] CIMMYT is the wheat and maize research centre of the international research organisation, CGIAR. CIMMYT is based in Mexico but works globally and is one of 15 CGIAR research centres.

Summary supporting narrative for the overall score in this review

This programme has scored an A in this reporting period, with very significant evidence of results and impacts being delivered in focal countries.

Key highlights include:
- Improved wheat varieties released and adopted in 6 focus countries: Between 2020 and 2024, partner countries in South Asia and East Africa (Kenya, Ethiopia, Bangladesh, India, Pakistan and Nepal) released more than 103 varieties of wheat with improved agronomic traits, climate resilience, disease resistance, derived from CIMMYT germplasm.
- Early indications of significant genetic gains: Early estimates by CIMMYT’s Quantitative Genetics team found yield gains under the AGG project of approximately 1.5%, while annual Zinc gain is about 2%.
- Disease advisory support in Ethiopia: Ethiopia remained a focus country for surveillance, with over 1,300 fields surveyed despite ongoing and increasing challenges due to insecurity. Accurate pre-season warnings were provided, followed by accurate in-season advisories to enable preparedness, and implement control measures. The continual threat from wheat rusts in Ethiopia continues to make it a focus for early warning and awareness. The predictions of high diseases pressure for stem rust, yellow rust and fusarium head blight (FHB) proved accurate and subsequent updated advisories during the season also gave accurate risk forecast information. Twenty advisories were developed and disseminated at scale in Ethiopia in 2023-24.
- Wheat varieties released in key countries:
  - Bangladesh Wheat and Maize Research Institute (BWMRI) leads wheat blast research and has evaluated 460 new high-yielding, climate-resilient stage 2 wheat lines annually in target population of environments (TPE) trials, while an additional 170 new high Zn elite lines were evaluated across locations.
  - Indian farmers achieved a record 8 tons/ha using CIMMYT-derived varieties. Three of the top wheat varieties (DWB187, 222, 303) are either directly released CIMMYT varieties or include CIMMYT germplasm.
  - Pakistan released 31 CIMMYT-related wheat varieties since 2021, including five zinc-biofortified varieties, benefiting 97 million consumers.
  - Over 89% of wheat area in Ethiopia is planted with CIMMYT-derived varieties, improving yields and rust resistance.
- High zinc varieties adopted in South Asia: Recent estimates show that high Zn varieties are now grown on over 9 million hectares in South Asia:
  - ‘Akbar-19’ is the most successful wheat variety in Pakistan, occupying more than 42% of the national wheat area. 15 million tons of Zn wheat have been produced in Pakistan, benefiting 97 million wheat consumers, where there are highest rates of per capita wheat consumption in the world, continuing to positively impact the health and quality of life of millions.
  - In Bangladesh, about 34% of wheat area is occupied by a CIMMYT-derived zinc-biofortified, wheat blast disease resistant variety.
  - In Nepal, five high-zinc varieties are growing on 25% of the wheat area in the country.

Major lessons and recommendations for the year ahead
No Cost Extension to support a final phase: This programme was due to close in March 2025. A NCE was approved in this reporting period to provide a final phase of funding to CIMMYT in 2025. This funding will be crucial for expanding and building upon the successes of the programme to date to enhance collaborative research efforts to implement breeding programme modernisations with partners, strengthen regional networks, and support capacity-strengthening in wheat breeding programs across South Asia and Eastern Africa, with a focus on integrating gender considerations in the target product profiles (TPP). This phase will support the co-design and logistics and capacity strengthening for implementing a network for the shared testing of early generation lines across diverse environments, with robust communities of practice that support the network partners to participate and benefit fully. This proposed approach supports social and gender equity ambitions, while building climate resilience of wheat farmers and nutrition security of consumers.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change for this programme is presented visually on page 28 of the business case (2019). The theory of change is supplemented by detailed GF results frameworks for the AGG (Advancing Genetic Gains) and zinc mainstreaming initiatives, developed by CGIAR-CIMMYT with GF during development of the project proposals in 2019 and 2020. CGIAR-CIMMYT submits an annual progress report for each project against these results frameworks to GF.

There has been no material change to the assumptions or evidence underpinning the programme’s theory of change during this year of the programme.

The budget of the project was adjusted downwards as it as part of the ODA prioritisation exercise, and then again as part of the business planning exercise in light of the UK ODA reduction. However, overall, the assumptions and results pathways in the theory of change remain valid.

In addition, the programme delivers on the following priorities:
Gender: This programme is compliant with the 2014 Gender Equality Act. FCDO and GF ensured that gender inclusive approaches were fully integrated in CGIAR-CIMMYT’s proposals for the AGG and zinc mainstreaming initiatives. CGIAR-CIMMYT is employing improved breeding decision-making tools to ensure that all wheat varieties developed through this programme will meet the needs and preferences of both women and men. The NCE phase will have a particular focus on developing target product profiles for women.
- Nutrition: This programme delivers against nutrition priorities, particularly through output 3, by increasing zinc (and by extension iron) in wheat.
- ICF/climate: This programme delivers against climate and ICF commitments. The project is actively aiming to improve climate resilience in wheat. This programme will report against ICF KPIs 2 and 15.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track to deliver its expected outcomes and impact. It has made good progress against the outputs and all three outputs are on track. As noted above, the NCE will allow FCDO and GF to support a final phase of support under this programme to build connections with national partners. FCDO and GF will work together to agree and design future support to global wheat breeding and disease control.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

As described in the programme business case, global demand for wheat is increasing against a backdrop of challenges to wheat production, including climate change, land shortages and wheat disease threats. These multiple challenges indicate an urgent need for investment to boost wheat productivity, to tackle emerging supply-side risks posed by climate change, pests and diseases, and resource scarcity, and to promote the stability of food prices on global markets.

At the same time, the combination of persistent undernutrition and heavy reliance on wheat among the poorest in many low-income countries indicates a need and an opportunity to improve the nutritional content of wheat, to contribute to better nutritional outcomes that can enable individual people and countries to reach their full economic potential.

This programme remains a critical FCDO investment to tackle these urgent needs and opportunities and continues to represent strong value for money for the UK government. In addition to co-funding, GF provides significant technical and grant management expertise, without charging any management fee or overhead to FCDO.

The NCE provides an important opportunity to support global food and nutrition security by developing:
- Strengthened Collaborative Networks
- Improved Capacities of Network Partners
- Modernise Breeding Programs
- Enhanced Nutritional Quality
- Increased Genetic Gain of wheat varieties

The NCE will also allow FCDO and GF to responsibly manage the closure of this project and facilitate the design of future work with GF.

## C. DETAILED OUTPUT SCORING

Output Title	Improved wheat varieties delivered to meet demand sustainably in the face of climate, pest and disease risks
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Improved pipeline of disease-resistant, higher-yielding wheat varieties, developed, tested and disseminated to smallholders	Accelerating Genetic Gain (AGG) project on track with milestones in GF results tracker	Exceeded (see 1.1.1 and 1.1.2): / 103 varieties released in target countries / AGG: 1.5% genetic gain (estimated) / Zinc: 2% (estimated)
Modernisation of the CGIAR-CIMMYT wheat programme	Accelerating Genetic Gain (AGG) project on track with milestones in GF results tracker relating to the Excellence in Breeding CGIAR initiative	On track (see 1.2.1 and 1.2.2): / Phenotyping platforms are operational / Enterprise Breeding System (EBS) is functional, used by CGIAR and on track to be taken up by NARS partners

This Output scores an A in this annual review. Substantial progress has been made against all targets. Targets under Output 1.1 have been exceeded and Output 1.2 is on track to be completed once the EBS is fully rolled out and adopted by NARS partners.

The two overall targets for Output 1.1 over the course of project are:

    1. The development and release of 60–80 improved wheat varieties

CIMMYT led wheat breeding programmes delivered a number of new varietal options to farmers by working closely with the NARS partners under the International Wheat Improvement Network (IWIN). Between 2020 and 2024, AGG partner countries in South Asia and East Africa (Kenya, Ethiopia, Bangladesh, India, Pakistan and Nepal) released more than 103 varieties of wheat with improved agronomic traits, climate resilience, disease resistance, derived from CIMMYT germplasm. This is an important example of success that will support global food security.

    1. A doubling of annual genetic gain from 0.7–1.5%
Significant progress was made towards doubling the rate of genetic gains in CIMMYT wheat breeding pipelines. During 2020-2024, accelerated breeding methods coupled with advances in genomics and phenomics techniques were implemented across the breeding pipelines. This included optimising the breeding strategy (using data-driven parental recycling and stage 2 lines (S2) testing) across target environments for yield potential, climate resilience, disease resistance and high grain Zn. Our support through this project supported the continuous modernisation and optimisation of the wider wheat breeding programme at CIMMYT, enhancing its capacity to deliver high-impact products.

An efficient and low-cost 3-year breeding cycle has been optimised using the screenhouse facility and field advancements in Mexico, laying the groundwork for faster varietal turnover. Through FCDO support to AGG and “Zinc Mainstreaming” projects, partners in Bangladesh, India, Nepal, Pakistan, and Ethiopia receive improved lines, many with increased zinc content, deriving from a programme that recycles elite germplasm every four years, instead of seven years – a 40% acceleration in the pathway to benefit farmers. Early estimates by CIMMYT’s Quantitative Genetics team found yield gains under the AGG project of approximately 1.5%, while annual Zinc gain is about 2%.

The two overall targets for Output 1.2 over the course of project are:

    1. Operationalise phenotyping platforms in Kenya, Ethiopia, and Bangladesh.
The phenotyping platforms in Kenya, Ethiopia and Bangladesh are fully functional. About 1,000 Stage 2 spring bread wheat breeding lines were evaluated for stem rust and yellow rusts at EIAR, Ethiopia, with 1,000 Stage 2 & 5,000 Stage 1 lines screened for stem rust and yellow rust at Njoro, Kenya (KALRO). These lines are rigorously evaluated for resistance to stem rust and yellow rust under high disease pressure. About 1,000 Stage 2 lines have been screened for wheat blast resistance in Bangladesh, which is a hotspot for the disease in South Asia. The resulting disease resistance data is being used in breeding and advancement decisions leading to the selection of lines for inclusion in recombination blocks and various IWIN nurseries.

    1. Operationalise a breeding system database which is used by CGIAR and National Agricultural Research Services (NARS).
CIMMYT wheat breeding pipelines continued to advance in the implementation of software and practices to enhance the effectiveness of wheat breeding efforts. The Enterprise Breeding System (EBS) has been routinely used for pedigree, field trial, nursery, and phenotypic data management in the CIMMYT wheat breeding program. The increasing usage of the EBS for storing high value historical data and newly generated germplasm, phenotypic, and genotypic data is evident in the database statistics. EBS will be rolled out to NARS partners, accompanied by training and support, for use and adoption in the near future.

Output Title	Strengthened global wheat disease surveillance
Output number:		2	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Global participation in wheat disease surveillance, coordinated by CGIAR-CIMMYT	Accelerating Genetic Gain (AGG) project on track with global wheat disease surveillance milestones in GF results tracker	On Track (see 2.1.1 and 2.1.2): / Surveys undertaken in 12 countries with more expansion planned / MARPLE system deployed in Ethiopia and Kenya laboratories
Regular alerts sent to smallholders, extension workers and other stakeholders, enabling preventative action to avoid outbreaks of wheat diseases	Accelerating Genetic Gain (AGG) project on track with early warning system alerts milestones in GF results tracker	On Track (see 2.2.1 and 2.2.2): / 20 advisories were developed and disseminated at scale in Ethiopia in 2023-24. / Varieties being developed and tested to respond to new threats in Nepal.

This output has scored an A in this annual review. The project has made significant progress against the targets under this output. Wheat pathogens continue to evolve rapidly, and new virulent races are moving between regions with increasing frequency. Sustained global surveillance and monitoring efforts that are linked to wheat breeding for disease resistance and disease management are increasingly important. Real-time surveillance and epidemiological modelling can dramatically improve responses to crop diseases. This Output builds upon and expands the surveillance successes achieved with previous FCDO and GF support. The primary focus of the surveillance system will continue to be wheat stem rust and wheat stripe rust (the most significant diseases of wheat), with added integration of data on other diseases including leaf rust, Septoria and fusarium head blight.

The two overall targets for Output 2.1 over the course of project are:

    1. To update databases with disease survey data from at least 15 countries each year.
Rust surveys were undertaken, and data received from 12 countries, with plans in place for further expansion. A total of 8657 fields were surveyed. The total number of geo-referenced survey records held in the wheat rust toolbox database now exceeds 70,000. Surveys were undertaken in East Africa (Ethiopia, Kenya, Tanzania, Uganda), North Africa (Morocco, Tunisia), Middle East / Central Asia (Lebanon, Turkey), South Asia (Bangladesh, Nepal, Pakistan) and South America (Uruguay). All data has been uploaded into the wheat rust toolbox database.

    1. To improve capacity at national rust laboratories in Ethiopia and Kenya.
MARPLE (Mobile and Real-time Plant disease) is the first operational system in the world using nanopore sequencing for rapid diagnostics and surveillance of complex fungal pathogens in situ. Generating results in 48 hours of field sampling, this new digital diagnostic strategy is leading to revolutionary changes in plant disease diagnostics. Rapid strain level diagnostics are essential to quickly find new emergent strains and guide appropriate control measures. This toolkit has been deployed to national rust laboratories in Ethiopia and Kenya.

The two overall targets for Output 2.2 over the course of project are:

    1. Information on risks from rusts and other diseases to farmers to prevent and mitigate disease outbreaks.

Through FCDO support the wheat rust surveillance and monitoring continues across large geographical areas, with a priority focus on East Africa and South Asia. Awareness raising in Ethiopia by the Ethiopian Institute of Agricultural Research (EIAR) and the Ethiopian Agricultural Transformation Institute (ATI), supported by CIMMYT, focused on the rising threat posed by fusarium head blight (FHB), with over 800 people in key sectors reached by the training programme. Ethiopia remained a focus country for surveillance, with over 1,300 fields surveyed despite on-going and increasing challenges due to insecurity. Accurate pre-season warnings were provided, followed by accurate in-season advisories to enable preparedness, and implement control measures. Twenty advisories were developed and disseminated at scale in Ethiopia in 2023-24.

Despite severe disease pressure, evidence suggests that effective control of wheat rusts has been achieved in some (but not all) key wheat areas in 2023/24. Without the early warning and advisory system, it is believed outcomes would have been much worse in Ethiopia in the 2024 season.

The highly virulent, yellow rust race PstS16 now dominates in Ethiopia and, as predicted, it has spread in East Africa, being confirmed in Uganda and Kenya with increasing frequency. The same race has now also been confirmed in Nepal. High levels of yellow rust are currently being observed in western Nepal (2024) and monitoring is in progress to check if PstS16 is the causal race. Stem rust Ug99 races continue to dominate in East Africa and further spread of Ug99 race TTKTT has been confirmed in Nepal (2024).

    1. Improving turnover of varieties to farmers where susceptibility risks are identified.

Successful global wheat disease surveillance and monitoring has resulted in early detection of wheat stem rust Ug99 in Nepal. A combination of field surveys and sampling by Nepal’s National Plant Pathology Research Centre (NPPRC) and National Wheat Research Program (NWRP), supported by disease diagnostics at the Global Rust Reference Center (GRRC), Denmark, resulted in confirmed detection of the Ug99 strain named TTKTT. Confirmed results were obtained from two field samples collected in early November 2023 from off-season summer wheat crops in Dolakha district, Nepal. Although the current risk of stem rust outbreaks is low, detection of the Ug99 race TTKTT in Nepal is a clear indicator of the threat posed to wheat production in South Asia by the incursion of virulent stem rust races or other plant diseases of concern. Hence, CIMMYT in partnership with NARS in Nepal stimulated screening of current major wheat varieties and candidate varieties for Ug99 races for resistance in Njoro, Kenya in 2024. About half of the varieties showed good levels of resistance to Ug99 stem rust in Kenya. Promising resistant varieties are being promoted among farmers and the resistant candidate lines will be advanced to variety-release testing in Nepal.

Output Title	Zinc (and by extension, iron) biofortification of CGIAR-CIMMYT wheat
Output number:		3	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Zinc ‘mainstreamed’ into CGIAR-CIMMYT wheat breeding	Zinc mainstreaming project on track with milestones in GF results tracker	Met: / 25 zinc-enriched varieties released in South Asia and Ethiopia / Varieties contain sufficient zinc content for consumers

This Output has scored an A in this annual review. This project has made significant progress against these milestones for Output 3 and has met targets. The objective of this Output is to enhance the zinc content (and by extension, iron – as there is a correlation between increased zinc and increased iron in wheat) of all new wheat varieties released by CGIAR-CIMMYT. This will contribute to improved nutritional outcomes for the 2.5 billion people globally who are reliant on wheat.

The two overall targets for Output 3 over the course of project are:

  1. To develop and release 20 zinc-enriched wheat varieties in Bangladesh, Nepal, Pakistan, India and Ethiopia

More than 25 CIMMYT-derived high-yielding, high zinc varieties have been released in South Asia between 2020 and 2024, with Ethiopia releasing its first high Zn variety (MELKA) in 2024. These varieties reach farmers faster through established public-private partnerships. Recent estimates show that high Zn varieties are now grown on over 9 million hectares in South Asia:
- ‘Akbar-19’ is the most successful wheat variety in Pakistan, occupying more than 42% of the national wheat area. 15 million tons of Zn wheat have been produced in Pakistan, benefiting 97 million wheat consumers, where there are highest rates of per capita wheat consumption in the world, continuing to positively impact the health and quality of life of millions.
- In Bangladesh, about 34% of wheat area is occupied by BARI Gom 33, a CIMMYT-derived zinc-biofortified, wheat blast disease resistant variety.
- In Nepal, five high-zinc varieties are growing on 25% of the wheat area in the country.

  1. To ensure that zinc-enriched varieties released will contain sufficient zinc content to provide up to 50% of the daily zinc requirement of consumers reliant on wheat as their main staple

The varieties highlighted above achieve grain yields at least as high as checks and have 8–10 ppm (25–40%) more Zn in the grain compared to conventional varieties released in the same regions (Govindan et al., 2022). Studies have shown that these varieties provide up to 50% of the daily zinc requirements of consumers reliant on wheat as their main staple (Lowe et al., 2022).

Mainstreaming of enhanced zinc (Zn) concentration continued in all bread wheat breeding pipelines by using parents with high Zn and high yield from extensive field phenotyping of Stage 1 and 2 yield trial lines. CIMMYT has also extended the routine measurement of grain zinc concentration to include samples from trials grown in multiple locations in target countries, including Pakistan, India, and others. CIMMYT bread wheat breeding now includes increased Zn as a “routine” trait, and the average concentration of Zn in CIMMYT’s elite wheat lines has increased from 40 to 45 parts per million (ppm or mg/kg) over the past 5 years while also increasing grain yield and other farmer-preferred traits.

CIMMYT’s breeding schemes are faster than ever, using facilities (for example, rapid generation advancement screenhouses in Toluca, near Mexico City) to reduce the time needed to develop new varieties. Accelerated breeding means that new cohorts of improved, high-zinc wheat lines are available in approximately half the time. Accelerated breeding schemes mean that partner breeding programmes in Bangladesh, India, Nepal, Pakistan, Ethiopia, and globally now have earlier access to improved, high-zinc lines for use in their own breeding and product development efforts.

## D: VALUE FOR MONEY

Key cost drivers and performance

The key cost drivers of this project are personnel and sub-awards to grantees. The project reports annually to FCDO through Annual Audited Account reports as well as through financial reporting.

For all projects within this portfolio, FCDO funding is channelled through the Gates Foundation to grantees. This funding arrangement is governed by the Gates Foundation-FCDO Collaboration Framework (2016-2026). The Gates Foundation directly manages all grantees in the portfolio. the Gates Foundation issues grant agreements on behalf of both the Gates Foundation and FCDO, manages the reporting and payment schedules, and shares progress reports, financial reports and annual audited statements received from grantees with FCDO. This represents significant value for money for FCDO, as it leverages the technical and programmatic capacity of the Foundation, as well as project co-investments.

The Gates Foundation covers the significant administrative and overhead costs of running these projects, without charging any management fee or overhead to FCDO. From an economy of inputs perspective, this partnership represents extremely high value for money. FCDO co-funds and steers the direction of a broad portfolio of R&D projects with strong potential for development impact, while maintaining very low transaction costs of managing the research. Since May 2018, FCDO has seconded a staff member into the Gates Foundation to coordinate and support the partnership, with a new secondee taking over the role in March 2021 until June 2025. This role has significantly strengthened the efficiency, effectiveness and success of the partnership and discussions are ongoing about renewing this role beyond 2025.

VfM performance compared to the original VfM proposition in the business case

4 Es	Summary of performance
Economy	GF manages the grant portfolio directly and does not charge any management fee or overhead to FCDO. This is a key component of this programme’s VFM proposition. FCDO’s co-funding contribution of USD$10m to AGG and USD$7m to zinc mainstreaming leverages GF co-funding of USD$56.9m and USD$5m, respectively. This is in addition to the significant in-kind contribution made by GF through their management of the procurement process and handling all grant management.
Efficiency	The partnership between FCDO and GF has become increasingly efficient, in part because the two funders have now been working together on research in the agriculture sector for a number of years. / The establishment of the FCDO secondment significantly strengthened the partnership between the two funders, and facilitates closer involvement from FCDO in the design of this programme.
Effectiveness	The programme is on track to deliver effectively on the goals described in the business case.
Equity	CGIAR-CIMMYT is employing improved breeding decision-making tools to ensure that all wheat varieties developed through this programme will meet the needs and preferences of both women and men. / This portfolio does not have an explicit focus on disability and other aspects of social inclusion.
Cost-effectiveness	There is significant value for money in this collaboration between two of the major funders of research in the agricultural research. In this programme, FCDO and GF are pooling resources, technical expertise and influence in the CGIAR system to maximise the impact of investments in CGIAR-CIMMYT wheat.

Assessment of whether the programme continues to represent value for money
This programme continues to represent a strong case for value for money for FCDO. It has delivered strong results. The NCE provides the opportunity to expand and build upon the successes of the programme to date to enhance collaborative research efforts to implement breeding programme modernisations with partners, strengthen regional networks, and support capacity-strengthening in wheat breeding programs across South Asia and Eastern Africa. The programme continues to deliver important progress for global food security and nutrition.

E: RISK

Overview of risk management

Overall, the risk rating is moderate. With the majority of outputs being achieved, and many activities closing out over the coming months, the main focus of the year ahead will be the supplemental support to deliver breeding programme modernisations, strengthen regional networks, and support capacity-strengthening. FCDO and the Gates Foundation will maintain close oversight of this work and ensure responsible close-out of this programme in 2026.

Risk category	Gross risk description	Mitigation strategy	Residual risk rating	Risk rating changed since business case was approved?	Likely trajectory of risk severity (to 2026)
Delivery	Slowing pipeline of co-funded work, due to FCDO budget uncertainty.	The FCDO programme teams is working closely with GF to design new work to follow on from this programme. The no-cost extension will provide time and resources to manage this transition.	Moderate	No
Delivery	The conflict in Ethiopia created some challenges and delays for the AGG and zinc mainstreaming initiatives.	Conflict in Ethiopia remains a risk for the country, but CIMMYT continued to manage and mitigate the challenges. Many activities are now completed despite the instability.	Moderate	No
Delivery	This research programme is highly technical and challenging, requiring CGIAR-CIMMYT to make significant improvements to modernise and accelerate breeding operations within the CGIAR and in the national agricultural research systems (NARS) in partner countries. There is a risk that, as a result, the pathway to impact and adoption of improved wheat varieties is overlooked, or not given consistent attention. The effect of this would be that this programme produces highly relevant technologies and products, but fails to get these into use by the intended beneficiaries.	Uptake and product adoption are challenging objectives for R&D work. However, GF and FCDO continue to work closely with CIMMYT and with the CGIAR system as a whole to engender sustained focus on pathways to impact at all stages of the research and development process, to resource adequately the partnerships between CIMMYT and NARS partners, and to track progress and document lessons throughout the projects. This progress is significantly strengthened by FCDO’s wider support to the CGIAR where breeding efforts are driven by performance and designed with closer links to end user demands.	Moderate	No
Innovation / Intellectual	This is an ambitious programme of research, aiming to increase the rate of genetic gain in wheat, mainstream micronutrient biofortification in all CGIAR wheat breeding lines, and expand a global surveillance network to track all significant diseases of wheat. There is a risk that, due to challenging and technical nature of these objectives, it is not possible to deliver against all of the aims during this programme’s lifespan.	Both donors continue to engage regularly with CGIAR-CIMMYT to track progress, and to discuss course-corrections where needed. The NCE is an important opportunity to build on the success of the programme’s achievements to date.	Moderate	No
Context	Priorities and strategy could change within GF, affecting the foundation’s interest in working in partnership with FCDO on wheat research and technology development for smallholder farmers and for improved nutritional outcomes in rural communities of low- and middle-income countries.	The GF and the FCDO team continue to collaborate on strategy for upcoming investments. This risk has been increased to moderate due to portfolio updates within GF. As of Feb 25, there is interest from both partners to design future support on wheat breeding and disease management beyond the NCE.	Moderate	No
Operational	One of the key benefits of working with GF on this research programme is that FCDO is able to harness GF’s considerable technical expertise and programme management capacity. Both AGG and zinc mainstreaming projects are managed by a GF Senior Programme Officer with significant technical expertise and experience in breeding operations and in development. While this is critical to reducing operational and delivery risk overall, it also creates a risk that FCDO’s input to the strategic direction and management of this programme is insufficient due to constraints on resources.	The FCDO-GF secondee continues to support collaboration and discussion between the two teams to ensure alignment. GF and CIMMYT are also engaged in discussions as needed.	Minor	No
Safeguarding	There is a risk that issues around gender and social inclusion are not sufficiently well integrated. This would mean the end-products (improved and biofortified wheat varieties) would not be suitable for all intended beneficiaries.	FCDO’s safeguarding standards and requirements are incorporated in the grant terms of all the Gates Foundation/FCDO co-funded grants. These standards will be reviewed as part of the due diligence review.		No
Fiduciary	There is an inherent risk in all commissioning activity that funds are not used for the intended purposes.	FCDO is updating the due diligence and is confident that the Gates Foundation has robust due diligence, whistleblowing, fraud and corruption policies and procedures. The FCDO also has a secondee in place who supports the Gates Foundation with the grant management and who has close oversight of the projects.	Minor	No

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

FCDO funding is channelled through GF to CGIAR-CIMMYT for both projects. This funding arrangement is governed by the GF-FCDO Collaboration Framework (2016-2026).

GF directly manages both projects in the portfolio. GF issues grant agreements on behalf of both GF and FCDO, manages the reporting and payment schedules, and shares progress reports, financial reports and annual audited statements received from grantees with FCDO. The grant agreements between GF and grantees include all of FCDO’s core requirements – including, for example, the requirement for an annual audited statement from co-funded grantees – and has been reviewed and approved by FCDO’s assurance teams.

Progress reports, financial reports and annual audited statements have been submitted on time (per GF reporting schedules) by all grantees during the reporting period. FCDO SRO/Lead Adviser approval of grantees progress reports and their annual audited statement is required before payment is released. Payment is then made in US Dollars to GF for onward transmission to the grantees.

Throughout the reporting period, FCDO engaged closely with GF Programme Officers to track progress on the grants, particularly through the FCDO secondee role.

Monitoring
GF maintains regular contact with FCDO on grantee progress and emerging issues. Additionally, the new FCDO seconded staff member to GF from March 2021 continues to coordinate and support the partnership building on the work of the first secondee. This role is supported by a FCDO Programme Manager. Both roles are strengthening the efficiency, effectiveness, and success of the FCDO-GF partnership.

Compliance with FCDO requirements
- This programme is compliant with the 2014 Gender Equality Act.
- The portfolio’s compliance with the International Aid Transparency Initiative (IATI) is under review as part of the Due Diligence process.
- Asset and risk registers: Assets and risks are reviewed in the progress reports and the annual reviews. Both of these processes will be reviewed through the Due Diligence process and updated if needed.

Approach to the Annual Review
This Review was conducted by the PRO and Lead Adviser. The Review draws on annual reports from grantees to GF, additional supplementary information provided by GF, and discussions with GF Programme Officers.

Key Documentation:
- Programme logframe
- Programme business case
- Progress reports from all grants, submitted to GF

Date of last narrative financial report	Grantees each submit financial reports and audited accounts at different points during the year, depending on the reporting schedule in their grant agreement with GF. All audited accounts requirements are up to date.
Date of last audited annual statement