## Annual Review – November 2025

Title: Reversing Environmental Degradation in Africa and Asia (REDAA)
Programme Value £ (full life): £ 35 million		Review date: Nov 2025
Programme Code: [AMP ID#] / 300760	AMP start date: / 30 August 2019	AMP end date: / 31 March 2029

Summary of Programme Performance
Year	1	2	3	4	5	6
Overall Output Score	A	A	A	A	A	A+
Risk Rating	Moderate (revised to Major mid year)	Moderate / (revised down to Moderate)	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/60046808.odt
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300760/summary

## A. SUMMARY AND OVERVIEW

Description of programme

Reversing Environmental Degradation in Africa and Asia (REDAA) addresses the challenge of environmental degradation in Africa and Asia by supporting locally led nature restoration. The programme’s mission is to catalyse demand-responsive and locally led research, innovation and action to help people and nature thrive together at local, national and regional levels across Africa and Asia. REDAA-funded initiatives are interdisciplinary and focused on solutions for ecosystem restoration and management, addressing gender equality and social inclusion, and enabling people and nature to thrive together in times of climate, resource and economic insecurity.

Outputs of REDAA are of three main types – evidence and actionable information, technical approaches and tools, and improved capacity and institutional arrangements – all of which are ‘nature-positive’, benefit local livelihoods and tackle climate change. REDAA generates these outputs through grant-making and the facilitation of technical support to projects and policy advocacy. REDAA supports 29 locally led research-to-action initiatives in sub-Saharan Africa, South and Southeast Asia. Technical support for these initiatives is arranged and a community of practice is facilitated among REDAA grantees and a wider network of stakeholders that enables learning, spreads use of evidence and tools, builds and strengthens networks, and supports capability development, in particular for gender equality and social inclusion, and policy engagement and influencing opportunities at national and international levels. Complementary to this, REDAA also hosts the ‘Nature Facility’, a support hub that helps FCDO staff and partners put nature at the heart of their work by providing technical support and expertise on specific issues.

The International Institute for Environment and Development (IIED), through an accountable grant, is leading the implementation of REDAA – via a specially constituted Scientific and Management Unit (SMU). The SMU provides joined-up functions of implementing and adapting REDAA strategy, managing the research-to-action grants, overseeing scientific rigour and providing technical support to projects, and facilitating targeted policy engagement.

Summary supporting narrative for the overall score in this review

Substantial further progress by the REDAA programme has been demonstrated in the Annual Review process this year, scoring an A+ overall. The programme has achieved its main objectives for the period: to sustain technical and management support to the first cohort of projects; to initiate such support for the second cohort of larger programmes; to facilitate learning within the REDAA Community; to further develop the Nature Facility and partnership initiatives; and to maintain strong programme governance and management. From this, positive outcomes and impact are emerging for gender equality and social inclusion[1], for nature and for the climate. This level of progress has been achieved despite postponing some actions and replanning others following the announcement of the reduction of ODA from 0.5% to 0.3% GNI in February 2025 and awaiting budget settlements for future financial years.
[1] Progress towards gender equality and social inclusion (GESI) is central to the REDAA programme. To date, REDAA-supported initiatives have reported on progress with GESI without a specific focus on disability. In the year ahead, disability will begin to be included as a specific focus. See also Recommendation 4b.

Key achievements in the period under review (Nov 2024 to Oct 2025):
Key achievements in the reporting period are represented in Figure 1. Outputs from community-led research in the Huye and Gisagara districts, Rwanda, has led to local government authorities, sector-level environment and agriculture officers, and civil society organisations more regularly integrating community consultations into district-level planning for land use and environmental management. Currently, 4,000 community members, 70% of them women, in Huye and Gisagara Districts, Rwanda, now actively practice sustainable agriculture and land restoration practices, including agroforestry, contour farming, crop rotation, and organic composting.

Major lessons and recommendations for the year ahead

Lesson 1. REDAA-funded initiatives need to be brought together at portfolio level to create added value and impact in the global context. Initial work was undertaken on this during the reporting year but further sharpening is needed. A portfolio approach will capitalise on synergies across projects and aim to inform policy across a range of geographic scales. With the number of projects across the REDAA portfolio, REDAA would benefit from centralised, easily accessible repository of key project information, and a unified Value for Money (VfM) framework that will improve assessing and communicating VfM across the programme.
- Recommendation 1a: Develop an ‘optimising impact’ section of REDAA Strategy to include plans for sustainability of project-level impacts and for scaling portfolio-level impacts up and out, and exploring opportunities for external funding. [SMU: By March 2026]
- Recommendation 1b: Explore plans for an ‘impact fund’. Pending clarity on multi-year budget allocations, the SMU should develop plans for existing REDAA-supported initiatives that demonstrate their effectiveness to be able to apply for additional financial support for specific, strategic activities that enhance their impact. [SMU: By March 2026]
- Recommendation 1c: SMU should create a simple, Excel-based ‘one-stop shop’ to track key grantee and delivery chain data, such as project dates, locations, lead organisations, funds paid each year, to support efficient oversight and coordination [SMU by January 2026]
- Recommendation 1d: SMU should develop a VfM framework aligned with FCDO’s 5Es, using the Business Case and Logframe to define clear indicators and benchmarks, and determine return on investment on research (RoI). This should be integrated into existing MEL systems and used to guide strategic decisions and future grant calls [SMU by April 2026]

Lesson 2. Identifying and managing potential risks across portfolio and projects requires sufficient capacity and flexibility within the SMU to deliver alongside managing projects.
- Recommendation 2a: Further strengthen SMU approach to ongoing due diligence and monitoring of projects. The SMU will continue to strengthen processes for IIED, REDAA and partner organisations, including regular updates for FCDO against these in SMU quarterly reports. This should also be considered when planning for a third grant call for catalytic grants. [SMU: Throughout November 2025 – October 2026]
- Recommendation 2b: Continue to strengthen safeguarding throughout the delivery chain. The SMU has begun to develop an action plan to further strengthen all aspects of safeguarding including SEAH, health and safety and environmental, throughout the delivery chain. This plan should be further developed and implemented within the next reporting period. [SMU: by February 2026]
- Recommendation 2c: Include greater flexibility in activity and resource planning to accommodate time for responding to unplanned issues. The SMU should scrutinise and refine work planning to ensure it includes sufficient contingency to react quickly to issues arising. [SMU: Throughout November 2025 – October 2026]

Lesson 3. The Nature Facility is an on-demand advisory service rather than a delivery project, and MEL provisions need to reflect that. It is also operating in an uncertain political environment and needs to be agile to learn, adapt and respond to maintain relevance.

Figure 1. REDAA key achievements November 2024 to October 2025
Recommendation 3: Continue to fine-tune the Nature Facility’s roles and mechanisms. Implement the new MEL plan for the Nature Facility (begun in current reporting period) including improvements to client feedback mechanism, carrying out a portfolio analysis, key questions and critical gap analysis, key informant interviews, and a lesson-learning exercise – and further refine the Facility’s strategy and procedures. [SMU: Throughout November 2025 – October 2026]

Lesson 4. GESI practice varies in quality across the REDAA portfolio reflecting differing levels of understanding and experience among initiatives’ local lead organisations and their partners. There is demand across cohorts 1 and 2 for support to dedicated capability development on GESI including on disability issues.
Recommendation 4a: Facilitate support to fill GESI capability gaps in the portfolio. Identify expertise, including in locations of REDAA-supported initiatives, and contract one or more experts to help fill GESI capability gaps amongst REDAA partner organisations. [SMU: Throughout November 2025 – October 2026]
Recommendation 4b: Include a specific focus on disability in GESI work. Enable REDAA-supported initiatives to put a specific focus on disability in projects. REDAA should explore the potential to integrate the ICF Gender Equality, Disability and Social Inclusion (GEDSI) Guidance for delivery partners published in 2025. [SMU: By February 2026]

Lesson 5. REDAA has shown substantial progress in the reporting year. The more local nature of REDAA projects means that knowledge and research products can sometimes be more focused on local populations. Wherever possible, knowledge and research products should be publicly available online, and the SMU should work with REDAA projects to determine whether knowledge and research products can be published in peer-reviewed journals. As grantees further progress, the impact level indicators should be expanded and the logframe milestones for future years should be updated to capture the full breadth of results and to maintain ambition in future years.
- Recommendation 5a: the SMU should work with REDAA projects to ensure that the knowledge and research products are publicly available online, and the SMU should work with REDAA projects to determine whether knowledge and research products can be published in peer-reviewed journals. [SMU, throughout November 2025 to October 2026]
- Recommendation 5b: SMU should update the impact indicators to capture the full breadth of results for the programme and beyond the programme’s lifetime, and further review and update the logframe so that the programme maintains ambition in future years. [FCDO and SMU: by March 2026]

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

REDAA continues to implement the programme adaptively and reviews its theory of change (TOC) and the logical framework (logframe) annually; they were last reviewed in April 2025. The review concluded that the TOC is still relevant and no changes were made. There have been selected changes to some logframe indicators at the impact and outcome level to add clarity, and to align them with the latest guidance on ICF KPIs and enable more effective assessment of progress towards impact.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Progress to date indicates that the programme is on track to achieve expected outcomes and impact. The first milestones for both outcomes and impact were largely reached in this reporting period.

Impact statement:	Improved understanding and decisions about natural landscapes in Africa and Asia enabling people and nature to thrive together in a changing climate
Impact indicator(s)		Milestone(s) for this review	Progress
1. Area (in hectares) of ecosystems under directly implemented sustainable management practices as a result of REDAA-supported interventions (contributing to ICF KPI 17)		500 hectares	Met / 502.3 hectares
2. Extent (as a score from 1-5) to which REDAA-supported interventions are likely to lead to transformational change (contributing to ICF KPI 15)		2 - Early stage implementation, partial evidence across six core criteria but not enough for broader change.	Exceeded / Score of 2.5 out of 5. Evidence indicates that REDAA has partial evidence that transformational change is likely.

For impact indicator 1: Among the 502.3 hectares of ecosystems under directly implemented sustainable management practices as a result of REDAA supported interventions were:
- 2ha of savannah and grassland in Zimbabwe (project led by Nutrition Action Zimbabwe).
- 58.3ha of Terrestrial Tropical-Subtropical Forests in Vietnam and Myanmar are under Agroecological Vegetation Management (project led by RECOFTC)
- 41ha of Terrestrial Intensive Land-use in Vietnam are under Other Restoration (project led by ICRAF)
- 401ha of Terrestrial Tropical-Subtropical Forests and Terrestrial Shrublands and Shrubby Woodland in Bangladesh are under Reforestation and Forest Management (project led by Arannayk Foundation)
For impact indicator 2: Evidence that the REDAA programme is at the early stages of implementation of interventions likely to lead to transformational change was assessed against 6 criteria:
Increased innovation. 9 innovative and appropriate technical approaches and applications under research and development identified. There is early evidence that grantees are developing and testing a diverse range of innovative tools and approaches, and technologies. However, evidence of replication or adoption into practice is limited at this early stage.
Evidence of effectiveness shared. 43 organisations and groups spreading or using the evidence and actionable information. However, there are 36 products with actionable information validated, and 12 organizations and groups spreading or using the products. Additional considerations on whether there have been significant number of engagement and outreach events revealed 37 events which includes different stakeholder engagement workshops, learning events, district and village level dialogues and others. Among these, 14 of these events were indicated as cross cultural by grantees with the majority having a having significant focus on or integration of GESI included. This criterion indicates an emerging stage of evidence sharing.
Capacity and capability. 1,571 people trained, of which 783 benefitted from activities to improve their capability for GESI. Main capabilities developed are organizational management, agricultural and environmental techniques and wildlife and conservancy management. There is emerging evidence of capacity development with the potential for increased capability in organisation and communities in future years.
Replicability. 6 pilots and/or field tests of technical approaches and tools and applications developed, alongside a number of organisations adopting various REDAA approaches. On the scale of application for the pilot tools tested, one manual to assess FLR (forest landscape restoration) in Nepal has indicated as being scaled at sub national/regional level. At this stage of the programme, there is limited evidence of replicability. However this is anticipate to improve in future years as more projects deliver research and outputs.
Sustainability. 7 improved policies and institutional arrangements within and between organisations and groups affecting ecosystems incorporated REDAA approaches. There is early evidence of emerging long-term adoption of practices through district plans and local partnerships, indicating an emerging stage of sustainability.
Political will and local ownership commitment. 20 landscapes benefiting from improved capacity, institutional and/or group arrangements and initiatives providing ongoing support. Political will and local ownership based on multiple signs of political commitment and local leadership with early shifts from national ministries and parliaments engaging REDAA partners in law reform and policy revision process in Congo to subnational authorities integrating community participation into environmental planning in Rwanda, Myanmar, Cambodia and the Philippines, including an MoU between the Keystone Foundation and a local environmental group. In addition, various landscapes are benefitting from improved institutional and group arrangements that provide ongoing support mechanisms attributable to REDAA-supported initiatives. These examples collectively illustrate emerging political buy-in, coordination, and capacity at different governance levels.

At this stage in the programme the indicators informing the ICF KPI 15 result are output level and consequently show promising indications of transformative change for the programme. In future years outcome level changes will start to be more substantively demonstrated and form a larger share of the ICF KPI 15 assessment. For both indicators and their supporting methodologies, they should be expanded to best capture the full breadth of effectiveness and sustainability of the results for the programme.
Outcome statement:	Improved governance systems which are informed by evidence and actionable information, adopt innovative and appropriate technical approaches and tools, and foster effective capacity and institutional arrangements for environmental management, and improved livelihoods
Outcome indicator(s)		Milestone(s) for this review (cumulative)	Progress in this review year (RY Nov 24 – Oct 25)
1. Number of instances of change in national and subnational development and environmental policies, plans, practice or investments demonstrating influence by, or utilising, REDAA-supported evidence, actionable information, tools and approaches		12	Moderately Not Met / Cumulative: 10 / RY 2024-25: 10 / Progress during RY2024-25: while results are not yet achieved against the milestone, there has still been positive and relevant underpinning progress.
2. Number of landscapes affected by national and subnational development and environmental policies, plans, practice or investments informed by or utilising REDAA evidence, tools and technical approaches, and improved capacity and institutional arrangements		4	Substantially Exceeded / Cumulative: 8 / RY 2024-25: 8

For outcome indicator 1: 10 new instances of change in national and subnational development and environmental policies, plans, and practice were identified during the reporting year. Positive progress to date indicates that milestones for this outcome will be achieved in future reporting years. Current and emerging examples (and the landscapes which they benefit) include:

1. Local actors in Shan State, Myanmar co-developed a shared district-level vision and strategy for developing a nature-positive and inclusive avocado sector. This represents a significant shift from fragmented efforts by different actors, typically dominated by the private sector, to a more coordinated and inclusive action approach involving diverse stakeholders that begins to address technical and market challenges. (Upland agroforestry and watershed restoration landscape by Inle Lake)
2. Government actors in Bangladesh demonstrated a shift from ignoring or criminalising informality toward recognising and valuing the community’s environmental stewardship. Various government officials visited the informal settlement for the first time, acknowledged community efforts, and granted user rights for the lakeside. The user rights are essential for the community’s security and confidence that they will benefit from their continued restoration investments along the lakeside. This demonstrates that government actors are moving away from a default stance of ignoring or criminalising informality toward recognising and valuing the community’s environmental stewardship practices. The granting of community user rights for the lakeside is an achievement that was not anticipated at this stage. (Urban deltaic wetland landscape. Gulshan-Baridhara lake system wetlands)
3. A national MP in the DRC endorsed a bill to amend and supplement the 2014 Nature Conservation Act (Law No. 14/003) – commonly referred to as the Engelemba Bill. The amendment introduces key human-rights and governance reforms to the 2014 law. The bill represents a significant advocacy milestone, and its parliamentary consideration in itself represents a major step forward in recognition of rights-based conservation. Adoption into law would represent substantial progress. These reforms would also align the DRC’s conservation framework more closely with the Kunming-Montreal Global Biodiversity Framework (Target 3) and with international human-rights standards.

For outcome indicator 2: 8 landscapes were reported to have benefited from improved policies, plans, practice or investments demonstrating influence by, or utilising, REDAA-supported evidence, actionable information, tools and approaches. Notable examples include:
- 3 landscapes associated with the instances 1, 2 and 3 listed above of various actors adopting or implementing new or improved policies, plans and practice (Outcome indicator 1).
- 1 landscape has benefited from equipment to enable the production of microbial fertiliser and organic fuel briquettes, farmers trained on the production and application of microbial fertilisers, and farmers participating in knowledge sharing and co-learning about gender-based research-to-action approaches that have the potential to improve livelihoods. (Tele Bere project)
- 1 landscape benefited from improved packaging and labelling system for organic fertilisers and biopesticides, and local master trainers promoting use of the organic fertiliser and biopesticide in the area. (SCOOPS-Tibi project)
These positive indications of outcomes indicate the effectiveness and efficiency of support for locally led nature restoration, and suggest that REDAA, if continued at full strength, can have substantial impact.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The REDAA programme should continue. Despite some major external stresses, delivery has been effective this year and the programme is on track to have strong positive impacts on people, nature and climate by programme-end in March 2029. Work is underway to identify strategic and specific actions to optimise project-level and portfolio-level to effect will enable deeper and wider impact post-programme. The spread of learning in the REDAA Community has ramped up this year with partners investing in this unique platform for locally led nature restoration not being provided by other programmes. REDAA is contributing to the UK’s modern development approach through equitable partnerships with in-country organisations, alongside generating evidence on conserving and restoring nature to contribute to the Foreign Secretary’s priority on climate and nature.

Figure 2. Planned actions for the next reporting period November 2025 - October 2026

## C. DETAILED OUTPUT SCORING

Output Title	Evidence on key ecosystems, their status from degradation to restoration, and their links to livelihoods, plus actionable information to improve their restoration and management
Output number:		1	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress in this review year (RY Nov 24 – Oct 25)
1.1 Number of knowledge and communications products with new evidence on the status, challenges and opportunities associated with key ecosystems produced and disseminated by REDAA programme (and identifying number of those products that: have been peer reviewed; include women authors; and include early career researchers)	45 / Peer reviewed: 1 / Incl. women authors: 33 / Incl. early career researcher (ECR) authors: 5	Moderately Exceeded / Cumulative: 80 / RY 2024-25: 57 / Of the new products: / Peer reviewed: 7 / Incl. women authors: 12 (sub-target substantially not met) / Incl. ECR authors: 19
1.2 Number of knowledge and communications products with actionable information for restoration and management of key ecosystems produced and disseminated by REDAA programme	28	Moderately Exceeded / Cumulative: 39 / RY 2024-25: 24
1.3 Number of organisations and groups spreading or using the evidence and actionable information with attribution to REDAA-supported initiatives	30	Moderately Exceeded / Cumulative: 43 / RY 2024-25: 25

Briefly describe the output’s activities and provide supporting narrative for the score.

For indicator 1.1: 57 new knowledge and communications products of this type, have been published and disseminated in the reporting period. They range from project baseline assessments to products from research on particular biophysical, social, socio-economic and institutional issues. Examples of knowledge and communication products published by project partners include:
- Gender equality and social inclusion baseline analysis for the LONG FALLOWS project, Lindi Region, Tanzania
- Characterizing the Biophysical Conditions for Improved Planning and Designing of Locally-led Sustainable Land Management Practices in Halaba, Ethiopia
- Communicating locally led restoration – themes and insights
- Digital case study: Financing mechanisms
- Risks and benefits of artificial intelligence in locally led nature restoration
- Gender equality and social inclusion in REDAA initiatives
For indicator 1.2: 24 new knowledge and communications products with actionable information have been, produced and disseminated in the reporting period, including a training manual on rural job creation for natural resource conservation and the development of the ReWET Collective Action Framework.
The Nature Facility has completed six further full assignments in the last year and delivered reports and webinars to help FCDO staff and partners put nature at the heart of their ODA-focused work. Report on “Costs of Maintaining Standing Tropical Forests” for the Tropical Forest Forever Facility (TFFF) has directly informed HMG, the Brazil Secretariat and the FAO. Another assignment focused on validation and improvements of claims surrounding indigenous peoples and local communities’ (IPLCs) rights and sustainable forest/land stewardship. Trainings have been provided on Nature and OneHealth; the One Health training increased HMG knowledge and understanding, including on links with the natural environment. Assignments completed in the reporting period are summarised in Table 1.

Assignment	Product title	Product type
OneHealth Training	OneHealth Explainer	Working paper
TFFF	How much difference would the Tropical Forest Forever Facility (TFFF) make?	Policy advice
DESNZ Forestry	Research to Inform International Forests Unit (IFU): Private Finance for Forests and Sustainable Land use Programming – Final report / Research to Inform International Forests Unit (IFU): Private Finance for Forests and Sustainable Land use Programming – Summary report	Policy advice
IPLC claims	Assessing the evidence of the importance of tenure security to IPLC land and forest stewardship	Policy advice
REACH Observatory approach	Scoping Study – Scaling the REACH Observatory Approach	Programme scoping
Principles for Inclusive Nature Action briefings	Briefing: Principles for Inclusive Nature Action: Principle 5 – Direct, patient, flexible, predictable and accessible funding / Briefing: Principles for Inclusive Nature Action: Principle 6 – Recognise the equal importance of scientific, and local and traditional knowledge	Policy Advice

Table 1: List of Nature Facility assignments and products delivered in the reporting period (Nov 2024-Oct 2025)
For indicator 1.3. 25 organisations and groups are newly spreading or using the evidence and actionable information with attribution to REDAA-supported initiatives. For example, partner organisations are using posters on adaptive management and game counts products developed under the WWF – UK-led project. They include WWF-Namibia and other organisations under Namibian Association of Community Based Natural Resource Management (NACSO) (such as Integrated Rural Development and Nature Conservation, NACSO Natural Resources Working Group, and Namibia Nature Foundation) with the ultimate aim of 38 communal conservancies within the Kunene Region using the products in improved livestock and wildlife management for local livelihoods.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Output 1.1 was refined in the reporting year to include a breakdown on the numbers of evidence products (indicator 1.1) that are: peer reviewed, involve women authors; and involve early career researcher (ECR) authors (a definition of ECR authors to better capture the scope of authors of research and knowledge). Milestones were clarified to better capture the programme’s progress. Due to the positive progress in the year under review, a further review of future output milestones is planned in the coming year. The SMU should facilitate support to fill GESI capability gaps in the portfolio.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from last year’s Annual Review:

Recommendation	Progress
1. Further develop SMU support for adaptive planning of initiatives. With effective communications between the SMU and project leads comes the ability to support re-planning and re-budgeting of projects to help keep them on track. The SMU should also optimise its guidance to Grant Call 2 applicants to plan realistic inception periods for programmes and prepare realistic budgets (SMU throughout November 2024 to October 2025)	Completed: Grants Managers’ quarterly calls and project support visits have continued, providing mutual value and helping grantees re-plan and re-budget where needed. First-cohort annual reports generated tailored SMU feedback to keep projects on track and inform adjustments. For the second grant call, SMU issued clearer guidance on realistic inception periods and reviewed all detailed proposals for feasibility, budgets and timelines to ensure deliverability. SMU has maintained budget flexibility to adapt to changing external conditions and optimise use of REDAA funds.
5. Further develop the Nature Facility’s roles and mechanisms. Develop its proactive role in nature communications and capacity development, consulting with diverse parts of FCDO, and exploring the potentials of engaging with the REDAA Community. Develop mechanisms for gaining feedback from FCDO, expert consultants and team experiences, so that the Facility and its work provide the best value for FCDO in a rapidly changing UK and international context. Maintain regular liaison with the Climate, Environment and Nature (CLEAN) Helpdesk to ensure effectiveness and efficiency in providing the most relevant advice for FCDO (Nature Facility team throughout November 2024 to October 2025)	Completed: The proactive role of the Nature Facility has been strengthened, focusing on nature-related evidence and ideas aligned with current FCDO priorities. Two new (proactive) nature briefings are in progress, and all assignment reports are now accessible to FCDO staff. A feedback survey was launched for assignment requesters and experts, though completion rates need improvement to ensure meaningful analysis. / Regular liaison with CLEAN has continued, with agreed ways of working, information-sharing, and one jointly delivered assignment.

Lessons learned this year:
See Lesson 3, 4 and 5 in Section A.

Recommendations for the year ahead:
See Recommendations 3, 4a, 4b, 5a and 5b.

Output Title	Innovative and appropriate technical approaches and tools for environment management, conservation and restoration that are nature-positive, benefit local livelihoods, and tackle climate change
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress in this review year (RY Nov 24 – Oct 25)
2.1 Number of innovative and appropriate technical approaches and tools and applications under research and development identified with attribution to REDAA-supported initiatives	9	Met / Cumulative: 9 / RY 2024-25: 6
2.2 Number of pilots and/or field tests of technical approaches and tools and applications developed by REDAA-supported initiatives	10	Moderately not met / Cumulative: 6 / RY 2024-25: 1
2.3 Number of organisations and groups applying innovative technical approaches, and adopting appropriate tools and applications with attribution to REDAA-supported initiatives	9	Substantially Exceeded / Cumulative: 102 / RY 2024-25: 97

Briefly describe the output’s activities and provide supporting narrative for the score.

For indicator 2.1. 6 new technical approaches and tools were developed including:
- Participation and transparency tool (PATT), a community-based monitoring and engagement tool designed to gather qualitative data on land and natural resource governance from the perspective of Indigenous Peoples and local communities. The tool supports inclusive analysis of rights awareness, tenure security, governance practices, and transparency, helping to inform advocacy, policy dialogue, and participatory land reform processes. Forest Peoples Programme, DRC and Republic of Congo.
- Eco-credit Guideline for Informal and Unbanked Communities – the audience for which is development practitioners, government agencies, research institutions community-based trainers and community microfinance groups. This tool is being adopted as a framework for capitalising community-specific loan schemes focused on commitments to sustainable farming practices in project locations, and by project partner Tanzania Informal Microfinance Association of Practitioners and other organisations in others areas, thus beginning to spread a practical eco-credit approach in Tanzania. Rikolto-led project, Tanzania
For indicator 2.2 is underachieved. While REDAA only reports on pilots and/or field tests which are fully developed, several are currently under development that are anticipated to meet future milestones. One tool was piloted and tested in this reporting period:
Manual to assess and improve forest landscape restoration in Nepal. This tool enables civil society and government bodies to recognise, and support improvements in, site-appropriate vegetation management, helping shift national policy from an inappropriate one-size-fits-all approach to increasing support for effective diverse restoration action. Forest Action Nepal.
For indicator 2.3. 97 organisations and groups have applied innovative technical approaches, and with attribution to REDAA-supported initiatives in this reporting period. These include 16 national and subnational government departments and agencies, a university, a private sector organisation, at least 6 CSOs and community groups including:

- Locally led loans financing land conservation. In the southern highlands of Tanzania, the changing climate is threatening existing agricultural systems and smallholder farmers are, unknowingly, resorting to harmful practices. In response, Rikolto’s REDAA-funded project, Nature Fundi, is piloting a loan-based mechanism that devolves funding, management and decision-making to the community level. It also incentivises sustainable farming because to access funding, farmers must demonstrate that they are engaging in land conservation activities. Through 44 ‘community microfinance groups’ across Katavi, Songwe and Mbeya regions, the project has engaged 1,375 smallholder farmers and trained them in sustainable agricultural practices such as soil and water conservation, agroforestry and climate-smart agriculture. As a result of the success, Nature Fundi has registered a growing number of unsolicited demands for participating in the scheme only a few months after implementation.
- The International Institute of Tropical Agriculture is working with Honey Pride Uganda Ltd. To train refugee and host communities farmers in modern beekeeping, and is using information developed by the project to inform apiary setup.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

Milestones were clarified to better capture the programme’s progress. Due to the positive progress in the year under review, a further review of future output milestones is planned in the coming year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from last year’s Annual Review:

Recommendation	Progress
2a. Review and identify strategic and synergistic opportunities across the REDAA portfolio to inform the REDAA strategy, future grant calls, and linkages to greater action relevant to the REDAA programme as appropriate. (SMU by March FY2024-25)	Some delays: The SMU has developed a Community Mapping and Learning Tool (using Excel) that allows the team to track emerging synergistic opportunities across the REDAA portfolio using information submitted by projects in their proposals and annual reports. For example, the tool is being used to map entry points to national, regional and global policy – and understand any key synergies or key gaps in ambition. SMU is developing an enhanced impact strategy with a focus on cross-cutting opportunities and policy impacts and what we aim to influence in these arenas. Two Community webinars were held in March 2025 on how governance dynamics influence locally led nature restoration efforts and how REDAA-funded projects are engaging with policy and tackling the external powers affecting them to strengthen their delivery.

Lessons learned this year:

See Lesson 1 in Section A.
Recommendations for the year ahead:
See Recommendations 1a and 1b.

Output Title	Capacity and institutional arrangements, including finance and support mechanisms, support gender-equal and socially inclusive, long-term decisions and action that are nature-positive, benefit local livelihoods, and tackle climate change
Output number:		3	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress in this review year (RY Nov 24 – Oct 25)
3.1 Number of people in organisations and groups affecting ecosystems benefiting from initiatives to improve their capability, including capability for achieving gender equality and social inclusion (GESI) in these organisations and groups, with attribution to REDAA-supported initiatives	850 (at least 290 of whom have benefitted from initiatives to improve their capability for achieving GESI)	Substantially Exceeded / Cumulative: 1,571 / RY 2024-25: 1,040 / Of these, 783 (cumulative) benefitted from activities to improve their capability for GESI (RY 2024-25: 552)
3.2 Number of improved policies and institutional arrangements within and between organisations and groups affecting ecosystems with attribution to REDAA-supported initiatives, including improved policies and institutional arrangements for gender equality and social inclusion	8 (at least 4 of which include a focus on improvements for GESI)	Almost met / Cumulative: 7 / RY 2024-25: 3 / Of these, 5 include a focus on improvements for GESI (RY 2024-25: 1)
3.3 Number of landscapes benefiting from improved capacity, institutional and/or group arrangements and initiatives providing ongoing support with attribution to or catalysed by REDAA-supported initiatives. / (Includes landscapes where there is evidence of activity supported by REDAA funded partners, or resulting from REDAA interventions: / piloting or applying new tools and approaches / implementing improved policies or institutional arrangements adopted / where actors reached are changing their practices based on REDAA evidence)	6	Substantially Exceeded / Cumulative: 20 / RY 2024-25: 17

Briefly describe the output’s activities and provide supporting narrative for the score.

For Indicator 3.1. 1,040 people in organisations and groups affecting ecosystems were newly benefiting in this reporting period from initiatives to improve their capability. Since the beginning of the programme, 783 benefited from project activities to improve their capability for GESI of whom 552 were new in this reporting period. Examples of project outreach and benefit to people include:

- Forest Peoples Programme in Congo and Democratic Republic of the Congo: 7 APEM (Actions pour la Promotion et Protection des Peuples et Espèces Menacés, partner) staff have improved GESI capacity; 6 CECD (Centre d'Encadrement Communautaire pour le Développement, partner) staff were trained in governance and management
- ICRAF in Vietnam: 29 Lao Cai Farmers' Union staff, agricultural staff, and key farmers were trained in soil fertility management and ecological farming at household level, including strengthened GESI; and 80 farmers in Nam Mon and Hoang Thu Pho communes were trained in perennial and fodder crop care and inclusive climate-resilient farming, including women’s skills
- WWF UK in Namibia: 51 Kunene Conservancy representatives, support NGOs, MEFT (Ministry of Environment and Tourism, Namibia) and independent stakeholders improved shared knowledge on the status of wildlife in the landscape and the key drivers of wildlife decline; and 38 Community game guards were trained in digitisation of patrol data collection.
The REDAA Community has supported strengthening capabilities across three key areas - strategic communications, gender equality and social inclusion, and governance and restoration.
- A six-week online Strategic Communications Learning Course improved capabilities of REDAA partner organisations to ensure research uptake in practice and policy. Two GESI peer exchange sessions supported 21 participants (13 women) to discuss best practice for how to embed GESI.
- Two public-facing regional webinars on power, politics, and restoration governance, featured REDAA partners from India, Nepal, Bangladesh, Ethiopia, the Congo Basin, and Tanzania, and were attended by 156 participants. The SMU created a Community Insight (Shifting power and strengthening locally led governance).
- Two REDAA projects (Philippines and India) were showcased at the World Conservation Congress (October 2025) as part of an interactive panel, “Restore Her Rights: Advancing Gender Equality and Women’s Roles in Ecosystem Restoration”. Additionally, a REDAA project (Vietnam) contributed to an event on the private sector’s role in enabling locally led action at Development and Climate Days, ahead of the UNFCCC CoP.
Indicator 3.2. has been marginally underachieved, but relevant headway has still been made in the reporting period to support achieving the output in due course. 3 new improved policies and institutional arrangements within and between organisations and groups affecting ecosystems have been reported in this review period, as follows:
- MoU between the Wayanad Wildlife Sanctuary and Keystone Foundation and a local environmental group (FernsNaturalists’ Society) to undertake the restoration within the wildlife sanctuary in India.
- TTGAU gender policy affecting Iringa landscape specifically the agriculture and tree growing areas of Njombe, Tanzania.
- MVIWAMA and MVIWAARUSHA adopted a shared Institutional Environmental Conservation Climate Change Policy Framework affecting Arusha landscape (semi-arid areas of Longido and Meru) and Manyara (semi-arid areas of Simanjiro and Kiteto) landscapes in Tanzania.
For indicator 3.3. 17 landscapes are newly benefiting from improved capacity, institutional and/or group arrangements and initiatives providing ongoing support with attribution to or catalysed by REDAA-supported initiatives in this reporting period. Notable examples:
- 3 landscapes in Tanzania: 1 in the Southern Highlands in Njombe District; and 2 in the Northern semi-arid areas in Longido and Meru Districts, and in Simanjiro and Kiteto. Each of the three landscapes in the Trias-led project in Tanzania are benefiting from the piloting of practices in vegetation management for restoration and land-use based livelihood improvements. These practices are based on participatory land and climate risk assessments and supported through the spread of community microfinance.
- 1 landscape in northwest Vietnam (Upland farming plots in Nam Mon and Hoang Thu Pho communes in Lào Cai province) where, in a project led by International Centre for Research in Agroforestry (ICRAF), degraded land is being restored through the implementation of contour-based agroforestry models integrating fruit trees, fodder grass, and nitrogen-fixing species, as sustainable management practice.
- 1 landscape in Cambodia (Customary land - Indigenous Forest, agroecology and upland agricultural landscape, Sesan commune, Oyadav district, Ratanakiri province) where the Indigenous community used participatory action research findings to develop plans to replant wild vegetables and trees. This was undertaken without prompting from the Cambodia Indigenous Peoples Organisation (project lead), and demonstrates the importance of community ownership for successful restoration of the forest.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

Milestones were clarified to better capture the programme’s progress. Due to the positive progress in the year under review, a further review of future output milestones is planned in the coming year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from last year’s Annual Review:

Recommendation	Progress
3. Prepare and facilitate an online strategic communications course and other REDAA Community learning events. Involve those with key communications roles for the 21 first-cohort projects in the communications learning course. On the basis of expressed demand, plan and implement other learning events and technical support actions that the SMU can facilitate for the REDAA Community over the coming year (Communications course - SMU by March 2025, other Community events – SMU throughout November 2024 to October 2025)	Completed: In total, the REDAA Community has hosted 24 learning events associated with the Strategic Communications Learning Course, GESI drop-in support sessions, two regional webinars and two ‘Cohort Connect’ sessions (see Box 1). In addition, SMU has provided hands-on support to individuals from across REDAA initiatives to contribute to events at the World Conservation Congress and Development and Climate Days.
2b. Strengthen REDAA’s monitoring, evaluation, reporting and learning tool to ensure NERC and other REDAA collaboration outputs are appropriately captured and informing cross learning and join-up across the REDAA portfolio including through review of REDAA’s logframe and strategy. (SMU by April 2025)	Completed: A new results reporting tracking tool was developed, rolled out, and is in use by all grantees. Feedback has been provided to cohort 1 grantees after their first annual reports on how they can improve their completion of the tool for future reports, which are being received on a quarterly basis. SMU has also developed and implemented a new aggregate results reporting tracking tool for programme-level tracking and reporting. / ResearchFish reports from the four REDAA-funded NERC projects were shared with the SMU in August 2025. Logframe targets were also updated to include figures of peer-reviewed outputs achieved, which will be particularly relevant for the NERC projects.

Lessons learned this year:

See Lesson 5 in Section A.

Recommendations for the year ahead:
See Recommendation 5b.
## D: VALUE FOR MONEY

Key cost drivers and performance

REDAA has disbursed £9.2 million cumulatively since its commencement. The main cost drivers in the reporting period (FY24/25 Q3-4 and FY25/26 Q1-2) continued to be research grant expenditure (77%) and SMU staff costs (13%). SMU indirect costs (including for the Nature Facility) accounted for ~6% of costs in the reporting period. Costs remained within budget.

The programme has met its output milestones for the year, and is now beginning to deliver at outcome and impact levels. 8 new grants (Cohort 2) have been issued and are progressing well alongside Cohort 1 projects. The Nature Facility continues to provide influential technical support to FCDO receiving strong client feedback.. The REDAA Community is growing with Cohort 2 grantees and several learning events held to advance shared learning experiences.

VfM performance compared to the original VfM proposition in the business case

The programme has met or exceeded most of its milestones for the reporting period and is on track to deliver high-impact activities in future years. Table 2 presents examples from the reporting period of how the programme has demonstrated value for money (VfM) across FCDO’s 5 Es framework.

Table 2. Examples of value for money in the reporting period

Economy – minimising input cost
Minimising Input Cost	85% of programme budget allocated to delivery vs. 15% to overheads / Of the programme funds directed via the SMU: / 78% are allocated to locally led grant initiatives in sub-Saharan Africa and South/Southeast Asia. / Less than 18% goes to SMU management costs, / 5% to the Nature Facility (including its management). / Indirect costs of the SMU are kept lean, currently under 6% of the total programme budget.
Cost-saving practices	In Nepal, the ForestAction Nepal-led project used community-based homestays instead of hotels for organising workshops and trainings, reducing costs and fostering community ties. ForestAction Nepal estimate accommodation costs were halved saving approximately £3000.
Efficiency – conversion of inputs to outputs
Strategic resource use	Tearfund and its partner AEE generated surplus funding of over £30,000 through favourable exchange rates and savings on activities. They proposed using it to enhance rural climate resilience. The strategic use of surplus funding will greatly contribute to the well-being and livelihoods of rural households, helping to maximise the project's impact and sustainability.
Driving Efficiency in Programme Management	By seeking experts at the appropriate level of seniority for the task, the Nature Facility has assessed the evidence of the importance of tenure security to IPLC land and forest stewardship for an assignment cost of less than £6000 – less than half of the budgeted average cost per assignment.
Effectiveness – conversion of outputs into outcomes
Policy Influence	6 (32%) of REDAA-funded initiatives are already influencing policies, plans, or practices within the projects’ scope.
Capacity Building through Strategic Communications	An online course improved REDAA Community teams’ ability to engage stakeholders and increase research impact, with participants reporting a 2–3 point confidence boost (on a 10-point scale). Ongoing ‘Comms Connect’ sessions continue to strengthen these skills.
High-Impact Assignments via the Nature Facility	The Nature Facility has spent a total of £610,116 to date and delivered 17 assignments (=average cost of £35,889 per assignment) and continues to receive positive feedback regarding utility and rapid uptake of assignment outputs by FCDO staff and other funding agencies.
Equity – degree to which results of intervention are equally distributed
Inclusive Reach of Programme Beneficiaries	All projects have GESI integrated into activities from the outset. / 59% of beneficiaries (both direct and indirect) are women
Removing Barriers to Participation	ForestAction Nepal promoted inclusion through reserved places and support for marginalised groups, resulting in strong participation from women, Indigenous Peoples, and differently abled individuals: / 3 workshops held with at least 50% women participation. / 1 leadership training for restoration practitioners: / 50% of 25 participants were women. / 9 Indigenous participants, including 2 Tharu representatives. / 1 participant was differently abled.
Overall cost-effectiveness – degree to which the programme is creating sufficient value to justify its input costs
Budget allocation efficiency	The programme demonstrates strong cost-effectiveness by directing 78% of SMU-managed funds to locally led delivery, with minimal overheads and indirect costs. This allocation model supports high-impact, locally driven outcomes across multiple regions.

Details of associations and partnerships that have been developed for REDAA over the past year that added value to its performance.

Co-funding with Natural Environment Research Council (NERC): REDAA contributes £500k to NERC’s-climate resilience programme, supporting four high quality research projects. This expanded REDAA’s UK research links and evidence base with minimal admin. The projects are now delivering REDAA-relevant outputs,as evidenced by their first full year’s ResearchFish reports. The four projects – REPAiR (IDS), Listen, Learn & Leap (UCL), REAL NbS (University of Sussex), and Co-designing NbS in Coastal West Africa (Manchester Metropolitan University) – represent cutting-edge research on equitable nature-based climate resilience in Sub-Saharan Africa. Next year, REDAA will deepen collaboration by working to integrate them into its Community for stronger engagement and peer learning.

Collaboration with Climate, Environment, and Nature (CLEAN): The Nature Facility continues to coordinate with the FCDO CLEAN Helpdesk to ensure complementary approaches and avoid duplication, supporting efficient use of UK government resources.

Synergies with emerging research priorities: Research scoping commissioned by the Economic and Social Research Council indicated that freshwater ecosystems were key ecosystems to further research, which aligned with previous REDAA scoping studies. REDAA has begun exploring how it can inform FCDO’s new Restoring Environment, Ecosystems and Water (RENEW) programme. Opportunities for complementarity are emerging, and REDAA plans to align future activities (e.g. GC3 catalytic grants) to maximise value for both programmes and their beneficiaries.

Assessment of whether the programme continues to represent value for money

REDAA offers excellent value for money and should continue. The programme is well into implementation, delivering strong outputs and showing early signs of impact. It operates within budget, with most funds supporting locally led initiatives. Lean management and minimal indirect costs ensure efficient use of resources and highlighting REDAA’s strong performance and cost effectiveness.

Lessons learned this year:
See Lesson 1 in Section A
Recommendation for the year ahead:
See Recommendation 1d.

E: RISK

Overview of risk management

The REDAA programme’s overall risk rating of ‘moderate’ remains unchanged and risks have remained within risk appetite. Key risks associated with REDAA-funded initiatives have been proactively managed through SMU due diligence checks, project support visits, regular meetings between SMU Grant Managers and grantees, and the roll-out and support provided on new output tracking tools. There are fiduciary and delivery risks given the local nature of interventions within the portfolio, and specific issues can and do arise during actual implementation. The operational REDAA risk management system is relevant, picking up emerging risks and issues which are discussed and mitigated, with escalation in SMU and FCDO where necessary. Active learning as well as mitigation is undertaken regarding any risks that do materialise. For example, REDAA has strengthened its approach to due diligence and monitoring of projects, focusing on improving capacity within REDAA partners to meet donor due diligence, financial management and safeguarding requirements. The SMU has begun to develop an action plan to focus on strengthening all aspects of safeguarding throughout the delivery chain. This will continue into the next reporting period.

SMU maintains a programme risk register, updated quarterly and shared with FCDO and IIED senior management with escalation as needed. REDAA-funded initiatives manage their own project-level risk registers. Lessons learned are logged and tracked via SMU’s internal tracker, or IIED’s audit tracker, which is shared directly with FCDO for institutional-level recommendations.

Table 3 summarises the most significant risks managed in the reporting year.

Table 3. Most relevant risks for the reporting period
Risk	Mitigating actions
Category: Safeguarding
Risk that REDAA’s safeguarding approach may not be consistently communicated or applied across the delivery chain, increasing the likelihood of incidents or inadequate response. / Environmental Safeguarding Risk - while REDAA projects aim to restore degraded ecosystems, there is a risk that poorly managed interventions could cause unintended ecological damage. This could undermine biodiversity, reduce ecosystem resilience, and compromise programme credibility.	Safeguarding policies are embedded in all grant documents, FCDO communications are cascaded and grantee policies reviewed during due diligence. Partner-specific risks are tracked via the Delivery Chain Risk Map. A Safeguarding Action Plan is being developed to strengthen practices across SEAH, health & safety and environmental, and cybersecurity. / Environmental safeguarding is integrated into REDAA’s broader safeguarding framework. The programme embeds these measures through due diligence checks and regular monitoring.
Category: Fiduciary
Misappropriation of funds: Due to the nature of REDAA’s delivery chain, there is exposure to potential financial irregularities, including fraud or mismanagement. These risks could result in misuse of funds, disruption to programme delivery, and reputational damage to REDAA and its partners.	Internal audits have informed improvements to payment processes and grantee onboarding. Progress on recommendations is being tracked and shared with FCDO. REDAA staff and grantees participated in an FCDO-led workshop (Sep25) to strengthen financial management awareness and good practice across the programme.
Category: Context
Civil unrest: Civil unrest, political instability and security concerns affected REDAA implementation in several countries including Bangladesh, Cambodia, DRC, Ethiopia, and Nepal.	SMU responded promptly in each case prioritising project team safety and supporting activity replanning to minimise risk and maintain progress. SMU continues to monitor higher-risk areas and adapt plans as needed – for example relocating a planned meeting from Nepal to Tanzania
Category: Delivery
General lack of progress with REDAA-funded initiatives: This reflects a general and ongoing risk that projects fail to make sufficient progress and therefore fail to achieve their ambitions or meet their targets and objectives.	SMU monitors project progress through quarterly reports, regular check-ins with Grants Managers, and annual progress reports. An annual review with FCDO assesses overall progress and potential risks. Improved. output tracking tools are also supporting this process.
Category: Operational
Global or national events: External events such as natural disasters, pandemics and political unrest continue to pose risks to project operations. In the reporting year this included civil unrest in several countries, a major earthquake affecting Myanmar and Thailand and IIED budget cuts from withdrawal of USAID funding.	SMU remains alert to emerging external risks maintaining communication with affected partners and FCDO and prioritising safety of personnel and communities. The impact of donor funding cuts was assessed and found not to pose a significant risk to REDAA operations.
Category: Sustainability
Positive impacts not being sustained beyond the lifetime of REDAA: With the programme now well into implementation phase, SMU is shifting attention to how it can ensure impacts are sustained beyond REDAA, and scaled beyond the influence of any individual initiative.	SMU is developing a new section of REDAA Strategy focused on sustaining and scaling impact beyond individual initiatives. Work has begun to map common themes across projects and identify global policy processes the programme could influence.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Programme management and reporting
SMU has continued to manage the programme attentively and has delivered comprehensive quarterly progress and financial reports.

Risk and asset oversight
SMU’s quarterly reports have included updates to the REDAA risk register, downstream partner risk map, and asset register. Following the first full submission of cohort-one asset registers, SMU issued additional guidance on asset management and plans to strengthen monitoring through upcoming support visits. SMU has also provided feedback to several grantees on improving their project-level risk management.

Management meetings & stakeholder engagement
SMU has maintained regular engagement through monthly catch-ups and two in-person meetings for deeper programme discussions and decision making. Grants Managers also hold quarterly online check ins with each grantee supported by in-person visits to 8 projects this year to review spending, progress and risk.

Financial performance
SMU has submitted invoices to FCDO each quarter for the next instalment, based on forecasted need for the following quarter adjusted for actual spend for the previous quarter. Table 4 shows overall expenditure by the SMU to date.

Table 4. Programme expenditure figures to September 2025
Expenditure category	Total programme spend to Sep25	Spend in Financial Year FY25/26 (Mar-Sep25)
SMU management costs	£ 2,689,166	£ 492,937
Nature Facility (management and assignment costs)	£ 610,116	£ 107,735
Grants	£ 5,916,101	£ 1,444,210
Total	£ 9,215,383	£ 2,044,882

Compliance
- IATI: IIED has fallen behind on IATI reporting (managed outside the SMU), but has assured that programme-level data will be up-to-date by end of November 2025.
- Financial management: Grantees submit quarterly expenditure and progress reports, and annual detailed updates. SMU reviews these and conducts spot checks on supporting evidence for sampled transactions.
- GEDSI: SMU is reviewing the latest ICF GEDSI guidance, and will propose to FCDO whether REDAA should adopt the Outcome-level indicator in its logframe (see Recommendation 4b).
- Safeguarding: SMU is finalising a Safeguarding Action Plan to strengthen delivery chain safeguards in the next reporting period.
- Audited accounts: Audited accounts for the year to 31 March 2025 received on 4 November 2025.
Progress on programme management recommendations from last year’s Annual Review
Recommendation	Progress
4. Learn from other relevant programmes about how best to plan and implement small grant management. In designing a well-targeted but manageable third grant call process, the SMU should establish practical systems for appropriate due diligence and management of small grants by learning further from other relevant programmes (SMU throughout November 2024 to October 2025)	Completed: Lessons from small grants programmes – including Adaptation Research Alliance’s Grassroots Action Research Microgrants programme, PCLG small grants initiative, Climate & Development Knowledge Network, Re-Wild, GEF Small Grants Programme, and Fundación Avina: BASE – were scoped to inform REDAA’s third grant call, particular around eligibility, application design, and process. While REDAA’s baseline proposal process remains, adaptations are needed to suit the catalytic call. Scoping also explored interest among target organisations, with further refinement planned to align with complementary programmes, REDAA’s impact strategy, and budget context. Feedback will be sought from the Independent Technical Advisory Panel and Steering Committee.

Lessons learned this year:
See Lesson 1 in Section A.
Recommendation for the year ahead
See Recommendation 1c.
G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation The FCDO REDAA programme team completed this Annual Review based on reporting from the SMU. Monitoring of the SMU has been carried out through regular email and online meetings, including a regular monthly catch-up call and two in-person meetings in the reporting period. The SMU reports on progress, risk and expenditure every quarter, which is then discussed with FCDO in an online meeting.

The SMU monitors grantees via quarterly reports and meetings with detailed expenditure reports every six months and annual narrative reports Support visits were made to eight projects across Vietnam, Cambodia, Tanzania, Kenya and Uganda, with FCDO joining two in Vietnam. Grantees and Community feedback is gathered through reporting templates and event surveys, informing future planning and process improvements. The Nature Facility also collects post-assignment feedback from FCDO and experts to support its ongoing evaluation. Significant progress was made in improving results tracking tools, with the SMU MEL team supporting downstream partners in their use.

Data management:
SMU manages programme data on a secure IIED-hosted SharePoint, shared with FCDO via Teams. All data handling is GDPR-compliant and REDAA grantees are contractually required to comply with GDPR.

Progress on M&E recommendations from last year’s Annual Review:

- Develop the Nature Facility’s learning aims for the coming year: The Nature Facility maintains oversight of assignment distribution, use, outcomes and lessons learned. It updates and implements the year 1 feedback and lessons log, with quarterly SMU reviews aligned to FCDO reporting Completed: A MEL plan for the Nature Facility has been developed and its implementation is already underway.
- Complete development of impact tracking approaches. The SMU will develop approaches for: Beneficiary tracking (Research and Evidence Division initiative); Transformational change tracking (KPI 15 – REDAA Impact Indicator 2); Sustainable management practices tracking (KPI 17 REDAA Impact Indicator 1); and Outcome harvesting and an annual stakeholder review. (SMU by March 2025). Partially Completed: Approaches for Beneficiary tracking, Transformational change tracking and Sustainable management practices tracking all completed, but Outcome harvesting approach not yet written up and stakeholder review plans deferred.

Evidence

Evidence for output-level indicators is captured in the Aggregate Results Reporting Tool shared with FCDO and linked to public outputs. Grantees submissions are reviewed by SMU before inclusion in programme reporting, with all published outputs logged in the R4D tracker. The quality and breadth of evidence varied across initiatives and the sections of the tools - some projects were able to report sex-disaggregated numbers of people reached and affected; none reported numbers disaggregated by other characteristics. This was the first round of reporting using the tools, and we anticipate that with further refinement of the tools and SMU support to funded partners, the quality and breadth of the evidence will improve.

REDAA is compliant with FCDO’s Open and Enhanced Access Policy, seeking to make all outputs publicly available except where there is a need for confidentiality.

Learning

REDAA fosters learning on locally led nature restoration through its Community with SMU facilitating peer-to-peer exchange via workshops and discussions. SMU also runs internal lesson-learning sessions to improve programme delivery, drawing on feedback from events and processes.
Progress with learning aims identified in last year’s Annual Review:
- SMU to further develop, implement and monitor the plan for facilitation of REDAA Community learning events over the year. Through the various learning events reported on, the SMU identified and captured lessons learned by participants in event reports, and drew on event evaluations carried out with the participants in adapting plans for Community learning events ahead.
- SMU to learn from other relevant programmes about how best to plan and implement small grant management. The SMU engaged with, and drew learning from, several other programmes about small grant management in framing the parameters and identifying the systems that can be applied to support a potential third cohort of REDAA partners manging small grants.
Examples of lessons identified in the reporting period include:

For the REDAA programme:
Internal audit reviews have led to strengthened identity verification and data handling processes, including the use of institutional email addresses. Improvements have been shared across IIED to support good practice.
Emerging themes from grantee reports: Annual reports from the first cohort highlighted cross-cutting themes for future Community focus, including:
- Land access and tenure, nature restoration and financing frameworks
- GEDSI (women, youth, disability, Indigenous Peoples) economic informality and microfinance
- Small-scale and micro-finance innovations
 Learning aims for the coming year

- SMU to continue to learn how to support the optimisation of impact through strategic actions by REDAA-supported projects and through strategic actions in international arenas.
- SMU to continue to learn how technical support and grant management experience with the first cohort of REDAA partners can enable the SMU to be more efficient and effective with such support to the second cohort managing the larger programmes, and in planning for the potential third cohort focused on small grants.

Date of last narrative financial report	IIED: July-September 2025 / NERC: Report received Oct 2025 covering 25/26 actuals and forecast	Date of last audited annual statement	IIED: April 2024-March 2025