## Annual Review

Title: Sierra Leone Secondary Education Improvement Programme, Phase II (SSEIP II)
Programme Value £ (full life): £35 million		Review date: 18/02/2026
Programme Code: 300767	AMP start date: 18/02/22	AMP end date: 31/03/27

Summary of Programme Performance
Year	2023	2024	2025	2026
Overall Output Score	B	A	A	A
Overall programme risk rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-300767 Documents
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-300767 Documents

## A. SUMMARY AND OVERVIEW

Description of programme
The Sierra Leone Secondary Education Improvement Programme (SSEIP II) is working with the Ministry of Basic and Senior Secondary Education (MBSSE) and Teaching Service Commission (TSC) to ensure safe access to free quality education, with an original target of 1.1 million children nationwide with a focus on adolescent girls and children with disabilities. It was designed to support: (i) 160,000 more girls to enrol in secondary school; (ii) a doubling in secondary enrolment of children with disabilities; (iii) 500,000 more girls to pass secondary examinations; and (iv) a reduction in adolescent childbearing.

The reduction in UK ODA announced in February 2025 has resulted in key changes to this programme which will now close in December 2026, earlier than the planned end date of 2028. This Annual Review reflects that the programme has had to refocus resources and will deliver against a new plan with new results targets over a reduced timeframe. The findings of this Annual Review reflect on a programme in transition. At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.

The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect. ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises. The UK remains committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

SSEIP II has two components[1]:
[1] A third Pillar providing enhanced Community Engagement was planned in the SSEIP II Business Case (up to £10m), but had already been indefinitely postponed due to budgetary constraints.
- Pillar 1 (assessed under Output 5): support to policy and planning reform – through Technical Assistance (TA) to the MBSSE – for improved education for girls and children with disabilities. Delivered through an Accountable Grant Agreement of GBP 3.6m with Education Development Trust (EDT), which commenced on 1 December 2023. The period under review in this report covered the first and last full year of implementation for this Pillar – which will close in March 2026 due to the reduction in ODA.
- Pillar 2 (assessed under Outputs 1-4): support to strengthen government systems – enhancing MBSSE capacity nationwide to deliver safe, free quality education, particularly for adolescent girls and children with disabilities. Delivered through a Contract of GBP 19m with Mott Macdonald (MM), which commenced on 1 April 2023. This component is known as Leh Wi Lan (LwL, “let us learn” in Krio). This pillar acts at national, district and school level across the entire country, although some specific interventions take place only in five pilot districts – a planned scale up for the 2025/26 school year was re-considered due to Mott Macdonald’s decision to exit the international development sector and early closure (this pillar will phase out – stopping work at school and district level in July and closing fully in December 2026).

Summary supporting narrative for the overall score in this review
The programme has been through significant uncertainty during this review period due to changes to the UK ODA budget, resulting in the decision to close the programme early. Fiscal space remains limited in Sierra Leone and this impacts public sector expenditure. Despite these significant challenges, SSEIP II has continued to perform well, with positive stakeholder feedback at all levels, from senior leadership of MBSSE and TSC to district education officials, school leaders, teachers and students. The introduction of systems strengthening milestones in the logframe has also tackled some previously reported tension between timely delivery of interventions and collaboration with system actors – GoSL and other development partners. Some key achievements from the period have included:

- Improving coherence between in-service and pre-service teacher training through the establishment of the Pre-Service Teacher Education Forum, supporting stronger relationships and collaboration MBSSE, TSC and the Ministry of Technical and Higher Education (MTHE).
- Strengthening district coordination for effective education service delivery, through improving communication and systematic reporting between national and district level actors at MBSSE and TSC.
- Consolidating efforts to support School Quality Assurance Officers supportive monitoring approach through the introduction of a new School Quality Assurance tool, dashboard and digital tracking to enable tracking of all relevant school indicators, and prioritisation and follow up on school visits.
- Strengthening school leadership through increasing the scale of the School Leadership Programme, including improving the number of female leaders engaged, and working with TSC and Institutes of Higher Education to embed the programme within the national system.
- Highlighting the importance of disability inclusion increasing the number of schools with active Inclusion Champions and having this category of teacher recognised as a core part of the government system at the Presidential Best Teachers Awards in 2025.
- Empowering young people to understand and report School-Related Gender Based Violence through work at national, district and school level, resulting in a doubling in the percentage of students with sufficient knowledge about Sexual and Reproductive Health and Rights (SRHR).

The decision to close the programme meant that several school-level interventions – notably work on School Safety Committees, Girls’ and Boys’ Clubs, and Inclusion Champions – that had been piloted in the initial stage of the programme were not scaled up. Although these interventions have been beneficial, the small proportion of schools that benefitted (200 schools in five districts of Sierra Leone) has led to a missed opportunity to embed these practises and learn lessons from them across the system. As part of the transition plan, the BHC will continue to advocate for their systematisation and sustainability.

As the programme has scored an A in all output sections, and has also performed well in systems-strengthening efforts, the programme scores an A overall for this period.

Major lessons and recommendations for the year ahead
As the programme is closing early, during the next review period, all recommendations concern responsible exit and sustainability of the programme:
1. Programme Sustainability Beyond Closure: The British High Commission (BHC) in Freetown should continue working with SSEIP II partners on the sustainability action plan, providing regular updates and supporting GoSL plan for sustainability of interventions after programme closure.
2. Identify Potential Partners/Donors for Unembedded Initiatives: BHC and SSEIP II partners should actively seek new partners or donors to support initiatives not yet embedded in government practice, such as the Boys and Girls clubs and Inclusion Champions, to ensure continuation and scale-up.
3. Handover of Tools, Materials, and Learning: BHC and SSEIP II partners should ensure all policy products, planning tools, training materials, data and documentation are handed over to MBSSE and TSC with clear guidance for ongoing use and ownership. Share lessons learned and evidence to inform future policy and sector reforms.
4. Support Integration and Accreditation of the School Leadership Programme: BHC and SSEIP II partners should continue working with TSC and higher education institutions to ensure the School Leadership Programme is accredited, integrated into national systems, and supported beyond the programme’s end.
5. Expand and Deepen Disability Inclusion Efforts: BHC and SSEIP II partners should work with GoSL to embed the position of Inclusion Champions within the system, and scale up the numbers of schools with Inclusion Champions. Advocate for the Screening, Assessment, Referral, and Follow-up (SARF) approach to be integrated into national systems.
6. Embed Safeguarding and Wellbeing Practices: BHC and SSEIP II partners should support MBSSE and district teams to embed safeguarding and wellbeing practices, such as Girls’ and Boys’ Clubs and School Safety Committees, into school routines and policies for local ownership and sustainability, and work with other donors to sustain and scale up School Safety Practices.
7. Strengthen Data Systems and Evidence-Based Decision Making: BHC and SSEIP II partners should support the final development and handover of education data systems, systematise the Education Data Working Group for sustainability, and provide training for district staff and IT clerks to use and maintain these systems effectively.
8. Consider linkages with other UK funded initiatives: Several other programmes funded by the UK – managed by BHC Freetown, centrally managed, and multilateral investments – have complementary objectives with SSEIP II (e.g. the MOVE programme which includes work on School Related Gender Based Violence). BHC teams should work together to ensure cohesive systematisation of interventions.

Progress against recommendations from last year’s Annual Review can be found in Annex C, with good progress against all overarching recommendations.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case
The SSEIP II Theory of Change and logframe were refreshed – by the BHC, MM and EDT with support from the Evaluation Quality Assurance and Learning Service (EQuALS) helpdesk – during the current review period following a recommendation in the 2025 Annual Review. The purpose of this review was to confirm targets remain reasonable and ambitious and reflects the indefinite postponement of Pillar 3 (which was to focus on community engagement). The update also enabled a new focus on systems strengthening, as well as delivering discrete deliverables. Working to strengthen the national education system is challenging and can lead to a tension between timely delivery of interventions and sustainable progress in all outputs. However, the refresh did not lead to any significant changes to the overall programme shape or objectives.

The intermediate outcome (“Sierra Leone’s education system is more effective, efficient and resilient at every level to deliver its ambitious reform agenda and driver the conditions for improvements in learning”) is new to demonstrate the emphasis on systems strengthening. The impact and outcome statements have changed slightly – this was approved by the SRO in compliance with the PrOF rules. New indicators are:

	Business Case	New Theory of Change
Impact	Improved education and health outcomes for adolescent girls and children with disabilities, leading to more opportunities and choices.	Improved learning, health and wellbeing outcomes for learners in Sierra Leone, especially for adolescent girls and learners with disabilities, leading to better opportunities and choices.
Outcome	Adolescent girls and children with disabilities will stay in secondary school or alternative safe spaces and be able to learn, progress, be safe and have improved life choices.	Learners in Sierra Leone, especially adolescent girls and learners with disabilities, access, stay in, and complete secondary school in safe and inclusive learning environments.

One additional change was the addition of Systems Strengthening indicators to Outputs 1-4 (as discussed in Section C below) to ensure that systems strengthening and delivery were both captured and measured.

The new Theory of Change is as follows:

Throughout this review period the programme partners (BHC, MM, and EDT) have focussed on coordination with the Government of Sierra Leone (GoSL) and other donor programming across the education sector, particularly the World Bank and the Global Partnership for Education (GPE – implemented by UNICEF) to improve harmonisation across interventions at primary and secondary level which is vital to a systems strengthening approach.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

As part of the refresh of the theory of change and logframe, some changes were made to impact and outcome indicators – mostly due to challenges in data availability which meant that previous indicators could not be tracked. Changes were approved by the SRO six months before this Annual Review date, in compliance with the PrOF Rues. Full details are available in Annex B – the current logframe impact and outcome indicators are set out in the table below:

Impact Indicators		Baseline	2023/24	2024/25	2025/26
Number of boys and girls passing the end of secondary school examinations (BECE & WASSCE)[2] with maintenance of gender parity	Planned	JSS (BECE): 124,477 (50% girls) SSS (WASSCE): 62,559 (50% girls)	BECE Baseline +5,000 (50% girls) WASSCE Baseline +5,000 (50% girls)	BECE Baseline +10,000 (50% girls) WASSCE Baseline +10,000 (50% girls)	BECE Baseline +15,000 (50% girls) / WASSCE Baseline +15,000 (50% girls)
	Achieved		Data not available	JSS (BECE): 119,801 (51% girls) / SSS (WASSCE): 39,982 (52% girls)	JSS (BECE): 114,709 (51% girls) / SSS (WASSCE): 47,434 (51% girls) / Not Met
Rate of early marriage of girls under 18	Planned	30%	28%	27%	26%
	Achieved		Updated data not available	Updated data not available	Updated data not available
Adolescent fertility rate: the number of 15-19 year old girls who gave birth (per 1,000 girls per annum)	Planned	103.5 per 1,000	100	95	90
	Achieved		100.9 (2021)	97.9 (2022)	94 / Not Met
Outcome Indicators		Baseline (2022)	2023/24	2024/25	2025/26
Number of girls enrolled in JSS and SSS	Planned	JSS: 298,930 SSS: 203,108 NFE: unavailable	JSS: Baseline + 12,000 SSS: Baseline + 12,000 NFE: Baseline + 8,000	JSS: Baseline + 24,000 (322,930) SSS: Baseline + 24,000 (227,108) NFE: Baseline + 16,000	JSS: Baseline +36,000 / SSS: Baseline +36,000
	Achieved		JSS: 299,728 SSS: 224,358 NFE: unavailable	JSS: 338,031 SSS: 264,732 NFE: unavailable	JSS: 353,048 / SSS: 276,791 / Met
Number of children with disabilities enrolled in secondary schools	Planned	7,086 (3,600 boys; 3,486 girls)	Baseline +2,700 (with gender equity)	Baseline +5,880 (with gender equity)	Baseline + 8,820 (with gender equity)
	Achieved		10,684 (5,530 boys; 5,154 girls)	Data not available	13,489 (7,007 boys; 6,482 girls. / Not Met
Girls’ Gross Completion Rate (GCR) junior and senior secondary schools	Planned	JSS 90%, SSS 89%	Maintain girls' GCR above 90% in JSS and SSS	Maintain girls' GCR above 90% in JSS and SSS	Maintain girls' GCR above 90% in JSS and SSS
	Achieved		JSS 98%, SSS 106%	JSS 95%, SSS 96%	JSS 94%, SSS 98% / Met
[2] Basic Education Certificate Examinations (BECE) and West African Senior School Certificate Examination (WASSCE)

The two impact indicators where data is available have not been met. However, this is a reflection of changing circumstances and ambitious targets, rather than a disconnect between activities and impacts. For indicator 1, the number of children passing BECE is lower than the baseline figure, and has reduced from last year. The number of students passing the WASSCE is also lower than the baseline, but has increased from last year. Gender parity has been sustained for both indicators. The decline in BECE and WASSCE passes since the baseline reflect two systems-wide changes to the examination process:
- First, MBSSE have tightened examination integrity controls and used data audits to identify “ghost candidates” and duplicate registrations. The result is that many thousands of results which would have counted as passes in previous years (including the baseline year) are now withheld.
- Second, the introduction of Continuous Assessment Scores (CAS) as part of the West African Senior Secondary School Certificate of Education (WASSCE – the senior secondary school leaving exam), which require schools to upload continuous assessment data digitally, has resulted in many thousands of students from non-compliant schools being prevented from sitting exams and having their results withheld[3].
  [3] The programme has been supporting this process – and this year 100% of the 1044 schools registered on the WAEC platform uploading SSS1 Continuous Assessment Scores (CAS) for students now in SSS3 who will sit the WASSCE exam this academic year (approximately 15% of schools failed to do this last year).
These factors combined have constrained national examination outcomes in Sierra Leone and meant that the programme’s targets, in hindsight, were unrealistic.

For indicator 3, the adolescent fertility rate has decreased, but at a lower rate than targeted. The adolescent fertility rate (estimated by the UN) declined steadily over the reporting period, falling from 103.5 per 1,000 at baseline to 93.6 in 2023. Although this improvement fell short of the target (90 per 1,000), the observed trend reflects strong progress during a difficult period, when COVID-19 interrupted adolescent pregnancy prevention mechanisms (contraceptive supply chains were disrupted and SRHR outreach was reduced) and increased the vulnerability of adolescent girls (through school closures and increased household economic stress) with spillover effects in fertility outcomes in the aftermath. To add to this, evidence from Sierra Leone and comparable settings indicates that changes in adolescent fertility typically occur more gradually (c.2-3 percentage points per year) than the programme’s targets anticipated (5 percentage points per year)[4].
[4] World Bank – Sub‑Saharan Africa adolescent fertility trend (UN Population Division data): World Bank data shows that adolescent fertility when aggregated across Sub‑Saharan African countries has declined steadily, but slowly from the mid-1970s, reaching 93 births per 1,000 in 2023. Between the peak in 1974 (162) and 2023 (93), the average annual decline was c.1.4 points per year. Over the same period, the average decline in Sierra Leone was c.2.2 points per year. https://data.worldbank.org/indicator/SP.ADO.TFRT?contextual=region&locations=ZG-SLSocioeconomic and geographical inequalities in adolescent fertility rates in Sierra Leone, 2008–2019: This study reports that Sierra Leone’s adolescent fertility rate fell from 142.5 (2008) to 103.5 (2019) — a reduction of 39 points over 11 years, or c.3.5 points per year. https://journals.plos.org/plosone/article?id=10.1371/journal.pone.0313030

The programme has been more successful in meeting its Outcomes. Outcomes 1 and 3 were met, and significant progress has been made under Outcome 2, although it has not been met. The number of girls enrolled across Junior and Senior Secondary School has increased 25% from 502,000 to 630,000 with the completion rate for these girls remaining over 90%. The number of children with disabilities enrolled in secondary education has increased by 90% (from 7,000 to 13,500) reflecting steady and impressive progress. The programme is supporting both gender and disability equality in a challenging context: high levels of SRGBV facing girls and particularly girls with disabilities, COVID-19 which caused learning loss disproportionately for the most marginalised groups, systems without standardised processes to identify and support children with disabilities, and where the understanding and ability of school leaders to absorb marginalised groups lags behind policy commitments for inclusive education.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Despite progress in enrollment – particularly for girls and learners with disabilities, Sierra Leone continues to face very low learning outcomes for learners at all levels, and systematic weaknesses that impact delivery of activities. Supporting systems strengthening to improve Human Development Outcomes remains a focus for the UK, and the programme is highly valued by Government and community stakeholders. The programme has continued to perform well, meeting or substantially meeting all output indicators over this review period. However, BHC Freetown’s funding context has changed since the original Business Case was approved, and a decision has been taken to close the programme early in 2026. The remainder of the programme’s life will be dedicated to finalizing priority actions where possible – focusing on the most impactful systems strengthening work and supporting transition and sustainability. The logframe will be refreshed to reflect this.

## C. DETAILED OUTPUT SCORING

Output Title	Strengthened monitoring, supervision and support for schools by districts
Output number:	1	Output Score:	A
Impact weighting (%):	20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.2: Percentage of schools monitored and supported through school quality assurance processes (disaggregated by school type and district)	70% of JSS and SSS receive a physical visit or remote support from an SQAO at least once per year	Exceeded. 84% of JSS and SSS received physical visits from SQAOs at least once per year.
	System strengthening milestones: / Mechanism for SQAOs to prioritise visits based on evidence developed. / Pilot completed on remote support by SQAOs	Met. New SQAO dashboards now prioritise school visits based on performance, currently using whether a school has had a visit with the new SQA tool. As coverage increases, other criteria like average scores and exam data will be used. / Met. LWL piloted remote SQAO support and reviewed its effectiveness, sharing findings with the MBSSE Education Data Working Group. All schools in the pilot also received physical visits, indicating remote support improved follow-up but did not increase physical visits.
1.4: Percentage of SQAOs who (a) take part in quarterly structured peer learning activities (b) use the Chatbot tool designed to support the provision of feedback to schools (disaggregated by gender and district)	(a) 80%; / (b) not applicable this year (Chatbot under development)	Moderately Exceeded. Three SQAO peer learning sessions were held in February, April, and November. 83% of SQAOs (142/171) attended all sessions, with district participation ranging from 100% to 60%.
	System strengthening milestones: / Development of Chatbot with select functionalities completed including small-scale, user-testing / Pilot phase of new SQA tool completed	Met: An SQAO chatbot was developed and tested, but not continued due to budget constraints. / Met: The new SQA tool was developed and tested (April–July). Feedback from MBSSE and partners informed updates before full deployment in 2025-26
1.5: Number of districts (e.g. DDs) who use SQAO-collected and other system data to inform targeted actions on core priorities at monthly PMMs	12 districts hold PMMs in at least 75% of months, use SQAO-collected and other system data to inform targeted actions on core priorities and agree on appropriate actions.	Exceeded. 15 of 16 districts held PMMs in at least 7 months (75%), using SQAO and system data for decisions.
	System strengthening milestone: / Support provided to improve district- and national-level routines to better incorporate and support the use of SQA data.	Met. Support included developing an SQA data dashboard for easier school performance analysis and training IT officers and DDs to use it. Quarterly routines on key indicators between National level and DDs were also agreed with the School Quality Assurance and Monitoring Director.
1.6: More effective management and development of the SQAO cadre (qualitative indicator)	SQAO management system developed and process for updating it agreed	Met. A digital SQAO management system was developed and tested, integrated with the School Master List for automatic updates and designed for dashboard compatibility and future FLN SQAOs.

Briefly describe the output’s activities and provide supporting narrative for the score
Output 1 aims to improve school management by supporting and professionalising the SQAOs, enabling them to provide regular, high-quality support to secondary schools. It strengthens school quality assurance by increasing the proportion of schools monitored and supported (Output 1.2), encouraging SQAOs to participate in quarterly peer learning activities (Output 1.4), and promoting the use of SQAO and system data by districts to inform targeted actions at monthly meetings (Output 1.5). The output also prioritises the effective management and development of the SQAO cadre (Output 1.6), with system strengthening indicators now embedded across all outputs. All indicators were met, with three exceeding their targets (one moderately so), resulting in an overall score of A for this output. As a result of the work under this output, SQAOs are now more confident in what to look for when monitoring schools, and have methods to provide advice and follow up to school leaders. District staff can access an overview of school quality in each district and able to manage SQAO visits and workload.

Enhancing School Support with a Comprehensive Data Dashboard
The introduction of the improved SQA data dashboard has changed how school quality is monitored and supported in Sierra Leone. With more detailed and accessible data, district teams and School Quality Assurance Officers (SQAOs) can now track which schools have been visited, when visits occurred, and identify areas where further support is needed. This has been supported by a shift from focusing on the total number of schools visited to monitoring the proportion of schools reached, helping to ensure support is distributed more evenly. The dashboard is supporting more informed decision-making, allowing districts to prioritise visits and address challenges as they arise. In the past year, 84% of secondary schools received at least one visit, and districts are using dashboard data to guide ongoing improvements. This approach is helping to strengthen accountability and ensure that all schools are included in efforts to improve education quality.

Output 1.2 was exceeded: 84% of JSS and SSS schools receiving at least one physical visit from SQAOs. System strengthening milestones were achieved through the introduction of the SQA data dashboard which enhanced evidence-based planning and prioritisation of school visits (based on need and date of last visit). Some SQAOs continued to face challenges in meeting visit targets due to logistical constraints, such as poorly maintained motorbikes and inaccessibility of schools during flooding. Remote support mechanisms presented partial mitigation to this, enabling sustained engagement with schools (although thesecannot replace in-person visits).

Output 1.4 was achieved: three SQAO peer learning sessions were held in February, April, and November, with 83% of SQAOs (142 of 171; 31 women, 111 men) attending all sessions.. To improve sustainability and reduce costs, additional training materials which support self-study and peer learning have also been developed. The new External SQA digital tool was collaboratively developed and piloted nationally, enabling evaluation across six domains. Chatbot pilot testing began but was paused due to funding prioritisation. A lessons learnt paper was shared.

Output 1.5: was exceeded: 15 out of 16 districts held Performance Management Meetings (PMMs) in at least 75% of months using the 5D Framework[5] to inform targeted actions on core priorities. Examples of actions taken include: in Kenema a drop in attendance was noted following the holidays – parental engagement was carried out to encourage timely return to school, and in Western Area Urban it was noted that many school do not have functioning school safety committees or suggestion boxes, so SQAOs were asked to make this the priority for future school visits – to ensure the importance of school safety is understood. System strengthening support included the development of – and district training on – an SQA data dashboard for easier school performance analysis.
[5] Dashboards, Data, Discussion, Decision, Delivery

Output 1.6 was met: a digital SQAO management system was developed and tested with MBSSE and district directors, including automated integration with the School Master List ensuring accurate SQAO-school allocations as school numbers or staffing change. National rollout to district directors and IT officers was completed in November 2025. In June and November 2025, SQAOs completed self-assessments using the MBSSE competency framework. Overall, the results suggest that SQAOs are confident in delivering core functions, while requiring further support to strengthen data use, digital skills, and deepen the quality of support provided to schools. Targeted support was provided, including enhanced data tools, peer learning, and problem-solving resources.

Describe any changes to this output during the past year, and any planned changes as a result of this review
Several major changes were made to the logframe under Output 1 during this review period. Output indicator 1.1 was discontinued and replaced with 1.2, shifting the focus from the number of SQAOs’ school visits to the percentage of schools monitored and supported, to reflect the spread of support to schools. Output indicator 1.3 was replaced with 1.4, which now also tracks SQAOs’ use of the Chatbot tool to support school feedback (although this was later cut for budget reasons). A new qualitative indicator, 1.6, was introduced to capture improvements in SQAO management and development. Output indicator 1.7 was discontinued, as system strengthening objectives are now embedded within each indicator.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Progress on last year’s recommendations:
Recommendation	Progress
SSEIP II (Pillar 2) to continue working with key stakeholders through the SQAO Technical Working Group (TWG) to ensure better collaboration. Particular attention should be paid to coordinating various digital tools used by SQAOs to reduce workload and confusion, and data fragmentation at the systems level (ongoing).	SSEIP II Pillar 2 has been active in SQAO TWG meetings since they started. We have used this forum to coordinate with the MBSSE and the GPE on the development of the SQA tool and on the role of SQAOs, including the new FLN SQAOs. The MBSSE lead for the TWG left in May, and a new director was appointed, so meetings have been on pause. However, SSEIP II Pillar 2 are supporting this to restart.
SSEIP II (Pillar 2) should provide continued support to Districts to critically evaluate data to further improve evidence-based decision making (ongoing – with plan for how to do this by April 2025). Logframe review to ensure that the quality (not just frequency) of SQAO visits is captured (April 2025).	The new SQA tool makes it easier to evaluate data as it provides clearer scoring and enables easier to understand benchmarks and rankings. This is being used to support improved evidence-based decision making. Though agreeing on which performance criteria are priorities still needs work. There was no agreed way to measure SQAO visit quality and so this wasn’t included in the logframe. However, the new SQA tool now enables more consistency in scoring and feedback, and this is being tracked to improve quality. In addition, discussions with MBSSE about peer review processes of SQA are in process.
BHC and SSEIP II to advocate with MBSSE and GPE stakeholders for payment of district IT clerks (ongoing). BHC’s funding on a Public Expenditure Tracking Survey over this reporting period should also support understanding (by March 2026).	Through various discussions that have involved SSEIP II partners, GPE have agreed to pay the MBSSE IT officers.
BHC and SSEIP II to coordinate with stakeholders, including other UK investments (e.g. EdTech Hub) and other programmes to consider how our joint investments can best collaborate to support the MBSSE on strategic data work (ongoing – with plan for how to do this by April 2025).	In a bid to drive a shift from project data needs to system-data driven needs, the programme led the presentation of the entire education data systems, tools and purposes to MBSSE leadership to showcase the availability of various data tools, its purpose, use and lay the basis for coordination of these data systems to ensure linkage to each other and enable data-driven decision making. Additional work is needed to strengthen the overall data system, to improve coherence, use of data, and as a core part of the sustainability of SSEIP II. Next steps are suggested in the third recommendation below. / In addition, across Pillar 1 and 2 data tools have been more effectively integrated this year with the School Master List, SQAO Management Rosters, External SQA tool and Integrated Data Dashboard now linked and talking to/supporting each other.

Lessons learned this year, and recommendations for future years:
Lesson	Recommendation
Peer learning sessions and new digital tools have contributed to increased confidence and professionalisation among SQAOs. However, ongoing support is needed to address remaining gaps in digital skills and data use, and to ensure that districts are able to critically evaluate and apply data to improve the quality and impact of school support.	SSEIP II (Pillar 2) to continue to support peer learning, self-study materials, and targeted digital skills development for SQAOs and district staff. Provide ongoing support to ensure all districts can confidently interpret and use data to inform decision-making and improve the quality and impact of school support (Ongoing).
Shifting from counting the number of school visits to monitoring the proportion of schools reached has enhanced both equity and coverage of support. However, persistent logistical challenges—such as poorly maintained motorbikes and schools becoming inaccessible during flooding—continue to hinder some SQAOs from meeting their targets. While remote support has helped address some access issues, in-person visits remain crucial for effective school quality assurance. Ongoing logistical constraints particularly affect the reach and impact of SQAOs in hard-to-reach areas.	Continue to advocate for and secure sustainable funding for SQAO transport (motorbikes, fuel, and maintenance) to ensure all schools, including those in remote areas, receive regular in-person support. Explore partnerships or alternative funding sources if government resources remain limited (BHC and Pillar 2, Ongoing).
The data showcase in September 2025 was a really helpful way to demonstrate the availability of various data tools, their purpose and use, and lay the groundwork for coordination of these data systems to ensure linkages – however, data tools, dashboards and use remain fragmented.	Pillar 2 to set out a complete plan for data sustainability and legacy, working with Director of School Quality Assurance and Resource Management to support the re-constitution of the SQAO TWG, continuing to strengthen reporting routines between district and national levels on the SQAO Dashboard, and working with the Education Data Working Group to support data cohesion following the initial meeting. (Ongoing, with plans in place by March 2026).

Output Title	Strengthened school leadership and teaching for inclusive learning
Output number:	2	Output Score:	A
Impact weighting (%):	25%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
2.2: Number of secondary school leaders who (a) enrol on and (b) complete the core School Leadership Programme (disaggregated by gender, disability and type of leader).	a) 300 additional school leaders enrol (at least 20% women); / b) 500 school leaders complete the Core Course.	a) Met 300 school leaders (32% female) were selected for Cohort 3 across all 16 districts in August 2025. / (b) Substantially met: Of the 500 school leaders enrolled in cohort 1 (150) and cohort 2 (350), 492 completed the programme. Sadly, 3 school leaders died over the year and 5 dropped out of the course.
	System strengthening milestones / First four toolkits updated based on learning from cohort 1 and 2 / Request for accreditation of the SLP Core Course submitted by TSC / School leadership policy drafted and shared with Cabinet for review and approval / Completion and dissemination of study/communication piece capturing learning from first and second cohort of SLP participants	I. Not met: Three of four toolkits updated, with toolkit 3 delayed (to be ready in time for the school leaders to use by April 2026). II. Met: SLP accreditation process started with five universities; curriculum preparation underway. III. Not met: School Leadership Policy developed and validated; awaiting CEO review and ministerial approval. IV. Met: Information brief on school leader surveys and research disseminated at key meetings; further study planned for summer 2026.
2.3: Percentage of LLLs that achieve the targets defined in the toolkits for (a) in-person visits and (b) remote contact with school leaders	Tracking system to record LLL support and participants progress through the SLP is designed, set up and tested	Met: developed three data collection tools and a dashboard, now live.
2.4: Number of JSS and SSS organising school-based continuous professional development (SB-CPD) using content developed by SSEIP II (disaggregated by district)	500 JSS and SSS	Met: In 2024/25, 505 out of 550 supported schools are delivering regular SB-CPD using SSEIP II content.
	System strengthening milestone: / Completion of SB-CPD framework	Met: SB-CPD framework completed and approved by TSC.

Briefly describe the output’s activities and provide supporting narrative for the score
This output supports the TSC and MBSSE to establish an accredited School Leadership Programme (Output 2.2s and 2.3) and a national system for school-based continuous professional development (SB-CPD) (Output 2.4), ensuring key school staff have the skills, knowledge, and support needed to perform effectively. All milestones were met except for two out of four of the systems strengthening milestones were only partially met resulting in an overall score of A.

Stronger Together: The Impact of School Leadership on Safety and Collaboration
Participation in the School Leadership Programme has transformed the work, attitude and motivation of school leaders. They have built lasting relationships with fellow leaders, teachers, learners, and the wider community, creating a strong network for teamwork and problem-solving. This collaboration has led to practical changes, such as rearranging classrooms into group tables to encourage peer learning and developing and implementing school development plans. Leaders report that the programme has increased learner safety in and around schools, notably through the adoption of positive discipline practices and the replacement of corporal punishment. Technology training has enabled leaders to manage administrative tasks more efficiently and access new learning materials. Feedback from School Leaders shows that support from Local Leaders of Learning (LLLs) has been invaluable, providing round-the-clock support to school leaders.

Output 2.2 was partially met – In August 2025, 300 additional school leaders (32% women) were selected for Cohort 3 of the School Leadership Programme (SLP) across all 16 districts, surpassing enrolment targets and improving gender representation. Of the 500 leaders enrolled in Cohorts 1 and 2, 492 completed the Core Course, with 452 achieving a pass mark under the TSC-approved assessment protocol Two out of the four system strengthening milestones were achieved in full and two were partially achieved - - three of four toolkits have been updated, SLP accreditation and policy development processes are underway, and key research findings have been disseminated to stakeholders, with further study planned for 2026. Further work gearing towards government uptake and sustainability of the model included strengthening the assessment process with future assessments now at the end of each toolkit. Expansion of the programme was led by TSC district teams (with support from SSEIP II), with targeted efforts to increase female participation. Systematisation is progressing, with a validation workshop held with higher education institutions and a draft strategy for handing over the SLP to Teacher Training Institutions (TTIs). Accreditation is underway, and the School Leadership Policy will further support long-term integration. Participant feedback remains positive, and further qualitative research is planned to inform the continued scale-up of the programme.

Output 2.3 was met – The tracking system for LLL support and SLP participant progress has been designed, set up, and tested. The team developed three data collection tools and an LLL dashboard: the weekly monitoring report and school visit report, and the school leader performance tool. By early November 2025, all LLLs were using the weekly report, and 60% had used the school visit tool. The performance tool tracks school leader progress and flags concerns. The dashboard, live since August 2025, enables regular monitoring and supports ongoing programme improvements.

Output 2.4 was met – In 2024/25, 505 out of 550 supported JSS and SSS schools delivered regular SB-CPD using SSEIP II content, moderately exceeding the milestone. The TSC has also approved the SB-CPD framework, which will be annexed to the School Leadership Policy, making regular continuous professional development mandatory for school leaders, representing progress in embedding these practices at school level and strengthening the system.

Describe any changes to this output during the past year, and any planned changes as a result of this review
Several changes were made to this output over the past year – linked to the recommended ToC and logframe refresh in the last Annual Review, and early programme closure. Targets for indicator 2.2 were reduced due to the high cost and management challenges of supporting sufficient LLLs. The original plan to develop multiple SLP courses was scaled back to focus on improving and sustaining the current programme, leading to the removal of indicator 2.1 and the addition of toolkit revision as a system strengthening target. Indicator 2.3 was introduced to reflect the critical role of LLLs and the need for real-time data on their work. Output indicator 2.5 was discontinued due to difficulties in collecting reliable attendance data.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Progress on last year’s recommendations:
Recommendation	Progress
SSEIP II (Pillars 1 and 2) to collaborate with TSC to understand current and future requirements for trained school leaders and use that to plan for a sustainable build up and roll out for future years, including a plan for accreditation (ongoing from last Annual Review) (by August 2025). SSEIP II (Pillar 2) to also share plans with other donors and programmes for use and adaptation at primary level if relevant (by April 2026).	Driven by the decision to close the programme early, BHC and Pillar 2 partners chose to focus on accelerated systematisation of the course. The TSC does not have easy access to data on the numbers of principals, vice-principals, heads of department and senior teachers are in the system – this requires further investigation as the data may be part of payroll data. It is possible to make projections, but for the SLP to be successful (and in demand) it is important to keep admission competitive for those who are willing to commit time and effort to completing the programme. The target scale of the SLP will be calculated next year (MM and LGI).
SSEIP II (Pillar 2) to work with TSC to consider ways to improve and encourage data collection – including exploring partnerships with other TSC partners including CGA technologies (by August 2025).	TSC have stated that they would need further financial support to upgrade the Teacher Management Information System to be able to record SB-SPD. However this is outside the scope of the programme and no alternative funding has been identified.
SSEIP II (Pillar 2) to consider evidence behind impact of SB- CPD on learning outcomes, and provide recommendation for the future of this component (given overarching recommendations on learning outcomes (by April 2025).	Due to the decision to close the programme early, BHC and partners jointly agreed to reduce focus on learning outcomes, given the need to accelerate sustainability.

Lessons learned this year, and recommendations for future years:
Lesson	Recommendation
The School Leadership Programme has improved collaboration, safety, and leadership in schools, but sustaining and scaling the programme requires continued coordination with higher education institutions and the TSC.	Continue to work with TSC and higher education institutions to ensure the sustainability and accreditation of the School Leadership Programme, including a clear strategy for handover and integration into national systems, and seeking additional donor funding to support (Pillar 2, by June 2026)
Targeted strategies have increased female participation in school leadership, but sustained efforts will be needed to continue to address gender disparities and ensure equitable access to leadership opportunities. This will include boosting overall gender participation in the teaching workforce	Maintain and strengthen targeted strategies to increase the participation of women in school leadership, including conducting research to better understand barriers and enablers, sharing this with future partners as lessons learned (MM and LGI by March 2026).
The introduction of SB-CPD frameworks and regular monitoring tools has strengthened professional development, but reliable data on school leader appointments and SB-CPD participation remains a challenge.	Collaborate with TSC and partners to improve data collection and management systems to track school leader appointments and SB-CPD participation, supporting better planning and monitoring (Pillar 2, by June 2026).

Output Title	Strengthened systems for inclusive education for children with disabilities
Output number:		3	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1: Percentage of schools with trained Inclusion Champions (disaggregated by gender and disability).	40% of 200 pilot schools.	Exceeded: 60% of 200 pilot schools have active Inclusion Champions—62% in JSSs, 54% in SSSs—meeting 6 of 8 criteria.[6]
	System strengthening milestone: / Paper on roles and selection criteria for ICs presented to and approved by NTAC.	Met. The Inclusion Champions roles and selection criteria paper was approved by NTAC in July 2025, establishing the framework for IC leadership and engagement in schools.
3.4: Percentage of schools with systems in place to connect learners with disability with support they need for learning.	System strengthening milestones: / Approach developed for strengthening processes for screening, referral, assessment and follow-up (SARF) including the tracking of outcomes for learners with disabilities. / Pilot completed on testing approach for SARF of learners with disabilities.	Met: A collaboratively developed school-based SARF approach for learners with disabilities was approved by NTAC, strengthening processes and outcome tracking. / Met: The SARF framework was developed through consultation and validated via a three-phase pilot.
3.6: Percentage of districts with OPDs that are influencing action at district and/or school level to improve education for learners with disability	80% of PMMs/Education meetings attended by OPD representatives.	Met: 81% of PMMs/Education meetings were attended by OPD representatives.
	System strengthening milestone: / Review completed of what constitutes meaningful and effective participation of OPDs in PMMs and district education meetings.	Met: A systems review found OPD participation in PMMs and District Education Committees is most effective through unified district teams, leading to their creation and enhanced engagement.
[6] ‘Active’ Inclusion Champions meet 6 of 8 criteria. Most schools excelled in having trained ICs, inclusion plans, learners with disability records, and disability awareness. Lower results were seen for supporting learners with disability and seeking external support (4 and 8).

Briefly describe the output’s activities and provide supporting narrative for the score
This output focuses on the inclusion of children and adults with disabilities in the education system, with a focus on strengthening school-level interventions (Outputs 3.1 and 3.4) and improving data and expertise for decision-making at district level (Output 3.6). All indicators were met, with one exceeded, resulting in an output score of A.

Championing Inclusion: The Vital Role of Inclusion Champions in Schools
Trained Inclusion Champions (ICs) in each school play a crucial role, offering expert guidance and fostering a network for collaborative problem-solving with other ICs, school leaders, teachers, parents and communities. Their training enables practical classroom adaptations – such as moving visually impaired learners to the front – and promotes acceptance and inclusion amongst fellow learners. ICs also ensure learners receive specialist referrals through the SARF approach. Without ICs and their training, support for learners with disabilities would be limited, fewer classroom adaptations would be made, and collaboration among staff would decrease, leaving children with disabilities at greater risk of marginalisation. Further support is needed to raise awareness of hidden disabilities, neurodivergence, and learning differences, as the ICs interviewed overwhelmingly focused on physical disabilities—particularly those affecting learners with visual and hearing impairments.

Output 3.1 was exceeded – 60% of 200 pilot schools now have active Inclusion Champions (ICs), surpassing the 40% milestone in both JSS (62%) and SSS (54%). The system strengthening milestone was met, with IC roles and selection criteria approved by NTAC in July 2025. IC activity criteria were developed, and Communities of Practice established in all five districts to support peer learning. ICs led on School Inclusion Plans (SIPs), formalising their role and setting measurable actions for inclusion. A district-wide training model in Kailahun provided a scalable approach for national expansion. The IC role is now recognised in the revised TSC Act and the President’s National Teacher Awards, supporting sustainability.

Output 3.4 was met – A school-based Screening, Assessment, Referral, and Follow-up (SARF) approach for learners with disabilities was collaboratively developed and approved by NTAC, strengthening systems for identifying and supporting learners with disabilities. The SARF framework was validated via a three-phase pilot[7]. Learning from the pilot is being used to advocate for national adoption and integration of the SARF into education and health systems, with ongoing engagement of MBSSE, MoH, MoSW, UNICEF, and the World Bank. The expansion of NTAC has further strengthened multi-sectoral policy coherence. While progress is evident, ongoing challenges include resource gaps and the need to address cultural and institutional barriers to sustain inclusive practices.
[7] The three steps were: (1) An orientation workshop with 30 teachers from 10 pilot schools and 16 OPD representatives from all districts, who provided feedback on the SARF framework and tools; (2) Inclusion Champions piloted the tools in schools and submitted quantitative feedback on usability, referral responsiveness, and outcomes via KoboCollect; (3) A review workshop in November 2025 analysed the pilot results.

Output 3.6 was met – 81% of PMMs and education meetings were attended by OPD representatives. A systems review on OPD participation found that unified district OPD teams are most effective in influencing action at district and school levels. As a result, OPD District Teams have been established, leading to enhanced engagement and coordination in PMMs and District Education Committee meetings. This approach has strengthened OPD influence within education governance structures and supports more meaningful, effective participation to improve education for learners with disabilities.

Describe any changes to this output during the past year, and any planned changes as a result of this review
Several changes were made to this output over the past year – linked to the recommended ToC and logframe refresh in the last Annual Review, and early programme closure. Output 3 activities were consolidated into three system change pathways for greater coherence and impact. The planned scale-up of Inclusion Champions was limited to one district rather than several.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Progress on last year’s recommendations:
Recommendation	Progress
SSEIP II (Pillar 2) to seek partnerships with stakeholders to explore opportunities for expanding service provision and reducing financial barriers for learners and their families. BHC to seek additional financing through other sources, advocacy with donors and Centrally Managed Programmes (ongoing).	SSEIP II strengthened partnerships to expand inclusive education, showcasing programme work at Output 3 at UNICEF’s 2030 Inclusive Education Strategy launch and engaging with the World Bank, FCDO, UNESCO IIEP and other partners. The World Bank has joined NTAC, with their Gender and Inclusion Specialist attending the next meeting, further supporting advocacy and collaboration. No specific additional finance has been identified but ongoing efforts will be made through the sustainability action plan work.
Continued work should be done to mainstream inclusion issues in all work under SSEIP II Pillar 1. Ensure that disability inclusion focus is represented on the SSEIP II Steering Committee (through head of NTAC – Deputy CEO – or Director of Special Educational Needs). Additional work through the NTAC will be needed to continue to strengthen coordination between donors and GoSL line ministries (ongoing).	SSEIP II mainstreamed inclusion in Pillar 1 by supporting the Radical Inclusion Policy Implementation Plan review and engaging new partners. Discussions continue on integrating Inclusion Champions into School Health and Safety Committees. Output 3 maintained active stakeholder engagement and strengthened advocacy through OPDs and Inclusion Champions, supporting a coordinated approach to cross-sectoral disability inclusion at district level.
SSEIP II (Pillar 2) and BHC will agree new, more ambitious targets during a refresh after this review to focus on depth of knowledge / quality of provision alongside scale up. This should include consideration of the types of disabilities found in schools (for example hearing and visual impairments are not the majority of disabilities, but support is focussed in these areas), more support on low-cost, school-based interventions to support learners with disabilities to learn, and understanding the progress made against systems-level recommendations through the NTAC. This should include moving towards monitoring and assessing quality of support and outcomes for learners with disabilities (April 2025).	Following the review, SSEIP II set more ambitious targets focused on both quality and scale. Inclusion Champions were trained in pan-disability identification and learner support, with clear criteria established for ‘‘Active Inclusion Champions’. Low-cost, school-based interventions were promoted through School Inclusion Plans, and the SARF process enabled better access to service providers for learners with disabilities.

Lessons learned this year, and recommendations for future years:
Lesson	Recommendation
Training and supporting Inclusion Champions (ICs) in schools has increased awareness and practical support for learners with disabilities, but these positions are not systematised and exist only in 200 schools. Additionally, most focus remains on visible disabilities, with less awareness of and attention to hidden or learning disabilities.	SSEIP II to focus on systematisation and sustainability of Inclusion Champions through MBSSE and TSC policies. Advocate for government or partners to take up Inclusion Champion training, including expansion of training and awareness-raising to cover a broader range of disabilities, including hidden and learning disabilities.
The development and piloting of the / SARF approach has improved identification and support for learners with disabilities, but resource and capacity gaps remain for wider implementation.	BHC to advocate with government and partners for the continued scale-up and integration of the SARF approach into national systems after programme closure.

Output Title	Improved safety and wellbeing of secondary school students through addressing School Related Gender Based Violence (SRGBV) and improving knowledge about Sexual and Reproductive Health and Rights (SRHR)
Output number:	4	Output Score:	A
Impact weighting (%):	20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1: Percentage of schools supported by SSEIP II with active Girls' and Boys' Clubs.	70% of 200 schools supported by SSEIP II	Met. Independent data from 50 schools estimated 72% have active Girls’ and Boys’ Clubs (73% JSS, 69% SSS), with district rates ranging from 100% in Port Loko to 40% in Western Rural.
4.2: Percentage of schools with a functioning school safety committees (schools to be disaggregated by district, school type).	70% of 200 schools supported by SSEIP II	Met. Independent data from 50 schools estimated 70% have functioning School Safety Committees (73% JSS, 62% SSS), with district rates from 100% in Port Loko to 50% in Bo and Bombali.
	System strengthening milestones: / SQAOs trained/coached to build capacity of SSCs to report and refer cases of violence / Approval of processes for TSC district staff to manage and monitor GBV cases that involve teachers or leaders	Met: i. SQAOs were trained in February and April 2025 to strengthen SSCs’ capacity to report and refer violence cases, focusing on school safety and inclusion. ii. In June 2025, TSC approved processes for district staff to manage and monitor SRGBV cases involving teachers or leaders.
4.3: Number of individuals (role to be determined, e.g. teacher, SQAO, guidance counsellors, etc) trained with SSEIP II's support for the roll-out of Child and Adolescent Health Skills content (disaggregated by gender, type of training, district).	300 individuals trained on CAHLS with SSEIP II's support	Partially met: 241 SQAOs, principals, and teachers (41 female, 200 male) received refresher training, as SSEIP II focused on existing trainees rather than scaling up the CAHLS pilot due to early close-out.
	System strengthening milestone: / Work commenced to create suitable TLMs for AHLS	Met: Draft TLMs for AHLS in SSS1–3 were discussed with MBSSE in October, revised with feedback, and will now be reviewed by teachers.
4.4: Percentage of students who demonstrate sufficient (or more) knowledge about SRHR and different types of violence at school (disaggregated by gender).	29.7%	Exceeded: 41.2% - 43.3% for males; 39.4% for females
	System strengthening milestone: / Findings from KAP survey presented to MBSSE	Met: KAP survey findings were presented to MBSSE at the TSC Retreat in October and at an AHLS workshop with partners.

Briefly describe the output’s activities and provide supporting narrative for the score
This output focuses on reducing barriers faced by girls to safely access quality education. This work covers support to vital features at the school level (Girls’ and Boys’ Clubs – Output 4.1, and School Safety Committees – Output 4.2), improving knowledge amongst children on SRHR (Child and Adolescent Health and Life Skills (CAHLS) in output 4.3 and measuring knowledge in Output 4.4). Out of four outputs, three were met, and one partially met, so this output scores an A.

Championing Safety and Voice: The Transformative Impact of the Boys’ and Girls’ Clubs
In schools, Boys’ and Girls’ clubs are playing a pivotal role in creating safer, more inclusive learning environments. Supported by weekly supervision from trained school leaders or teachers, these clubs provide a trusted space for students to discuss sensitive issues, build confidence, and support one another. / Through club activities and radio sessions, students are developing a clearer understanding of issues such as sexual harassment and gender-based violence, and crucially, how to report concerns and protect themselves both in and out of school. This has led to increased reporting and a stronger culture of safeguarding, supported by trained staff and active School Safety Committees. / The clubs also foster greater empathy and awareness of the unique challenges faced by both girls and boys, promoting mutual respect and inclusion. Without these clubs, students would have fewer opportunities to learn about their rights, share their experiences, and access support—leaving them more vulnerable to harm and exclusion.

Output 4.1 was met – 72% of supported schools met the criteria for active clubs. Clubs are considered active if they meet four out of five criteria: existence of the club, trained teacher mentors, regular sessions, sufficient membership, and good attendance. At the school level, 73% of JSS and 69% of SSS have active clubs. However, activity rates vary significantly across districts, with Port Loko achieving 100% and Western Rural only 40%[8]. While all schools have trained teacher mentors, ongoing actions such as radio programmes, expanded peer mentor training, and targeted support for low-performing schools are being implemented to further strengthen club activity. District teams are working closely with school leadership to address barriers, with a particular focus on increasing participation in SSS and underperforming districts.
[8] In Western Rural, the percentage of schools with active GBCs was low primarily because of two criteria: (1) 7 out of the 14 GBCs in the 10 sampled schools had two trained peer mentors leading the GBC; (2) 8 of the 14 GBCs had organised at least three sessions in the previous four weeks. In addition 3 of the 10 sampled schools no longer had the requisite 2 trained teacher mentors in place.

Output 4.2 was met – 70% of supported schools have functioning School Safety Committees (73% in JSS, 62% in SSS), with district rates ranging from 100% in Port Loko to 50% in Bo and Bombali[9]. System strengthening milestones were also achieved: SQAOs were trained in February and April 2025 to build the capacity of SSCs to report and refer cases of violence, with a focus on school safety and inclusion. In June 2025, TSC approved new processes for district staff to manage and monitor GBV cases involving teachers or school leaders, further strengthening safeguarding and accountability mechanisms.
[9] Every school sampled in these two districts had an SSC, with the right membership and they had a current action plan. They were scored down because of one or more of (1) not having met in the previous month, (2) not keeping minutes of the last meeting and (3) not using the template provided for recording cases of violence.

Output 4.3 was partially met – 241 SQAOs, principals, and teachers (41 female, 200 male) received refresher training. The shortfall against the target reflects SSEIP II’s strategic decision to focus on strengthening the capacity of existing trainees, rather than expanding the CAHLS pilot, due to the decision to close the programme early. Additionally, draft teaching and learning materials (TLMs) for AHLS in SSS1–3 were collaboratively validated with key stakeholders at a three-day workshop, and have now been validated and presented to the MBSSE and partners.

Output 4.4 was exceeded, with 41% students (43% of males and 40% of females) demonstrating sufficient or greater knowledge about SRHR and different types of violence at school – more than double the baseline of 20% in 2024. The average overall for all the three domains student score increased for all the three domains (knowledge, attitude and practice) by 7% to 56%, with teachers’ scores also rising from 63% to 68%. These improvements reflect SSEIP II’s holistic approach, engaging students, school staff, and district and central-level stakeholders. However, gaps remain, particularly around knowledge of Female Genital Mutilation/Cutting and acceptance of pregnant learners. The programme will continue to respond to this through sharing messages with teachers and mentors for use in both School Safety Committees and Girls’ and Boys’ Clubs. The system strengthening milestone was met, with KAP survey findings presented to MBSSE, TSC, and partners, emphasising the need for continued accountability and commitment at all levels.

Describe any changes to this output during the past year, and any planned changes as a result of this review
Several changes were made to this output over the past year – linked to the recommended ToC and logframe refresh in the last Annual Review, and programme closure plans. The scale-up of Girls’ and Boys’ Clubs (GBCs) and School Safety Committees (SSCs) was accelerated, with both now reaching an additional 300 schools this year, and the remaining 600 radios distributed accordingly. Efforts shifted towards embedding the Girls’ and Boys’ Club model into national systems by sharing all materials with MBSSE and disseminating lessons learnt to donors and partners to support future scaling. SSCs, already integrated into national policies, were further strengthened through guideline development and dissemination with MBSSE. To do this, the expansion of the CAHLS pilot was deprioritised and instead, focus moved to sharing recommendations for future scale-up. For AHLS, teacher guides were developed and handed over to MBSSE, with advocacy for partners such as UNFPA and UNICEF to support implementation. Across all activities, priority was given to sharing tools and learning with MBSSE and ensuring sustainability through the national knowledge platform. Logframe targets were adjusted and system strengthening targets were added to reflect these changes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Progress on last year’s recommendations:
Recommendation	Progress
SSEIP II (Pillar 2) to explore reasons for the disparity between intervention success at JSS and SSS, and put in place interventions to improve presence of Girls’ and Boys’ Clubs at SSS level and to explore what more can be done to support increased knowledge for learners with disabilities. (April 2025).	SSEIP II developed and delivered new content on youth leadership, empowerment, and life skills for SSS Teacher Mentors, who have since cascaded this training to SSS Girls’ and Boys’ Clubs. The content is designed to be interactive and inclusive, with a focus on building confidence and decision-making skills, particularly for learners with disabilities and other vulnerable groups such as pregnant learners. Implementation is being monitored through regular WhatsApp calls with mentors by MM District Staff.
SSEIP II (Pillar 2) to consider strategies to ensure that all children (especially in SSS) get a coherent exposure to CAHLS education – including advocacy with MBSSE (decision on how to support this by April 2026).	SSEIP II strengthened CAHLS delivery at JSS level, with positive feedback from teachers and field visits, and MBSSE expressing willingness to scale up with further partner support. At SSS level, LWL conducted a nationwide survey on AHLS implementation and used the findings to advocate with MBSSE for a more standardised approach. This led to agreement on teacher selection, assessment methods, and the development of teaching and learning materials. Draft teacher guides for SSS1–3 were developed and validated with MBSSE in October, with further feedback from teachers and principals planned for November.
SSEIP II and BHC to reassess the logframe and ensure that it fits the overall purpose of the programme (April 2025). Focus should stay on school-level SRGBV committees (with work coordinated between Pillars 1 and 2), with appropriate reporting mechanisms to District and National levels.	The focus remained on strengthening school-level GBV prevention structures through School Safety Committees. LWL worked with TSC District Officers and SQAOs to clarify SSC responsibilities and improve reporting mechanisms from school to district and national levels. Regular meetings of the MBSSE SRGBV working group were also supported to enhance coordination and collaboration across all levels and central actors.

Lessons learned this year, and recommendations for future years:
Lesson	Recommendation
Girls’ and Boys’ Clubs and School / Safety Committees have contributed to / safer, more inclusive school / environments, but activity levels and / effectiveness vary across districts, with / some schools facing challenges in / sustaining engagement of staff.	SSEIP II to prioritise the handover of all tools, training materials, guidance, and lessons learned on Girls’ and Boys’ Clubs, School Safety Committees, and SRHR/SRGBV content to MBSSE and relevant partners to support continued implementation after programme closure, and inform future interventions and policy development in school safety and student wellbeing (Pillars 1 and 2, throughout 2026).
Embedding safeguarding and wellbeing / initiatives into school and district / routines has increased reporting and / awareness, but ongoing support and / monitoring will be needed after / programme closure.	SSEIP II to support MBSSE and district / teams to embed safeguarding and / wellbeing practices into existing school routines and policies, ensuring local ownership and sustainability.

Output Title	Strengthened policy and planning reform to improve education provision for girls and children with disabilities
Output number:	5	Output Score:	A
Impact weighting (%):	20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1: percentage of specified policy implementation products developed as per tracker for year in review.	75% of specified policy implementation products[10] developed as per tracker for year in review	Met: 80% of products completed (4/5)
5.2: percentage of annual workplan milestones for policy and planning pillar met during the year in review.	85%	Met: 87% of products scheduled have been completed.
5.3: Number of case studies developed and validated with clear story of change.	4 case studies produced during the year in review	Met: / 100% of case studies (4/4 completed)
[10] (1) Teacher Licensing Exam Question Bank System Manual, (2) RIP rapid assessment report, (3) RIP MEL framework, (4) CSSP MEL framework, and (5) partner mapping.

Briefly describe the output’s activities and provide supporting narrative for the score
Output 5 focusses on strengthened systems for MBSSE and TSC, advancing the GoSL’s reform agenda through capacity building and policy implementation.

Unlocking the Power of Data for Better Education Planning
The introduction of the School Master List (SML), developed with support from Fab Inc, has transformed education planning and delivery across Sierra Leone. By providing a single, reliable source of school data, the SML has eliminated duplication, reduced errors, and ensured every school is accurately accounted for. Since its adoption, discrepancies in school records have dropped by 71%, and 94% of School Quality Assurance Officers now report high confidence in updating the SML. District and central teams use the SML to guide resource allocation, monitor performance, and plan interventions with confidence. This shift to evidence-based management has improved service delivery, strengthened accountability, and built trust across the education system.

Output 5.1 was moderately exceeded – four out of five planned policy implementation products were delivered, including:
- Teacher Licensing Exam Question Bank System Manual: step-by-step guidance for managing questions, generating exams, and user access, supporting malpractice mitigation and improved exam quality to strengthen teacher competencies.
- RIP rapid assessment report: a mid-term review of progress and gaps, informing data-driven revisions and accountability for the Radical Inclusion Policy.
- MEL framework for the Radical Inclusion Policy (RIP): enabling systematic monitoring and evaluation, helping MBSSE and partners identify effective practices and make evidence-based decisions.
- MEL framework for the Comprehensive School Safety Policy (CSSP): assessing implementation and impact to ensure efficient resource use and achievement of policy objectives.
These products collectively strengthen policy delivery, monitoring, and accountability in the education sector. The final product – a partner mapping which is intended to support better understanding within the MBSSE of activities across the sector, enabling GoSL to drive more equitable and efficient partner support – is progressing but has faced challenges in collecting partner data. The partner mapping will be completed before the end of the programme, alongside joint reflection with the MBSSE and partners on data sharing systems.

Output 5.2 was met – 87% of planned milestones for this review period were completed. Key achievements include:
- Supported TSC in data-driven recruitment and deployment of over 2,150 teachers, ensuring equitable distribution.
- Completed School Master List refresher training for SQAOs, improving understanding by 15 percentage points.
- Provided technical support for Annual School Census data collection, introducing real-time checks and integrating the School Master List for greater accuracy and sustainability.
- Developed and distributed the Comprehensive School Safety Policy literacy leaflet, and co-created a related MEL framework
- Established a Non Formal Education Working Group to foster collaboration and support policy rollout and, and co-created a Community Engagement Framework and MEL framework for the policy.
- Aligned the school leadership programme with TSC guidelines, supported the new recruitment process, and established the Pre-Service Teacher Education Forum.
These achievements have strengthened education system governance, data management, and teacher workforce reforms.

Output 5.3 was met - 100% (4 out of 4) case studies scheduled for this review period have been completed, including:
Strengthening District Coordination for Effective Education Delivery:
Quarterly Deputy Directors’ Coordination Meetings were institutionalised, improving communication, data flow, and accountability between central and district offices. Standardised processes and feedback loops have enabled more timely, evidence-based management and strengthened ownership of education outcomes.
Turning Fragmentation into Focus – NFE Technical Working Group
The NFE Technical Working Group, established in April 2025, transformed fragmented coordination into a formal, accountable structure. It aligned partner activities, standardised data, and improved planning, enhancing collaboration, government ownership, and advocacy for sustainable sector growth.
Strengthening Data-Driven Planning through the School Master List:
The live School Master List unified school data, improving accuracy and reducing discrepancies by 71%. This system now underpins evidence-based planning and equitable service delivery, with ongoing training supporting sustainability and staff confidence.
Transforming the Education Workforce:
SSEIP II Pillar 1 clarified school leadership roles and improved pre-service teacher education coordination. Achievements include validated guidelines, district training, recruitment tools, and a national forum, standardising leadership and teacher preparation for sustainable improvements in teaching quality and equity.

Describe any changes to this output during the past year, and any planned changes as a result of this review
During this reporting period, output 5.3 was revised to replace the indicator on the Operations and Policy Pillar executive and secretariat functionality with a new measure tracking the number of case studies produced. This change enables more direct assessment of strengthened capacity and the impact of SSEIP II Pillar One interventions within MBSSE and TSC.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Progress on last year’s recommendations:
Recommendation	Progress
BHC and SSEIP II partners to continue proactive and persistent engagement with MBSSE and TSC stakeholders, prioritising joint working and co-ownership over speed of delivery. Monthly management and coordination meetings to continue to enable timely response to emerging priorities and shared ownership of joint thematic areas of interest (e.g. school leadership) across pillars (ongoing).	Both MBSSE and TSC remain consistently engaged and are increasingly taking lead roles in key programme activities. Notably, they have chaired Radical Inclusion Steering Committee meetings, NFE Technical Working Group sessions, School Master Listing training for School Quality Assurance Officers and Deputy Directors, as well as pre-service forum meetings. This demonstrates strong co-ownership and proactive collaboration across priority thematic areas. However, the early closure of the programme has meant that the process to move from boosting capacity to building capacity to handover has been expedited, likely impacting on the longtime success of the intervention.
SSEIP II (Pillar 1) to suggest a logframe indicator to enable tracking of systems strengthening – for example most significant change case studies on technical capacity, process and policy (by April 2025). / SSEIP II (Pillar 1 and BHC) to agree on refreshed and ambitious logframe indicators to track (by April 2025).	Completed (see above).

Lessons learned this year, and recommendations for future years:
Lesson	Recommendation
Availability of in-house technical assistance support is highly valued by MBSSE and TSC staff, who reported faster progress on their policy areas than could have been possible without this support. With the programme closing soon, this will lead to a substantial gap for certain directorates.	BHC and Pillar 2 to work on the joint transition plan, and seek ways to sustain and systematise the gains from Pillar 1’s support to date.
The integration of evidence-based / planning tools, such as the School / Master List, has improved data / accuracy and resource allocation, but / ongoing support will be needed to / maintain these systems.	With this component closing soon, priority should be on transferring all tools, processes, and learning to government counterparts. Ensure all policy products, planning tools, and documentation are handed over to MBSSE and TSC with clear guidance for ongoing use and ownership. Share lessons learned and evidence with government and partners to inform future policy and sector reforms.

## D: VALUE FOR MONEY

Key cost drivers and performance
As a systems strengthening intervention, the largest share of spending is on consultancy / TA fees. Other significant cost drivers include training government officials at national, district, and school levels to strengthen leadership, oversight, and delivery of education services, with only minimal proportions of spend going towards replacement of tablets for school and district leaders to support quality control and data collection.

VfM performance compared to the original VfM proposition in the business case
The Business Case proposition is that this programme can deliver high value for money (VfM) because:
- Education investments that support girls’ education offer very good VfM because of broader societal impacts including early marriage, childbearing and health seeking behaviours.
- Strengthening the education system, preventing drop-out and improving quality of education, has significant returns given the large number of children already in school.

This is the second year in which both Pillar 1 and Pillar 2 have been actively implementing. Both partners (MM and EDT) have developed VFM indicators based on indicative measures in the Business Case. A selection of baselines from the 2025 Annual Review, and results for the current reporting period are included, are set out below.

Indicator	2025	2026	Comment
Economy (cost and quality of input)
Unit cost per SQAO visit per school (MM)	£16.57	£29.72	The increased unit cost appears to be the result of two main factors: (1) increases to the salaries of SQAOS paid by the government, and (2) reductions in the numbers of SQAOs achieving targets for the number of schools visited. SQAOs faced challenges meeting their visit targets due to old or faulty motorcycles, poor roads, and competing administrative duties. In addition, the data on schools visited was compromised by the outdated school database in Tangerine meaning that some visits carried out by SQAOs could not be reported.
Average cost of SRGBV training per person per day.	£38.42	£32.49	This is comparable between years.
The average cost of professional development per policymaker per cycle (2 days training) (EDT)	Not available	£143	The average professional cost is slightly below the planned £150
Efficiency (productivity)
Number of teachers attending School Based Continuous Professional Development (SB-CPD) using content developed by SSEIP II (MM)	Not available	68% - 20,499 teachers	SB-CPD is a new offering, no schools were completing this for the majority of the previous reporting period. Target for the year was 70%, which was substantially met.
Percentage of policymakers and planners finding training relevant and useful (EDT)	100%	96%	Remains high, no significant difference from last year.
Effectiveness
Number of secondary school leaders who (a) enrol on and (b) complete the core course in the School Leadership Programme (disaggregated by gender, disability and type of leader) (MM)	Not available	(a) 500 / (b) 492	(a) 500 school leaders were enrolled in the SLP (150 in cohort 1 and 350 in cohort 2) / (b) 492 school leaders completed the School Leadership Programme (SLP) across 2 cohorts. 5 school leaders dropped out of the course and sadly, 3 school leaders died over the year.
Percentage of students who demonstrate sufficient (or more) knowledge about SRHR and different types of violence at school (disaggregated by gender) (MM)	19.7%	41.2%	The based on the representative sample of respondents for a KAP study, 43.3% male students and 39.4% female students demonstrated sufficient knowledge about SRHR and different types of violence at school.
Percentage of specific products produced as agreed with the client that are in use (EDT)	40%	70%	This increase reflects further integration of the policy advisers with government counterparts, and indicates strong relevance of outputs.
Equity
Proportion of female school leaders completing leadership courses/toolkits (MM)		17.1%	84 females and 408 male school leaders have so far completed the school leadership programme course. This means that 17.1% of all school leaders who have successfully completed the course are females.The percentage of women school leaders in the latest cohort (cohort 3) is 32% - up from 14% in Cohort 2 and 23% in Cohort 1 and significantly exceeding the target of 20%.

Assessment of whether the programme continues to represent value for money

As set out in throughout this Review, there have been significant changes made to the logframe, Theory of Change, and overall budget and timing scope of the programme during this review period. This has meant that there are not that many exactly comparable indicators between the previous two periods to compare to assess value for money. From the indicators that we do have, it appears that the programme is consistently meeting targets or improving year on year for indicators under efficiency, effectiveness, and equity. This is expected, as the programme entered a full implementation period after inception, the team coalesced and delivered, and the GoSL and other stakeholders understood the aims of the programme and supported improved performance. However, the one economy indicator that we have tracked across both years has shown a substantial increase in cost of SQAO visits – which is driven by out of programme costs (GoSL SQAO salaries) and a decrease in efficiency (fewer SQAOs meeting their targets). Overall, the programme is meeting the objectives set out in the Business Case, at budget, and continues to represent value for money.

E: RISK

Overview of risk management
Risk for SSEIP II is managed through a live programme risk register, and regular risk reviews (both monthly meetings with partners and quarterly BHC-internal sessions to review and revise ongoing and emerging risks). The SSEIP II Risk Appetite Statement sets appetite for all seven risk categories as either receptive or cautious – aligned with the British High Commission’s overall risk appetite. During this review period the risk appetite for safeguarding was moved from receptive to cautious – and so is now in line with the overall BHC risk appetite to reflect that this is a systems strengthening programme with minimal direct interaction with vulnerable children.

One risk was outside of the defined risk appetite: a policy and programme delivery risk due to the UK Government ODA spending reductions impacting planned outcomes of the programme. In response to this risk, the BHC programme team has prioritised key activities and maintained active engagement with partners to adjust delivery timelines where needed to maintain core programme activities,and ensure a focus on sustainability of interventions due to the decision for early programme closure.

Major trends in risk exposure and response over the review period
Key programme risks include:
- Policy & Programme Delivery (sustainability): SSEIP II will close two years earlier than planned, forcing an accelerated transition of activities and reducing the ambition of the objectives GoSL may not have adequate financial and human resources – or alternative funding – to continue implementation of existing interventions beyond the project period. It appears likely that the programme will not realise intended impact and sustained outcomes. To mitigate against this, the BHC programme team are working with Implementing Partners to ensure prioritisation, reformulation of delivery timelines, and consideration of sustainability. The programme Steering Committee is a shared forum with GoSL, through which we are planning for transition and sustainability.
- Strategy and Context (stakeholder engagement): the announcement of early closure may lead to reduced MBSSE and TSC leadership engagement with SSEIP II, thus risking the strong relationships built over years and delaying action on key programme actions. To mitigate against this, the programme team (BHC, MM and EDT) are continuing to work closely with GoSL partners to agree on and delivery priorities. Senior BHC colleagues are continuing to engage with GoSL to demonstrate BHC’s continued commitment to the programme.
- Financial and Fiduciary (fraud): the period leading up to programme closure is typically associated with an increased risk of fraud – due to staff disengagement, lower perceived risk of identification or penalty, or to inappropriately billing for full agreement amounts (finances cannot be moved forward). This risk may involve staff, implementing partners, or other stakeholders connected to the programme. To mitigate against this, the programme team has increased invoice spot checks, and partners have included budgetto retain employees until the end of contracts.
- Safeguarding (Sexual Exploitation, Abuse and Harassment): early programme closure undermines safeguarding outcomes. There is a risk that the programme closes earlier than planned, resulting in incomplete delivery of safeguarding commitments, weakened risk controls for beneficiaries and staff, reduced referral coverage, and potential harm to at-risk groups including any victims who have reported incidents. Gender-based violence rates remain high, and school-related gender-based violence is a systemic issue. A high focus on safeguarding and school safety will be kept until the end of the programme and transition planned for carefully to mitigate against these increased risks.

Assurance
The programme remains compliant with our equalities obligations, and markers – principal for gender and significant for disability – remain valid. The early closure of SSEIP II is likely to have equalities impacts, which have been considered as part of a portfolio Equalities Impact Assessment. Impacts will remain under review and communicated as they change, or if unforeseen impacts emerge.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues

Overall partners have performed well this period, completing activities in line with delivery plans and Key Performance Indicators (KPIs), and acceptable levels of variance. Programme management has included regular narrative and financial reporting, and monthly programme management discussions between partners and BHC to discuss finance, risks (particularly safeguarding and fraud), assets, and other programme management issues. Regular safeguarding training is undertaken by both partners, and reporting lines for safeguarding and fraud are well understood.

During this reporting period, there have been several changes to the available programme budget in the current financial year, and also a decision to close the programme early. This has required high levels of flexibility from both partners, who have responded to requests quickly and professionally.

Pillar 1 (Output 5) – Education Development Trust (EDT)
This was the first full review period following inception – and due to early programme closure the agreement will now finish in March 2026. Good progress has been made with milestones on track, and narrative and financial reporting expectations met. EDT spend to their forecast and monthly financial reports include quarterly forecasts, burn rates, and variance analysis. A new team leader was appointed just before the current reporting period, which has helped regularise reporting expectations. Downstream partners under this work include Fab Inc. and the Learning Generation Initiative, both of which are delivering well and attend programme coordination meetings.

Pillar 2 (Outputs 1-4) – Mott MacDonald (MM)
The £19m commercial contract for the delivery of Pillar 2 was signed with Mott MacDonald) on 3 April 2023, with a planned end date of 31 March 2028 – however, due to Mott Macdonald’s decision to exit the international sector, and early programme closure – this contract will now end in December 2026. Quarterly narrative and financial reports continued to be of high quality and submitted promptly, including regular updates on risk management and safeguarding. The majority of KPIs are met during the expected period, and those that were not were fulfilled and billed for in the following period. Robust asset management systems remain in place. Second tier contracts are being effectively managed with a range of downstream partners including: Purposeful, Focus 1000, Sightsavers, EdTech Hub and Fab Inc. Sightsavers are taking the lead in delivery on Outcome 3 (Disability Inclusion). Mott Macdonald has been identified as a ‘gold’ supplier by the FCDO Transparency Initiative, based on the value and complexity of programmes implemented. The MM team has maintained an exemplary consultative relationship with MBSSE and TSC officials at both national and district levels.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
Monitoring sector performance is core programmatic activity, for example through strengthening the ability of SQAOs and principals to collect data, and leadership at national, district and school level to use this data, or high-frequency quality checks and hands-on supervision for the Annual School Census. The programme is also funding one consultant to take part in the ongoing Education Sector Analysis – an integral piece of the Education Sector Planning and Monitoring process.

Both partners regularly monitor the activities they support. EDT conducted an internal programme stock take to provide a formative check on delivery and clarify priority adjustments, and MM focussed on tracking specific areas to support technical delivery – for example collaborating with the technical team to introduce processes for monitoring the School Leadership Programme through Local Leaders of Learning.

BHC’s monitoring included school visits in June and December. This Annual Review was led by an education adviser from the central FCDO Education, Gender, and Inclusion Research Team. The adviser – alongside the BHC programme team – carried out interviews with key stakeholders at national level (MBSSE, TSC, EDT, MM, and donor partners) to seek feedback and expectations for the remainder of the programme. They also visited schools and district officials in Port Loko to understand in detail the impact of the project on beneficiaries. This included discussions with Organisations of Persons with Disabilities, teachers and school leaders, parent learners and pregnant girls, and children with disabilities. The findings from these visits and interviews are included in the review write-up and recommendations above.

The SSEIP II Steering Committee (comprised of MBSSE, BHC, EDT and MM) only planned and executed one joint monitoring visit – to Bo in December 2025.This helped raise joint understanding of the work of the programme, ongoing implementation challenges, and to discuss the impact of and how to mitigate against the planned early closure.

Evidence
The programme was designed based on the best global evidence, and context-specific evidence from previous programming. SSEIP II continues to increase the available evidence base, through commissioning studies including: the Knowledge and Attitudes and Practices (KAP) survey (which has heavily influenced the Ministry’s approach to SRGBV prevention), and a survey on the teaching of Adolescent Health and Life Skills in Senior Secondary Schools.

Learning
During the review period, both Pillars carried out numerous exercises to capture evidence and lessons to support adaptations to the programme and assist the work to influence change in the sector. For example quarterly District Deputy Director workshops and standardised reporting tools were introduced to create a space for peer learning across districts, and better understanding of support needed at central level and the establishment of the pre-service education forum created an opportunity to discuss critical issues affecting pre-service and in-service education.

Learning products created this quarter include:
- A survey of SSSs to map the provision of AHLS teaching across the country found that AHLS is offered in every school, but that provision in SS3 is much less common than SS1 and SS2, and a widespread need for professional development for AHLS teachers as well as teaching and learning resources for the subject.
- A survey completed by 150 JSS teachers about their experience with teaching CAHLS revealed that half of CAHLS teachers find it hard to teach CAHLS because parents are not happy with the content or students are uncomfortable with it, while a third of teachers themselves disagreed with the content. Despite this, there were numerous examples given of positive changes that had resulted from the teaching of CAHLS.
- A survey that was completed by School Leadership Programme participants in Toolkit 2 – findings (for example a preference for hard copy over virtual workbooks, clarity of instructions, and areas for LLL feedback) were used to improve the mode of delivery and the support provided to participants for Toolkit 3.
- The second KAP survey found that there had been a doubling in the percentage of students with sufficient knowledge about SRHR and different types of violence at school. It also identified that gaps remain, notably around FGM and the acceptance of pregnant learners in school.

Sharing evidence and learning from the programme will be a core part of SSEIP II’s closure plan. This will be done in collaboration between GoSL, BHC, MM and EDT and will range from ensuring that all policy, learning and data products are shared directly with relevant stakeholders and made available on the MBSSE Knowledge Platform (https://mbsseknowledgeplatform.gov.sl/), to policy dialogue learning events in Sierra Leone, bringing together thematic experts to share knowledge and discuss next steps, to sharing of key evidence globally through partner webinars and sharing evidence at global conferences such as the UK Education Development Conference (UKFIET).

Date of last narrative financial report	Mott Macdonald: 12 Jan 26 – for the period 3 April 23-31 March 25 / Education Development Trust: 2 June 25 – for the period 1 Dec 23-30 Nov 24	Date of last audited annual statement	Mott Macdonald: 12 Jan 26 – for the period 3 April 23-31 March 25 / Education Development Trust: 2 June 25 – for the period 1 Dec 23-30 Nov 24

Annex A: Glossary of abbreviations

BECE	Basic Education Certificate Examination (end of JSS exam)
BHC	British High Commission Freetown
CAHLS	Child and Adolescent Health and Life Skills
CEO	Chief Education Officer
CSSP	Comprehensive School Safety Policy
CPD	Continuing Professional Development
EDT	Education Development Trust
GBC	Girls & Boys Club
GCR	Gross Completion Rate
GoSL	Government of Sierra Leone
GPE	Global Partnership for Education
JSS	Junior Secondary School
IC	Inclusion Champion
KAP	Knowledge Attitudes and Practices study
KPI	Key Performance Indicator
LAYS	Learning Adjusted Years of Schooling
LLL	Local Leader of Learning
LwL	Leh Wi Lan (let us learn)x1
MBSSE	Ministry of Basic and Senior Secondary Education
MEL	Monitoring, Evaluation and Learning
MM	Mott Macdonald
MTHE	Ministry of Technical and Higher Education
NFE	Non-formal Education
NTAC	National Technical Advisory Committee on Inclusive Education
OPD	Organisations of Persons with Disabilities
PMM	Performance Management Meeting
RIP	Radical Inclusion Policy
SARF	Screening, Assessment, Referral, and Follow-up (for Learners with Disabilities)
SB-CPD	School Based Continuous Professional Development
SIP	School Improvement Plan
SLP	School Leadership Programme
SRGBV	School-related Gender Based Violence
SRHR	Sexual and Reproductive Health and Rights
SSC	School Safety Committee
SSEIP II	Sierra Leone Secondary Education Improvement Programme, Phase II
SSS	Senior Secondary School
SQAO	School Quality Assurance Officers
TA	Technical Assistance
TLMs	Teaching and Learning Materials
TSC	Teaching Service Commission
TTI	Teacher Training Institute
TWG	Technical Working Group
VfM	Value for Money
WASSCE	West African Senior School Certificate Examination (end of SSS exam)

Annex B: Changes to Impact and Outcome Indicators
As set out in Section B above, there were changes made to the programme’s impact and outcome indicators. These are described below – where an indicator has been discontinued it is marked in grey, and other changes are explained in the comments column.
Impact Indicators		Baseline	2023/24	2024/25	2025/26	Comments
Discontinued 1: Percentage of adolescent girls who are out of school (age 12-17)	Planned	32%	32%	28%
	Achieved		Updated data not available	Updated data not available
Discontinued 2: Average Learning-Adjusted Years of Schooling (LAYS) achieved by children in Sierra Leone	Planned	4.9 years	5.1 years	5.2 years
	Achieved		Updated data not available	Updated data not available
Number of boys and girls passing the end of secondary school examinations (BECE & WASSCE)[11] with maintenance of gender parity	Planned	JSS (BECE): 124,477 (50% girls) SSS (WASSCE): 62,559 (50% girls)	BECE Baseline +5,000 (50% girls) WASSCE Baseline +5,000 (50% girls)	BECE Baseline +10,000 (50% girls) WASSCE Baseline +10,000 (50% girls)	BECE Baseline +15,000 (50% girls) / WASSCE Baseline +15,000 (50% girls)	Moved from Outcome to Impact, as no other learning data available at impact level (e.g. LAYS)
	Achieved		Data not available	JSS (BECE): 119,801 (51% girls) / SSS (WASSCE): 39,982 (52% girls)	JSS (BECE): 114,709 (51% girls) / SSS (WASSCE): 47,434 (51% girls)
Rate of early marriage of girls under 18	Planned	30%	28%	27%	26%	Planned DHS has not yet been completed.
	Achieved		Updated data not available	Updated data not available	Updated data not available
Adolescent fertility rate: the number of 15-19 year old girls who gave birth (per 1,000 girls per annum)	Planned	103.5 per 1,000	100	95	90	Continued indicator
	Achieved		100.9 (2021)	97.9 (2022)	94
Outcome Indicators		Baseline (2022)	2023/24	2024/25	2025/26	Comments
Number of girls enrolled in JSS and SSS	Planned	JSS: 298,930 SSS: 203,108 NFE: unavailable	JSS: Baseline + 12,000 SSS: Baseline + 12,000 NFE: Baseline + 8,000	JSS: Baseline + 24,000 (322,930) SSS: Baseline + 24,000 (227,108) NFE: Baseline + 16,000	JSS: Baseline +36,000 / SSS: Baseline +36,000	Non-formal Education (NFE) indicator removed due to indefinite discontinuation of Pillar 3
	Achieved		JSS: 299,728 SSS: 224,358 NFE: unavailable	JSS: 338,031 SSS: 264,732 NFE: unavailable	JSS: 353,048 / SSS: 276,791
Number of children with disabilities enrolled in secondary schools	Planned	7,086 (3,600 boys; 3,486 girls)	Baseline +2,700 (with gender equity)	Baseline +5,880 (with gender equity)	Baseline + 8,820 (with gender equity)
	Achieved		10,684 (5,530 boys; 5,154 girls)	Data not available	13,489 (7,007 boys; 6,482 girls.	Data comes out from ASC so is a year behind.
Discontinued 3: Number of boys and girls passing the end of secondary school examinations	JSS (BECE): 124,477 (50% girls) SSS (WASSCE): 62,559 (50% girls)	BECE Baseline +5,000 (50% girls) WASSCE Baseline +5,000 (50% girls)	BECE Baseline +10,000 (50% girls) WASSCE Baseline +10,000 (50% girls)			Moved to Impact indicator
		JSS (BECE): / 119,801 (51% girls) (AY 2022-23) / SSS (WASSCE): / 113,824 (51% girls) (AY 2021-22) / 137,796 (53% girls) (AY 2022-23)	JSS (BECE): JSS (BECE): 119,801 (51% girls) SSS (WASSCE): 39,982 (52% girls)
Girls’ Gross Completion Rate (GCR) junior and senior secondary schools	Planned	JSS 90%, SSS 89%	Maintain girls' GCR above 90% in JSS and SSS	Maintain girls' GCR above 90% in JSS and SSS	Maintain girls' GCR above 90% in JSS and SSS
	Achieved		JSS 98%, SSS 106%	JSS 95%, SSS 96%	JSS 94%, SSS 98%
[11] Basic Education Certificate Examinations (BECE) and West African Senior School Certificate Examination (WASSCE)

Annex C: Progress on last year’s Annual Review recommendations

Progress on lessons from last year’s Annual Review are set out under each relevant output, with more general recommendations and progress included below.

Recommendation	Progress
SSEIP II (Pillar 2) to continue and strengthen implementation working with boards of governors and other community members engaged in schools as possible under existing outputs. British High Commission Freetown (BHC) to explore possibility of re-activating P3 should funds allow, and to advocate with government and donors to mitigate the gap (ongoing).	This recommendation was not followed in this reporting period. Although increasing community engagement would support impact and outcomes of the programme, budget constrains have made further work in this area impossible.
BHC and SSEIP II (Pillar 2) to review options to increase emphasis on learning outcomes, specifically for Output 2 (by April 2025).	Several options for increased emphasis on learning outcomes were considered, including introduction of remedial education. However, due to sustainability issues with introduction of a new area when the programme will end early these were not activated. SB-CPD activities were used to strengthen teaching and learning.
A logframe review to be carried out by BHC, in conjunction with SSEIP II partners (MM and EDT) to confirm targets remain reasonable and ambitious, and to ensure the programme is tracking success in strengthening systems as well as delivering discrete activities. This will include: / full Theory of Change and Impact / Outcome indicators review, given data challenges and indefinite delay of Pillar 3. / a review of scalability plans given government staffing constraints / ensuring that indicators measure quality of activities including Inclusion Champions, SQAOs, SLP, and school clubs. / Reporting templates to be reviewed to ensure that logframe indicators are tracked quarterly. Impact and outcome indicator targets to be reviewed as part of this (April 2025).	This took place in April 2025 – full actions and changes to the Theory of Change, logframe, and activities, set out in relevant sections above.
SSEIP II (Pillar 2) to continue working closely with SQAOs, alongside the MBSSE and TSC at District and National level, and other Development Partners through the new SQAO Technical Working Group and the Education Data Working Group to continue to strengthen coordination. Drive a shift from project data needs to systems-data needs to facilitate the engagement of MBSSE leadership in data, enabling data-driven decision making (ongoing).	This work continued to be a focus for SSEIP II during the reporting period, with ongoing coordination meetings with government and partners (particularly from GPE). A workshop on data to improve senior MBSSE and TSC understanding of data availability took place in September 2025. The programme will continue to focus on data uptake and use in the final year of operation.
SSEIP II (Pillars 1 and 2) to explore strategies to boost the number of female teachers and teachers with disabilities in leadership positions. This will include data on overall proportion of female / disabled school leaders in the sector. This will be done as a comprehensive effort across the programme considering how to strengthen female participation and leadership as a whole to form a working paper to be approved by TSC (by December 2025).	There has been a deliberate effort to increase the number of female candidates into the SLP – which has paid off (with an increase from 19% in cohorts 1 and 2 to 32% in cohort 3). All partners (in SSEIP II and beyond) remain focussed on increasing female participation in the workforce. SSEIP II partners plan to carry out a more formal study in March 2026.
SSEIP II (Pillars 1 and 2) to provide quarterly updates on sustainability considerations throughout the remaining life of the programme. Each output and activity should be considered separately, alongside an overall sustainability plan for the programme. Continued focus on value for money and coordination will increase likely sustainability (ongoing).	This was done in the reporting period in internal programme reporting. Due to the decision to close the programme early, the programme partners (BHC, MM and EDT) have also compiled a joint transition plan to support conversations with GoSL and other partners on sustainability and transition. This activity will continue to be a focus in the final year of the programme.