## Annual Review Template

Title: MAJI - Mozambique Agricultural Jobs and Climate-Resilient Investment Programme
Programme Value £ (full life): £18,5million		Review date: August 2025
Programme Code : [AMP ID#] 300777	AMP start date: 11/08/2023	AMP end date: 31/03/2029

Summary of Programme Performance
Year	2024	2025
Overall Output Score	B	B
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003507.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004676.xlsx

A. SUMMARY AND OVERVIEW

## Description of programme
The Mozambique Agriculture Jobs and Climate Resilient Investment (MAJI) programme aims to enhance incomes, create more and better jobs for both women and men, and strengthen their resilience to climate shocks. The programme interventions aim to address key constraints to private sector participation in selected agricultural markets, promote greater climate resilience and stimulate sectoral growth and transformation of Mozambique’s economy.

The programme components are:
- Component 1: Investment and Finance (up to £14.5m) aiming to increase the availability of finance and attract catalytic investments, enabling farmers and agri-SMEs to scale operations and build resilience to climate shocks.
- Component 2: Policy, influencing, and research (up to £3m) through a World Bank technical assistance component. This aims to (i) improve the enabling environment for private (and public) investment in agricultural markets, (ii) encourage a shift to climate-smart agriculture practices, (iii) strengthen government capacity on commercial and climate-smart agriculture policy, and (iv) to conduct the analytical work for informed policymaking, including on climate mitigation, adaptation, and nature.
- Component 3: Technical Cooperation (to £1m), to provide technical assistance for monitoring and evaluation, including external reviews and programme-level evaluation.

Following the UK Government’s decision to reduce Official Development Assistance (ODA) to 0.3% of GNI by 2027 to increase defence spending, the programme has been restructured to maintain momentum and relevance. Component 1 has shifted its programme approach, and currently, it is forming a partnership with FSD Africa under a centrally managed agreement. This new approach focuses on designing a Venture Finance Programme tailored to Mozambique, targeting early-stage investments in small and growing businesses (SGBs) in agriculture and climate sectors to unlock market-based capital flows. Component 2 remains unchanged, with the World Bank implementing more targeted interventions to preserve the programme’s climate-smart vision. Component 3 has been temporarily paused to prioritize the mobilization of Components 1 and 2 and will be reactivated once Component 1 begins delivering results.

This review provides a light-touch assessment of programme performance, reflecting the impact of ODA budget reduction and the early termination of the AGRA agreement. It focuses on evaluating Output 2 (de-risking investment opportunities) under Component 1 and Output 5 (policy and influence) under Component 2.

Summary supporting narrative for the overall score in this review
The overall programme score in this review is B - Outputs moderately did not meet expectations, due to a mixed performance. Both components have been affected by ODA budget announcements. The policy influencing and research demonstrated early positive performance despite a brief pause, whereas the Investment and Finance has seen a termination of agreement with implementing partner. The latter is being reshaped to stimulate market-led, innovative financing solutions for the agriculture sector, rather than setting up a new financing vehicle as initially designed.

The Component 1 was, reformulated to respond to budget cuts and spending restrictions, therefore could not meet expectations set at the beginning of the year, while Component 2 met expectations by delivering effectively on crucial studies to improve climate resilience, strengthening key government units, delivering policy dialogues and notably contributing to the submission of a land law reform proposal to the Council of Ministers.

Major lessons and recommendations for the year ahead

Major lessons
This year’s programmatic and political challenges that led to a termination of AGRA agreement, highlighted the importance of adaptability. The programme is pivoting to a new delivery model with a different partner while maintaining alignment with the original business case. This was made possible through the programme team’s sustained engagement with potential delivery partners over the past few months.
As a result, the main lessons are:
- Maintain flexibility: The ability to adapt the delivery model without requiring formal amendment was critical to maintain the programme and its expected results and impact.
- A flexible partnership with the World Bank is contributing to advance the policy and reform agenda on Government priorities in the sector. The programme was able to address key topics in support of smallholder farmers improved livelihoods.
- FCDO corporate challenges can also be a helpful opportunity to enhance programme model:  Partnering with local capital providers rather than setting up a new vehicle presents a unique opportunity to reduce transaction costs and manage risk more effectively. The programme is well positioned to have FSD Africa investing further, aligning with the UK’s broader mobilisation agenda and paving the way for future British International Investment (BII) interventions.

Recommendations

Recommendation	Responsibility	Deadline
1. To define new indicators for outputs 1, 2, 3 and 4 and a new proportionate value for money framework aligned with the new approach. The team should remain adaptable to continue to deliver desired outputs	FCDO	01/03/2026
2. To develop and implement a performance improvement plan to ensure continued delivery of the programme’s intended outputs.	FCDO	01/03/2026
3. To update the log frame based on activities that will be implemented.	FCDO	31/03/2026
4. The partnership approach with the World Bank on agricultural policy should be maintained and, as part of performance improvement plans, further aligned with the investment and finance component to achieve programme impact.	FCDO and World Bank	31/03/2026
6. Once the VfM framework is developed and implemented a VfM analysis should be conducted in time to be reported on in the next Annual Review.	Programme team, FSDA and World Bank	30/06/2026

Despite scoring two consecutives Bs, this has been due in part to circumstances beyond programme control. We have confidence that the new approach will deliver the programme outputs and outcome and we will use the Performance Improvement Plan in recommendation 2 to strengthen the programme.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

## Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The theory of change (ToC) outlined in the original business case remains valid. It is based on the premise that channelling investment into agriculture, via traders, aggregators, retailers, and other agri-SMEs, will increase smallholder incomes and generate rural employment.

In response to the reduction of ODA to 0.3% of GNI, the programme team engaged with stakeholders to reorient the programme toward a more practical and time-sensitive financing mechanism. A field visit to Manica province provided an opportunity to further test the viability of this revised approach. The new approach focuses on mobilizing local capital providers to finance small and medium-sized agribusinesses and climate-focused enterprises through more affordable and innovative financial solutions. Despite the absence of ODA funding in future years, based on the findings of the Manica field visit and early interactions with our new partner FSDA, the programme team is confident that this approach will deliver meaningful impact and remain relevant beyond the current financial year. These developments suggest that the theory of change developed in the original business case still holds.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Due to delays in fully mobilizing the programme and uncertainties of ODA budgets, programme implementation is currently off track compared to the original timeline. Progress against outputs, outcome and impact indicators remains limited, with the exception of output 5, which is showing early signs to contribute to the intended outcomes and impact.

Given the programme has received consecutive “B” scores, a performance improvement plan is necessary to realign implementation and ensure delivery of expected results. As the programme undergoes restructuring to adapt to the evolving context, a revised set of key performance indicators (KPIs) will be essential to demonstrate that corrective measures are in place and effective.

Recommendation 1: Programme team to define new indicators for outputs 1, 2 ,3 and 4 and a new proportionate value for money framework aligned with the new approach. The team should remain adaptable to continue to deliver desired outputs (February 2026).

Recommendation #2: The programme team should develop and implement a performance improvement plan to ensure continued delivery of the programme’s intended outputs by February 2026.
## Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.
Based on initial activities and agreed plans, the programme shows early signs of delivering results and remains strategically aligned with both Mozambique’s national priorities and the UK’s objectives, particularly in climate and economic growth. Key observations include:
- The programme aligns well with Mozambique’s political and economic agenda, especially the new Ministry of Agriculture’s focus on private sector-led growth, and the World Bank partnership is effectively advancing key policy and reform agenda.
- Based on programme team engagement with various stakeholders, it is confirmed that the programme has strong potential to generate job opportunities for smallholder farmers through increased productivity and market linkages.
- The programme team also believes that the revised investment and finance approach offers a promising path to attract private capital and adapt to evolving development financing models.
With these observations the programme team has confidence that the programme will deliver its objectives and impact.

## C. DETAILED OUTPUT SCORING

Output Title	Facilitated and de-risked investment opportunities, including green investments
Output number:		2	Output Score:	B
Impact weighting (%):		60%	Weighting revised since last AR?	NA

Indicator(s)	Milestone(s) for this review	Progress
Programme component on financing and investment mobilized	Programme formally launched	Partially met / The component has been mobilised; programme launch plans and the process for setting up an SPV were initiated.
Number of investments deals supported	10	Not met / An investment pipeline was prepared based on engagement of various recently terminated USAID projects.
Number of businesses receiving technical assistance (cumulative)	10	Not met / Not implemented due to change of the approach for business support.

Briefly describe the output’s activities and provide supporting narrative for the score.
The output has scored B, indicating that expectations were moderately not met. At the time of ODA reduction announcement, the programme was already in the mobilisation phase with a consortium of partners led by AGRA. The programme initiated a series of activities aligned with its intended programme impact, including:
- A market intelligence scoping study was conducted and the inception report submitted and approved.
- Core staff was recruited, and office was established, however staff onboarding was not initiated.
- A call for proposals was ready to be launched, and procurement for branding and visuals was initiated.
- An updated logframe, workplan and budget was completed and agreed at programme team level.
- A governance arrangement between AGRA and the World Bank was agreed to enhance coordination between the two components.

However, anticipated ODA reductions have made it difficult to maintain the approach while delivering impact. Therefore a decision was taken to terminate the agreement with AGRA in May 2025, and this output was unable to achieve its expected results for this year.

As a result, we decided to move away from establishing a Special Purpose Vehicle. Instead, the team moved to a model of building a venture investment platform to provide seed and early-stage capital in partnership with a centrally managed programme, through an existing delivery partner, FSD Africa.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes were made to this output during the review period. As this programme component undergoes a strategic reorientation, further adjustments to the programme interventions, and updates to log frame indicators will be implemented once the component is fully mobilised and operational.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Based on last year’s recommendations, the programme team revised the indicators to ensure they were more realistic and better aligned with the time and effort required to implement activities. A revised logframe was developed and jointly agreed with AGRA, incorporating additional evidence to reflect Mozambique’s current economic and political context. However, due to the early termination of the agreement, the revised indicators were not submitted for final approval.

A key lesson was that, following the ODA reduction announcements, the programme approach was lacking time and flexibility to meet its goals under uncertain and reduced future funding.

As a result, the team is pivoting a new approach. Based on the funding available for this financial year, the programme will now pursue targeted interventions through FSDA using an appropriate financing vehicle as described in the Theory of Change section above.

Recommendation 3. The programme team to update the log frame by March 2026 based on activities that will be implemented under this output .

Output Title	Policy and regulatory reforms related to climate smart, commercial agriculture are implemented
Output number:		5	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	NA

Indicator(s)	Milestone(s) for this review	Progress
Number of research and policy dialogue conducted (cumulative)	3	Exceeded / (4) four of which: / 1. Diagnostic of farmers groups and other forms of rural productive organization completed. / 2. PACE (Small Commercial Farmers) third party model assessed. / 3. Policy dialogue on agriculture insurance conducted / 4. Climate Smart Agriculture toolkit study completed.
Number of government key units technical capabilities actions supported (cumulative)	2	Met / (2) Two actions were completed during this review period of which: 1. Government officials were trained on OECD methodology for agriculture policy monitoring and evaluation. / 2. A study tour to further understand the Electronic Voucher System (EVS) was carried out with participation of senior officials of three units from Ministry of Agriculture and one from National Fund for Sustainable Development.
Number of key reforms are enacted by the Government (cumulative)	1	Partially met / A task force was formed to review submissions and integrate them into the final land law, which has been submitted to the Council of Ministers and is pending Government approval.

Briefly describe the output’s activities and provide supporting narrative for the score.
The output has scored an A overall, indicating that expectations were met. The indicator on research and policy dialogue exceeded its target, while support to technical capacity building in key government units met its goal. However, the target for policy reforms was not fully met as the approval is beyond programme’s control and was affected by political transitions and disruptions during this period.

During the review period, the programme conducted four research studies, convened two policy dialogues and provided capacity building to two key government units. It also contributed to the submission of a policy reform focused on land law and agriculture insurance dialogue. This dialogue, led by Ministry of Agriculture and involving a broad range of stakeholders, resulted in consensus towards improving policy and legal environment for agricultural insurance, with Government leading actions to develop a dedicated policy.

The programme also developed a toolkit on Climate Smart Agriculture to support public extension workers and promote adoption of climate resilient farming nationwide. It also completed the farmers-based diagnostic underlining the untapped potential of Farmers Based Organizations to drive inclusive growth. The results will inform policy reforms in Mozambique’s three main development corridors, enabling structured market participation of farmers’ organizations. Additionally, the PACE diagnostic recommended private sector partnerships with small commercial farmers to boost productivity, which are now being integrated into the new World Bank Agriculture Programme.
MAJI, through World Bank MozRural programme, supported the national consultation forum for the new land law. The consultation convened different stakeholders and culminated with the establishment of a task force which has reviewed, finalised and submitted the land law to the Council of Ministers for approval. This reform is crucial for enhancing women’s land rights, encouraging private sector investment, and reducing land-related conflicts.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes were made to this output

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There are no recommendations from the previous annual review.

Key lessons learned include the relevance of stakeholder-informed research and recommendations to strengthen policy and government capacity to implement transformative agricultural strategies. Ongoing seminars and policy dialogues continue to foster collaboration, with increased engagement from academia and civil society to support agricultural transformation in Mozambique.

Recommendation 4 T The partnership approach with the World Bank on agricultural policy should be maintained and, as part of performance improvement plans, further aligned with the investment and finance component to achieve programme impact
## D: VALUE FOR MONEY
## Key cost drivers and performance
At this stage programme team cannot accurately assess key cost drivers or performance for component 1, as its implementation was paused, and the agreement with the selected partner was terminated. During mobilisation, the key cost drivers anticipated were subsidies to private sector companies, technical assistance and support to financial regulatory improvements. However, due to programme early termination, these did not materialise and most costs were primarily linked to agreement closure with AGRA.

On Component 2, the main cost drivers during this period were external consultancies for research studies. Technical assistance and expert time to deliver the policy interventions were delivered by World Bank staff which has contributed to better cost control and good VfM, compared with external experts provided by consultant firms. Where external consultants were engaged, they were competitively selected combining local and regional expertise under FCDO oversight.

## VfM performance compared to the original VfM proposition in the business case
The value for money proposition as set out in the business case still holds. Based on the current programme implementation, there is insufficient cost data to fully perform a value for money analysis. However, the slow pace of disbursement is an inefficiency that has reduced vfm. As the programme becomes fully operational, a value for money analysis will be conducted including on programme delays, and the findings will be presented in the next annual review.
## Assessment of whether the programme continues to represent value for money
Based on early stage of component 2 implementation, and consultations with the wider stakeholders for component 1 reorientation, there is no reason to change the VfM assumptions and assessment defined in the original business case.

Recommendation 5. As soon as component 1 is completely mobilised the programme team should develop a value for money framework to track programme vfm performance. By end March 2026

Recommendation 6. Once the vfm framework is developed and implemented a vfm analysis should be conducted in time to be reported in the next Annual Review. by end June 2026.

E: RISK

Overview of risk management
The overall risk remains moderate. Contextual and Strategic risk of the programme which played a part in programme delays was the Presidential General Elections of October 2024 marked by major events outside the programme’s control. Civil unrest that gave rise to unforeseen post-election violence contributed to delays in both the AGRA and World Bank components, specifically the signing of the agreement, the recruitment of key personnel for AGRA and policy-related activities for World Bank such as identifying priorities for new incoming government.

A reputational risk was the recent announcement on UK ODA reductions which contributed to operational risks as FCDO requested that AGRA team to pause on activities until further clarification of budget cuts which directly impacted on the programme resulting in the termination of the Agreement with AGRA. The possible decision to terminate the entire MAJI programme while still in its early days, prompted the FCDO team to explore options to evolve the programme during a 12-month window. This led to onboarding FSD Africa through an existing agreement with the Centre, to lead implementation of component 1, allowing the programme to remain viable.

All other risks (including safeguarding, environmental and fiduciary) remained minor to moderate. The overall programme risk register is updated on a quarterly basis. The risk appetite for each category has also been updated and uploaded on AMP.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
This is a 5-year programme with a total budget of £18.5M delivered through three components:

Component 1 – Investment and Finance implemented by AGRA
This component was managed through AGRA, a third-party organisation legally registered as a non-for-profit organisation. AGRA was selected through a competitive process, and an Accountable Grant signed on the 1st of December 2024, with an end date of 31st of March 2029 (“Project End Date”), for an amount not exceeding £14,5million. The procurement process for AGRA was meant to have been completed in October but was only finalised in December at a time where there was civil unrest in the Country due to post election results hence the team could not come into country, the kick-off meeting only happened in January 2025,

However, the AGRA team experienced delays in initiating key activities particularly in the recruitment of key personnel such as team leader, senior programme officer. The FCDO team implemented fortnightly meetings to keep track on progress however these delays contributed to the decision to terminate the contract.

Following the UK Minister’s announcing ODA budget cuts in January 2025, the team took the decision to terminate the AGRA contract. A total £303,000 was disbursed to AGRA. Currently, AGRA has only spent a total of £133,000 to date, and the remaining £170,000 will returned to FCDO by the agreed programme end date of 15th of August 2025.

Component 2 – Policy and Influence implemented by the World Bank
An Administrative Agreement has been established with World Bank under the Food System 2030 Multi-Donor Trust Fund, with a total value of £2.5 million and the Bank is overall performing well as a supplier. This is a Bank Executed Trust Fund (BETF) and forms a broader local programme supporting climate-smart agriculture policy reforms. It is designed to facilitate synergies with both SUSTENTA and Sustainable Rural Economy Programme managed by the World Bank. To date, £1.5million has been disbursed. The grant is structured around four key domains: (i) analytical products, (ii) policy analysis and dialogue, (iii) operational support, and (iv) capacity building. Of these 68% of the total funds received have been used and allocated to agreed activities, while the remaining 32% will be used to respond to emerging priorities in the next two years including effective linkages with component 1.

Component 3 – Technical Cooperation
This component will be implemented by a supplier selected through a call-down contract. A decision was made to pause this component to allow the programme team to initially focus on mobilisation of Components 1 and 2.

G: MONITORING, EVIDENCE AND LEARNING

## Monitoring and Evaluation
Monitoring activities for component 1 and 3, were not conducted, as programme interventions under this component have not started. However, the programme team visited Manica province to assess the relevance of the new FSDA approach under component 1 for existing local business. . The team visited business already financed through AgDevco using debt and equity, showing early success in supporting smallholder farmers through agribusiness investment. The team has also identified potential business for MAJI and agreed to explore different approaches of financing according to the stage of the companies, ranging from promoting industrial clusters, provide capital and expertise and addressing policy issues that hinder business development.

On component 2, the monthly meetings with World Bank provided an opportunity for the programme team to measure progress at these early stages of programme implementation. In addition, the Programme PRO joined the World Bank missions, providing further opportunities for monitoring the implementation of an agreed intervention and reassuring the MAJI approach is relevant and valid in the wider agriculture transformation agenda.

## Evidence
Based on the evidence gathered throughout the year and during the visits to Manica where there exist cohorts of agricultural firms with growth potential that, with additional investment could improve small holder livelihoods by integrating them into the value chain, it confirms that the evidence presented in the approved business case is still valid.
## Learning
One key learning from the second year of the programme was the importance of a flexible business case, which enabled the onboarding of a new implementing partner without requiring formal amendments.

No audit is required for the World Bank Component. An audit would have been necessary for the AGRA component but given that the agreement was terminated just four months after the Accountable Grant signature, the programme team agreed with the supplier that a signed Statement of Expenditure should be submitted. This statement will confirm that the funds were used for their intended purposes and that no balances remain.

Date of last narrative financial report	31st of March 2025	Date of last audited annual statement	Signed Statement of Expenditure to be submitted by the 15th of September 2025