## Annual Review

Title: Project Soteria: stopping perpetrators of sexual exploitation and abuse and sexual harassment from working in the aid sector
Programme Value £ (full life): £10,000,000		Review date: 06/06/2026
Programme Code: 300784	AMP start date: 25/06/2019	AMP end date: 31/03/2026

Summary of Programme Performance
Year	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25
Overall Output Score	B	A	A	A	B	A
Risk Rating	Moderate	Moderate	Moderate	Major	Major	Major

DevTracker Link to Business Case:	47927966.odt
DevTracker Link to results framework:	D0007066.xlsx

Scoring your programme

The Annual Review assesses and rates outputs using the following scale. The Aid Management Platform (AMP) and the programme scoring calculator will calculate the overall output score, taking account of the weightings and individual output scores.

Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

## A: SUMMARY AND OVERVIEW

Description of programme

Project Soteria is a joint initiative between the UK Foreign Commonwealth and Development Office (FCDO) and the International Criminal Police Organisation (INTERPOL). It aims to prevent perpetrators of sexual exploitation and abuse and sexual harassment (SEAH) from working in the aid sector by strengthening cooperation between Law Enforcement Agencies (LEAs) and aid organisations. Aid organisations employ highly mobile staff to work in fragile environments, delivering development and humanitarian assistance to some of the world’s poorest and most vulnerable people. Strong vetting is required to safeguard beneficiaries and staff against SEAH. The project is one of several initiatives launched at the October 2018 International Safeguarding Summit in London designed to prevent such abuses from happening and to respond appropriately when they do. The programme was designed in two phases: the first phase (2019-2021) built key stakeholder relationships and designed the scope of the current implementation phase (2021-2025) which focuses on the following activities:
1. Capacity building for Law Enforcement to use INTERPOL capabilities more effectively, as well as actions such as criminal record keeping and monitoring, particularly of sexual offenders, and building understanding of SEAH in aid work;

2. Promoting information sharing, e.g. using INTERPOL Notices, to gather and disseminate intelligence internationally and reinforce border management capacity to assess and use this information;

3. Criminal Analysis and Investigative Support including using a Criminal Analysis File (CAF) to develop a wider understanding of the nature, location and patterns of sexual abuse and exploitation by aid sector staff to help inform prevention and response measures;

4. Assistance to the aid sector to help them collaborate more closely with law enforcement communities to jointly tackle SEAH;

5. Threat Identification Scheme (TIS) pilot to allow aid sector organisations to send INTERPOL information on newly hired candidates to identify individuals that could pose a risk to vulnerable adults and children;

6. Digital solutions via the Vulnerable Communities Secure Collaborative Platform to i) ingest misconduct data, ii) ingest CVs and other searchable data to check candidates and iii) share non-operational data; and

7. An Incident Response Team (IRT) to support Law Enforcement Agencies in humanitarian emergencies if requested and/or consented by a member country.

Summary supporting narrative for the overall score in this review

The programme scored an A, up from a B last year. It made steady progress in its potential penultimate year, with a renewed focus on embedding sustainable systems. Three of the six outputs scored an A (“met expectations”) or above, and the remaining three -of less combined weight- scored a B (“moderately did not meet expectations”) resulting in an overall A. Key achievements included: extensive capability building work; the launch of the updated Soteria public website; continued bilateral engagement with NGOs and law enforcement agencies to build support for data sharing; and progress on the Threat Identification Scheme (TIS), the Substantiated Misconduct Referral Mechanism (SMRM) and Criminal Analysis File (CAF).

Capacity building training and outreach activities continued to reach both law enforcement and aid sector partners. INTERPOL reported strong engagement from member states. The project-maintained momentum through bilateral meetings and targeted communications. While the website was updated at the end of the year, the full professional communications package was not finalised or widely disseminated so limiting visibility and momentum.
The data sharing tools – TIS and CAF - are technically ready, but uptake by aid organisations has been limited by administrative barriers and delays within INTERPOL.
Major lessons and recommendations for the year ahead

There are many obstacles to investigating and prosecuting sexual violence crimes; these obstacles impede accountability and make it difficult to identify offenders via current and established mechanisms. Even organizations with relatively robust vetting and screening mechanisms remain vulnerable to inadvertently hiring known perpetrators. Soteria needs to continue to act jointly with other actors such as the Misconduct Disclosure Scheme (MDS) to reduce the vulnerabilities in the overarching system. This includes retaining a focus on building awareness of risk, addressing fears around data sharing and supporting law enforcement to manage all Sexual and Gender-Based Violence (SGBV) and SEAH cases more effectively with a victim-centric and ‘do no harm’ approach.
The past year has made it even clearer that more time is needed than was initially envisaged by the project team to ensure compliance with national regulations and INTERPOL data sharing rules and safeguards. This includes for organisations to conduct formal assessments to clarify the legal basis for data sharing as per the local jurisdiction, and comprehensive data protection impact assessments to identify and mitigate risk. This is particularly challenging for smaller NGOs. On INTERPOL’s side, processing initial paperwork and completing standard due diligence prior to signing a cooperation agreement has been slower than hoped.
Soteria is concerned that some legal departments over-evaluate the risks of Soteria and may not be striking the appropriate balance between protecting the rights of candidates and offenders and protecting vulnerable lives and communities. To address this, Soteria will encourage NGOs that have completed such assessments to share findings with their local counterparts. This will help to both disseminate knowledge and build confidence in the sector regarding the ability and low risk of entering into data sharing agreements with INTERPOL.
The initial focus of the project was to seek data on SEAH cases from aid sector partners and to use the data to inform security checks and develop analysis. In reality, aid organisations still have many reservations about sharing SEAH misconduct data and especially nominal data with INTERPOL. Explorations by the project with more traditional partners, such as INTERPOL member countries with strong criminal information systems and sex offender registries, have proved more fruitful: designated officers have assessed their registries for offenders with clear links to the aid sector and begun sharing these files for the first time at the international level or with INTERPOL. This should make it harder for offenders to travel and re-offend.
The Soteria team has also approached government bodies that manage data on sexual misconduct, for example, teachers and education oversight bodies. These entities hold relevant information on known offenders that can be used to prevent these individuals working in other institutions with people in vulnerable situations and offending against them.
While many SEAH cases are still not reported to police, and less so to INTERPOL, capacity development initiatives and network building exercises have yielded an increase in reports both to the project and to networks that have been established on the ground through project interventions. This is thought to be because the sessions build awareness, confidence and trust to raise the cases with appropriate authorities. Since 2021 and project implementation 19 cases have been referred by NGOs directly or indirectly involved in project work and/or events.

Recommendation 1: / INTERPOL should organise bilaterial meetings and open online events to facilitate frank conversations with aid sector stakeholders on the suitability of Soteria’s data sharing mechanisms and lessons learned to date in trying to use them. This could include involving the organisation that has signed the cooperation agreement explaining how they overcame data protection challenges.
Recommendation 2: / Use the knowledge of FCDO staff in country to help ensure alignment, secure aid sector buy-in in local settings, including signposting national published data protection advice.
Recommendation 3: / Continue to invest in a series of capability development actions that are tailored to national and regional contexts and deliver different and complementary trainings to the same individuals to build broader competencies in the SEAH / SGBV prevention and response domain.
Recommendation 4: / The project should consider expanding the reach and lifespan of Soteria capacity development by investing in digitized versions of flagship training programmes, including: Safe and Ethical Use of the Internet for Safer Recruitment; Open-Source Intelligence training (OSINT) for Sexual and Gender-Based Violence (SGBV) Investigation; and Foundations of SGBV Investigations. In-person training programmes should also continue to be absorbed into INTERPOL’s Global Academy catalogue, to make trainings available to all 196 countries.
Recommendation 5: / The Soteria team should continue to build and maximise the relationship with entities such as the International Committee of Sex Offender Registries (ICSOR) to improve data gathering on sex offenders, support analysis and leverage their capabilities to support countries intent on developing national skillsets and capabilities to counter SGBV.
Recommendation 6: / Building on recommendation 1 from the last Annual Review, it would be useful to carry out a mapping exercise in priority countries of smaller NGOs, religious trusts and national charitable bodies that are not registered as NGOs but who work in the aid sector.
Recommendation 7 / INTERPOL still needs to enhance evaluation and impact assessment work to better understand the impact of Soteria’s work on organisations directly involved and also wider community / SEAH prevention and response efforts.
Recommendation 8: / Soteria to make further links with the Misconduct Disclosure Scheme (MDS) and the 2024 Common Approach to Protection from SEAH (CAPSEAH) -including possible endorsement of CAPSEAH- to explore further collaboration opportunities and joint solutions.

Progress on recommendations from Previous Annual Review 2024
Recommendation	Progress
Recommendation 1 (Sustainability) INTERPOL to develop tailored aide memoirs and toolkits to be distributed to local stakeholders to support both retention of knowledge and skills taught as well as to facilitate induction of new recruits.	During the reporting period, the project delivered 15 training and awareness raising programmes in five of the six pilot countries (No events were delivered in Tanzania, but several in previous years). Eight events targeted law enforcement officers, seven were directed to aid sector staff. Aide memoirs in the form of handouts with the information delivered, plus copies of training material and INTERPOL / Soteria processes were provided to all participants in hard and soft copy. / For aid sector participants of the Safe and Ethical Recruitment series, a 20-page manual has been developed and shared with all trainees. This was because the bulk of the material is new for course participants, complex and difficult to remember. To add to this and expand reach, in the forthcoming period the project will digitize and share self-paced e-learnings on the Safe and Ethical use of the Internet for Safer Recruitment for aid sector series. / The project is trying to be more inclusive and develop instructional material that is more long-lasting and reflects the varying situations, ideas and aspirations wherever the project operates. Therefore, the project team is establishing a network of specialized officers to operate as a working group to review and if needed revise instructional material shared. These working group networks will focus on i) SGBV investigations and ii) use of INTERPOL tools for sexual crimes. Working group outputs will be proposed for sharing with all INTERPOL Member Countries via the restricted website and in all four official languages (Arabic, English, French and Spanish), as well as via operational networks such as ICSOR. / INTERPOL maintains networks of specialised officers already in other crime domains, and these have proved especially useful, so this recommendation follows current good practice.
Recommendation 2 – (Coherence) Ensure the project aligns with national development plans, police and related services strategic plans, as well as overarching plans to address SGBV, takes into consideration employment, data protection and other related acts and legislation and also factors in and links up with the interventions of other actors.	For all six pilot countries, the project documented national development plans, policies for addressing violence against women and girls, sexual and gender-based violence (SGBV), SEAH and equivalent, as well as plans of national and international actors such as the national UN Development Cooperation Frameworks. / The project has engaged with representatives from the aid sector and law enforcement communities in the six countries focusing both on individuals based centrally and locations where aid is delivered; (approx. 1,000 staff were engaged between 2021 – 2022 and a further 2,000+ in 2023 – 2025). This allowed the project to assess the reality on the ground and tailor country project plans appropriately. / Local legal advice is sought during the development of project deliverables to ensure that project material aligns with and does not contradict national legislation. The project only delivers awareness raising and capacity development actions at the national level, so each delivery is adapted as needed. / The project also proactively seeks advice to ensure that project deliverables do not contradict with the local cultural reality. This has resulted in changes in, for example, project visuals used during training and awareness raising exercises.
Recommendation 3 – (Efficiency) INTERPOL needs to enhance evaluation and impact assessment work immediately and in the medium to longer-term, to better understand the impact of Soteria’s work on the receiving unit and wider community / SEAH prevention and response efforts.	INTERPOL adheres to the Kirkpatrick Model, a globally recognized method of evaluating the results of training and learning programs. / An assessment at Kirkpatrick levels 1 (reaction) and 2 (learning) is undertaken systematically after each project awareness raising and learning delivery. The assessment findings have resulted in adaptation of later deliverables. The project also records changes achieved as a result of project intervention at levels 3 (behaviour) and 4 (Result). / Some indicators such as an increase in the use of INTERPOL tools following a project training are relatively easy to record as the figures are easily available to the project team. / Recording other applications of learning within trainees’ own environment has proven more challenging and the project could still improve the indicators used, develop and implement an accountability and support package to better understand the long-term impact of the project.
Recommendation 4 – (Relevance) Once the data protection and legal basis for the sharing of data have been resolved, a communications plan needs to be updated and implemented that specifically addresses and supports project partners to understand their obligations related to data protection, SEAH prevention and response and where Soteria fits within these efforts.	The project communications plan has been revised and is updated on a quarterly basis jointly with the Communications directorate. The project website and basic information sheets have also been updated and two short videos produced based on Soteria work in Kenya and Nepal. / The legal basis and data protection issues around aid sector organisations sharing data with INTERPOL differ across the world. INTERPOL’s legal team does not permit the project to offer national legal advice. These factors combined make it difficult for the project to integrate advice into INTERPOL published communications materials, though the team does signpost stakeholders to published advice where we are aware it exists.
Recommendation 5 – (Effectiveness) INTERPOL need to be proactive in following up with all stakeholders in the criminal justice sector to secure ongoing availability and confirmation of relevant and usable data, as well as with partners in the aid and development sector to build understanding, trust and buy-in to the data exchange pilot.	The team has done this. The most effective approach has been the continued investment and engagement with the same individuals for different project actions for a graduated learning and stronger relationships. More can always be done, and the team will seek to build on this in the coming period through the establishment and recognition of specialized networks for SEAH and SGBV in both aid and police sectors. The project will then bring these networks together as an additional trust and bridge building exercise that we plan will yield to more and safe reporting of SEAH cases to the relevant authorities.
Recommendation 6 – (Impact) The project has maintained a steady input on cases reported and referred but should increase focus on the provision of investigative and operational support in the coming months, to achieve progress on cases, improve reporting, increase use of INTERPOL tools for this crime area and support enhanced learning.	Use of INTERPOL tools for SGBV and SEAH has increased substantially during the project implementation period and in countries where the project is more active. / NGOs and police are reporting more cases. These are open/ ongoing cases upon which the project can report, as well as historical cases but where records are still relevant for crime analysis files.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of change remains the same from the last Annual Review. It is still in line with the goal and vision of the Business Case. In this reporting period, three small changes at Outcome level were made to the Logframe. The text in Outcome Indicator 2 baseline March 2021 ‘Use of INTERPOL capabilities for SEAH and SGBV cases in the partner countries is low’ was sharpened to focus more clearly on the aid sector (rather than partner countries): to achieve that a new Outcome Indicator 3 was added with the addition of 'Use of INTERPOL for SEAH in the aid sector is virtually zero' into the new indicators in the baseline 2021. Second, the May 2025 milestone target for Outcome Indicator 5 was changed from 'aid delivery setting' to 'in one additional country': this broadens the scope, but the spirit of the target remains the same. Finally, a new more specific Outcome indicator was added; 'Demand and Supply of INTERPOL tools (Coloured Notices, Diffusions, Secure messaging, analytical, investigative and operational support) for sexual and gender-based crimes and Sexual Exploitation, Abuse and Harassment in particular is increased.'

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The project data sharing components are significantly delayed from what was foreseen in the original proposal. It seems that Soteria can be successful, and the project is slowly proving this, but initial expectations about how long this will take proved optimistic.

Capacity development and awareness raising with police and similar authorities is yielding strong results, notably clear increases in the use of INTERPOL tools for SGBV and increased data sharing on dangerous sexual offenders. These changes are improving the effectiveness of security checks while also strengthening data availability and understanding of trends.

Many of the project police trainees have emphasized that this is the first time that they have received awareness-raising programmes on SEAH, including on victim-centric and do-no-harm approaches. Considering the proximity of Soteria trainees to individuals in exceptionally vulnerable circumstances, the value of these initiatives and potential for long-term positive impact is clear.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The programme should continue. It is mostly on-track and exceeding results in one of the main result areas relating to capacity development actions and outcomes for the criminal justice sector. It helps contribute to delivery of HMG’s 2020 Safeguarding Strategy.

## C. DETAILED OUTPUT SCORING

Output Title	Targeted capacity development for aid and development organisations
Output number:	1	Output Score:	A
Impact weighting (%):	20	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of aid organisation professionals participating in formal training programmes (disaggregated by age, gender, position, geography, proximity to aid delivery, organisation size and scope).	i. Open-Source Intelligence training (OSINT) referred to as ‘Safe and Ethical use of the Internet for Safe Recruitment’ delivered to 60 relevant aid workers (Safeguarding and Recruitment functions) from more than 15 organisations during the reporting period. / ii. Internal administrative investigations training delivered to 30 relevant aid workers in 4 countries during the reporting period (There should be a balance of staff trained that operate at central and remote (aid delivery) locations). / iii. Minimum 75% of all training participants rate the intervention as very good or excellent, and highly relevant to their work.	1.1. Milestone target met. (A) / i. Met expectations (A) / 37 aid workers (20 male, 17 female) completed OSINT training, against a target of 60. 33 aid organisations were reached against a target of 15. Arguably the impact of reaching many more organisations is greater. With one sub-indicator scoring C and one A++, that averages out as an A. / ii. Moderately did not meet expectations (B) / Training delivered to 25 aid workers during the reporting period. They were 9 male and 16 female aid workers from 25 organisations in 3 countries (Kenya, Nepal, Philippines). Training scheduled in Bangladesh, was postponed for reasons outside of the project’s control. / iii. Substantially exceeded expectation (A++) / For both training deliveries, 100% of training participants rated the training as very good or excellent, and highly relevant to their work.
1.2 Percent of trained officials reporting application of new skills and knowledge taught.	At least 75% of officials trained report being able to apply new skills and knowledge taught immediately in their professional position.	Moderately exceeded the target set. (A+) / For ‘Safe and Ethical use of the internet for Safer Recruitment’, 100% of trainees reported being able to immediately apply learning in the context of their daily work and to improve due diligence on new recruits. This would equate to an A++ / For staff trained in the Investigator Qualification Training Scheme (IQTS), trainees specifically mentioned various areas where they would apply learning. But participants also commented that the full application of skills taught is in part dependent upon circumstances, and all reported a need for ongoing mentoring, training and adaptation of the material to the national context. It is harder to score this precisely, but it feels like a B (moderately did not meet expectations) or possibly an A. Only 52% of IQTS trainees completed the evaluations, with 80% of those reporting that the course exceeded expectations, but lower scores (71%) for how the course achieved to be engaging and effective. The team plan to conduct their own evaluations as part of the registration for any future training intervention.

Briefly describe the output’s activities and provide supporting narrative for the score.

The Safe and Ethical use of the Internet for Safer Recruitment training under Indicator 1.1i. was designed by the project team for the aid sector. It applies techniques and governance frameworks of Open-Source Intelligence training (OSINT) traditionally delivered to police. It adapts OSINT techniques for aid sector staff to enhance due diligence when recruiting staff and supporting internal investigations of SEAH allegations. The training uses free resources that are readily available using internet browsers and searches. Great attention is paid to personal safety online, the adherence to recognized international principles, respecting the dignity of individuals, simple and secure means of validating online information and in proper documentation and reporting of all actions taken.

Following recommendations and requests from previous online iterations of this training, this time it was delivered in-person over three days as individual one-day training events. This enabled more instructor–trainee interaction, questions and practical exercises. Four of the organisations represented were international charitable organisations each operating in more than 100 countries. All other organisations were small grassroots entities operating at national or regional level in Nepal in fields such as community development and child protection. Signup was lower than anticipated due to context specific challenges such as impact of flooding in the region, so while more organisations joined the sessions than was forecast, numbers of participants did not meet the target of 60.

The feedback on the changed format was extremely positive with trainees reporting they could immediately apply and use learning. For example: “Very applicable to our HR teams in terms of safe and ethical searching, especially the security around the activity”. And “The sheer amount of useful tools freely available that I did not know about before. I feel very empowered to use them. I also found the practical exercises excellent.”

The project is aware of the need to balance the benefit of face-to-face training with the constraints of long-term resourcing and organisations’ need for flexibility on when and where they do can do things. INTERPOL staff can deliver the Safe and Ethical use of the Internet for Safer Recruitment training themselves, or in collaboration with other units if Soteria staff are not available / the project has closed. The session generated recommendations to further develop this initiative which will be combined with comments from previous iterations into a final digitized package to be shared cost-free, initially in English, by March 2026. The online package is intended as a download for local organisations to easily access. This will mean longer-term impact and wider distribution allowing users to review and refresh training as needed. Digital delivery will also be more cost effective than in-person delivery. The online course option remains available to organisations that sign a cooperation agreement with Soteria.

For Indicator 1.1.ii (Internal administrative investigations training) Soteria continued to use the Investigator Qualification Training Scheme (IQTS) coordinated by the Core Humanitarian Standard (CHS) Alliance and Humentum. IQTS is a multi-tiered external online package to strengthen aid sector capacity for conducting survivor-centred SEAH investigations. The project capitalises on this course to build a foundation of knowledge that can later be developed and tailored to the delivery location and also reviews referral mechanisms to police. By ultimately connecting networks both trained by the project and IQTS, Soteria aims to break down silos and build bridges between aid sector and police.

The project achieved over 68% of its target; 62 aid workers trained were under this output during the period, against an initial target of 90. These workers represented 35 organisations, exceeding the project’s plan (15). 88% of these are small organisations operating at local or national level; the project especially targets smaller organisations as they may have fewer resources to invest in staff training, and secondly, having fewer resources can make such organisations potentially more vulnerable to abuse. Training for the aid sector was delivered in three of the pilot countries (Kenya, Nepal, Philippines). Training had been scheduled in Bangladesh, but this was postponed outside of the project’s control. The lower numbers achieved are due to the temporary suspension of one planned delivery (18 individuals from Bangladesh, Kenya and the Philippines were booked into an online IQTS Tier III cohort due to start in February 2025 that was postponed by the provider), plus three individuals registered for training but never logged into the online platform.

The types of organisations engaging in this course differ per country. Those who were due to take part in IQTS training (but could not) who work in Bangladesh represent large international NGOs and UN entities operating in the Cox’s Bazaar refugee complex. In Kenya and the Philippines, the course targets individuals attached to national institutions related to protection of individuals, where embedding this capability brings long-term value. In Nepal, 7 of the staff trained are affiliated to UN entities and the other 12 work for small grassroots organisations operating at the community level.

Cumulatively since 2019 project formal capacity building and awareness raising activities (not including online presentations at external events) have reached 560 male and 619 female aid workers. As noted above the project witnessed a lower than anticipated signup or completion of courses in the latest reporting year for various reasons. This is also partly a result of a project shift in focus during the reporting period to place greater attention on building awareness of risk and promoting Soteria data sharing mechanisms.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The project is exploring alternative mechanisms for delivering the IQTS series. Currently, IQTS includes access to an online platform with structured course material supported by interactive webinars which are recorded for participants to view at their convenience. Identifying suitable staff with sufficient time to commit to the online course has been challenging, even with a letter of support from participants’ hierarchy that they will be allocated time to complete the course. For those who were able to attend webinars, interaction was good, and participants used the opportunity working individually and in groups to discuss real and possible issues, experiences, challenges, and solutions. The still limited availability and high competing priorities of course participants may have prevented many from taking full advantage of the course and material provided.

While delivery with Humentum was put on hold (following withdrawal of USAID funding), the project explored alternative options with CHS to trial in-person delivery to allow tailoring to the legal and cultural environment.

Overall, expenditure in this area dropped in the past year with a shift in focus to deliver fewer field and capacity development activities and place the project attention more centrally on the main legacy item, the data sharing mechanisms.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no specific recommendations from last year’s AR. The project continued to be as inclusive to the views and aspirations of the target audience as possible. Key recommendations from the previous reporting period included: i) increasing monitoring, evaluation and learning (MEL); ii) build sustainability measures; and iii) focus on bridge-building between the law enforcement and aid sectors. The project has intensified MEL actions during the reporting period, and this will remain a key focus in the forthcoming period. Sustainability actions will also be intensified. The project has held workshops to explore referral mechanisms between the sectors to develop a good practice model that can potentially be shared – this will be continued in the coming period.

Output Title	Targeted capacity development for criminal justice officials in partner countries
Output number:		2	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No, (however, wording of indicator 2.2 altered)

Indicator(s)	Milestone(s) for this review		Progress
2.1 Number of criminal justice officers participating in formal training programmes (disaggregated by age, gender, rank, unit, geography including proximity to aid delivery).	Project delivered capacity development actions have reached 800+ criminal justice officials (Police, Prosecution, Immigration and Border Control, INTERPOL National Central Bureau (NCB) Officers and Specialized police units) in minimum six countries. / Delivery achieves: / - A 10% increase in the application of INTERPOL tools for SGBV / - Greater awareness of SEAH in aid settings recorded. / - Clear enhancements to SGBV investigations, including the application of a victim-centric approach, demonstrated by case reports and case outcomes.	Target significantly exceeded (A++) / Cumulatively, project activities have now reached 848 female and 1,092 male law enforcement officers. Collectively 1,940 reached in 12 countries; Bangladesh, Canada, France, Kenya, Lithuania, Moldova, Nepal, Nigeria, Philippines, Poland, Tanzania and Uganda. / During the reporting period, the project delivered 10 in-person formal capacity development and awareness raising exercises in 5 countries, reaching 182 male and 83 female police officers and related staff. At least 70% of trainees work in remote areas where aid is delivered, and many received training for the first time on SEAH and SGBV through Soteria. / The increase in application of INTERPOL tools ranges between 25 and 38% with much greater awareness of SEAH and clear enhancements in investigations (see narrative section below table for more detail).
2.2 Enhanced knowledge and sharing of good practice examples relating to criminal record management, sex offender management and SEAH prevention and response.	i. Direct support facilitated by the project to enhance management of information relating to offenders of sex crimes in two countries. / ii. Ten officers receive training in Train-the Trainer, to support long term sustainability / replication of Soteria training in country.	i. moderately did not meet expectation (B) / Only one country has received support facilitated by the project although another is in the pipeline. / ii. Moderately exceeded target (A+) with 20.

Briefly describe the output’s activities and provide supporting narrative for the score.

The project has now developed a series of training interventions that complement one another to offer a more complete package to prevent and respond to SGBV and SEAH.

Events delivered under Indicator 2.1 included: INTERPOL Policing Capabilities for SGBV (Kenya, Philippines, Uganda); Prevention of SEA for law enforcement frontliners (delivered for officers working in and around refugee settlements in Kenya and Uganda); SGBV Investigations Tier I (Kenya); Detecting sex offenders and using INTERPOL tools at border points (Nepal); Open-Source Intelligence for SGBV investigations (Nepal); INTERPOL Policing Capabilities Tabletop Exercise and Instructor Development Course (Kenya); SEAH Referrals workshop from aid to police (France).

The project also supported a two-day online event focusing on how INTERPOL can support investigations involving virtual assets and the Dark Web. 279 law enforcement officers from at least 26 countries joined this session, though gender and location could not systematically be recorded for all present. In coordination with the INTERPOL Crimes Against Children (CAC) team, the project facilitated four officers from Bangladesh and Nepal to undertake training to use the INTERPOL image database for Child Exploitation Material, called ICSE. Finally, the project co-facilitated and presented Soteria at the 6th annual meeting of the International Committee of Sex Offender Registries (ICSOR), held in Australia in 2024 with presence of 40 male and 34 female law enforcement and government officials involved in sex offender management from 12 countries.

In terms of impact linked to this indicator: the number of Green Notices and Diffusions published globally for known sex offenders has increased by 25% since May 2021 when the project was launched, with a 5% increase during the last 12 months; the number of all INTERPOL tools (Notices, Diffusions, case messages) used for sex offenders has increased by 27% with a 3% increase over the last 12 months;
in the pilot countries, where the project is operating more intensely, there has been a 38% increase in the use of INTERPOL for SGBV since the project was launched in 2021, with some training participants using INTERPOL to share details on sexual offenders and offences during the last year for the first time following intervention from the project; evaluations conducted following project deliveries especially PSEA for frontliners revealed that most trainees had never received training in PSEA and victim centric behaviours and investigations before. Trainees spoke in the evaluation of building their understanding of the implications of power imbalances and the importance of always respecting victims, of proper case reporting among other areas; and 85% of SGBV investigations training participants reported that they felt very confident to apply learning in practice. The greatest increase in the use of tools has been in Nepal and Kenya. Nepal has seen a 162% increase between 2021 and 2025, and 50% increase between 2024 and 2025. Kenya has published using INTERPOL for sexual crimes for the first time in 2024 - Soteria trainees initiated and managed this process.

Under Indicator 2.2.i, following participation at the ICSOR meeting in 2024, ICSOR members are now actively supporting one Soteria partner pilot country with the provision of legal and technical advice and if needed, software to develop their national sex offender registries. Additional support to one other pilot country was planned but is currently on hold though this country is scheduled to attend the next ICSOR meeting in the UK in November. The project will continue to connect in-country experts with their technical counterparts abroad and leverage as much technical expertise as possible.

For 2.2.ii, 12 male and 8 female police officers from the National Police College, Senior Staff College, National Criminal Investigation Academy, Leadership Academy and Administrative Police Services completed a two-week course on INTERPOL tools in Kenya for SGBV and the INTERPOL Instructor Development Course. 18 officers were fully certified as INTERPOL certified instructors during the session and the project is supporting the remaining two officers to complete their certification. The trainees are expected to rerun project training to cascade this learning across the Kenyan police force in the coming months.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The key difference to the project approach during the reporting period is that, rather than deliver capacity development, training and awareness raising actions across a broad spectrum of criminal justice officials, the project is now channelling tailored packages designed specifically for Soteria and for each geographic location through a smaller set of policing professionals. The objective is to develop a cadre of policing professionals who operate in areas where aid is delivered, are fully sensitized to SEAH risks, have been trained in the detection, recognition, prevention and response to SGBV and SEAH, can operate with a victim centred and do no harm approach, have a full understanding of which INTERPOL tools apply within SGBV investigations and how these tools may be requested and used.

To support longer-term sustainability, one train-the-trainer exercise has been delivered to a selection of officers from one country’s national policing academies. Soteria will support these trained and certified officers to repeat Soteria trainings at the national level. Once this is tried and tested, and with budget permitting, a further train-the-trainer will be delivered to develop the maximum capacity for this country to sustain Soteria activities autonomously in the future.

As a separate sustainability measure, two Soteria training packages (PSEA Awareness Raising and SGBV investigations) have been absorbed into the INTERPOL catalogue of trainings maintained by the INTERPOL Capacity Building Directorate. This makes the training material available for all INTERPOL member countries and internal units. As evidence of this, INTERPOL is currently assessing whether to digitize part of the Soteria SGBV investigations and translating the course into Arabic for the MENA region. Additionally, the Crimes Against Children team will fund and deliver SGBV investigations tiers I and II in Soteria pilot partner country Nepal later this year.

Finally, two INTERPOL staff operating outside of Soteria have been trained in the PSEA Awareness Raising package. One of these officers co-facilitated this package in Kenya during the reporting period and the second trained officer is expected to do the same during the forthcoming period. This will help to build internal capacity to sustain, adapt and continue delivering these modules after the project closes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous period still apply, the project is carefully aligned with national and international policy frameworks plus the work of other actors. The partnership with The Office of the United Nations High Commissioner for Refugees (UNHCR) and the International Organization for Migration (IOM) has been fruitful; jointly this tripartite relationship has started to address a gap in PSEA knowledge-building for police working in and around refugee camps. The PSEA training was successfully tailored for the East-Africa region; local police and aid sector partners helped ensure that content, visuals and voiceovers were appropriate for the region. The package has not yet been tailored for an Asian audience; this could be achieved in the forthcoming year. The project has expanded actions around MEL and it is expected this will be further expanded in the next period.

A key lesson learned has been to leverage as much as possible local expertise of police officers already dedicated to the SGBV crime domain and familiar with the locations where aid is delivered to ensure the selection of the most suitable officers for project training and awareness raising interventions. Officers proposed for training are carefully assessed by the project team in partnership with local experts and selected based on their areas of responsibility and likelihood to encounter SEAH and SGBV cases. Ensuring that these officers are prioritized for project training interventions is an opportunity to ensure that training interventions are delivered in more remote regions where risk and need is greatest. In the forthcoming period, the project plans to recognize these trainees as an INTERPOL Specialized Network for SGBV and SEAH. The team will then connect this network as SGBV and SEAH police champions with similarly trained aid sector professionals as a hopefully enduring relationship building exercise.

The project should continue to invest in various capability development actions that are tailored to national and regional contexts and delivered as a suite of different but complementary capacity development actions to the same set of individuals. This will support the establishment of a network of trusted specialised officers with a broad range of competencies, including: i) foundational aspects of SGBV investigations for police, to enhance the quality, safety and dignity of all SEAH and SGBV investigations; and ii) the use of INTERPOL tools to prevent and respond to SGBV and SEAH cases also for police and to build knowledge around SEAH risks, Safe Recruitment skills and systems, safe and victim centric investigations for aid sector and ultimately safe referral pathways from aid to police. Wherever feasible, sustainability will be sought through digitization where appropriate and train-the-trainer deliveries, so that knowledge and skills developed by Soteria are cascaded through for example, national police colleges and similar entities for longer-term impact of the project.

Output Title	Soteria Advocacy, Engagement and Influence
Output number:		3		Output Score:		A
Impact weighting (%):		10		Weighting revised since last AR?		No
Indicator(s)			Milestone(s) for this review		Progress
3.1 Communications, Advocacy and Outreach Plan developed and updated on a rolling six month basis.			Soteria conducts 2nd global public campaign to promote the launch of the data sharing pilot including: / 1. Website updated; / 2. Soteria information package redrafted and shared with minimum 10 key stakeholders. / 3. Soteria presented at one key INTERPOL statutory event. / 4. Five stories posted on social media from INTERPOL accounts on different platforms. / 5. Launch of Soteria newsletter.		Met Expectations (A) (3 As and 2 Bs) / 1. Met. (A) Content for the website updates were internally approved and moved to a more prominent location under the heading ‘Safeguarding Vulnerable Communities’. The new page went live in early June. / 2.Met (A) A professionalised and updated information package has been drafted and will be shared with key stakeholders with a target date of August. The project is hosting bilateral meetings with large NGOs starting in June and over the coming months. A tailor-made package dedicated for criminal justice sector will be developed. In the interim, for police, a communication was made to all 196 member countries in English in February, and in Arabic, Spanish and French in March. Multiple bilateral meetings have also been held to explain the project and build support. / 3. Met (A) Soteria was presented at the Heads of NCB meeting in April 2025. Soteria presented together with representatives of Nepal and used the event to meet with representatives of 12 key member countries who are large users of INTERPOL for sexual crimes as well as members of the Executive Committee. / 4. Not met (B) Three short video-stories featuring Soteria work with police and aid sector have been developed and shared on INTERPOL HQ social media accounts. This material is part of a longer feature video under development / 5. Not met (B) Soteria newsletter scheduled to be launched in July.
3.2 Number of aid organisations engaged by the project in project promotional events, capacity development activities, and information gathering and sharing processes.			In total, 300 organisations engaged (disaggregate by geography, size and scope).		Target moderately exceeded. (A+) / During the reporting period, 278 aid workers representing 90 large and small organisations operating in four countries have been engaged in project events. / Cumulatively, the project has engaged 560 male and 619 female aid workers representing 508 aid organisations since its launch. These figures do not include representation or presentations at externally organized online or in-person events.
3.3 Number and type of supportive communications and statements made by project stakeholders and policy makers.			Soteria publicly endorsed by five aid organisations, by police in two countries (disaggregate by geography, size and scope) and by one key policy maker.		Moderately not met. B / These are in the pipeline but not yet public. The testimonials with be gathered during the second half of 2025 as part of the feature video.

Briefly describe the output’s activities and provide supporting narrative for the score.

In discussion with INTERPOL’s Communications Directorate, the project elected a slow but scaled up communications campaign in place of a large and public launch. The updated roadmap includes: updated pages on the public and restricted websites; develop / produce engaging video content from activities in two partner countries – showcase video content combined with testimonials at INTERPOL major statutory events including the General Assembly; use social media to spotlight issues under project remit; and identify key media contacts to pitch stories and features on the project to.

The updated advocacy and outreach plan aims to raise awareness and build engagement with stakeholders and INTERPOL partners, positioning INTERPOL as a necessary and trusted partner to prevent SEAH. The project jointly with the INTERPOL Communications Directorate has defined an evolving list of internal and external stakeholders, key messages, road map activities and key performance indicators. The core project team meet with the Communications Directorate weekly and as needed to develop, revise and publish materials. Key features of the updated strategy and plan are to celebrate the work of the aid sector, demonstrate the critical work delivered in often demanding physical environments, spotlight risk, demonstrate that trust-based and operational relations already exist between INTERPOL and aid sector actors and through this, strive to build on and further enhance that trusted relationship for the prevention and response to SEAH. During the reporting period three interviews with aid workers operating in different fields of need / expertise have been conducted in Asia. A second visit will take place in August and September in Africa. Soteria partners in the aid sector and police are expected to participate.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the reporting period the project has faced challenges in recruiting a full-time staff member to drive communications, as the INTERPOL Communications Directorate has been heavily engaged in other international campaigns, limiting resources for this component and therefore traction. However, progress made during this reporting period is promising and the project will seek to recruit a short-term and full-time position by the summer. This will permit the project to provide optimal advocacy and outreach during the scale-up of the pilot operational phase of Soteria data sharing components.

Last year the project reported three NGOs were in the process of signing a cooperation agreement with INTERPOL to exchange data with INTERPOL to enhance SEAH prevention and response. This has not come to fruition. One NGO has signed a cooperation agreement during the reporting period.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations under the previous review included building updated legal and data protection analysis into project communications actions. This has turned out to be challenging as firstly, legal and data protection issues differ in each geographic location and organisational setting, and INTERPOL does not traditionally provide national-level legal advice in this area.

An operational review and legal assessment of Soteria in the context of UK law may be published soon by an independent legal consultant. The project will seek out the opinions of other national experts to inform the project moving forward and in case any are willing to offer a national legal opinion. The project asks NGOs considering partnering with Soteria to inform INTERPOL of the legal basis and any data protection issues for sharing data with INTERPOL from their jurisdictions. With NGO permission, the project shares this information with NGOs from the same jurisdiction considering entering into a data sharing agreement to help inform their opinion.

The project needs to focus on tangible deadlines for public comms which it failed to achieve for the reporting period: deadlines were pushed back resulting in slower public comms appeal. Aid agencies that have signed a cooperation agreement should and could be relied upon more on the comms promotion of the programme and speaking with other aid organisations on the complexities and how to overcome these, especially on operational challenges such as licencing and access rights. One stakeholder provided feedback that ‘We have been a forefront of suggesting changes to the VCCP (platform) to make it more functional for our organisation which should also benefit others.’ Ultimately this demonstrates how NGOs signed up currently have real ability to influence the ongoing evolution of the pilot and long-term programme.

The updated communications roadmap needs to have deadlines to keep it accountable especially for a professional comms package. More reliance should be placed on how training and workshops have benefited actors/ how capacity building has helped actors in the field of justice.

Furthermore, overall links and engagement with MDS (which around 320 aid organisations use for background checks) and CAPSEAH should be considered in terms of public communications. CAPSEAH has been endorsed by over 215 aid organisations and countries, including NGOs, private sector and UN agencies (e.g. the World Health organisation - WHO). International discussions around Protection from SEAH are increasingly built around CAPSEAH. INTERPOL should consider endorsing it.

Output Title	Crime Analysis Support
Output number:		4		Output Score:		B
Impact weighting (%):		20		Weighting revised since last AR?		No
Indicator(s)			Milestone(s) for this review		Progress
4.1 Legal and Technical framework for INTERPOL to receive, process, store and act upon data from non-traditional partners including large and small aid organisations is developed and endorsed by INTERPOL Governance bodies.			Pilot has been running for minimum six months. / Draft interim report on findings prepared for presentation to key partners and the INTERPOL Heads of NCBs, Executive Committee and General Assembly.		Moderately Not met.(B) / The first cooperation agreement was signed in December 2024, effectively launching the data sharing pilot. At the operational level however, data sharing could not be launched immediately, due to INTERPOL Rules on Processing Data which mean that all member countries must be informed of new data sharing arrangements and be permitted to object to their data being used for this purpose. / Additionally, staff must undergo mandatory training and then be onboarded to the secure collaborative platform that has been developed for the project, and this process also takes time to be completed. Data sharing is now operational, and the first Soteria checks have been conducted as of April 2025. / The interim report on pilot progress is scheduled to be presented to the Executive Committee at their meeting in November instead of June.
4.2 Data Ingestion: Number of entities (individuals, organisations etc.) related to SEAH recorded in the Criminal Analysis File (increases over time).			150 new entities recorded in the CAF.		Moderately Not met.(B) / 108 new entities have been recorded in the CAF. In addition, following Soteria training events, trainees requested and successfully published two Red Notices for fugitives wanted for arrest and extradition for sexual violence crimes – this was the first time that the requesting country had ever requested a Red Notice for a sexual violence crime. Rather than being recorded in the CAF, which is only accessible to INTERPOL staff and data cannot be seen by member countries, the Red Notice data is entered into INTERPOL main structured database and data is visible to all member countries to support international police cooperation in, on this case, persons wanted for serious sexual crimes.
4.3 Number of Technical, Operational and Strategic Analytical reports relating to SEAH trends and offender modus operandi generated and shared.			Six (cumulative) trends and modus operandi reports generated and submitted to project stakeholders and INTERPOL member countries.		Met. (A) / Two new operational reports featuring suspect offenders were shared with member countries (which when added to the five cumulative total from last year takes the total to seven, but the rate of progress in the past year was as expected so scoring an A). One report generated a local intervention to safeguard children, and a local investigation is ongoing. A detailed report was shared by the country where the individual is located with Soteria and the individual’s country of nationality. / A trends brief is under preparation to be published in restricted version at the end of June and a public version over the summer. This is based on national police data submitted to Soteria by one member country regarding individuals recorded in their national sex offender registry with known links to the aid sector. / The analysis of INTERPOL holdings on sex offenders / offences that was launched during the last period is now subject to peer review; the goal is to share the outcome, if publishable, by the end of this calendar year.

Briefly describe the output’s activities and provide supporting narrative for the score.

With the project still not receiving formally substantiated misconduct reports from aid sector organisations that have signed a cooperation agreement with INTERPOL, the project has continued to focus both internally and externally to where useful and exploitable data on sex offenders resides.

The assessment of internal data is an extensive piece of work as the project is assessing large numbers of files submitted in four languages. It is not clear yet if findings will be sufficient to generate a report that the project can publish.

The analysis of open-source data (for example, published following court cases) continues, though this is also resource-heavy as it requires extensive follow-up and validation with member countries.

The relationship with ICSOR continues to yield useful results. One ICSOR / INTERPOL member country assessed their national sex offender registry for offenders with known links to the aid sector and has shared these files with the project – these files are ingested into the Crime Analysis File (CAF) to be part of Soteria TIS checks and subject to ongoing analysis by the team. A second ICSOR / INTERPOL member country has on suggestion of the project, conducted their own analysis of their national sex offenders with links to the aid sector, and commented that very little analysis has been conducted in this area previously. This country will present findings to the project team at the end of July with a view to share findings for a potential joint publication. A third ICSOR / INTERPOL member country has now suggested doing the same and indicated willingness to request a Purple Notice to share this particular modus operandi with all INTERPOL membership and potentially, the public. The 7th Annual meeting of ICSOR will be held in the UK in November 2025. The project plans to present analytical findings jointly with supporting countries at this event and through this, encourage and catalyse other countries in possession of strong data on sex offenders to undertake similar assessments and share findings with the project to be ingested into the CAF and to contribute to a wider analytical piece.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As was reported last year, the project is no longer relying on the receipt of data from the aid sector to contribute to this output but will focus instead on capitalising on INTERPOL membership and project relations to derive useful results. There is no real change here from last year, only an intensification of this effort to look beyond aid sector data. With the launch of the data exchange pilot this situation may change in the coming reporting period.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

One interesting finding from project actions in this area to date is that, while many countries do hold strong data on sex offenders, very little analysis of offenders with links to specific professions and specifically the aid sector seems to have been undertaken to date. If the project can secure a broader assessment here so that member countries undertake and share such an assessment, this has potential to contribute enormously to the understanding of risk and of how and where known offenders are operating so that enhanced protection and prevention measures can be taken.

Output Title	Data and Information Exchange
Output number:		5		Output Score:		C
Impact weighting (%):		15		Weighting revised since last AR?		No
Indicator(s)			Milestone(s) for this review		Progress
5.1 Threat Identification Scheme (TIS) for security checks on aid organisation staff and volunteers created and used			TIS used by 15 aid and development organisations / To fully assess use of the TIS, the project will measure: / - Number of signed Cooperation Agreements. / - Number of TIS submissions / - Total number of referrals made / - Number and list of countries receiving Soteria referrals / - Number and list of countries responding to Soteria referrals. / - Follow up as reported by member countries and / or aid organisations based on a TIS referral / - (No) Adverse reaction reported.		Substantially did not meet expectations. (C) / The TIS is currently used by one UK-based NGO. Six staff from four country offices of this NGO have access to and are using the secure platform to submit data. / 14 NGOs from Kenya, Netherlands, Nepal, Nigeria, the Philippines, Tanzania, Uganda and USA have submitted all required paperwork. The Soteria team has completed the first part of the internal due diligence assessment and the files are now with the INTERPOL Office of Internal Oversight, Due Diligence Desk for a second review and final assessment. / No data hits have been reported.
5.2 / INTERPOL Substantiated and Criminal Misconduct Referral Mechanism (SMRM) for criminal SEAH cases in aid organisations created and used.			SMRM used by 15 aid and development organisations / This entails: / - 15 signed Cooperation Agreements. / In addition, a record of: / - The number of SMRM referrals made by aid organisations. / - The number of referrals rejected by Soteria. / - The number of new entries in the crime analysis file / - The number of positive data matches based on SMRM referrals.		Substantially did not meet. (C) / As above, one UK-based NGO is currently able to use the SMRM and has informed Soteria that it intends to use both data exchange services. Six staff from four country offices of this NGO have access to and are able to submit SMRM reports to the secure platform. / 14 NGOs from Kenya, Netherlands, Nepal, Nigeria, the Philippines, Tanzania, Uganda and USA have submitted all required paperwork. The Soteria team has completed the first part of the internal due diligence assessment – the files are now with the Office of Internal Oversight, Due Diligence Desk for a second review and final assessment.
5.3 INTERPOL Vulnerable Communities Secure Collaborative Platform (VCCP) created and used (formerly this was the Global Knowledge Hub).			1. VCCP Secure workspaces created for i) International Commission on Sex Offender Registries (ICSOR); ii) INTERPOL SEAH Investigators Network (ISIN); iii) Individual workspaces for users of TIS and SMRM. / 2. 50 new users are allocated space on and using the VCCP / 3. Project delivers at least four online sessions on how to access and use the VCCP to support access and encourage engagement. / 4. VCCP ICSOR workspace populated with good practice data and policy examples for sound sex offender management from at least four countries.		1-2 not met, 3-4 met/exceeded. Overall, “A” / 1. Moderately not met.(B) / i) ICSOR has a workspace and has begun to share data though not all members have access to the platform yet. / ii) The working groups / SEAH investigators network is still in the process of being established; workspaces will be created for these groups in the forthcoming period. / iii) Five workspaces have been created for the one NGO that has successfully signed a cooperation agreement. / 2. Moderately Not met (B) / 8 new users have been onboarded to the platform and 35 from ICSOR have requested access – access is pending approval and creation of a login from their national authorities. / 3. Moderately exceeded target. (A+) / The project has delivered five online sessions on how to access and use the VCCP to the one NGO that has signed a cooperation agreement. This included completion of mandatory training sessions and guided sessions to walk users how to access the platform, how to upload documents, security measures, communication facilities and etc. / Two sessions have been held with ICSOR members and more will be held once their access is authorized. / 4. Met (A) / Five countries have shared official government / police data related to sex offender management that is now published on the VCCP. One NGO has also shared guidance and working papers related to the establishment of national sex offender registries.

Briefly describe the output’s activities and provide supporting narrative for the score.

The project team has focused during the reporting period on the groundwork that will lead to greater progress under this component. Five one-day Safe Recruitment workshops and one online Safe Recruitment workshop were held during the period; all workshops led to serious enquiries to enter a data exchange arrangement as part of the Soteria pilot. The updated and targeted sharing of project information combined with bilateral meetings is expected to yield more enquiries in the coming months.

Once an NGO expresses interest in signing a Cooperation Agreement (CA), the project firstly conducts a basic due diligence assessment to know more about and understand better the position of each enquiring NGO. The team then proposes a bilateral meeting to talk through the process with the NGO concerned, address any questions or concerns and set expectations. 10 meetings were held during the reporting period. A detailed Entity Questionnaire must be completed by all NGOs interested in signing to provide basic legal data about the NGO, its core activities, sphere of operations, key personnel and to answer three essential questions that NGOs are bound within the terms of the Cooperation Agreement to respond to. These questions relate to the legal basis to share data with INTERPOL and to known data protection issues. With a completed entity questionnaire, the project can complete a more detailed due diligence assessment and then refer the file to the Office of Internal Oversight (OIO) for final assessment. OIO issues a recommendation and assessment of risk and the entire file is then referred to the Executive Directorate of Legal Affairs (EDLA) for submission for signature to the Secretary General (SG). Once the CA is signed and countersigned, the team informs member countries via an all-country message and launches the onboarding process for the Vulnerable Communities Secure Collaborative Platform (VCCP).

During the reporting period, the project provided a demonstration of the VCCP to 74 participants from 12 countries at the ICSOR meeting and held two subsequent demonstrations for ICSOR members. 35 police officers and sex offender managers from ICSOR have now requested access to the VCCP. For police entities wishing to use the VCCP for information and operational exchange, they must submit a request access via their local INTERPOL office, the National Central Bureau (NCB). The NCB must authorize access and provide the initial login details. While access is being granted, the project has gathered material from requesting members and begun populating the platform.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Changes to this output relate primarily to the time needed to implement, test and improve the pilot. The current range of NGOs in the process of signing with Soteria suggests that smaller NGOs in Africa and Asia face fewer jurisdictional and institutional challenges to sharing data with INTERPOL. 17 of the 21 NGOs that have expressed concrete interest and launched the paperwork process to be able to sign a CA are based in Africa or Asia and operate at the local or national level. The project is aware that some larger NGOs based in the UK and the Netherlands have launched legal assessments, but these seem to be extensive and very time consuming. From the INTERPOL side, the process to prepare and sign a CA completing all required due diligence and then onboard individuals and entities onto the secure platform also takes around six months (some have taken much longer this year), though the project team will explore means to expedite the different steps of this process in the forthcoming period. The broader advocacy and engagement campaign that was launched in the last months will likely result in more NGOs requesting to collaborate with Soteria: this will not for now impact the time needed to complete the required processes both at NGO and INTERPOL level. On the positive side, once this lengthy process is complete and the NGOs secure access to the VCCP, the process to submit the required forms for the TIS and SMRM are simple and fast. This has been demonstrated by the one NGO that is currently sharing data. Checks on INTERPOL side are also fast and then follow standard operational procedures not inhibited by additional administration or bureaucracy.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The last annual review recommended increased stakeholder engagement. This has been implemented through in-country and online workshops, project presence at various NGO events and the launch of the advocacy campaign. The project needs to sustain these actions while also focussing on shrinking, improving and building efficiency in internal procedures while still adhering to INTERPOL rules and not sacrificing safeguards. Identifying the most effective approach should be a collaborative effort.
Output Title	Investigative and Operational Support
Output number:		6		Output Score:		B
Impact weighting (%):		15		Weighting revised since last AR?		No. However, language for 6.2 amended
Indicator(s)			Milestone(s) for this review		Progress
6.1 SEAH Risk-Prevention, Incident Response Team (RP-IRT) developed and deployed.			SEAH Risk Prevention Incident Response Team embedded as part of standard INTERPOL offer of assistance to countries experiencing a humanitarian crisis.		Met Expectations. (A) / The Soteria Risk Prevention Incident Response Team (IRT) has been presented to the Command and Coordination Centre (CCC) through which all IRTs are deployed and accepted into CCC standard procedures for offering assistance to member countries in a time of crisis.
6.2 Criminal SEAH cases supported			10 cases (cumulative) of SEAH in the aid sector supported by the project. Cases are submitted via NCBs, other project stakeholders in police / aid sector or identified by the project in open sources. / The project provides standard INTERPOL operational and investigative support to all cases, effectively leveraging INTERPOL tools to a new crime area while encouraging partners to report SEAH crimes.		Moderately did not meet expectations (B) / The project has followed 32 operational cases of which 25 were cases submitted by NCBs. The project confirmed links to the aid sector for 8 the cases submitted plus one was related to a peacekeeping deployment. / 3 cases were submitted by NGOs without a formal cooperation agreement and were also referred to impacted countries for follow up using the standard operating procedure for information submitted by the public. As already reported, one of these cases resulted in a coordinated intervention from the local police to safeguard a large number of children and a local investigation has been launched. Four cases were a result of the Kenya-based team following up local police and court cases. / The project continues to provide operational and investigative support to all implicated NCBs and specialized units and cases linked to the aid sector will also be used to contribute to the teams ongoing analysis.
6.3 Promotion of INTERPOL tools for sexual crimes including: / - Green Notices and Diffusions for known sex offenders / - Red Notices for wanted persons / - Blue Notices for persons of interest / - Purple Notices for Modus Operandi / - Orange Notice for an Imminent Threat / - Secure messaging and alerts for traveling sex offenders.			Online and in-person awareness raising and training sessions delivered to more than 100 officers directly involved in sex offender management from at least five countries. / Working Group established from the trainee group and other relevant professionals to review and enhance guidelines on use of INTERPOL tools for sexual crimes.		Substantially not met. (C) / The online sessions to promote the use of INTERPOL tools for sexual crimes will be launched in July instead of March. This delay is to allow the two working groups that will support these sessions and take recommendations forward to be fully established: / Online group to review and develop international guidance on the use of INTERPOL tools for sexual crimes. / In-person and online groups to be launched in Kenya in September.
6.4 Operational support to aid organisations to fill safe recruitment gaps			Eight online or in-person Safe Recruitment Workshops held in at least five countries with participation of 150+ aid organisations. / Each workshop leads to two serious expressions of interest to collaborate with Soteria. / Project baseline for the aid sector updated in preparation for distribution to project stakeholders. / The Baseline will provide an updated view of policy and practice re SEAH prevention and response policy and practice in aid organisations globally.		Moderately Not met (B) / Five in-person and one online Safe Recruitment workshops were held during the reporting period, engaging in total 182 aid workers, 10 police and 87 NGOs across three countries (Kenya, Nepal, Nigeria). / These workshops have resulted in 11 serious requests to collaborate with Soteria for data exchange, six of the 11 NGOs have completed all required paperwork and their application is under review with INTERPOL OIO.
6.5			Operational support to aid organisations - Enhancing systematic coordination with Police		Met (A) / The project held a one-day workshop between large aid organisations and specialized police and prosecutors in France to start developing a good practice for SEAH referrals that might be relevant across Europe. Members of the INTERPOL SEAH and SGBV Investigator Network (ISIN) have been identified through project training and related activities. Work will be undertaken to establish this peer network and onboard them to the secure platform in the forthcoming period.

Briefly describe the output’s activities and provide supporting narrative for the score.

The main focus of project activity under this output in the reporting period has been: (i) to gather and support actual cases with real links to Soteria (ii) to gauge interest in participating in the two working groups and prepare a suitable terms of reference; and (iii) to prepare and deliver the Safe Recruitment series, and build understanding of INTERPOL as a necessary and complementary tool for the prevention and response of SEAH. No IRT has been requested or proposed during the period, however the possibility to deploy a slightly different model of on-the-ground assistance called an Operational Support Team (OST) has now been discussed internally as a means to support countries and NGOs should they wish to conduct security checks against large numbers of people in a short period of time.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Operational and investigative support remains an important component of Soteria and allows the project to build knowledge both on SEAH and on how to correctly use INTERPOL for SGBV with a wide audience. The project is receiving increasing numbers of cases. Referrals also suggest a gap in knowledge regarding where individuals or NGOs can refer concerns when they spot them, especially when there is no concrete relationship between the subject of concern and the entity that sees and might submit this. The project will maintain focus on this, supported by the working groups. During the forthcoming period, the project will expand on work conducted in France on good practice for SEAH referrals and seek to replicate this in at least one partner country. The OST model can potentially be expanded and tested, if agreed by the national jurisdiction where a team is proposed, INTERPOL hierarchy and FCDO as funding partner.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

As was recommended in the last annual review, the project has maintained a steady input on cases reported and referred but should increase focus on the provision of investigative and operational support in the coming months, to achieve progress on cases, improve reporting, increase use of INTERPOL tools for this crime area and support enhanced learning.

## D: VALUE FOR MONEY
Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

VfM performance remains on track. Overall, the project has demonstrated good evidence that it has provided value for money. It continues to develop and build relationships with partner countries, LEAs and aid sector organisations via bilateral meetings, capacity building training and workshops.

It is achieving value for money indicators across the 5 ‘Es’:

Economy – the key cost driver continues to be staff travel and salaries and INTERPOL mitigates this by using existing systems and organising online events wherever possible. Value for money is also being seen where other projects and units are picking up Soteria deliverables and adapting these for their own environments at their own cost. This will be demonstrated in the forthcoming period: i) the Capacity Building and Training Directorate will likely fund a digitization of core aspects of the SGBV investigations training, to be used as a foundational course before in-person delivery. The course content will be translated into Arabic and adapted for a Middle East audience; (ii) The Crimes Against Children team will also pick up the same training package and deliver this at their own cost to specialized police in Nepal.

Efficiency –where outputs were unmet, this was not a reflection of INTERPOL’s capability. Some of the tasks are outside their control and would only be achieved with the cooperation of the aid sector and large multilateral organisations. The project delivery model, delivering at the national level, where aid is delivered, and wherever possible coordinated and cost-shared with other partners is cost-effective and has permitted the project to retain funds for potentially more actions and longer implementation.

Effectiveness – this programme continues to be flexible, adapting to the changing environment and resources. The outputs have contributed to the overall aims of the programme alongside broader work of FCDO’s Safeguarding Unit and the international aid sector e.g. MDS.

Equity – the programme continues to focus on the most vulnerable and marginalised groups exposed to the risk of SEAH and will help the international aid sector better tackle an issue which is driven by power imbalances and often underpinned by gender inequality, recognising that SEAH is known to particularly affect women and girls, minority groups, disabled persons and other groups who may have less power or be more marginalised.

Environment - Soteria’s main environmental impact is travel. The nature of the programme makes international travel a key component and feedback from stakeholders has noted face to face training has been invaluable for holistic training and learning. During the reporting year, some of these were mitigated by using online methods. Online delivery and use of existing INTERPOL systems will continue to help mitigate travel and operational costs.

Assessment of whether the programme continues to represent value for money

Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, the programme should continue. A reduction in annual expenditure, with fewer field activities and more emphasis on sustainable infrastructure is assessed as VFM for the upcoming year. It is widely recognised within the FCDO and among international partners as a cost-effective, strategically important initiative. It has adapted to budget constraints without compromising its core mission. Shrinking operational activities and project team size again will mitigate strategic VFM drivers.
team size again will mitigate strategic VFM drivers.

## E: RISK
Overview of risk management

The overall risk appetite for the programme is receptive. The overall ‘major’ level of risk is aligned with that and judged to be manageable, proportionate and within FCDO Safeguarding Unit’s risk appetite given the potential high returns in terms of prevention of and safeguarding against SEAH.

The delivery risk appetite is cautious, with a key risk being that projects do not deliver in line with expectations, gather sufficient buy-in or otherwise fail proof of concept.

The financial and fiduciary risk appetite is cautious. This reflects our zero-tolerance approach towards fraud and corruption - in line with FCDO policy. We take all possible measures to prevent fraud and corruption, and reporting and acting upon all suspicions.

The people risk appetite is cautious. The programme should ensure the lead suppliers have the key people with leadership and management skills and the capacity and capability to deliver the project

The safeguarding and reputational risk appetites are both cautious, given that the programme’s focus is to address SEAH, there is significant reputational risk associated with any actions a partner might take that would undermine the UK’s reputation, or to make it appear that the UK is deprioritising SEAH.

On environment and climate, there continues to be no environmental or climate risks within the programme.

## F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.

INTERPOL has shown commitment to transparency and delivery, though some delays -notably on Due Diligence linked to Cooperation Agreements- and documentation gaps remain for the reporting period, namely narrative reports. The partnership is functioning well overall, with clear mechanisms for accountability and continuous improvement via collaboration between the project team and FCDO. Monthly financial meetings and bi-weekly partner check-ins have ensured close monitoring of spend and delivery variances related to the Logframe.

INTERPOL have subcontracted with Humentum and CHS Alliance for the delivery of internal investigations training for aid sector staff. These and any other future suppliers will be monitored and evaluated according to the Procurement And Contracts Management Strategy 2023-2026.

Financial Regulations, Directives, Staff and Procurement Manuals provide the regulatory framework for the required internal controls, the range of procurement services INTERPOL can offer are well controlled at the sectoral and operational level, with added reach through an electronic tender platform for publishing procurement opportunities above established thresholds.

The procurement and contracts practices and systems must align with best practices in the industry and international community, to facilitate efficiency and transparency, and apply a modern procurement and contracts risk approach.
## G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Reviews are systematically conducted after each Soteria exercise / events. Feedback is reviewed by the team and built into all future project deliveries. The team takes time to engage in the field with both operational / field-level staff as well as their hierarchies, to better understand on-the-ground challenges and how Soteria can support these while also align and build strategic support for such interventions. These activities led to for example, the request from the National Police in one country for Soteria to train a cadre of their National Police trainers. Soteria has now implemented this request, and the outlook is promising for the long-term impact of this intervention. Outside of the project team but internal to INTERPOL, the project is planning an evaluation exercise with the Project Portfolio Management Office (PPMO) to gain their insights and expertise on how the project has performed against the original proposal and their recommendations for any future intervention.

Evidence

A critical lesson has been the need to embed Soteria’s tools and training into INTERPOL’s core systems to ensure sustainability beyond FCDO funding. The integration of training modules into INTERPOL’s Global Academy and the digitisation of some content are steps in this direction. However, without a clear path to institutionalisation—such as endorsement by the INTERPOL General Assembly—there is a risk that the project’s gains may not be sustained long term which is in and of itself a significant reputational risk undermining the programme’s aims.

Learning

A major lesson has been the importance of timing and clarity in external communications. The project team recognised that launching high-profile communications (e.g. presenting to the INTERPOL General Assembly) before sufficient data and sign-ups were in place could risk reputational damage. As a result, the team opted for a more gradual, stakeholder-focused approach, including bilateral NGO meetings and a phased website rollout.

Additionally, the updated communications plan emphasised the need to tailor messaging for different audiences—law enforcement, aid organisations, and donors—highlighting the importance of clarity around the project’s scope and mechanisms. Feedback from one stakeholder who attended one of the above workshops was that;

‘the project has expertly communicated with key actors in a diplomatic and respectful manner, with the constant aim to create and maintain communication lines. They successfully created communication and engagement between actors who did not communicate before and were often reluctant to. This is a significant win. A next step could be to communicate more broadly on these nascent collaborations / Discussions between these actors (justice/police/NGOs), should they all agree to.’

Feedback from aid sector and law enforcement partners highlighted the value of Soteria’s collaborative model but also pointed to the need for deeper engagement and clearer pathways for participation. For example, some NGOs expressed uncertainty about how to sign up or use the system effectively. One stakeholder noted the system itself is clunky and manual – might need to reduce the bureaucracy of it. This might refer to the TIS forms – as they need to be uploaded manually. It would be beneficial if a slicker way of doing that could be found. There is a risk that administrative burden may act as a barrier to using INTERPOL systems thus failing to utilise the data and exchange suite. However, manual checks bring intensive and accurate checks of far more data comparative to automation, this should be emphasised with stakeholders to further facilitate deeper engagement and participation.

Feedback on from one stakeholder noted that; ‘[we] have worked together in the areas of SEAH Investigations, forging linkages between IQTS and project Soteria. Closer collaboration could be forged through continued training on investigations and bringing survivor centred approaches to law enforcement.’

Overall, feedback from stakeholders over the reporting period was positive with emphasis on a safe framework between law enforcement and the aid sector being invaluable. For the next reporting period engagement on an ad hoc basis with members of the Advisory board, which provide particularly valuable at the beginning of the programme, would be advantageous to gather feedback.

On tangible positive change, one stakeholder noted that, ‘ [following the workshop,] the NGO changed its protocols and process in terms of addressing cases with sexual offenders.’

Date of last narrative financial report	31/12/2024	Date of last audited annual statement	Year for 01 April 2023 – 31 March 2024: Audit report dated 24 September 2024.