## GRP Annual Review 2024

Title: Ghana Revenue Programme (GRP) 2025
Programme Value £ (full life): £8,500,000		Review date: June 2025
Programme Code : 300787	AMP start date: 06 August 2021	AMP end date: 31 July 2026

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Project GB-GOV-1-300787 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	DevTracker Project GB-GOV-1-300787 Documents (fcdo.gov.uk)

A. SUMMARY AND OVERVIEW

The Ghana Revenue Programme (GRP) is an £8.5 million programme running from 2021 to 2026, aimed at supporting the Government of Ghana (GoG) in strengthening sustainable and equitable revenue collection by addressing structural weaknesses in the tax system.
The programme secured a costed extension in January 2025 to increase the funding envelope from £4.6m to £8.5m and amend the end date from March 2027 to July 2026. The programme spent a total of £2.6m in the year under review, spending £0.81m on the World Bank agreement, £1.12m on Ghana Revenue Authority and Ministry of Finance, £78,000 on Civil Society interventions, £0.6m on Technical Assistance support to MoF and GRA. The increase in programme value was in part to accommodate an Externally Financed Output (EFO) agreement with the World Bank. The EFO is delivering technical support and capacity building to Ghana’s Parliament in relation to their oversight of economics, revenue and public finance. The additional funding is also enabling the programme to deepen benefits derived from GRP investments.
Key implementing partners include the Revenue Policy Division (RPD) of the Ministry of Finance, the Ghana Revenue Authority (GRA), the World Bank (WB), the Africa Centre for Energy Policy (ACEP) and the UK-Ghana Chamber of Commerce (UKGCC). GRP also collaborates closely with central UK programmes such as HMRC’s Capacity Building Unit (CBU) and the Institute for Fiscal Studies (IFS-UK) under the TaxDev programme. GRP has also received support from the Public Finance Resource Centre (PFRC)in procuring experts to provide technical assistance to GRA in the areas of investigations and prosecutions and procuring Ernst & Young (EY) who have embedded four data experts within GRA’s data mining and analytics unit to support the GRA teams build capacity and the required systems to advance the authority’s strategy to become data and analytics driven.

The programme was launched before a period of fiscal crisis in Ghana, characterised by rising public debt, a 10% fiscal deficit, and increasing reliance on tax revenue under an IMF Extended Credit Facility (ECF). With over 70% of projected 2024 revenue expected from taxes, the GRP has become increasingly central to Government of Ghana’s (GoG) priorities. Support for significant revenue generating areas included support to E-VAT, Automatic Exchange of Information (AEOI), E-commerce, and High Net Worth Taxpayers (HNWT).

The programme continues to offer significant complementarity to wider UK interests in Ghana. GRP’s increased focus on improving the experience of taxpayers/customers offers secondary benefits to DBT and UK Growth objectives by improving Ghana’s business environment and resource mobilization so that it can self-finance its human development and exit from aid. The GRP programme is also part of BHC Accra’s cross HMG renewed focus on anti-corruption. Finally, GRP’s efforts to strengthen Ghana’s fiscal sustainability remains critical to reduce the risk to future UKEF investments, with such investments having suffered significant losses following Ghana’s external debt default in December 2022.

The 2024-2025 reporting period presented unique challenges to tax administration in the country. Political activities preceding the 2024 general elections preoccupied the priorities of senior Government officials in the reporting year. The political activities intensified during the final half of 2024, softening enforcement across the tax system, whilst a change of top leadership in both early 2024 and again in 2025 slowed the signing-off of work plans and strategies for implementation. Despite these short-term disruptions, evidence from the annual review indicates that the programme’s long-term investments are yielding positive results and contributing to transformative changes. The Commissioner for Domestic Taxes in a meeting with the GRP team and HMRC acknowledged how the UK’s support played a key role in assisting GRA to exceed its revenue targets as well as support GDP growth in 2024. This is the first time in modern history that the GRA has exceeded revenue targets in an election year.

The priority of the GRA Commissioner General (CG) and team is to meet this year’s revenue target through a focus on revenue generating initiatives such as e-commerce and HNWT. There is also recognition of the long-term link between initiatives like improved customer experience and data utilisation with revenue growth, and the CG has successfully secured the support of the Minister of Finance and the GRA board to invest proportional resources and efforts into driving organisation reform.

This annual review covers the period from 6 August 2024 to 31 July 2025.[1] The programme scores an A overall: outputs were generally delivered to expectation, and great progress has been made in key strategic areas during the period under review. Two out of four outputs were assessed at ‘A’ and two others assessed as ‘B’. This report was written by Naghma-e-Tehniat Jerral - Economic and Governance Adviser from FCDO Pakistan. The reviewer engaged some of the partners remotely and spent five days in Accra engaging programme partners and FCDO teams in person.
[1] This cycle does not directly align with the Government of Ghana and UK financial years. Where relevant, activity reports cover pre-agreed periods falling within the AR period – for example, GRA statistics are reported for the year ended December 2024.

On tax policy, significant achievements included:
1. The 2023 Tax Expenditure Report was completed and published following ministerial approval, advancing fiscal transparency and oversight of tax incentives.
2. The draft exemptions regulations were completed by the Tax Policy Unit and submitted to the Subsidiary Legislation Committee of Parliament for consideration—marking a critical step toward operationalising the Exemptions Act.
3. Publication of the survey of the Ghanaian Tax System Survey of the Ghanaian Tax System | Taxdev
4. Joint undertaking between the MoF/TPU and the GRA to produce a tax policy analysis of political party manifesto tax policies ahead of 2024 election.
5. Policy Reforms enhancing transparency in mineral revenue management and unlocking funds for education, healthcare, and infrastructure.

The most significant achievement on revenue mobilisation was 35.8% Year on Year (YoY) growth, surpassing fiscal targets. Major, GRP-supported initiatives feeding into growth in revenue included:
  1. High Net Worth Office exceeding voluntary filing rate target by 2.5 percentage points, hitting 7.4% YoY
  2. Onboarding of 2,600 taxpayers bringing 85% of VAT receipts onto the electronic VAT (E-VAT) system
  3. 123% increase in e-commerce revenues despite the fact that only 40 new foreign platforms registered against the target of 54
  4. 1,723 individuals disclosed under Voluntary Disclosure Programme (AEOI) leading to collection of GHS 900 million.

- On systems strengthening side, major developments were:
  - Prosecutions & Investigations: 78 cases investigated (target: 20); 11 prosecuted (target: 15)
  - Development of data Governance, Quality Management systems and Taxpayer-360 portal
  - Development and launch of a new web-based organisation wide risk and incidence register. 67% of incidents reported through the risk and incidence portal were resolved.
  - The HMRC Long Term Strategic Adviser (LTA) to the Commissioner General has been in the role for close to one year now. The LTA is well respected within the GRA and has managed to secure the attention of the CG and his management team in driving the needed organisational reforms aligned with the CG’s priorities.
The programme team with support of HMRC Capacity Building Unit (CBU) organised a five-day learning visit to HMRC, HM Treasury and IFS UK. This visit afforded the Deputy Finance Minister, GRA Commissioner General and Commissioners an opportunity to have better understanding of the UKs offering on Domestic Resource Mobilisation (DRM) and provide the leadership an opportunity to build and consolidate the long-standing relationship between the UK and Ghana.

The most significant programme limitations this year were
- A 26.5% YoY reduction in revenue collection from HNWI taxpayers.
- Many indicators under Output 2 being developed or drafted but have not reached operationalisation or implementation in the time frame as envisioned.

Major lessons and recommendations for the year ahead

Recommendations:

Continued FCDO and HMRC support should be sustained in revenue generating workstreams. GRA officials recognized that reduced ODA spending may limit future support but emphasized the continued need for sustained engagement from FCDO and HMRC. The current finance minister commended the UK-Ghana revenue partnership and requested its extension during his first official meeting with the outgone High Commissioner. The CG has personally committed to supporting and promoting GRA’s efforts to become a data driven authority. The new government's demonstrated commitment presents a timely opportunity to deepen impact; targeted support to the data work stream will enhance GRA’s capacity to increase revenue from HNWIs, AEOI, and compliance—key areas currently supported by FCDO and HMRC. Whilst we need to understand the drivers of success and examine why certain programme areas fell short of output targets, it should be noted that the size of possible revenue gains in relation to the size of costs associated with the programme warrants a relatively high-risk appetite in taking forward further support. Institutional reform typically is high risk, high return. However, with small ODA where significant direct delivery is no longer possible for FCDO, supporting institutional change may offer the highest risk adjusted return, despite inherent risks and potential slow pace. Government commitment and political economy is often one of the largest risks to success. Clear commitment to reform by this new government reduces one of the major success risks making it even more opportune to continue this potentially transformative support. The office should take benefit of this window of opportunity and design a new programme in this space to keep the excellent momentum of reforms. The office should extend the current programme for another year (up to July 2027) to help maximize the gains secured since 2021, and enable planning of what well-targeted and high impact longer-term programming should look like post July 2027 once there is more clarity on future budgets at BHC Accra.

Support should focus on long-term impact areas. The programme needs to deepen its involvement in initiatives with medium- to long-term benefits, such as expanding the e-commerce sector and broadening the HNWI tax base. As these areas bring revenue yields only in long term (though have high revenue yield potentials), short-term revenue pressures often divert GRA’s focus from such systemic reforms. Continued FCDO investment in underfunded areas—such as embedded consultants and audit tools—will help build institutional capacity needed for sustained revenue growth in the longer term. The GRP and HMRC CBU team to take this forward.

HMRC’s role should come out more prominently in results reporting: Currently the GRP results logframe depends on contributions by HMRC, for example the HMRC peer-to-peer support on AEOI had a significant contribution to GHS 900 million collected through Voluntary Disclosure Programme (AEOI) but their role does not come out as strongly in results reporting. Now that there is a permanent Long Term Strategic Adviser with clear responsibilities to deliver these results, the programme should incorporate his deliverables as milestones in logframe. This will reflect one-HMG effort in a stronger way. There should also be specific GRP deliverables that focus on enabling and amplifying the HMRC work. The GRP and HMRC CBU team to take this forward.

Sustainability considerations. The programme team needs to develop a sustainability plan taking cognisance of the fact that the current programme ends in July 2027. With limited ODA allocation and limited clarity on future support for DRM, the team should work to determine plans beyond July 2027, develop and focus on delivering an associated plan with GoG counterparts to drive ongoing sustainability in the run up to closure in 2027. The GRP team should take this forward.

Continued strong coordination and advocacy is critical for reform continuity. Sustained coordination and strategic advocacy remain essential to advancing domestic revenue mobilization (DRM) reforms in Ghana. The programme continues to provide targeted technical assistance to the Ghana Revenue Authority (GRA), supporting improvements in key areas such as the High-Net-Worth Unit (HNWU) and the e-commerce tax unit. To ensure these reforms translate into lasting institutional change, consistent support from His Majesty’s Government (HMG)—particularly through the Foreign, Commonwealth & Development Office (FCDO) and HM Revenue & Customs (HMRC)—as well as from Development Partners (DPs), is vital. Their engagement helps reinforce reform priorities at the highest levels of government. The International Monetary Fund’s (IMF) emphasis on increasing domestic revenue presents a strategic opportunity to advocate for enhanced performance in these units. HMG’s diplomatic and technical support can be leveraged to align government priorities with reform goals. Progress to date has been driven by high-level engagements, including: The GRA and Ministry of Finance leadership visit to HMRC; Strategic meetings with the Minister of Finance; Breakfast briefings with the Commissioner-General; Consultations with political party manifesto teams; Engagements with the President of Ghana and Cabinet Ministers through the Heads of Corporation platform. These interactions have helped build momentum and secure buy-in for reform.

Creating direct linkages between ACEP’s work to support GoG efforts in DRM. The programme should deepen its collaboration with the Africa Centre for Energy Policy (ACEP) to support the Government of Ghana’s domestic revenue mobilization (DRM) efforts, particularly in the extractives sector. ACEP’s technical expertise and policy insights should be systematically integrated into the Ghana Revenue Authority (GRA) and Ministry of Finance (MoF) reform strategies to ensure relevance and impact. Additionally, the programme should support ACEP in leveraging its advocacy network—including civil society organizations, think tanks, and media influencers—to promote voluntary tax compliance. This can be achieved through coordinated public education campaigns, community outreach, and media engagements focused on improving public understanding of tax obligations and the benefits of taxation. By aligning ACEP’s technical outputs with government priorities and amplifying its public engagement efforts, the programme can contribute to more inclusive and sustainable DRM reforms. The GRP team should take this forward.

Provide sustained support for cultural shifts. Institutional reforms—such as strengthening parliamentary oversight and improving accountability mechanisms—require long-term commitment and resources. Given anticipated reductions in Official Development Assistance (ODA) for future programmes, the programme should proactively explore cost-effective and sustainable financing options, such as leveraging World Bank trust funds and other multilateral instruments. There should be a clear interrogation of the end goal of support to Parliament to ensure activities are well targeted. Beyond July 2026 it should be considered whether activity supporting parliamentary accountability fits with this programme TOC or is it better delivered in conjunction with different FCDO programming. GRP team to take this forward.

The following recommendations are to be reflected in a future programme design. Undertaking an overhaul of the logframe will not be the most appropriate action to take immediately, noting GRP has a year and a few months to closure. The GRP team should engage the results adviser on how best to ensure these recommendations are well catered for in the future programme design.

FCDO can enhance impact by connecting interrelated initiatives. Synergies across workstreams—such as data analytics, HNWI, AEOI, and e-commerce—should be leveraged through a coordinated approach and reflected in the programme logframe. The programme team needs to map out and formalise these linkages at least six months before the next review period using findings from planned outcome harvesting evaluation exercise.

The programme is meeting milestone indicators against the outputs and contributing to outcomes. However, there is a need to estimate the direct contribution of GRP’s initiative to outcome level indicators such as tax to GDP ratio and revenue growth. For example, support to the data unit has helped draw better insights, ensuring the data received becomes useful to driving compliance and revenue collection but its direct contribution to revenue collection is difficult to estimate. There is a need to focus some monitoring and evaluation expertise to estimate contribution/attribution in order to better inform pipeline planning especially with limited resources going forward.

Outputs are bringing in impressive results, however, the links between some outputs and impact/outcome indicators are better established in some areas like HNWU and AEOI but less well established in some other areas of support. For example, the onboarding of 2,600 taxpayers has brought 85% of VAT receipts on to the electronic VAT (E-VAT) system but how much this has contributed to revenue growth is not quantified. Similarly, a 23% increase in e-commerce revenue is momentous but its proportion in relation to total revenue collection is not known. There is a need to add intermediate outcomes to make this connection clearer.

Below are some lessons learnt over the review period:
1. The programme relies on sound evidence that supports transformation in determining which specific project areas to invest in. The changing context and priorities have meant such initiatives suddenly become crucial in meeting transformational or revenue demands. An example is how GRA resorted to GRP investments in AEOI and E-Vat to meet agreed structural benchmarks as part of the IMF programme. Another example is how the programme’s interventions has supported internal GRA teams in driving the organisation’s focus on data analytics and customer experience in a challenging operating environment. These efforts have provided the CG a good platform to drive his priority of turning GRA into a data driven and customer centric revenue authority.
2. The programme team have relied not only on working level engagements to deliver GRP results, but the team has been deliberate about combining all of UK Ghana levers including programmatic and diplomatic resources to drive the needed reform. UK Ministers, the High Commissioner, Development Director and HMRC leadership team use their engagements with senior GoG Officials including the President, Minister of Finance and Commissioner General to encourage them to champion the needed reforms. This programme has evidenced how important coherent and targeted x-HMG working is. It is recommended this is taken further by using diplomatic levers more deliberately to help drive programme outcomes.
3. A significant review of GRA operations - a requirement of Ghana's Medium Term Revenue Strategy (MTRS) delayed for close to 5 months because of lack of shared ownership and collaboration between the leadership teams of Ministry of Finance and GRA. The programme team should have foreseen this in the onset and pressed for joint ownership to be secured. The review is now back on track after the delays but based on this lesson the programme team should identify the challenges in advance and have focus on joint ownership at the scoping stage wherever works strands relate to both the MoF and GRA.
4. BHC Accra made a concerted effort to engage political parties on manifesto development in 2024, with positive results that exceeded expectations in terms of manifesto content, and in the positive relationships built with the incoming government. This approach should be a default in Ghana, and possibly further afield.”
5. Political economy dynamics must continue to inform reform strategies. Success of reforms, particularly their implementation, depends on navigating political realities. Political economy analysis and strong accountability mechanisms should be embedded in high-risk initiatives with regular PEA check-ins to identify and mitigate risks. The programme remains successful because of how the team has consistently embedded PEA in the design and delivery of programme activities, this is anchored on the team’s delivery approach which is built on a longstanding partnership based on respect and trust as well as the hands-on approach used by HMRC experts, the FCDO team and embedded delivery consultants. An example is the launch of the Voluntary Disclosure Programme (VDP) as part of the AEOI workstream which had to navigate a number of political economy considerations to be a success.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The programme’s ToC assumes £8.5m in funding for a range of technical and institutional support. Key outputs include substantial reforms within the Ghana Revenue Authority (GRA), such as enhanced audit processes, IT system upgrades, digitalisation, and improvements in risk management, AEOI, high-net-worth individual (HNWI) profiling, and prosecution frameworks. Outcomes aim to increase tax collection from key sectors while reducing tax losses and boosting voluntary compliance. The programme also seeks to embed evidence-based policymaking and administration, enhancing the social contract and fiscal accountability. The impact level ambition is for the GoG to sustainably and equitably increase its tax-to-GDP ratio.

The 2025 logframe underwent several adjustments between January and March 2025 and was approved in April 2025 to align with evolving programme priorities and resource realities (detail in Section C against each output). The Theory of Change was revised in 2023 to ensure clarity, stakeholder alignment, and evidence-based assumptions, but there were no changes made to outcome and impact ambition.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The programme is on track to contribute to the expected outcomes and impact.

Tax revenue hit GHS 153billion in December 2024 exceeding the budget target by 0.2% (first time tax targets have been achieved in an election year). The performance represents a nominal growth of 37.6% over the same period for 2023. These figures are affected by high rates of inflation, but the tax to GDP figure is not affected by this. Tax to GDP also improved from 11.3% at the start of programme to 14.4% in 2024 which is an improvement over last year (14% for 2023)[2]. GRP’s ambitious impact level target (of 14.5%) for the review period is therefore almost achieved.
[2] GRA and MoF official figures

The programme is focussed on supporting GRA to keep improving the tax to GDP ratio as well as improving voluntary compliance among taxpayers. The programme performed well against logframe outcome indicators and targets. The High Net Worth rate of filing of returns moved from 60.4% in 2023 to 83.9% in 2024, the rate of large taxpayers filing returns moved from 75% in 2023 to 80.5% in 2024.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

OUTPUT DESCRIPTION	OUTPUT SCORING
Improved Systems in GRA for Revenue Generation	A
Improved GRA-wide information systems for identifying and monitoring taxpayers for Improved Compliance	B
Strengthened Tax Policy and Forecasting	A
Improved capacity for accountability of tax revenue through Citizen’s engagement	B

The programme presents strong evidence of significant value for money and should continue on this basis. The UK’s support to GoG on DRM has steadily progressed since its inception in 2017. At the impact level, Ghana’s tax to GDP ratio has moved from 11.3 in 2020 to 14.4 in 2024. There is an unprecedented level of traction and buy-in from GoG’s side which has ensured consistency and sustainability in reforms. This buy-in is likely strong linked to the pressures of the IMF programme following Ghana’s fiscal crisis. However, the momentum has further increased after the elections, and it has been reflected in the appointment of a highly technocratic expert leader to the position of Commissioner General. The programme has built a trusted relationship with the government, putting it in a good position to use the window of opportunity to influence and support government to make substantive reforms, and there are examples of good VFM. This also highlights why the team should secure a costed extension for a year (from July 2026 to July 2027) this is critical at this point and it will help to sustain momentum and maximize the impact. This review finds that the WB component, being newly commenced, is not strongly aligned to GRP’s theory of change

## C. DETAILED OUTPUT SCORING

Output Title	Improved Systems in GRA for Revenue Generation
Output number:		1	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 High Net Worth Office (HNWO) able to effectively use third party data to identify and profile High Net Worth Individuals (HNWI) for appropriate compliance. interventions: Delivery of research that estimates the total number of HNWI within Ghana in support of improved capacity for revenue mobilisation.	• Year on year increase in voluntary filing rate by HNWI taxpayers by 5% (on previous year's performance) / • High Net Worth Office Data Strategy Document developed and approved by Top Management. / • Improved year on year revenue collection from HNWI taxpayers by 3% (on previous collection of GHC 390million)	1.1.1 Exceeded - The voluntary filing rate increased by 7.4% over the past year exceeding the target of 5%[3]. / 1.1.2 Partially Met - an abridged form is drafted / 1.1.3 Not Met – HNWI revenue went down compared to last year by 26.5% and revenue collected was GHC 285 million
1.2 Development and usage of E-Vat system leads to increased contribution of VAT to tax revenue	• 100% of the delivery plan for EVAT phase 2 implemented / • Improve compliance in VAT - in filing, payment, onetime filing and payment - 30% / • Compliance rate to E-VAT system usage – 70% taxpayers onboarded are using the electronic invoicing systems (monitors the % of taxpayers who are consistently issuing electronic invoices in compliance with regulations	1.2.1 Met - 100% implementation of delivery plan / 1.2.2 Not Met - None of the taxpayer onboarding groups (50, 600 and 2000 taxpayers) achieved 30% increase. / 1.2.3 Met – More than 70% adoption rate in first two batches. 98% for the first batch, 72% for the second, and 58% for third batch.
1.3 Development, implementation and socialisation of prosecution and investigation policies and processes to improve GRA compliance systems	• 20 cases adopted for criminal investigations of which 15 are presented for prosecutions / • Capacity building - Training of Prosecutors, Investigators and Intelligence officers (20) trained in assets tracing, confiscation and recovery of proceeds from tax related crimes, financial investigations techniques and cyber crimes	1.3.1 Partially Met - 11 cases progressed to prosecutions. / 1.3.2 Exceeded - Training held for Prosecutors, Investigators and Intelligence Officers. 31 officers were trained.
1.4 Ecommerce. Supporting the team, to set up processes and systems as well as build the needed technical capacity to effectively tax the E-Commerce sector	•Increases in taxpayer registration - additional 54 non-resident entities are registered to fulfil their tax obligations / •Revenue Contribution - 25% increase in revenue by year end. / •Capacity building of the E commerce unit in data analysis - All E commerce unit staff trained in data analytics techniques (100%) / •Strengthening operational efficiency of the team - Evaluation report of the unit delivered including capacity gaps and recommendations and a training plan for the unit identified	1.4.1 Partially Met - 40 non-resident e-Commerce entities registered. / 1.4.2 Substantially Exceeded – 91% increase in revenue from non-resident entities over past year. / 1.4.3 Met - E-commerce team trained in data analytics / 1.4.4 Met - Capacity building exercise conducted, report publishes, training plan identified.
[3] (HNWO 2024 Annual Report)

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output focused on capacity building through training and analysis of operations, designed to lead to improvements in specific areas of tax collection, prosecution and tax policy, and thus directly leading to increased revenue.

On balance, the output scores an ‘A with three milestones exceeding expectations, four fully meeting expectations, three demonstrating notable progress toward the target but falling short, and two not meeting expectations. Overall, the work and immediate impact of the programme in this output area can be said to have been positive and consistent with overall expectations. Some of the targets met were Output oriented (such as capacity building trainings delivered or strategies drafted or implemented) from which impact is hard to glean. However, several of the Outputs that met or exceeded were more “Outcome” in nature demonstrating genuine progress toward end goals, such as significant increases in the voluntary filing of HNWI, consistent adoption of electronic invoicing systems, and “partially met” indicators of 11 prosecutions and registry of 40 non-resident e-commerce entities. Unfortunately, only three targets related to actual revenue collection (1.1c, 1.2b) and 1.4b), two of which were “not met”. This may indicate that some scrutiny is needed of the assumptions underpinning the theory of change for how (and when) activities may lead to increased revenues, and an examination of when and how target setting takes appropriate account of baseline figures. This should be a focus in the ongoing evaluation work to inform design of new or further programming. It should be recognised that achieving the e-commerce target of GHC 349 million (almost double the collection in 2023 of GHC 177 million) is significant enough to warrant further support from GRP, despite shortcomings across some other indicators. More assessment of GRPs contribution is needed to determine future funding plans.

1.1 Partially Met. Revenue collection growth among HNWI taxpayers fell short of the target of a 3% increase on the previous year’s achievement, instead, registering a 26.5% decline, a performance that has partly been attributed to the drop in political will to enforce tax compliance and to pursue tax debt within the election year.  HNWO had consistently registered increases in their revenue collection ranging from their first collection of 6.2 million cedis in the election year of 2020 to 390 million cedis in 2023. Over the period of the operations of the HNWO, the tax gap between what the identified HNWI paid and what they were supposed to pay has reduced leading to less additional collection. Also, the HNWO lost access to a key source of data for the identification and tax assessment of high-net-worth individuals. Access to Automatic Exchange of Information (AEOI) data was a main factor considered in the estimation of the target for the year, but this data was not made available to the HNWO due to HNWO’s lack of a secured perimeter status. Administratively, the staff strength of the HNWO was reduced to 12 (out of an expected 40 staff) within the course of the year due to inadequate recruitment as well as absences of some staff on long term training at the GRA Training School.

With compliance rates going up among the identified HNWIs, future revenue increases will depend much on the identification and profiling of new HNWIs, an objective that will depend much on a sustained access to GRA and third-party data. The HNW office is also focusing on sectoral analyses in the identification of more HNWI, an example being the contracts awards database from the Controller and Accountant-General’s office. GIZ is also supporting GoG in HNW taxation and FCDO’s work is coordinated with GIZ’s for impact. GIZ are supporting development of a HNW Policy being championed by the Revenue Policy Division of the Ministry of Finance with the active involvement of the FCDO.

1.2 Met. This output focused on expanding the E-VAT system to boost VAT revenues. Nearly 100% of the Phase 2 delivery plan was implemented, with 2,600 taxpayers (85% large taxpayers) onboarded. Although 30% increases across all the compliance measures is not achieved—partly due to a high baseline from the previous year without due consideration to the existing context, as well as setting output indicators measuring VAT compliance instead of measuring E-Vat contribution to wider VAT collections, this is a lesson well learnt. However, system usage exceeded expectations: 98% for the first batch, 72% for the second, and 58% for the third[4]. Success was driven by strategic deployment of relationship managers, third-party developer engagement and a strengthened compliance framework. The reason for the downward trend across the three batches was a delay in the onboarding of later batches – linked in turn to a slowing down of activity at the GRA during the election period.
[4] GRA official system

1.3 Partially Met. This output aimed to enhance compliance through prosecution and investigation policies. During the year, 78 cases were referred to for investigation against a target of 20 but, only eleven cases out of an expected number of 15 were prosecuted. It was easier to detect cases for investigations however, bringing them to the prosecution stage was more difficult than expected. Reasons included poorly documented dockets, the absence of dedicated tax courts and the absence of legal advisers. However, the second milestone was achieved through specialised training for GRA staff in asset tracing, financial investigations, and cybercrime, supported by a capacity-building strategy and a Lessons Learned workshop.

1.4 Met. This output focused on taxing the e-commerce sector through system development and capacity building. Registration of non-resident entities fell short (40 vs. 54 target), reflecting a maturing base but also data limitations and issues in third party data acquisition, due to absence of multilateral agreements. Despite this, revenue from non-resident taxpayers rose by 91% to GHS 349.4 million, far exceeding the 25% target. The reason for the spike was a few cases involving very large revenue amounts. Total e-commerce revenue (resident and non-resident) reached GHS 1.13 billion in 2024, up 123% from 2022. The third milestone was also met through a benchmarking and capacity-building exercise led by Deloitte, with an evaluation report submitted in December 2024.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The logframe’ s Output 1 underwent some changes before review period in response to past annual review recommendations. Indicator 1.3 saw the removal of Domestic Tax Revenue Division (DTRD) Rationalisation which was replaced with "Investigations/Prosecutions" due to the former's lack of momentum because of capacity constraints withing GRA in meeting revenue targets and the latter's relevance to compliance enforcement. A new indicator was introduced to Output 4 to accommodate the EFO agreement with the World Bank.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

All recommendations for this output were progressed – see annex I for details.

An important lesson learnt on this output is that target setting at times disregarded improvements in baseline. For example, the case of HNW revenue targets since compliance improved over the base year so the need or space for disclosure also went down. Going forward, there is a need to take cognizance of these changes in baseline. All logframe targets will be reviewed ahead of the final year of implementation to ensure they are appropriately ambitious based on current context.

During the review, GRA officials consistently emphasised the need for continued FCDO support, particularly in fast-evolving areas where government prioritisation and funding remain limited. For instance, Deloitte’s work on digital market exploration shows strong potential and this has been acknowledged by the C.G who has recognised the revenue potential E-commerce taxation presents to GRA. Similarly, while FCDO’s support in DTRD restructuring project was appreciated, officials highlighted the need for GRP support to deliver the last component of the restructuring project to secure sustainability.

The programme should prioritise the continuation and deepening of its support in this output area, within budget constraints. This is especially recommended in the areas where impact is expected to be achieved in long or medium term such as broadening of e-commerce and HNWI tax base (Programme SRO and PRO, while finalising next year’s work plan).

Output Title	Improved GRA-wide Systems for identifying and monitoring taxpayers for improved compliance
Output number:		2	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Data Analytics Unit mature its data analytics Capabilities to deliver analytics that meet GRA needs - an integrated data analytics function in GRA, ensuring a holistic data analytics approach to data	•Data Governance/Management Framework (DGF) approved by senior management for implementation / • Data Governance Framework (including Data Quality Management Framework) operationalised within GRA, / • The 'Taxpayer 360 portal' completed and rolled out as part of GRA’s Data Warehouse	2.1.1 Partially Met - Data Governance Framework drafted pending approval from GRA. / 2.1.2 Partially Met - Change Management strategy for operationalising Data Governance Framework developed. / 2.1.3 Partially Met - Reporting module of the Taxpayer 360 completed.
2.2 GRA fully compliant with the global standards with an established, documented strategy for the effective ongoing use of Automatic Exchange of Information (AEOI) data	• 5000 individuals voluntarily respond to the VDP and GHS 1 billion collected by the end of first phase (December 2024) of implementation / • EOI Unit reviews Common Reporting Standards (CRS) Compliance Audit training materials and apply 50% of principles and tools in practice. / • Implementation of all Confidentiality and Data Safeguards (CDS) assessment recommendations on track for Information Security Management within the Authority.	2.2.1 Partially Met - 1,723 individuals made the required disclosures, GHS 900 million collected. / 2.2.2 Met - workshops organised, audit Manual developed, specific risk registers created. 60% of principles and tools applied in practice / 2.2.3 Partially Met - some measures undertaken but not full implementation.
2.3 Annual Compliance Improvement Plan (CIP) implementation for the GRA	• LTO CIP draft document approved, and pilot commenced. / • 90% of Middle Management sensitised on the CIP to ensure its effective implementation / • Taxpayer voluntary compliance improves by 10% following rollout of CIP in all TSCs.	2.3.1 Partially Met - draft document is approved / 2.3.2 Not Met - due to delay in 2.3.1 / 2.3.3 Not Met - due to delay in 2.3.1
2.4 Development of a risk-based audit selection process to improve the risk and data-driven selection of taxpayers for audit as well as embed excellence in GRA’s audit function by upskilling skills of auditors and working to set standards.	• 100 audit officers retrained on the use of the Audit Model in GITMIS 3 with a usage adoption rate of 40%. / • Audit manuals developed for 3 specialized sectors adopted. / • Post Audit Survey platform developed and operationalised	2.4.1 Partially Met - 109 Audit Officers trained but usage rate of 11.37%. / 2.4.2 Partially Met – 3 Audit Manuals for the Telecommunications, Manufacturing and Financial Services sectors developed, yet to be approved, so adoption is delayed. / 2.4.3 Not Met - Delay in development of platform, operationalisation is also delayed
2.5 Development and embedding enterprise and compliance risk management functions within GRA to enhance decision making and improving revenue collection	•Utilisation of GRA risk register, Percentage of Risks identified for GRA operations (DTRD-30%, Customs-30%, SSD -20%) / GRA's operational compliance improved by 10%, / • 30% of risks/incidences reported, resolved by well-defined mitigation strategies	2.5.1: Not Met - Risks Register could not be reviewed within the timeframe. / 2.5.2 Met – GRA’s operational compliance improved by 49%, all Units and Departments have Standard Operating Procedures (SOPs) in place to guide their work. / 2.5.3 Exceeded - A total of 162 incidents have been reported, out of which 109 / (67 %) have been resolved, with 53 incidents (33%) unresolved.
2.6 Customer experience and communications and public affairs function- as tools to improve voluntary compliance.	• CPA Restructuring Plan completed and approved by senior management for implementation. / • 100 selected staff and taxpayers participated in focus group discussion to track the impact of the maiden Customer Experience Conference. / • 600 GRA frontline staff trained on customer service and ethical behaviour	2.6.1 Partially Met - Draft CPA restructuring plan is completed pending approval. / 2.6.2 Not Met - Focus group discussion not conducted / 2.6.3 Exceeded - 793 staff trained

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The output scores a B with two milestones exceeding expectation, eleven meeting expectations (nine partially and two fully) and five not meeting expectations. Most targets related to stronger systems and policies being developed and implemented. This Output delivered well in relation to drafts being developed and trainings delivered but consistently fell short in relation to sign off by GRA leadership team and subsequent implementation. Most output indicators having been partially met, the overall score for this output is B even though delays were because of a critical point in political cycle and not because of the delivery team’s lack of efficiency. The outputs which have partially met expectation are expected to be finalised. As with Output 1, the delay in indicators being implemented may indicate that some scrutiny is needed of the assumptions underpinning the theory of change. This should be a focus in the ongoing evaluation work to inform design of new or further programming. Again, it should be recognised that the 900m revenue from the VDP achieved is significant enough to warrant GRP support, despite shortcomings across some other indicators. More assessment of GRPs contribution is needed to determine future funding plans.

2.1 Partially Met with progress in all three milestones towards target. Progress was made across all milestones. Draft Data Governance Framework (DGF) and change management strategy were developed and showcased, but both await GRA approval due to top-heavy decision-making. Data cleansing was conducted which did contribute to increased taxpayer registrations. The Taxpayer 360 reporting module was completed and shared for internal review. While there was progress in developing the DGF, its rollout strategy and the taxpayer 360 portal none are yet to be reviewed, signed off or rolled out, so little can be said about quality or impact.

2.2 Partially Met - GRA advanced Automatic Exchange of Information (AEOI) compliance with partial achievement across three milestones and full delivery on one. The Special Voluntary Disclosure Program (SVDP) helped reach 1,723 disclosures, collecting GHS 900 million, which means GRA almost hit the revenue collection target which was made possible through programme’s interventions including securing the technical assistance of a team of VDP experts from HMRC to quality assure GRA’s VDP strategy and delivery plan Common Reporting Standard (CRS) workshops and audits were conducted. FCDO has also supported sensitising and registering banks on their CRS obligations with Reporting Financial Institutions (RFI)’s registrations rising by 44%. A compliance manual and risk registers were developed. Some measures for information security are undertaken, for example, training for GRA staff, enforcement of restrictions on public mail services and public cloud storage service, adequate Bring Your Own Device (BYOD) policies and mobile device management within the secure perimeter, and restriction of access to confidential email to selected EOI staff. There is a requirement for GRA to comply with the standards and all these efforts led to compliance of these standards which enable GRA to identify GHS 3.1 billion in liabilities; GHS1.6 billion are sub-judice whereas GHS1.4 billion are ready for recovery out of which GHS 900 million have been collected to date.

2.3: Not Met - The Compliance Improvement Plan (CIP) pilot was delayed due to late approval, affecting rollout and sensitization targets. Despite this, the draft informed the 2025–2026 enterprise-wide CIP, which is due for publication, launching and operationalization by the end of July 2025. Milestone for taxpayer voluntary compliance improving by 10% is also not achieved as the rollout of CIPs in all TSCs was delayed. Interim activities, including training and roadshows, were undertaken with HMRC support.

2.4: Partially Met - Audit reform progressed with 109 officers retrained (exceeding the target), but system adoption remained low at 11.37% due to technical and behavioural barriers. Some of the barriers were short term such as functionality/connectivity/ low baseline issues which can be resolved through technological and programmatic solutions while others more complex such as resistance to change. Audit manuals were drafted but not approved and development of the audit performance platform is underway, with completion expected by September 2025. There is delay in development of post audit survey platform and consequently its operationalisation is also delayed

2.5 Partially Met – There were mixed results on embedding of the risk management. SOP development exceeded the target of ensuring 30% of departments and units within GRA having SOPs in place. GRA managed to reach a 49% mark. The risk register reviews could not be completed. Incident reporting showed 67% resolution, but underreporting remains a concern. Business process reengineering is expected to improve SOP coverage and risk tracking.

2.6: Met - The CPA Restructuring plan is completed pending approval by the GRA senior leadership, focus group discussions are not conducted due to scheduling reasons and realignment of top management priorities in the last financial year. However, the target of training GRA frontline staff trained on customer service and ethical behaviour was exceeded by 793 staff getting trained against the target of 600.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

In contrast to Output 1, Output 2 underwent an expansion in scope, with the number of indicators increasing from four to six. This change reflects a broader emphasis on institutional strengthening and taxpayer engagement. A new indicator under 2.5 was introduced to cover "Enterprise and Compliance Risk," highlighting the importance of risk-based decision-making in tax administration. Additionally, "Customer Service and Communication and Public Affairs" were added under 2.6, recognising their role in improving voluntary compliance and public trust. These additions aim to enhance the GRA’s capacity to manage taxpayer relationships, improve service delivery, and embed a culture of data-driven compliance. The expansion also supports the programme’s shift toward outcome-focused measurement and more integrated approaches to taxpayer engagement and risk management.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

All recommendations for this output were progressed – see annex I for details.

There are inter-connections between various pieces of work being delivered and FCDO’s programme team should update the log frame to set out how these connections will be supported. For example, connecting the data unit with the HNWI and AEOI units can provide a holistic view on data which can contribute to broadening of the tax base. Similarly, country by country reporting (CbCr), AEOI and E-commerce work has a bearing on tax transparency. Work is being done on these inter-connections on a need or ask basis but there is the need to spell this out through the logframe so it can be captured in results reporting..

Reforms often do not contribute to revenue generation in the short term, whereas GRA’s focus is on meeting revenue targets, which diverts resource allocation to areas which bring revenue growth more quickly. Auditor’s performance, for example is measured in terms of value of detections made so instead of undertaking audit using Ghana Integrated Tax Management Information System (GITMIS), the auditors rely more on manual selection of audit to generate revenue quickly rather than building capacity and familiarisation that would support greater revenue long-term. Similarly voluntary disclosure and AEOI work needs patient handholding from HMRC’s experts and consistent peer review. Embedding audit systems, risk management and specialised comms in GRA’s systems will lead to revenue generation through better compliance. To embed long-term reforms, FCDO should continue investing in areas where GRA lacks short-term capacity—such as deploying embedded consultants (a proven model) and providing targeted capital support, for example, funding audit software licenses rather than one-off events like conferences.

While elections were cited as a key cause of delays in the new frameworks, portals and plans not being implemented, the programme should interrogate the barriers to effective implementation further and potentially update the final year’s workplan in response. Election effects should also have been predicted and reflected in target.

The FCDO programme team should confirm that planned outputs are in line with GRA’s strategic plans and have sufficient political buy-in for uptake, to avoid situations of reports and models being left on the shelf. These pieces of work are important to improve revenue long-term, but attention is often diverted due to short-term pressures. FCDO should confirm the change being aimed for is viable, without diverting GRA officials time so much that they are not able to do their day-jobs (this should be looked at in the round alongside other Development Partner engagements with the GRA).

Functionality/connectivity, low baseline and behavioural aspects were cited as core issues. These could be quite fundamental barriers to success. The programme team should check that the workplans are viable within the realities of the GRA office, that the systems being developed are functional in context, and have the necessary follow-on support to enable take up and that the context of incentives allows progress. In work strands where behavioural challenges exist the team should consider the risk-benefit balance to test what are the most effective work strands to focus on. This assessment should be cognisant of incentive structures. It may be sensible to revise targets to be less ambitious in terms of scope, ensure they are focused on changes that can be high-impact and are sufficiently high GRA priorities to be followed up on implementation, and that training and take up is focused on the most relevant individuals. Political economy should be assessed.

Output Title	Strengthened Tax Policy and Forecasting
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Capacity to develop effective Tax and Non-Tax Policy	• Tax Policy Costing for 2025 budget and options paper produced / • Fees and Charges database completed and functional / • Developed Revenue Policy Division Strategic plan for the implementation of the Medium-Term Revenue Strategy	3.1.1 Met Joint Policy Costing session held to cost the impact of tax policies in the various party manifestoes. / 3.1.2 Partially Met Database completed. Undergoing tests prior to full functional usage. / 3.1.3 Not Met - USAID part-funding stalled.
3.2 Tax Exemptions	• Publication of the 2023 Tax Expenditure Report / • Exemptions Regulations submitted to Parliament	3.2.1 Met, 2023 Tax Expenditure Report approved. / 3.2.2. Met, draft Exemptions Regulations completed and submitted to Parliament.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The output scores an A with three out of five milestones meeting expectations, one partially and one not meeting expectations.

3.1 Met - This output aims at capacity development for effective Tax and Non-Tax Policy. A joint policy costing session to cost the impact of tax policies in the various party manifestoes was achieved as planned. Moreover, staff members were trained in building financial model agreements for the mining sector which enabled them to forecast expected revenues. A fully developed fees and charges database was delivered within the year, pending routine tests prior to full functional usage. The fees and charges database will improve accuracy and timeliness of the annual review of fees and charges for ministries, departments and agencies. This is a legal requirement which feeds into the national budgeting process. The database system is meant to introduce efficiency into the administration of non-tax revenue especially as the number of collecting entities continue to grow. The third milestone was developing Revenue Policy Division (RPD) Strategic plan for the implementation of the Medium-Term Revenue Strategy. This is not met yet. The revoking of USAID funding stalled this joint initiative between the FCDO and the USAID. MOF has made a fresh request to FCDO to fill in the gap in funding resulting from the USAID pull out This request is subject to the already commercial agreements in place between RPD and the consultants plus cost implications so will be reviewed in more detail for whether it is VfM.

3.2 Met - with the 2023 Tax Expenditure Report approved and published on the Ministry of Finance Website and exemptions regulations submitted to Parliament. The regulations are meant to bring clarity to the Act already passed.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The previous output 3.1 description focusing on MoF capacity to implement tax and non-tax policy was changed to ‘Capacity to develop effective tax and non-tax policy’ to highlight MoF core function.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

All recommendations for this output were progressed – see annex I for details.

The delay in the delivery of the Revenue Policy Division (RPD) Strategic plan is due to the unforeseen cut in USAID funding which meant an output (funded by USAID) which was expected to be the building block upon which the RPD strategy was to be built on was suddenly truncated. The RPD director has requested FCDO to help complete the task to enable the division to progress work on developing their strategy. The GRP should consider this, alongside reviewing other outputs that are delayed before implementation and causes of delays, to review what is the best thing to focus on what could be its final year (depending on extension). UKGCC consultants should be requested to review the status of the RPD strategic plan, how much effort or funding would be needed to get it to delivery and to be of good quality, and likely chance of uptake once complete. The impact of USAID withdrawal highlights the importance of ramping up the development partners coordination to ensure sustainability of reform process, targeted and coherent support, and avoiding overlaps. It may also strengthen the case for multiple donors providing project focused budget support to a single agreed plan, which gives agencies more scope to refocus funds to highest priorities if there are unforeseen changes in funding from individual development partners.

Output Title	Improved Capacity for accountability of tax revenue through citizens engagement
Output number:		4	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Evidence of tax losses and or evasion as part of governance challenges in the extractive sector publicised	• Commitment secured from National Petroleum Authority (NPA) to scrap redundant petroleum margins such as the Unified Petroleum Pricing Fund (UPPF) / • Commitment secured from NPA to end the premix fuel subsidy. / • Bill initiated to pass a levy to fund the regulatory functions of the National Petroleum Authority.	4.1.1 Not Met - ACEP provided research evidence which contributed to surcharges against the former NPA boss elevating the national visibility of issue. / 4.1.2. Not Met - ACEP is ready with inputs to be presented. / 4.1.3. Not Met - ACEP plans to advocate during the review window of the NPA Act.
4.2 Citizen's interest and engagement with Tax Reform, compels duty bearers to be more accountable with tax related issues.	• 1 CSO-government forum organised to discuss policy alternatives on PFM and anti-corruption issues. / • 6 podcast recordings done to focus on policy conversations on Governance, Transparency and Accountability. / • 6 high quality investigative reports produced on PFM and anti-corruption by trained journalists. / • 1 breakfast meeting held with media influencers to discuss PFM and anti-corruption issues.	4.2.1 Exceeded - 3 meetings held / 4.2.2 Not Met ACEP to refocus the content of the podcasts to respond to current macroeconomic governance issues. / 4.2.3. Not met. Consultant has been procured to train journalist. Once training is concluded the reports will be produced and published. / 4.2.4. Met Breakfast meeting held
4.3 Building capacity of selected parliamentary committees to improve accountability and transparency in economic governance	• Five relevant parliamentary committees engaged as part of project inception. / • Baseline study of Parliamentary capacity completed to inform year 1 workplan	4.3.1 Met - More than 5 engaged / 4.3.2 Met - Baseline study completed

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Output 4: This output scores a B, with five out of nine milestones not meeting expectation, three meeting and one exceeding expectation. Despite this, and the related political and coordination challenges, it contributed notably to programme’s outcomes, including investigations into petroleum fund mismanagement uncovering GHS 1.3 billion in recoverable funds and government reforms influenced by civil society advocacy.

4.1 Partially Met. Progress was made across all three milestones, though none were fully completed. A policy paper on inefficiencies in downstream petroleum tax administration informed stakeholder engagement and contributed to accountability actions against former NPA leadership. Efforts to eliminate the Unified Petroleum Pricing Fund (UPPF) and end the premix fuel subsidy are under policy consideration. Additionally, a proposal to introduce a levy to fund NPA’s regulatory functions is being pursued through the review of the NPA Act. With the change in government and appetite of the new government to pursue reforms in the downstream petroleum sector, ACEP is well placed now to progress these activities. The team should consider the limitations or barriers to meeting this target to consider if the programme can flex to respond effectively.

4.2 Partially Met - Citizen engagement in tax reform advanced through a CSO-government forum and a media influencer breakfast meeting, both generating strong media traction. Investigative journalism and podcast initiatives are underway, with trained journalists and influencers now actively engaging in fiscal governance with proactive coverage of public financial management. A follow-up residential training is planned to deepen media involvement in public financial management and anti-corruption discourse. The groundwork for producing six high-quality investigative reports is on track, with journalists selected and training processes initiated, completion is anticipated before the July 2025 deadline.

4.3 – Met - This output was added last year, considering Political Economy Analysis (PEA) and PFRC’s scoping study findings which looked at fiscal management to identify opportunities. Five relevant parliamentary committees were engaged as part of project inception – they include the Public Finance, Economy and Development, Budget, Public Accounts, Public Administration and State Interests Committees. The next phase is to start working more intently, findings of inception baseline study will inform the project workplan. Support to Parliamentarians will run through to GRP’s completion date, over which time the programme team will work with the World Bank and other development partners to ensure a smooth transition after the project is completed.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No change during review period.

The output indicators in this output are process oriented, targeting, for example, the number of podcasts or reports. For results-based management and becoming a better fit for the theory of change, the output indicators need to be redrafted to become more results oriented so that their contribution to GRP impact and outcome can be better evaluated. For example, “the number of influencers produced number of policies with the potential to bring in xxx% revenue growth. Similarly, the Word Bank’s output indicators can be more sharply defined.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

All recommendations for this output were complied with– see annex I for details.

Reform process is incremental and keeps changing pace within the context of existing political economy analysis; success is not a given until it is implemented. The need for aggressive work and improving accountability is important and the solution to evolving problems lies in thinking through the interests and incentives of different actors at a more micro-level. The team should consider commissioning a political economy analysis before embarking on politically sensitive or high-risk initiatives and building in resilience to political pressures through commitments from government counterparts and strong governance /accountability mechanisms.

Reforms are painstakingly slow especially when it involves cultural change. For example, for parliamentary committees to be fully effective, parliamentary budget office needs to be established, while the parliamentary research office is at a nascent stage. To make strong foundations, it needs skills training, fresh discourse on economy, and governance systems for committees. With the programme reaching its finishing line, FCDO’s programme team should consider and the sustainability of such high importance reform areas and delivery model for delivering these in a resource constrained future.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

The overall VFM of the GRP programme broadly relies on the additional revenue that is generated by the programme, compared to programme costs. On this basis, the programme has recently become extremely successful as it becomes more evident that reforms and new practices driven by the programme are plausibly responsible for increases in revenue – up to £100m in 2024 – that far outstrip project costs. While this headline result is the culmination of many years of GRP work (that is, the whole-of-programme costs, rather than annual programme costs are the right comparator), it is also evident that ongoing work continues to hold the promise of delivering further increases in revenue, even if these are in the medium to long term. Overall, therefore, the GRP VFM story is one of the most positive amongst development interventions and can plausibly be described as one of the foundations of Ghana moving away from aid dependence.
The key cost drivers for the programme are the international and local consultants contracted. Overall, the programme is largely a technical assistance (TA) intervention and some associated activities (for example workshops), so costs are relatively modest relative to the outcomes that are being supported.

The table above provides context on how the programme strategically contributed to revenue growth, aligning investment with key revenue-generating streams. The data illustrates how targeted interventions yielded measurable outcomes, reflecting both efficiency in resource allocation and effectiveness in enhancing domestic revenue mobilisation. One reflection of the efficiency is that total taxes attributed to these four interventions make almost 1.07% of total tax revenues collected during 2024 (GHS 1,921 billion), for which we can’t prove direct contribution but even attribution is significant from a tightly financed ODA programme.
This contracting model avoids the use of a managing agent (MA), placing a high burden on FCDO staff, but limiting overhead costs – an approach which seems practicable for delivering a low spend programme in a dwindling ODA environment. The absence of an MA means FCDO programme staff are required to provide programmatic and technical delivery support to the UKGCC-managed delivery consultants who are embedded within GRA and MoF.

Economy: Implementing partners demonstrated a strong commitment to the VfM principle of economy by pursuing cost-effective delivery strategies and ensuring that financial resources were utilized prudently. The approach centred on minimizing the cost of input such as facilities, expertise, logistics, and service provision—while maintaining the quality of outputs and outcomes.
1. Strategic Procurement and Cost Avoidance in Training Delivery
A notable example of this cost-conscious approach was demonstrated by High-Net-Worth workplan, which restructured a planned five-day residential training on Development Data Strategy for 15 participants. Originally budgeted for delivery at an external conference facility, the cost was projected at GHS 127,500, inclusive of venue hire, accommodation, and logistics. However, the High-Net-Worth team strategically converted the training into an in-house session, leveraging its own facilities and technical staff. This shift not only retained the intended training quality but also resulted in full cost avoidance of the projected external expense—saving the programme GHS 127,500.
2. Leveraging Strategic Partnerships for Reduced Rates
ACEP also played a significant role in driving cost efficiency by engaging fellow coalition member IMANI Ghana to support training for selected journalists on Public Financial Management (PFM) and anti-corruption reporting. The partnership was negotiated at significantly reduced rates due to the shared objectives and prior collaboration frameworks between the organizations. This resulted in direct cost savings of approximately GHS 20,000 compared to market rates for similar consultancy services.
3. In-House Facilities and Pro Bono Services for Stakeholder Engagements
Further cost savings were achieved by ACEP through a shift from high-cost venues to their in-house facilities for hosting stakeholder engagements. In addition, the organization secured pro bono validation services from external experts for critical policy papers. These strategic decisions eliminated costs associated with venue rentals, hospitality, and consultancy fees—accumulating an estimated saving of GHS 50,000. In total, ACEP’s cost-saving interventions generated approximately GHS 70,000 in direct savings for the programme.
4. Digital Innovation and Internal Capacity Utilization by the Ministry of Finance
The Ministry of Finance’s Tax Policy Unit also made notable contributions to VfM through economic use of resources. In response to rising logistical costs and the need to broaden stakeholder engagement, the Unit transitioned several workshops—including the Medium-Term Revenue Strategy (MTRS) sensitisation sessions—to virtual platforms. This transition allowed for nationwide participation without incurring travel, accommodation, and venue-related expenses. The use of virtual delivery methods was effective and resulted in estimated cost savings of over GHS 250,000.
Moreover, the Unit increasingly leveraged internal expertise to lead technical analyses and deliver training, reducing reliance on external consultants. This not only optimized the use of available human resources but also ensured knowledge retention and institutional sustainability within the Ministry.
Efficiency: HMRC technical missions under GRP effectively built GRA’s capacity in high-priority areas like HNWIs, AEOI, compliance, and data analytics—delivering strong results with efficient resource use. AEOI’s in-house training for the E-Commerce unit improved EOI request drafting, contributing to GHS 105M in revenue from a GHS 1M investment. EVAT implementation onboarded 2,600 taxpayers, covering 85% of VAT revenue. Support to the Tax Audit Centre of Excellence led to an 11.37% increase in GITMIS Audit Model usage, enhancing audit quality. AEOI staff are now equipped for international engagement, presented at the OECD Global Forum and are supporting peer institutions like Zambia and Uganda—demonstrating regional leadership and multiplier effects from targeted capacity building.
Effectiveness: In 2024, the programme achieved strong results through targeted investments in high-impact revenue streams. Key outcomes included GHS 387 million from the E-VAT initiative, GHS 349 million from E-Commerce taxation and GHS 900 million collected under AEOI and VDP—demonstrating effective investments in high-impact, revenue-generating workstreams that directly contributed to measurable increases in tax collection. Despite registering a fall to GHS 285 million from the High-Net-Worth taxpayer unit, due to some specific challenges in this implementation year, over the lifetime of this programme this output has also been highly effective rising from 6.2m GHS since 2020 through targeted programme support. Just to highlight the effectiveness, E-Commerce has yielded more than hundred times the value of investment (on inputs) in the form of revenues (outcome), e-commerce almost 40 times and HNWU almost 30 times.	As mentioned at the start there is a strong case that these small investments across the board are worthwhile even if only one strand pays off, given how significantly revenue increases outstrip the size of GRP investments. This is particularly true with small ODA allocations which mean direct delivery at scale is not possible for FCDO, and this increases the value of focusing on system change even where this is more unpredictable and higher risk.
Equity: The programme prioritised equity by ensuring inclusive capacity-building, with 45% of the 1,555 trained GRA staff being women and targeted outreach to staff outside Accra. ACEP interventions further promoted inclusivity by engaging youth and underrepresented groups in fiscal policy discussions and highlighting structural inequities, particularly in petroleum pricing and access to accountability platforms. The biggest contribution of programme is by delivering systems reforms that drive effective tax collection from High-net-worth individuals, developing risk-based audits which enabled tax evaders to come forth and pay taxes and strengthening e-commerce and AEOI platforms that can detect hidden taxable income of higher income individuals. This has brought equity in tax system while generating public resources which can be utilized for human development outcomes.
Alignment of all UK Official Development Assistance to the Paris Agreement - In line with the UK’s commitment to aligning all Official Development Assistance (ODA) with the Paris Agreement, the programme’s environmental impact has been assessed using the Climate and Environmental Risk Assurance flow chart. The only emissions generated by the programme come from unavoidable international travel, which is minimised using remote working and local experts where possible. The programme does not involve any investment in fossil fuels, and its activities do not conflict with Ghana’s climate and environmental policies. Mechanisms are in place to track and reduce travel-related emissions, and virtual engagement is prioritised to further minimise the programme’s carbon footprint.
Assessment of whether the programme continues to represent value for money
The programme not only warrants continuation considering its VFM, but it also justifies further work on a successor programme to embed the reform process and institutionalisation of reforms, on the same VFM case.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The current operational context of GRP demonstrates good working relationships and clear understanding of programme priorities and activities with senior GoG officials within public and civil service, including political appointees this helps the programme team to identify risk and they emerge and develop mitigation strategies with relevant implementing partners.

The GRP risk appetite is ‘receptive’ for strategy and context, policy & programme delivery, public service delivery & operations risks; and ‘cautious’ for people, reputational, financial & fiduciary, and safeguarding. GRA as an organisation has developed internal safeguarding policies which are well socialised within the organisation, a strong complement to the programme’s focus on safeguarding.

The programme’s overall risk rating remains moderate; the political will from GoG to transform revenue mobilisation being the most important element of risk reduction for a project of this nature. Securing the backing from political leadership limits the chances of the programme getting off track.

In the year under review, the programme envisaged the election as a major risk because of the potential shift in political focus and a drop in support for the ongoing reform agenda. The programme team's prior engagement with the opposition party at the time provided a good foundation to secure acceptance and co-operation when they took office in January 2025. The programme team with support of HMRC CBU organised a five-day learning visit to HMRC, HM Treasury and IFS UK. This visited afforded the Deputy Finance Minister, CG and GRA Commissioners an opportunity to have better understanding of the UKs offering on DRM and provide the leadership an opportunity to build and consolidate the long-standing partnership
Another risk was the lack of senior leadership engagement in the run up to December elections, which materialised. This caused temporary delays to programme delivery especially with activities that required approval of senior management. The programme tried to maximise business continuity by adjusting timelines, focusing on preparatory work ahead of the new leadership while prioritising activities that could progress without senior management approval. However, as the Output report above demonstrates, many sub-outputs were delayed, and the score of B for Outputs 2 and 4 is partly attributed to this.
Additionally, the 2024 general elections affected ACEP’s ability to effectively engage with Government leading to a halt to critical project activities which affected programme timelines. This risk was mitigated by securing a no cost -extension to allow ACEP to complete planned activities to achieve intended targets.
Another significant delivery risk the programme faced was caused by the FCDO-wide pause in ODA spend. This impacted on the programme’s ability to re-engage delivery consultants who play critical roles providing support across projects with Government and CSO partners. While this risk materialised, its impact was minimised by re-prioritising consultant activity in the final month of the contract. The team expedited the contract process to re-engage the consultants once funds were approved as well as scheduling an engagement meeting to ensure programme workplans are aligned and map up delivery strategies to make up for the delays.
The programme uses the following approaches to ensure it is on top of its risks:
Firstly, programme partners participated in supplier day events where refresher practical trainings on risk management including safeguarding are organised. This forum affords programme partners the opportunity to learn from other partners as they share varied lessons and experiences.
Secondly, the programme has a robust approach to identifying, documenting, reporting, mitigating, and monitoring risks. The embedded local consultants, FCDO programme team and HMRC experts can quickly identify and address risks because of how close they are to the GRA and MoF. The project team with delivery consultants have progress meetings with implementing partners, monthly and quarterly progress reports from GRA, MoF. HMRC experts and delivery consultants have proven to be a credible source to identify risks. FCDO team works closely with other Development Partners working on DRM to ensure coordination exists, minimising risks of duplication and overloading GRA and MoF staff with competing activities.
The programme conducts annual audits, quarterly expenditure verifications and spot checks to mitigate financial and fiduciary risks.

Annual Statement of Progress (financial aid programmes only – delete if n/a) [1 page]

GRP’s support to GRA and MoF is a non-budget financial aid and is therefore relatively low risk: funds are ringfenced in a separate account specific for the programme activity.  The programme team can trace the flow of funds for each expenditure.  The Ghana Revenue Programme independently commissions annual audits as well as quarterly expenditure verifications. The latter process is supported by an embedded finance consultant, funded by the programme but working in the GRA, who reviews project expenditures, processes and invoicing and checking, for example, that invoice costs are at market rates. No specific fiduciary risk or fraud has been raised in the reporting period.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

The Programme operates through a collaborative delivery model involving five key implementing partners: the Ghana Revenue Authority (GRA), Revenue Policy Division (RPD), Africa Centre for Energy Policy (ACEP), the World Bank and the UK-Ghana Chamber of Commerce (UKGCC). Each partner contributes to advancing tax policy reform, strengthening systems, enhancing public engagement, and supporting compliance. The FCDO programme team—comprising a Lead Advisor (PRO), a programme manager, a programme officer, and a Regional Tax Advisor (whose posting ended in March 2025) and the programme SRO provide strategic oversight and quality assurance, ensuring accountability and transparency across all workstreams. UKGCC has engaged delivery consultants to manage day-to-day coordination with GRA, RPD, and ACEP, they work closely with respective project managers in the development of workplans, setting output indicators, ensuring planned activities happen and coordinate quarterly reporting. They work closely with the programme coordinators in GRA and MoF to ensure programme funds are utilised effectively to achieve good value for money. GRP also collaborates with HMRC’s Capacity Building Unit (CBU) and the UK’s Institute for Fiscal Studies (IFS) to equip partners with tools and methodologies to enhance policy development and revenue administration.

GRP is guided by a comprehensive log frame, with each partner accountable for specific outputs and milestones. Monthly and quarterly narrative reports enable the FCDO team to monitor progress, identify risks, and take timely corrective actions. While some delays in report submissions have occurred, they have not significantly impacted overall programme targets. Quarterly review meetings serve as a key mechanism for performance and risk management, providing a platform for policy leads and project managers to report on milestone achievements, financial performance, and risk mitigation. A consolidated delivery chain map further strengthens risk assurance.

An independent audit of all partners found no major financial or operational risks, reflecting strong financial management and internal controls. This improvement is attributed to regular expenditure verification and spot checks conducted by programme finance delivery consultant.

During the 2024–2025 financial year, total forecasted funds across all partners amounted to GHS 36.85 million, out of which GHS 28.16 million was spent, representing an overall utilisation rate of 78%. This reflects a slight decline from the 84% recorded in the previous year, despite an increase in total forecasted resources.
At the partner level, the Ghana Revenue Authority (GRA) and the Ministry of Finance (MoF) demonstrated strong performance regarding utilization, with rates of 80% and 79% respectively, maintaining spending levels consistent with prior year trends. In contrast, ACEP recorded a significant drop in performance, with only 40% utilisation, down from 92% the previous year, indicating challenges in programme delivery.
The table below provides details of the programme’s forecasting and utilisation in the year under review

The programme through the Public Finance and Resource Centre (PFRC) procured both international and local consultants to provide technical assistance to the Data Mining and Analytics Unit, Prosecution and Investigations units and the Customer Experience Unit within GRA. The outputs from the consulting firms met the expectation of the beneficiaries. GRP partnership with the WB progressed in the year under review with the Bank engaging the Africa Centre for Parliamentary Affairs (ACEPA) as delivery partners for the intervention

.
G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

The Ghana Revenue Programme (GRP) integrates robust monitoring mechanisms across all activities to enable timely adjustments and informed decision-making.

Monitoring and Evaluation is conducted through a combination of internal reviews, partner reporting, and stakeholder engagement.

Key monitoring activities during year in review were:

- Quarterly Progress Reviews: Regular review meetings with implementing partners provided a platform to assess progress, manage delivery risks, and align activities with logframe targets. For instance, during a review with a CSO partner, FCDO supported the revision of targets to better reflect the scope of planned activities.
- Annual Reports: All government and civil society partners share annual review reports to feed into FCDO’s annual review. This also reflects strong buy-in of counterparts.

Stakeholder’s engagement: In anticipation of national elections, GRP proactively engaged political stakeholders to mitigate reform disruption risks. This positioned the programme as a credible, neutral platform for fiscal reform and enabled readiness to support new leadership with tailored technical assistance. This approach reflects GRP’s understanding of the political economy of tax reform and the importance of institutional continuity.
Key evaluation activities during year in review were:

Outcome Harvesting: GRP under the leadership of the Results Adviser has initiated the process to undertake an evaluation to focus on linking programme activities to outcomes achieved over time. This will culminate in a comprehensive evaluation of the UK’s decade-long support to domestic revenue mobilisation, to be documented in the Project Completion Report.

Evidence and Theory of Change (ToC): The programme’s refreshed ToC is regularly reviewed with partners to ensure alignment with evolving contexts. The team should consider whether assumptions underpinning the TOC need to be further elaborated and regularly tested. Evidence from partners is used to inform workplans and strategic direction.

Learning is a consistent part and parcel of the programme, with following activities undertaken during review period:

Workshops: The programme team actively participated in key events, including customer service and ethics training for GRA frontline staff; HMRC peer-to-peer sessions with GRA’s Data Management Unit; and GRA’s audit conference. These engagements ensured clarity on deliverables and alignment with programme objectives. A joint workshop by HMRC’s Capacity Building Unit and FCDO captured lessons learned and identified areas for delivery improvement.

Date of last narrative financial report	12 May 2025	Date of last audited annual statement	7 May 2025